## README
PAIMANA Flash Report Data — April & May 2025
Source: MoSPI Central Sector Infrastructure Projects Flash Reports
(Projects costing Rs. 150 crore and above)
Sheets:
Sector Overview — sector-wise project count & cost totals, both months
State Overview — state-wise project count & cost totals, both months
Completed Projects — projects completed that month
Added Projects — new projects added that month
Frozen-Deleted Projects — projects frozen/deleted (May only; April had none)
NE Region Ongoing — ongoing projects in North-East states
All Ongoing Projects — full project-level list, all states/sectors (main dataset)
Notes:
- Every sheet includes both April 2025 and May 2025 rows, distinguished by the 'Month' column.
- Cost/expenditure/progress figures are numeric (Rs. Crore); 'N.A.' in the source was left blank.
- Cost columns follow the report's own structure: Original, Revised, Anticipated.
- All Ongoing Projects row counts (April: 1670, May: 1637) were cross-checked against each report's own Sector Overview totals and match exactly.

## Sector Overview
Month | Sl No | Sector | Projects | Cost Original (Rs Cr) | Cost Revised (Rs Cr) | Cost Anticipated (Rs Cr) | Cumulative Expenditure (Rs Cr)
April 2025 | 1 | CIVIL AVIATION | 38 | 26718.18 | 27771.19 | 30473.9 | 17430.52
April 2025 | 2 | COAL | 113 | 188127.06 | 192671.1 | 197500.35 | 66702.32
April 2025 | 3 | DEPARTMENT OF HIGHER EDUCATION | 20 | 9680.92 | 10152.14 | 10206.43 | 7219.42
April 2025 | 4 | DPIIT | 2 | 24857 | 31457 | 32085 | 9939.78
April 2025 | 5 | FINANCE | 2 | 577.27 | 577.27 | 569.04 | 399.67
April 2025 | 6 | HEALTH AND FAMILY WELFARE | 8 | 7301.27 | 7358.4 | 7356.19 | 4704.48
April 2025 | 7 | HOME AFFAIRS | 5 | 2025.73 | 2949.25 | 2949.25 | 2466.6
April 2025 | 8 | MINES | 8 | 7559.78 | 9356.73 | 9845.57 | 5983.2
April 2025 | 9 | PETROLEUM | 106 | 423588.3 | 474888 | 485041.21 | 238890.69
April 2025 | 10 | POWER | 106 | 378959.85 | 397275.55 | 464282.09 | 229667.95
April 2025 | 11 | RAILWAYS | 213 | 631896.84 | 620968.2 | 658071.79 | 450664.81
April 2025 | 12 | ROAD TRANSPORT AND HIGHWAYS | 979 | 762272.76 | 793364.28 | 805114.24 | 401122.11
April 2025 | 13 | SHIPPING AND PORTS | 1 | 5369.18 | 5061.15 | 5061.15 | 3414.95
April 2025 | 14 | SOCIAL JUSTICE | 1 | 170.99 | 170.99 | 170.99 | 73.8
April 2025 | 15 | STEEL | 20 | 16297.2 | 20228.73 | 20228.73 | 7561.3
April 2025 | 16 | TELECOMMUNICATIONS | 6 | 26961.69 | 26949.89 | 26949.89 | 9434.73
April 2025 | 17 | URBAN DEVELOPMENT | 27 | 265881.46 | 272720.33 | 286578.3 | 198371.86
April 2025 | 18 | WATER RESOURCES | 15 | 15428.28 | 15429.03 | 61880.31 | 27431.76
May 2025 | 1 | CIVIL AVIATION | 38 | 26718.18 | 27878.25 | 30473.9 | 17738.02
May 2025 | 2 | COAL | 113 | 186109.83 | 190653.87 | 195483.12 | 66730.38
May 2025 | 3 | DEPARTMENT OF HIGHER EDUCATION | 20 | 9680.92 | 10152.14 | 10271.25 | 7192.52
May 2025 | 4 | DPIIT | 2 | 24857 | 31457 | 32085 | 16231.95
May 2025 | 5 | FINANCE | 2 | 577.27 | 577.27 | 569.04 | 399.67
May 2025 | 6 | HEALTH AND FAMILY WELFARE | 7 | 7150.98 | 7459.11 | 7194.19 | 4900.15
May 2025 | 7 | HOME AFFAIRS | 3 | 1663.54 | 2539.11 | 2539.11 | 2193.78
May 2025 | 8 | MINES | 8 | 7559.78 | 9356.73 | 9845.57 | 6034.59
May 2025 | 9 | PETROLEUM | 105 | 423126 | 474335.56 | 484488.77 | 244464.96
May 2025 | 10 | POWER | 108 | 379828.26 | 403113.29 | 457814.84 | 223684.2
May 2025 | 11 | RAILWAYS | 203 | 579886.47 | 569688.23 | 599321.52 | 397884.96
May 2025 | 12 | ROAD TRANSPORT AND HIGHWAYS | 958 | 742316.73 | 770508.11 | 781211.2 | 387038.64
May 2025 | 13 | SHIPPING AND PORTS | 1 | 5369.18 | 5061.15 | 5061.15 | 3441.55
May 2025 | 14 | SOCIAL JUSTICE | 1 | 170.99 | 170.99 | 170.99 | 73.8
May 2025 | 15 | STEEL | 20 | 16297.2 | 20228.73 | 20228.73 | 7838.89
May 2025 | 16 | TELECOMMUNICATIONS | 6 | 26961.69 | 26949.89 | 26949.89 | 9650.92
May 2025 | 17 | URBAN DEVELOPMENT | 27 | 265881.46 | 272720.33 | 286578.3 | 200218.7
May 2025 | 18 | WATER RESOURCES | 15 | 15428.28 | 15429.03 | 61880.31 | 27441.75

## State Overview
Month | Sl No | State | Projects | Cost Original (Rs Cr) | Cost Revised (Rs Cr) | Cost Anticipated (Rs Cr) | Cumulative Expenditure (Rs Cr)
April 2025 | 1 | ANDAMAN AND NICOBAR ISLANDS | 10 | 2956.02 | 3029.18 | 3010.04 | 1808.58
April 2025 | 2 | ANDHRA PRADESH | 101 | 137833.86 | 138333.19 | 186185.06 | 98734.38
April 2025 | 3 | ARUNACHAL PRADESH | 15 | 45355.1 | 45418.63 | 65231.68 | 29936.93
April 2025 | 4 | ASSAM | 66 | 70951.17 | 71435.04 | 78927.98 | 48896.87
April 2025 | 5 | BIHAR | 91 | 132025.16 | 143881.81 | 156093.17 | 98897.94
April 2025 | 6 | CHHATTISGARH | 50 | 75244.87 | 79134.3 | 79609.36 | 34568.92
April 2025 | 7 | DELHI | 21 | 90609.18 | 96063.03 | 94869.54 | 75889.17
April 2025 | 8 | GOA | 3 | 1201.05 | 1201.05 | 1287.55 | 479.89
April 2025 | 9 | GUJARAT | 93 | 171766.13 | 178643.2 | 180047.13 | 88746.28
April 2025 | 10 | HARYANA | 27 | 64666.15 | 75462.06 | 75513.65 | 38801.14
April 2025 | 11 | HIMACHAL PRADESH | 29 | 38377.91 | 39407.59 | 47304.24 | 31113.84
April 2025 | 12 | JAMMU AND KASHMIR | 54 | 110434.59 | 111493.16 | 124794.68 | 78431.58
April 2025 | 13 | JHARKHAND | 63 | 113244.62 | 117005.23 | 116157.04 | 64585.11
April 2025 | 14 | KARNATAKA | 79 | 100786.16 | 102083.89 | 101111.19 | 48636.34
April 2025 | 15 | KERALA | 32 | 64106.75 | 69889.93 | 70321.9 | 35689.51
April 2025 | 16 | LADAKH | 6 | 2474.97 | 2474.97 | 2634.64 | 1335.62
April 2025 | 17 | MADHYA PRADESH | 59 | 113890.17 | 113291.57 | 119877.89 | 40597.62
April 2025 | 19 | MANIPUR | 32 | 25355.56 | 23343 | 33267.37 | 19554.67
April 2025 | 20 | MEGHALAYA | 15 | 6583.27 | 6574.29 | 6528.65 | 3555.45
April 2025 | 21 | MIZORAM | 17 | 14519.38 | 13013.38 | 18688.72 | 16133.12
April 2025 | 22 | MULTI STATE | 51 | 333913.59 | 338914.31 | 352924.44 | 243139.16
April 2025 | 23 | NAGALAND | 30 | 15476.91 | 16825.59 | 16524.56 | 9021.07
April 2025 | 24 | ODISHA | 79 | 149765.57 | 151845.86 | 154533.92 | 64807.08
April 2025 | 25 | PUNJAB | 38 | 37743.85 | 38226.32 | 38643.81 | 14813.37
April 2025 | 26 | RAJASTHAN | 65 | 138451.86 | 166631.81 | 167672.73 | 91740.84
April 2025 | 27 | SIKKIM | 21 | 20872.24 | 25371.63 | 26215.2 | 18481.26
April 2025 | 28 | TAMIL NADU | 63 | 92087.08 | 98096.1 | 103639.15 | 27057.19
April 2025 | 29 | TELANGANA | 52 | 29124.48 | 29461.83 | 31449.35 | 14352.84
April 2025 | 30 | TRIPURA | 14 | 7910.17 | 7947.06 | 8032.54 | 1230.63
April 2025 | 31 | UTTAR PRADESH | 128 | 212871.97 | 218361.06 | 224779.8 | 110082.09
April 2025 | 32 | UTTARAKHAND | 31 | 58781.06 | 63618.31 | 62977.39 | 46271.73
April 2025 | 33 | WEST BENGAL | 58 | 79080.16 | 83881.33 | 91512.25 | 47633.12
May 2025 | 1 | ANDAMAN AND NICOBAR ISLANDS | 10 | 2956.02 | 3029.18 | 3010.04 | 1826
May 2025 | 2 | ANDHRA PRADESH | 101 | 137833.86 | 138333.19 | 186185.06 | 99775.15
May 2025 | 3 | ARUNACHAL PRADESH | 14 | 45061.06 | 45210.96 | 64937.64 | 30118.63
May 2025 | 4 | ASSAM | 68 | 72160.68 | 72644.55 | 80137.49 | 50194.44
May 2025 | 5 | BIHAR | 90 | 128697.89 | 141442.84 | 153398.13 | 96957.04
May 2025 | 6 | CHHATTISGARH | 50 | 75244.87 | 79134.3 | 79609.36 | 35044.7
May 2025 | 7 | DELHI | 21 | 90609.18 | 96063.03 | 94869.54 | 76426.03
May 2025 | 8 | GOA | 3 | 1201.05 | 1201.05 | 1287.55 | 479.89
May 2025 | 9 | GUJARAT | 90 | 167579.54 | 173666.23 | 174375.7 | 86950.93
May 2025 | 10 | HARYANA | 24 | 60500.88 | 69284.79 | 69434.48 | 34812.67
May 2025 | 11 | HIMACHAL PRADESH | 28 | 34458.32 | 35488 | 34472.16 | 18362.46
May 2025 | 12 | JAMMU AND KASHMIR | 53 | 73422.59 | 74733.7 | 81014.68 | 36996.5
May 2025 | 13 | JHARKHAND | 63 | 113244.62 | 117005.23 | 116157.04 | 64794.39
May 2025 | 14 | KARNATAKA | 79 | 103071.74 | 104310.55 | 103281.26 | 48548.52
May 2025 | 15 | KERALA | 31 | 63956.46 | 69579.05 | 70159.9 | 36274.03
May 2025 | 16 | LADAKH | 6 | 2474.97 | 2634.64 | 2634.64 | 1336.77
May 2025 | 17 | MADHYA PRADESH | 55 | 111980.58 | 111381.98 | 118179.99 | 39850.9
May 2025 | 18 | MAHARASHTRA | 177 | 235212.75 | 239003.84 | 263997.81 | 139123.44
May 2025 | 19 | MANIPUR | 33 | 25919.61 | 23907.05 | 33831.42 | 19613.61
May 2025 | 20 | MEGHALAYA | 15 | 6827.06 | 6818.08 | 6837.26 | 3427.3
May 2025 | 21 | MIZORAM | 17 | 14519.38 | 13013.38 | 18688.72 | 15940.7
May 2025 | 22 | MULTI STATE | 50 | 331866.08 | 337419.07 | 350641.22 | 248890.31
May 2025 | 23 | NAGALAND | 25 | 13894.53 | 15243.21 | 14942.18 | 8322.44
May 2025 | 24 | ODISHA | 76 | 141702.2 | 143692.35 | 146380.41 | 64716.85
May 2025 | 25 | PUNJAB | 37 | 37339.85 | 37800.41 | 38239.81 | 14582.9
May 2025 | 26 | RAJASTHAN | 62 | 138216.71 | 168368.04 | 167962.23 | 91585.48
May 2025 | 27 | SIKKIM | 20 | 20540.04 | 25022.71 | 25866.28 | 18480.28
May 2025 | 28 | TAMIL NADU | 61 | 88967.98 | 94410.41 | 99894.68 | 24829.27
May 2025 | 29 | TELANGANA | 52 | 29124.48 | 29461.83 | 31449.35 | 14511.12
May 2025 | 30 | TRIPURA | 14 | 7910.17 | 7947.06 | 8032.54 | 1291.48
May 2025 | 31 | UTTAR PRADESH | 125 | 205554.6 | 213896.31 | 217968.91 | 106018.1
May 2025 | 32 | UTTARAKHAND | 31 | 58781.06 | 63618.31 | 63170.51 | 44929.76
May 2025 | 33 | WEST BENGAL | 56 | 78752.95 | 83513.46 | 91118.89 | 48147.34

## Completed Projects
Month | Sector | Sl No | Project Name | Agency | Project Code | State | Original Cost (Rs Cr) | Date of Commissioning | Cumulative Expenditure (Rs Cr)
April 2025 | CIVIL AVIATION | 1 | UPGRADATION OF PASSENGER TERMINAL BUILDING AND AIRSIDE FACILITIES AT TIRUCHIRAPALLI INTERNATIONAL AI | AAI | N04000075 | TAMIL NADU | 951.28 | 10/2021 | 1084.94
April 2025 | CIVIL AVIATION | 2 | CO CIVIL AVIATION REASEARCH ORG. (PH-II) AT BEGUMPET AIRPORT, HYDRABAD | AAI | N04000086 | TELANGANA | 353.61 | 05/2022 | 303.22
April 2025 | CIVIL AVIATION | 3 | EXT AND STR. OF EXISTING RUNWAY 08/26 AT TIRUPATI AIRPORT | AAI | N04000089 | ANDHRA PRADESH | 177.1 | 02/2020 | 143.08
April 2025 | PETROLEUM | 4 | REVAMPING OF FACILITIES AT VIZAG TERMINAL | IOCL | N16000343 | ANDHRA PRADESH | 355 | 04/2022 | 249
April 2025 | PETROLEUM | 5 | MUMBAI HIGH NORTH REDEVELOPMENT PHASE-IV | ONGC | N16000358 | MAHARASHTRA | 3228.8 | 03/2022 | 3867.19
April 2025 | PETROLEUM | 6 | AUGMENTATION OF FACILITIES AT THE EXISTING RAIPUR DEPOT | HPCL | N16000413 | CHHATTISGARH | 456 | 03/2024 | 271.44
April 2025 | PETROLEUM | 7 | TRANSMISSION NETWORK EXPANSION IN GUJARAT TO INCREASE ATC FROM ISTS: PART C | PGCIL | N18000338 | MULTI STATE | 186.19 | 03/2025 | 91.53
April 2025 | PETROLEUM | 8 | TRANSMISSION SYSTEM ASSOCIATED WITH WESTERN REGION EXPANSION SCHEME XXVII | PGCIL | N18000354 | CHHATTISGARH | 271.69 | 09/2024 | 192.03
April 2025 |  | 9 | TRANSMISSION SYSTEM ASSOCIATED WITH WESTERN REGION EXPANSION SCHEME-XXVIII AND XXIX | PGCIL | N18000355 | CHHATTISGARH | 260.3 | 03/2025 | 197.79
April 2025 |  | 10 | IMPROVEMENT AND UP-GRADATION OF EXISTING ROAD TO 4L PS FROM KM 175.080 TO 229.070, FROM END OF HARDO | NHAI | N24001728 | UTTAR PRADESH | 1138.81 | 07/2025 | 528.1
April 2025 |  | 11 | CONSTRUCTION OF 8LANE EXPRESSWAY NE4 STARTING BEFORE KMP EXPRESSWAY AND ENDS AT CH. 47+000 NEAR KHAN | NHAI | N24001783 | HARYANA | 2252.75 | 09/2021 | 1223.07
April 2025 |  | 12 | SANCHORE - SANTALPUR FROM KM 4.888 - KM 35.000 OF NH-754K (AJ-RGBS-PACKAGE-1) | NHAI | N24001791 | GUJARAT | 606.51 | 06/2023 | 453.89
April 2025 |  | 13 | 4 LANING OF BATHALAPALLI TO MUDIGUBBA SECTION (DESIGN CHAINAGE KM. 96.300 TO 129.300) INCLUDING BATH | MoRTH | N24001931 | ANDHRA PRADESH | 536 | 02/2025 | 334.06
April 2025 |  | 14 | NH167B FROM KM 99.103 CS PURAM TO KM 143.320 MALAKONDA TO 2LPS | MoRTH | N24001949 | ANDHRA PRADESH | 277.3 | 03/2024 | 206.25
April 2025 |  | 15 | NH167B FROM KM.143.320 MALAKONDA TO 189.050 SINGARAYAKONDA ON NH 16 TO TWO LANE WITH PAVED SHOULDERS | MoRTH | N24001950 | ANDHRA PRADESH | 369.81 | 02/2025 | 303.78
April 2025 |  | 16 | 2 LANE WITH PAVED SHOULDER CONFIGURATION FROM SEETHARAMAPURAM TO DUTTALURU SECTION OF NH-167 BG FROM | MoRTH | N24002141 | ANDHRA PRADESH | 364.07 | 07/2025 | 227.21
April 2025 |  | 17 | DIBRUGARH-LAHOAL-CHABUA BYPASS PACKAGE-1 | NHIDCL | N24001451 | ASSAM | 215.27 | 07/2024 | 105.4
April 2025 |  | 18 | 6L OF MH/KN BORDER (NIMBAL VILLAGE) TO KN/TS BORDER (SINGNODI VILLAGE) FROM KM. 162.5 TO KM. 203.100 | NHAI | N24001675 | KARNATAKA | 1732.73 | 05/2025 | 754.79
April 2025 |  | 19 | AURAD - BIDAR KM 0.00 TO KM 45.878 | NHAI | N24001683 | KARNATAKA | 912.37 | 04/2023 | 255.94
April 2025 |  | 20 | FOUR LANING OF BANAVARA TO BETTADAHALLI SECTION FROM KM. 119+790 (DESIGN KM. 121+900) TO KM. 166+100 | NHAI | N24001686 | KARNATAKA | 1065.06 | 03/2023 | 736.55
April 2025 |  | 21 | FOUR LANING OF KARADI TO BANAVARA SECTION FROM KM. 66+540 (DESIGN KM. 65+195) TO KM. 119+790 (DESIGN | NHAI | N24001691 | KARNATAKA | 1225.24 | 10/2021 | 1043
April 2025 |  | 22 | 4-LANNING EXISTING KM 189.700 TO 237.00] HASSAN TO MARANAHALLY | NHAI | N24000552 | KARNATAKA | 701.4 | 03/2019 | 923.99
April 2025 |  | 23 | CONSTRUCTION OF NH-24 EXTENSION 4-LANE BYPASS STARTING FROM BEHTA ROAD AND TERMINATING AT SITAPUR RO | NHAI | N24000796 | UTTAR PRADESH | 1117.84 | 12/2021 | 1960.91
April 2025 |  | 24 | SHAHPUR PATGAON SECTION I | MoRTH | N24001027 | MAHARASHTRA | 150.79 | 12/2019 | 81.14
April 2025 |  | 25 | JINTUR TO PARBHANI | MoRTH | N24001039 | MAHARASHTRA | 356.66 | N.A. | 209.48
April 2025 |  | 26 | HIMAYATNAGAR TO PHULSAWANGI | MoRTH | N24001081 | MAHARASHTRA | 294.87 | 12/2019 | 183.17
April 2025 |  | 27 | SELDOH TO PANVAR | MoRTH | N24001097 | MAHARASHTRA | 404.33 | 05/2020 | 140.65
April 2025 |  | 28 | SATARA MURVAD PILLOV PANDHARPUR | MoRTH | N24001095 | MAHARASHTRA | 388.44 | N.A. | 240.05
April 2025 |  | 29 | KOLHA TO NASRATPUR | MoRTH | N24001111 | MAHARASHTRA | 281.78 | 04/2019 | 77.83
April 2025 |  | 30 | KUMBHARI PHTA TO DEULGAON RAJA | MoRTH | N24001127 | MAHARASHTRA | 406.51 | 06/2019 | 340.26
April 2025 |  | 31 | WIDENING AND UP-GRADATION TO 2-LANE WITH PAVED SHOULDER CONFIGURATION AND GEOMETRIC IMPROVEMENTS FRO | NHIDCL | N24000859 | MIZORAM | 642.96 | 06/2023 | 686.42
April 2025 |  | 32 | REHABILITATION AND UPGRADATION TO 2 LANE WITH PAVED SHOULDER OF MOGA (DESIGN CH 0.000) TO MAKHU (DES | MoRTH | N24000941 | PUNJAB | 293.64 | 08/2020 | 295.46
April 2025 |  | 33 | CONSTRUCTION OF 2 LANING OF EXISTING HUNLI- ANINI ROAD ON EPC BASIS FROM DESIGN KM 53.500 TO KM 92.50 | NHIDCL | N24000948 | ARUNACHAL PRADESH | 568.92 | 12/2019 | 508.65
April 2025 |  | 34 | CONSTRUCTION OF CHHIATHLANG -SERCHHIP BYPASS (PKG-1) ON AIZAWL-TUIPANG SECTION OF NH-54 | NHIDCL | N24001277 | MIZORAM | 275.02 | 10/2022 | 237.68
May 2025 | COAL | 1 | TALABIRA II AND III OCP | NLC | N06000189 | ODISHA | 2401.07 | 01/2027 | 1626.71
May 2025 | HEALTH AND FAMILY WELFARE | 2 | C/O NEW HOSPITAL BLOCK FOR SREE CHITRA TIRUNAL INSTITIUTE OF MEDICAL SCIENCE AND TECHNOLOGY (SCTIMST | CPWD FOR HEALTH | N28000112 | KERALA | 150.29 | 03/2020 | 162.52
May 2025 | HOME AFFAIRS | 3 | NSG AT KOLKATA | CPWD FOR MHA | N28000104 | WEST BENGAL | 162.88 | 04/2018 | 193.91
May 2025 | HOME AFFAIRS | 4 | CONSTRUCTION OF 683 VARIOUS TYPE FAMILY QUARTERS AT GROUP CENTRE CRPF CHANDAULI | CPWD FOR MHA | N45000003 | UTTAR PRADESH | 199.31 | 01/2022 | 86.49
May 2025 | PETROLEUM | 5 | ADDITIONAL STORAGE TANKS AT PARADIP | IOCL | N16000361 | ODISHA | 462.3 | 09/2021 | 493.72
May 2025 | POWER | 6 | PARBATI HEP (4X200 MW) (NHPC) II | NHPC | 180100210 | HIMACHAL PRADESH | 3919.59 | 09/2009 | 12832.59
May 2025 | POWER | 7 | UDHAMPUR-SRINAGAR-BARAMULLA (NL),NR | NR | 220100133 | JAMMU AND KASHMIR | 37012 | 08/2024 | 42328.83
May 2025 | POWER | 8 | NEW BONGAIGAON-RANGIA-KAMAKGHYA DOUBLING | NFR | N22000183 | MULTI STATE | 2047.51 | 08/2024 | 3709.47
May 2025 |  | 9 | VARANASI-MODHOSINGH-ALLAHABAD DOUBLING | RVNL | N22000401 | UTTAR PRADESH | 2018.23 | 12/2024 | 1780.22
May 2025 |  | 10 | 2880.4 | ECR | N22000417 | UTTAR PRADESH | 2880.4 | 08/2024 | 3074.78
May 2025 |  | 11 | EXECUTION OF RAIL CONNECTIVITY PROJECT FOR COAL TRANSPORTATION IN ODISHA FOR MCRL | IRCON | N22000418 | ODISHA | 5200 | 03/2020 | 389
May 2025 |  | 12 | KARAILA ROAD - SHAKTINAGAR DOUBLING | ECR | N22000419 | UTTAR PRADESH | 762.97 | 08/2024 | 808.96
May 2025 |  | 13 | MANSA-BHATINDA (PHASE-I), INCL. NEW MATERIAL MODIFICATION FOR RAMA MANDI (RAMAN) - SADA SINGHWALA VI | NR | N22000502 | PUNJAB | 404 | 08/2016 | 190
May 2025 |  | 14 | DARBHANGA - BYPASS LINE CONNECTING SHISHO HALT AND KAKARGHATI EXCL DARBHANGA YARD (7.64 KM) | ECR | N22000523 | BIHAR | 983.62 | 06/2025 | 417.57
May 2025 |  | 15 | AZIMGANJ-MURSHIDABAD (JIYAGANJ) INCL. RLY. BRIDGE OVER RIVER BHAGIRATHI | ER | N22000609 | WEST BENGAL | 164.33 | 02/2024 | 160.82
May 2025 |  | 16 | MEHSANA PALANPUR DOUBLING PROJECT 65.10 KMS | WR | N22000505 | GUJARAT | 537.31 | 03/2024 | 944.55
May 2025 |  | 17 | FOUR LANING OF VILUPPURAM TO PUDHUCHERRY (DESIGN CH. KM. 00/000 TO KM. 29/000) SECTION OF NH-45A ON | NHAI | N24001428 | TAMIL NADU | 998.7 | 11/2021 | 975.68
May 2025 |  | 18 | FOUR LANING OF POONDIYANKUPPAM (KM.67/000) TO SATTANATHAPOURAM (KM.123/800) SECTION OF NH-45A ON HAM | NHAI | N24001430 | TAMIL NADU | 2120.4 | 01/2022 | 1588.17
May 2025 |  | 19 | CONSTRUCTION OF 2 LANE WITH HARD SHOULDER FROM DESIGN CHAINAGE KM 283.000 TO KM 325.440 (5- LEGGED J | NHIDCL | N24001475 | NAGALAND | 605.36 | 12/2024 | 273.21
May 2025 |  | 20 | CONSTRUCTION OF 4-LANE NH-344P-PACKAGE-4 (FROM KM 0+000 TO KM 29+600, 29.6KM), STARTING FROM BAWANA | NHAI | N24001532 | HARYANA | 694 | 11/2023 | 1466.82
May 2025 |  | 21 | CONSTRUCTION OF 4-LANE GREEN FIELD DELHI-AMRITSAR- KATRA EXPRESSWAY (NE-05) FROM JUSSUR KHERI ON KMP | NHAI | N24001533 | HARYANA | 1690.23 | 12/2023 | 1462.45
May 2025 |  | 22 | CONSTRUCTION OF FOUR-LANE GREENFIELD DELHI- AMRITSAR-KATRA EXPRESSWAY FROM JUNCTION WITH ROHTAK-PANIP | NHAI | N24001534 | HARYANA | 1334.04 | 01/2024 | 1048.12
May 2025 |  | 23 | FOUR LANING OF JIND GOHANA GREENFIELD ALIGNMENT PACKAGE 1 IN THE STATE OF HARYANA UNDER HYBRID ANNUI | NHAI | N24001536 | HARYANA | 817 | 07/2022 | 986.08
May 2025 |  | 24 | 2L PS OF SATNA - MAIHAR SECTION OF NH-135BG FROM KM 80.800 TO KM 120.125 | NHAI | N24001616 | MADHYA PRADESH | 428.04 | 10/2023 | 351.97
May 2025 |  | 25 | BAKHTIYARPUR RAJAULI PKG-III FROM KM 101.630 TO KM 152.520 NH20 | NHAI | N24001708 | BIHAR | 2156.22 | 06/2024 | 1397.72
May 2025 |  | 26 | 6L OF KANHAULI RAMNAGAR PATNA RING ROAD PKG I FROM KM 0.000 TO KM 39.160 OF SH78 NEW NH131G | NHAI | N24001711 | BIHAR | 939.43 | 03/2023 | 1030.75
May 2025 |  | 27 | ADDITIONAL WORKS (2VUPS, MR-10 JUNCTION FLYOVER AND UNDERPASS) IN SIX LANE INDORE-DEWAS SECTION OF N | NHAI | N24001765 | MADHYA PRADESH | 207.77 | 07/2024 | 147.24
May 2025 |  | 28 | BALANCE WORK OF 4L OF INDORE-GUJARAT/MP BORDER FROM KM 106.210 TO KM 115.250 (START AND END POINT OF | NHAI | N24001768 | MADHYA PRADESH | 323.51 | 04/2023 | 246.27
May 2025 |  | 29 | CONSTRUCTION OF EIGHT LANE ACCESS CONTROLLED EXPRESSWAY FROM KM 217.500 TO KM 254.430 OF VADODARA MU | NHAI | N24001788 | GUJARAT | 2271.86 | 12/2023 | 2655.78
May 2025 |  | 30 | 4L BYPASSES FOR JAGATPUR, B4ABUGANJ, UNCHAHAR, ALAPUR BYPASS, AND SAI RIVER BRIDGE OF RAEBARELI- PRA | NHAI | N24001815 | UTTAR PRADESH | 1699 | 11/2024 | 1033.72
May 2025 |  | 31 | UPGRADATION AND REHABILITATION TO TWO LANE WITH PAVED SHOULDER OF GHAGARIYA- MUNABAO SECTION FROM KM | MoRTH | N24001869 | RAJASTHAN | 235.15 | 08/2025 | 152.69
May 2025 |  | 32 | WIDENING OF RAEBARELI TO PRAYAGRAJ SECTION FROM KM. 82.650 TO KM. 161.450 OF NH-30 AND LINK ROAD FRO | NHAI | N24002085 | UTTAR PRADESH | 1470.93 | 03/2025 | 1088.3
May 2025 |  | 33 | CHANGTONGYA TO LONGLENG ROAD PKG-2 | NHIDCL | N24001389 | NAGALAND | 206.53 | 06/2022 | 119.25
May 2025 |  | 34 | JORAM ? KOLORIANG ROAD FROM EXISTING KM 70.00 TO KM 88.700 (PKG-4) | NHIDCL | N24001391 | ARUNACHAL PRADESH | 294.04 | 04/2022 | 147.13
May 2025 |  | 35 | RANIKOR-MAHESHKHOLA- BAGHMARA (RMB) PKG-3 | NHIDCL | N24001360 | MEGHALAYA | 260.21 | 12/2022 | 239.35
May 2025 |  | 36 | BALANCE WORK FOR FOUR LANING OF ITARSI TO BETUL SECTION OF NH69 FROM KM 63.000 TO KM 137.00 (DESIGN | NHAI | N24000709 | MADHYA PRADESH | 950.27 | 02/2020 | 643.9
May 2025 |  | 37 | CONSTRUCTION OF 2 LANE WITH PAVED SHOULDER FROM KM. 168 TO 183.783 (YESEMYONG TO UNGER) ON MOKOKCHUN | MoRTH | N24001179 | NAGALAND | 217.35 | 11/2020 | 214.18
May 2025 |  | 38 | WIDENING OF EXISTING SINGLE/INTERMEDIATE LANE ROAD TO 2 LANE ROAD FROM KM. 83.00 TO KM 101.00 ON NH- | MoRTH | N24001180 | NAGALAND | 237.51 | 12/2022 | 215.47
May 2025 |  | 39 | FOUR LANING OF BHAVNAGAR-TALAJA SECTION OF NH-8E FROM KM. 7.090 TO KM. 53.585 (DESIGN CH FROM KM. 6. | NHAI | N24000567 | GUJARAT | 998.18 | 08/2019 | 1105.25
May 2025 |  | 40 | FOUR LANING OF UNA TO KODINAR OF NH-8E FROM KM. 180.478 TO KM 221.610 (PACKAGE-V) IN THE STATE OF GU | NHAI | N24000570 | GUJARAT | 763.08 | 08/2019 | 734.78

## Added Projects
Month | Sector | Sl No | Project Name | Agency | Project Code | State | Date of Approval | Cost Original (Rs Cr) | Cost Revised (Rs Cr) | Cost Anticipated (Rs Cr) | Commissioning Original | Commissioning Revised | Commissioning Anticipated
April 2025 |  | 1 | TRANSMISSION SYSTEM FOR EVACUATION OF POWER FROM RAJASTHAN REZ PH-IV (PART-4: 3.5 GW): PART A | PGCIL | N18000407 | UTTAR PRADESH | 12-2024 | 5846 |  | 5846 | 12/2026 | N.A. | 12/2026
April 2025 |  | 2 | TRANSMISSION SYSTEM UNDER ISTS FOR EVACUATION OF POWER FROM KUDANKULAM UNIT - 3 & 4 (2X1000 MW) | PGCIL | N18000408 | TAMIL NADU | 1-2025 | 548 |  | 548 | 7/2028 | N.A. | 7/2028
April 2025 |  | 3 | SYSTEM STRENGTHENING AT KOPPAL-II AND GADAG-II FOR INTEGRATION OF RE GENERATION PROJECTS | PGCIL | N18000409 | KARNATAKA | 1-2025 | 1354 |  | 1354 | 1/2027 | N.A. | 1/2027
April 2025 |  | 4 | AUGMENTATION OF TRANSFORMATION CAPACITY AT BIDAR PS | PGCIL | N18000410 | KARNATAKA | 2-2025 | 288 |  | 288 | 2/2027 | N.A. | 2/2027
April 2025 |  | 5 | AUGMENTATION OF TRANSFORMATION CAPACITY AT KPS2 & KPS2 | PGCIL | N18000411 | GUJARAT | 3-2025 | 466 |  | 466 | 3/2027 | N.A. | 3/2027
April 2025 |  | 6 | AUGMENTATION OF BANASKANTHA (RAGHANESDA) PS (GIS) | PGCIL | N18000412 | GUJARAT | 3-2025 | 172 |  | 172 | 3/2027 | N.A. | 3/2027
April 2025 |  | 7 | TRANSMISSION SYSTEM FOR INTEGRATION OF KURNOOL-IV REZ ? PHASE-I (FOR 4.5 GW) | PGCIL | N18000413 | ANDHRA PRADESH | 3-2025 | 5000 |  | 5000 | 3/2027 | N.A. | 3/2027
April 2025 |  | 8 | RAJASTHAN REZ PH-V (PART-1: 4 GW) [SIROHI/NAGAUR] COMPLEX | PGCIL | N18000414 | RAJASTHAN | 3-2025 | 5028 |  | 5028 | 3/2027 | N.A. | 3/2027
April 2025 |  | 9 | AUGMENTATION AT FATEHGARH-II PS, FATEHGARH-IV PS (SECTION-II) AND BARMER-I | PGCIL | N18000415 | RAJASTHAN | 3-2025 | 404 |  | 404 | 12/2026 | N.A. | 12/2026
April 2025 |  | 10 | TRANSMISSION SYSTEM STRENGTHENING AT KURNOOL- III PS FOR INTEGRATION OF ADDITIONAL RE GENERATION PRO | PGCIL | N18000416 | ANDHRA PRADESH | 3-2025 | 2886 |  | 2886 | 3/2027 | N.A. | 3/2027
April 2025 |  | 11 | TRANSMISSION SCHEME FOR EVACUATION OF POWER FROM RATLE HEP (850 MW) & KIRU (624 MW): PART B | PGCIL | N18000417 | JAMMU AND KASHMIR | 3-2025 | 219 |  | 219 | 3/2027 | N.A. | 3/2027
April 2025 |  | 12 | BILASIPURA- GUWAHATI ROAD PKG-2 | NHIDCL | N24002229 | ASSAM | 11-2023 | 1338.61 |  | 1338.61 | 6/2027 | N.A. | 6/2027
April 2025 |  | 13 | BADARPUR ? CHURAIBARI PKG-6 | NHIDCL | N24002230 | ASSAM | 3-2024 | 870 |  | 870 | 3/2027 | N.A. | 3/2027
April 2025 |  | 14 | KARIMGANI - SUTARKANDI SECTION ON SILCHAR-CHURAIBARI PKG-7 | NHIDCL | N24002231 | ASSAM | 2-2024 | 791.79 |  | 791.79 | 2/2027 | N.A. | 2/2027
April 2025 |  | 15 | IMPHAL-KOHIMA ROAD PKG-5A | NHIDCL | N24002232 | MANIPUR | 9-2020 | 228.97 |  | 228.97 | 8/2026 | N.A. | 8/2026
April 2025 |  | 16 | DAINADUBI-DARUGIRI PKG-1B | NHIDCL | N24002233 | MEGHALAYA | 3-2023 | 705.83 |  | 705.83 | 3/2027 | N.A. | 3/2027
April 2025 |  | 17 | WIDENING TO 4L FROM KM.108.50 TO 139.00 OF NH-135A PKG- II (JAUNPUR TO AKBARPUR SECTION) ON HAM IN TH | MoRTH | N24002234 | UTTAR PRADESH | 3-2023 | 1511.57 |  | 1511.57 | 3/2027 | N.A. | 3/2027
April 2025 |  | 18 | CONSTRUCTION OF RAEBARELI RING ROAD (PHASE-2) WITH FOUR LANE CONFIGURATION FOR RAEBARELI CITY IN THE | MoRTH | N24002235 | UTTAR PRADESH | 3-2022 | 1273.72 |  | 1273.72 | 5/2027 | N.A. | 5/2027
April 2025 |  | 19 | CONSTRUCTION OF 4-LANE ACCESS CONTROLLED GREENFIELD HIGHWAY SECTION ON NH-163G (KHAMMAM - VIJAYAWADA | NHAI | N24002236 | TELANGANA | 3-2023 | 832.62 |  | 832.62 | 3/2025 | N.A. | 3/2027
April 2025 |  | 20 | REPLACEMENT OF HOT LEVELLER-1 OF PLATE MILL AT BHILAI STEEL PLANT | SAIL | N12000137 | CHHATTISGARH | 7-2024 | 198.62 |  | 198.62 | 7/2026 | N.A. | 7/2026
April 2025 |  | 21 | INSTALLATION OF NEW BAR MILL AT DURGAPUR STEEL PLANT | SAIL | N12000138 | WEST BENGAL | 9-2024 | 2115.44 |  | 2115.44 | 6/2027 | N.A. | 6/2027
April 2025 |  | 22 | UP-GRADATION OF BLAST FURNACE NO. 3 AT DURGAPUR STEEL PLANT | SAIL | N12000139 | WEST BENGAL | 9-2024 | 758.09 |  | 758.09 | 6/2026 | N.A. | 6/2026
April 2025 |  | 23 | REVAMPING OF AIR POLLUTION CONTROL SYSTEMS OF SP-1 AT DURGAPUR STEEL PLANT | SAIL | N12000140 | WEST BENGAL | 11-2024 | 196.4 |  | 196.4 | 5/2026 | N.A. | 5/2026
April 2025 |  | 24 | THIRD LADLE FURNACE IN SECONDARY REFINERY UNIT AT IISCO STEEL PLANT | SAIL | N12000141 | WEST BENGAL | 11-2024 | 227.96 |  | 227.96 | 7/2026 | N.A. | 7/2026
April 2025 |  | 25 | REPLACEMENT OF EXISTING GRINDERS IN CRM-I & II AT BOKARO STEEL PLANT | SAIL | N12000142 | JHARKHAND | 1-2025 | 211.94 |  | 211.94 | 1/2027 | N.A. | 1/2027
April 2025 |  | 26 | SECONDARY EMISSION CONTROL IN CONVERTERS OF SMS-II AT BOKARO STEEL PLANT | SAIL | N12000143 | JHARKHAND | 1-2025 | 207.13 |  | 207.13 | 10/2026 | N.A. | 10/2026
May 2025 |  | 1 | 50 MW WIND POWER PROJECT PART OF 150 MW SECI HYBRID | NLC | N06000292 | GUJARAT | 7-2022 | 383.84 |  | 383.84 | 6/2025 | Jan-2026 | 1/2026
May 2025 |  | 2 | NOKH SOLAR PV PROJECT 735 MW | NTPC | N18000418 | RAJASTHAN | 3-2022 | 4189.17 | 4378.17 | 4378.17 | 4/2024 | Jul-2025 | 7/2025
May 2025 |  | 3 | TRANSMISSION SCHEME FOR INTEGRATION OF DAVANAGERE / CHITRADURGA AND BELLARY REZ IN KARNATAKA | PGCIL | N18000419 | KARNATAKA | 3-2025 | 3453 |  | 3453 | 3/2027 | N.A. | 3/2027
May 2025 |  | 4 | IMPLEMENTATION OF LILO OF BOTH CIRCUITS OF 400KV VIDHYACHAL PS TO SASAN D/C LINE AT HINDALCO SWITCHY | PGCIL | N18000420 | HARYANA | 2-2025 | 370 |  | 370 | 12/2026 | N.A. | 12/2026
May 2025 |  | 5 | EASTERN REGION EXPANSION SCHEME: 43 [ERES: 43] | PGCIL | N18000421 | BIHAR | 5-2025 | 343 |  | 343 | 5/2026 | N.A. | 5/2026
May 2025 |  | 6 | EASTERN REGION EXPANSION SCHEME: 44 [ERES: 44] | PGCIL | N18000422 | BIHAR | 5-2025 | 409 |  | 409 | 5/2026 | N.A. | 5/2026
May 2025 |  | 7 | TRANSMISSION SYSTEM FOR STRENGTHENING TO FACILITATE EVACUATION OF POWER FROM BHADLA/BIKANER COMPLEX | PGCIL | N18000423 | UTTAR PRADESH | 12-2024 | 213 |  | 213 | 6/2026 | N.A. | 6/2026
May 2025 |  | 8 | CONSTRUCTION OF 4 LANE GAURIPUR BYPASS ON NH-17 IN THE STATE OF ASSAM | MoRTH | N24002237 | ASSAM | 3-2024 | 421.15 |  | 421.15 | 10/2026 | N.A. | 10/2026
May 2025 |  | 9 | CONSTRUCTION OF 2 LANE BARPETA BYPASS FROM KM 77+900(BARADI) TO KM 86+150( DEURIKUCHI) (LENGTH=8.25K | MoRTH | N24002238 | ASSAM | 3-2023 | 173.65 |  | 173.65 | 8/2026 | N.A. | 8/2026
May 2025 |  | 10 | IMPROVEMENT AND WIDENING TWO LANNIG WITH PAVED SHOULDER OF NATIONAL HIGHWAY 127B FROM KM 31.500 (GOE | MoRTH | N24002239 | MEGHALAYA | 12-2023 | 504 |  | 504 | 5/2027 | N.A. | 5/2027
May 2025 |  | 11 | IMPROVEMENT AND UP-GRADATION OF NH-227B (84 KOSI PARIKRAMA MARG) PACKAGE ?I, FROM KM 228.920 (JAGARN | MoRTH | N24002240 | UTTAR PRADESH | 3-2022 | 912.5 |  | 912.5 | 11/2026 | N.A. | 11/2026
May 2025 |  | 12 | IMPROVEMENT AND UP-GRADATION OF NH-227B (84 KOSI PARIKRAMA MARG) PACKAGE ?III, FROM KM.47.800 (GOSAI | MoRTH | N24002241 | UTTAR PRADESH | 3-2022 | 587.97 |  | 587.97 | 11/2026 | N.A. | 11/2026
May 2025 |  | 13 | CHOITHAR TO MARREM KHULLEN SECTION IMPHAL- UKHRUL - JESSAMI PKG-5 | NHIDCL | N24002242 | MANIPUR | 3-2023 | 564.05 |  | 564.05 | 3/2027 | N.A. | 3/2027
May 2025 |  | 14 | SILCHAR- CHURAIBARI PKG-5 | NHIDCL | N24002243 | ASSAM | 2-2024 | 1258.13 |  | 1258.13 | 10/2027 | N.A. | 10/2027
May 2025 |  | 15 | IMPHAL - KHONGSANG - JIRIBAM PKG-2 | NHIDCL | N24002244 | MANIPUR | 3-2021 | 195.14 |  | 195.14 | 3/2026 | N.A. | 3/2026

## Frozen-Deleted Projects
Month | Sector | Sl No | Project Name | Agency | Project Code | State | Original Cost (Rs Cr) | Date of Commissioning | Cumulative Expenditure (Rs Cr) | Progress (%)
May 2025 | POWER | 1 | NOKH PLOT-1 SOLAR PV PROJECT 245MW | NTPC | N18000320 | RAJASTHAN | 1352.71 | 08/2023 | 1057.36
May 2025 | POWER | 2 | NOKH PLOT-2 SOLAR PV PROJECT 245MW | NTPC | N18000321 | RAJASTHAN | 1409.52 | 08/2023 | 1403.89
May 2025 | POWER | 3 | NOKH PLOT-3 SOLAR PV PROJECT 245MW | NTPC | N18000322 | RAJASTHAN | 1426.94 | 08/2023 | 1170.29
May 2025 | POWER | 4 | 2 LANE WITH PAVED SHOULDER FROM KM 27+150 (GOLAI GAON) TO KM 47+682 (LEDO) ON EXISTING DIBRUGARH TO | NHIDCL | N24002026 | ASSAM | 643.42 | 12/2025 | 69.47
May 2025 | POWER | 5 | HOSPET-BELLARY-KARNATAKA AP BORDER | NHAI | N24000603 | KARNATAKA | 1167.42 | 03/2019 | 1028.39
May 2025 | POWER | 6 | UPGRADATION OF EXISTING ROAD TO 2-LANE WITH PAVED SHOULDER FROM KOHIMA TO MAO FROM KM 185.540 TO KM | NHIDCL | N24001259 | NAGALAND | 315.63 | 04/2022 | 116.7
May 2025 | POWER | 7 | IMPHAL - KHONGSANG PKG-2 | NHIDCL | N24001353 | MANIPUR | 195.14 | 12/2022 | 61.81
May 2025 | POWER | 8 | RISHI BORDER- ROLEP- MENLA PKG- 2A | NHIDCL | N24001361 | SIKKIM | 332.2 | 09/2023 | 149.38

## NE Region Ongoing
Month | State | Sector | Sl No | Project Name | Agency | Project Code | Date of Approval | Commissioning Original | Commissioning Revised | Commissioning Anticipated | Cost Original (Rs Cr) | Cost Revised (Rs Cr) | Cost Anticipated (Rs Cr) | Cumulative Expenditure (Rs Cr) | Physical Progress (%)
April 2025 |  | CIVIL AVIATION | 1 | CONSTRUCTION OF NEW GREEN FIELD AIRPORT AT HOLLONGI ITANAGAR ARUNACHAL PRADESH | AAI | N04000092 | 2-2019 | 8/2022 | 5/2025 | 5/2025 | 645.63 |  | 732 | 690.39 | 99.5
April 2025 |  | POWER | 2 | SUBANSIRI LOWER H.E.P (8X250 MW) | NHPC | NHPC | 9-2003 | 9/2010 | N.A. | 5/2026 | 6285.33 |  | 26075.54 | 24022.52 | 96.2
April 2025 |  | POWER | 3 | DIBANG MULTIPURPOSE PROJECT 2880 MW ARUNACHAL PRADESH | NHPC | N18000362 | 2-2023 | 2/2032 | N.A. | 2/2032 | 31876.39 |  | 31876.39 | 3222.41 | 14.7
April 2025 |  | ROAD TRANSPORT AND HIGHWAYS | 4 | TWO LANING OF JORAM KOLORIANG ROAD (NH 713) ON EPC BASIS FROM DESIGN KM. 138+000 TO KM. 154+036 [EX | NHIDCL | N24000683 | 2-2017 | 11/2023 | 3/2024 | 3/2025 | 180.57 | 244.1 | 180.57 | 160.46 | 96.62
April 2025 |  | ROAD TRANSPORT AND HIGHWAYS | 5 | CONSTRUCTION OF 2-LANE ROAD WITH PAVED SHOULDERS FROM KM16.00 OF ROING-HUNLI SECTION TO KM 21.500 OF | NHIDCL | N24000946 | 3-2017 | 3/2022 | 6/2025 | 12/2025 | 1718.59 | 1718.59 | 1718.59 | 728.21 | 73.2
April 2025 |  | ROAD TRANSPORT AND HIGHWAYS | 6 | TWO-LANING OF HAYULIANG? HAWAI BYPASS ROAD ON EPC BASIS FROM DESIGN KM. 51.825 TO KM. 63.131 EXISTI | NHIDCL | N24000979 | 1-2017 | 5/2023 | 5/2023 | 3/2025 | 256.66 |  | 256.66 | 0 | 63.59
April 2025 |  | ROAD TRANSPORT AND HIGHWAYS | 7 | CONSTRUCTION OF 2-LANING WITH HARD SHOULDERS OF ARROWA-KHUPA- HAYULIANG SECTION OF NH-113 FROM CH.68. | NHIDCL | N24001244 | 8-2020 | 4/2022 | 2/2025 | 2/2025 | 301.06 |  | 301.06 | 191.34 | 81.06
April 2025 |  | ROAD TRANSPORT AND HIGHWAYS | 8 | CONSTRUCTION OF 2 LANE ROAD OF POTIN TO PANGIN SECTION OF NH 13 FROM KM 163.59 TO KM 206.66 (PACKAGE | MoRTH | N24001297 | 3-2019 | 3/2027 | N.A. | 3/2027 | 450.65 |  | 450.65 | 389.68 | 95.28
April 2025 |  |  | 9 | 4 LANING OF ITANAGAR TO BANDARDEWA SECTION OF NH-415 FROM KM 40+430 TO KM 51+735 (PACKAGE B) ON EPC | MoRTH | N24001375 | 6-2020 | 3/2027 | N.A. | 3/2027 | 496.47 |  | 496.47 | 179.53 | 41.94
April 2025 |  |  | 10 | JORAM ? KOLORIANG ROAD FROM EXISTING KM 50.050 TO KM 70.00 (PKG-3) | NHIDCL | N24001390 | 8-2020 | 4/2022 | 8/2024 | 9/2024 | 228.71 |  | 228.71 | 98.86 | 99.52
April 2025 |  |  | 11 | JORAM ? KOLORIANG ROAD FROM EXISTING KM 70.00 TO KM 88.700 (PKG-4) | NHIDCL | N24001391 | 8-2020 | 4/2022 | 2/2024 | 9/2024 | 294.04 |  | 294.04 | 147.13 | 100
April 2025 |  |  | 12 | JORAM ? KOLORIANG ROAD FROM EXISTING KM122.600 TO KM138.00 (PKG-7) | NHIDCL | N24001393 | 8-2020 | 4/2022 | 2/2024 | 4/2025 | 184.88 |  | 184.88 | 99.32 | 97.42
April 2025 |  |  | 13 | HUNLI TO HAYULIANG PKG-1 | NHIDCL | N24002222 | 2-2024 | 2/2028 | N.A. | 2/2028 | 1262.43 |  | 1262.43 | 0 | 0.75
April 2025 |  |  | 14 | HUNLI TO ITHUN BRIDGE SECTION | NHIDCL | N24002223 | 2-2024 | 1/2027 | N.A. | 1/2027 | 275.5 |  | 275.5 | 0 | 1.2
April 2025 |  |  | 15 | PANGO TO JORGING ROAD PKG-1 | NHIDCL | N24002224 | 1-2024 | 7/2027 | N.A. | 7/2027 | 898.19 |  | 898.19 | 7.08 | 1.97
April 2025 |  | CIVIL AVIATION | 16 | CONSTRUCTION OF NEW INTEGRATED TERMINAL BUILDING AT LGBI AIRPORT GUWAHATI | AAI | N04000083 | 12-2016 | 3/2021 | 8/2025 | 8/2025 | 1142 |  | 2333 | 1850.93 | 86.95
April 2025 |  | CIVIL AVIATION | 17 | TIKAK EXTENSION OCP - 0.2 MTY | CIL | N06000290 | 7-2022 | 11/2030 | N.A. | 11/2030 | 159.77 |  | 159.77 | 81.45 | 0
April 2025 |  |  | 18 | TIRAP OCP | CIL | N06000291 | 11-2022 | 11/2027 | N.A. | 11/2027 | 289.46 |  | 289.46 | 105.59 | 0
April 2025 |  | HEALTH AND FAMILY WELFARE | 19 | ALL INDIA INSTITUTE OF MEDICAL SCIENCE AT GUWAHATI, ASSAM | HITES | N21000027 | 5-2017 | 5/2021 | 4/2023 | 11/2024 | 875 | 873.92 | 860 | 787.9 | 99.4
April 2025 |  | HEALTH AND FAMILY WELFARE | 20 | BORHOLLA GGS LIFE EXTENSION PROJECT | ONGC | N16000532 | 9-2023 | 5/2026 | N.A. | 5/2026 | 198.7 |  | 198.7 | 99.52 | 20.1
April 2025 |  | HEALTH AND FAMILY WELFARE | 21 | POWER RECOVERY TURBINE IN PFCCU | NRL | N16000510 | 3-2023 | 7/2025 | N.A. | 7/2025 | 293.5 |  | 293.5 | 97.22 | 90
April 2025 |  | HEALTH AND FAMILY WELFARE | 22 | DCU REVAMP PROJECT | NRL | N16000511 | 8-2021 | 3/2025 | N.A. | 10/2025 | 370 |  | 370 | 250.17 | 55.2
April 2025 |  | HEALTH AND FAMILY WELFARE | 23 | PIPELINE NETWORK PROJECT RUDRASAGAR | ONGC | N16000528 | 1-2023 | 4/2026 | N.A. | 4/2026 | 344.99 |  | 344.99 | 169.95 | 44.1
April 2025 |  | HEALTH AND FAMILY WELFARE | 24 | DEVELOPMENT OF SURFACE FACILITIES FOR PRODUCTION AND EVACUATION OF CRUDE OIL AND NATURAL GAS FROM NA | OIL | N16000331 | 1-2018 | 2/2020 | 12/2024 | 6/2025 | 543.91 | 726.93 | 726.93 | 491.56 | 93.89
April 2025 |  | HEALTH AND FAMILY WELFARE | 25 | NUMALIGARH REFINERY EXPANSION PROJECT 6 MMTPA REFINARY | NRL | N16000379 | 1-2019 | 10/2024 | N.A. | 12/2025 | 12366 |  | 18968 | 15412.49 | 73.06
April 2025 |  | HEALTH AND FAMILY WELFARE | 26 | NUMALIGARH REFINERY EXPANSION PROJECT COIT AND PIPELINES | NRL | N16000394 | 1-2019 | 10/2024 | N.A. | 9/2025 | 10228 |  | 9058 | 9247.5 | 84.53
April 2025 |  |  | 27 | EXPANSION OF GUWAHATI REFINERY FROM 1 TO 1.2 MMTPA ALONG WITH INSTALLATION OF CATALYTIC REFORMING UN | IOCL | N16000414 | 5-2021 | 10/2023 | 5/2026 | 5/2026 | 412 | 595.2 | 595.2 | 399.81 | 82.5
April 2025 |  |  | 28 | REVAMPING OF FACILITIES AT EXISTING GUWAHATI TERMINAL, ASSAM | IOCL | N16000441 | 3-2022 | 7/2026 | 9/2026 | 9/2026 | 277 |  | 277 | 175.69 | 66.02
April 2025 |  |  | 29 | UPGRADATION OF FACILITIES OF NUMALIGARH-SILIGURI PRODUCT PIPELINE (NSPL) FOR TRANSPORTATION OF ADDIT | OIL | N16000449 | 6-2021 | 12/2024 | 4/2025 | 7/2025 | 860 |  | 860 | 535.46 | 96
April 2025 |  |  | 30 | PROJECT TO CONSTRUCT A FIELD GAS GATHERING STATION AT BAGHJAN AREA FOR COLLECTION,PROCESSING | OIL | N16000450 | 12-2020 | 7/2024 | 3/2024 | 6/2025 | 430.76 |  | 430.76 | 308.9 | 83.56
April 2025 |  |  | 31 | CAPACITY EXPANSION OF DIGBOI REFINERY FROM 0.65 TO 1.0 MMTPA | IOCL | N16000457 | 6-2022 | 10/2025 | N.A. | 3/2026 | 768 |  | 768 | 80.34 | 31.4
April 2025 |  |  | 32 | CONSTRUCTION OF LPG FACILITIES AT KAMARDANGA, ASSAM | HPCL | N16000484 | 3-2023 | 7/2027 | 7/2027 | 7/2027 | 156.36 | 156.36 | 156.36 | 38.92 | 28.5
April 2025 |  |  | 33 | SETTING UP OF NEW RAIL FED POL FACILITY AT KAMARDANGA, ASSAM | HPCL | N16000494 | 3-2023 | 7/2027 | 7/2027 | 7/2027 | 384.04 |  | 384.04 | 87.82 | 30.7
April 2025 |  | RAILWAYS | 34 | BONGAIGAON-GOALPARA-GUWAHATI (176 KM) | NFR | N22000388 | 4-2015 | 3/2026 | N.A. | 3/2027 | 4059.65 |  | 4983.94 | 3626.2 | 92.31
April 2025 |  | ROAD TRANSPORT AND HIGHWAYS | 35 | BILASIPURA- GUWAHATI ROAD PKG-1 | NHIDCL | N24002225 | 2-2024 | 8/2027 | N.A. | 8/2027 | 1081.15 |  | 1081.15 | 0 | 1.16
April 2025 |  |  | 36 | SILCHAR-JIRIBAM PKG-1 | NHIDCL | N24002226 | 1-2024 | 1/2028 | N.A. | 1/2028 | 957.95 |  | 957.95 | 0 | 0
April 2025 |  |  | 37 | BILASIPURA- GUWAHATI ROAD PKG-2 | NHIDCL | N24002229 | 11-2023 | 6/2027 | N.A. | 6/2027 | 1338.61 |  | 1338.61 | 0.5 | 0
April 2025 |  |  | 38 | BADARPUR ? CHURAIBARI PKG-6 | NHIDCL | N24002230 | 3-2024 | 3/2027 | N.A. | 3/2027 | 870 |  | 870 | 0 | 0
April 2025 |  |  | 39 | KARIMGANI - SUTARKANDI SECTION ON SILCHAR-CHURAIBARI PKG-7 | NHIDCL | N24002231 | 2-2024 | 2/2027 | N.A. | 2/2027 | 791.79 |  | 791.79 | 0 | 0
April 2025 |  |  | 40 | DEVELOPMENT OF EXTERNAL TRUNK CONNECTIVITY AND INTERNAL INFRASTRUCTURE WORKS AT MULTI MODEL LOGISTIC | NHIDCL | N24002030 | 2-2020 | 3/2022 | N.A. | 9/2024 | 592.06 |  | 592.06 | 308.87 | 100
April 2025 |  |  | 41 | SILCHAR VAIRENGTE SAIRANG ROAD PKG- 1 | NHIDCL | N24002127 | 2-2023 | 7/2026 | N.A. | 7/2026 | 1256.9 |  | 1256.9 | 520.82 | 36.05
April 2025 |  |  | 42 | SILCHAR VAIRENGTE SAIRANG ROAD PKG- 2 | NHIDCL | N24002128 | 3-2023 | 8/2026 | N.A. | 8/2026 | 1716.21 |  | 1716.21 | 983.58 | 63.52
April 2025 |  |  | 43 | FOUR LANNING OF BADARPUR BYPASS FROM DESIGN CHAINAGE KM 27+300 AT CROSSING WITH NH-6 | NHIDCL | N24002129 | 2-2023 | 8/2026 | N.A. | 8/2026 | 574.26 |  | 574.26 | 283.15 | 51.88
April 2025 |  |  | 44 | TAMENGLONG- MAHUR ROAD PKG-7 | NHIDCL | N24002130 | 12-2023 | 3/2026 | N.A. | 3/2026 | 846.82 |  | 846.82 | 380.59 | 61.1
April 2025 |  |  | 45 | BILASIPURA-GUWAHATI ROAD PKG-8 | NHIDCL | N24002021 | 3-2023 | 12/2026 | N.A. | 12/2026 | 1457.59 |  | 1457.59 | 522.78 | 44.9
April 2025 |  |  | 46 | BILASIPURA-GUWAHATI ROAD PKG-9 | NHIDCL | N24002022 | 3-2023 | 6/2026 | N.A. | 6/2026 | 1000.27 |  | 1000.27 | 303.94 | 24.5
April 2025 |  |  | 47 | BILASIPURA-GUWAHATI ROAD PKG-10 | NHIDCL | N24002023 | 3-2023 | 6/2026 | N.A. | 6/2026 | 1264.9 |  | 1264.9 | 422.31 | 24.26
April 2025 |  |  | 48 | DABOKA BYPASS OF DABOKA - PAROKHAOWA PKG -1 | NHIDCL | N24002024 | 1-2023 | 11/2025 | N.A. | 11/2025 | 516.88 |  | 516.88 | 236.11 | 72.87
April 2025 |  |  | 49 | 2 LANE WITH PAVED SHOULDER FROM KM 16+900 (BOGAPANI) TO KM 27+150 (GOLAI GAON) ON EXISTING DIBRUGARH | NHIDCL | N24002025 | 1-2023 | 12/2025 | N.A. | 12/2026 | 356.65 |  | 356.65 | 129.18 | 14.06
April 2025 |  |  | 50 | 2 LANE WITH PAVED SHOULDER FROM KM 27+150 (GOLAI GAON) TO KM 47+682 (LEDO) ON EXISTING DIBRUGARH TO | NHIDCL | N24002026 | 3-2023 | 12/2025 | N.A. | 12/2026 | 643.42 |  | 643.42 | 69.47 | 8.89
April 2025 |  |  | 51 | CONSTRUCTION OF 4-LANE PANCHGRAM BYPASS FROM DESIGN CHAINAGE KM 15+500 ON NH-37 (OLD NH-53) AT KALIN | NHIDCL | N24002154 | 3-2023 | 2/2027 | N.A. | 2/2027 | 728.97 |  | 728.97 | 279.86 | 41.57
April 2025 |  |  | 52 | WIDENING/IMPROVEMENT TO 4-LANE WITH PAVED SHOULDER FROM KM 55+000 (NAGABANG GAMSUK) TO KM 82+514 (OY | NHIDCL | N24002155 | 3-2023 | 3/2027 | N.A. | 3/2027 | 665.47 |  | 665.47 | 153.6 | 36.55
April 2025 |  |  | 53 | DABOKA KATHKATI PACKAGE-5 | NHIDCL | N24001366 | 3-2021 | 1/2023 | N.A. | 11/2024 | 288.85 |  | 288.85 | 247.76 | 100
April 2025 |  |  | 54 | TULUNGIA-JOGIGHOPA-PAIKAN ROAD PKG- 7 | NHIDCL | N24001368 | 3-2021 | 1/2024 | N.A. | 10/2025 | 286.72 |  | 286.72 | 147.96 | 75.89
April 2025 |  |  | 55 | 4-L DHUBRI PHULBARI BRIDGE WITH APPROACH ROAD | NHIDCL | N24001326 | 11-2020 | 9/2028 | N.A. | 9/2028 | 4997.04 |  | 4997.04 | 2382.39 | 60.8
April 2025 |  |  | 56 | 2-LANING FROM YAINGANGPOKPI TO FINCH CORNER (PKG-I) | NHIDCL | N24001331 | 3-2020 | 6/2022 | 5/2025 | 12/2025 | 261.13 |  | 261.13 | 68.75 | 57.42
April 2025 |  |  | 57 | 2-LANING FROM YAINGANGPOKPI TO FINCH CORNER (PKG-II) | NHIDCL | N24001332 | 3-2020 | 6/2022 | 4/2025 | 12/2025 | 217.5 |  | 217.5 | 88.99 | 68.03
April 2025 |  |  | 58 | CONSTRUCTION OF 2-LANE MAJOR BRIDGE INCLUDING APPROACHESOVER BRAHMAPUTRA BETWEEN MAJULI ON NORTH BAN | MoRTH | N24001408 | 2-2021 | 7/2025 | N.A. | 7/2025 | 925.47 | 1019.17 | 925.47 | 192.5 | 30.65
April 2025 |  |  | 59 | JOGIGHOPA BRIDGE | NHIDCL | N24001434 | 8-2021 | 11/2024 | N.A. | 12/2026 | 746.76 |  | 746.76 | 328.49 | 65.84
April 2025 |  |  | 60 | DABOKA KATHKATI PACKAGE-6 | NHIDCL | N24001450 | 9-2021 | 7/2024 | N.A. | 5/2025 | 625.64 |  | 625.64 | 550.6 | 100
April 2025 |  |  | 61 | DABOKA KATHKATI PACKAGE-7 | NHIDCL | N24001537 | 11-2021 | 7/2024 | N.A. | 5/2025 | 204.1 |  | 204.1 | 142.31 | 95.01
April 2025 |  |  | 62 | FOUR LANING OF SRIRAMPUR-DHUBRI PKG- 2 | NHIDCL | N24001544 | 3-2022 | 1/2025 | N.A. | 6/2025 | 909.02 |  | 909.02 | 509.89 | 97.63
April 2025 |  |  | 63 | 6L STANDALONE FLYOVERS AT RAHA, DEMOW, BORGHAT, KATHIATALI JUNCTIONS AND ROB AT JAGIROAD ON STRETCHE | NHAI | N24001545 | 8-2022 | 12/2022 | 9/2024 | 6/2024 | 175 |  | 175 | 200.8 | 100
April 2025 |  |  | 64 | BALANCE WORK OF 4L OF NARIMBANGLO?JATINGA JUNCTION- HARANGAJO ROAD SECTION FROM KM 0.000 TO KM 49.23 | NHAI | N24001547 | 3-2022 | 1/2026 | N.A. | 1/2026 | 1909.98 |  | 1909.98 | 567.75 | 76.4
April 2025 |  |  | 65 | 6L STANDALONE FLYOVERS AT BONGAIGAON, CHAPAGURI, PATHSALA, SIMLAGURI CHOWK AND BAIHATA BYPASS JUNCTI | NHAI | N24001548 | 3-2022 | 6/2024 | N.A. | 5/2025 | 457.72 |  | 457.72 | 365.99 | 100
April 2025 |  |  | 66 | SRIRAMPUR - DHUBRI PKG-1 | NHIDCL | N24001831 | 3-2022 | 2/2025 | N.A. | 11/2026 | 613.89 |  | 613.89 | 110.75 | 35.63
April 2025 |  |  | 67 | DIBRUGARH-LAHOAL-CHABUA BYPASS PACKAGE-3 | NHIDCL | N24001832 | 1-2023 | 5/2025 | N.A. | 7/2025 | 458.59 |  | 458.59 | 196.51 | 61.42
April 2025 |  |  | 68 | CONSTRUCTION OF MANGALDOI BYPASS (NH-15) STARTING AT CH 26+400 AND TERMINATING AT CH 41+505 UNDER RA | MoRTH | N24001840 | 3-2022 | 4/2025 | N.A. | 4/2025 | 535.03 |  | 535.03 | 102.23 | 31.23
April 2025 |  |  | 69 | WIDENING AND UPGRADATION TO TWO LANES WITH PAVED SHOULDERS ROAD FROM TAMENGLONG TO MAHUR (NH-137) I | NHIDCL | N24001969 | 3-2023 | 8/2025 | N.A. | 8/2025 | 904.04 |  | 904.04 | 391.08 | 62.21
April 2025 |  |  | 70 | WIDENING AND UPGRADATION TO TWO LANES WITH PAVED SHOULDERS ROAD FROM TAMENGLONG TO MAHUR (NH-137) IN | NHIDCL | N24001970 | 3-2023 | 8/2025 | N.A. | 8/2025 | 860.37 |  | 860.37 | 365.69 | 62.61
April 2025 |  |  | 71 | WIDENING AND UPGRADATION TO TWO LANES WITH PAVED SHOULDERS ROAD FROM TAMENGLONG TO MAHUR (NH-137) IN | NHIDCL | N24001971 | 3-2023 | 8/2025 | N.A. | 8/2025 | 890.33 |  | 890.33 | 417.14 | 60.47
April 2025 |  |  | 72 | WIDENING/IMPROVEMENT TO 4-LANE WITH PAVED SHOULDER FROM KM 0+800 (KANDULIJAN GAON) TO KM 27+701 (SI | NHIDCL | N24001972 | 3-2023 | 4/2026 | N.A. | 4/2026 | 609.16 |  | 609.16 | 293.45 | 91.18
April 2025 |  |  | 73 | WIDENING/IMPROVEMENT TO 4-LANE WITH PAVED SHOULDER FROM KM 27+701 (SIMEN CHAPORI) TO KM 55+000 (NAG | NHIDCL | N24001973 | 3-2023 | 2/2026 | N.A. | 2/2026 | 562.05 |  | 562.05 | 276.61 | 92.13
April 2025 |  |  | 74 | 4-LANING OF HAPACHARA - TULUNGIA SECTION | NHIDCL | N24001246 | 3-2020 | 12/2022 | N.A. | 6/2024 | 220.2 |  | 220.2 | 217.06 | 97.76
April 2025 |  |  | 75 | 2-LANING OF CHURACHANDPUR TUIVAI SECTION OF NH-102B (PKG- IB) | NHIDCL | N24001269 | 3-2020 | 3/2022 | 1/2025 | 6/2025 | 216.49 | 241.52 | 216.49 | 111.59 | 82.79
April 2025 |  |  | 76 | 4 LANING OF JORHAT TO JHANJI SECTION FROM KM. 453.00 TO KM. 491.08 (DESIGN KM 403.200 TO KM 454.240) | NHIDCL | N24000319 | 6-2015 | 8/2023 | N.A. | 5/2025 | 437.39 |  | 437.39 | 547.95 | 96.13
April 2025 |  |  | 77 | FOUR LANING OF JHANJHI JN TO DEMOW SECTION FROM KM. 491.050 TO KM. 535.250(DESIGN KM 490.800 TO KM 5 | NHIDCL | N24000320 | 6-2015 | 3/2024 | N.A. | 10/2025 | 463.49 |  | 463.49 | 490.44 | 75.52
April 2025 |  |  | 78 | 4 LANING FROM JAMUGURI TO BISWANATH CHARIALI FROM KM 182 TO KM 208 OF NH- 52 | NHIDCL | N24000431 | 1-1991 | 6/2019 | 6/2019 | 6/2025 | 520.01 |  | 520.01 | 305.76 | 97.7
April 2025 |  |  | 79 | 4 LANING FROM RANGAGARA TO KALIABHOR TINALI FROM KM 297.00 TO KM 315.315 OF NH-37 ON EPC BASIS. | NHIDCL | N24000438 | 12-2015 | 12/2018 | 7/2021 | 12/2025 | 289.99 |  | 289.99 | 233.23 | 88.03
April 2025 |  |  | 80 | 4 LANING OF NH-37 SECTION BETWEEN DEMOW TO END OF MORAN BYPASS (FROM KM. 534.800 TO KM. 561.700) O | NHIDCL | N24000582 | 1-2016 | 1/2016 | N.A. | 5/2025 | 294.17 |  | 294.17 | 381.37 | 97.63
April 2025 |  |  | 81 | 4 LANING OF NH 37 SECTION BETWEEN END OF MORAN BYPASS TO BOGIBEEL JUNCTION NEAR LAPETKETA (KM. 561 | NHIDCL | N24000583 | 1-2016 | 12/2021 | N.A. | 5/2025 | 252 |  | 330.3 | 219.65 | 87.19
April 2025 |  | CIVIL AVIATION | 82 | CONSTRUCTION OF NEW INTEGRATED TERMINAL BUILDING, CONTROL TOWER CUM TECHNICAL BLOCK, APRON, LINK TAX | AAI | N04000100 | 11-2021 | 7/2024 | 3/2026 | 3/2026 | 499 |  | 499 | 154.47 | 39.4
April 2025 |  | RAILWAYS | 83 | JIRIBAM TO IMPHAL (TUPUI)(NL)(NEFR) | NFR | 220100288 | 4-2003 | 12/2026 | 3/2028 | 3/2028 | 14322.79 | 12274.06 | 22234.6 | 15265.4 | 68.7
April 2025 |  | ROAD TRANSPORT AND HIGHWAYS | 84 | 2-LANING OF CHURACHANDPUR TUIVAI SECTION OF NH-102B (PKG- 2A) | NHIDCL | N24001270 | 3-2020 | 6/2022 | 1/2025 | 9/2025 | 292.24 |  | 292.24 | 130.66 | 89.72
April 2025 |  | ROAD TRANSPORT AND HIGHWAYS | 85 | 2-LANING OF CHURACHANDPUR TUIVAI SECTION OF NH-102B (PKG- 2B) | NHIDCL | N24001271 | 6-2020 | 8/2022 | 1/2025 | 10/2025 | 365.53 |  | 365.53 | 156.31 | 77.36
April 2025 |  | ROAD TRANSPORT AND HIGHWAYS | 86 | 2-LANING OF CHURACHANDPUR TUIVAI SECTION OF NH-102B (PKG- 4A) | NHIDCL | N24001272 | 3-2020 | 6/2022 | 1/2025 | 5/2025 | 167.95 | 204.12 | 167.95 | 88.05 | 69.89
April 2025 |  | ROAD TRANSPORT AND HIGHWAYS | 87 | 2-LANING OF CHURACHANDPUR TUIVAI SECTION OF NH-102B (PKG- 4B) | NHIDCL | N24001273 | 7-2020 | 8/2022 | 2/2025 | 5/2025 | 177.76 |  | 177.76 | 89.67 | 80.53
April 2025 |  |  | 88 | IMPROVEMENT/UPGRADATION OF EXISTING 2-LANE TO 4-LANE DIVIDED HIGHWAY FROM TAPHOU KUKI TO DAILI SECTI | NHIDCL | N24001274 | 8-2020 | 4/2022 | 6/2025 | 10/2025 | 379.39 |  | 379.39 | 214.93 | 67.72
April 2025 |  |  | 89 | CONSTRUCTION OF 2-LANING WITH HARD SHOULDER ROAD OF UKHRUL - TOLOI - TADUBI SECTION OF NH-102A FROM | NHIDCL | N24001974 | 9-2021 | 1/2025 | 1/2025 | 9/2025 | 315.56 |  | 315.56 | 121.49 | 79.4
April 2025 |  |  | 90 | IMPHAL - KHONGSANG PKG-5 | NHIDCL | N24001538 | 12-2021 | 5/2024 | 2/2025 | 3/2026 | 410.68 |  | 410.68 | 147.81 | 67.64
April 2025 |  |  | 91 | IMPHAL - KHONGSANG PKG-6 | NHIDCL | N24001539 | 12-2021 | 2/2025 | 9/2025 | 12/2025 | 504.76 |  | 504.76 | 183.15 | 74.23
April 2025 |  |  | 92 | AKASH BRIDGE - JESSAMI SECTION PKG-2 | NHIDCL | N24001540 | 3-2022 | 2/2025 | 2/2025 | 3/2025 | 152.11 |  | 152.11 | 73.48 | 100
April 2025 |  |  | 93 | IMPHAL - KHONGSANG PKG-4 | NHIDCL | N24001453 | 8-2021 | 12/2023 | 7/2025 | 12/2025 | 579.63 |  | 579.63 | 172.65 | 69.38
April 2025 |  |  | 94 | TAMENGLONG - MAHUR PKG-5 | NHIDCL | N24001436 | 8-2021 | 5/2023 | 1/2025 | 1/2026 | 477.86 |  | 477.86 | 243.46 | 83.92
April 2025 |  |  | 95 | TAMENGLONG - MAHUR PKG-6 | NHIDCL | N24001437 | 9-2021 | 5/2023 | 11/2024 | 12/2025 | 311.18 |  | 311.18 | 186.15 | 81.65
April 2025 |  |  | 96 | MARAM - PEREN PKG-3 | NHIDCL | N24001439 | 8-2021 | 5/2023 | 10/2024 | 2/2025 | 467.41 |  | 467.41 | 264.83 | 100
April 2025 |  |  | 97 | MARIAM - PEREN PKG-1A | NHIDCL | N24001349 | 2-2021 | 12/2022 | 3/2025 | 7/2025 | 226.32 |  | 226.32 | 104.95 | 74.48
April 2025 |  |  | 98 | MARIAM - PEREN (PKG 1B) | NHIDCL | N24001350 | 2-2021 | 12/2022 | 10/2024 | 2/2025 | 188.36 |  | 188.36 | 126.71 | 100
April 2025 |  |  | 99 | IMPHAL - KHONGSANG PKG-2 | NHIDCL | N24001353 | 3-2021 | 12/2022 | 3/2025 | 3/2026 | 195.14 |  | 195.14 | 61.81 | 50.79
April 2025 |  |  | 100 | TAMENGLONG - MAHUR PKG-3 | NHIDCL | N24001354 | 3-2021 | 12/2022 | 9/2024 | 11/2025 | 234.08 |  | 234.08 | 139.45 | 91.85
April 2025 |  |  | 101 | SENAPATI- IMPHAL PKG-5B | NHIDCL | N24001400 | 3-2021 | 1/2023 | 5/2025 | 10/2025 | 211.7 |  | 211.7 | 83.79 | 68.65
April 2025 |  |  | 102 | IMPHAL - KHONGSANG PKG-3 | NHIDCL | N24001401 | 7-2021 | 3/2023 | 3/2025 | 10/2025 | 467 |  | 467 | 193.81 | 77.74
April 2025 |  |  | 103 | TAMENGLONG - MAHUR PKG-1 | NHIDCL | N24001402 | 7-2021 | 3/2023 | 1/2025 | 1/2025 | 185.8 |  | 185.8 | 117.78 | 100
April 2025 |  |  | 104 | TAMENGLONG - MAHUR PKG-2 | NHIDCL | N24001403 | 7-2021 | 3/2023 | 8/2024 | 12/2025 | 483.87 |  | 483.87 | 278.89 | 92.8
April 2025 |  |  | 105 | TAMENGLONG - MAHUR PKG-4 | NHIDCL | N24001404 | 7-2021 | 3/2023 | 2/2025 | 3/2025 | 198.77 |  | 198.77 | 127.86 | 100
April 2025 |  |  | 106 | CHURACHANPUR TUIVAI PKG-3 | NHIDCL | N24001405 | 7-2021 | 10/2023 | 3/2025 | 5/2025 | 673.27 |  | 673.27 | 377.12 | 78.46
April 2025 |  |  | 107 | CONSTRUCTION OF 2-LANING WITH HARD SHOULDER ROAD OF UKHRUL - TOLOI - TADUBI SECTION OF NH-102A FROM | NHIDCL | N24001473 | 9-2021 | 2/2024 | 3/2025 | 5/2025 | 310.76 |  | 310.76 | 129.15 | 96.77
April 2025 |  |  | 108 | LMPHAL TO JIRIBAM PKG-7 | NHIDCL | N24002028 | 1-2023 | 12/2025 | 12/2025 | 3/2026 | 760.16 |  | 760.16 | 148.98 | 58.19
April 2025 |  |  | 109 | UKHRUL TOLOI TADUBI PKG-2 | NHIDCL | N24002131 | 3-2023 | 2/2026 | 3/2026 | 3/2026 | 578.98 |  | 578.98 | 145.62 | 69.25
April 2025 |  |  | 110 | MARREM KHULLEN TO JESSAMI SECTION IMPHAL- UKHRUL - JESSAMI PKG-6 (DESIGN CHAINAGE KM 95.700 TO KM 14 | NHIDCL | N24002202 | 3-2023 | 12/2026 | N.A. | 12/2026 | 554.66 |  | 554.66 | 11.64 | 9.21
April 2025 |  |  | 111 | IMPHAL-KOHIMA ROAD PKG-4B | NHIDCL | N24002203 | 9-2020 | 6/2026 | N.A. | 6/2026 | 268.98 |  | 268.98 | 13.14 | 14.91
April 2025 |  |  | 112 | IMPHAL-KOHIMA ROAD PKG-5A | NHIDCL | N24002232 | 9-2020 | 8/2026 | N.A. | 8/2026 | 228.97 |  | 228.97 | 0 | 4.6
April 2025 |  |  | 113 | JESSAMI TO LAYNEN BRIDGE UKHRUL - JESSAMI PKG-7 | NHIDCL | N24002227 | 3-2023 | 6/2026 | N.A. | 6/2026 | 164.89 |  | 164.89 | 1.46 | 3.28
April 2025 |  | DEPARTMENT OF HIGHER EDUCATION | 114 | CONSTRUCTION AND DEVELOPMENT OF NATINAL INSTITUTE OF TECHNOLOGY MEGHALAYA PERMANENT CAMPUS AT SOHRA | RITES OF HIGHER | N42000001 | 9-2013 | 9/2014 | 7/2025 | 7/2025 | 484.32 | 429.7 | 429.7 | 295.55 | 83
April 2025 |  | ROAD TRANSPORT AND HIGHWAYS | 115 | DAINADUBI-DARUGIRI PKG-1B | NHIDCL | N24002233 | 3-2023 | 3/2027 | N.A. | 3/2027 | 705.83 |  | 705.83 | 0.31 | 0
April 2025 |  |  | 116 | RANIKOR-MAHESHKHOLA- BAGHMARA | RMB) PKG-4 (KANAI-RONGARA | NHIDCL | 10-2020 | 4/2022 | 6/2024 | 2/2025 | 157.86 | 146.92 | 157.86 | 152.95 | 100
April 2025 |  |  | 117 | REHABITITATION AND UP GRADATION OF NONGSTOIN-RAMBRAI-KYRSHAI ROAD UP TO MEGHALAYA-ASSAM BORDER FROM | NHIDCL | N24001474 | 9-2021 | 5/2024 | 12/2024 | 12/2025 | 359.86 |  | 359.86 | 232.55 | 89
April 2025 |  |  | 118 | CONSTRUCTION OF 2-LANE WITH PAVED SHOULDER OF SHILLONG WESTERN BYPASS STARTING FROM NH-06 NEAR LADUM | NHIDCL | N24002156 | 3-2023 | 9/2026 | N.A. | 9/2026 | 620.3 |  | 620.3 | 210.58 | 28
April 2025 |  |  | 119 | SHILLONG WESTERN BYPASS PACKAGE-2 | NHIDCL | N24002157 | 3-2023 | 9/2026 | N.A. | 9/2026 | 686 |  | 686 | 281.9 | 23
April 2025 |  |  | 120 | CONSTRUCTION OF 2-LANE WITH PAVED SHOULDERS OF SHILLONG WESTERN BYPASS STARTING FROM NH-06 NEAR LADU | NHIDCL | N24002158 | 3-2023 | 9/2026 | N.A. | 9/2026 | 562.48 |  | 562.48 | 297.79 | 24
April 2025 |  |  | 121 | RANIKOR-MAHESHKHOLA- BAGHMARA (RMB) PKG-3 | NHIDCL | N24001360 | 3-2021 | 12/2022 | 6/2024 | 2/2025 | 260.21 |  | 260.21 | 239.35 | 100
April 2025 |  |  | 122 | IMPROVEMENT/WIDENING TO 2-LANE WITH PAVED SHOULDER FROM (DESIGN KM 45.760 TO KM 63.530) BETWEEN SHIL | NHIDCL | N24001334 | 11-2020 | 12/2023 | N.A. | 4/2026 | 445.51 |  | 445.51 | 206.15 | 26
April 2025 |  |  | 123 | IMPROVEMENT/WIDENING TO 2-LANE WITH PAVED SHOULDER / 4-LANING FROM (DESIGN KM 63.530 TO KM 71.520) B | NHIDCL | N24001335 | 11-2020 | 12/2023 | N.A. | 11/2026 | 284.21 |  | 284.21 | 100.93 | 23.1
April 2025 |  |  | 124 | IMPROVEMENT/WIDENING TO 2-L WITH PAVED SHOULDER FROM (DESIGN KM 0.00 TO KM 10.670) / 4-LANING FROM ( | NHIDCL | N24001313 | 11-2020 | 12/2023 | 10/2025 | 10/2025 | 351.12 |  | 351.12 | 295.87 | 61.5
April 2025 |  |  | 125 | IMPROVEMENT/WIDENING TO 2-LANE WITH PAVED SHOULDER FROM (DESIGN KM 10.670 TO KM 37.550) BETWEEN SHIL | NHIDCL | N24001314 | 11-2020 | 12/2023 | N.A. | 8/2026 | 525.68 |  | 525.68 | 425.76 | 31
April 2025 |  |  | 126 | REHABILITATION AND UPGRADATION OF NONGSTOIN TO WAHKAJI SECTION OF PROJECT ROAD KM 0.000 TO KM 43.06 | MoRTH | N24001441 | 8-2020 | 2/2022 | 3/2025 | 3/2025 | 302.88 |  | 302.88 | 140.2 | 95
April 2025 |  |  | 127 | RANIKOR- MAHESHKHOLA- BAGHMARA PKG-2 | NHIDCL | N24001541 | 11-2021 | 6/2024 | 12/2024 | 5/2025 | 283.5 |  | 283.5 | 256.07 | 96.93
April 2025 |  |  | 128 | WIDENING TO 2-LANE WITH GEOMETRIC IMPROVEMENTS OF TURA DALU ROAD UNDER JICA FUNDING FROM KM 85.000 T | NHIDCL | N24000771 | 4-2017 | 9/2021 | 3/2025 | 6/2025 | 553.51 | 610.09 | 553.51 | 419.49 | 84.94
April 2025 |  | RAILWAYS | 129 | BHAIRABI SAIRONG, NL, NEFR | NFR | N22000100 | 4-2008 | 3/2025 | N.A. | 7/2025 | 6527.45 | 5021.45 | 8213.72 | 7948.91 | 96
April 2025 |  | ROAD TRANSPORT AND HIGHWAYS | 130 | WIDENING AND UP-GRADATION TO 2-LANE WITH PAVED SHOULDER CONFIGURATION AND GEOMETRIC IMPROVEMENTS FRO | NHIDCL | N24000857 | 4-2017 | 4/2023 | N.A. | 6/2025 | 519.09 |  | 785.65 | 667.78 | 96.6
April 2025 |  | ROAD TRANSPORT AND HIGHWAYS | 131 | WIDENING AND UP-GRADATION TO 2-LANE WITH PAVED SHOULDER CONFIGURATION AND GEOMETRIC IMPROVEMENTS FRO | NHIDCL | N24000858 | 4-2017 | 7/2023 | N.A. | 5/2024 | 640.07 |  | 1286.35 | 1192.26 | 98.9
April 2025 |  |  | 132 | WIDENING AND UP-GRADATION TO 2-LANE WITH PAVED SHOULDER CONFIGURATION AND GEOMETRIC IMPROVEMENTS FRO | NHIDCL | N24000861 | 4-2017 | 4/2023 | N.A. | 6/2025 | 473.18 |  | 688.25 | 539.93 | 94.38
April 2025 |  |  | 133 | WIDENING AND UP-GRADATION TO 2-LANE WITH PAVED SHOULDER CONFIGURATION AND GEOMETRIC IMPROVEMENTS FRO | NHIDCL | N24000862 | 4-2017 | 4/2023 | N.A. | 6/2025 | 537.82 |  | 789.05 | 768.85 | 96.82
April 2025 |  |  | 134 | WIDENING AND UP-GRADATION TO 2-LANE WITH PAVED SHOULDER CONFIGURATION AND GEOMETRIC IMPROVEMENTS FRO | NHIDCL | N24000863 | 4-2017 | 6/2023 | N.A. | 5/2025 | 518.53 |  | 906.76 | 847.17 | 97.2
April 2025 |  |  | 135 | WIDENING AND UP-GRADATION TO 2-LANE WITH PAVED SHOULDER CONFIGURATION AND GEOMETRIC IMPROVEMENTS FRO | NHIDCL | N24000864 | 4-2017 | 4/2024 | N.A. | 5/2025 | 404.29 |  | 750.32 | 654.75 | 97.71
April 2025 |  |  | 136 | WIDENING AND UP-GRADATION TO 2-LANE WITH PAVED SHOULDER CONFIGURATION AND GEOMETRIC IMPROVEMENTS FRO | NHIDCL | N24000865 | 4-2017 | 9/2023 | N.A. | 5/2025 | 428.11 |  | 746.39 | 606.93 | 97.9
April 2025 |  |  | 137 | CONSTRUCTION OF TWO LANE WITH PAVED SHOULDER OF SELLING-DULTE SECTION OF NH-06 (PKG-I) | NHIDCL | N24001278 | 3-2020 | 7/2022 | N.A. | 6/2024 | 206.88 |  | 219.33 | 265.18 | 100
April 2025 |  |  | 138 | CONSTRUCTION OF TWO LANE WITH PAVED SHOULDER OF SELLING-DULTE SECTION OF NH-06 (PKG-III) | NHIDCL | N24001281 | 3-2020 | 7/2022 | N.A. | 6/2025 | 292.24 |  | 331.17 | 291.2 | 93.2
April 2025 |  |  | 139 | KEIFANG - TUVAI PKG-1 | NHIDCL | N24001440 | 9-2021 | 5/2023 | N.A. | 5/2024 | 492.94 |  | 492.94 | 354.89 | 90.5
April 2025 |  |  | 140 | UP-GRADATION TO 2-LANE WITH PAVED SHOULDERS OF NGOPA - PAWLRANG SECTION OF NH 102B OF AIZAWL - IMPHA | NHIDCL | N24001975 | 9-2021 | 2/2025 | N.A. | 12/2025 | 523.78 |  | 523.78 | 643.63 | 78
April 2025 |  |  | 141 | DULTE- KWALKULH - CHAMPAI PKG.2 | NHIDCL | N24001356 | 3-2021 | 12/2022 | 4/2024 | 4/2024 | 233.25 |  | 233.25 | 172.09 | 100
April 2025 |  |  | 142 | TLABUNG - LUNGLEI PKG-A | NHIDCL | N24001358 | 3-2021 | 12/2022 | N.A. | 3/2026 | 698.44 |  | 698.45 | 499.26 | 59.4
April 2025 |  |  | 143 | TLABUNG - LUNGLEI PKG-B | NHIDCL | N24001359 | 3-2021 | 1/2023 | N.A. | 3/2026 | 740.58 |  | 740.58 | 362.71 | 57.4
April 2025 |  |  | 144 | KEIFANG - TUVAI PKG-3 | NHIDCL | N24002027 | 12-2021 | 2/2025 | N.A. | 12/2025 | 500.88 |  | 500.88 | 250.46 | 65.1
April 2025 |  |  | 145 | ZORINPUI- HMAWNGBU-LONGMASU (NH- 502A) | NHIDCL | N24002204 | 2-2023 | 12/2026 | N.A. | 12/2026 | 781.85 |  | 781.85 | 67.12 | 1.12
April 2025 |  | PETROLEUM | 146 | AUGMENTATION OF DIMAPUR DEPOT, DIMAPUR | IOCL | N16000529 | 8-2023 | 11/2027 | N.A. | 11/2027 | 227.62 |  | 227.62 | 4.54 | 17.5
April 2025 |  | RAILWAYS | 147 | NEW LINE FROM DIMAPUR TO ZUBZA(KOHIMA) NATIONAL PROJECT | NEFR | NFR | 4-2006 | 3/2026 | N.A. | 12/2029 | 6663.2 | 6663.2 | 6663.2 | 4611.24 | 71
April 2025 |  | ROAD TRANSPORT AND HIGHWAYS | 148 | CONSTRUCTION OF 2 LANE WITH HARD SHOULDER FROM DESIGN CHAINAGE KM 283.000 TO KM 325.440 (5- LEGGED J | NHIDCL | N24001475 | 3-2022 | 12/2024 | N.A. | 1/2025 | 605.36 |  | 605.36 | 273.21 | 100
April 2025 |  |  | 149 | CHANGTONGYA TO LONGLENG ROAD PKG- 2 | NHIDCL | N24001389 | 3-2020 | 6/2022 | 9/2022 | 1/2025 | 206.53 |  | 206.53 | 119.25 | 99.4
April 2025 |  |  | 150 | PEREN-DIMAPUR SECTION PKG-2 | NHIDCL | N24001406 | 7-2021 | 3/2023 | 9/2025 | 9/2025 | 258.52 |  | 258.52 | 83.96 | 77.9
April 2025 |  |  | 151 | WIDENING TO 2 LANE WITH HARD SHOULDER OF AKEGWO-AVANGKHU SECTION OF NH-202K FOR PACKAGE-I (DESIGN CH | NHIDCL | N24001976 | 12-2022 | 2/2026 | N.A. | 2/2026 | 430.24 |  | 430.24 | 92.24 | 49.95
April 2025 |  |  | 152 | WIDENING TO 2 LANE WITH HARD SHOULDER OF AKEGWO-AVANGKHU SECTION OF NH-202K FOR PACKAGE-II (DESIGN C | NHIDCL | N24001977 | 12-2022 | 2/2026 | N.A. | 2/2026 | 442.54 |  | 442.54 | 39.97 | 22.28
April 2025 |  |  | 153 | WIDENING TO 2 LANE WITH HARD SHOULDER OF AKEGWO-AVANGKHU SECTION OF NH-202K FOR PACKAGE-III (DESIGN | NHIDCL | N24001978 | 12-2022 | 2/2026 | N.A. | 2/2026 | 497.18 |  | 497.18 | 159.36 | 59.2
April 2025 |  |  | 154 | WIDENING OF EXISTING SINGLE LANE ROAD TO INTERMEDIATE LANE ROAD FROM MOKOKCHUNG TO CHARE VIA DIKHU I | MoRTH | N24001855 | 2-2021 | 6/2025 | 6/2025 | 6/2025 | 192.93 |  | 192.93 | 103.62 | 88.6
April 2025 |  |  | 155 | PEREN-DIMAPUR PKG-3 | NHIDCL | N24001912 | 2-2021 | 6/2025 | N.A. | 12/2025 | 177.77 | 199.02 | 199.02 | 43.33 | 61.13
April 2025 |  |  | 156 | MERANGKONG-TAMLU-MON (MTM) PKG-5 | NHIDCL | N24001438 | 7-2021 | 12/2023 | N.A. | 9/2025 | 161.73 |  | 161.73 | 62.08 | 66.76
April 2025 |  |  | 157 | WIDENING OF EXISTING SINGLE LANE / INTERMEDIATE LANE ROAD TO 2 LANE FROM KM 101 TO KM 125 OF NH 61 I | MoRTH | N24001465 | 6-2020 | 9/2024 | 6/2026 | 6/2026 | 252.19 |  | 252.19 | 11.97 | 14.5
April 2025 |  |  | 158 | WIDENING TO EXISTING SINGLE LANE /INTERMEDIATE LANE TO 2 LANE FROM KM185.00 TO KM 220.00 OF NH-61 (N | MoRTH | N24001466 | 3-2021 | 7/2024 | 6/2025 | 6/2025 | 297.24 |  | 297.24 | 137.57 | 76.2
April 2025 |  |  | 159 | WIDENING TO EXISTING SINGRE/INTERMEDIATE RANE TO 2 LANE FROM KM 135 TO KM 147 AND FROM KM 156.00 TO | MoRTH | N24001467 | 3-2021 | 2/2024 | 3/2025 | 3/2025 | 226.44 |  | 226.44 | 140.24 | 100
April 2025 |  |  | 160 | FOUR LANING OF DIMAPUR KOHIMA ROAD FROM DESIGN KM 123.840 TO KM 138.775 (EXISTING KM 124.100 TO KM 1 | NHIDCL | N24000686 | 3-2016 | 9/2019 | 11/2022 | 5/2025 | 373.07 | 534.41 | 534.41 | 382.5 | 99.81
April 2025 |  |  | 161 | FOUR LANING OF EXISTING DIMAPUR KOHIMA ROAD FROM DESIGN KM 152.490 TO KM 166.700 (EXISTING KM 156.00 | NHIDCL | N24000688 | 3-2016 | 8/2022 | 9/2025 | 9/2025 | 429.52 | 794.74 | 794.74 | 321.4 | 90.84
April 2025 |  |  | 162 | (I) CONSTRUCTION OF FOUR/SIX LANING FROM KM 132.375 TO KM 158.058 (TOTAL NEW ALIGNMENT LENGTH OF 20. | NHIDCL | N24000752 | 2-2017 | 9/2020 | 2/2023 | 4/2025 | 387 | 688.12 | 688.12 | 389.81 | 100
April 2025 |  |  | 163 | (II) CONSTRUCTION OF DIMAPUR BYPASS (ASSAM PORTION) OF 4/6 LANE PAVEMENT ON EPC BASIS FROM EXISTING | NHIDCL | N24000753 | 3-2018 | 11/2022 | 8/2024 | 4/2025 | 500.09 | 698.81 | 698.81 | 393.53 | 100
April 2025 |  |  | 164 | CONSTRUCTION OF TWO LANE WITH HARD SHOULDERS OF MERANGKONG-TAMLU- MON ROAD FROM EXISTING KM 20.456 TO | NHIDCL | N24000763 | 3-2018 | 12/2021 | 8/2022 | 8/2025 | 215.79 |  | 215.79 | 127.85 | 77.1
April 2025 |  |  | 165 | CONSTRUCTION OF TWO LANE WITH HARD SHOULDERS OF MERANGKONG-TAMLU- MON ROAD FROM EXISTING KM 60.345 TO | NHIDCL | N24000765 | 3-2018 | 9/2018 | 6/2023 | 9/2025 | 323.98 |  | 323.98 | 112.43 | 52.47
April 2025 |  |  | 166 | 2 LANING OF KOHIMA - JESSAMI SECTION | PACKAGE II | NHIDCL | 3-2020 | 6/2022 | N.A. | 1/2026 | 355.79 |  | 355.79 | 114.35 | 63.2
April 2025 |  |  | 167 | 2-LANING OF CHANGTONGYA TO LONGLENG ROAD OF NH-702 (PKG-I) | NHIDCL | N24001286 | 3-2020 | 6/2022 | 10/2022 | 6/2023 | 278.95 |  | 278.95 | 166.29 | 100
April 2025 |  |  | 168 | 2 LANING OF KOHIMA - JESSAMI SECTION | PACKAGE V | NHIDCL | 4-2020 | 12/2021 | 11/2025 | 11/2025 | 330.8 |  | 330.8 | 168.02 | 91.97
April 2025 |  |  | 169 | CONSTRUCTION OF 2-LANE WITH PAVED SHOULDER OF KOHIMA-BYPASS ROAD FROM DESIGN KM 0.00 TO KM 10.500 [D | NHIDCL | N24001288 | 8-2020 | 4/2022 | 11/2026 | 11/2026 | 232.29 | 350.88 | 232.29 | 69.98 | 14.42
April 2025 |  |  | 170 | CONSTRUCTION OF 2-LANE WITH PAVED SHOULDER OF KOHIMA-BYPASS ROAD FROM DESIGN KM10.500 TO 21.00KM [D | NHIDCL | N24001255 | 9-2020 | 10/2022 | 9/2024 | 6/2026 | 277.44 |  | 277.44 | 168.88 | 66.12
April 2025 |  |  | 171 | CONSTRUCTION OF 2-LANE WITH PAVED SHOULDER OF KOHIMA-BYPASS ROAD FROM DESIGN KM21.0 TO KM32.0 [DESIG | NHIDCL | N24001257 | 8-2020 | 10/2022 | 6/2025 | 6/2025 | 159.85 | 342.29 | 159.85 | 101.93 | 29.36
April 2025 |  |  | 172 | CONSTRUCTION OF 2-LANE WITH PAVED SHOULDER OF KOHIMA-BYPASS ROAD FROM DSIGN KM32.0 TO KM43.454 [DES | NHIDCL | N24001258 | 8-2020 | 4/2022 | 4/2023 | 8/2025 | 202.36 |  | 202.36 | 75.17 | 30.8
April 2025 |  |  | 173 | UPGRADATION OF EXISTING ROAD TO 2- LANE WITH PAVED SHOULDER FROM KOHIMA TO MAO FROM KM 185.540 TO KM | NHIDCL | N24001259 | 9-2020 | 4/2022 | 5/2024 | 12/2025 | 315.63 |  | 315.63 | 116.7 | 74.23
April 2025 |  |  | 174 | CONSTRUCTION OF 2 LANE WITH PAVED SHOULDER FROM KM. 168 TO 183.783 (YESEMYONG TO UNGER) ON MOKOKCHUN | MoRTH | N24001179 | 3-2017 | 11/2020 | 2/2023 | 2/2023 | 217.35 |  | 217.35 | 214.18 | 100
April 2025 |  |  | 175 | WIDENING OF EXISTING SINGLE/INTERMEDIATE LANE ROAD TO 2 LANE ROAD FROM KM. 83.00 TO KM 101.00 ON NH- | MoRTH | N24001180 | 3-2019 | 12/2022 | 1/2023 | 1/2023 | 237.51 |  | 237.51 | 215.47 | 100
April 2025 |  | CIVIL AVIATION | 176 | PAKYONG AIRPORT- WIDENING OF BASIC STRIP AT WESTERN SIDE OF RUNWAY CHAINAGE 80M TO 920M I/C SLOPE ST | AAI | N04000110 | 11-2023 | 6/2026 | N.A. | 6/2026 | 323.26 |  | 323.26 | 24.98 | 9.9
April 2025 |  | DEPARTMENT OF HIGHER EDUCATION | 177 | CONSTRUCTION OF SIKKIM UNIVERSITY CAMPUS PHASE-I, PACKAGE -II AT YANGANG SOUTH SIKKIM | Sikkim Universi | N44000002 | 8-2020 | 1/2025 | N.A. | 1/2025 | 314.06 |  | 303.55 | 157.24 | 76
April 2025 |  | POWER | 178 | TEESTA VI HE PROJECT | NHPC | N18000325 | 3-2019 | 3/2024 | N.A. | 12/2027 | 5748.04 |  | 5748.04 | 4249.86 | 67.08
April 2025 |  | POWER | 179 | RANGIT IV HE PROJECT | NHPC | N18000326 | 3-2021 | 5/2024 | N.A. | 12/2025 | 938.29 |  | 1828.11 | 1439.46 | 87.07
April 2025 |  | RAILWAYS | 180 | SEVOK RANGPO, NEFR | NFR | N22000102 | 4-2008 | 5/2015 | 12/2027 | 12/2027 | 7876.92 | 11963.43 | 11963.43 | 8569.25 | 76.5
April 2025 |  | ROAD TRANSPORT AND HIGHWAYS | 181 | CONSTRUCTION AND UPGRADATION OFEXISTINGROAD TO 2-LANE WITH PAVED SHOULDER INCLUDING GEOMETRIC IMPROV | NHIDCL | N24001261 | 8-2020 | 4/2023 | N.A. | 4/2025 | 311 |  | 273.78 | 257.86 | 94.94
April 2025 |  | ROAD TRANSPORT AND HIGHWAYS | 182 | CONSTRUCTION AND UPGRADATION OFEXISTINGROAD TO 2-LANE WITH PAVED SHOULDER INCLUDING GEOMETRIC IMPROV | NHIDCL | N24001262 | 7-2020 | 4/2023 | 8/2024 | 4/2025 | 345.38 | 395.59 | 395.59 | 362.61 | 90.82
April 2025 |  |  | 183 | CONSTUCTION/UPGRADATION OF EXISTING HIGHWAY TO 2 LANE WITH PAVED SHOULDER FROM KM 0.00 TO KM 13.00 N | NHIDCL | N24001251 | 3-2019 | 4/2022 | N.A. | 6/2025 | 402.94 |  | 402.94 | 247.12 | 76.54
April 2025 |  |  | 184 | CONSTUCTION/UPGRADATION OF EXISTING HIGHWAY TO 2 LANE WITH PAVED SHOULDER FROM KM 13.00 TO KM 25.600 | NHIDCL | N24001252 | 8-2020 | 4/2023 | 11/2024 | 7/2025 | 295.97 |  | 295.97 | 248.39 | 95.22
April 2025 |  |  | 185 | CONSTUCTION/UPGRADATION OF EXISTING HIGHWAY TO 2 LANE WITH PAVED SHOULDER FROM KM 26.10 TO KM 40.00 | NHIDCL | N24001254 | 3-2020 | 6/2022 | N.A. | 1/2024 | 242.97 |  | 244.45 | 246.91 | 100
April 2025 |  |  | 186 | CONSTRUCTION OF 2-LANE WITH PAVED SHOULDER INCLUDING GEOMETRIC IMPROVEMENT FROM KM 0.000 TO KM 16.00 | NHIDCL | N24000767 | 3-2017 | 4/2022 | 5/2022 | 12/2023 | 375.8 |  | 375.8 | 288.56 | 96.55
April 2025 |  |  | 187 | CONSTRUCTION OF 2-LANE WITH PAVED SHOULDER INCLUDING GEOMETRIC IMPROVEMENT FROM KM 16.000 TO KM 32.5 | NHIDCL | N24000768 | 11-2017 | 10/2020 | 8/2023 | 4/2024 | 290.05 |  | 290.05 | 218.36 | 100
April 2025 |  |  | 188 | CONSTRUCTION OF 2-LANE WITH PAVED SHOULDER GANGTOK BYPASS ROAD FROM RANIPOOL TO BURTUK (L=23.316KM) | MoRTH | N24001442 | 10-2021 | 5/2024 | 1/2026 | 1/2026 | 385.15 |  | 385.15 | 170.32 | 81.11
April 2025 |  |  | 189 | RISHI BORDER- ROLEP- MENLA PKG- 2A | NHIDCL | N24001361 | 1-2021 | 9/2023 | 4/2025 | 12/2025 | 332.2 | 348.92 | 348.92 | 149.38 | 41.04
April 2025 |  |  | 190 | RISHI BORDER- ROLEP- MENLA PKG- 3B | NHIDCL | N24001362 | 12-2020 | 2/2024 | 4/2025 | 12/2025 | 410.6 | 379.3 | 379.3 | 234.27 | 73.22
April 2025 |  |  | 191 | CONSTRUCTION AND UPGRADATION OF EXISTING ROAD TO 2-LANE WITH PAVED SHOULDER FROM KM27.200 (END OF RO | NHIDCL | N24001336 | 8-2020 | 4/2023 | 10/2024 | 12/2025 | 230.45 | 244.91 | 244.91 | 206.95 | 82.32
April 2025 |  |  | 192 | CONSTRUCTION AND UPGRADATION OF EXISTING ROAD TO 2-LANE WITH PAVED SHOULDER FROM NEW ROLEP BRIDGE AT | NHIDCL | N24001337 | 10-2020 | 11/2023 | 7/2025 | 3/2026 | 493.42 | 478.79 | 478.79 | 302.83 | 55.21
April 2025 |  |  | 193 | CONSTRUCTION OF 2-LANE WITH PAVED SHOULDER OF NEW GREEN FIELD ALIGNMENT FROM CHOCHENPHERI AT KM 52.0 | NHIDCL | N24001338 | 10-2020 | 12/2023 | 6/2025 | 12/2026 | 816.79 | 786.6 | 786.6 | 326.82 | 50.6
April 2025 |  |  | 194 | REHABILITATION AND UPGRADATION OF EXISTING ROAD TO 2-LANE WITH PAVED SHOULDER INCLUDING GEOMETRIC IM | NHIDCL | N24001327 | 8-2020 | 5/2022 | 10/2023 | 12/2025 | 292.8 |  | 292.8 | 202.92 | 60.8
April 2025 |  |  | 195 | CONSTRUCTION OF 2-LANE ROAD WITH PAVED SHOULDER (GREENFIELD ALIGNMENT) OF EXISTING STRETCH BETWEEN L | NHIDCL | N24001322 | 9-2020 | 5/2022 | 10/2023 | 12/2025 | 183.31 | 439.56 | 439.56 | 355.31 | 51.85
April 2025 |  |  | 196 | CONSTRUCTION OF 2-LANE SPECIFICATION ROAD WITH PAVED SHOULDER AS REALIGNMENT | GREENFIELD ALIGNMENT | NHIDCL | 9-2020 | 5/2023 | 8/2024 | 12/2025 | 262.84 | 414.2 | 414.2 | 221.86 | 47.56
April 2025 |  | PETROLEUM | 197 | GRASS ROOT RAIL FED DEPOT AT SEKERKOTE, AGARTALA AS RESITEMENT OF EXISTING DHARMANAGAR DEPOT | IOCL | N16000495 | 6-2022 | 8/2025 | 9/2025 | 9/2025 | 656 |  | 656 | 395.18 | 81.15
April 2025 |  | ROAD TRANSPORT AND HIGHWAYS | 198 | KHOWAI ?TELIAMURA-AMARPUR-HARINA- SABROOM SECTION PKG-4 | NHIDCL | N24002228 | 1-2024 | 12/2026 | N.A. | 12/2026 | 726.9 |  | 726.9 | 0 | 2.25
April 2025 |  |  | 199 | CHAMPAK NAGAR TO KHAYERPUR SECTION (DESIGN KM 242+500 TO KM 261+610) | NHIDCL | N24002205 | 12-2023 | 9/2026 | N.A. | 9/2026 | 920.66 |  | 920.66 | 63.55 | 18.6
April 2025 |  |  | 200 | 4 LANE WITH PAVED SHOULDER AGARTALA BYPASS (WESTERN SIDE) CONNECTING NH- 8 | NHIDCL | N24002132 | 3-2023 | 3/2027 | N.A. | 3/2027 | 2026.05 |  | 2026.05 | 18.44 | 7.96
April 2025 |  |  | 201 | REHABILITATION AND UP-GRADATION OF ROAD FROM DESIGN KM 25.250 TO KM 36.460 (TOTAL LENGH: 11.210 KM) | NHIDCL | N24002159 | 2-2020 | 3/2026 | N.A. | 3/2026 | 174.43 |  | 174.43 | 7.56 | 16.61
April 2025 |  |  | 202 | IMPROVEMENT AND WIDENING TO 2-LANE WITH PAVED SHOULDER OF ROAD FROM KM 101.300 TO KM 127.319 (TOTAL | NHIDCL | N24002160 | 1-2024 | 7/2026 | N.A. | 7/2026 | 431.78 |  | 431.78 | 46.6 | 31.45
April 2025 |  |  | 203 | KHOWAI ?TELIAMURA-AMARPUR-HARINA- SABROOM PACKAGE-2 | NHIDCL | N24002161 | 1-2024 | 9/2026 | N.A. | 9/2026 | 657.21 |  | 657.21 | 11.96 | 27.5
April 2025 |  |  | 204 | KHOWAI ?TELIAMURA-AMARPUR-HARINA- SABROOM PACKAGE-3 | NHIDCL | N24002162 | 1-2024 | 9/2026 | N.A. | 9/2026 | 670.9 |  | 670.9 | 0 | 0
April 2025 |  |  | 205 | 2-LANING FROM JOLAIBARI - BELONIA | NHIDCL | N24001317 | 6-2020 | 1/2022 | N.A. | 4/2025 | 201.99 |  | 287.47 | 148.22 | 100
April 2025 |  |  | 206 | KAILASHAHAR TO KHOWAI PKG-4 | NHIDCL | N24001309 | 11-2020 | 6/2022 | 10/2023 | 11/2024 | 159.13 | 171.5 | 171.5 | 84.33 | 100
April 2025 |  |  | 207 | MANU-SIMLUNG ( PKG 4) | NHIDCL | N24001363 | 3-2021 | 12/2022 | N.A. | 12/2025 | 354.79 |  | 354.79 | 34.08 | 0
April 2025 |  |  | 208 | 2 LANING FROM MANU-SIMLUNG PKG-2 | NHIDCL | N24001542 | 2-2022 | 1/2025 | 5/2025 | 5/2025 | 456.88 |  | 456.88 | 122.23 | 49.17
April 2025 |  |  | 209 | IMPROVEMENT AND WIDENING TO 2-LANE WITH EARTHEN PAVED SHOULDER FROM UDAIPUR TO SRIMANTAPUR | NHIDCL | N24001914 | 5-2023 | 11/2024 | N.A. | 11/2025 | 195.95 |  | 195.95 | 38.1 | 38.44
April 2025 |  |  | 210 | REHABILITATION AND UPGRADATION OF ROAD FROM KM 0.00 TO KM 18.600 OF KUMARGHAT-KAILASHAHAR SECTION | NHIDCL | N24001263 | 6-2020 | 1/2022 | 2/2024 | 12/2024 | 277.5 | 302.02 | 302.02 | 260.38 | 99.94
May 2025 |  | CIVIL AVIATION | 1 | CONSTRUCTION OF NEW GREEN FIELD AIRPORT AT HOLLONGI ITANAGAR ARUNACHAL PRADESH | AAI | N04000092 | 2-2019 | 8/2022 | Jun-2025 | 6/2025 | 645.63 | 732 | 732 | 693.71 | 99.72
May 2025 |  | POWER | 2 | SUBANSIRI LOWER H.E.P (8X250 MW) | NHPC | NHPC | 9-2003 | 9/2010 | N.A. | 5/2026 | 6285.33 |  | 26075.54 | 24213.84 | 96.49
May 2025 |  | POWER | 3 | DIBANG MULTIPURPOSE PROJECT 2880 MW ARUNACHAL PRADESH | NHPC | N18000362 | 2-2023 | 2/2032 | N.A. | 2/2032 | 31876.39 |  | 31876.39 | 3306.4 | 15.74
May 2025 |  | ROAD TRANSPORT AND HIGHWAYS | 4 | TWO LANING OF JORAM KOLORIANG ROAD (NH 713) ON EPC BASIS FROM DESIGN KM. 138+000 TO KM. 154+036 [EX | NHIDCL | N24000683 | 2-2017 | 11/2023 | Mar-2024 | 12/2024 | 180.57 | 244.1 | 180.57 | 160.46 | 96.62
May 2025 |  | ROAD TRANSPORT AND HIGHWAYS | 5 | CONSTRUCTION OF 2-LANE ROAD WITH PAVED SHOULDERS FROM KM16.00 OF ROING-HUNLI SECTION TO KM 21.500 OF | NHIDCL | N24000946 | 3-2017 | 3/2022 | Jun-2025 | 12/2025 | 1718.59 | 1718.59 | 1718.59 | 728.21 | 73.64
May 2025 |  | ROAD TRANSPORT AND HIGHWAYS | 6 | TWO-LANING OF HAYULIANG? HAWAI BYPASS ROAD ON EPC BASIS FROM DESIGN KM. 51.825 TO KM. 63.131 EXISTI | NHIDCL | N24000979 | 1-2017 | 5/2023 | May-2023 | 3/2025 | 256.66 |  | 256.66 | 0 | 63.59
May 2025 |  | ROAD TRANSPORT AND HIGHWAYS | 7 | CONSTRUCTION OF 2-LANING WITH HARD SHOULDERS OF ARROWA-KHUPA- HAYULIANG SECTION OF NH-113 FROM CH.68. | NHIDCL | N24001244 | 8-2020 | 4/2022 | Feb-2025 | 2/2025 | 301.06 |  | 301.06 | 198.22 | 81.06
May 2025 |  | ROAD TRANSPORT AND HIGHWAYS | 8 | CONSTRUCTION OF 2 LANE ROAD OF POTIN TO PANGIN SECTION OF NH 13 FROM KM 163.59 TO KM 206.66 (PACKAGE | MoRTH | N24001297 | 3-2019 | 3/2027 | N.A. | 3/2027 | 450.65 |  | 450.65 | 398.18 | 95.84
May 2025 |  |  | 9 | 4 LANING OF ITANAGAR TO BANDARDEWA SECTION OF NH-415 FROM KM 40+430 TO KM 51+735 (PACKAGE B) ON EPC | MoRTH | N24001375 | 6-2020 | 3/2027 | N.A. | 3/2027 | 496.47 |  | 496.47 | 194.62 | 42.69
May 2025 |  |  | 10 | JORAM ? KOLORIANG ROAD FROM EXISTING KM 50.050 TO KM 70.00 (PKG-3) | NHIDCL | N24001390 | 8-2020 | 4/2022 | Aug-2024 | 9/2024 | 228.71 |  | 228.71 | 98.86 | 99.52
May 2025 |  |  | 11 | JORAM ? KOLORIANG ROAD FROM EXISTING KM122.600 TO KM138.00 (PKG-7) | NHIDCL | N24001393 | 8-2020 | 4/2022 | Feb-2024 | 6/2025 | 184.88 |  | 184.88 | 99.32 | 97.42
May 2025 |  |  | 12 | HUNLI TO HAYULIANG PKG-1 | NHIDCL | N24002222 | 2-2024 | 2/2028 | N.A. | 2/2028 | 1262.43 |  | 1262.43 | 12.12 | 2.35
May 2025 |  |  | 13 | HUNLI TO ITHUN BRIDGE SECTION | NHIDCL | N24002223 | 2-2024 | 1/2027 | N.A. | 1/2027 | 275.5 |  | 275.5 | 7.61 | 6.01
May 2025 |  |  | 14 | PANGO TO JORGING ROAD PKG-1 | NHIDCL | N24002224 | 1-2024 | 7/2027 | N.A. | 7/2027 | 898.19 |  | 898.19 | 7.08 | 4.06
May 2025 |  | CIVIL AVIATION | 15 | CONSTRUCTION OF NEW INTEGRATED TERMINAL BUILDING AT LGBI AIRPORT GUWAHATI | AAI | N04000083 | 12-2016 | 3/2021 | Aug-2025 | 8/2025 | 1142 |  | 2333 | 1884.13 | 87.93
May 2025 |  | COAL | 16 | TIKAK EXTENSION OCP - 0.2 MTY | CIL | N06000290 | 7-2022 | 11/2030 | N.A. | 11/2030 | 159.77 |  | 159.77 | 81.45 | 0
May 2025 |  | COAL | 17 | TIRAP OCP | CIL | N06000291 | 11-2022 | 11/2027 | N.A. | 11/2027 | 289.46 |  | 289.46 | 105.59 | 0
May 2025 |  | HEALTH AND FAMILY WELFARE | 18 | ALL INDIA INSTITUTE OF MEDICAL SCIENCE AT GUWAHATI, ASSAM | HITES | N21000027 | 5-2017 | 5/2021 | Apr-2023 | 6/2025 | 875 | 873.92 | 860 | 787.9 | 99.52
May 2025 |  | HEALTH AND FAMILY WELFARE | 19 | BORHOLLA GGS LIFE EXTENSION PROJECT | ONGC | N16000532 | 9-2023 | 5/2026 | N.A. | 5/2026 | 198.7 |  | 198.7 | 99.52 | 23.8
May 2025 |  | HEALTH AND FAMILY WELFARE | 20 | POWER RECOVERY TURBINE IN PFCCU | NRL | N16000510 | 3-2023 | 7/2025 | N.A. | 7/2025 | 293.5 |  | 293.5 | 97.22 | 91
May 2025 |  | HEALTH AND FAMILY WELFARE | 21 | DCU REVAMP PROJECT | NRL | N16000511 | 8-2021 | 3/2025 | N.A. | 10/2025 | 370 |  | 370 | 255.51 | 56.1
May 2025 |  | HEALTH AND FAMILY WELFARE | 22 | PIPELINE NETWORK PROJECT RUDRASAGAR | ONGC | N16000528 | 1-2023 | 4/2026 | N.A. | 4/2026 | 344.99 |  | 344.99 | 172.04 | 45.3
May 2025 |  | HEALTH AND FAMILY WELFARE | 23 | DEVELOPMENT OF SURFACE FACILITIES FOR PRODUCTION AND EVACUATION OF CRUDE OIL AND NATURAL GAS FROM NA | OIL | N16000331 | 1-2018 | 2/2020 | Dec-2024 | 6/2025 | 543.91 | 726.93 | 726.93 | 491.56 | 93.95
May 2025 |  | HEALTH AND FAMILY WELFARE | 24 | NUMALIGARH REFINERY EXPANSION PROJECT 6 MMTPA REFINARY | NRL | N16000379 | 1-2019 | 10/2024 | N.A. | 12/2025 | 12366 |  | 18968 | 16013.82 | 74.01
May 2025 |  | HEALTH AND FAMILY WELFARE | 25 | NUMALIGARH REFINERY EXPANSION PROJECT COIT AND PIPELINES | NRL | N16000394 | 1-2019 | 10/2024 | N.A. | 9/2025 | 10228 |  | 9058 | 9447.83 | 85.06
May 2025 |  | HEALTH AND FAMILY WELFARE | 26 | EXPANSION OF GUWAHATI REFINERY FROM 1 TO 1.2 MMTPA ALONG WITH INSTALLATION OF CATALYTIC REFORMING UN | IOCL | N16000414 | 5-2021 | 10/2023 | May-2026 | 5/2026 | 412 | 595.2 | 595.2 | 396.08 | 82.8
May 2025 |  |  | 27 | REVAMPING OF FACILITIES AT EXISTING GUWAHATI TERMINAL, ASSAM | IOCL | N16000441 | 3-2022 | 7/2026 | Sep-2026 | 9/2026 | 277 |  | 277 | 180.17 | 66.4
May 2025 |  |  | 28 | UPGRADATION OF FACILITIES OF NUMALIGARH-SILIGURI PRODUCT PIPELINE (NSPL) FOR TRANSPORTATION OF ADDIT | OIL | N16000449 | 6-2021 | 12/2024 | Apr-2025 | 7/2025 | 860 |  | 860 | 535.46 | 96.5
May 2025 |  |  | 29 | PROJECT TO CONSTRUCT A FIELD GAS GATHERING STATION AT BAGHJAN AREA FOR COLLECTION,PROCESSING | OIL | N16000450 | 12-2020 | 7/2024 | Mar-2024 | 6/2025 | 430.76 |  | 430.76 | 319.86 | 83.66
May 2025 |  |  | 30 | CAPACITY EXPANSION OF DIGBOI REFINERY FROM 0.65 TO 1.0 MMTPA | IOCL | N16000457 | 6-2022 | 10/2025 | N.A. | 3/2026 | 768 |  | 768 | 86.75 | 33.1
May 2025 |  |  | 31 | CONSTRUCTION OF LPG FACILITIES AT KAMARDANGA, ASSAM | HPCL | N16000484 | 3-2023 | 7/2027 | Jul-2027 | 7/2027 | 156.36 | 156.36 | 156.36 | 41.02 | 31.5
May 2025 |  |  | 32 | SETTING UP OF NEW RAIL FED POL FACILITY AT KAMARDANGA, ASSAM | HPCL | N16000494 | 3-2023 | 7/2027 | Jul-2027 | 7/2027 | 384.04 |  | 384.04 | 94 | 34.4
May 2025 |  | RAILWAYS | 33 | BONGAIGAON-GOALPARA-GUWAHATI (176 KM) | NFR | N22000388 | 4-2015 | 3/2026 | N.A. | 3/2027 | 4059.65 |  | 4983.94 | 3652.94 | 92.31
May 2025 |  | ROAD TRANSPORT AND HIGHWAYS | 34 | BILASIPURA- GUWAHATI ROAD PKG-1 | NHIDCL | N24002225 | 2-2024 | 8/2027 | N.A. | 8/2027 | 1081.15 |  | 1081.15 | 33.93 | 2.76
May 2025 |  | ROAD TRANSPORT AND HIGHWAYS | 35 | SILCHAR-JIRIBAM PKG-1 | NHIDCL | N24002226 | 1-2024 | 1/2028 | N.A. | 1/2028 | 957.95 |  | 957.95 | 0 | 16.25
May 2025 |  |  | 36 | BILASIPURA- GUWAHATI ROAD PKG-2 | NHIDCL | N24002229 | 11-2023 | 6/2027 | N.A. | 6/2027 | 1338.61 |  | 1338.61 | 0.5 | 0
May 2025 |  |  | 37 | BADARPUR ? CHURAIBARI PKG-6 | NHIDCL | N24002230 | 3-2024 | 3/2027 | N.A. | 3/2027 | 870 |  | 870 | 0 | 0
May 2025 |  |  | 38 | KARIMGANI - SUTARKANDI SECTION ON SILCHAR-CHURAIBARI PKG-7 | NHIDCL | N24002231 | 2-2024 | 2/2027 | N.A. | 2/2027 | 791.79 |  | 791.79 | 0 | 0
May 2025 |  |  | 39 | CONSTRUCTION OF 4 LANE GAURIPUR BYPASS ON NH-17 IN THE STATE OF ASSAM | MoRTH | N24002237 | 3-2024 | 10/2026 | N.A. | 10/2026 | 421.15 |  | 421.15 | 0 | 0
May 2025 |  |  | 40 | CONSTRUCTION OF 2 LANE BARPETA BYPASS FROM KM 77+900(BARADI) TO KM 86+150( DEURIKUCHI) (LENGTH=8.25K | MoRTH | N24002238 | 3-2023 | 8/2026 | N.A. | 8/2026 | 173.65 |  | 173.65 | 0 | 0
May 2025 |  |  | 41 | SILCHAR- CHURAIBARI PKG-5 | NHIDCL | N24002243 | 2-2024 | 10/2027 | N.A. | 10/2027 | 1258.13 |  | 1258.13 | 0 | 0
May 2025 |  |  | 42 | CONSTRUCTION OF 4-LANE PANCHGRAM BYPASS FROM DESIGN CHAINAGE KM 15+500 ON NH-37 (OLD NH-53) AT KALIN | NHIDCL | N24002154 | 3-2023 | 2/2027 | N.A. | 2/2027 | 728.97 |  | 728.97 | 279.87 | 42.68
May 2025 |  |  | 43 | WIDENING/IMPROVEMENT TO 4-LANE WITH PAVED SHOULDER FROM KM 55+000 (NAGABANG GAMSUK) TO KM 82+514 (OY | NHIDCL | N24002155 | 3-2023 | 3/2027 | N.A. | 3/2027 | 665.47 |  | 665.47 | 183.63 | 45.53
May 2025 |  |  | 44 | DEVELOPMENT OF EXTERNAL TRUNK CONNECTIVITY AND INTERNAL INFRASTRUCTURE WORKS AT MULTI MODEL LOGISTIC | NHIDCL | N24002030 | 2-2020 | 3/2022 | N.A. | 9/2024 | 592.06 |  | 592.06 | 308.87 | 100
May 2025 |  |  | 45 | SILCHAR VAIRENGTE SAIRANG ROAD PKG- 1 | NHIDCL | N24002127 | 2-2023 | 7/2026 | N.A. | 7/2026 | 1256.9 |  | 1256.9 | 537.26 | 38.6
May 2025 |  |  | 46 | SILCHAR VAIRENGTE SAIRANG ROAD PKG- 2 | NHIDCL | N24002128 | 3-2023 | 8/2026 | N.A. | 8/2026 | 1716.21 |  | 1716.21 | 983.58 | 64.03
May 2025 |  |  | 47 | FOUR LANNING OF BADARPUR BYPASS FROM DESIGN CHAINAGE KM 27+300 AT CROSSING WITH NH-6 | NHIDCL | N24002129 | 2-2023 | 8/2026 | N.A. | 8/2026 | 574.26 |  | 574.26 | 297.5 | 54.88
May 2025 |  |  | 48 | TAMENGLONG- MAHUR ROAD PKG-7 | NHIDCL | N24002130 | 12-2023 | 3/2026 | N.A. | 3/2026 | 846.82 |  | 846.82 | 404.51 | 68.8
May 2025 |  |  | 49 | CONSTRUCTION OF 2-LANE MAJOR BRIDGE INCLUDING APPROACHESOVER BRAHMAPUTRA BETWEEN MAJULI ON NORTH BAN | MoRTH | N24001408 | 2-2021 | 7/2025 | N.A. | 7/2025 | 925.47 | 1019.17 | 925.47 | 192.5 | 30.65
May 2025 |  |  | 50 | JOGIGHOPA BRIDGE | NHIDCL | N24001434 | 8-2021 | 11/2024 | N.A. | 12/2026 | 746.76 |  | 746.76 | 335.2 | 66.96
May 2025 |  |  | 51 | DABOKA KATHKATI PACKAGE-5 | NHIDCL | N24001366 | 3-2021 | 1/2023 | N.A. | 11/2024 | 288.85 |  | 288.85 | 247.76 | 100
May 2025 |  |  | 52 | TULUNGIA-JOGIGHOPA-PAIKAN ROAD PKG- 7 | NHIDCL | N24001368 | 3-2021 | 1/2024 | N.A. | 10/2025 | 286.72 |  | 286.72 | 158.15 | 81.63
May 2025 |  |  | 53 | 4-L DHUBRI PHULBARI BRIDGE WITH APPROACH ROAD | NHIDCL | N24001326 | 11-2020 | 9/2028 | N.A. | 9/2028 | 4997.04 |  | 4997.04 | 2408.8 | 62.1
May 2025 |  |  | 54 | 2-LANING FROM YAINGANGPOKPI TO FINCH CORNER (PKG-I) | NHIDCL | N24001331 | 3-2020 | 6/2022 | May-2025 | 12/2025 | 261.13 |  | 261.13 | 68.75 | 57.42
May 2025 |  |  | 55 | 2-LANING FROM YAINGANGPOKPI TO FINCH CORNER (PKG-II) | NHIDCL | N24001332 | 3-2020 | 6/2022 | Apr-2025 | 12/2025 | 217.5 |  | 217.5 | 88.99 | 68.03
May 2025 |  |  | 56 | DABOKA KATHKATI PACKAGE-6 | NHIDCL | N24001450 | 9-2021 | 7/2024 | N.A. | 5/2025 | 625.64 |  | 625.64 | 556.44 | 100
May 2025 |  |  | 57 | FOUR LANING OF SRIRAMPUR-DHUBRI PKG- 2 | NHIDCL | N24001544 | 3-2022 | 1/2025 | N.A. | 6/2025 | 909.02 |  | 909.02 | 532.44 | 98.92
May 2025 |  |  | 58 | 6L STANDALONE FLYOVERS AT RAHA, DEMOW, BORGHAT, KATHIATALI JUNCTIONS AND ROB AT JAGIROAD ON STRETCHE | NHAI | N24001545 | 8-2022 | 12/2022 | Sep-2024 | 6/2024 | 175 |  | 175 | 200.8 | 100
May 2025 |  |  | 59 | BALANCE WORK OF 4L OF NARIMBANGLO?JATINGA JUNCTION- HARANGAJO ROAD SECTION FROM KM 0.000 TO KM 49.23 | NHAI | N24001547 | 3-2022 | 1/2026 | N.A. | 1/2026 | 1909.98 |  | 1909.98 | 654.6 | 77.1
May 2025 |  |  | 60 | 6L STANDALONE FLYOVERS AT BONGAIGAON, CHAPAGURI, PATHSALA, SIMLAGURI CHOWK AND BAIHATA BYPASS JUNCTI | NHAI | N24001548 | 3-2022 | 6/2024 | N.A. | 5/2025 | 457.72 |  | 457.72 | 366.34 | 100
May 2025 |  |  | 61 | SRIRAMPUR - DHUBRI PKG-1 | NHIDCL | N24001831 | 3-2022 | 2/2025 | N.A. | 11/2026 | 613.89 |  | 613.89 | 110.76 | 35.7
May 2025 |  |  | 62 | DIBRUGARH-LAHOAL-CHABUA BYPASS PACKAGE-3 | NHIDCL | N24001832 | 1-2023 | 5/2025 | N.A. | 7/2025 | 458.59 |  | 458.59 | 198.15 | 65.62
May 2025 |  |  | 63 | CONSTRUCTION OF MANGALDOI BYPASS (NH-15) STARTING AT CH 26+400 AND TERMINATING AT CH 41+505 UNDER RA | MoRTH | N24001840 | 3-2022 | 4/2025 | N.A. | 3/2026 | 535.03 |  | 535.03 | 102.23 | 34.15
May 2025 |  |  | 64 | WIDENING AND UPGRADATION TO TWO LANES WITH PAVED SHOULDERS ROAD FROM TAMENGLONG TO MAHUR (NH-137) I | NHIDCL | N24001969 | 3-2023 | 8/2025 | N.A. | 8/2025 | 904.04 |  | 904.04 | 409.15 | 67.3
May 2025 |  |  | 65 | WIDENING AND UPGRADATION TO TWO LANES WITH PAVED SHOULDERS ROAD FROM TAMENGLONG TO MAHUR (NH-137) IN | NHIDCL | N24001970 | 3-2023 | 8/2025 | N.A. | 8/2025 | 860.37 |  | 860.37 | 393.82 | 65.95
May 2025 |  |  | 66 | WIDENING AND UPGRADATION TO TWO LANES WITH PAVED SHOULDERS ROAD FROM TAMENGLONG TO MAHUR (NH-137) IN | NHIDCL | N24001971 | 3-2023 | 8/2025 | N.A. | 8/2025 | 890.33 |  | 890.33 | 454.34 | 63.7
May 2025 |  |  | 67 | WIDENING/IMPROVEMENT TO 4-LANE WITH PAVED SHOULDER FROM KM 0+800 (KANDULIJAN GAON) TO KM 27+701 (SI | NHIDCL | N24001972 | 3-2023 | 4/2026 | N.A. | 4/2026 | 609.16 |  | 609.16 | 305.73 | 94.97
May 2025 |  |  | 68 | WIDENING/IMPROVEMENT TO 4-LANE WITH PAVED SHOULDER FROM KM 27+701 (SIMEN CHAPORI) TO KM 55+000 (NAG | NHIDCL | N24001973 | 3-2023 | 2/2026 | N.A. | 2/2026 | 562.05 |  | 562.05 | 290.2 | 95.71
May 2025 |  |  | 69 | DABOKA KATHKATI PACKAGE-7 | NHIDCL | N24001537 | 11-2021 | 7/2024 | N.A. | 7/2025 | 204.1 |  | 204.1 | 143.45 | 96.02
May 2025 |  |  | 70 | BILASIPURA-GUWAHATI ROAD PKG-8 | NHIDCL | N24002021 | 3-2023 | 12/2026 | N.A. | 12/2026 | 1457.59 |  | 1457.59 | 537.09 | 46.78
May 2025 |  |  | 71 | BILASIPURA-GUWAHATI ROAD PKG-9 | NHIDCL | N24002022 | 3-2023 | 6/2026 | N.A. | 6/2026 | 1000.27 |  | 1000.27 | 304.61 | 27.07
May 2025 |  |  | 72 | BILASIPURA-GUWAHATI ROAD PKG-10 | NHIDCL | N24002023 | 3-2023 | 6/2026 | N.A. | 6/2026 | 1264.9 |  | 1264.9 | 422.31 | 25.57
May 2025 |  |  | 73 | DABOKA BYPASS OF DABOKA - PAROKHAOWA PKG -1 | NHIDCL | N24002024 | 1-2023 | 11/2025 | N.A. | 11/2025 | 516.88 |  | 516.88 | 242.91 | 73.5
May 2025 |  |  | 74 | 2 LANE WITH PAVED SHOULDER FROM KM 16+900 (BOGAPANI) TO KM 27+150 (GOLAI GAON) ON EXISTING DIBRUGARH | NHIDCL | N24002025 | 1-2023 | 12/2025 | N.A. | 12/2026 | 356.65 |  | 356.65 | 129.18 | 16.28
May 2025 |  |  | 75 | 2-LANING OF CHURACHANDPUR TUIVAI SECTION OF NH-102B (PKG- IB) | NHIDCL | N24001269 | 3-2020 | 3/2022 | Jun-2025 | 8/2025 | 216.49 | 241.52 | 216.49 | 111.59 | 85.83
May 2025 |  |  | 76 | 4-LANING OF HAPACHARA - TULUNGIA SECTION | NHIDCL | N24001246 | 3-2020 | 12/2022 | N.A. | 6/2024 | 220.2 |  | 220.2 | 217.18 | 97.76
May 2025 |  |  | 77 | 4 LANING OF JORHAT TO JHANJI SECTION FROM KM. 453.00 TO KM. 491.08 (DESIGN KM 403.200 TO KM 454.240) | NHIDCL | N24000319 | 6-2015 | 8/2023 | N.A. | 6/2025 | 437.39 |  | 437.39 | 574.56 | 96.95
May 2025 |  |  | 78 | FOUR LANING OF JHANJHI JN TO DEMOW SECTION FROM KM. 491.050 TO KM. 535.250(DESIGN KM 490.800 TO KM 5 | NHIDCL | N24000320 | 6-2015 | 3/2024 | N.A. | 10/2025 | 463.49 |  | 463.49 | 515.52 | 76.95
May 2025 |  |  | 79 | 4 LANING FROM JAMUGURI TO BISWANATH CHARIALI FROM KM 182 TO KM 208 OF NH- 52 | NHIDCL | N24000431 | 1-1991 | 6/2019 | Jun-2019 | 7/2025 | 520.01 |  | 520.01 | 305.76 | 97.9
May 2025 |  |  | 80 | 4 LANING FROM RANGAGARA TO KALIABHOR TINALI FROM KM 297.00 TO KM 315.315 OF NH-37 ON EPC BASIS. | NHIDCL | N24000438 | 12-2015 | 12/2018 | Jul-2021 | 12/2025 | 289.99 |  | 289.99 | 233.23 | 88.03
May 2025 |  |  | 81 | 4 LANING OF NH-37 SECTION BETWEEN DEMOW TO END OF MORAN BYPASS (FROM KM. 534.800 TO KM. 561.700) O | NHIDCL | N24000582 | 1-2016 | 1/2016 | N.A. | 7/2025 | 294.17 |  | 294.17 | 389.75 | 97.88
May 2025 |  |  | 82 | 4 LANING OF NH 37 SECTION BETWEEN END OF MORAN BYPASS TO BOGIBEEL JUNCTION NEAR LAPETKETA (KM. 561 | NHIDCL | N24000583 | 1-2016 | 12/2021 | N.A. | 7/2025 | 252 |  | 330.3 | 219.65 | 91.31
May 2025 |  | CIVIL AVIATION | 83 | CONSTRUCTION OF NEW INTEGRATED TERMINAL BUILDING, CONTROL TOWER CUM TECHNICAL BLOCK, APRON, LINK TAX | AAI | N04000100 | 11-2021 | 7/2024 | Mar-2026 | 3/2026 | 499 |  | 499 | 154.47 | 40.36
May 2025 |  | RAILWAYS | 84 | JIRIBAM TO IMPHAL (TUPUI)(NL)(NEFR) | NFR | 220100288 | 4-2003 | 12/2026 | Mar-2028 | 3/2028 | 14322.79 | 12274.06 | 22234.6 | 15338.76 | 69
May 2025 |  | ROAD TRANSPORT AND HIGHWAYS | 85 | 2-LANING OF CHURACHANDPUR TUIVAI SECTION OF NH-102B (PKG- 2A) | NHIDCL | N24001270 | 3-2020 | 6/2022 | Jun-2025 | 9/2025 | 292.24 |  | 292.24 | 130.66 | 89.88
May 2025 |  | ROAD TRANSPORT AND HIGHWAYS | 86 | 2-LANING OF CHURACHANDPUR TUIVAI SECTION OF NH-102B (PKG- 2B) | NHIDCL | N24001271 | 6-2020 | 8/2022 | Jun-2025 | 10/2025 | 365.53 |  | 365.53 | 156.31 | 77.36
May 2025 |  | ROAD TRANSPORT AND HIGHWAYS | 87 | 2-LANING OF CHURACHANDPUR TUIVAI SECTION OF NH-102B (PKG- 4A) | NHIDCL | N24001272 | 3-2020 | 6/2022 | Jan-2025 | 6/2025 | 167.95 | 204.12 | 167.95 | 88.05 | 69.89
May 2025 |  | ROAD TRANSPORT AND HIGHWAYS | 88 | 2-LANING OF CHURACHANDPUR TUIVAI SECTION OF NH-102B (PKG- 4B) | NHIDCL | N24001273 | 7-2020 | 8/2022 | Feb-2025 | 6/2025 | 177.76 |  | 177.76 | 89.67 | 80.53
May 2025 |  |  | 89 | IMPROVEMENT/UPGRADATION OF EXISTING 2-LANE TO 4-LANE DIVIDED HIGHWAY FROM TAPHOU KUKI TO DAILI SECTI | NHIDCL | N24001274 | 8-2020 | 4/2022 | Jun-2025 | 12/2025 | 379.39 |  | 379.39 | 218.03 | 70.31
May 2025 |  |  | 90 | IMPHAL - KHONGSANG PKG-5 | NHIDCL | N24001538 | 12-2021 | 5/2024 | Jan-2026 | 3/2026 | 410.68 |  | 410.68 | 147.81 | 68.79
May 2025 |  |  | 91 | IMPHAL - KHONGSANG PKG-6 | NHIDCL | N24001539 | 12-2021 | 2/2025 | Sep-2025 | 12/2025 | 504.76 |  | 504.76 | 183.15 | 76.52
May 2025 |  |  | 92 | AKASH BRIDGE - JESSAMI SECTION PKG-2 | NHIDCL | N24001540 | 3-2022 | 2/2025 | Feb-2025 | 3/2025 | 152.11 |  | 152.11 | 73.48 | 100
May 2025 |  |  | 93 | CONSTRUCTION OF 2-LANING WITH HARD SHOULDER ROAD OF UKHRUL - TOLOI - TADUBI SECTION OF NH-102A FROM | NHIDCL | N24001974 | 9-2021 | 1/2025 | Aug-2025 | 8/2025 | 315.56 |  | 315.56 | 137.81 | 88.54
May 2025 |  |  | 94 | IMPHAL - KHONGSANG PKG-4 | NHIDCL | N24001453 | 8-2021 | 12/2023 | Jul-2025 | 12/2025 | 579.63 |  | 579.63 | 172.65 | 72
May 2025 |  |  | 95 | CONSTRUCTION OF 2-LANING WITH HARD SHOULDER ROAD OF UKHRUL - TOLOI - TADUBI SECTION OF NH-102A FROM | NHIDCL | N24001473 | 9-2021 | 2/2024 | Mar-2025 | 6/2025 | 310.76 |  | 310.76 | 129.15 | 96.77
May 2025 |  |  | 96 | MARIAM - PEREN PKG-1A | NHIDCL | N24001349 | 2-2021 | 12/2022 | Mar-2025 | 12/2025 | 226.32 |  | 226.32 | 105.78 | 74.48
May 2025 |  |  | 97 | MARIAM - PEREN (PKG 1B) | NHIDCL | N24001350 | 2-2021 | 12/2022 | Jan-2025 | 9/2025 | 188.36 |  | 188.36 | 126.71 | 100
May 2025 |  |  | 98 | TAMENGLONG - MAHUR PKG-3 | NHIDCL | N24001354 | 3-2021 | 12/2022 | Sep-2024 | 11/2025 | 234.08 |  | 234.08 | 139.45 | 92.82
May 2025 |  |  | 99 | MARAM - PEREN PKG-3 | NHIDCL | N24001439 | 8-2021 | 5/2023 | Oct-2024 | 2/2025 | 467.41 |  | 467.41 | 264.83 | 100
May 2025 |  |  | 100 | TAMENGLONG - MAHUR PKG-5 | NHIDCL | N24001436 | 8-2021 | 5/2023 | Jan-2025 | 1/2026 | 477.86 |  | 477.86 | 246.09 | 84.6
May 2025 |  |  | 101 | TAMENGLONG - MAHUR PKG-6 | NHIDCL | N24001437 | 9-2021 | 5/2023 | Nov-2024 | 12/2025 | 311.18 |  | 311.18 | 190.96 | 83.5
May 2025 |  |  | 102 | SENAPATI- IMPHAL PKG-5B | NHIDCL | N24001400 | 3-2021 | 1/2023 | May-2025 | 10/2025 | 211.7 |  | 211.7 | 83.79 | 70.72
May 2025 |  |  | 103 | IMPHAL - KHONGSANG PKG-3 | NHIDCL | N24001401 | 7-2021 | 3/2023 | Mar-2025 | 10/2025 | 467 |  | 467 | 193.81 | 77.8
May 2025 |  |  | 104 | TAMENGLONG - MAHUR PKG-1 | NHIDCL | N24001402 | 7-2021 | 3/2023 | Jan-2025 | 1/2025 | 185.8 |  | 185.8 | 117.78 | 100
May 2025 |  |  | 105 | TAMENGLONG - MAHUR PKG-2 | NHIDCL | N24001403 | 7-2021 | 3/2023 | Jan-2025 | 12/2025 | 483.87 |  | 483.87 | 278.89 | 92.94
May 2025 |  |  | 106 | TAMENGLONG - MAHUR PKG-4 | NHIDCL | N24001404 | 7-2021 | 3/2023 | Feb-2025 | 3/2025 | 198.77 |  | 198.77 | 127.86 | 100
May 2025 |  |  | 107 | CHURACHANPUR TUIVAI PKG-3 | NHIDCL | N24001405 | 7-2021 | 10/2023 | Mar-2025 | 12/2025 | 673.27 |  | 673.27 | 382.37 | 79.47
May 2025 |  |  | 108 | UKHRUL TOLOI TADUBI PKG-2 | NHIDCL | N24002131 | 3-2023 | 2/2026 | Mar-2026 | 3/2026 | 578.98 |  | 578.98 | 153.92 | 71.25
May 2025 |  |  | 109 | MARREM KHULLEN TO JESSAMI SECTION IMPHAL- UKHRUL - JESSAMI PKG-6 (DESIGN CHAINAGE KM 95.700 TO KM 14 | NHIDCL | N24002202 | 3-2023 | 12/2026 | N.A. | 12/2026 | 554.66 |  | 554.66 | 17.79 | 11.93
May 2025 |  |  | 110 | IMPHAL-KOHIMA ROAD PKG-4B | NHIDCL | N24002203 | 9-2020 | 6/2026 | N.A. | 6/2026 | 268.98 |  | 268.98 | 13.14 | 15.9
May 2025 |  |  | 111 | IMPHAL - KHONGSANG - JIRIBAM PKG-2 | NHIDCL | N24002244 | 3-2021 | 3/2026 | N.A. | 3/2026 | 195.14 |  | 195.14 | 0 | 7.19
May 2025 |  |  | 112 | LMPHAL TO JIRIBAM PKG-7 | NHIDCL | N24002028 | 1-2023 | 12/2025 | Dec-2025 | 3/2026 | 760.16 |  | 760.16 | 148.98 | 60.6
May 2025 |  |  | 113 | IMPHAL-KOHIMA ROAD PKG-5A | NHIDCL | N24002232 | 9-2020 | 8/2026 | N.A. | 8/2026 | 228.97 |  | 228.97 | 0 | 5.96
May 2025 |  |  | 114 | JESSAMI TO LAYNEN BRIDGE UKHRUL - JESSAMI PKG-7 | NHIDCL | N24002227 | 3-2023 | 6/2026 | N.A. | 6/2026 | 164.89 |  | 164.89 | 1.46 | 6.5
May 2025 |  |  | 115 | CHOITHAR TO MARREM KHULLEN SECTION IMPHAL- UKHRUL - JESSAMI PKG-5 | NHIDCL | N24002242 | 3-2023 | 3/2027 | N.A. | 3/2027 | 564.05 |  | 564.05 | 0 | 0
May 2025 |  | DEPARTMENT OF HIGHER EDUCATION | 116 | CONSTRUCTION AND DEVELOPMENT OF NATINAL INSTITUTE OF TECHNOLOGY MEGHALAYA PERMANENT CAMPUS AT SOHRA | RITES OF HIGHER | N42000001 | 9-2013 | 9/2014 | Jul-2025 | 7/2025 | 484.32 | 429.7 | 494.52 | 270.55 | 84
May 2025 |  | ROAD TRANSPORT AND HIGHWAYS | 117 | DAINADUBI-DARUGIRI PKG-1B | NHIDCL | N24002233 | 3-2023 | 3/2027 | N.A. | 3/2027 | 705.83 |  | 705.83 | 0.31 | 1.55
May 2025 |  | ROAD TRANSPORT AND HIGHWAYS | 118 | RANIKOR-MAHESHKHOLA- BAGHMARA | RMB) PKG-4 (KANAI-RONGARA | NHIDCL | 10-2020 | 4/2022 | Jun-2024 | 2/2025 | 157.86 | 146.92 | 157.86 | 152.95 | 100
May 2025 |  | ROAD TRANSPORT AND HIGHWAYS | 119 | IMPROVEMENT AND WIDENING TWO LANNIG WITH PAVED SHOULDER OF NATIONAL HIGHWAY 127B FROM KM 31.500 (GOE | MoRTH | N24002239 | 12-2023 | 5/2027 | N.A. | 5/2027 | 504 |  | 504 | 0 | 0
May 2025 |  | ROAD TRANSPORT AND HIGHWAYS | 120 | CONSTRUCTION OF 2-LANE WITH PAVED SHOULDER OF SHILLONG WESTERN BYPASS STARTING FROM NH-06 NEAR LADUM | NHIDCL | N24002156 | 3-2023 | 9/2026 | N.A. | 9/2026 | 620.3 |  | 620.3 | 221.86 | 28
May 2025 |  | ROAD TRANSPORT AND HIGHWAYS | 121 | SHILLONG WESTERN BYPASS PACKAGE-2 | NHIDCL | N24002157 | 3-2023 | 9/2026 | N.A. | 9/2026 | 686 |  | 686 | 292.69 | 25.52
May 2025 |  | ROAD TRANSPORT AND HIGHWAYS | 122 | CONSTRUCTION OF 2-LANE WITH PAVED SHOULDERS OF SHILLONG WESTERN BYPASS STARTING FROM NH-06 NEAR LADU | NHIDCL | N24002158 | 3-2023 | 9/2026 | N.A. | 9/2026 | 562.48 |  | 562.48 | 297.79 | 24
May 2025 |  | ROAD TRANSPORT AND HIGHWAYS | 123 | IMPROVEMENT/WIDENING TO 2-LANE WITH PAVED SHOULDER FROM (DESIGN KM 45.760 TO KM 63.530) BETWEEN SHIL | NHIDCL | N24001334 | 11-2020 | 12/2023 | N.A. | 4/2026 | 445.51 |  | 445.51 | 207.2 | 26
May 2025 |  | ROAD TRANSPORT AND HIGHWAYS | 124 | IMPROVEMENT/WIDENING TO 2-LANE WITH PAVED SHOULDER / 4-LANING FROM (DESIGN KM 63.530 TO KM 71.520) B | NHIDCL | N24001335 | 11-2020 | 12/2023 | N.A. | 11/2026 | 284.21 |  | 284.21 | 101.98 | 24
May 2025 |  |  | 125 | REHABITITATION AND UP GRADATION OF NONGSTOIN-RAMBRAI-KYRSHAI ROAD UP TO MEGHALAYA-ASSAM BORDER FROM | NHIDCL | N24001474 | 9-2021 | 5/2024 | Dec-2024 | 5/2026 | 359.86 |  | 359.86 | 233.26 | 87
May 2025 |  |  | 126 | REHABILITATION AND UPGRADATION OF NONGSTOIN TO WAHKAJI SECTION OF PROJECT ROAD KM 0.000 TO KM 43.06 | MoRTH | N24001441 | 8-2020 | 2/2022 | N.A. | 3/2025 | 302.88 |  | 302.88 | 228.68 | 96
May 2025 |  |  | 127 | RANIKOR- MAHESHKHOLA- BAGHMARA PKG-2 | NHIDCL | N24001541 | 11-2021 | 6/2024 | Dec-2024 | 5/2025 | 283.5 |  | 283.5 | 257.26 | 100
May 2025 |  |  | 128 | IMPROVEMENT/WIDENING TO 2-L WITH PAVED SHOULDER FROM (DESIGN KM 0.00 TO KM 10.670) / 4-LANING FROM ( | NHIDCL | N24001313 | 11-2020 | 12/2023 | Oct-2025 | 10/2025 | 351.12 |  | 351.12 | 295.88 | 62.5
May 2025 |  |  | 129 | IMPROVEMENT/WIDENING TO 2-LANE WITH PAVED SHOULDER FROM (DESIGN KM 10.670 TO KM 37.550) BETWEEN SHIL | NHIDCL | N24001314 | 11-2020 | 12/2023 | N.A. | 8/2026 | 525.68 |  | 525.68 | 434.11 | 31
May 2025 |  |  | 130 | WIDENING TO 2-LANE WITH GEOMETRIC IMPROVEMENTS OF TURA DALU ROAD UNDER JICA FUNDING FROM KM 85.000 T | NHIDCL | N24000771 | 4-2017 | 9/2021 | Mar-2025 | 6/2025 | 553.51 | 610.09 | 553.51 | 432.78 | 92.01
May 2025 |  | RAILWAYS | 131 | BHAIRABI SAIRONG, NL, NEFR | NFR | N22000100 | 4-2008 | 3/2025 | N.A. | 6/2025 | 6527.45 | 5021.45 | 8213.72 | 8001.88 | 97
May 2025 |  | ROAD TRANSPORT AND HIGHWAYS | 132 | WIDENING AND UP-GRADATION TO 2-LANE WITH PAVED SHOULDER CONFIGURATION AND GEOMETRIC IMPROVEMENTS FRO | NHIDCL | N24000857 | 4-2017 | 4/2023 | N.A. | 4/2025 | 519.09 |  | 785.65 | 670.91 | 97.51
May 2025 |  |  | 133 | WIDENING AND UP-GRADATION TO 2-LANE WITH PAVED SHOULDER CONFIGURATION AND GEOMETRIC IMPROVEMENTS FRO | NHIDCL | N24000858 | 4-2017 | 7/2023 | N.A. | 5/2024 | 640.07 |  | 1286.35 | 1195.84 | 98.9
May 2025 |  |  | 134 | WIDENING AND UP-GRADATION TO 2-LANE WITH PAVED SHOULDER CONFIGURATION AND GEOMETRIC IMPROVEMENTS FRO | NHIDCL | N24000861 | 4-2017 | 4/2023 | N.A. | 4/2025 | 473.18 |  | 688.25 | 541.04 | 94.7
May 2025 |  |  | 135 | WIDENING AND UP-GRADATION TO 2-LANE WITH PAVED SHOULDER CONFIGURATION AND GEOMETRIC IMPROVEMENTS FRO | NHIDCL | N24000862 | 4-2017 | 4/2023 | N.A. | 5/2025 | 537.82 |  | 789.05 | 778.16 | 99.82
May 2025 |  |  | 136 | WIDENING AND UP-GRADATION TO 2-LANE WITH PAVED SHOULDER CONFIGURATION AND GEOMETRIC IMPROVEMENTS FRO | NHIDCL | N24000863 | 4-2017 | 6/2023 | N.A. | 5/2025 | 518.53 |  | 906.76 | 849.68 | 97.9
May 2025 |  |  | 137 | WIDENING AND UP-GRADATION TO 2-LANE WITH PAVED SHOULDER CONFIGURATION AND GEOMETRIC IMPROVEMENTS FRO | NHIDCL | N24000864 | 4-2017 | 4/2024 | N.A. | 5/2025 | 404.29 |  | 750.32 | 666.58 | 100
May 2025 |  |  | 138 | WIDENING AND UP-GRADATION TO 2-LANE WITH PAVED SHOULDER CONFIGURATION AND GEOMETRIC IMPROVEMENTS FRO | NHIDCL | N24000865 | 4-2017 | 9/2023 | N.A. | 5/2025 | 428.11 |  | 746.39 | 613.69 | 98.7
May 2025 |  |  | 139 | CONSTRUCTION OF TWO LANE WITH PAVED SHOULDER OF SELLING-DULTE SECTION OF NH-06 (PKG-I) | NHIDCL | N24001278 | 3-2020 | 7/2022 | N.A. | 6/2024 | 206.88 |  | 219.33 | 265.34 | 100
May 2025 |  |  | 140 | CONSTRUCTION OF TWO LANE WITH PAVED SHOULDER OF SELLING-DULTE SECTION OF NH-06 (PKG-III) | NHIDCL | N24001281 | 3-2020 | 7/2022 | N.A. | 10/2024 | 292.24 |  | 331.17 | 294.6 | 93.2
May 2025 |  |  | 141 | KEIFANG - TUVAI PKG-3 | NHIDCL | N24002027 | 12-2021 | 2/2025 | N.A. | 12/2025 | 500.88 |  | 500.88 | 263.48 | 68.8
May 2025 |  |  | 142 | UP-GRADATION TO 2-LANE WITH PAVED SHOULDERS OF NGOPA - PAWLRANG SECTION OF NH 102B OF AIZAWL - IMPHA | NHIDCL | N24001975 | 9-2021 | 2/2025 | N.A. | 12/2025 | 523.78 |  | 523.78 | 366.81 | 80.51
May 2025 |  |  | 143 | DULTE- KWALKULH - CHAMPAI PKG.2 | NHIDCL | N24001356 | 3-2021 | 12/2022 | Apr-2024 | 4/2024 | 233.25 |  | 233.25 | 172.09 | 100
May 2025 |  |  | 144 | TLABUNG - LUNGLEI PKG-A | NHIDCL | N24001358 | 3-2021 | 12/2022 | N.A. | 3/2026 | 698.44 |  | 698.45 | 496.84 | 59.4
May 2025 |  |  | 145 | TLABUNG - LUNGLEI PKG-B | NHIDCL | N24001359 | 3-2021 | 1/2023 | N.A. | 3/2026 | 740.58 |  | 740.58 | 364.34 | 57.4
May 2025 |  |  | 146 | KEIFANG - TUVAI PKG-1 | NHIDCL | N24001440 | 9-2021 | 5/2023 | N.A. | 5/2024 | 492.94 |  | 492.94 | 365.86 | 90.5
May 2025 |  |  | 147 | ZORINPUI- HMAWNGBU-LONGMASU (NH- 502A) | NHIDCL | N24002204 | 2-2023 | 12/2026 | N.A. | 12/2026 | 781.85 |  | 781.85 | 33.56 | 3
May 2025 |  | PETROLEUM | 148 | AUGMENTATION OF DIMAPUR DEPOT, DIMAPUR | IOCL | N16000529 | 8-2023 | 11/2027 | N.A. | 11/2027 | 227.62 |  | 227.62 | 6.12 | 18
May 2025 |  | RAILWAYS | 149 | NEW LINE FROM DIMAPUR TO ZUBZA(KOHIMA) NATIONAL PROJECT | NEFR | NFR | 4-2006 | 3/2026 | N.A. | 12/2029 | 6663.2 | 6663.2 | 6663.2 | 4789.15 | 73
May 2025 |  | ROAD TRANSPORT AND HIGHWAYS | 150 | MERANGKONG-TAMLU-MON (MTM) PKG-5 | NHIDCL | N24001438 | 7-2021 | 12/2023 | N.A. | 9/2025 | 161.73 |  | 161.73 | 62.08 | 67.82
May 2025 |  |  | 151 | PEREN-DIMAPUR SECTION PKG-2 | NHIDCL | N24001406 | 7-2021 | 3/2023 | Sep-2025 | 9/2025 | 258.52 |  | 258.52 | 89.46 | 79.7
May 2025 |  |  | 152 | WIDENING TO 2 LANE WITH HARD SHOULDER OF AKEGWO-AVANGKHU SECTION OF NH-202K FOR PACKAGE-I (DESIGN CH | NHIDCL | N24001976 | 12-2022 | 2/2026 | N.A. | 2/2026 | 430.24 |  | 430.24 | 100.51 | 54.28
May 2025 |  |  | 153 | WIDENING TO 2 LANE WITH HARD SHOULDER OF AKEGWO-AVANGKHU SECTION OF NH-202K FOR PACKAGE-II (DESIGN C | NHIDCL | N24001977 | 12-2022 | 2/2026 | N.A. | 2/2026 | 442.54 |  | 442.54 | 50.6 | 26.58
May 2025 |  |  | 154 | WIDENING TO 2 LANE WITH HARD SHOULDER OF AKEGWO-AVANGKHU SECTION OF NH-202K FOR PACKAGE-III (DESIGN | NHIDCL | N24001978 | 12-2022 | 2/2026 | N.A. | 2/2026 | 497.18 |  | 497.18 | 163.84 | 62.02
May 2025 |  |  | 155 | WIDENING OF EXISTING SINGLE LANE / INTERMEDIATE LANE ROAD TO 2 LANE FROM KM 101 TO KM 125 OF NH 61 I | MoRTH | N24001465 | 6-2020 | 9/2024 | Jun-2026 | 6/2026 | 252.19 |  | 252.19 | 14.25 | 17.9
May 2025 |  |  | 156 | WIDENING TO EXISTING SINGLE LANE /INTERMEDIATE LANE TO 2 LANE FROM KM185.00 TO KM 220.00 OF NH-61 (N | MoRTH | N24001466 | 3-2021 | 7/2024 | Dec-2025 | 12/2025 | 297.24 |  | 297.24 | 137.76 | 79.47
May 2025 |  |  | 157 | WIDENING TO EXISTING SINGRE/INTERMEDIATE RANE TO 2 LANE FROM KM 135 TO KM 147 AND FROM KM 156.00 TO | MoRTH | N24001467 | 3-2021 | 2/2024 | Mar-2025 | 3/2025 | 226.44 |  | 226.44 | 140.24 | 100
May 2025 |  |  | 158 | WIDENING OF EXISTING SINGLE LANE ROAD TO INTERMEDIATE LANE ROAD FROM MOKOKCHUNG TO CHARE VIA DIKHU I | MoRTH | N24001855 | 2-2021 | 6/2025 | Sep-2025 | 9/2025 | 192.93 |  | 192.93 | 105.41 | 92.82
May 2025 |  |  | 159 | PEREN-DIMAPUR PKG-3 | NHIDCL | N24001912 | 2-2021 | 6/2025 | N.A. | 12/2025 | 177.77 | 199.02 | 199.02 | 46.94 | 61.25
May 2025 |  |  | 160 | FOUR LANING OF DIMAPUR KOHIMA ROAD FROM DESIGN KM 123.840 TO KM 138.775 (EXISTING KM 124.100 TO KM 1 | NHIDCL | N24000686 | 3-2016 | 9/2019 | Nov-2022 | 5/2025 | 373.07 | 534.41 | 534.41 | 382.5 | 99.81
May 2025 |  |  | 161 | FOUR LANING OF EXISTING DIMAPUR KOHIMA ROAD FROM DESIGN KM 152.490 TO KM 166.700 (EXISTING KM 156.00 | NHIDCL | N24000688 | 3-2016 | 8/2022 | Sep-2025 | 9/2025 | 429.52 | 794.74 | 794.74 | 321.4 | 91.49
May 2025 |  |  | 162 | (I) CONSTRUCTION OF FOUR/SIX LANING FROM KM 132.375 TO KM 158.058 (TOTAL NEW ALIGNMENT LENGTH OF 20. | NHIDCL | N24000752 | 2-2017 | 9/2020 | Feb-2023 | 4/2025 | 387 | 688.12 | 688.12 | 392.01 | 100
May 2025 |  |  | 163 | (II) CONSTRUCTION OF DIMAPUR BYPASS (ASSAM PORTION) OF 4/6 LANE PAVEMENT ON EPC BASIS FROM EXISTING | NHIDCL | N24000753 | 3-2018 | 11/2022 | Aug-2024 | 4/2025 | 500.09 | 698.81 | 698.81 | 393.53 | 100
May 2025 |  |  | 164 | CONSTRUCTION OF TWO LANE WITH HARD SHOULDERS OF MERANGKONG-TAMLU- MON ROAD FROM EXISTING KM 20.456 TO | NHIDCL | N24000763 | 3-2018 | 12/2021 | Aug-2022 | 8/2025 | 215.79 |  | 215.79 | 130.2 | 79.58
May 2025 |  |  | 165 | CONSTRUCTION OF TWO LANE WITH HARD SHOULDERS OF MERANGKONG-TAMLU- MON ROAD FROM EXISTING KM 60.345 TO | NHIDCL | N24000765 | 3-2018 | 9/2018 | Jun-2023 | 9/2025 | 323.98 |  | 323.98 | 119.94 | 59.68
May 2025 |  |  | 166 | 2 LANING OF KOHIMA - JESSAMI SECTION | PACKAGE II | NHIDCL | 3-2020 | 6/2022 | N.A. | 1/2026 | 355.79 |  | 355.79 | 119.2 | 65.06
May 2025 |  |  | 167 | 2-LANING OF CHANGTONGYA TO LONGLENG ROAD OF NH-702 (PKG-I) | NHIDCL | N24001286 | 3-2020 | 6/2022 | Oct-2022 | 6/2023 | 278.95 |  | 278.95 | 166.29 | 100
May 2025 |  |  | 168 | 2 LANING OF KOHIMA - JESSAMI SECTION | PACKAGE V | NHIDCL | 4-2020 | 12/2021 | Nov-2025 | 11/2025 | 330.8 |  | 330.8 | 171.89 | 92.44
May 2025 |  |  | 169 | CONSTRUCTION OF 2-LANE WITH PAVED SHOULDER OF KOHIMA-BYPASS ROAD FROM DESIGN KM 0.00 TO KM 10.500 [D | NHIDCL | N24001288 | 8-2020 | 4/2022 | Nov-2026 | 11/2026 | 232.29 | 350.88 | 232.29 | 70.9 | 14.7
May 2025 |  |  | 170 | CONSTRUCTION OF 2-LANE WITH PAVED SHOULDER OF KOHIMA-BYPASS ROAD FROM DESIGN KM10.500 TO 21.00KM [D | NHIDCL | N24001255 | 9-2020 | 10/2022 | Sep-2024 | 6/2026 | 277.44 |  | 277.44 | 168.88 | 67.81
May 2025 |  |  | 171 | CONSTRUCTION OF 2-LANE WITH PAVED SHOULDER OF KOHIMA-BYPASS ROAD FROM DESIGN KM21.0 TO KM32.0 [DESIG | NHIDCL | N24001257 | 8-2020 | 10/2022 | Jun-2025 | 12/2025 | 159.85 | 342.29 | 159.85 | 103.95 | 29.9
May 2025 |  |  | 172 | CONSTRUCTION OF 2-LANE WITH PAVED SHOULDER OF KOHIMA-BYPASS ROAD FROM DSIGN KM32.0 TO KM43.454 [DES | NHIDCL | N24001258 | 8-2020 | 4/2022 | Apr-2023 | 8/2025 | 202.36 |  | 202.36 | 75.39 | 31.02
May 2025 |  | CIVIL AVIATION | 173 | PAKYONG AIRPORT- WIDENING OF BASIC STRIP AT WESTERN SIDE OF RUNWAY CHAINAGE 80M TO 920M I/C SLOPE ST | AAI | N04000110 | 11-2023 | 6/2026 | N.A. | 6/2026 | 323.26 |  | 323.26 | 24.99 | 12
May 2025 |  | DEPARTMENT OF HIGHER EDUCATION | 174 | CONSTRUCTION OF SIKKIM UNIVERSITY CAMPUS PHASE-I, PACKAGE -II AT YANGANG SOUTH SIKKIM | Sikkim Universi | N44000002 | 8-2020 | 1/2025 | N.A. | 1/2025 | 314.06 |  | 303.55 | 157.24 | 80
May 2025 |  | POWER | 175 | TEESTA VI HE PROJECT | NHPC | N18000325 | 3-2019 | 3/2024 | N.A. | 12/2027 | 5748.04 |  | 5748.04 | 4341.5 | 67.67
May 2025 |  | POWER | 176 | RANGIT IV HE PROJECT | NHPC | N18000326 | 3-2021 | 5/2024 | N.A. | 12/2025 | 938.29 |  | 1828.11 | 1486.3 | 88.51
May 2025 |  | RAILWAYS | 177 | SEVOK RANGPO, NEFR | NFR | N22000102 | 4-2008 | 5/2015 | Dec-2027 | 12/2027 | 7876.92 | 11963.43 | 11963.43 | 8569.25 | 80
May 2025 |  | ROAD TRANSPORT AND HIGHWAYS | 178 | CONSTRUCTION AND UPGRADATION OFEXISTINGROAD TO 2-LANE WITH PAVED SHOULDER INCLUDING GEOMETRIC IMPROV | NHIDCL | N24001261 | 8-2020 | 4/2023 | N.A. | 4/2025 | 311 |  | 273.78 | 257.86 | 95.12
May 2025 |  | ROAD TRANSPORT AND HIGHWAYS | 179 | CONSTRUCTION AND UPGRADATION OFEXISTINGROAD TO 2-LANE WITH PAVED SHOULDER INCLUDING GEOMETRIC IMPROV | NHIDCL | N24001262 | 7-2020 | 4/2023 | Aug-2024 | 10/2025 | 345.38 | 395.59 | 395.59 | 362.61 | 91.24
May 2025 |  | ROAD TRANSPORT AND HIGHWAYS | 180 | CONSTUCTION/UPGRADATION OF EXISTING HIGHWAY TO 2 LANE WITH PAVED SHOULDER FROM KM 0.00 TO KM 13.00 N | NHIDCL | N24001251 | 3-2019 | 4/2022 | N.A. | 6/2025 | 402.94 |  | 402.94 | 247.12 | 76.54
May 2025 |  | ROAD TRANSPORT AND HIGHWAYS | 181 | CONSTUCTION/UPGRADATION OF EXISTING HIGHWAY TO 2 LANE WITH PAVED SHOULDER FROM KM 13.00 TO KM 25.600 | NHIDCL | N24001252 | 8-2020 | 4/2023 | Nov-2024 | 7/2025 | 295.97 |  | 295.97 | 249.8 | 95.66
May 2025 |  | ROAD TRANSPORT AND HIGHWAYS | 182 | CONSTUCTION/UPGRADATION OF EXISTING HIGHWAY TO 2 LANE WITH PAVED SHOULDER FROM KM 26.10 TO KM 40.00 | NHIDCL | N24001254 | 3-2020 | 6/2022 | N.A. | 1/2024 | 242.97 |  | 244.45 | 246.91 | 100
May 2025 |  | ROAD TRANSPORT AND HIGHWAYS | 183 | CONSTRUCTION OF 2-LANE WITH PAVED SHOULDER INCLUDING GEOMETRIC IMPROVEMENT FROM KM 0.000 TO KM 16.00 | NHIDCL | N24000767 | 3-2017 | 4/2022 | May-2022 | 12/2023 | 375.8 |  | 375.8 | 288.56 | 96.55
May 2025 |  |  | 184 | CONSTRUCTION OF 2-LANE WITH PAVED SHOULDER INCLUDING GEOMETRIC IMPROVEMENT FROM KM 16.000 TO KM 32.5 | NHIDCL | N24000768 | 11-2017 | 10/2020 | Aug-2023 | 4/2024 | 290.05 |  | 290.05 | 218.36 | 100
May 2025 |  |  | 185 | CONSTRUCTION OF 2-LANE WITH PAVED SHOULDER GANGTOK BYPASS ROAD FROM RANIPOOL TO BURTUK (L=23.316KM) | MoRTH | N24001442 | 10-2021 | 5/2024 | Jan-2026 | 1/2026 | 385.15 |  | 385.15 | 170.32 | 81.3
May 2025 |  |  | 186 | RISHI BORDER- ROLEP- MENLA PKG- 3B | NHIDCL | N24001362 | 12-2020 | 2/2024 | Apr-2025 | 12/2025 | 410.6 | 379.3 | 379.3 | 234.98 | 74.58
May 2025 |  |  | 187 | CONSTRUCTION AND UPGRADATION OF EXISTING ROAD TO 2-LANE WITH PAVED SHOULDER FROM KM27.200 (END OF RO | NHIDCL | N24001336 | 8-2020 | 4/2023 | Oct-2024 | 12/2025 | 230.45 | 244.91 | 244.91 | 206.95 | 82.32
May 2025 |  |  | 188 | CONSTRUCTION AND UPGRADATION OF EXISTING ROAD TO 2-LANE WITH PAVED SHOULDER FROM NEW ROLEP BRIDGE AT | NHIDCL | N24001337 | 10-2020 | 11/2023 | Jul-2025 | 3/2026 | 493.42 | 478.79 | 478.79 | 305.2 | 58.28
May 2025 |  |  | 189 | CONSTRUCTION OF 2-LANE WITH PAVED SHOULDER OF NEW GREEN FIELD ALIGNMENT FROM CHOCHENPHERI AT KM 52.0 | NHIDCL | N24001338 | 10-2020 | 12/2023 | Jun-2025 | 12/2026 | 816.79 | 786.6 | 786.6 | 332.24 | 51.45
May 2025 |  |  | 190 | REHABILITATION AND UPGRADATION OF EXISTING ROAD TO 2-LANE WITH PAVED SHOULDER INCLUDING GEOMETRIC IM | NHIDCL | N24001327 | 8-2020 | 5/2022 | Oct-2023 | 12/2025 | 292.8 |  | 292.8 | 202.92 | 60.9
May 2025 |  |  | 191 | CONSTRUCTION OF 2-LANE ROAD WITH PAVED SHOULDER (GREENFIELD ALIGNMENT) OF EXISTING STRETCH BETWEEN L | NHIDCL | N24001322 | 9-2020 | 5/2022 | Oct-2023 | 12/2025 | 183.31 | 439.56 | 439.56 | 355.31 | 51.19
May 2025 |  |  | 192 | CONSTRUCTION OF 2-LANE SPECIFICATION ROAD WITH PAVED SHOULDER AS REALIGNMENT | GREENFIELD ALIGNMENT | NHIDCL | 9-2020 | 5/2023 | Aug-2024 | 12/2025 | 262.84 | 414.2 | 414.2 | 221.86 | 47.57
May 2025 |  | PETROLEUM | 193 | GRASS ROOT RAIL FED DEPOT AT SEKERKOTE, AGARTALA AS RESITEMENT OF EXISTING DHARMANAGAR DEPOT | IOCL | N16000495 | 6-2022 | 8/2025 | Sep-2025 | 9/2025 | 656 |  | 656 | 415.86 | 82.2
May 2025 |  | ROAD TRANSPORT AND HIGHWAYS | 194 | KHOWAI ?TELIAMURA-AMARPUR-HARINA- SABROOM SECTION PKG-4 | NHIDCL | N24002228 | 1-2024 | 12/2026 | N.A. | 12/2026 | 726.9 |  | 726.9 | 0 | 3.1
May 2025 |  | ROAD TRANSPORT AND HIGHWAYS | 195 | CHAMPAK NAGAR TO KHAYERPUR SECTION (DESIGN KM 242+500 TO KM 261+610) | NHIDCL | N24002205 | 12-2023 | 9/2026 | N.A. | 9/2026 | 920.66 |  | 920.66 | 73.41 | 22
May 2025 |  | ROAD TRANSPORT AND HIGHWAYS | 196 | 4 LANE WITH PAVED SHOULDER AGARTALA BYPASS (WESTERN SIDE) CONNECTING NH- 8 | NHIDCL | N24002132 | 3-2023 | 3/2027 | N.A. | 3/2027 | 2026.05 |  | 2026.05 | 26.34 | 8.38
May 2025 |  | ROAD TRANSPORT AND HIGHWAYS | 197 | REHABILITATION AND UP-GRADATION OF ROAD FROM DESIGN KM 25.250 TO KM 36.460 (TOTAL LENGH: 11.210 KM) | NHIDCL | N24002159 | 2-2020 | 3/2026 | N.A. | 3/2026 | 174.43 |  | 174.43 | 9.34 | 16.61
May 2025 |  | ROAD TRANSPORT AND HIGHWAYS | 198 | IMPROVEMENT AND WIDENING TO 2-LANE WITH PAVED SHOULDER OF ROAD FROM KM 101.300 TO KM 127.319 (TOTAL | NHIDCL | N24002160 | 1-2024 | 7/2026 | N.A. | 7/2026 | 431.78 |  | 431.78 | 52.82 | 34.61
May 2025 |  | ROAD TRANSPORT AND HIGHWAYS | 199 | KHOWAI ?TELIAMURA-AMARPUR-HARINA- SABROOM PACKAGE-2 | NHIDCL | N24002161 | 1-2024 | 9/2026 | N.A. | 9/2026 | 657.21 |  | 657.21 | 26.37 | 31.5
May 2025 |  | ROAD TRANSPORT AND HIGHWAYS | 200 | KHOWAI ?TELIAMURA-AMARPUR-HARINA- SABROOM PACKAGE-3 | NHIDCL | N24002162 | 1-2024 | 9/2026 | N.A. | 9/2026 | 670.9 |  | 670.9 | 0 | 2
May 2025 |  |  | 201 | MANU-SIMLUNG ( PKG 4) | NHIDCL | N24001363 | 3-2021 | 12/2022 | N.A. | 12/2025 | 354.79 |  | 354.79 | 34.08 | 0
May 2025 |  |  | 202 | IMPROVEMENT AND WIDENING TO 2-LANE WITH EARTHEN PAVED SHOULDER FROM UDAIPUR TO SRIMANTAPUR | NHIDCL | N24001914 | 5-2023 | 11/2024 | N.A. | 12/2025 | 195.95 |  | 195.95 | 38.1 | 45.3
May 2025 |  |  | 203 | 2 LANING FROM MANU-SIMLUNG PKG-2 | NHIDCL | N24001542 | 2-2022 | 1/2025 | May-2025 | 5/2025 | 456.88 |  | 456.88 | 122.23 | 49.88
May 2025 |  |  | 204 | REHABILITATION AND UPGRADATION OF ROAD FROM KM 0.00 TO KM 18.600 OF KUMARGHAT-KAILASHAHAR SECTION | NHIDCL | N24001263 | 6-2020 | 1/2022 | Feb-2024 | 12/2024 | 277.5 | 302.02 | 302.02 | 260.38 | 99.94
May 2025 |  |  | 205 | 2-LANING FROM JOLAIBARI - BELONIA | NHIDCL | N24001317 | 6-2020 | 1/2022 | N.A. | 4/2025 | 201.99 |  | 287.47 | 148.22 | 100
May 2025 |  |  | 206 | KAILASHAHAR TO KHOWAI PKG-4 | NHIDCL | N24001309 | 11-2020 | 6/2022 | Oct-2023 | 11/2024 | 159.13 | 171.5 | 171.5 | 84.33 | 100

## All Ongoing Projects
Month | State | Sector | Sl No | Project Name | Agency | Project Code | Date of Approval | Commissioning Original | Commissioning Revised | Commissioning Anticipated | Cost Original (Rs Cr) | Cost Revised (Rs Cr) | Cost Anticipated (Rs Cr) | Cumulative Expenditure (Rs Cr) | Physical Progress (%)
April 2025 | ANDAMAN AND NICOBAR ISLANDS | CIVIL AVIATION | 1 | CONSTRUCTION OF NEW INTEGRATED TERMINAL BUILDING AT VSI AIRPORT, PORTBLAIR | AAI | N04000073 | 10-2013 | 9/2018 | 6/2023 | 6/2023 | 417.23 | 707.73 | 707.73 | 698.8 | 100
April 2025 | ANDAMAN AND NICOBAR ISLANDS | RAILWAYS | 2 | LUDHIANA KILA RAIPUR (19 KMS) WITH FREIGHT LINE AT GILL STATION ON LDH-JHL SECTION | NR | N22000584 | 3-2019 | 3/2025 | 12/2025 | 12/2025 | 235.72 |  | 235.72 | 54.28 | 55
April 2025 | ANDAMAN AND NICOBAR ISLANDS | RAILWAYS | 3 | 2 LANE WITH HARD SHOLDER , REHABILITATION AND UP GRADATION OF SECTION FROM KM 242.0 TO KM 298.0 OF N | NHIDCL | N24000745 | 3-2017 | 12/2019 | 3/2023 | 5/2025 | 409.85 |  | 409.85 | 214.23 | 95.1
April 2025 | ANDAMAN AND NICOBAR ISLANDS | RAILWAYS | 4 | REHABILITATION AND UP GRADATION OF SECTION FROM KM 206.00 TO KM 242.00 (NIMBUTALA TO AUSTIN CREEK) O | NHIDCL | N24000749 | 3-2018 | 9/2020 | 11/2022 | 5/2025 | 234.27 |  | 234.27 | 126.5 | 82.93
April 2025 | ANDAMAN AND NICOBAR ISLANDS | RAILWAYS | 5 | Rehabilitation and up gradation to 2 lane with paved shoulder configuration from existing km. 122.00 | MoRTH | N24000820 | 11-2017 | 11/2019 | N.A. | 11/2019 | 237.8 |  | 238 | 222.13 | 98.23
April 2025 | ANDAMAN AND NICOBAR ISLANDS | RAILWAYS | 6 | RECONSTRUCTION WITH GEOMETRIC IMPROVEMENT OF EXISTING 2 LANE/INTERMEDIATE LANE TO 2LANE WITH PAVED S | MoRTH | N24000821 | 11-2017 | 11/2019 | N.A. | 11/2019 | 257.34 |  | 238 | 214.9 | 100
April 2025 | ANDAMAN AND NICOBAR ISLANDS | RAILWAYS | 7 | AJANTHA TO BULDHANA | MoRTH | N24001008 | 2-2017 | 7/2019 | N.A. | 12/2023 | 401 | 401 | 401 | 260.08 | 97
April 2025 | ANDAMAN AND NICOBAR ISLANDS | RAILWAYS | 8 | MAJOR BRIDGE OVER MIDDLE STRAIT CREEK | NHIDCL | N24002207 | 12-2024 | 2/2026 | N.A. | 2/2026 | 371.8 | 207.99 | 207.99 | 0 | 2.11
April 2025 |  |  | 9 | PACKAGE-3A | NHIDCL | N24002208 | 2-2018 | 9/2025 | 3/2024 | 9/2025 | 207.54 | 154.01 | 154.01 | 16.21 | 35.5
April 2025 |  |  | 10 | PACKAGE-3B | NHIDCL | N24002209 | 2-2018 | 11/2025 | N.A. | 11/2025 | 183.47 |  | 183.47 | 1.45 | 25.27
April 2025 |  | CIVIL AVIATION | 11 | C/O OF NITB AND ASSOCIATED WORK AT VIJAYAWADA AIRPORT | AAI | N04000091 | 4-2020 | 3/2023 | 8/2025 | 8/2025 | 611.8 |  | 611.8 | 433.85 | 73
April 2025 |  | CIVIL AVIATION | 12 | RAJAHMUNDRY AIRPORT: CONSTRUCTION OF NEW DOMESTIC TERMINAL BUILDING AND MISCELLANEOUS WORKS INCLUD | AAI | N04000103 | 12-2022 | 8/2025 | N.A. | 8/2025 | 347.15 | 347.15 | 347.15 | 72.12 | 43
April 2025 |  | CIVIL AVIATION | 13 | KADAPPA AIRPORT- CONSTRUCTION OF NEW DOMESTIC TERMINAL BUILDING AND MISCELLANEOUS WORKS INCLUDING MA | AAI | N04000106 | 3-2023 | 1/2026 | N.A. | 1/2026 | 265.91 |  | 265.91 | 39.49 | 27
April 2025 |  | DEPARTMENT OF HIGHER EDUCATION | 14 | CONSTRUCTION OF PERMANENT CAMPUS FOR INDIAN INSTITUTE OF TECHNOLOGY TIRUPATI AT MERLAPAKA VILLAGE YE | CPWD EDUCATION | N42000005 | 2-2019 | 6/2020 | N.A. | 6/2020 | 655.34 |  | 655.34 | 366.21 | 95
April 2025 |  | DEPARTMENT OF HIGHER EDUCATION | 15 | CONSTRUCTION OF PERMANENT CAMPUS FOR IISER AT JANGALAPALLI VILLAGE, YERPEDU MANDAL, CHITTOOR DISTRIC | CPWD EDUCATION | N42000007 | 9-2019 | 9/2022 | N.A. | 6/2024 | 588.72 | 656.39 | 656.39 | 630.55 | 100
April 2025 |  | PETROLEUM | 16 | KG-DWN-98-2 CLUSTER II DEVELOPMENT PROJECT | ONGC | N16000247 | 3-2016 | 6/2020 | 3/2025 | 6/2025 | 34012 |  | 34012 | 33149.29 | 96.4
April 2025 |  | PETROLEUM | 17 | HP CRUDE TO OLEFINS AND AROMATICS TECHNOLOGY DEMO UNIT AT VISAKH REFINERY | HPCL | N16000432 | 9-2021 | 6/2024 | 3/2026 | 3/2026 | 160 | 220 | 220 | 50.04 | 56
April 2025 |  | PETROLEUM | 18 | CGD PROJECT AT KURNOOL, GUNTUR AND PRAKASAM DISTRICTS | IOCL | N16000485 | 3-2022 | 3/2030 | N.A. | 3/2030 | 1420 |  | 1420 | 144.41 | 6.1
April 2025 |  | PETROLEUM | 19 | MULTI-PRODUCT PIPELINE FROM KRISHNAPATNAM COASTAL INSTALLATION TO THE PROPOSED INSTALLATION AT HYDER | BPCL | N16000499 | 9-2019 | 3/2025 | N.A. | 10/2025 | 1932 |  | 1932 | 1491.64 | 85.3
April 2025 |  | PETROLEUM | 20 | HP TRIJET UNIT IN VR | HPCL | N16000535 | 7-2024 | 7/2027 | N.A. | 7/2027 | 193 |  | 193 | 0.38 | 19
April 2025 |  | PETROLEUM | 21 | CONSTRUCTION OF AVIATION FUEL FARM FACILITIES AT BHOGAPURAM AIRPORT | HPCL | N16000538 | 8-2024 | 3/2026 | N.A. | 3/2026 | 240 |  | 240 | 16.74 | 25.5
April 2025 |  | PETROLEUM | 22 | VISAKHA RAIPUR PIPELINE PROJECT | HPCL | N16000539 | 9-2024 | 9/2027 | N.A. | 9/2027 | 2212 |  | 2212 | 2.41 | 3.65
April 2025 |  | PETROLEUM | 23 | TRANSMISSION SCHEME FOR SOLAR ENERGY ZONE IN ANANTHPURAM (2500MW) AND KURNOOL (1000MW) | PGCIL | N18000380 | 9-2023 | 3/2025 | N.A. | 9/2025 | 1249 |  | 1249 | 418.81 | 53
April 2025 |  |  | 24 | AUGMENTATION OF 1500MVA 3RD 765/400KV TRANSFORMATION CAPACITY AT KURNOOL NEW SUBSTATION | PGCIL | N18000395 | 5-2023 | 9/2025 | N.A. | 9/2025 | 164 |  | 164 | 66 | 15
April 2025 |  |  | 25 | TRANSMISSION SYSTEM FOR INTEGRATION OF KURNOOL-IV REZ ? PHASE-I (FOR 4.5 GW) | PGCIL | N18000413 | 3-2025 | 3/2027 | N.A. | 3/2027 | 5000 |  | 5000 | 0 | -
April 2025 |  |  | 26 | TRANSMISSION SYSTEM STRENGTHENING AT KURNOOL- III PS FOR INTEGRATION OF ADDITIONAL RE GENERATION PRO | PGCIL | N18000416 | 3-2025 | 3/2027 | N.A. | 3/2027 | 2886 |  | 2886 | 0 | -
April 2025 |  |  | 27 | KOTLPALLI-NARASAPUR (NL) | SCR | SCR | 12-2001 | 3/2028 | N.A. | 3/2027 | 2500.98 |  | 2500.98 | 1141.44 | 18
April 2025 |  |  | 28 | NADIKUDE-SRI KALAHASTI | SCR | N22000286 | 4-2011 | 5/2027 | N.A. | 5/2027 | 2312 |  | 3122.35 | 1935.77 | -
April 2025 |  |  | 29 | GUNTUR-GUNTAKAL | SCR | N22000368 | 4-2016 | 12/2025 | N.A. | 12/2025 | 3733.37 |  | 3887.48 | 3478.23 | -
April 2025 |  |  | 30 | VIJAYAWADA-GUDUR | RVNL | N22000369 | 4-2015 | 11/2024 | N.A. | 12/2024 | 6654 |  | 6238.67 | 5883.89 | -
April 2025 |  |  | 31 | KOTTAVALSA - KORAPUT DOUBLING | ECOR | N22000377 | 4-2015 | 3/2022 | N.A. | 3/2022 | 2499.71 |  | 2499.71 | 1919.28 | 69.5
April 2025 |  |  | 32 | PENUKONDA-DHARMAVARAM, EXCL. DHARMAVARAM (41.5 KM) | SWR | N22000555 | 4-2019 | 3/2026 | N.A. | 12/2025 | 294.67 | 307.66 | 307.66 | 197.73 | 50
April 2025 |  |  | 33 | MALUGUR-PALASAMUDRAM | 17.98 KM) (PB#29/NR/2022-23 | SWR | 9-2022 | 12/2025 | N.A. | 12/2026 | 323.14 | 342.41 | 342.41 | 46.89 | 12
April 2025 |  |  | 34 | DOUBLING BETWEEN GOOTY- PENDAKALLU (29.225) | SCR | N22000585 | 3-2023 | 3/2027 | N.A. | 3/2027 | 351.83 |  | 351.83 | 0 | -
April 2025 |  |  | 35 | VIJAYAWADA KAZIPET BYEPASS LINE | SCR | N22000586 | 4-2016 | 12/2025 | N.A. | 12/2025 | 647.37 |  | 226.72 | 235.48 | -
April 2025 |  |  | 36 | RENIGUNTA WADI GOOTY - BYPASS | SCR | N22000587 | 4-2016 | 12/2025 | N.A. | 12/2025 | 302 |  | 302 | 209.83 | 50
April 2025 |  |  | 37 | REHABILITATION AND UPGRADATION OF NH-219 FROM KM 58-600 TO KM 140-750 IN THE STATE OF ANDHRA PRADES | MoRTH | N24000301 | 3-2015 | 10/2015 | 5/2021 | 5/2021 | 271.45 |  | 271.45 | 238.23 | 100
April 2025 |  |  | 38 | CONSTRUCTION OF SIX LANING OF DEDICATED PORT ROAD TO KRISHNAPATNAM PORT (PACKAGE-I) KM 0+000 TO KM 1 | NHAI | N24000811 | 3-2018 | 12/2020 | 12/2022 | 12/2024 | 314.43 |  | 348.72 | 85.61 | 68.1
April 2025 |  |  | 39 | REHABILITATION AND UPGRADATION OF EXISTING NH- 167 FROM KM 14.900 TO KM 70.00 (DESIGN CH.14.900 TO 69 | MoRTH | N24000931 | 11-2016 | 5/2017 | N.A. | 11/2024 | 290.15 |  | 236.16 | 205.02 | 90
April 2025 |  |  | 40 | REHABILITATION AND UPGRADATION OF NEW NH- 544DD FROM DESIGN CHAINAGE KM 56.00 TO 102.20 OF KALYANDURG | MoRTH | N24000937 | 3-2018 | 8/2018 | N.A. | 11/2024 | 289.67 | 290 | 285.29 | 254.19 | 98.5
April 2025 |  |  | 41 | CONSTRUCTION OF TIMMAPURAM TO GURJANAPALLE SECTION FROM KM 26.150 TO 41.161 OF NH- 214(NH216)(KAKINAD | MoRTH | N24000964 | 8-2016 | 1/2017 | N.A. | 5/2025 | 350.61 |  | 411.18 | 407.92 | 98
April 2025 |  |  | 42 | CONSTRUCTION OF 2L+PS FROM PASARLAPUDI-DHINDI (105/700 TO 127.500 OF NH-214) OF NH-216 | MoRTH | N24000969 | 1-2017 | 9/2017 | N.A. | 6/2025 | 263.45 |  | 263.45 | 208.15 | 85
April 2025 |  |  | 43 | 6-LANING OF VIJAYAWADA BYPASS FROM GOLLAPUDI (DESIGN CH. 30+000) TO CHINNAKAKANI (DESIGN CH. 47+881) | NHAI | N24001301 | 11-2019 | 1/2024 | N.A. | 7/2024 | 1601.1 |  | 1601.1 | 1386.24 | 88.5
April 2025 |  |  | 44 | REHABILITATION AND UPGRADATION TO 2-LANE WITH PAVED SHOULDERS CONFIGURATION OF PADERU- GONDIGUDA SECT | MoRTH | N24001386 | 8-2020 | 3/2021 | N.A. | 6/2025 | 222.61 |  | 222.61 | 120.46 | 95
April 2025 |  |  | 45 | CONSTRUCTION OF 4 LANE ACCESS CONTROLLED NEW GREENFIELD HIGHWAY SECTION OF NH 365BG FROM RECHARLA VI | NHAI | N24001476 | 9-2021 | 9/2022 | 9/2024 | 6/2025 | 517.05 |  | 655.06 | 515.3 | 90.14
April 2025 |  |  | 46 | CONSTRUCTION OF 4 LANE ACCESS CONTROLLED NEW GREENFIELD HIGHWAY SECTION OF NH-365BG (KHAMMAM-DEVARAP | NHAI | N24001477 | 9-2021 | 9/2022 | 9/2024 | 6/2025 | 622 |  | 817.91 | 533.42 | 73.89
April 2025 |  |  | 47 | 6L OF CHILKARARUPET BYPASS FROM KM. 357.400 TO KM. 371.920 OF NH-16 | NHAI | N24001817 | 2-2019 | 3/2023 | 10/2024 | 10/2024 | 757.45 |  | 757.45 | 607.76 | 99.41
April 2025 |  |  | 48 | 6L OF PONDAVAKKAM TO KANNIGAIPAIR FROM KM 96.040 TO KM 116.100 OF NH 716B (PKG- IV) | NHAI | N24001818 | 2-2021 | 1/2025 | N.A. | 1/2025 | 818.73 |  | 1105 | 556.95 | 24.23
April 2025 |  |  | 49 | 6L OF VEERA KAVERI RAJA PURAM TO PONDAVAKKAM FROM KM 61.380 TO KM 96.040 OF NH 716B (PKG-III) | NHAI | N24001819 | 3-2021 | 1/2025 | N.A. | 1/2025 | 1102.63 |  | 1303 | 1082.99 | 91.81
April 2025 |  |  | 50 | 6L OF VARADHARAJULA TO KUMARAJAPET FROM KM 0.000 TO KM 43.800 OF NH-716B (PKG- I) | NHAI | N24001820 | 2-2021 | 12/2024 | N.A. | 12/2024 | 1484.83 |  | 1768 | 1493.57 | 87.5
April 2025 |  |  | 51 | BANGALORE CHENNAI EXPRESSWAY (PHASE-II PKG-III) FROM KM.127.000 TO KM 156.000 (BANGARUPALEM TO GUDIP | NHAI | N24001821 | 11-2020 | 10/2024 | N.A. | 10/2024 | 1137.74 |  | 1289 | 1256.44 | 94.6
April 2025 |  |  | 52 | BANGALORE CHENNAI EXPRESSWAY (PHASE-II PKG-I) FROM KM.71.000 TO KM 96.000 (BETHAMANGALA IN THE STATE | NHAI | N24001822 | 12-2020 | 10/2024 | N.A. | 10/2024 | 1075.27 |  | 1307 | 1092.9 | 81.5
April 2025 |  |  | 53 | 4L OF MADANAPALLE TO PILERU SECTION FROM KM 0.000 TO KM 55.900 OF NH-71(PACKAGE-I) - N/05060/01002/A | NHAI | N24001823 | 1-2022 | 1/2025 | 1/2023 | 1/2025 | 1852.12 |  | 1787 | 774.62 | 86
April 2025 |  |  | 54 | RENIGUNTA - POYYA - NAIDUPETA KM 124.60 TO KM 183.4 OF NH 71 - N/04027/06001/AP | NHAI | N24001824 | 3-2020 | 1/2024 | 12/2024 | 12/2024 | 1863.09 |  | 2238 | 1227.61 | 98.76
April 2025 |  |  | 55 | 6L KANTAKAPALLE ? SABBAVARAM SECTION OF NH- 130CD ROAD FROM KM 445.100 TO KM 464.662 (PKG-4) | NHAI | N24001836 | 2-2021 | 10/2024 | N.A. | 3/2026 | 824.29 |  | 924 | 424.23 | 70.2
April 2025 |  |  | 56 | 6L JAKKUVA ? KORLAM SECTION OF NH-130CD ROAD FROM KM 396.800 TO KM 421.100 (PKG 2) | NHAI | N24001837 | 2-2021 | 3/2024 | 7/2024 | 12/2025 | 663.6 |  | 768 | 380.88 | 98.8
April 2025 |  |  | 57 | 6L ALURU - JAKKUVA SECTION OF NH-130CD ROAD FROM KM 365.033 TO KM 396.800 (PKG. 1) | NHAI | N24001838 | 2-2021 | 3/2024 | N.A. | 9/2025 | 922.5 |  | 1128.68 | 473.8 | 82.92
April 2025 |  |  | 58 | 6L ACCESS CONTROLLED GREENFIELD HIGHWAY FROM KODUR 0.000 KMS TO VANAVOLU 24.300 KMS OF NH 544G PACKA | NHAI | N24001841 | 12-2022 | 9/2025 | N.A. | 2/2026 | 912.94 |  | 912.94 | 238.71 | 54.23
April 2025 |  |  | 59 | 6L ACCESS CONTROLLED GREENFIELD HIGHWAY FROM VANAVOLU 24.300 KM. TO VANKARAKUNTA 45.700 KM. OF NH 5 | NHAI | N24001842 | 12-2022 | 11/2025 | N.A. | 11/2025 | 750.81 |  | 750.81 | 145.15 | 45.65
April 2025 |  |  | 60 | 6L ACCESS CONTROLLED GREENFIELD HIGHWAY FROM VANKARAKUNTA 45.700 KM. TO ODULAPALLE 72.000 KM. OF NH | NHAI | N24001843 | 12-2022 | 11/2025 | N.A. | 11/2025 | 992.89 |  | 992.89 | 163.14 | 42.06
April 2025 |  |  | 61 | 6L ACCESS CONTROLLED GREENFIELD HIGHWAY FROM ODULAPALLE 72.000 KM. TO NALLACHERUVUPALLI 96.300 KM. | NHAI | N24001844 | 12-2022 | 10/2025 | N.A. | 10/2025 | 1058.9 |  | 1058.9 | 249.94 | 42.47
April 2025 |  |  | 62 | 6L ACCESS CONTROLLED GREENFIELD HIGHWAY FROM NALLACHERUVU PALLI 96.300 KM. TO YERRAGUDIPADU 129.000 | NHAI | N24001845 | 2-2023 | 10/2025 | N.A. | 10/2025 | 1253.24 |  | 1253.24 | 156.15 | 16.5
April 2025 |  |  | 63 | 6L ACCESS CONTROLLED GREENFIELD HIGHWAY FROM YERRAGUDIPADU 129.000 KM. TO AUDIREDDIPALLE 160.000 KM. | NHAI | N24001846 | 2-2023 | 10/2025 | N.A. | 10/2025 | 1200.42 |  | 1200.42 | 57.99 | 5.2
April 2025 |  |  | 64 | 6L ACCESS CONTROLLED GREENFIELD HIGHWAY FROM AUDIREDDIPALLE 160.000 KM. TO MALLAPALLE 176.000 KM. PA | NHAI | N24001847 | 1-2023 | 11/2025 | N.A. | 11/2025 | 956.14 |  | 956.14 | 176.3 | 35.54
April 2025 |  |  | 65 | 6L ACCESS CONTROLLED GREENFIELD HIGHWAY FROM MALLAPALLE 176.000 KM. TO KAVULAKUNTLA 196.000 KM. PACK | NHAI | N24001848 | 2-2023 | 10/2025 | N.A. | 10/2025 | 909.02 |  | 909.02 | 128.01 | 13.2
April 2025 |  |  | 66 | 4L PS MYDUKUR BADVEL FROM KM 585.820 TO KM 630.960 SECTION OF NH 67 | NHAI | N24001849 | 5-2022 | 7/2025 | N.A. | 9/2025 | 1063.72 |  | 1063.72 | 458.56 | 72.29
April 2025 |  |  | 67 | CONSTRUCTION OF 4-LANE HIGHWAY FROM SAMARLAKOTA TO ACHAMPETA JUNCTION (FROM KM. 0.000 TO KM. 12.250 | NHAI | N24001856 | 5-2023 | 8/2025 | N.A. | 8/2025 | 648.75 |  | 648.75 | 223.27 | 54.13
April 2025 |  |  | 68 | 2L+PS FROM KM. 0+000 TO KM. 32+000 (MUDIGUBBA TO PUTTAPARTHI) OF NH-342 | MoRTH | N24001932 | 3-2022 | 9/2024 | N.A. | 6/2025 | 401.72 |  | 401.72 | 139.07 | 80
April 2025 |  |  | 69 | NH440 RAYACHOTY TOVEMPALLI 2LPS | MoRTH | N24001934 | 12-2021 | 5/2024 | N.A. | 7/2025 | 439.82 |  | 439.82 | 119.72 | 27
April 2025 |  |  | 70 | 4 LANE WITH PAVED SHOULDER FROM KM 0.000 TO KM 51.119 OF TADIPATRI TO MUDDANUR OF NH67 | MoRTH | N24001935 | 3-2022 | 8/2025 | N.A. | 8/2025 | 724.17 |  | 724.17 | 229.73 | 97
April 2025 |  |  | 71 | NH165 FROM KM 0.000 TO KM 64.020 PAMARRU TO AKIVEEDU SECTION TO TWO LANE WITH PAVED SHOULDERS | MoRTH | N24001939 | 3-2020 | 9/2023 | N.A. | 12/2025 | 529.24 |  | 529.24 | 224.81 | 52
April 2025 |  |  | 72 | 2LPS FROM KM36.400 TO KM. 107.224 OF NH167BG FROM DUTTALUR TO KAVALI SECTION | MoRTH | N24001942 | 3-2021 | 7/2024 | N.A. | 3/2025 | 423.67 |  | 423.67 | 145.72 | 61
April 2025 |  |  | 73 | NH167AD FROM MACHERLA TO DACHEPALLI FROM KM.0.000 TO 43.659 TO 2LPS | MoRTH | N24001951 | 1-2022 | 1/2025 | N.A. | 1/2025 | 403.22 |  | 403.22 | 201.69 | 97
April 2025 |  |  | 74 | NH 167 B KADAPA NELLORE BORDER TO CSPURAM I.E. FROM KM 58.635 TO KM 99.409 | MoRTH | N24001952 | 3-2022 | 8/2025 | N.A. | 8/2025 | 285.5 |  | 285.5 | 204.29 | 95
April 2025 |  |  | 75 | NH-30-BHADRACHALAM TO KONTA SECTION 2LPS | MoRTH | N24001953 | 12-2021 | 9/2024 | N.A. | 3/2025 | 388.71 |  | 388.71 | 159.29 | 80
April 2025 |  |  | 76 | WIDENING TO 2LPS OF RAMPACHODAVARAM - KOYYURU SECTION OF NH516E FROM KM.43.700 TO KM 113.820 | MoRTH | N24001954 | 3-2022 | 1/2025 | N.A. | 1/2025 | 568.12 |  | 568.12 | 215.09 | 91.5
April 2025 |  |  | 77 | GUDIWADA TOWN 2 LANE ROB AND ROAD IMPROVEMENT OF NH165 IN REPLACEMENT OF LC NO 3ESPL3 AT KM 231.700 | MoRTH | N24001955 | 3-2022 | 5/2025 | N.A. | 5/2025 | 317.22 |  | 317.22 | 84.57 | 80
April 2025 |  |  | 78 | 2LPS FROM GONDIGUDA TO ARAKU BHALLAGUDA KM 27.480 TO KM 51.772 SECTION OF NH 516E | MoRTH | N24001956 | 8-2020 | 9/2023 | N.A. | 12/2024 | 296.66 |  | 296.66 | 190.3 | 87
April 2025 |  |  | 79 | 2LPS OF KOYYURU TO CHAPRATHIPALEM SECTION OF NH 516E | MoRTH | N24001957 | 8-2020 | 7/2024 | N.A. | 6/2025 | 349.29 |  | 349.29 | 114.53 | 76
April 2025 |  |  | 80 | 2LPS OF CHAPRATHIPALEM TO LAMBASINGI SECTION OF NH 516E | MoRTH | N24001958 | 8-2020 | 10/2024 | N.A. | 6/2025 | 311.22 |  | 311.22 | 85.45 | 72
April 2025 |  |  | 81 | 4 LANE FROM KM 56.400 TO KM 120.300 FROM B.KOTHAPALLI JUNCTION TO GORANTLA OF NH 716G | MoRTH | N24001959 | 3-2022 | 9/2025 | N.A. | 9/2025 | 839.98 |  | 839.98 | 146.12 | 67
April 2025 |  |  | 82 | 4L GREENFIELD ROAD CONNECTING NORTH AND SOUTH INDUSTRIAL CLUSTER OF KHANDALERU CREEK NEAR KRISHNAPAT | NHAI | N24001979 | 8-2022 | 9/2025 | N.A. | 9/2025 | 609.43 |  | 609.43 | 25.24 | 48.8
April 2025 |  |  | 83 | 4 LANING OF NH 544D FROM EXISTING KM 346.300 OF NH 44 (DESIGN CHAINAGE KM 0.000) TO KM 39.380 (DESIG | NHAI | N24001980 | 10-2022 | 7/2025 | N.A. | 7/2025 | 907.76 |  | 907.76 | 387.99 | 81.07
April 2025 |  |  | 84 | CONSTRUCTION OF SIX LANING OF NAIDUPETA JUNCTION - TURPUKANUPUR SECTION FROM KM.57+046 TO KM.91+927 | NHAI | N24001981 | 7-2022 | 10/2025 | N.A. | 10/2025 | 1398.84 |  | 1398.84 | 58.68 | 13.52
April 2025 |  |  | 85 | 4L PS FROM KURNOOL (EXISTING KM. 5.400 OF NH- 40/DESIGN KM.0.000) TO MANDLEM (EXISTING KM.38.000/DESI | NHAI | N24001982 | 3-2023 | 10/2025 | N.A. | 10/2025 | 827.39 |  | 827.39 | 332.64 | 99.15
April 2025 |  |  | 86 | 4 LANING FROM EXISTING KM 39.380 (DESIGN CH. 37.000) TO KM 74.450 (DESIGN CH. 69.000) OF MUCHUKOTA ? | NHAI | N24001983 | 10-2022 | 8/2025 | N.A. | 8/2025 | 972.63 |  | 1055.23 | 309.39 | 50.9
April 2025 |  |  | 87 | 4L PS FROM MANDLEM (EXISTING KM. 38.000/DESIGN KM.30.600) TO ATMAKUR (EXISTING KM.73.000/DESIGN KM 6 | NHAI | N24001984 | 3-2023 | 10/2025 | N.A. | 10/2025 | 887.28 |  | 887.28 | 263.47 | 78.5
April 2025 |  |  | 88 | BANGALORE CHENNAI EXPRESSWAY (PHASE-II PKG-II) FROM KM.96.000 TO KM 127.000 (BAIREDDYPALLE TO BANGAR | NHAI | N24001985 | 3-2021 | 6/2025 | N.A. | 6/2025 | 1942.94 | 2171 | 2171 | 1569.61 | 60.5
April 2025 |  |  | 89 | 4L OF PILERU TO KALUR SECTION FROM KM 55.900 TO KM 92.800 AND KM 94.500 TO KM 95.717 | NHAI | N24001986 | 10-2023 | 4/2025 | N.A. | 4/2025 | 1047.32 |  | 1047.32 | 301.2 | 82.5
April 2025 |  |  | 90 | CONSTRUCTION OF 1 NOS ROB, 2 NOS VUPS, SERVICE ROADS, PROVISION OF LIGHTING AND CONSTRUCTION OF OTHE | NHAI | N24001987 | 6-2023 | 12/2024 | N.A. | 12/2024 | 152.05 |  | 152.05 | 133.08 | 76.62
April 2025 |  |  | 91 | 6L OF CHITTOOR TO THATCHUR FROM KUMARAJAPET TO VEERA KAVERI RAJA PURAM FROM KM 43.800 TO KM 61.380 O | NHAI | N24001988 | 2-2021 | 10/2025 | N.A. | 10/2025 | 591.99 | 703 | 703 | 496.65 | 60.16
April 2025 |  |  | 92 | CONSTRUCTION OF 4 LANE ACCESS CONTROLLED HIGHWAY FROM CHILLAKURU CROSS ROAD TO TURPUKANUPUR KM 0+000 | NHAI | N24002033 | 7-2022 | 12/2025 | N.A. | 12/2025 | 909.47 |  | 909.47 | 97.03 | 26.9
April 2025 |  |  | 93 | COMPLETION OF BALANCE WORKS PENDING IN BIT AND PIECES (INCOMPLETE STRETCH AT 7 LOCATIONS) AND LISTED | NHAI | N24002103 | 9-2022 | 1/2025 | N.A. | 4/2025 | 166.52 |  | 166.52 | 52.79 | 93
April 2025 |  |  | 94 | 6L ACCESS CONTROLLED GREENFIELD HIGHWAY FROM NARAYANMPET (CH. 203+500) TO CHANDRASEKHARPURAM (CH. 22 | NHAI | N24002122 | 2-2024 | 2/2026 | N.A. | 2/2026 | 813.66 |  | 813.66 | 91.47 | 21.19
April 2025 |  |  | 95 | 6L ACCESS CONTROLLED GREENFIELD HIGHWAY FROM CHANDRASEKHARAPURAM (CH. 228+000) TO POLAVARAM (CH. 260 | NHAI | N24002123 | 2-2024 | 2/2026 | N.A. | 2/2026 | 1292.65 |  | 1292.65 | 135.06 | 13.1
April 2025 |  |  | 96 | 6L ACCESS CONTROLLED GREENFIELD HIGHWAY FROM POLAVARAM (CH. 260+000) TO MARRIPUDI (CH. 285+500) OF [ | NHAI | N24002124 | 2-2024 | 2/2026 | N.A. | 2/2026 | 747.29 |  | 747.29 | 118.3 | 28.1
April 2025 |  |  | 97 | 6L ACCESS CONTROLLED GREENFIELD HIGHWAY FROM MARRIPUDI (CH. 285+500) TO SOMAVARAPPADU (CH. 314+600) | NHAI | N24002125 | 2-2024 | 2/2026 | N.A. | 2/2026 | 976.4 |  | 976.4 | 197.02 | 37.9
April 2025 |  |  | 98 | 6L ACCESS CONTROLLED GREENFIELD HIGHWAY FROM SOMAVARAPPADU (CH.314.600) TO MUPPAVARAM (CH.343+240) O | NHAI | N24002126 | 2-2024 | 2/2026 | N.A. | 2/2026 | 1103.89 |  | 1103.89 | 133.52 | 12.04
April 2025 |  |  | 99 | 4-LANE WITH PAVED SHOULDERS FROM KM 32/0 TO KM 79/650 (DESIGN CHAINAGE KM 32+000 TO KM 78+760) PUTTA | MoRTH | N24002139 | 3-2023 | 12/2025 | N.A. | 11/2025 | 1318.57 |  | 1318.57 | 201 | 56
April 2025 |  |  | 100 | SOMAYAJULAPALLI ? DHONE SECTION OF NH ? 340B FROM KM.0/0 TO 56/200 [DESIGN CH. KM 0/00 TO KM 53/33] | MoRTH | N24002140 | 4-2023 | 12/2025 | N.A. | 12/2025 | 629.73 |  | 629.73 | 103 | 62
April 2025 |  |  | 101 | 2-LANE WITH PAVED SHOULDER CONFIGURATION OF LAMBASINGI TO PADERU SECTION (KM 205+000 TO KM 253+974) | MoRTH | N24002142 | 8-2023 | 11/2025 | N.A. | 11/2025 | 361.24 |  | 361.24 | 7 | 26
April 2025 |  |  | 102 | BYPASS ROAD TO ADONI TOWN CONNECTING NH-167 (HAGARI - JADCHARLA ROAD) FROM KM.62/700 TO 71/400 IN KU | MoRTH | N24002143 | 8-2023 | 2/2026 | N.A. | 2/2026 | 361.24 |  | 361.24 | 109.65 | 56
April 2025 |  |  | 103 | VODAREVU-CHILAKALURIPET SECTION (DESIGN CHAINAGE 0+00 TO 47+000) OF NH-167A | PACKAGE-I | MoRTH | 8-2023 | 2/2026 | N.A. | 2/2026 | 1064.24 |  | 1064.24 | 80 | 60
April 2025 |  |  | 104 | TADIPATRI BYPASS (KM 0+000 TO KM 6+285) OF 4-LANE ON NH- 67 IN ANANTAPURAMU | MoRTH | N24002145 | 11-2023 | 3/2026 | N.A. | 3/2026 | 159.66 |  | 159.66 | 11.95 | 63.5
April 2025 |  |  | 105 | KURNOOL/KADAPA BORDER- JAMMALAMADUGU SECTION OF NH-167K I.E. DESIGN CH. KM 248+010 TO KM 269+900 | MoRTH | N24002146 | 11-2023 | 11/2025 | N.A. | 11/2025 | 292.63 |  | 292.63 | 61.36 | 20
April 2025 |  |  | 106 | DORNALA TO KUNTA JUNCTION FROM DESIGN CHAINAGE KM 244+000 TO 267+990 SECTION OF NH-765 (PACKAGE-2) | MoRTH | N24002147 | 12-2022 | 1/2024 | N.A. | 3/2026 | 244.83 |  | 244.83 | 104.32 | 74
April 2025 |  |  | 107 | PADERU BYPASS (KM 0+000 TO KM 13+000) OF 2- LANE WITH PAVED SHOULDER ON NH-516E | MoRTH | N24002148 | 3-2023 | 3/2024 | N.A. | 2/2026 | 244.43 |  | 244.43 | 22.77 | -
April 2025 |  |  | 108 | DAVUALAPALLY TO MALLAPALEM SECTION {DESIGN CH. KM 133+922 TO KM 154+216 (EXISTING CH. KM 133+922 TO | MoRTH | N24002149 | 1-2024 | 2/2024 | N.A. | 2/2026 | 393.61 |  | 393.61 | 40 | 24
April 2025 |  |  | 109 | DEVELOPMENT OF SIX LANE ACCESS CONTROLLED GREEN FIELD HIGHWAY FROM KAVULAKUNTLA (KM.196+000) TO NARA | NHAI | N24002215 | 2-2023 | 2/2027 | N.A. | 2/2027 | 1092.18 |  | 1092.18 | 0.14 | -
April 2025 |  |  | 110 | ACCESS CONTROLLED HIGHWAY OF 4 LANE WITH PAVED SHOULDERS FROM TN/AP BORDER (DESIGN CHAINAGE KM 61+51 | NHAI | N24002217 | 12-2024 | 12/2026 | N.A. | 12/2026 | 1346.82 |  | 1346.82 | 0 | 5.64
April 2025 |  | WATER RESOURCES | 111 | POLAVARAM IRRIGATION PROJECT | PPA | N30000002 | 2-2009 | 3/2020 | 3/2027 | 12/2027 | 10151.04 |  | 55548.87 | 23775.68 | 75.68
April 2025 |  | CIVIL AVIATION | 112 | CONSTRUCTION OF NEW GREEN FIELD AIRPORT AT HOLLONGI ITANAGAR ARUNACHAL PRADESH | AAI | N04000092 | 2-2019 | 8/2022 | 5/2025 | 5/2025 | 645.63 |  | 732 | 690.39 | 99.5
April 2025 |  | CIVIL AVIATION | 113 | SUBANSIRI LOWER H.E.P (8X250 MW) (NHPC) | NHPC | 180100221 | 9-2003 | 9/2010 | N.A. | 5/2026 | 6285.33 |  | 26075.54 | 24022.52 | 96.2
April 2025 |  |  | 114 | DIBANG MULTIPURPOSE PROJECT 2880 MW ARUNACHAL PRADESH | NHPC | N18000362 | 2-2023 | 2/2032 | N.A. | 2/2032 | 31876.39 |  | 31876.39 | 3222.41 | 14.7
April 2025 |  |  | 115 | TWO LANING OF JORAM KOLORIANG ROAD (NH 713) ON EPC BASIS FROM DESIGN KM. 138+000 TO KM. 154+036 [EX | NHIDCL | N24000683 | 2-2017 | 11/2023 | 3/2024 | 3/2025 | 180.57 | 244.1 | 180.57 | 160.46 | 96.62
April 2025 |  |  | 116 | CONSTRUCTION OF 2-LANE ROAD WITH PAVED SHOULDERS FROM KM16.00 OF ROING-HUNLI SECTION TO KM 21.500 OF | NHIDCL | N24000946 | 3-2017 | 3/2022 | 6/2025 | 12/2025 | 1718.59 | 1718.59 | 1718.59 | 728.21 | 73.2
April 2025 |  |  | 117 | TWO-LANING OF HAYULIANG? HAWAI BYPASS ROAD ON EPC BASIS FROM DESIGN KM. 51.825 TO KM. 63.131 EXISTI | NHIDCL | N24000979 | 1-2017 | 5/2023 | 5/2023 | 3/2025 | 256.66 |  | 256.66 | 0 | 63.59
April 2025 |  |  | 118 | CONSTRUCTION OF 2-LANING WITH HARD SHOULDERS OF ARROWA-KHUPA-HAYULIANG SECTION OF NH-113 FROM CH.68. | NHIDCL | N24001244 | 8-2020 | 4/2022 | 2/2025 | 2/2025 | 301.06 |  | 301.06 | 191.34 | 81.06
April 2025 |  |  | 119 | CONSTRUCTION OF 2 LANE ROAD OF POTIN TO PANGIN SECTION OF NH 13 FROM KM 163.59 TO KM 206.66 (PACKAGE | MoRTH | N24001297 | 3-2019 | 3/2027 | N.A. | 3/2027 | 450.65 |  | 450.65 | 389.68 | 95.28
April 2025 |  |  | 120 | 4 LANING OF ITANAGAR TO BANDARDEWA SECTION OF NH- 415 FROM KM 40+430 TO KM 51+735 (PACKAGE B) ON EPC | MoRTH | N24001375 | 6-2020 | 3/2027 | N.A. | 3/2027 | 496.47 |  | 496.47 | 179.53 | 41.94
April 2025 |  |  | 121 | JORAM ? KOLORIANG ROAD FROM EXISTING KM 50.050 TO KM 70.00 (PKG-3) | NHIDCL | N24001390 | 8-2020 | 4/2022 | 8/2024 | 9/2024 | 228.71 |  | 228.71 | 98.86 | 99.52
April 2025 |  |  | 122 | JORAM ? KOLORIANG ROAD FROM EXISTING KM 70.00 TO KM 88.700 (PKG-4) | NHIDCL | N24001391 | 8-2020 | 4/2022 | 2/2024 | 9/2024 | 294.04 |  | 294.04 | 147.13 | 100
April 2025 |  |  | 123 | JORAM ? KOLORIANG ROAD FROM EXISTING KM122.600 TO KM138.00 (PKG-7) | NHIDCL | N24001393 | 8-2020 | 4/2022 | 2/2024 | 4/2025 | 184.88 |  | 184.88 | 99.32 | 97.42
April 2025 |  |  | 124 | HUNLI TO HAYULIANG PKG-1 | NHIDCL | N24002222 | 2-2024 | 2/2028 | N.A. | 2/2028 | 1262.43 |  | 1262.43 | 0 | 0.75
April 2025 |  |  | 125 | HUNLI TO ITHUN BRIDGE SECTION | NHIDCL | N24002223 | 2-2024 | 1/2027 | N.A. | 1/2027 | 275.5 |  | 275.5 | 0 | 1.2
April 2025 |  |  | 126 | PANGO TO JORGING ROAD PKG- 1 | NHIDCL | N24002224 | 1-2024 | 7/2027 | N.A. | 7/2027 | 898.19 |  | 898.19 | 7.08 | 1.97
April 2025 |  | CIVIL AVIATION | 127 | CONSTRUCTION OF NEW INTEGRATED TERMINAL BUILDING AT LGBI AIRPORT GUWAHATI | AAI | N04000083 | 12-2016 | 3/2021 | 8/2025 | 8/2025 | 1142 |  | 2333 | 1850.93 | 86.95
April 2025 |  | COAL | 128 | TIKAK EXTENSION OCP - 0.2 MTY | CIL | N06000290 | 7-2022 | 11/2030 | N.A. | 11/2030 | 159.77 |  | 159.77 | 81.45 | -
April 2025 |  | COAL | 129 | TIRAP OCP | CIL | N06000291 | 11-2022 | 11/2027 | N.A. | 11/2027 | 289.46 |  | 289.46 | 105.59 | -
April 2025 |  | HEALTH AND FAMILY WELFARE | 130 | ALL INDIA INSTITUTE OF MEDICAL SCIENCE AT GUWAHATI, ASSAM | HITES | N21000027 | 5-2017 | 5/2021 | 4/2023 | 11/2024 | 875 | 873.92 | 860 | 787.9 | 99.4
April 2025 |  | HEALTH AND FAMILY WELFARE | 131 | DEVELOPMENT OF SURFACE FACILITIES FOR PRODUCTION AND EVACUATION OF CRUDE OIL AND NATURAL GAS FROM NA | OIL | N16000331 | 1-2018 | 2/2020 | 12/2024 | 6/2025 | 543.91 | 726.93 | 726.93 | 491.56 | 93.89
April 2025 |  | HEALTH AND FAMILY WELFARE | 132 | NUMALIGARH REFINERY EXPANSION PROJECT 6 MMTPA REFINARY | NRL | N16000379 | 1-2019 | 10/2024 | N.A. | 12/2025 | 12366 |  | 18968 | 15412.49 | 73.06
April 2025 |  | HEALTH AND FAMILY WELFARE | 133 | NUMALIGARH REFINERY EXPANSION PROJECT COIT AND PIPELINES | NRL | N16000394 | 1-2019 | 10/2024 | N.A. | 9/2025 | 10228 |  | 9058 | 9247.5 | 84.53
April 2025 |  | HEALTH AND FAMILY WELFARE | 134 | EXPANSION OF GUWAHATI REFINERY FROM 1 TO 1.2 MMTPA ALONG WITH INSTALLATION OF CATALYTIC REFORMING UN | IOCL | N16000414 | 5-2021 | 10/2023 | 5/2026 | 5/2026 | 412 | 595.2 | 595.2 | 399.81 | 82.5
April 2025 |  | HEALTH AND FAMILY WELFARE | 135 | REVAMPING OF FACILITIES AT EXISTING GUWAHATI TERMINAL, ASSAM | IOCL | N16000441 | 3-2022 | 7/2026 | 9/2026 | 9/2026 | 277 |  | 277 | 175.69 | 66.02
April 2025 |  | HEALTH AND FAMILY WELFARE | 136 | UPGRADATION OF FACILITIES OF NUMALIGARH-SILIGURI PRODUCT PIPELINE (NSPL) FOR TRANSPORTATION OF ADDIT | OIL | N16000449 | 6-2021 | 12/2024 | 4/2025 | 7/2025 | 860 |  | 860 | 535.46 | 96
April 2025 |  |  | 137 | PROJECT TO CONSTRUCT A FIELD GAS GATHERING STATION AT BAGHJAN AREA FOR COLLECTION,PROCESSING | OIL | N16000450 | 12-2020 | 7/2024 | 3/2024 | 6/2025 | 430.76 |  | 430.76 | 308.9 | 83.56
April 2025 |  |  | 138 | CAPACITY EXPANSION OF DIGBOI REFINERY FROM 0.65 TO 1.0 MMTPA | IOCL | N16000457 | 6-2022 | 10/2025 | N.A. | 3/2026 | 768 |  | 768 | 80.34 | 31.4
April 2025 |  |  | 139 | CONSTRUCTION OF LPG FACILITIES AT KAMARDANGA, ASSAM | HPCL | N16000484 | 3-2023 | 7/2027 | 7/2027 | 7/2027 | 156.36 | 156.36 | 156.36 | 38.92 | 28.5
April 2025 |  |  | 140 | SETTING UP OF NEW RAIL FED POL FACILITY AT KAMARDANGA, ASSAM | HPCL | N16000494 | 3-2023 | 7/2027 | 7/2027 | 7/2027 | 384.04 |  | 384.04 | 87.82 | 30.7
April 2025 |  |  | 141 | POWER RECOVERY TURBINE IN PFCCU | NRL | N16000510 | 3-2023 | 7/2025 | N.A. | 7/2025 | 293.5 |  | 293.5 | 97.22 | 90
April 2025 |  |  | 142 | DCU REVAMP PROJECT | NRL | N16000511 | 8-2021 | 3/2025 | N.A. | 10/2025 | 370 |  | 370 | 250.17 | 55.2
April 2025 |  |  | 143 | PIPELINE NETWORK PROJECT RUDRASAGAR | ONGC | N16000528 | 1-2023 | 4/2026 | N.A. | 4/2026 | 344.99 |  | 344.99 | 169.95 | 44.1
April 2025 |  |  | 144 | BORHOLLA GGS LIFE EXTENSION PROJECT | ONGC | N16000532 | 9-2023 | 5/2026 | N.A. | 5/2026 | 198.7 |  | 198.7 | 99.52 | 20.1
April 2025 |  | RAILWAYS | 145 | BONGAIGAON-GOALPARA- GUWAHATI (176 KM) | NFR | N22000388 | 4-2015 | 3/2026 | N.A. | 3/2027 | 4059.65 |  | 4983.94 | 3626.2 | 92.31
April 2025 |  | RAILWAYS | 146 | 4 LANING OF JORHAT TO JHANJI SECTION FROM KM. 453.00 TO KM. 491.08 (DESIGN KM 403.200 TO KM 454.240) | NHIDCL | N24000319 | 6-2015 | 8/2023 | N.A. | 5/2025 | 437.39 |  | 437.39 | 547.95 | 96.13
April 2025 |  | RAILWAYS | 147 | FOUR LANING OF JHANJHI JN TO DEMOW SECTION FROM KM. 491.050 TO KM. 535.250(DESIGN KM 490.800 TO KM 5 | NHIDCL | N24000320 | 6-2015 | 3/2024 | N.A. | 10/2025 | 463.49 |  | 463.49 | 490.44 | 75.52
April 2025 |  | RAILWAYS | 148 | 4 LANING FROM JAMUGURI TO BISWANATH CHARIALI FROM KM 182 TO KM 208 OF NH-52 | NHIDCL | N24000431 | 1-1991 | 6/2019 | 6/2019 | 6/2025 | 520.01 |  | 520.01 | 305.76 | 97.7
April 2025 |  | RAILWAYS | 149 | 4 LANING FROM RANGAGARA TO KALIABHOR TINALI FROM KM 297.00 TO KM 315.315 OF NH-37 ON EPC BASIS. | NHIDCL | N24000438 | 12-2015 | 12/2018 | 7/2021 | 12/2025 | 289.99 |  | 289.99 | 233.23 | 88.03
April 2025 |  | RAILWAYS | 150 | 4 LANING OF NH-37 SECTION BETWEEN DEMOW TO END OF MORAN BYPASS (FROM KM. 534.800 TO KM. 561.700) O | NHIDCL | N24000582 | 1-2016 | 1/2016 | N.A. | 5/2025 | 294.17 |  | 294.17 | 381.37 | 97.63
April 2025 |  | RAILWAYS | 151 | 4 LANING OF NH 37 SECTION BETWEEN END OF MORAN BYPASS TO BOGIBEEL JUNCTION NEAR LAPETKETA (KM. 561 | NHIDCL | N24000583 | 1-2016 | 12/2021 | N.A. | 5/2025 | 252 |  | 330.3 | 219.65 | 87.19
April 2025 |  |  | 152 | 4-LANING OF HAPACHARA - TULUNGIA SECTION | NHIDCL | N24001246 | 3-2020 | 12/2022 | N.A. | 6/2024 | 220.2 |  | 220.2 | 217.06 | 97.76
April 2025 |  |  | 153 | 2-LANING OF CHURACHANDPUR TUIVAI SECTION OF NH-102B | PKG- IB | NHIDCL | 3-2020 | 3/2022 | 1/2025 | 6/2025 | 216.49 | 241.52 | 216.49 | 111.59 | 82.79
April 2025 |  |  | 154 | 4-L DHUBRI PHULBARI BRIDGE WITH APPROACH ROAD | NHIDCL | N24001326 | 11-2020 | 9/2028 | N.A. | 9/2028 | 4997.04 |  | 4997.04 | 2382.39 | 60.8
April 2025 |  |  | 155 | 2-LANING FROM YAINGANGPOKPI TO FINCH CORNER (PKG-I) | NHIDCL | N24001331 | 3-2020 | 6/2022 | 5/2025 | 12/2025 | 261.13 |  | 261.13 | 68.75 | 57.42
April 2025 |  |  | 156 | 2-LANING FROM YAINGANGPOKPI TO FINCH CORNER (PKG-II) | NHIDCL | N24001332 | 3-2020 | 6/2022 | 4/2025 | 12/2025 | 217.5 |  | 217.5 | 88.99 | 68.03
April 2025 |  |  | 157 | DABOKA KATHKATI PACKAGE-5 | NHIDCL | N24001366 | 3-2021 | 1/2023 | N.A. | 11/2024 | 288.85 |  | 288.85 | 247.76 | 100
April 2025 |  |  | 158 | TULUNGIA-JOGIGHOPA-PAIKAN ROAD PKG-7 | NHIDCL | N24001368 | 3-2021 | 1/2024 | N.A. | 10/2025 | 286.72 |  | 286.72 | 147.96 | 75.89
April 2025 |  |  | 159 | CONSTRUCTION OF 2-LANE MAJOR BRIDGE INCLUDING APPROACHESOVER BRAHMAPUTRA BETWEEN MAJULI ON NORTH BAN | MoRTH | N24001408 | 2-2021 | 7/2025 | N.A. | 7/2025 | 925.47 | 1019.17 | 925.47 | 192.5 | 30.65
April 2025 |  |  | 160 | JOGIGHOPA BRIDGE | NHIDCL | N24001434 | 8-2021 | 11/2024 | N.A. | 12/2026 | 746.76 |  | 746.76 | 328.49 | 65.84
April 2025 |  |  | 161 | DABOKA KATHKATI PACKAGE-6 | NHIDCL | N24001450 | 9-2021 | 7/2024 | N.A. | 5/2025 | 625.64 |  | 625.64 | 550.6 | 100
April 2025 |  |  | 162 | DABOKA KATHKATI PACKAGE-7 | NHIDCL | N24001537 | 11-2021 | 7/2024 | N.A. | 5/2025 | 204.1 |  | 204.1 | 142.31 | 95.01
April 2025 |  |  | 163 | FOUR LANING OF SRIRAMPUR- DHUBRI PKG-2 | NHIDCL | N24001544 | 3-2022 | 1/2025 | N.A. | 6/2025 | 909.02 |  | 909.02 | 509.89 | 97.63
April 2025 |  |  | 164 | 6L STANDALONE FLYOVERS AT RAHA, DEMOW, BORGHAT, KATHIATALI JUNCTIONS AND ROB AT JAGIROAD ON STRETCHE | NHAI | N24001545 | 8-2022 | 12/2022 | 9/2024 | 6/2024 | 175 |  | 175 | 200.8 | 100
April 2025 |  |  | 165 | BALANCE WORK OF 4L OF NARIMBANGLO?JATINGA JUNCTION- HARANGAJO ROAD SECTION FROM KM 0.000 TO KM 49.23 | NHAI | N24001547 | 3-2022 | 1/2026 | N.A. | 1/2026 | 1909.98 |  | 1909.98 | 567.75 | 76.4
April 2025 |  |  | 166 | 6L STANDALONE FLYOVERS AT BONGAIGAON, CHAPAGURI, PATHSALA, SIMLAGURI CHOWK AND BAIHATA BYPASS JUNCTI | NHAI | N24001548 | 3-2022 | 6/2024 | N.A. | 5/2025 | 457.72 |  | 457.72 | 365.99 | 100
April 2025 |  |  | 167 | SRIRAMPUR - DHUBRI PKG-1 | NHIDCL | N24001831 | 3-2022 | 2/2025 | N.A. | 11/2026 | 613.89 |  | 613.89 | 110.75 | 35.63
April 2025 |  |  | 168 | DIBRUGARH-LAHOAL-CHABUA BYPASS PACKAGE-3 | NHIDCL | N24001832 | 1-2023 | 5/2025 | N.A. | 7/2025 | 458.59 |  | 458.59 | 196.51 | 61.42
April 2025 |  |  | 169 | CONSTRUCTION OF MANGALDOI BYPASS (NH-15) STARTING AT CH 26+400 AND TERMINATING AT CH 41+505 UNDER RA | MoRTH | N24001840 | 3-2022 | 4/2025 | N.A. | 4/2025 | 535.03 |  | 535.03 | 102.23 | 31.23
April 2025 |  |  | 170 | WIDENING AND UPGRADATION TO TWO LANES WITH PAVED SHOULDERS ROAD FROM TAMENGLONG TO MAHUR (NH- 137) I | NHIDCL | N24001969 | 3-2023 | 8/2025 | N.A. | 8/2025 | 904.04 |  | 904.04 | 391.08 | 62.21
April 2025 |  |  | 171 | WIDENING AND UPGRADATION TO TWO LANES WITH PAVED SHOULDERS ROAD FROM TAMENGLONG TO MAHUR (NH- 137) IN | NHIDCL | N24001970 | 3-2023 | 8/2025 | N.A. | 8/2025 | 860.37 |  | 860.37 | 365.69 | 62.61
April 2025 |  |  | 172 | WIDENING AND UPGRADATION TO TWO LANES WITH PAVED SHOULDERS ROAD FROM TAMENGLONG TO MAHUR (NH- 137) IN | NHIDCL | N24001971 | 3-2023 | 8/2025 | N.A. | 8/2025 | 890.33 |  | 890.33 | 417.14 | 60.47
April 2025 |  |  | 173 | WIDENING/IMPROVEMENT TO 4- LANE WITH PAVED SHOULDER FROM KM 0+800 (KANDULIJAN GAON) TO KM 27+701 (SI | NHIDCL | N24001972 | 3-2023 | 4/2026 | N.A. | 4/2026 | 609.16 |  | 609.16 | 293.45 | 91.18
April 2025 |  |  | 174 | WIDENING/IMPROVEMENT TO 4- LANE WITH PAVED SHOULDER FROM KM 27+701 (SIMEN CHAPORI) TO KM 55+000 (NAG | NHIDCL | N24001973 | 3-2023 | 2/2026 | N.A. | 2/2026 | 562.05 |  | 562.05 | 276.61 | 92.13
April 2025 |  |  | 175 | BILASIPURA-GUWAHATI ROAD PKG-8 | NHIDCL | N24002021 | 3-2023 | 12/2026 | N.A. | 12/2026 | 1457.59 |  | 1457.59 | 522.78 | 44.9
April 2025 |  |  | 176 | BILASIPURA-GUWAHATI ROAD PKG-9 | NHIDCL | N24002022 | 3-2023 | 6/2026 | N.A. | 6/2026 | 1000.27 |  | 1000.27 | 303.94 | 24.5
April 2025 |  |  | 177 | BILASIPURA-GUWAHATI ROAD PKG-10 | NHIDCL | N24002023 | 3-2023 | 6/2026 | N.A. | 6/2026 | 1264.9 |  | 1264.9 | 422.31 | 24.26
April 2025 |  |  | 178 | DABOKA BYPASS OF DABOKA - PAROKHAOWA PKG -1 | NHIDCL | N24002024 | 1-2023 | 11/2025 | N.A. | 11/2025 | 516.88 |  | 516.88 | 236.11 | 72.87
April 2025 |  |  | 179 | 2 LANE WITH PAVED SHOULDER FROM KM 16+900 (BOGAPANI) TO KM 27+150 (GOLAI GAON) ON EXISTING DIBRUGARH | NHIDCL | N24002025 | 1-2023 | 12/2025 | N.A. | 12/2026 | 356.65 |  | 356.65 | 129.18 | 14.06
April 2025 |  |  | 180 | 2 LANE WITH PAVED SHOULDER FROM KM 27+150 (GOLAI GAON) TO KM 47+682 (LEDO) ON EXISTING DIBRUGARH TO | NHIDCL | N24002026 | 3-2023 | 12/2025 | N.A. | 12/2026 | 643.42 |  | 643.42 | 69.47 | 8.89
April 2025 |  |  | 181 | DEVELOPMENT OF EXTERNAL TRUNK CONNECTIVITY AND INTERNAL INFRASTRUCTURE WORKS AT MULTI MODEL LOGISTIC | NHIDCL | N24002030 | 2-2020 | 3/2022 | N.A. | 9/2024 | 592.06 |  | 592.06 | 308.87 | 100
April 2025 |  |  | 182 | SILCHAR VAIRENGTE SAIRANG ROAD PKG-1 | NHIDCL | N24002127 | 2-2023 | 7/2026 | N.A. | 7/2026 | 1256.9 |  | 1256.9 | 520.82 | 36.05
April 2025 |  |  | 183 | SILCHAR VAIRENGTE SAIRANG ROAD PKG-2 | NHIDCL | N24002128 | 3-2023 | 8/2026 | N.A. | 8/2026 | 1716.21 |  | 1716.21 | 983.58 | 63.52
April 2025 |  |  | 184 | FOUR LANNING OF BADARPUR BYPASS FROM DESIGN CHAINAGE KM 27+300 AT CROSSING WITH NH-6 | NHIDCL | N24002129 | 2-2023 | 8/2026 | N.A. | 8/2026 | 574.26 |  | 574.26 | 283.15 | 51.88
April 2025 |  |  | 185 | TAMENGLONG- MAHUR ROAD PKG-7 | NHIDCL | N24002130 | 12-2023 | 3/2026 | N.A. | 3/2026 | 846.82 |  | 846.82 | 380.59 | 61.1
April 2025 |  |  | 186 | CONSTRUCTION OF 4-LANE PANCHGRAM BYPASS FROM DESIGN CHAINAGE KM 15+500 ON NH-37 (OLD NH-53) AT KALIN | NHIDCL | N24002154 | 3-2023 | 2/2027 | N.A. | 2/2027 | 728.97 |  | 728.97 | 279.86 | 41.57
April 2025 |  |  | 187 | WIDENING/IMPROVEMENT TO 4- LANE WITH PAVED SHOULDER FROM KM 55+000 (NAGABANG GAMSUK) TO KM 82+514 (OY | NHIDCL | N24002155 | 3-2023 | 3/2027 | N.A. | 3/2027 | 665.47 |  | 665.47 | 153.6 | 36.55
April 2025 |  |  | 188 | BILASIPURA- GUWAHATI ROAD PKG-1 | NHIDCL | N24002225 | 2-2024 | 8/2027 | N.A. | 8/2027 | 1081.15 |  | 1081.15 | 0 | 1.16
April 2025 |  |  | 189 | SILCHAR-JIRIBAM PKG-1 | NHIDCL | N24002226 | 1-2024 | 1/2028 | N.A. | 1/2028 | 957.95 |  | 957.95 | 0 | -
April 2025 |  |  | 190 | BILASIPURA- GUWAHATI ROAD PKG-2 | NHIDCL | N24002229 | 11-2023 | 6/2027 | N.A. | 6/2027 | 1338.61 |  | 1338.61 | 0.5 | -
April 2025 |  |  | 191 | BADARPUR ? CHURAIBARI PKG- 6 | NHIDCL | N24002230 | 3-2024 | 3/2027 | N.A. | 3/2027 | 870 |  | 870 | 0 | -
April 2025 |  |  | 192 | KARIMGANI - SUTARKANDI SECTION ON SILCHAR- CHURAIBARI PKG-7 | NHIDCL | N24002231 | 2-2024 | 2/2027 | N.A. | 2/2027 | 791.79 |  | 791.79 | 0 | -
April 2025 |  | CIVIL AVIATION | 193 | CONSTRUCTION OF NEW DORNESTIC TERMINAL BUILDING AND OTHER STRUCTURES, PHASE I AND II | AAI | N04000082 | 5-2018 | 10/2022 | 6/2025 | 6/2025 | 1216.9 |  | 1216.9 | 987.35 | 89.06
April 2025 |  | CIVIL AVIATION | 194 | DARBHANGA:DEVELOPMENT OF NEW CIVIL ENCLAVE AT DARBHANGA, BIHAR. SH- CONSTRUCTION OF NEW TERMINAL BUI | AAI | N04000112 | 7-2024 | 7/2026 | N.A. | 7/2026 | 911.66 |  | 911.66 | 112.84 | 15
April 2025 |  | DEPARTMENT OF HIGHER EDUCATION | 195 | CONSTRUCTION OF ACADEMIC AND RESIDENTIAL COMPLEX UNDER PHASE-II FOR THE CAMPUS OF IIT PATNA | CPWD EDUCATION | N28000100 | 2-2016 | 6/2017 | N.A. | 1/2024 | 496.18 | 496 | 460 | 390.15 | 100
April 2025 |  | DEPARTMENT OF HIGHER EDUCATION | 196 | PERMANENT CAMPUS FOR IIM BODH GAYA | CPWD EDUCATION | N42000009 | 9-2018 | 9/2020 | N.A. | 9/2020 | 375 |  | 375 | 342.18 | 99.5
April 2025 |  | DEPARTMENT OF HIGHER EDUCATION | 197 | BARAUNI REFINERY CAPACITY EXPANSION FROM 6.0 TO 9.0 MMTPA | IOCL | N16000386 | 1-2020 | 4/2023 | 8/2026 | 8/2026 | 14810 | 18113 | 18113 | 10668.28 | 85.1
April 2025 |  |  | 198 | CGD PROJECT AT KHAGARIA, SAHARSA AND MADHEPURA | IOCL | N16000423 | 6-2019 | 12/2029 | 3/2030 | 3/2030 | 163 |  | 163 | 96.78 | 40.1
April 2025 |  |  | 199 | INSTALLATION OF BITUMEN MANUFACTURING UNIT ALONG WITH ALLIED FACILITIES AT BARAUNI | IOCL | N16000453 | 1-2022 | 4/2025 | N.A. | 5/2026 | 389 |  | 389 | 37.55 | 30.9
April 2025 |  |  | 200 | CITY GAS DISTRIBUTION PROJECTS AT GOPALGANJ SIWAN WEST CHAMPARAN EAST CHAMPARAN AND DEORIA DISTRICTS | BPCL | N16000523 | 12-2022 | 6/2030 | N.A. | 6/2030 | 3919 |  | 3919 | 376.96 | 13
April 2025 |  |  | 201 | CITY GAS DISTRIBUTION PROJECTS AT DARBHANGA, MADHUBANI, SUPAUL, SITAMARHI AND SHEOHAR DISTRICTS | BPCL | N16000524 | 12-2022 | 3/2030 | N.A. | 3/2030 | 3638 |  | 3638 | 376.61 | 19
April 2025 |  | POWER | 202 | BARH STPP(3X660MW) NTPC | NTPC | 180100242 | 2-2005 | 10/2011 | 7/2023 | 3/2025 | 8692.97 | 21312.11 | 21312.11 | 22290.14 | 95
April 2025 |  | POWER | 203 | BUXAR THERMAL POWER PLANT (1320 MW) | SJVN | N18000194 | 3-2019 | 1/2024 | N.A. | 9/2025 | 10439.09 |  | 14390.09 | 11451.47 | 89.95
April 2025 |  | POWER | 204 | KHAGARIA-KUSHESHWAR ASTHAN (NL) (ECR) | ECR | 220100257 | 4-1997 | 12/2024 | N.A. | 3/2027 | 614.45 | 614.45 | 614.45 | 474.57 | 52
April 2025 |  | POWER | 205 | HAJIPUR-SUGAULI VIA VAISHALI (NL), ECR | ECR | 220100303 | 4-2003 | 12/2014 | N.A. | 12/2026 | 2066.78 | 2087.36 | 2087.36 | 2294.71 | 73
April 2025 |  |  | 206 | NEW B.G. LINE FROM ARARIA TO GALGALIA (THAKURGUNG), NEFR | NFR | N22000087 | 9-2006 | 12/2024 | N.A. | 9/2025 | 2650 | 2132.03 | 4412.25 | 3787.25 | 90
April 2025 |  |  | 207 | SAKRI-HASANPUR ROAD (NL) | ECR | N22000171 | 4-1999 | (N.A.) | {3/2027} |  | 325 | 735.2 | 735.2 | 602.01 | 78
April 2025 |  |  | 208 | ARARIA-SUPAUL (NL) | ECR | N22000177 | 4-2008 | 3/2024 | N.A. | 5/2025 | 1605.17 | 1605.17 | 1605.17 | 1654.14 | 65
April 2025 |  |  | 209 | JAYNAGAR-BIJALPURA INCLUDING EXTENSION BIJALPURA-BARDIBAS(NEPAL) GC | ECR | N22000181 | 4-2009 | 3/2022 | N.A. | 3/2026 | 819 | 548 | 783.83 | 544.31 | 75
April 2025 |  |  | 210 | SAMASTIPUR-DARBANGHA | ECR | N22000329 | 5-2015 | 3/2025 | N.A. | 10/2025 | 519.33 | 519.33 | 519.33 | 626.71 | 80
April 2025 |  |  | 211 | KIUL - GAYA DOUBLING PROJECT | ECR | N22000349 | 12-2015 | 9/2024 | N.A. | 2/2025 | 2462.11 | 1200.2 | 1771.07 | 1833.59 | 99
April 2025 |  |  | 212 | RAMPUR DUMRA - TAL - RAJENDRAPUL DOUBLING INCLUDING GANGA BRIDGE | ECR | N22000350 | 12-2015 | 12/2024 | N.A. | 12/2025 | 2373.64 | 1491.47 | 1600 | 1763.21 | 77
April 2025 |  |  | 213 | SAGAULI VALMIKINAGAR DOUBLING 109.7 KM | ECR | N22000472 | 4-2016 | 12/2024 | N.A. | 6/2025 | 1215.54 | 1215.54 | 1215.54 | 1556.04 | 90
April 2025 |  |  | 214 | MUZAFFARPUR SAGAULI DOUBLING 100.60 KM | ECR | N22000473 | 4-2016 | 6/2024 | N.A. | 5/2025 | 1586.22 | 1185.73 | 1300 | 1470.35 | 96
April 2025 |  |  | 215 | FATUHA-ISLAMPUR INCL. MM FOR EXTENSION OF NEW LINE FORM BIHARSHARIF-BARBIGHA, DANIYAWAN-BIHARSHARIF, | ECR | N22000476 | 4-1991 | 3/2023 | N.A. | 5/2025 | 1473.3 | 803.09 | 2722.16 | 2764.98 | 90
April 2025 |  |  | 216 | DARBHANGA - BYPASS LINE CONNECTING SHISHO HALT AND KAKARGHATI EXCL DARBHANGA YARD (7.64 KM) | ECR | N22000523 | 6-2019 | 6/2025 | N.A. | 10/2024 | 983.62 | 253.23 | 415 | 417.57 | 100
April 2025 |  |  | 217 | BARAUNI- BACHWARA 3RD AND 4TH LINE | ECR | N22000524 | 7-2022 | 7/2027 | N.A. | 12/2025 | 486 |  | 486 | 123.91 | 33
April 2025 |  |  | 218 | JHAJHA - BATIA (UMBRELLA WORK PB#23/2018-19/NR) | ECR | N22000526 | 2-2019 | 6/2028 | N.A. | 12/2026 | 496.47 |  | 496.47 | 22.53 | -
April 2025 |  |  | 219 | SONENAGAR BYE PASS LINE FROM CHIRALAPOTHU TO BAGHA BISHUNPUR | ECR | N22000528 | 10-2022 | 10/2027 | N.A. | 12/2026 | 234 | 223.69 | 223.69 | 22.57 | -
April 2025 |  |  | 220 | KATIHAR-KUMEDPUR AND KATIHAR-MUKURIA (64.5 KM) (UMBRELLA WORK PB#57/2019- 20/NR) | NFR | N22000570 | 8-2022 | 8/2027 | N.A. | 8/2026 | 745 |  | 942.64 | 280.1 | 25
April 2025 |  |  | 221 | PATNA-MUZZAFFARPUR | NHAI | N24000165 | 8-2010 | 2/2013 | N.A. | 12/2024 | 671.3 |  | 671.3 | 1830.13 | 97.78
April 2025 |  |  | 222 | 4-LANNING OF CHAPRA- HAJIPUR | NHAI | N24000187 | 1-2011 | 7/2013 | 6/2025 | 6/2025 | 575 |  | 575 | 573.48 | 89.81
April 2025 |  |  | 223 | REHABILITATION AND UPGRADING TO 2 LANES/2 LANE WITH PAVED SHOULDERS CONFIGURATION OF BIRPUR - BIHPUR | MoRTH | N24000382 | 1-2014 | 10/2019 | 6/2025 | 6/2025 | 675 |  | 780.77 | 764.69 | 96.13
April 2025 |  |  | 224 | FOUR OF SIMARIA - KHAGARIA SECTION OF NH-31 | NHAI | N24000480 | 12-2015 | 4/2019 | 3/2025 | 7/2025 | 1041.1 | 567 | 639.58 | 553.73 | 97.58
April 2025 |  |  | 225 | FOUR LANING OF BAKHTIYARPUR - MOKAMA SECTION OF NH-31 | NHAI | N24000507 | 12-2015 | 12/2019 | N.A. | 12/2024 | 1167.45 |  | 1182.94 | 735.99 | 96
April 2025 |  |  | 226 | REHABILITATION AND UPGRADING TO 2 LANES/2 LANE WITH PAVED SHOULDERS (KM 40 TO KM 219.945) OF NH-104 | MoRTH | N24000531 | 2-2016 | 11/2018 | N.A. | 5/2025 | 319.68 |  | 503.28 | 453 | 98.8
April 2025 |  |  | 227 | CONSTRUCTION OF REHABILITATION AND UPGRADING TO 2 LANES/2 LANE(FOR LOT-I-KM 40.00 TO KM 65.400 AND K | MoRTH | N24000576 | 2-2016 | 5/2016 | N.A. | 5/2025 | 178.85 |  | 278.54 | 232.61 | 98.35
April 2025 |  |  | 228 | PROCUREMENT, AND CONSTRUCTION OF REHABILITATION AND UPGRADING TO 2 LANES/2 LANE(FOR LOT-III-KM 156.5 | MoRTH | N24000578 | 2-2016 | 5/2016 | N.A. | 5/2025 | 553.3 |  | 706.39 | 712.38 | 98
April 2025 |  |  | 229 | FOUR LANING OF GAYA-HISUA- RAJGIRI-NALANDA- BIHARSHARIF SECTION (KM0.00 TO 92.935) ON NH-82 IN BIHAR | MoRTH | N24000579 | 1-2014 | 10/2016 | 6/2025 | 6/2025 | 1408.85 |  | 2138.16 | 1738.55 | 96.95
April 2025 |  |  | 230 | TWO-LANNING WITH PAVED SHOULDER OF MAHSHKUNT- SAHARSA-PURNEA SECTION FROM EXISTING KM.89.020 (DESIGN | NHAI | N24000665 | 3-2017 | 3/2020 | 12/2025 | 12/2025 | 672.89 | 736.01 | 830.31 | 678.03 | 85.27
April 2025 |  |  | 231 | SIX LANNING OF AUNTA- SIMARIA(GANGA BRIDGE WITH APPROACH ROADS) SECTION OF NH-31 | NHAI | N24000696 | 8-2017 | 2/2022 | 10/2024 | 5/2025 | 950.64 | 1161 | 1168.33 | 1126.75 | 97.05
April 2025 |  |  | 232 | CONSTRUCTION OF NEW LINK (NH-133B) FROM KM 0/00 (KM 200/87 OF SAHIBANJ BYPASS) IN JHARKHAND TO KM 15 | NHAI | N24000714 | 12-2017 | 10/2024 | 4/2025 | 12/2026 | 2598 |  | 1978.01 | 1381.14 | 76.76
April 2025 |  |  | 233 | REHABILITATION AND UPGRADATION OF TWO LANING OF MAHESHKHUNT - SAHARSA - PURNEA SECTION PKG - I | NHAI | N24000723 | 1-2018 | 12/2021 | 12/2024 | 8/2025 | 573.7 | 644.5 | 726.99 | 492.33 | 81.84
April 2025 |  |  | 234 | DEVELOPMENT OF NEWLY DECLARED NH-527C FROM MAJHAULI TO CHAROUT SECTION TO 2 LANE WITH PAVED SHOULDER | NHAI | N24000813 | 3-2018 | 11/2021 | 12/2024 | 5/2025 | 496.2 | 470.18 | 470.18 | 399.41 | 98.25
April 2025 |  |  | 235 | CONSTRUCTION OF A NEW 4 LANE MAJOR BRIDGE ACROSS RIVER KOSI AT PHULAUT INCLUDING RHABILITATION AND | MoRTH | N24000943 | 9-2018 | 6/2024 | 5/2026 | 5/2026 | 1478.4 |  | 1478.4 | 941.27 | 69.88
April 2025 |  |  | 236 | CONSTRUCTION OF A NEW 4 LANE BRIDGE PARALLEL TO EXISTING MG SETU WITH ITS APPROACHES FROM KM 0.00 | MoRTH | N24001201 | 2-2019 | 9/2024 | N.A. | 9/2026 | 2926.42 |  | 2926.42 | 1300.42 | 56.27
April 2025 |  |  | 237 | BALANCE WORK OF 4- LANING OF PATNA-GAYA-DOBHI SECTION (KM. 0.00 TO KM. 127.217) OF NH-83 IN THE STAT | NHAI | N24001303 | 10-2013 | 12/2020 | 12/2024 | 12/2024 | 649.9 |  | 750 | 711.53 | 98.3
April 2025 |  |  | 238 | BALANCE WORK OF 4- LANING OF PATNA-GAYA-DOBHI SECTION (KM. 39.00 TO KM. 83.00) OF NH-83 IN THE STATE | NHAI | N24001304 | 10-2013 | 11/2020 | 12/2024 | 12/2024 | 446.97 | 598.48 | 740.5 | 638.8 | 96.3
April 2025 |  |  | 239 | BALANCE WORK OF 4- L ANING OF PATNA-GAYA-DOBHI SECTION (KM.83.00 TO KM. 127.217) OF NH-83 IN THE STA | NHAI | N24001305 | 10-2013 | 11/2020 | 12/2024 | 12/2024 | 464.09 | 605.53 | 765.12 | 698.25 | 97.3
April 2025 |  |  | 240 | CONSTRUCTION OF 2 LANE BRIDGE ACROSS RIVER KOSI WITH APPROACH ROAD FROM BHEJA TO BAKAUR SECTION OF N | NHAI | N24001371 | 10-2019 | 8/2023 | 12/2025 | 12/2025 | 1101.99 |  | 1101.99 | 854.9 | 75.92
April 2025 |  |  | 241 | 4L GREENFIELD ALIGNMENT FROM KALYANAPUR TO TAL DASHRAHA OF NH-119D (PKG-III) | NHAI | N24001697 | 2-2023 | 2/2025 | N.A. | 12/2025 | 1358 |  | 1358 | 183.47 | 13.51
April 2025 |  |  | 242 | FOUR LANING OF MUNGER TO MIRZACHAUKI (NH-80) SECTION FROM NEAR RASULPUR TO MIRZACHAUKI (DESIGN CH | NHAI | N24001698 | 8-2022 | 8/2024 | 9/2025 | 9/2025 | 1198.02 |  | 1198.02 | 14.85 | -
April 2025 |  |  | 243 | CONSTRUCTION OF 4 LANE ELEVATED SECTION AND AT- GRADE IMPROVEMENTS AT BEGUSARAI TOWN SECTION OF NH-3 | NHAI | N24001699 | 3-2022 | 12/2024 | N.A. | 12/2025 | 312.58 |  | 312.58 | 189.18 | 78.29
April 2025 |  |  | 244 | SIX LANNING OF AURANGABAD TO BIHAR/JHARKHAND BORDER SECTION OF NH-19 (OLD NH-2) FROM KM. 209.827 TO | NHAI | N24001700 | 12-2021 | 3/2024 | 12/2024 | 12/2024 | 552.55 | 553 | 553 | 414.79 | 74.39
April 2025 |  |  | 245 | FOUR LANING OF MUNGER TO MIRZACHAUKI (NH-80) SECTION FROM START OF EXISTING BHAGALPUR BYPASS TO RASU | NHAI | N24001701 | 4-2022 | 4/2024 | 9/2025 | 9/2025 | 1769.5 |  | 1769.5 | 3.12 | -
April 2025 |  |  | 246 | CONSTRUCTION OF 4 LANE ELEVATED HIGHWAY AND AT- GRADE IMPROVEMENTS AT GOPALGANJ TOWN FROM DESIGN CH: | NHAI | N24001702 | 12-2021 | 9/2024 | N.A. | 5/2025 | 184.9 | 185 | 185 | 163.01 | 97.42
April 2025 |  |  | 247 | 6 L OF AURANGABAD TO BIHAR- JHARKHAND BORDER (CHORDAHA) SECTION FROM KM. 180.000 TO KM. 209.827 OF N | NHAI | N24001703 | 2-2022 | 5/2025 | N.A. | 5/2025 | 786.81 | 787 | 787 | 0 | 3.04
April 2025 |  |  | 248 | FOUR LANING OF MUNGER TO MIRZACHAUKI (NH-80) SECTION FROM KHARIA VILLAGE JUNCTION TO START OF EXISTI | NHAI | N24001704 | 3-2021 | 3/2024 | 9/2025 | 9/2025 | 1020.84 |  | 1020.84 | 120.84 | -
April 2025 |  |  | 249 | FOUR LANING OF MUNGER TO MIRZACHAUKI (NH-80) SECTION FROM MUNGER TO KHARIA VILLAGE JUNCTION DESIGN C | NHAI | N24001705 | 3-2022 | 3/2024 | 12/2025 | 12/2025 | 1485.66 |  | 1485.66 | 0 | -
April 2025 |  |  | 250 | BAKHTIYARPUR RAJAULI PKG-III FROM KM 101.630 TO KM 152.520 NH20 | NHAI | N24001708 | 9-2020 | 6/2024 | N.A. | 12/2024 | 2156.22 |  | 2156.22 | 2134.67 | 98.23
April 2025 |  |  | 251 | BAKHTIYARPUR RAJAULI PKG-II FROM KM 54.405 TO KM 101.630 NH20 | NHAI | N24001709 | 9-2020 | 4/2023 | 12/2024 | 12/2024 | 897.45 |  | 1090 | 1037.63 | 97.85
April 2025 |  |  | 252 | 6L OF KANHAULI RAMNAGAR PATNA RING ROAD PKG I FROM KM 0.000 TO KM 39.160 OF SH78 NEW NH131G | NHAI | N24001711 | 9-2020 | 3/2023 | 12/2024 | 12/2024 | 939.43 |  | 939.43 | 370.62 | 100
April 2025 |  |  | 253 | FOUR LANING OF PARARIA TO MOHANIA SECTION OF NH 319 (OLD NH 30) FROM KM. 54+530 (DESIGN CHAINAGE) TO | NHAI | N24001712 | 8-2020 | 7/2023 | 5/2025 | 5/2025 | 690 |  | 690 | 770.73 | 98.8
April 2025 |  |  | 254 | BALANCE WORK OF TWO LANING WITH PAVED SHOULDER OF PIPRAKOTHI?MOTIHARI- RAXAUL SECTION OF NH-28A FRO | NHAI | N24001715 | 12-2018 | 10/2020 | N.A. | 1/2024 | 333.6 | 466.59 | 461.41 | 460.38 | 100
April 2025 |  |  | 255 | IMPROVEMENT TO TWO LANE WITH PAVED SHOULDERS OF NH 122B FROM KM 29.730 TO KM 72.348 IN STATE OF BIH | MoRTH | N24001870 | 2-2022 | 11/2024 | N.A. | 11/2025 | 624.43 |  | 624.43 | 280.98 | 82
April 2025 |  |  | 256 | WIDENING AND STRENTHENING FROM KM 70.15 TO KM 121.025 OF NH-80 | MoRTH | N24001875 | 3-2021 | 1/2025 | N.A. | 6/2025 | 477.54 |  | 477.54 | 334.36 | 89.73
April 2025 |  |  | 257 | WIDENING and STRENTHENING FROM KM132.895 TO KM 190.15 NH-80 | MoRTH | N24001876 | 3-2021 | 3/2024 | N.A. | 9/2025 | 566.15 |  | 566.15 | 239.2 | 56.12
April 2025 |  |  | 258 | CONSTRUCTION OF NEW 4- LANE BRIDGE (PARALLEL TO EXISTING VIKRAMASHILA SETU)FROM KM 8+920 TO KM 13+375 | MoRTH | N24001877 | 7-2020 | 5/2027 | N.A. | 5/2027 | 1110.23 |  | 1110.23 | 425.49 | 40.12
April 2025 |  |  | 259 | IMPROVEMENT TO TWO LANE WITH PAVED SHOULDERS OF NH-319A FROM KM 0 TO KM 45 IN STATE OF BIHAR UNDER | MoRTH | N24001878 | 2-2022 | 12/2024 | N.A. | 7/2025 | 427.29 |  | 427.29 | 197.04 | 78
April 2025 |  |  | 260 | CONSTRUCTION OF PROPOSED 4_LANE REVELGUNJ BYPASS NH- 19 IN THE STATE OF BIHAR ON EPC MODE CONNECTING | MoRTH | N24001879 | 3-2022 | 7/2025 | N.A. | 7/2025 | 295.24 |  | 295.24 | 77.05 | 53.46
April 2025 |  |  | 261 | CONSTRUCTION OF 6- LANE BRIDGE AND ITS APPROACHES ACROSS RIVER GANGA AS PART OF PATNA RING ROAD (NH- | NHAI | N24002062 | 3-2023 | 9/2027 | N.A. | 9/2027 | 3012.27 |  | 3012.27 | 215.85 | 8.1
April 2025 |  |  | 262 | BALANCE WORK - WB-10 (GANDAK BRIDGE) KM 402.00 TO KM 440.00 (DEVANPUR - KOTWA) | NHAI | N24002063 | 12-2021 | 1/2024 | N.A. | 6/2025 | 210.05 |  | 210.05 | 104.35 | 69
April 2025 |  |  | 263 | PERMANENT RECTIFICATION OF 3 NOS. OF BLACK SPOTS IN PROJECT HIGHWAY NH-27 OF U.P BORDER - DEWAPUR - | NHAI | N24002064 | 12-2022 | 12/2025 | N.A. | 12/2025 | 381.8 |  | 381.8 | 115.3 | 43
April 2025 |  |  | 264 | 4L GREENFIELD ALIGNMENT OF AMAS TO SHIVRAMPUR FROM 0.000 KM. TO 55.002 KM. OF NH 119 D (PKG-I) | NHAI | N24002065 | 2-2022 | 3/2025 | N.A. | 3/2025 | 1390.92 |  | 1390.92 | 150.71 | 20.76
April 2025 |  |  | 265 | 4L GREENFIELD ALIGNMENT OF SHIVRAMPUR TO RAMNAGAR FROM KM. 55.002 TO KM. 109.300 OF NH 119 D (PKG-I | NHAI | N24002066 | 2-2022 | 7/2025 | N.A. | 7/2025 | 1494.31 |  | 1494.31 | 38.28 | 4.59
April 2025 |  |  | 266 | IMPROVEMENT OF 2 LANE WITH PAVED SHOULDER OF STRETCH FROM BIKRAMGANJ DAWATH MELAYABAGH NAWANAGR -DUM | MoRTH | N24002133 | 3-2021 | 3/2025 | N.A. | 6/2025 | 178.63 |  | 178.63 | 116.16 | 90.61
April 2025 |  |  | 267 | CONSTRUCTION OF 4 LANE ROB AND ITS APPROACHES AT THE LEVEL OF CROSSING (L C NO. 29-B) OF KM 29 (EKAN | MoRTH | N24002193 | 3-2023 | 7/2026 | N.A. | 7/2026 | 201.08 |  | 201.08 | 23.73 | 24
April 2025 |  |  | 268 | CONSTRUCTION OF 6-LANE ELEVATED / EXTRA DOSE CABLE BRIDGE ON RIVER GANGA PARALLEL TO AND WESTERN SID | MoRTH | N24002194 | 1-2024 | 11/2027 | N.A. | 11/2027 | 3064.45 |  | 3064.45 | 78.87 | 2.4
April 2025 |  |  | 269 | ESTIMATE FOR IMPROVEMENT TO TWO LANE WITH PAVED SHOULDER FROM RAMNAGAR TO ROSEDA FROM (KM 3.500 TO 4 | MoRTH | N24002195 | 1-2022 | 4/2026 | N.A. | 4/2026 | 495.16 |  | 495.16 | 129.17 | 9.5
April 2025 |  |  | 270 | CONSTRUCTION OF BHABHUA BYPASS FROM CH. 10+800(DESIGN CH. 10+800) TO CH. 19+860 (DESIGN CH. 18+150) | MoRTH | N24002196 | 2-2022 | 3/2026 | N.A. | 7/2026 | 179.86 |  | 179.86 | 25.07 | 0.03
April 2025 |  |  | 271 | IMPROVEMENT TO TWO LANE WITH PAVED SHOULDER FROM JUNCTION OF NH-22 NEAR HAJIPUR TO JUNCTION OF NH-12 | MoRTH | N24002197 | 2-2024 | 2/2026 | N.A. | 2/2026 | 226.15 |  | 226.15 | 9.77 | 13
April 2025 |  |  | 272 | IMPROVEMENT TO TWO LANE WITH PAVED SHOULDERS OF BH/WBBORDER-AMDABAD- MANIHARI SECTION FROM DESIGN KM | MoRTH | N24002198 | 1-2022 | 3/2026 | N.A. | 3/2026 | 353.27 |  | 353.27 | 25.33 | -
April 2025 |  |  | 273 | PERMANENT RECTIFICATION OF 4 NOS. OF BLACKSPOTS ON NH 27 OF KOTWA MEHSI MUZAFFARPUR SECTION FROM | NHAI | N24002220 | 12-2022 | 11/2026 | N.A. | 11/2026 | 410.75 |  | 410.75 | 34.83 | 21.04
April 2025 |  |  | 274 | 4L OF GREENFIELD ALIGNMENT FROM KM. 47.000 TO KM. 89.210 OF BALBHADARPUR TO BELA NAWDA SECTION OF NH | NHAI | N24002221 | 2-2022 | 3/2026 | N.A. | 3/2026 | 2185.75 |  | 2185.75 | 513.47 | 10.57
April 2025 |  | URBAN DEVELOPMENT | 275 | PATNA METRO RAIL CORPORATION LIMITED | PATNA METRO RAI | N28000148 | 2-2019 | 6/2024 | N.A. | 9/2024 | 13365.77 |  | 13925.5 | 3158.18 | 44.03
April 2025 |  | URBAN DEVELOPMENT | 276 | SEWER NETWORK SPS AND STP BEGUSARAI | BUIDCO | N30000026 | 3-2018 | 7/2021 | 12/2019 | 4/2025 | 230.06 |  | 230.06 | 261.47 | 97
April 2025 |  |  | 277 | I AND D AND STP WORKS FOR BHAGALPUR | BUIDCO | N30000027 | 10-2017 | 9/2020 | 11/2020 | 4/2025 | 254.13 | 413.29 | 413.29 | 123.1 | 90
April 2025 |  |  | 278 | SEWER NETWORKS SPS AND STP HAJIPUR | BUIDCO | N30000035 | 3-2018 | 8/2021 | 3/2018 | 6/2025 | 305.19 |  | 305.19 | 346.46 | 95
April 2025 |  |  | 279 | SEWER NETWORKS, SPS AND STP, MUNGER | BUIDCO | N30000036 | 3-2018 | 10/2021 | 3/2018 | 6/2024 | 294.02 | 350.79 | 522.85 | 428.7 | 100
April 2025 |  |  | 280 | SAIDPUR SEWER NETWORK PATNA | BUIDCO | N30000039 | 4-2015 | 1/2021 | N.A. | 6/2022 | 268.63 |  | 493.85 | 491.13 | 100
April 2025 |  |  | 281 | SEWERAGE SYSTEM WITH SEWER NETWORK PATNA KARMALICHAK | BUIDCO | N30000044 | 3-2017 | 5/2021 | 3/2017 | 2/2023 | 277.42 | 253.98 | 277.42 | 355.31 | 100
April 2025 |  |  | 282 | SEWERAGE SYSTEM AND STP FOR KANKARBAG ZONE PATNA | BUIDCO | N30000050 | 8-2017 | 6/2022 | N.A. | 12/2025 | 578.89 | 453.83 | 578.89 | 164.87 | 52
April 2025 |  |  | 283 | SEWERAGE SYSTEM AND STP FOR DIGHA ZONE, PATNA | BUIDCO | N30000051 | 8-2017 | 6/2022 | N.A. | 12/2025 | 824 | 734.09 | 824 | 384.17 | 55
April 2025 | CHHATTISGARH |  | 284 | GEVRA EXPANSION OCP (SECL) (35-70) MTY | SECL | 060100093 | 6-2010 | 3/2023 | 3/2026 | 3/2026 | 11816.4 |  | 11816.4 | 6584.29 | 77.2
April 2025 |  |  | 285 | PELMA OCP(15.00MTY) | SECL | N06000045 | 10-2022 | 3/2023 | N.A. | 3/2033 | 1624.59 |  | 1725.04 | 15.52 | 17
April 2025 |  |  | 286 | CHHAL OC SEAM -III (6.00 MTY) | SECL | N06000104 | 12-2013 | 3/2022 | 6/2025 | 6/2025 | 610.63 |  | 610.63 | 576.41 | 85
April 2025 |  |  | 287 | AMERA OC RCE | SECL | N06000123 | 2-2015 | 3/2018 | 3/2026 | 3/2026 | 335.97 |  | 335.97 | 86.98 | 42
April 2025 |  |  | 288 | AMGAON OPENCAST PROJECT RCE | SECL | N06000135 | 7-2015 | 3/2020 | 3/2026 | 3/2026 | 316.1 |  | 316.1 | 188.33 | 71
April 2025 |  |  | 289 | MAHAMAYA OPENCAST PROJECT | SECL | N06000164 | 5-2018 | 3/2026 | N.A. | 3/2026 | 410.26 |  | 410.26 | 180.18 | 38
April 2025 |  |  | 290 | JHIRIA WEST OPENCAST PROJECT | SECL | N06000166 | 1-2024 | 3/2029 | N.A. | 3/2029 | 366.94 |  | 366.94 | 33.37 | 41
April 2025 |  |  | 291 | BAROUD OC EXPANSION (3-10 MTY) | SECL | N06000197 | 8-2020 | 3/2029 | N.A. | 3/2029 | 2309.8 |  | 2309.8 | 904.69 | 41
April 2025 |  |  | 292 | JAMPALI OCP RCE | SECL | N06000198 | 5-2020 | 3/2024 | 3/2025 | 6/2025 | 278.64 |  | 278.64 | 208.65 | 82
April 2025 |  |  | 293 | PORDA CHIMTAPANI OCP (10 MTY) | SECL | N06000199 | 12-2020 | 3/2029 | N.A. | 3/2029 | 2310.12 |  | 2310.12 | 46.52 | 10
April 2025 |  |  | 294 | DIPKA OC EXPANSION 40 MTY | SECL | N06000200 | 12-2020 | 3/2029 | N.A. | 3/2029 | 5241.4 |  | 5241.4 | 2800.26 | 37.3
April 2025 |  |  | 295 | JAGANNATHPUR OC RCE (3.0 MTY) | SECL | N06000232 | 7-2016 | 3/2020 | 3/2026 | 3/2026 | 459.49 |  | 459.49 | 263.63 | 92
April 2025 |  |  | 296 | KATKONA RO UG PROJECT (1.74 MTY) | SECL | N06000274 | 1-2023 | 3/2029 | N.A. | 3/2029 | 329.22 |  | 329.22 | 60.38 | 2
April 2025 |  | DEPARTMENT OF HIGHER EDUCATION | 297 | C/O PERMANENT CAMPUS OF IIT BHILAI AT KUTHELABHATA, DURG CHHATTISGARH, STAGE I PHASE I. | CPWD EDUCATION | N28000141 | 3-2020 | 7/2022 | 2/2024 | 3/2024 | 808.62 | 879.22 | 808.62 | 640.7 | 100
April 2025 |  | POWER | 298 | WESTERN REGION EXPANSION SCHEME XXV | PGCIL | N18000350 | 2-2023 | 11/2023 | N.A. | 6/2025 | 385.84 |  | 385.84 | 258.71 | 91
April 2025 |  | POWER | 299 | LARA SUPER THERMAL POWER PROJECT, STAGE-II (2X800 MW) | NTPC | N18000381 | 8-2023 | 6/2028 | N.A. | 6/2028 | 15530 |  | 15530 | 1636.45 | 6.5
April 2025 |  | POWER | 300 | KIRANDUL - JAGDALPUR DOUBLING | ECOR | N22000318 | 12-2012 | 3/2020 | N.A. | 3/2024 | 1588.7 |  | 1553.11 | 1515.71 | 94.5
April 2025 |  | POWER | 301 | JHARSUGUDA-BILASPUR 4TH LINE | SECR | N22000484 | 4-2015 | 10/2024 | 12/2023 | 12/2025 | 2140.34 | 2135.34 | 2135.34 | 2264.16 | 88
April 2025 |  | POWER | 302 | KHARSIA DHARAMJAIGARH WITH SPUR LINE EAST CORRIDOR-PHASE I | IRCON | N22000489 | 4-2013 | 9/2018 | N.A. | 3/2026 | 3055 |  | 3438.39 | 3112.73 | 92.6
April 2025 |  |  | 303 | Gauge conversion of Raipur(Kendri)- Dhamtari and Abhanpur-Rajim branch (67.20 km) | SECR | N22000572 | 7-2011 | 10/2024 | N.A. | 6/2025 | 1171.3 |  | 1171.3 | 573.1 | 82
April 2025 |  |  | 304 | NIPANIA-BHATAPRA (14.4 KM) 4TH LINE (PB#72/NR/2022-23) | SECR | N22000573 | 9-2022 | 12/2026 | N.A. | 12/2026 | 170.49 |  | 170.49 | 0.13 | 2
April 2025 |  |  | 305 | 4TH LINE - BHATAPARA- HATHBAND (8.8 KM) | PB#72/NR/2022-23 | SECR | 12-2022 | 12/2026 | N.A. | 12/2026 | 177.03 |  | 177.03 | 6.23 | 2
April 2025 |  |  | 306 | 4TH LINE - BHILAI-BHILAI NAGAR | 8.8 KM) (PB#72/NR/2022-23 | SECR | 9-2022 | 9/2026 | N.A. | 9/2026 | 169.06 |  | 177.34 | 1.72 | 2
April 2025 |  |  | 307 | 4TH LINE - DADHAPARA-BELHA | 9.2 KM) (PB#72/NR/2022-23 | SECR | 9-2022 | 9/2026 | N.A. | 9/2026 | 169.06 |  | 169.06 | 15.05 | 30
April 2025 |  |  | 308 | 4TH LINE - RAJNANDGAON- DONGARHGARH (31.2 KM) | PB#72/NR/2022-23 | SECR | 9-2022 | 9/2026 | N.A. | 9/2026 | 328.34 |  | 328.34 | 13.35 | 20
April 2025 |  |  | 309 | 3RD AND 4TH LINE - SARAGBUNDIA AND MADWARANI | SECR | N22000579 | 9-2022 | 9/2026 | N.A. | 9/2026 | 167.64 |  | 167.64 | 0 | -
April 2025 |  |  | 310 | DOUBLING OF BORIDAND - AMBIKAPUR ( SURAJPUR) | SECR | N22000580 | 6-2022 | 6/2030 | N.A. | 3/2027 | 1376.2 | 1242.94 | 1242.94 | 158.88 | 12
April 2025 |  |  | 311 | DALLIRAJHARA - ROWGHAT (95 KM) {PART OF DALLIRAJHARA- JAGDALPUR (235 KM)} | RVNL | N22000602 | 3-2008 | 6/2025 | N.A. | 6/2025 | 1627.56 |  | 1627.56 | 1349.09 | -
April 2025 |  |  | 312 | CHIRIMIRI-NAGPUR HALT | SECR | N22000616 | 10-2018 | 6/2030 | N.A. | 6/2030 | 241 |  | 241 | 0 | -
April 2025 |  |  | 313 | REHABILITATION AND UPGRADATION OF NH 43 KANKER TO BEDMA SECTION KM. 130 TO 180 | MoRTH | N24001217 | 1-2016 | 8/2016 | N.A. | 6/2025 | 497.14 | 572.66 | 572.66 | 385.27 | 60.41
April 2025 |  |  | 314 | REHABILITATION AND UPGRADATION OF NH 78 FROM KM 373.505 TO 469.300 AMBIKAPUR TO PATHALGAON SECTION | MoRTH | N24001221 | 1-2016 | 10/2016 | N.A. | 3/2025 | 624.98 |  | 731.5 | 620.67 | 100
April 2025 |  |  | 315 | REHABILITATION AND UPGRADATION OF NH 78 FROM KM 469.000 TO 531.000 PATTHALGAON TO KUNKURI | MoRTH | N24001222 | 3-2016 | 7/2016 | N.A. | 12/2025 | 452.94 |  | 435.61 | 322.59 | 69.99
April 2025 |  |  | 316 | CONSTRUCTION OF 4 NOS GRADE SEPARATOR BETWEEN KM. 281.000 TO KM 307.600 KM. 286.400 KUMHARI KM. 299. | MoRTH | N24001227 | 3-2018 | 1/2019 | N.A. | 5/2025 | 349.03 |  | 349.03 | 316.52 | 97.9
April 2025 |  |  | 317 | UPGRADATION AND WIDENING OF BILASPUR TO MUNGELI SECTION NH-130A | MoRTH | N24001228 | 11-2017 | 5/2019 | N.A. | 5/2025 | 188.8 |  | 188.8 | 136.81 | 97
April 2025 |  |  | 318 | DEVELOPMENT OF SIX LANE SARGI-BASANWAHI OF NH 130 CD FROM KM.42+800 TO 99+500 UNDER RAIPUR VISAKHAPA | NHAI | N24001588 | 12-2021 | 1/2025 | N.A. | 9/2025 | 1470.73 |  | 1470.73 | 646.79 | 76.62
April 2025 |  |  | 319 | DEVELOPMENT OF SIX LANE JHANKI SARGI OF NH 130 CD FROM KM.0+000 TO 42+800 UNDER RAIPUR VISAKHAPATTNA | NHAI | N24001593 | 11-2021 | 9/2024 | N.A. | 6/2025 | 1368.19 |  | 1368.19 | 896.51 | 96.12
April 2025 |  |  | 320 | 4 LANE OF BILASPUR TO URGA PROJECT (KM 0.00 TO KM 70.2) OF NH-130A | NHAI | N24001611 | 4-2020 | 3/2024 | N.A. | 9/2025 | 1855.59 | 2523.86 | 2523.86 | 683.34 | 91.78
April 2025 |  |  | 321 | UP GRADATION OF NH 930 SHERPAR TO KOHKA FROM KM 67.880 TO KM 114.860 TO TWO LANE WITH PAVED SHOULDER | MoRTH | N24001917 | 3-2020 | 5/2024 | N.A. | 6/2025 | 278.97 |  | 278.97 | 206.61 | 87.05
April 2025 |  |  | 322 | UP GRADATION OF NH 130C ABHANPUR TO PAUND FROM NK KM 0.000 TO KM. 40.380 TO TWO LANE WITH PAVED SHOU | MoRTH | N24001919 | 12-2020 | 9/2023 | 2/2025 | 6/2025 | 193.16 |  | 193.16 | 103.83 | 80.71
April 2025 |  |  | 323 | UPGRADATION OF NH 130A MUNGELI TO PONDI FROM NH KM. 51.600 TO KM. 77.870 KM. 80.970 TO 96.970 TO 2 | MoRTH | N24001920 | 3-2021 | 9/2024 | N.A. | 5/2025 | 218.57 |  | 218.57 | 136.26 | 88.71
April 2025 |  |  | 324 | DEVELOPMENT OF SIX LANE BASANWAHI-MARANGPURI OF NH 130 CD FROM KM.99+500 TO 124+661 UNDER RAIPUR VIS | NHAI | N24002017 | 3-2022 | 10/2025 | N.A. | 9/2026 | 1307.16 |  | 1307.16 | 199.96 | 30.33
April 2025 |  |  | 325 | CONSTRUCTION OF 6 LANE DURG RAIPUR ARANG BYPASS PKG 1 SECTION OF NH 53 FROM CH 0.000 TO CH 44.50 | NHAI | N24002045 | 6-2022 | 7/2025 | N.A. | 7/2025 | 1828 |  | 1828 | 499.83 | 39.85
April 2025 |  |  | 326 | CONSTRUCTION OF 6 LANE DURG RAIPUR ARANG BYPASS PKG 2 SECTION OF NH 53 FROM CH 44+500 TO CH.92+230 I | NHAI | N24002046 | 6-2022 | 5/2025 | N.A. | 5/2025 | 1958.94 | 1959 | 1958.94 | 659.49 | 35.58
April 2025 |  | STEEL | 327 | NMDC SLURRY PIPE LINE PROJECT - PHASE-1 | NMDC | N12000124 | 11-2015 | 6/2023 | 7/2024 | 12/2025 | 2907 | 5427.06 | 5427.06 | 2865.64 | 75.2
April 2025 |  | STEEL | 328 | SCREENING PLANT-III AT KIRANDUL | NMDC | N12000127 | 3-2021 | 8/2024 | N.A. | 1/2026 | 2092.97 | 2718.84 | 2718.84 | 1472.86 | 70.31
April 2025 |  | STEEL | 329 | CONSTRUCTION OF RESIDENTIAL TOWERS AT BIOM KIRANDUL COMPLEX | NMDC | N12000130 | 7-2021 | 11/2024 | N.A. | 12/2025 | 282.44 | 349.75 | 349.75 | 218.55 | 78
April 2025 |  | STEEL | 330 | REPLACEMENT OF CONVERTER VESSELS, TRUNNION RINGS, SUPPORT SYSTEM AND INSTALLATION OF SECONDARY EMISS | SAIL | N12000131 | 10-2023 | 6/2026 | N.A. | 6/2026 | 471.83 |  | 471.83 | 77.95 | 17.5
April 2025 |  | STEEL | 331 | REBUILDING OF COKE OVEN BATTERY NO.7 AND 8 OF BHILAI STEEL PLANT | SAIL | N12000134 | 11-2023 | 10/2025 | N.A. | 10/2025 | 884.1 |  | 884.1 | 352.17 | 66
April 2025 |  | STEEL | 332 | REPLACEMENT OF HOT LEVELLER-1 OF PLATE MILL AT BHILAI STEEL PLANT | SAIL | N12000137 | 7-2024 | 7/2026 | N.A. | 7/2026 | 198.62 |  | 198.62 | 0 | 4.55
April 2025 |  | URBAN DEVELOPMENT | 333 | CONSTRUCTION729 QUARTERS (TYPE II-180 TYPE III-364 TYPE IV- 112 TYPE V-68 TYPE-VI-5 SHOPS COMMUNI | CPWD | N28000149 | 5-2019 | 9/2020 | 10/2024 | 10/2024 | 299.97 | 299.97 | 299.97 | 272.05 | 90
April 2025 |  | CIVIL AVIATION | 334 | CONSTRUCTION OF COMBINED OPERATIONAL OFFICES FOR DGCA, BCAS, AAIB, AERA AND AAI AT SAFDARJUNG AIRPOR | AAI | N04000076 | 11-2016 | 4/2020 | 4/2024 | 4/2024 | 303.8 | 374.98 | 351.21 | 344.49 | 100
April 2025 |  | DPIIT | 335 | INDIA INTERNATIONAL CONVENTION AND EXPO CENTRE | IICC FOR DPIIT | N40000002 | 11-2017 | 12/2019 | N.A. | 12/2019 | 4773 |  | 5401 | 4969.89 | 99.74
April 2025 |  | FINANCE | 336 | C/O RESIDENTIAL COMPLEX BUILDING FOR CENTRAL BOARD OF INDIRECT TAXES AND CUSTOMS AT SECTOR-9, DWARKA | NPCC | N07000001 | 7-2018 | 4/2022 | N.A. | 4/2022 | 228.5 |  | 220.27 | 176.28 | 85
April 2025 |  | HOME AFFAIRS | 337 | ESTABLISHMENT OF CENTRAL ARMED POLICE FORCE INSTITUTE OF MEDICAL SCIENCES(CAPFIMS) AT NEW DELHI | CPWD FOR MHA | N28000071 | 10-2013 | 10/2019 | N.A. | 9/2024 | 1219.21 | 2091.53 | 2091.53 | 1947.12 | 100
April 2025 |  | HOME AFFAIRS | 338 | CONSTRUCTION OF HEADQUARTER BUILDING OF CRPF AT LODHI ROAD NEW DELHI | CPWD FOR MHA | N45000002 | 6-2019 | 7/2022 | N.A. | 9/2025 | 277.35 |  | 277.35 | 107 | 63
April 2025 |  | RAILWAYS | 339 | ANAND VIHAR-TILAK BRIDGE 3RD AND 4TH LINE | NR | N22000281 | 4-2012 | 3/2023 | N.A. | 6/2026 | 586.36 |  | 699 | 169.99 | 45
April 2025 |  | ROAD TRANSPORT AND HIGHWAYS | 340 | SIX LANE ACCESS CONTROLLED OF DELHI SAHARANPUR HIGHWAY FROM AKSHARDHAM NH 9 JUNCTION TO DELHI UP BOR | NHAI | N24001771 | 6-2020 | 12/2024 | N.A. | 12/2024 | 1479.22 |  | 1479.22 | 1491.26 | 99
April 2025 |  | ROAD TRANSPORT AND HIGHWAYS | 341 | 6L ACCESS CONTROLLED HIGHWAY FROM DND MAHARANI BAGH JN. WITH JAITPUR PUSHTA ROAD OF NH 148NA FROM | NHAI | N24001773 | 5-2020 | 7/2024 | N.A. | 9/2025 | 1467.44 |  | 1942.89 | 1015.86 | 90.07
April 2025 |  | ROAD TRANSPORT AND HIGHWAYS | 342 | DEVELOPMENT OF 6L UER-II (PACKAGE-I) (NH-1 NEAR BAKOLI TILL KARALA KANJHAWALA ROAD) FROM KM. (-)0.70 | NHAI | N24001777 | 7-2020 | 10/2023 | N.A. | 6/2025 | 2171.8 |  | 2171.8 | 958.13 | 99.99
April 2025 |  | ROAD TRANSPORT AND HIGHWAYS | 343 | DWARKA EXPRESSWAY FROM KM -0.600 TO KM 5.300 - PKG-I (SHIVMURTI CHOWK-RUB NEAR DWARKA SECTOR 21) | NHAI | N24001779 | 3-2018 | 9/2022 | N.A. | 6/2025 | 2507 |  | 3030.73 | 1155.7 | 94.27
April 2025 |  | ROAD TRANSPORT AND HIGHWAYS | 344 | 8L OF DWARKA EXPRESSWAY PKG-II (RUB NEAR DWARKA SECTOR 21-DL/HR BORDER) FROM 5.300 KM.TO 9.500 KM. O | NHAI | N24001781 | 1-2018 | 10/2021 | N.A. | 5/2025 | 2067.67 |  | 2160 | 1496.49 | 99.3
April 2025 |  | ROAD TRANSPORT AND HIGHWAYS | 345 | DEVELOPMENT OF 6L UER II [PACKAGE - II] (KARALA KANJHAWALA ROAD TILL NANGLOI - NAJAFGARH ROAD) FROM | NHAI | N24001825 | 7-2020 | 10/2023 | N.A. | 6/2025 | 1894.96 |  | 1894.96 | 741.88 | 93.81
April 2025 |  | TELECOMMUNICATIONS | 346 | SETTING UP PHYSICAL INFRASTRUCTURE FOR THE NATIONAL INSTITUTE OF COMMUNICATION FINANCE(NICF) AT GHIT | CPWD FOR TELECO | N28000115 | 10-2014 | 3/2018 | N.A. | 10/2025 | 248.2 |  | 248.2 | 236.27 | 98
April 2025 |  | URBAN DEVELOPMENT | 347 | DELHI MRTS PHASE-III | DMRC | N28000056 | 9-2011 | 3/2016 | 8/2021 | 8/2021 | 38585 | 43095.35 | 40180.91 | 40602.26 | 100
April 2025 |  | URBAN DEVELOPMENT | 348 | REDEVELOPMENT OF GPRA COLONY AT NAUROJI NAGAR | NBCC | N28000105 | 7-2016 | (N.A.) | {10/2024} |  | 2694 |  | 2694 | 2247.61 | 98
April 2025 |  | URBAN DEVELOPMENT | 349 | REDEVELOPMENT OF GENERAL POOL RESIDENTIAL COLONY AT SRINIWASPURI NEW DELHI PHASE-I | CPWD | N28000128 | 10-2016 | 7/2021 | N.A. | 6/2024 | 1180 |  | 1100.8 | 36.69 | 2
April 2025 |  | URBAN DEVELOPMENT | 350 | REDEVELOPMENT OF GPRA AT KASTURBA NAGAR PHASE I | CPWD | N28000129 | 10-2016 | 3/2022 | N.A. | 6/2024 | 1128 |  | 1128 | 709.96 | 64
April 2025 |  | URBAN DEVELOPMENT | 351 | DELHI METRO PHASE IV THREE PRIORITY CORRIDORS | DMRC | N28000135 | 7-2019 | 3/2025 | N.A. | 3/2026 | 24948.65 |  | 24948.65 | 15744.3 | 64.58
April 2025 |  | URBAN DEVELOPMENT | 352 | CONSTRUCTION OF 184 MULTI STORIED FLATS FOR HON'BLE MPS AT BKS MARG, NEW DELHI | CPWD | N28000153 | 1-2022 | 11/2024 | 5/2025 | 5/2025 | 646.52 |  | 646.52 | 473.63 | 91
April 2025 |  | URBAN DEVELOPMENT | 353 | REDEVELOPMENT OF GPRA AT NETAJI NAGAR NEW DELHI PACKAGE 2 | NBCC | N28000156 | 10-2016 | 3/2024 | 6/2025 | 3/2025 | 1536.72 |  | 1536.72 | 481.85 | -
April 2025 |  | WATER RESOURCES | 354 | CONSTRUCTION OF 564 MLD 124 MGD WASTE WATER TREATMENT PLANT WITH EFFLUENT STANDARDS OF BOD ? 10MG/L | DJB | N30000014 | 3-2017 | 12/2022 | N.A. | 3/2025 | 665.78 |  | 665.78 | 782.51 | 100
April 2025 | GOA | CIVIL AVIATION | 355 | EXTENSION OF EXISTING INTEGRATED TERMINAL BUILDING AND ALLIED WORKS AT GOA AIRPORT. | AAI | N04000095 | 11-2017 | 9/2021 | 6/2025 | 6/2025 | 255.69 |  | 255.69 | 119.89 | 84
April 2025 | GOA | DEPARTMENT OF HIGHER EDUCATION | 356 | CONSTRUCTION OF PERMANENT CAMPUS FOR NATIONAL INSTITUTE OF TECHNOLOGY GOA AT CUNCOLIM, GOA. | CPWD EDUCATION | N42000002 | 5-2019 | 8/2021 | N.A. | 12/2024 | 303.9 |  | 390.4 | 360 | 99.3
April 2025 | GOA | ROAD TRANSPORT AND HIGHWAYS | 357 | CONSTRUCTION OF SIX LANE ELEVATED CORRIDOR FROM KM. 508.000 TO KM. 513.150 INCLUDING APPROACHES ON N | MoRTH | N24002181 | 4-2023 | 4/2026 | N.A. | 4/2026 | 641.46 |  | 641.46 | 0 | -
April 2025 | GOA | CIVIL AVIATION | 358 | C/O NEW GREENFIELD AIRPORT AT HISSAR, RAJKOT, GUJARAT | AAI | N04000088 | 1-2018 | 8/2022 | 12/2024 | 12/2024 | 1405 |  | 1405 | 1304.38 | 100
April 2025 | GOA | CIVIL AVIATION | 359 | EXTENSION OF TERMINAL BUILDING, PTT, APRON AND CAR PARK AT SURAT AIRPORT. | AAI | N04000093 | 8-2018 | 2/2021 | 3/2025 | 3/2025 | 353.25 |  | 353.25 | 348.77 | 100
April 2025 | GOA | CIVIL AVIATION | 360 | DEVELOPMENT OF NEW GREENFIELD AIRPORT AT DHOLERA, AHMEDABAD (GUJARAT). PHASE-1. | AAI | N04000099 | 6-2022 | 12/2025 | N.A. | 12/2025 | 1305 | 1143.95 | 1143.95 | 560.95 | 55
April 2025 | GOA | CIVIL AVIATION | 361 | REDEVELOPMENT OF SANTHAL FIELD | ONGC | N16000279 | 2-2017 | 3/2026 | N.A. | 3/2026 | 1162.56 |  | 1162.56 | 1156.2 | 93.6
April 2025 |  |  | 362 | ACRYLICS OR OXO-ALCOHOL PROJECT AT GUJARAT REFINERY | IOCL | N16000382 | 11-2019 | 5/2023 | 3/2024 | 5/2025 | 5251 | 5894 | 5894 | 4571.49 | 99.5
April 2025 |  |  | 363 | PETROCHEMICAL AND LUBE INTEGRATION PROJECT AT GUJARAT REFINERY | IOCL | N16000409 | 9-2020 | 8/2024 | 12/2025 | 12/2025 | 18936 |  | 18936 | 10618.86 | 81.1
April 2025 |  |  | 364 | AUGUMENTATION OF SALAYA MATHURA CRUDE OIL PIPELINE SYSTEM | IOCL | N16000411 | 10-2020 | 8/2023 | 6/2025 | 6/2025 | 1614 |  | 1614 | 1087.52 | 94.77
April 2025 |  |  | 365 | REDEVELOPMENT OF LINCH FIELD | ONGC | N16000428 | 4-2021 | 3/2025 | N.A. | 7/2025 | 631.03 | 860.04 | 860.04 | 385.12 | 65.9
April 2025 |  |  | 366 | REDEVELOPMENT OF SOBHASAN COMPLEX | ONGC | N16000431 | 8-2021 | 2/2026 | N.A. | 2/2026 | 885.63 | 1286.67 | 1286.67 | 547.42 | 69.4
April 2025 |  |  | 367 | COMMERCIAL POLYMER FLOODING PROJECT IN BECHRAJI FIELD | ONGC | N16000444 | 1-2022 | 11/2024 | N.A. | 11/2025 | 621.4 |  | 621.4 | 137.69 | 21.4
April 2025 |  |  | 368 | INSTALLATION OF NEW BITUMEN UNIT ALONG WITH ALLIED FACILITIES AT GUJARAT | IOCL | N16000454 | 1-2022 | 9/2024 | N.A. | 5/2025 | 328 |  | 328 | 74.19 | 44.5
April 2025 |  |  | 369 | RESTORATION OF GAS TERMINAL, PHASE-I (PART-A), HAZIRA PLANT | ONGC | N16000477 | 5-2022 | 2/2025 | N.A. | 9/2025 | 249.43 |  | 249.43 | 208.81 | 92
April 2025 |  |  | 370 | KALOL REDEVELOPMENT PROJECT | ONGC | N16000481 | 8-2022 | 3/2027 | N.A. | 3/2027 | 1487.41 |  | 1487.41 | 926.54 | 60
April 2025 |  |  | 371 | OLD PIPE LINE REPLACEMENT (OPRP) GROUP-A | ONGC | N16000483 | 7-2021 | 7/2025 | N.A. | 7/2025 | 173.03 |  | 169.84 | 140.4 | 84
April 2025 |  |  | 372 | REVAMPING OF SV STATIONS, GAS TERMINAL AND KRIBHCO TERMINAL | ONGC | N16000514 | 11-2022 | 8/2026 | N.A. | 8/2026 | 837.34 |  | 837.34 | 163.26 | 42.1
April 2025 |  |  | 373 | GUJARAT 200 MW (GUVNL TENDER) | NTPC | N18000295 | 1-2021 | 7/2022 | N.A. | 3/2026 | 842.27 |  | 842.27 | 769.66 | 30
April 2025 |  |  | 374 | 150 MW SOLAR PV PROJECT IN GUJARAT (LIMBDI, MESANKA AND RADHANPUR) | NTPC | N18000296 | 5-2021 | 9/2022 | N.A. | 4/2025 | 674.92 |  | 674.92 | 572.53 | 91
April 2025 |  |  | 375 | Bagodara Solar Power Project | SJVN | N18000297 | 5-2021 | 10/2022 | N.A. | 12/2025 | 339.35 |  | 339.35 | 317.31 | 51.22
April 2025 |  |  | 376 | DAYAPAR WIND ENERGY PROJECT 150MW | NTPC | N18000319 | 11-2021 | 5/2023 | N.A. | 5/2025 | 937.8 |  | 937.8 | 798.89 | 98
April 2025 |  |  | 377 | DAYAPAR WIND ENERGY PROJECT 200MW | NTPC | N18000345 | 7-2022 | 3/2025 | N.A. | 3/2026 | 1316.02 |  | 1316.02 | 324.35 | 23
April 2025 |  |  | 378 | KHAWDA 1255MW SOLAR PROJECT (KHAWDA SOLAR PARK) | NTPC | N18000346 | 9-2022 | 9/2024 | N.A. | 6/2025 | 7179.54 |  | 7179.54 | 4714.2 | 61
April 2025 |  |  | 379 | BHUJ SOLAR 300MW (TRANCHE- IV WIND SOLAR HYBRID) | NTPC | N18000349 | 11-2022 | 3/2024 | N.A. | 1/2026 | 1442.6 |  | 1442.6 | 793.54 | 2
April 2025 |  |  | 380 | ESTABLISHMENT OF KHAVDA POOLING STATION 3 (KPS3) IN KHAVDA RE PARK | PGCIL | N18000357 | 3-2023 | 12/2024 | N.A. | 5/2025 | 922.3 |  | 922.3 | 672.67 | 88.7
April 2025 |  |  | 381 | TRANSMISSION NETWORK EXPANSION IN GUJARAT ASSOCIATED WITH INTEGRATION OF RE PROJECTS FROM KHAVDA POT | PGCIL | N18000358 | 3-2023 | 3/2025 | N.A. | 6/2025 | 815.12 |  | 815.12 | 10.99 | 88
April 2025 |  |  | 382 | KHAVDA-2, GUJARAT- ESTABLISHMENT OF KHAVDA POOLING STATION-2 (KPS2) IN KHAVDA RE PARK | PGCIL | N18000359 | 3-2023 | 12/2024 | N.A. | 5/2025 | 966.79 |  | 966.79 | 646.22 | 93
April 2025 |  |  | 383 | KHAVDA PHASE-II-PART B, GUJARAT- TRANSMISSION SCHEME FOR EVACUATION OF 4.5 GW RE INJECTION AT KHAVDA | PGCIL | N18000360 | 3-2023 | 3/2025 | N.A. | 9/2025 | 1167.55 |  | 1167.55 | 712.14 | 83.7
April 2025 |  |  | 384 | KHAVDA PHASE-II-PART C, GUJARAT- TRANSMISSION SCHEME FOR EVACUATION OF 4.5 GW RE INJECTION AT KHAVDA | PGCIL | N18000361 | 3-2023 | 3/2025 | N.A. | 6/2025 | 2820.99 |  | 2820.99 | 2304.46 | 68
April 2025 |  |  | 385 | KHAVDA 1200MW (4X300MW) IN KHAVDA RE PARK | NTPC | N18000365 | 6-2023 | 12/2024 | N.A. | 2/2026 | 6283.81 |  | 6283.81 | 1731.91 | 16
April 2025 |  |  | 386 | DAYAPAR WIND- III (HYBRID TRANCHE-V) | NTPC | N18000366 | 5-2023 | 1/2025 | N.A. | 12/2025 | 1095.01 |  | 1095.01 | 345.08 | -
April 2025 |  |  | 387 | TS FOR EVACUATION OF POWER FROM POTENTIAL RE ZONE IN KHAVDA AREA OF GUJARAT UNDER PH-IV PART E3 | PGCIL | N18000383 | 7-2023 | 7/2025 | N.A. | 8/2025 | 334 |  | 334 | 0 | 15
April 2025 |  |  | 388 | TS FOR EVACUATION OF ADDITIONAL 7GW RE POWER FROM KHAVDA RE PARK UNDER PHASE-III PART B [VATAMAN TRA | PGCIL | N18000384 | 12-2023 | 12/2025 | N.A. | 6/2026 | 3752 |  | 3752 | 797.02 | 12
April 2025 |  |  | 389 | TS FOR EVACUATION OF POWER FROM 7GW REZ IN KHAVDA AREA UNDER PHASE-IV PART E2 | PGCIL | N18000390 | 5-2024 | 5/2026 | N.A. | 5/2026 | 679 |  | 679 | 0 | 12
April 2025 |  |  | 390 | AUGMENTATION OF TRANSFORMATION CAPACITY AT JAM KHAMBHALIYA PS [GIS] [SPV NAME POWERGRID JAM KHAMBHAL | PGCIL | N18000398 | 10-2024 | 7/2026 | N.A. | 7/2026 | 329 |  | 329 | 0 | 1
April 2025 |  |  | 391 | TRANSMISSION SYSTEM FOR EVACUATION OF POWER FROM POTENTIAL RENEWABLE ENERGY ZONE IN KHAVDA AREA OF G | PGCIL | N18000400 | 10-2024 | 10/2026 | N.A. | 10/2026 | 4766 |  | 4766 | 155 | 2.5
April 2025 |  |  | 392 | PROVISION OF DYNAMIC REACTIVE COMPENSATION AT KHAVDA POOLING STATION 1 [KPS1] AND KHAVDA POOLING STA | PGCIL | N18000402 | 11-2024 | 11/2026 | N.A. | 11/2026 | 501 |  | 501 | 0 | 1
April 2025 |  |  | 393 | TRANSMISSION SYSTEM FOR EVACUATION OF POWER FROM POTENTIAL RENEWABLE ENERGY ZONE IN KHAVDA AREA OF G | PGCIL | N18000405 | 11-2024 | 5/2029 | N.A. | 5/2029 | 24819 |  | 24819 | 1340 | 1
April 2025 |  |  | 394 | 600 MW SOLAR POWER PROJECT UNDER CPSU SCHEME | NHPC | N18000406 | 4-2022 | 3/2026 | N.A. | 3/2026 | 4100.45 |  | 4100.45 | 0.71 | 9
April 2025 |  |  | 395 | AUGMENTATION OF TRANSFORMATION CAPACITY AT KPS2 & KPS2 | PGCIL | N18000411 | 3-2025 | 3/2027 | N.A. | 3/2027 | 466 |  | 466 | 0 | -
April 2025 |  |  | 396 | AUGMENTATION OF BANASKANTHA (RAGHANESDA) PS (GIS) | PGCIL | N18000412 | 3-2025 | 3/2027 | N.A. | 3/2027 | 172 |  | 172 | 0 | -
April 2025 |  |  | 397 | MIYAGAM-KARJAN-DABHOI- SAMLAYA (GC) | WR | N22000142 | 4-2011 | 3/2021 | 10/2026 | 10/2026 | 844.1 | 844.1 | 844.1 | 597.62 | 41
April 2025 |  |  | 398 | ANAND GODHRA DOUBLING PROJECT 79 KMS | WR | N22000504 | 4-2017 | 12/2024 | 2/2025 | 2/2025 | 692.26 | 692.26 | 692.26 | 676.64 | 97
April 2025 |  |  | 399 | MEHSANA PALANPUR DOUBLING PROJECT 65.10 KMS | WR | N22000505 | 4-2018 | 3/2024 | 10/2024 | 10/2024 | 537.31 | 537.31 | 688.74 | 844.55 | 100
April 2025 |  |  | 400 | 4TH LINE BETWEEN BAREJADI NANDEJ (GERATPUR)- SANAND (38.20 KM) (AHMEDABAD BYPASS). | WR | N22000532 | 2-2023 | 3/2027 | 2/2027 | 2/2027 | 961.67 | 961.67 | 961.67 | 108.78 | 16
April 2025 |  |  | 401 | QUADRUPLING BETWEEN GANDHIDHAM - ADIPUR WITH Y CONNECTION AT ADIPUR FOR PROVIDING DIRECT ENTRY TOWAR | WR | N22000533 | 2-2023 | 12/2025 | 12/2025 | 12/2025 | 152.44 | 152.44 | 152.44 | 62.26 | 32
April 2025 |  |  | 402 | RAJKOT-KANALUS (111.20 KM) | WR | N22000535 | 10-2021 | 10/2026 | 3/2026 | 3/2026 | 1080.58 | 1080.58 | 1080.58 | 1337.86 | 65
April 2025 |  |  | 403 | HIMMATNAGAR-KHEDBRAHMA | 54.83 KM | WR | 6-2022 | 2/2030 | 6/2025 | 6/2025 | 354.99 | 482.42 | 482.42 | 834.53 | 84
April 2025 |  |  | 404 | PETLAD-BHADRAN (22.5 KM) | WR | N22000538 | 5-2022 | 5/2030 | 12/2025 | 12/2025 | 202.5 | 307.12 | 307.12 | 80.49 | 8
April 2025 |  |  | 405 | NADIAD-PETLAD (37.26 KM) | WR | N22000539 | 5-2022 | 6/2030 | N.A. | 12/2025 | 335.34 | 461.91 | 461.91 | 73.29 | 7
April 2025 |  |  | 406 | SAMLAYA-TIMBA ROAD (53.53 KM) | WR | N22000540 | 2-2023 | 3/2030 | 7/2026 | 7/2026 | 670 | 670.17 | 670.17 | 89.31 | 12
April 2025 |  |  | 407 | SAMNI-JAMBUSAR (24.08 KM) | WR | N22000541 | 5-2022 | 3/2030 | 12/2025 | 12/2025 | 216.72 | 349.93 | 349.93 | 86.23 | 25
April 2025 |  |  | 408 | VIJAPUR-AMBLIYASAN (41.53 KM) | WR | N22000547 | 5-2022 | 3/2030 | 7/2025 | 7/2025 | 309.81 | 415.38 | 415.38 | 565.62 | 85
April 2025 |  |  | 409 | ADRAJ MOTI-VIAJAPUR (39.75 KM) | WR | N22000548 | 5-2022 | 5/2030 | 7/2025 | 5/2030 | 296.54 |  | 296.54 | 20.09 | 65
April 2025 |  |  | 410 | NEW BG LINE BETWEEN NALIYA- JAKHAU PORT | WR | N22000550 | 2-2023 | 1/2028 | 9/2026 | 9/2026 | 410.46 | 410.46 | 410.46 | 33.63 | 2
April 2025 |  |  | 411 | NEW BG LINE INTERSECTION (5 NOS) BETWEEN GERATPUR- SANAND AND BOTAD- AHMEDABAD (16.51 KM) (PB29/NR/20 | WR | N22000551 | 10-2022 | 10/2027 | 2/2027 | 10/2027 | 437.21 |  | 437.21 | 23.75 | -
April 2025 |  |  | 412 | TARANGA HILL ABU ROAD VIA AMBAJI NEW LINE | NWR | N22000592 | 7-2022 | 7/2030 | N.A. | 12/2026 | 2798.16 |  | 2798.16 | 1020.7 | 11
April 2025 |  |  | 413 | JUNAGARH -VISAVADAR (42.28) KM | RVNL | N22000600 | 6-2022 | 9/2028 | N.A. | 12/2026 | 493 |  | 492.83 | 0 | -
April 2025 |  |  | 414 | MODASA- SHAMLAJI NEW LINE ( MM OF AHMEDABAD- HIMMATNAGAR-UDAIPUR (299.2 KM)) | WR | N22000622 | 9-2012 | 3/2027 | 2/2026 | 2/2026 | 261.68 | 261.68 | 261.68 | 649.6 | 55
April 2025 |  |  | 415 | FOUR LANING OF BHAVNAGAR- TALAJA SECTION OF NH-8E FROM KM. 7.090 TO KM. 53.585 (DESIGN CH FROM KM. 6. | NHAI | N24000567 | 5-2016 | 8/2019 | N.A. | 6/2024 | 998.18 |  | 998.18 | 802.89 | 100
April 2025 |  |  | 416 | FOUR LANING OF KAGAVADAR - UNA SECTION OF NH-8E FROM KM 139.915 TO KM 180.478 (PACKAGE-IV) IN THE ST | NHAI | N24000569 | 5-2016 | 9/2019 | 5/2024 | 5/2025 | 723.64 |  | 723.64 | 562.31 | 97
April 2025 |  |  | 417 | FOUR LANING OF UNA TO KODINAR OF NH-8E FROM KM. 180.478 TO KM 221.610 (PACKAGE-V) IN THE STATE OF GU | NHAI | N24000570 | 5-2016 | 8/2019 | N.A. | 3/2025 | 763.08 |  | 763.08 | 520.19 | 99.54
April 2025 |  |  | 418 | 4-LANNING OF KODINAR TO VERAVAL SECTION OF NH-8E FROM KM 221.610 TO KM 263.000 | NHAI | N24000592 | 7-2016 | 7/2020 | N.A. | 5/2025 | 829.97 |  | 829.97 | 486.93 | 96.63
April 2025 |  |  | 419 | SIX LANNING FROM KM. 401.200 TO 494.410 OF NH-8 ON HYBRID ANNUITY MODE UNDER NHDP- V(PKG VI)REG. | NHAI | N24000649 | 1-2017 | 12/2020 | 10/2025 | 10/2025 | 1251.11 | 1527.75 | 1527.75 | 684.97 | 89.22
April 2025 |  |  | 420 | CONSTRUCTION OF EIGHT LANE VADODARA KIM EXPRESSWAY FROM KM 254.430 TO KM 279.000 (KIM TO ANKLESHWAR | NHAI | N24000834 | 3-2018 | 10/2021 | 5/2025 | 7/2025 | 1161.39 | 1738.03 | 1404 | 679.63 | 83
April 2025 |  |  | 421 | CONSTRUCTION OF MISSING LINKS (SINGLE LANE) IN LAKHPAT GADULI HAJIPIR ODMA KHAVDA DHOLAVIRA MAUVANA | MoRTH | N24000925 | 10-2018 | 11/2020 | 9/2024 | 9/2024 | 400.76 | 394.44 | 394.44 | 287.04 | 87
April 2025 |  |  | 422 | CONSTRUCTION OF ROB WITH APPROACHES IN LIEU OF L C NO 165 OF AHMEDABAD PALANPUR BETWEEN RAILWAY STAT | MoRTH | N24001427 | 6-2020 | 4/2023 | 9/2024 | 9/2024 | 166.21 |  | 166.21 | 97.12 | 93
April 2025 |  |  | 423 | CONSTRUCTION OF FOUR LANE EXPRESSWAY FROM START OF SARDAR PATEL RING ROAD TO SINDHREJ VILLAGE (CH. 0 | NHAI | N24001443 | 5-2020 | 3/2024 | 6/2025 | 6/2025 | 690.3 | 929.95 | 929.95 | 828.47 | 93.27
April 2025 |  |  | 424 | CONSTRUCTION OF FOUR LANE EXPRESSWAY FROM START OF SINDHREJ VILLAGE (CH. 22.00 TO CH. 48.52) SECTION | NHAI | N24001444 | 5-2020 | 1/2024 | 6/2025 | 6/2025 | 882 | 1229.37 | 1229.37 | 979.04 | 86.22
April 2025 |  |  | 425 | CONSTRUCTION OF FOUR LANE EXPRESSWAY FROM START OF VEJALLKA VILLAGE TO START OF DSIR ZONE OF AHMEDAB | NHAI | N24001445 | 5-2020 | 7/2023 | 5/2025 | 5/2025 | 691.52 | 903.85 | 903.85 | 872.33 | 98.75
April 2025 |  |  | 426 | CONSTRUCTION OF FOUR LANE EXPRESSWAY FROM START OF DSIR ZONE OF AHMEDABAD DISTRICT TO ADHELAI VILLAG | NHAI | N24001446 | 5-2020 | 12/2023 | 5/2025 | 5/2025 | 894 | 1210.06 | 1210.06 | 1130.52 | 96.11
April 2025 |  |  | 427 | DELHI VADODARA GREENFIELD ALIGNMENT SECTION OF NH 148N PACKAGE 26 | NHAI | N24001515 | 9-2020 | 2/2024 | N.A. | 3/2026 | 1542.02 |  | 1542.02 | 969.46 | 68.35
April 2025 |  |  | 428 | DELHI VADODARA GREENFIELD ALIGNMENT SECTION OF NH 148N PACKAGE 27 | NHAI | N24001516 | 9-2020 | 2/2024 | 4/2025 | 8/2025 | 1185.69 |  | 1185.69 | 979.62 | 93.52
April 2025 |  |  | 429 | DELHI VADODARA GREENFIELD ALIGNMENT SECTION OF NH 148N PACKAGE 30 | NHAI | N24001518 | 11-2019 | 9/2023 | N.A. | 4/2025 | 1669.56 |  | 1669.56 | 1066.35 | 96.9
April 2025 |  |  | 430 | DELHI VADODARA GREENFIELD ALIGNMENT SECTION OF NH 148N PACKAGE 28 | NHAI | N24001519 | 9-2020 | 11/2023 | N.A. | 4/2025 | 1198.55 |  | 1198.55 | 911.04 | 95.78
April 2025 |  |  | 431 | DELHI VADODARA GREENFIELD ALIGNMENT SECTION OF NH 148N PACKAGE 31 | NHAI | N24001520 | 11-2019 | 5/2024 | N.A. | 6/2025 | 1604.06 |  | 1604.06 | 1241.4 | 95.73
April 2025 |  |  | 432 | UP-GRADATION TO 4-LANE WITH PAVED SHOULDER OF BHIMASAR JUNCTION OF NH-41 TO ANJAR BHUJ UPTO AIRPORT | NHAI | N24001785 | 3-2022 | 6/2025 | N.A. | 6/2025 | 1373.06 | 1085 | 1373.06 | 594.59 | 83.06
April 2025 |  |  | 433 | CONSTRUCTION OF EIGHT LANE ACCESS CONTROLLED EXPRESSWAY FROM KM 103.400 TO KM 128.000 OF VADODARA MU | NHAI | N24001786 | 3-2021 | 3/2024 | N.A. | 3/2026 | 1259 | 2652.24 | 1910 | 278.29 | 34.08
April 2025 |  |  | 434 | CONSTRUCTION OF EIGHT LANE ACCESS CONTROLLED EXPRESSWAY FROM KM 217.500 TO KM 254.430 OF VADODARA MU | NHAI | N24001788 | 7-2020 | 12/2023 | N.A. | 5/2025 | 2271.86 | 3372.97 | 3916 | 1101.59 | 98.1
April 2025 |  |  | 435 | CONSTRUCTION OF EIGHT LANE EXPRESSWAY FROM KM 190.000 TO KM 217.500 GANDEVA TO ENA SECTION OF VADODA | NHAI | N24001789 | 7-2020 | 8/2023 | N.A. | 4/2025 | 1710.3 | 2665.08 | 1927 | 891.83 | 90.56
April 2025 |  |  | 436 | SANCHORE - SANTALPUR FROM KM 67.000- KM 99.000 OF NH- 754K (AJ-RGBS-PACKAGE-3) | NHAI | N24001790 | 2-2020 | 8/2023 | 12/2024 | 12/2024 | 752.3 |  | 766.2 | 452.13 | 98.14
April 2025 |  |  | 437 | 4L OF BAL WORKS OF TALAJA - MAHUVA FROM 54.990 KM. TO 100.450 KM. OF OLD NH-8E | PACKAGE-II | NHAI | 3-2021 | 9/2022 | N.A. | 1/2025 | 536.03 |  | 536.03 | 480.77 | 100
April 2025 |  |  | 438 | 4L OF BAL WORKS OF MAHUVA TO KAGVADAR FROM 100.450 KM. TO 140.470 KM. OF NH-8E | PKG- III | NHAI | 3-2021 | 9/2022 | N.A. | 5/2025 | 485.75 |  | 485.75 | 393.88 | 99.36
April 2025 |  |  | 439 | SANCHORE - SANTALPUR FROM KM 99.000- KM 130.073 OF NH- 754K (AJ-RGBS-PACKAGE-4) | NHAI | N24001794 | 2-2020 | 3/2023 | 12/2024 | 12/2024 | 778.15 |  | 785.67 | 547.22 | 99.7
April 2025 |  |  | 440 | 4L KODINAR - VERAVAL (PACKAGE VI) FROM KM. 222.400 TO KM. 230.00 (KODINAR BYPASS) OF NH-8E (NH 51 NE | NHAI | N24001827 | 3-2022 | 3/2023 | N.A. | 3/2025 | 162.73 |  | 162.73 | 131.79 | 100
April 2025 |  |  | 441 | UPGRADATION AND STRENGTHENING TO 2 LANE PS FROM KM 95/500 TO KM 129/775 OF NH 168 G IDAR BHILODA SA | MoRTH | N24002014 | 9-2022 | 12/2023 | 12/2025 | 12/2025 | 237.28 |  | 237.28 | 0.34 | -
April 2025 |  |  | 442 | UPGRADATION TO 4L PS DIVIDED CARRIAGEWAY FROM PATAN (NEAR RAJPUR) TO GOJARIYA FROM KM 52.000 TO KM 1 | NHAI | N24002034 | 12-2021 | 3/2025 | N.A. | 3/2025 | 1181.34 | 1181 | 1181.34 | 515.21 | 74.72
April 2025 |  |  | 443 | WIDENING TO 6L OF EXISTING 4L JETPUR - GONDAL - RAJKOT SECTION FROM KM. 117.600 TO KM. 185.00 ON NH- | NHAI | N24002035 | 9-2023 | 9/2025 | N.A. | 9/2025 | 2070.44 |  | 2070.44 | 740.96 | 20.77
April 2025 |  |  | 444 | UPGRADATION OF DHORAJI JAMKANDORNA KALAVAD SECTION OF NH 927D FROM DESIGN CHAINAGE KM 00 TO KM 58.11 | MoRTH | N24002117 | 10-2022 | 2/2024 | 2/2026 | 2/2026 | 246.6 | 291 | 291 | 27.57 | 15
April 2025 |  |  | 445 | UPGRADATION TO TWO LANE WITH PAVED SHULDER CONFIGUARATION FROM KM 00 TO 47 OF NH 351 MAHUVA TO BADHA | MoRTH | N24002118 | 12-2022 | 2/2024 | 8/2025 | 8/2025 | 173.06 |  | 219 | 0.15 | -
April 2025 |  |  | 446 | WORK OF DEVELOPMENT AND CONSTRUCTION OF ELEVATED CORRIDORFROM KM 38/660 TO KM 42/690 (ISCON JUNCTION | MoRTH | N24002182 | 3-2023 | 3/2026 | N.A. | 3/2026 | 530.2 |  | 530.2 | 0 | -
April 2025 |  |  | 447 | WIDENING 2 LANE TO 4-LANE FROM KM 92/320 TO KM 115/320 (VAV CHOKDI-SATLASANA TO TO VRUNDAVAN CHOKDI, | MoRTH | N24002183 | 3-2022 | 3/2026 | N.A. | 3/2026 | 151.13 |  | 171 | 0 | -
April 2025 |  | URBAN DEVELOPMENT | 448 | AHMEDABAD METRO RAIL PROJECT PHASE 1 | AMR | N28000122 | 11-2014 | 12/2018 | N.A. | 8/2025 | 10773 |  | 12924.55 | 12462.07 | 99.88
April 2025 |  | URBAN DEVELOPMENT | 449 | AHMEDABAD METRO RAIL PROJECT PHASE II | AMR | N28000137 | 3-2019 | 3/2024 | N.A. | 12/2025 | 5384.17 |  | 5384.17 | 3999.66 | 85.1
April 2025 |  | URBAN DEVELOPMENT | 450 | SURAT METRO RAIL PROJECT | AMR | N28000138 | 3-2019 | 3/2024 | N.A. | 6/2026 | 12020.32 |  | 12020.32 | 6685.69 | 64.3
April 2025 |  | HEALTH AND FAMILY WELFARE | 451 | ALL INDIA INSTITUTE OF MEDICAL SCIENCES AT MANETHI, HARYANA. | HITES | N21000032 | 3-2019 | 3/2023 | 3/2026 | 3/2026 | 1294.34 | 1294.34 | 1294.34 | 244.2 | 19
April 2025 |  | HOME AFFAIRS | 452 | C/o separate family accommodation (Phase-I) on EPC basis for SSB at Faridabad (Haryana)" | CPWD FOR MHA | N28000147 | 1-2020 | 10/2023 | 3/2025 | 6/2025 | 166.98 | 170.23 | 170.23 | 132.08 | 96
April 2025 |  | PETROLEUM | 453 | R and D CAMPUS II AT FARIDABAD | IOCL | N16000375 | 6-2019 | 12/2022 | 7/2025 | 3/2026 | 2281.94 | 3219.94 | 3219.94 | 1697.83 | 62.6
April 2025 |  | PETROLEUM | 454 | CAPACITY EXPANSION OF PANIPAT REFINERY FROM 15 TO 25 MMTPA | IOCL | N16000412 | 2-2021 | 9/2024 | 12/2025 | 12/2025 | 34627 | 38231 | 38231 | 19698.88 | 85.2
April 2025 |  | PETROLEUM | 455 | POLY BUTADIENE RUBBER PLANT AT PANIPAT | IOCL | N16000458 | 3-2022 | 3/2025 | 6/2026 | 6/2026 | 1459 | 2948.62 | 2948.62 | 904.44 | 63.9
April 2025 |  | RAILWAYS | 456 | DOUBLING BETWEEN BHIWANI- DOBH BAHALI | NWR | N22000604 | 2-2023 | 2/2028 | N.A. | 12/2025 | 471.06 |  | 471.06 | 97.11 | 41
April 2025 |  | RAILWAYS | 457 | DOUBLING BETWEEN REWARI- KATHUWAS (27.73 KM) | NWR | N22000606 | 2-2023 | 6/2027 | N.A. | 12/2025 | 352.41 |  | 352.41 | 158.65 | 31
April 2025 |  | RAILWAYS | 458 | CONSTRUCTION OF 4-LANE NH- 344P-PACKAGE-4 (FROM KM 0+000 TO KM 29+600, 29.6KM), STARTING FROM BAWANA | NHAI | N24001532 | 11-2021 | 11/2023 | 1/2024 | 8/2024 | 694 | 1918 | 1500 | 1682.82 | 100
April 2025 |  |  | 459 | CONSTRUCTION OF 4-LANE GREEN FIELD DELHI-AMRITSAR- KATRA EXPRESSWAY (NE-05) FROM JUSSUR KHERI ON KMP | NHAI | N24001533 | 11-2020 | 12/2023 | N.A. | 5/2025 | 1690.23 |  | 2010.17 | 1451.11 | 98.5
April 2025 |  |  | 460 | CONSTRUCTION OF FOUR-LANE GREENFIELD DELHI-AMRITSAR- KATRA EXPRESSWAY FROM JUNCTION WITH ROHTAK-PANIP | NHAI | N24001534 | 12-2020 | 1/2024 | 4/2024 | 5/2025 | 1334.04 |  | 1334 | 1044.27 | 99
April 2025 |  |  | 461 | 4-LANING OF GOHANA-SONIPAT (PKG-2) SECTION FROM KM 40.601 TO KM 78.837 (LENGTH = 38.236KM) OF NH-352 | NHAI | N24001535 | 7-2020 | 7/2022 | 5/2024 | 8/2025 | 899 | 1882.46 | 1882.46 | 1123.98 | 97.1
April 2025 |  |  | 462 | FOUR LANING OF JIND GOHANA GREENFIELD ALIGNMENT PACKAGE 1 IN THE STATE OF HARYANA UNDER HYBRID ANNUI | NHAI | N24001536 | 7-2020 | 7/2022 | N.A. | 6/2025 | 817 | 1605 | 1605 | 1026.56 | 99.9
April 2025 |  |  | 463 | CONSTRUCTION OF FOUR LANE GREENFIELD PROJECT OF DELHI-AMRITSAR-KATRA EXPRESSWAY (PHASE-I PKG-III) F | NHAI | N24001633 | 12-2020 | 12/2023 | 3/2024 | 3/2025 | 1430.88 | 1813.91 | 1813.91 | 1122.45 | 99.9
April 2025 |  |  | 464 | CONSTRUCTION OF FOUR LANE GREENFIELD PROJECT OF DELHI-AMRITSAR-KATRA EXPRESSWAY (PHASE-I PKG-IV) FRO | NHAI | N24001634 | 1-2021 | 12/2023 | 3/2024 | 4/2025 | 1306.95 | 1564.14 | 1564.14 | 942.66 | 99.97
April 2025 |  |  | 465 | 4 LANING OF JAGADHRI TAJEWALA ROAD SECTION OF NH 907 (OLD NH 73A) UNDER NH(O) (PKG 1) IN THE STATE O | NHAI | N24001635 | 3-2022 | 2/2025 | N.A. | 2/2025 | 1269.5 |  | 1269.5 | 233 | 51
April 2025 |  |  | 466 | 4- LANING OF ROHTAK-JIND SECTION FROM KM. 307+000 TO KM. 347+800 OF NH-71 AND CONNECTING LINK FROM K | NHAI | N24001673 | 3-2020 | 3/2023 | 11/2024 | 6/2025 | 510.97 |  | 510.97 | 529 | 95.5
April 2025 |  |  | 467 | CONSTRUCTION OF GURGAON - PATAUDI - REWARI SECTION OF NH-352W (DESIGN LENGTH 46.11 KM) AS FEEDER ROU | NHAI | N24001774 | 12-2020 | 11/2023 | N.A. | 6/2024 | 1524.03 |  | 1524.03 | 1092.97 | 64.79
April 2025 |  |  | 468 | CONSTRUCTION OF PROPOSED REWARI BYPASS (DESIGN LENGTH 14.4 KM) NH-11 AS A FEEDER ROUTE IN THE STATE | NHAI | N24001775 | 2-2020 | 1/2023 | 12/2024 | 12/2024 | 808.31 |  | 958 | 915.12 | 100
April 2025 |  |  | 469 | UPGRADATION OF EXISTING 4 LANE ISMAILABAD-AMBALA SECTION (KM. 0+000 TO KM 42+500) (PART OF AMBALA-KO | NHAI | N24002037 | 1-2023 | 12/2025 | N.A. | 3/2026 | 609.32 | 609 | 609 | 180.2 | 43.8
April 2025 |  |  | 470 | CONSTRUCTION OF 6-LANE GREENFIELD KARNAL RING ROAD STARTING FROM NH-44 NEAR VILLAGE SHAMGARH (DESIGN | NHAI | N24002038 | 11-2022 | 8/2025 | N.A. | 8/2025 | 1691.45 | 1998 | 1998 | 649.71 | 58.76
April 2025 |  |  | 471 | CONSTRUCTION OF 6-LANE GREENFIELD AMBALA RING ROAD STARTING FROM JUNCTION WITH SHAMLI- AMBALA SECTION | NHAI | N24002039 | 2-2023 | 10/2025 | N.A. | 10/2025 | 1088.64 | 1178 | 1178 | 391.51 | 45
April 2025 |  |  | 472 | DEVELOPMENT OF SIX-LANE ACCESS CONTROLLED HIGHWAY FROM RANIPUR BARSI (SAHARANPUR DISTRICT) TO ADHOYA | NHAI | N24002040 | 4-2022 | 5/2025 | N.A. | 5/2028 | 1554.21 |  | 1554.21 | 517.05 | 54
April 2025 |  |  | 473 | DEVELOPMENT OF SIX-LANE ACCESS CONTROLLED HIGHWAY FROM ADHOYA MUSALMANA (AMBALA DISTRICT) TO SADOPUR | NHAI | N24002041 | 4-2022 | 5/2025 | N.A. | 5/2025 | 1491.71 |  | 1491.71 | 706.26 | 49.7
April 2025 |  |  | 474 | CONSTRUCTION OF 4-LANING OF BHIWANI HANSI ROAD SECTION OF NH 148B (DESIGN LENGTH 42.934 KM) UNDER BH | NHAI | N24002042 | 11-2022 | 12/2025 | N.A. | 12/2025 | 1322.13 |  | 1322.13 | 354.52 | 73.13
April 2025 |  |  | 475 | CONSTRUCTION OF 4-LANE GREENFIELD JALBEHRA - SHAHBAD SECTION OF NH ? 152G FROM KM 0+000 TO KM 22+850 | NHAI | N24002043 | 3-2022 | 6/2025 | N.A. | 6/2025 | 927.22 | 1173.66 | 1173.66 | 458.86 | 78.65
April 2025 |  |  | 476 | 4L AMBALA - KALAAMB FROM KM. -0.800 TO KM. 33.015 OF OLD NH-72 | NHAI | N24002044 | 6-2023 | 6/2025 | N.A. | 6/2025 | 629.16 |  | 629.16 | 216 | 88
April 2025 |  |  | 477 | CONSTRUCTION OF GREENFIELD CONNECTIVITY TO JEWAR INTERNATIONAL AIRPORT FROM DND FARIDABAD BALLABHGAR | NHAI | N24002048 | 7-2022 | 6/2025 | N.A. | 3/2026 | 2414.67 | 2898 | 2898 | 1229.9 | 45.56
April 2025 |  |  | 478 | ESTABLISHMENT OF PERMANENT CAMPUS PHASE 1 OF IIM SIRMAUR | CPWD EDUCATION | N42000008 | 9-2018 | 6/2022 | 12/2024 | 8/2025 | 392.51 |  | 446.43 | 316.16 | 91.5
April 2025 |  |  | 479 | CONSTRUCTION OF PERMANENT CAMPUSES OF CENTRAL UNIVERSITY OF HIMACHAL PRADESH AT DEHRA AND DHARAMSHAL | CPWD | N42000011 | 3-2021 | 11/2024 | 7/2025 | 7/2025 | 512.37 | 300.45 | 300.45 | 144.32 | 70
April 2025 |  | POWER | 480 | PARBATI HEP (4X200 MW) (NHPC) II | NHPC | 180100210 | 9-2002 | 9/2009 | 4/2025 | 4/2025 | 3919.59 |  | 13045 | 12832.59 | 100
April 2025 |  | POWER | 481 | LUHRI HYDROELECTRIC PROJECT (STAGE1) | SJVN | N18000279 | 11-2020 | 1/2026 | N.A. | 12/2028 | 1810.56 |  | 3371.61 | 1704.72 | 51.32
April 2025 |  | POWER | 482 | DHAULASIDH HYDROELECTRIC PROJECT (66 MW) | SJVN | N18000291 | 10-2020 | 11/2025 | N.A. | 3/2027 | 687.97 |  | 1511.87 | 851.02 | 66.2
April 2025 |  | POWER | 483 | SUNNI DAM HYDRO ELECTRIC PROJECT | SJVN | N18000344 | 1-2023 | 4/2028 | N.A. | 12/2028 | 2614.51 |  | 4540.71 | 935.08 | 28.58
April 2025 |  | RAILWAYS | 484 | BHANUPALI-BILASPUR BERI NL | RVNL | N22000273 | 4-2008 | 12/2026 | N.A. | 3/2025 | 13370.29 |  | 6753.42 | 5369.57 | -
April 2025 |  | RAILWAYS | 485 | FOUR LANNING OF NERCHOWK- PANDOH BYPASS SECTION OF NH-21(PACKAGE-I KM 190.000 TO KM 221.305) UNDER NH | NHAI | N24000613 | 9-2016 | 7/2020 | N.A. | 3/2025 | 1273.71 |  | 1478.61 | 1439.49 | 96.68
April 2025 |  | RAILWAYS | 486 | FOUR LANING OF SOLAN- KAITHLIGHAT SECTION OF NH- 22 (NOW NH-5) FROM KM 106.139 TO KM 129.050, ON EPC M | NHAI | N24000852 | 3-2018 | 5/2021 | 12/2024 | 12/2024 | 478.74 |  | 1514.46 | 1349.59 | 83
April 2025 |  |  | 487 | REHABILITATION AND UPGRADATION TO 2-LANE/2- LANE WITH PAVED SHOULDERS/4-LANE CONFIGURATION OF PAONTA | MoRTH | N24001381 | 8-2020 | 4/2021 | N.A. | 4/2021 | 272.98 |  | 272.98 | 140.69 | -
April 2025 |  |  | 488 | REHABILITATION AND UPGRADATION TO 2-LANE CONFIGURATION OF HEWNA- ASHYARI SECTION (KM 25.000 TO KM 50. | MoRTH | N24001382 | 8-2020 | 3/2021 | N.A. | 3/2021 | 242.8 |  | 242.8 | 96.76 | 90.94
April 2025 |  |  | 489 | REHABILITATION AND UPGRADATION TO INTERMEDIATE LANE CONFIGURATION OF SHRI KYARI-GUMMA SECTION (KM 75 | MoRTH | N24001383 | 8-2020 | 4/2021 | N.A. | 4/2021 | 349.2 |  | 349.2 | 239.34 | 100
April 2025 |  |  | 490 | REHABILITATION AND UPGRADATION TO 2-LANE CONFIGURATION OF ASHYARI- SHRI KYARI SECTION (KM 50.000 TO K | MoRTH | N24001422 | 2-2021 | 9/2021 | N.A. | 9/2021 | 345.89 |  | 345.89 | 152.01 | 90.02
April 2025 |  |  | 491 | REHABILITATION AND UPGRADATION TO 2-LANE CONFIGURATION OF HAMIRPUR- KARNOHAL SECTION (KM 141.000 TO K | MoRTH | N24001447 | 8-2020 | 12/2024 | N.A. | 12/2024 | 371.93 |  | 371.93 | 154.04 | 80
April 2025 |  |  | 492 | REHABILITATION AND UPGRADATION TO 2-LANE CONFIGURATION OF KALWAHAN-MANDI SECTION (KM 208.950 TO KM 2 | MoRTH | N24001470 | 8-2020 | 4/2025 | N.A. | 4/2025 | 314.32 |  | 314.32 | 49.26 | 44
April 2025 |  |  | 493 | REHABILITATION AND UPGRADING FROM 2 L TO 4 L FROM BHANGBAR(NEAR RANITAL) TO KANGRA BYPASS SECTION OF | NHAI | N24001808 | 3-2021 | 12/2024 | 12/2024 | 12/2024 | 1322.95 | 1442.47 | 1442.47 | 887.6 | 96.61
April 2025 |  |  | 494 | CONVERSION OF PARTIALLY EXCAVATED ESCAPE TUNNEL TO UNIDIRECTIONAL TWO LANE TUNNEL (INCLUDING CONSTRU | NHAI | N24001809 | 5-2022 | 3/2024 | 12/2024 | 12/2024 | 469.95 |  | 280 | 302.91 | 97.9
April 2025 |  |  | 495 | 4L SUNDER NAGAR BYPASS FROM KM173.900 TO KM 179.600 OF NH-21 IN THE STATE OF HP | NHAI | N24001810 | 2-2022 | 6/2024 | N.A. | 6/2024 | 190.6 |  | 163 | 103.48 | 100
April 2025 |  |  | 496 | 4L OF MO - SIHUNI FROM KM. 42.00 TO KM. 51.00 OF OLD NH- 20 (NEW NH-154) (PACKAGE-IB) | NHAI | N24001811 | 4-2021 | 6/2024 | N.A. | 5/2025 | 583.93 | 770 | 770 | 171.98 | 99.96
April 2025 |  |  | 497 | 4L OF HP/PUNJAB BO4L OF HP/PUNJAB BORDER - MO FROM KM. 11.00 TO KM. 42.00 OF OLD NH-20 (NEW NH-154) | NHAI | N24001812 | 3-2021 | 5/2024 | N.A. | 12/2025 | 1002.11 | 1361.79 | 1361.76 | 189.98 | 45.67
April 2025 |  |  | 498 | 4L OF END OF PINJORE BYPASS - BADDI - NALAGARH SECTION (KM. 4.200 TO KM. 35.370) OF NH21A | NHAI | N24001813 | 7-2021 | 9/2024 | N.A. | 9/2024 | 1692.05 |  | 1692.05 | 942.14 | 21.6
April 2025 |  |  | 499 | IMPROVEMENT/CONSTRUCTION OF EXISTING CLASS-5 ROAD TO NH INTERMEDIATE LANE SPECIFICATION WITH HARD SH | BRO | N24001915 | 3-2021 | 6/2026 | N.A. | 6/2026 | 230.54 |  | 230.54 | 20.16 | 20.16
April 2025 |  |  | 500 | IMPROVEMENT/CONSTRUCTION OF EXISTING CLASS 5 ROAD TO NH INTERMEDIATE LANE SPECIFICATION WITH HARD SH | BRO | N24001916 | 3-2021 | 5/2026 | N.A. | 5/2026 | 314.67 |  | 314.67 | 76.05 | 44
April 2025 |  |  | 501 | PKG NAME: 4L OF KATHLIGHAT TO SHAKRAL VILLAGE FROM KM 128.835 TO KM 146.300 OF NH- 5 (SHIMLA BYPASS | NHAI | N24002049 | 3-2022 | 4/2026 | N.A. | 4/2026 | 1703.48 | 2278 | 2278 | 651.98 | 14.5
April 2025 |  |  | 502 | REHABILITATION AND UPGRADATION TO 4L CONFIGURATION and STRENGTHENING OF SIHUNI TO RAJOL FROM KM 51.0 | NHAI | N24002050 | 2-2022 | 9/2025 | N.A. | 9/2025 | 696.65 | 698.46 | 698.46 | 367.52 | 61.78
April 2025 |  |  | 503 | CONSTRUCTION OF NEW 2 LANE WITH PAVED SHOULDER OF HAMIRPUR BYPASS (PACKAGE IVA) OF NH-88 (NEW NH-103 | NHAI | N24002051 | 7-2022 | 10/2025 | N.A. | 10/2025 | 739.39 |  | 739.39 | 328.46 | 78
April 2025 |  |  | 504 | REHABILITATION AND UP- GRADATION OF EXISTING ROAD TO 2L PS FROM END OF HAMIRPUR BYPASS (NEAR CHILBAHA | NHAI | N24002052 | 2-2022 | 4/2025 | N.A. | 4/2025 | 1146.19 |  | 1146.19 | 918.75 | 65.3
April 2025 |  |  | 505 | REHABILITATION AND UP- GRADATION TO 4L CONFIGURATION AND STRENGTHENING OF THANPURI TO PAROR SECTION F | NHAI | N24002192 | 6-2022 | 12/2025 | N.A. | 12/2025 | 815.69 | 815.69 | 815.69 | 378.19 | 28.9
April 2025 |  | URBAN DEVELOPMENT | 506 | CONSTRUCTION OF PERMANENT CAMPUS OF CENTRAL UNIVERSITY OF HIMACHAL PRADESH AT DEHRA AND JADRANGAL (D | CPWD | N28000154 | 4-2022 | 11/2024 | N.A. | 11/2024 | 512.34 |  | 512.34 | 0 | -
April 2025 |  | CIVIL AVIATION | 507 | JAMMU - CONSTRUCTION OF NEW CIVIL ENCLAVE | AAI | N04000107 | 7-2022 | 6/2026 | N.A. | 6/2026 | 861.37 |  | 861.37 | 133.82 | 29.5
April 2025 |  | DEPARTMENT OF HIGHER EDUCATION | 508 | CONSTRUCTION OF PERMANENT CAMPUS OF IIM JAMMU (PHASE 1) | CPWD EDUCATION | N28000130 | 3-2019 | 7/2022 | 1/2025 | 1/2025 | 424.93 |  | 500.91 | 448.15 | 96
April 2025 |  | DEPARTMENT OF HIGHER EDUCATION | 509 | CONSTRUCTION OF PERMANENT CAMPUS IIT JAMMU (PHASE 1C) | CPWD EDUCATION | N28000131 | 1-2018 | 4/2023 | 4/2025 | 4/2025 | 676 | 1144.68 | 1144.68 | 54.75 | 100
April 2025 |  | HEALTH AND FAMILY WELFARE | 510 | CONSTRUCTION OF AIIMS AT JAMMU VIJAYPUR, SAMBA JAMMU AND KASHMIR | CPWD FOR HEALTH | N21000029 | 3-2019 | 9/2023 | 5/2025 | 5/2025 | 1404 | 1642 | 1642 | 1461.68 | 99.9
April 2025 |  | HEALTH AND FAMILY WELFARE | 511 | C/O AIIMS AT AWANTIPORA (KASHMIR) JAMMU AND KASHMIR | CPWD FOR HEALTH | N28000150 | 3-2019 | 9/2025 | 1/2025 | 11/2025 | 1828 | 1577 | 1577 | 976.64 | 64
April 2025 |  | PETROLEUM | 512 | SETTING UP A COMMON USER PETROLEUM TERMINAL AT JAMMU FOR RE-SITEMENT OF EXISTING DEPOTS OF PSU OMCS | BPCL | N16000500 | 4-2021 | 3/2025 | N.A. | 3/2025 | 676.89 |  | 676.89 | 478.41 | 74
April 2025 |  | PETROLEUM | 513 | CGD PROJECT AT JAMMU DISTRICTS | IOCL | N16000527 | 3-2022 | 3/2032 | 9/2034 | 9/2034 | 538 |  | 538 | 3.87 | 0.6
April 2025 |  | PETROLEUM | 514 | PAKAL DUL HYDRO ELECTRIC PROJECT (1000 MW) | CVPPPL | N18000172 | 10-2014 | 4/2020 | 7/2025 | 9/2026 | 8112.12 |  | 12727.76 | 6321.4 | 67.9
April 2025 |  | PETROLEUM | 515 | KIRU HYDRO ELECTRIC PROJECT | CVPPPL | N18000278 | 3-2019 | 8/2024 | N.A. | 9/2026 | 4287.59 |  | 5409 | 2503.38 | 59.14
April 2025 |  |  | 516 | RATLE HE PROJECT | NHPC | N18000324 | 2-2021 | 2/2026 | N.A. | 11/2028 | 5281.94 |  | 5281.94 | 932.07 | 22.1
April 2025 |  |  | 517 | KWAR HE PROJECT | CVPPPL | N18000363 | 5-2022 | 11/2026 | N.A. | 12/2027 | 4526.12 |  | 4526.12 | 1083.48 | 20.8
April 2025 |  |  | 518 | TRANSMISSION SCHEME FOR EVACUATION OF POWER FROM RATLE HEP (850 MW) & KIRU (624 MW): PART B | PGCIL | N18000417 | 3-2025 | 3/2027 | N.A. | 3/2027 | 219 |  | 219 | 0 | -
April 2025 |  | RAILWAYS | 519 | UDHAMPUR-SRINAGAR- BARAMULLA (NL),NR | NR | 220100133 | 3-1995 | 8/2024 | 12/2024 | 12/2024 | 37012 | 37012.26 | 43780 | 42328.83 | 100
April 2025 |  | RAILWAYS | 520 | FOUR LANING OF UDHAMBUR - RAMBAN SECTION OF NH-1A | NHAI | N24000488 | 12-2015 | 12/2018 | 5/2025 | 5/2025 | 2136.97 | 2644 | 2644 | 2386.51 | 99.5
April 2025 |  | RAILWAYS | 521 | CONSTRUCTION OF STAND ALONE RING ROAD/ BYPASS AROUND JAMMU CITY IN THE STATE OF J AND K ON EPC MODE | NHAI | N24000717 | 12-2017 | 7/2021 | 5/2025 | 5/2025 | 1471.75 | 1471.75 | 1903.98 | 1715.72 | 98.64
April 2025 |  | RAILWAYS | 522 | UP-GRADATION TO 4-LANE WITH PAVED SHOULDER OF JAMMU- AKHNOOR ROAD SECTION OF NH-144A FROM GANESH VIHA | NHIDCL | N24000868 | 3-2018 | 7/2021 | 8/2023 | 10/2025 | 253.44 |  | 253.44 | 187.74 | 82.1
April 2025 |  | RAILWAYS | 523 | CONSTRUCTION OF (I) CONNECTING ROAD FROM Z- MORH TUNNEL TO ZOJILA TUNNEL AND (II) 14.150 KM LONG BI-D | NHIDCL | N24001256 | 8-2020 | 9/2026 | N.A. | 9/2026 | 6808.69 |  | 6808.69 | 3013.84 | 49.92
April 2025 |  |  | 524 | UP-GRADATION TO 2-LANE WITH PAVED SHOULDER FROM KM 12.850 TO KM20.300 OF 7.450KM LENGTH ON GOHA-KHEL | NHIDCL | N24001264 | 7-2020 | 4/2022 | 10/2024 | 10/2026 | 228.39 |  | 228.39 | 67.6 | 87.6
April 2025 |  |  | 525 | UP-GRADATION TO 2-LANE WITH PAVED SHOULDER FROM KM 20.300 TO KM 29.030 OF 8.730 KM LENGTH ON GOHA-K | NHIDCL | N24001266 | 7-2020 | 4/2022 | 11/2023 | 6/2025 | 210.79 |  | 210.79 | 71 | 90.14
April 2025 |  |  | 526 | KHELLANI-KHANABAL PKG-1 | NHIDCL | N24001323 | 3-2021 | 9/2022 | 10/2024 | 10/2024 | 486.45 |  | 486.45 | 126.73 | 96.58
April 2025 |  |  | 527 | KHELLANI-KHANABAL PKG-3 | NHIDCL | N24001341 | 3-2021 | 12/2022 | 10/2024 | 5/2025 | 398.51 |  | 398.51 | 80.64 | 95.52
April 2025 |  |  | 528 | KHELLANI-KHANABAL PKG-2 | NHIDCL | N24001394 | 7-2021 | 2/2023 | 6/2025 | 6/2026 | 512.43 |  | 512.43 | 71.65 | 51.21
April 2025 |  |  | 529 | KHELLANI-KHANABAL PKG-4 | NHIDCL | N24001395 | 7-2021 | 8/2023 | 12/2025 | 6/2026 | 859.67 |  | 859.67 | 190.91 | 44.02
April 2025 |  |  | 530 | KHELLANI-KHANABAL PKG-5 | NHIDCL | N24001396 | 7-2021 | 2/2023 | 3/2025 | 8/2025 | 497.09 |  | 497.09 | 172.85 | 87.14
April 2025 |  |  | 531 | GOHA-KHELLANI PKG-3 | NHIDCL | N24001397 | 2-2021 | 3/2023 | 2/2025 | 3/2025 | 431.28 |  | 431.28 | 365.12 | 100
April 2025 |  |  | 532 | BALANCE WORKS OF FOUR LANING FROM RAMBAN KM 151.00 TO BANIHAL KM 187.00 OF NH-1A (NOW NH-44) WITH VA | NHAI | N24001472 | 9-2021 | 12/2023 | 6/2024 | 6/2024 | 811.19 |  | 811.19 | 848.57 | 99
April 2025 |  |  | 533 | CONSTRUCTION OF FOUR LANE RINGROAD BYPASS SRINAGAR CITY | NHAI | N24001511 | 3-2021 | 2/2024 | 4/2025 | 10/2025 | 2919.96 |  | 2919.96 | 2293.76 | 67.5
April 2025 |  |  | 534 | FOUR LANING OF JAMMU- AKHNOOR PKG-1 | NHIDCL | N24001543 | 7-2022 | 1/2025 | N.A. | 10/2025 | 245.34 |  | 245.34 | 57.03 | 38.48
April 2025 |  |  | 535 | DELHI-AMRITSAR-KATRA EXPRESSWAY (PHASE-II PKG- XVI) EXISTING JAKH (VIJAYPUR)- KUNJWANI SECTION OF NH-4 | NHAI | N24001550 | 9-2021 | 9/2024 | 9/2025 | 9/2025 | 1821.72 | 1917.32 | 1917.32 | 1005.24 | 81.2
April 2025 |  |  | 536 | DELHI-AMRITSAR-KATRA EXPRESSWAY (PHASE-II PKG- XIV) FROM JUNCTION WITH PATHANKOT-GURDASPUR ROAD (NH-5 | NHAI | N24001551 | 10-2021 | 9/2024 | 7/2025 | 7/2025 | 3044.02 | 3044.02 | 3044.02 | 1585.04 | 70.15
April 2025 |  |  | 537 | DELHI-AMRITSAR-KATRA EXPRESSWAY (PHASE-II PKG- XV) [JUNCTION WITH HIRANAGAR ROAD NEAR VILLAGE GURHA B | NHAI | N24001552 | 10-2021 | 9/2024 | 9/2025 | 9/2025 | 2714.95 | 2714.95 | 2714.95 | 1641.42 | 83.5
April 2025 |  |  | 538 | CORRIDOR EFFICIENCY IMPROVEMENT INCLUDING REMOVAL OF BLACK SPOTS IN LAKHANPUR - SAMBA SECTION OF NH- | NHAI | N24001619 | 8-2022 | 6/2024 | 6/2025 | 6/2025 | 200.05 | 200.05 | 208.92 | 153.05 | 58.6
April 2025 |  |  | 539 | CONSTRUCTION OF TUNNELS/VIADUCTS AT IDENTIFIED SLIDING/SLIP ZONES AT KM 130.550 TO KM.130.750; KM. | NHAI | N24001620 | 9-2021 | 10/2023 | 12/2025 | 12/2025 | 442.14 |  | 442.14 | 328.36 | 19.88
April 2025 |  |  | 540 | 4L OF KM.165.092 TO KM.171.855 (NORTH BOUND) AND FROM KM.166.895 TO KM.173.638 (SOUTH BOUND), EXCL. | NHAI | N24001621 | 7-2021 | 8/2024 | 6/2025 | 6/2025 | 614.48 |  | 614.48 | 185.83 | 7
April 2025 |  |  | 541 | 4L TWIN TUBE TUNNEL INCLUDING APPROACHES FROM DIGDOL TO KHUNI NALLAH (NORTH BOUND CONNECTING WITH EX | NHAI | N24001622 | 7-2021 | 6/2024 | 6/2025 | 6/2025 | 1401.87 |  | 1401.87 | 686.33 | -
April 2025 |  |  | 542 | BANIHAL BYPASS (DELINKED FROM SRINAGAR - BANIHAL) FROM KM. 187.00 TO KM. 189.350 | NHAI | N24001623 | 1-2020 | 1/2024 | 4/2025 | 4/2025 | 336.01 |  | 336.01 | 222.92 | 34
April 2025 |  |  | 543 | CONSTRUCTION OF EMERGENCY LANDING FACILITY FROM KM. 246.60 TO KM. 249.70 ON SRINAGAR - BANIHAL SECTI | NHAI | N24001624 | 7-2019 | 10/2020 | 4/2023 | 9/2024 | 157.05 |  | 157.05 | 139.54 | 100
April 2025 |  |  | 544 | 4L OF TWIN TUBE TUNNEL CONFIGURATION INCLUDING APPROACHES FROM MAROG TO DIGDOL (FROM KM.154.210 TO K | NHAI | N24001627 | 7-2021 | 2/2025 | 5/2026 | 5/2026 | 1912.17 |  | 1912.17 | 129.05 | -
April 2025 |  |  | 545 | JAMMU - AKHNOOR SECTION OF NH 144A PKG-3B | NHIDCL | N24001833 | 7-2022 | 3/2025 | N.A. | 8/2025 | 198.28 |  | 198.28 | 85.39 | 71.09
April 2025 |  |  | 546 | REHABILITATION AND UPGRADATION TO 2 LANE WITH PAVED SHOULDER FROM EXISTING CHAINAGE KM 102 TO KM 13 | BRO | N24001897 | 3-2021 | 7/2024 | 3/2025 | 3/2024 | 642.24 |  | 642.24 | 345.14 | 95
April 2025 |  |  | 547 | REHABILITATION AND UPGRADATION TO 2 LANE WITH PAVED SHOULDER FROM EXISTING CHAINAGE KM 30.000 TO K | BRO | N24001898 | 7-2020 | 11/2024 | N.A. | 11/2024 | 272.49 |  | 272.49 | 133.66 | 88
April 2025 |  |  | 548 | REHABILITATION AND UPGRADATION TO 2 LANE WITH PAVED SHOULDER FROM EXISTING CHAINAGE KM 134.95 TO KM | BRO | N24001899 | 2-2021 | 7/2024 | N.A. | 3/2025 | 395.25 |  | 395.25 | 140.42 | 64
April 2025 |  |  | 549 | REHABILITATION AND UPGRADATION TO 2 LANE WITH PAVED SHOULDER FROM EXISTING CHAINAGE KM 49.150 TO KM | BRO | N24001900 | 3-2020 | 8/2024 | N.A. | 3/2025 | 796.97 |  | 796.97 | 323.85 | 79
April 2025 |  |  | 550 | REHABILITATION AND UPGRADATION TO 2 LANE WITH PAVED SHOULDER FROM EXISTING CHAINAGE KM 64.535 TO K | BRO | N24001901 | 3-2020 | 9/2023 | N.A. | 3/2025 | 152.93 |  | 152.93 | 90.3 | 78.27
April 2025 |  |  | 551 | CONSTRUCTION OF TWIN TUBE TUNNELS ON JAMMU KASHMIR RING ROAD (NH-244A) BETWEEN DESIGN CH. 50+600 TO | NHAI | N24001926 | 3-2023 | 6/2025 | N.A. | 6/2025 | 939.86 |  | 939.86 | 475.07 | 63.93
April 2025 |  |  | 552 | CONSTRUCTION OF 4 LANE WITH PAVED SHOULDER FROM (DESIGN CH. 14+200 TO 24+400), (DESIGN CH. 35+300 TO | BRO | N24001998 | 6-2022 | 8/2025 | N.A. | 8/2025 | 832.46 |  | 823.46 | 227.5 | 46
April 2025 |  |  | 553 | 2L NH-1 FROM KM 8.660 TO KM 33.775 (SUMBAL TO WAYUL) TO 4L DUAL CARRIAGEWAY NH STANDARD AS PART OF S | NHAI | N24002059 | 9-2022 | 6/2026 | 6/2026 | 12/2026 | 1183.6 |  | 1183.6 | 185.45 | 11.75
April 2025 |  |  | 554 | DELHI AMRITSAR KATRA EXPRESSWAY (PHASE-II PKG XVIII) DEVELOPMENT AND UPGRADATION OF FOUR LANE ACCESS | NHAI | N24002060 | 3-2023 | 11/2025 | N.A. | 11/2025 | 1107 |  | 975.38 | 291.41 | 36.79
April 2025 |  |  | 555 | 4/6L ACCESS CONTROL EXPRESSWAY FROM DESIGN CHAINAGE KM 515.000 TO 528.300 (KUNJWANI TO SIDHRA SECTIO | NHAI | N24002061 | 8-2022 | 6/2025 | N.A. | 8/2025 | 2474.47 |  | 2894.74 | 923.45 | 36.2
April 2025 |  |  | 556 | REHABILITATION AND UPGRADATION TO 2 LANE WITH PAVED SHOULDER FROM DESIGN CHAINAGE KM 162.800 TO KM | BRO | N24002119 | 10-2022 | 1/2026 | N.A. | 1/2026 | 562.45 |  | 562.45 | 99.06 | 25
April 2025 |  |  | 557 | CONSTRUCTION OF 4 LANE WITH PAVED SHOULDER (PATTAN BYPASS) GREENFIELD BYPASS FROM EXISTING CH. KM 24 | BRO | N24002179 | 3-2023 | 7/2026 | N.A. | 7/2026 | 980.21 |  | 980.21 | 300.02 | 8
April 2025 |  |  | 558 | REHABILITATION AND UPGRADATION TO 2 LANE WITH PAVED SHOULDER FROM EXISTING CHAINAGE KM 166.100 TO KM | BRO | N24002180 | 9-2021 | 7/2026 | N.A. | 7/2026 | 734.64 |  | 734.64 | 19.6 | 8
April 2025 |  |  | 559 | CONSTRUCTION OF 2 LANE WITH PAVED SHOULDERS (BARAMULLA BYPASS) GREENFIELD BYPASS FROM EXISTING CH. K | BRO | N24002185 | 3-2023 | 9/2026 | N.A. | 9/2026 | 992.43 |  | 992.43 | 338.33 | -
April 2025 |  |  | 560 | WIDENING AND STRENGTHENING OF RAFIABAD- KUPWARA-CHOWKIBAL- TANGDHAR-CHAMKOT (NH-701) ROAD FROM DESIGN | BRO | N24002210 | 3-2024 | 5/2027 | N.A. | 5/2027 | 1404.94 |  | 1404.94 | 0 | -
April 2025 |  |  | 561 | RAJRAPPA RCE OCP ( 3.0 MTY) | CCL | N06000087 | 12-2009 | 3/2016 | N.A. | 3/2027 | 510.85 |  | 510.85 | 488.57 | 75
April 2025 |  |  | 562 | MURAIDIH UG TURN-KEY PROJECT | BCCL | N06000096 | 2-2011 | 4/2014 | N.A. | 1/2026 | 339.88 |  | 339.88 | 190.48 | 70
April 2025 |  |  | 563 | MOONIDIH XV SEAM UG | BCCL | N06000098 | 8-2011 | 3/2019 | N.A. | 5/2026 | 1230.27 |  | 1230.27 | 603.82 | 81
April 2025 |  |  | 564 | CHITRA EAST (RCE) OCP | ECL | N06000169 | 8-2018 | 3/2026 | 3/2026 | 3/2026 | 513.98 |  | 513.98 | 227.24 | 51
April 2025 |  |  | 565 | TETARIAKHAR EXPANSION OCP | CCL | N06000186 | 11-2019 | 3/2023 | N.A. | 3/2027 | 243.52 |  | 243.52 | 44.64 | 24
April 2025 |  |  | 566 | PACHWARA SOUTH COAL BLOCK | NLC | N06000193 | 7-2013 | 9/2028 | N.A. | 9/2028 | 2242.92 | 2242.9 | 2242.9 | 583.81 | 54
April 2025 |  |  | 567 | PATHERDIH 2.5 NLW COAL WASHERY | BCCL | N06000194 | 10-2015 | 4/2018 | N.A. | 3/2026 | 334.27 |  | 334.27 | 135.25 | 45
April 2025 |  |  | 568 | REVISED PROJECT REPORT MAGADH EXPANSION OCP | CCL | N06000216 | 8-2020 | 3/2028 | N.A. | 3/2028 | 7254.37 |  | 7254.37 | 1495.43 | 29
April 2025 |  |  | 569 | EXPANSION PROJECT AMRAPALI OCP | CCL | N06000217 | 8-2020 | 3/2028 | N.A. | 3/2028 | 5136.15 |  | 5136.15 | 1063.25 | 41
April 2025 |  |  | 570 | UCE OF EPR OF NORTH URIMARI OCP | CCL | N06000218 | 7-2021 | 3/2029 | N.A. | 3/2029 | 778.8 |  | 778.8 | 694.11 | 75
April 2025 |  |  | 571 | KOTRE BASANTPUR PACHMO OCP | CCL | N06000237 | 8-2020 | 3/2032 | N.A. | 3/2032 | 625.4 | 625.4 | 625.4 | 441.24 | 41
April 2025 |  |  | 572 | CHANDRAGUPT OCP | CCL | N06000238 | 8-2020 | 3/2032 | N.A. | 3/2032 | 973.5 |  | 973.5 | 339.32 | 12.4
April 2025 |  |  | 573 | SIRKA OCP | CCL | N06000239 | 5-2020 | 3/2028 | N.A. | 3/2028 | 222.82 |  | 222.82 | 139.31 | 60
April 2025 |  |  | 574 | JHARKHAND LAIYO OCP | CCL | N06000240 | 8-2020 | 3/2031 | N.A. | 3/2031 | 764.57 |  | 764.57 | 145.8 | 28
April 2025 |  |  | 575 | EPR TAPIN SOUTH OCP | CCL | N06000241 | 11-2020 | 3/2028 | N.A. | 3/2028 | 230.41 |  | 230.41 | 20.77 | 18.3
April 2025 |  |  | 576 | EPR PUNDI OCP | CCL | N06000242 | 11-2020 | 3/2027 | N.A. | 3/2027 | 713.35 |  | 713.35 | 236.57 | 21
April 2025 |  |  | 577 | EPR ROHINI KARKATA OCP | CCL | N06000243 | 1-2021 | 3/2028 | N.A. | 3/2028 | 1020.42 |  | 1020.42 | 83.44 | 11.7
April 2025 |  |  | 578 | EXPANSION OF KONAR OCP | CCL | N06000245 | 1-2022 | 3/2032 | N.A. | 3/2032 | 799.34 |  | 799.34 | 416.73 | 32
April 2025 |  |  | 579 | EXPANSION OF KARO OCP | CCL | N06000246 | 1-2022 | 3/2029 | N.A. | 3/2029 | 908.47 |  | 908.47 | 217.68 | 20
April 2025 |  |  | 580 | EXPANSION OF ASHOK OCP | CCL | N06000247 | 5-2021 | 3/2028 | N.A. | 3/2028 | 2898.28 |  | 2898.28 | 176.5 | 20
April 2025 |  |  | 581 | AMALGAMATED NTST KUJAMA OCP 8.5 MTY | BCCL | N06000273 | 1-2023 | 3/2030 | N.A. | 3/2030 | 4011.85 |  | 4011.85 | 397.65 | 25
April 2025 |  |  | 582 | HURA C OC | ECL | N06000275 | 8-2022 | 3/2029 | N.A. | 3/2029 | 859.41 |  | 859.41 | 442.98 | 62
April 2025 |  |  | 583 | CHUPERBHITA- SIMLONG OCP | ECL | N06000280 | 12-2023 | 3/2037 | 3/2037 | 3/2037 | 979.08 |  | 979.08 | 0 | -
April 2025 |  |  | 584 | BLOCK-E OCP (15 MTY) | BCCL | N06000287 | 3-2024 | 3/2029 | N.A. | 3/2029 | 5850.83 |  | 5850.83 | 5.85 | 2
April 2025 |  | DEPARTMENT OF HIGHER EDUCATION | 585 | 2000 BOYS HOSTEL(1000 DOUBLE BEDDED ROOM) AT ISM DHANBAD | CPWD EDUCATION | N28000067 | 9-2012 | 3/2016 | N.A. | 3/2016 | 171.86 |  | 171.86 | 174.48 | 99
April 2025 |  | DEPARTMENT OF HIGHER EDUCATION | 586 | DEVELOPMENT OF JHARIA CBM BLOCK (PHASE-1) | ONGC | N16000445 | 11-2019 | 1/2024 | 3/2025 | 6/2025 | 431 |  | 431 | 186.95 | 57.9
April 2025 |  | DEPARTMENT OF HIGHER EDUCATION | 587 | LAYING OF NATURAL GAS PIPELINE FROM HAZARIBAGH TO RANCHI | IOCL | N16000480 | 3-2023 | 2/2026 | N.A. | 2/2026 | 202.07 |  | 202.07 | 48.39 | 42.06
April 2025 |  |  | 588 | CGD PROJECT IN BIHAR JHARKHAND | HPCL | N16000497 | 6-2022 | 6/2030 | N.A. | 6/2030 | 1377 |  | 1377 | 274.32 | 22
April 2025 |  | POWER | 589 | NORTH KARANPURA STPP | 3X660 MW | NTPC | 2-2014 | 6/2019 | 10/2022 | 3/2025 | 16242.9 |  | 16242.9 | 16745.68 | 98
April 2025 |  | POWER | 590 | PATRATU STPP-I (3X800MW) | NTPC | N18000275 | 11-2017 | 3/2023 | N.A. | 3/2026 | 17112 |  | 17112 | 16305.18 | 81
April 2025 |  | POWER | 591 | BADAM COAL MINING PROJECT | NTPC | N18000367 | 2-2019 | 10/2024 | 4/2027 | 4/2027 | 501.79 | 784.39 | 501.79 | 302.22 | 59.79
April 2025 |  | POWER | 592 | KERANDARI COAL MINING PROJECT | NTPC | N18000370 | 9-2015 | 11/2019 | 3/2025 | 3/2025 | 1553 | 2896.64 | 2896.64 | 2014.94 | 64
April 2025 |  | POWER | 593 | KODERMA-TILAIYA (NL), ECR | ECR | 220100305 | 4-2002 | 3/2023 | N.A. | 12/2025 | 1625.87 | 1625.87 | 1700 | 2000.95 | 80
April 2025 |  | POWER | 594 | BONDAMUNDA RANCHI DOUBLING | SER | N22000396 | 3-2016 | 6/2024 | N.A. | 6/2026 | 3029.04 | 3029.04 | 3029.04 | 2349.31 | 83
April 2025 |  | POWER | 595 | LODHMA TO PISKA LINK LINE BY PASSING HATIA/RANCHI WITH Y CONNECTION (17.2 KM) | SER | N22000508 | 4-2018 | 6/2026 | N.A. | 6/2026 | 501.52 |  | 472.5 | 275.66 | 2
April 2025 |  |  | 596 | DOUBLING OF PRADHANKHUNTA JN - PATHERDIH BAZAR-BHOJUDIH | ECR | N22000529 | 11-2022 | 11/2027 | N.A. | 3/2026 | 202 | 349.22 | 349.22 | 57.76 | 2
April 2025 |  |  | 597 | KHARAGPUR-ADITYAPUR - 3RD LINE (132 KM) | RVNL | N22000595 | 12-2015 | 3/2025 | N.A. | 3/2025 | 3249.98 |  | 3270.07 | 2899.45 | -
April 2025 |  |  | 598 | 3RD LINE BETWEEN DHANBAD SONNAGAR | RVNL | N22000599 | 11-2016 | 3/2026 | N.A. | 3/2026 | 8975 |  | 7906.38 | 4705.38 | -
April 2025 |  |  | 599 | GARHWA ROAD - RAIL OVER RAIL | ECR | N22000610 | 3-2017 | 6/2024 | N.A. | 2/2026 | 262.71 |  | 262.71 | 221.66 | 70
April 2025 |  |  | 600 | GOMOH - FLYOVER FOR DOWN TRAINS | ECR | N22000611 | 1-2018 | 3/2023 | N.A. | 3/2026 | 686.03 |  | 487.73 | 385.56 | 45
April 2025 |  |  | 601 | SIX LANING OF BIHAR - JHARKHAND BORDER (CHORDAHA) TO GORHAR SECTION | NHAI | N24000726 | 1-2018 | 11/2021 | 6/2025 | 6/2025 | 1155.16 |  | 950.49 | 657.82 | 70
April 2025 |  |  | 602 | WIDENING TO 2 LANE WITH PAVED SHOULDERS AND GEOMETRIC IMPROVEMENT OF NH-114A FROM KM 141 TO KM 184 I | MoRTH | N24001216 | 12-2016 | 9/2021 | N.A. | 12/2024 | 196 |  | 196 | 164.21 | 90.1
April 2025 |  |  | 603 | HARIHARGANJ TO PARWA MODE SECTION FROM KM 23.284 TO KM 57.049 OF NH-98 | NHAI | N24001589 | 9-2020 | 3/2024 | 12/2024 | 4/2025 | 755.26 |  | 1039 | 621.92 | 85.8
April 2025 |  |  | 604 | 4L FROM KM 196.87 (SANKHA) TO KM 219.6 (KHAJURI) ON NH- 75 [REHLA / GARHWA BYPASS] | NHAI | N24001590 | 9-2020 | 10/2023 | 12/2024 | 1/2025 | 748.99 |  | 903 | 831.75 | 100
April 2025 |  |  | 605 | ELEVATED CORRIDOR IN RANCHI CITY FROM KM 0.00 TO KM 3.260 OF NH-75 INCLUDING DOWN RAMP ON NH-23 FROM | NHAI | N24001594 | 2-2022 | 1/2025 | 3/2025 | 3/2025 | 534.73 |  | 534.73 | 155.31 | 97
April 2025 |  |  | 606 | 4L OF PALMA TO GUMLA SECTION OF NH23 FROM KM. 26.00 TO KM. 89.170 ON HAM MODE IN THE STATE OF JHARKH | NHAI | N24001595 | 8-2020 | 3/2024 | 6/2025 | 6/2025 | 1034 | 1879.55 | 1879.55 | 41.5 | 96.5
April 2025 |  |  | 607 | 4L OF MIRZA CHAUKI TO FARKKA SECTION OF NH80 FROM KM 215.00 TO KM 260.00 ON HAM MODE IN THE STATE OF | NHAI | N24001596 | 11-2021 | 7/2023 | 6/2025 | 6/2025 | 1302.72 | 1504.8 | 1504.8 | 875.86 | 74.51
April 2025 |  |  | 608 | FOUR LANING WITH PAVED SHOULDER OF SECTION FROM KM 53.600 (GOLA ON NH-320) TO KM 81.446 (ORMANJHI ON | NHAI | N24001854 | 6-2023 | 6/2025 | N.A. | 6/2025 | 1214.93 | 1324.95 | 1462 | 998.69 | 70
April 2025 |  |  | 609 | WIDENING TO 2-LANE WITH PAVED SHOULDER FROM KM 0.00 TO 44.00 (KURU-GHAGHRA SECTION) OF NH-143A INCLU | MoRTH | N24001922 | 2-2020 | 8/2023 | N.A. | 12/2024 | 153.01 |  | 153.01 | 83.63 | 96.23
April 2025 |  |  | 610 | WIDENING AND STRENGTHENING OF EXISTING PAVEEMNT TO TWO LANE WITH PAVED SHOULDERS FROM KM 116.00 TO K | MoRTH | N24001923 | 1-2022 | 7/2024 | N.A. | 12/2024 | 315.21 |  | 315.21 | 117.26 | 80
April 2025 |  |  | 611 | WIDENING AND STRENGTHENING TO TWO LANE WITH PAVED SHOULDER/TWO LANE+ PAVED SHOULDER WITH SERVICE ROA | MoRTH | N24001924 | 3-2022 | 8/2025 | N.A. | 8/2025 | 514.22 |  | 514.22 | 15.19 | 6.1
April 2025 |  |  | 612 | WIDENING AND STRENGTHENING/RECONSTRUC TION TO TWO LANE WITH PAVED SHOULDER/ TWO LANE WITH PAVED SHOUL | MoRTH | N24001925 | 3-2022 | 8/2025 | N.A. | 8/2025 | 423.18 |  | 423.18 | 0.11 | -
April 2025 |  |  | 613 | FOUR LANING OF KHAJURI TO WYNDHAMGANJ FROM KM 219.600 TO KM 260.483 ON NH-75 PKG SEC-V ON HAM | NHAI | N24002053 | 4-2022 | 9/2025 | N.A. | 9/2025 | 1232 | 1343 | 1400 | 606.6 | 77.45
April 2025 |  |  | 614 | FOUR LANING OF BHOGU TO SANKHA FROM KM 147.450 TO KM 196.870 ON NH-75 PKG SEC- III | NHAI | N24002054 | 10-2022 | 11/2025 | N.A. | 11/2025 | 1390.77 | 1391 | 1600 | 296.46 | 65.95
April 2025 |  |  | 615 | FOUR LANING OF BASUKINATH- DEOGHAR SECTION OF NH-114A FROM KM 85.081 TO KM 130.240 UNDER NHDP PHASE-I | NHAI | N24002055 | 3-2023 | 12/2025 | N.A. | 12/2025 | 1444.94 |  | 1444.94 | 0 | -
April 2025 |  |  | 616 | BHARATMALA PARIYOJANA OF BOKARO JAINA MORE - GOLA SECTION OF NH-320 FROM KM. 21.110 TO KM. 53.600 IN | NHAI | N24002056 | 6-2020 | 6/2025 | N.A. | 6/2025 | 964.64 |  | 964.64 | 432.7 | 52.91
April 2025 |  |  | 617 | FOUR LANING OF MEHGAMA HANSDIHA SECTION OF NH-33 FROM EXISTING KM 41.900 TO 93.000 IN THE STATE OF J | NHAI | N24002057 | 12-2022 | 5/2025 | N.A. | 5/2025 | 1443.77 |  | 1443.77 | 0 | -
April 2025 |  | STEEL | 618 | NEW SINTER PLANT AT BOKARO STEEL PLANT | SAIL | N12000095 | 3-2015 | 10/2017 | 11/2026 | 11/2026 | 1034.01 | 1752.3 | 1752.3 | 874.42 | 51.75
April 2025 |  | STEEL | 619 | REVAMPING OF OLD SUB SYSTEM OF BLAST FURNACE 3 AT BOKARO STEEL PLANT | SAIL | N12000129 | 9-2023 | 7/2025 | 11/2025 | 11/2025 | 513.82 |  | 513.82 | 153.95 | 62
April 2025 |  | STEEL | 620 | REBUILDING OF COKE OVEN BATTERY NO.6 OF BOKARO STEEL PLANT | SAIL | N12000133 | 11-2023 | 11/2026 | N.A. | 11/2026 | 627.31 |  | 627.31 | 80.19 | 31
April 2025 |  | STEEL | 621 | REPLACEMENT OF REMAINING 04 NOS. OF BATTERY CYCLONES WITH 04 NOS. OF ESPS IN SINTER PLANT-1 AT BSL | SAIL | N12000135 | 3-2024 | 6/2026 | N.A. | 6/2026 | 260.37 |  | 260.37 | 39.21 | 10
April 2025 |  | STEEL | 622 | REPLACEMENT OF EXISTING GRINDERS IN CRM-I & II AT BOKARO STEEL PLANT | SAIL | N12000142 | 1-2025 | 1/2027 | N.A. | 1/2027 | 211.94 |  | 211.94 | 0 | -
April 2025 |  | STEEL | 623 | SECONDARY EMISSION CONTROL IN CONVERTERS OF SMS-II AT BOKARO STEEL PLANT | SAIL | N12000143 | 1-2025 | 10/2026 | N.A. | 10/2026 | 207.13 |  | 207.13 | 0
April 2025 |  | CIVIL AVIATION | 624 | BELAGAVI AIRPORT- EXPANSION OF TERMINAL BUILDING AND ASSOCIATED WORKS | AAI | N04000105 | 6-2023 | 2/2026 | N.A. | 2/2026 | 322.45 |  | 322.45 | 88.75 | 38
April 2025 |  | CIVIL AVIATION | 625 | HUBBALI AIRPORT - CONSTRUCTION OF NEW DOMESTIC TERMINAL BUILDING AND MISCELLANEOUS WORKS | AAI | N04000108 | 6-2023 | 2/2026 | N.A. | 2/2026 | 320.47 |  | 320.47 | 49.67 | 27
April 2025 |  | DEPARTMENT OF HIGHER EDUCATION | 626 | CONSTRUCTION OF PERMANENT CAMPUS FOR INDIAN INSTITUTE OF TECHNOLOGY, DHARWAD | PHASE 1A | CPWD EDUCATION | 7-2019 | 3/2022 | 6/2025 | 11/2025 | 851 | 930.36 | 930.36 | 918.06 | 98.75
April 2025 |  | DEPARTMENT OF HIGHER EDUCATION | 627 | ADDITIONAL INFRASTRUCTURE AT IISC BANGALORE SH RCC MONOLITHIC FOR MEN WOMEN HOSTEL | CPWD | N42000010 | 8-2021 | 2/2024 | 11/2024 | 11/2024 | 316.25 |  | 316.25 | 281.32 | 94
April 2025 |  | DEPARTMENT OF HIGHER EDUCATION | 628 | CONSTRUCTION OF 80000MT LPG CAVERN AT MANGALORE | HPCL | N16000369 | 12-2018 | 12/2022 | 8/2025 | 8/2025 | 854 | 854 | 854 | 692.71 | 97.2
April 2025 |  | DEPARTMENT OF HIGHER EDUCATION | 629 | REVAMPING, AUGMENTATION OF FACILITIES AT EXISTING PORT TERMINAL AT MANGALORE | IOCL | N16000437 | 1-2022 | 7/2025 | 12/2025 | 12/2025 | 463 | 500.62 | 500.62 | 233.4 | 70.72
April 2025 |  | DEPARTMENT OF HIGHER EDUCATION | 630 | POWER SYSTEM UPGRADATION PROJECT | MANGALORE REFIN | N16000509 | 10-2023 | 2/2026 | N.A. | 2/2026 | 385 |  | 385 | 121.87 | 52.41
April 2025 |  |  | 631 | DEMO PLANT FOR PRODUCTION OF BIO-ATF | MANGALORE REFIN | N16000536 | 3-2024 | 3/2027 | N.A. | 3/2027 | 364 |  | 364 | 9.92 | 5.2
April 2025 |  | POWER | 632 | TS FOR INTRGRATION OF RE ZONE (PHASE II) IN KOPPAL II (PHASE A and B) AND GADAG II (PHASE A) IN KARN | PGCIL | N18000385 | 12-2023 | 12/2025 | N.A. | 12/2025 | 2889 |  | 2889 | 602 | 24.9
April 2025 |  | POWER | 633 | TS FOR SOLAR ENERGY ZONE IN BIDAR (2500MW), KARNATAKA [BIDAR TRANSMISSION LTD] | PGCIL | N18000388 | 2-2024 | 2/2026 | N.A. | 2/2026 | 2148 |  | 2148 | 557 | 36
April 2025 |  | POWER | 634 | SYSTEM STRENGTHENING AT KOPPAL-II AND GADAG-II FOR INTEGRATION OF RE GENERATION PROJECTS | PGCIL | N18000409 | 1-2025 | 1/2027 | N.A. | 1/2027 | 1354 |  | 1354 | 0 | -
April 2025 |  | POWER | 635 | AUGMENTATION OF TRANSFORMATION CAPACITY AT BIDAR PS | PGCIL | N18000410 | 2-2025 | 2/2027 | N.A. | 2/2027 | 288 |  | 288 | 0 | -
April 2025 |  | POWER | 636 | TUMKUR-CHITRADURGA- DAVENGERE NL | SWR | N22000256 | 4-2011 | 3/2019 | N.A. | 12/2027 | 1876 |  | 1801.01 | 494.03 | 12
April 2025 |  | POWER | 637 | BAGALKOT-KUDACHI NL | SWR | N22000258 | 4-2010 | 3/2027 | N.A. | 3/2027 | 1378 | 1378 | 1378 | 627.04 | 34
April 2025 |  | POWER | 638 | HOSPET-HUBLI-LONDA- VASCODAGAMA DL | RVNL | N22000297 | 4-2010 | 3/2027 | N.A. | 12/2026 | 5060.36 |  | 3692.6 | 3505.49 | -
April 2025 |  |  | 639 | GADAG-WADI NL | SWR | N22000299 | 4-2013 | 3/2027 | N.A. | 12/2027 | 2841.84 |  | 2841.84 | 1300.11 | 28
April 2025 |  |  | 640 | MARIKUPPAM - KUPPAM | SWR | N22000308 | 4-2012 | 3/2016 | N.A. | 12/2027 | 279.54 | 296.72 | 296.72 | 120.94 | 14
April 2025 |  |  | 641 | KADUR CHIKMAGALUR SAKLESHPUR NEW LINE (93 KM) | SWR | N22000486 | 3-1996 | 6/2025 | N.A. | 3/2026 | 825.31 | 825.31 | 825.31 | 682.36 | 66
April 2025 |  |  | 642 | BAIYYAPPANAHALLI-HOSUR (48 KM) | NCRTC | N22000542 | 4-2019 | 3/2026 | N.A. | 3/2026 | 375.67 |  | 375.67 | 0 | -
April 2025 |  |  | 643 | YESHVANTHPUR- CHANNASANDRA (21.7 KM) | NCRTC | N22000543 | 4-2019 | 3/2026 | N.A. | 3/2026 | 169.65 |  | 169.65 | 71.75 | -
April 2025 |  |  | 644 | BELGAUM-DHARWAD VIA KITTUR (73.10 KM) (UMBRELLA WORK PB#22/2019-20/NR) | SWR | N22000557 | 9-2020 | 12/2027 | N.A. | 12/2027 | 1590.8 | 927.42 | 927.42 | 0.72 | -
April 2025 |  |  | 645 | HASSAN (ALUR) - BELUR (32 KM) (UMBRELLA WORK PB#23/2018- 19/NR) | SWR | N22000558 | 6-2019 | 4/2028 | N.A. | 3/2028 | 748.86 | 748.85 | 748.85 | 0.88 | 1
April 2025 |  |  | 646 | SHIMOGA-SHIKARIPURA- RANEBENNUR (UMBRELLA WORK PB#23/2018-19/NR) | SWR | N22000559 | 9-2019 | 12/2027 | N.A. | 12/2027 | 1453.73 | 994.47 | 994.47 | 71.25 | 7
April 2025 |  |  | 647 | BANGALORE-WHITEFIELD- BANGALORE CITY- KRISHNARAJAPURAM QUADRUPLING | SWR | N22000621 | 3-2018 | 6/2025 | N.A. | 6/2025 | 492.87 |  | 492.87 | 241.18 | 75
April 2025 |  |  | 648 | STRENGTHENING AND WIDENING TO TWO LANE WITH PAVED SHOULDERS FROM KM.106.00 TO 153.00 OF NH-218 BIJAP | MoRTH | N24000334 | 3-2015 | 11/2015 | 8/2024 | 8/2024 | 165.67 |  | 165.67 | 126.47 | 99
April 2025 |  |  | 649 | 4-LANING OF GOA/KARNATAKA BORDER-KUNDAPUR SECTION | NHAI | N24000462 | 7-2012 | 8/2016 | 1/2020 | 6/2025 | 1655.01 | 1990.99 | 1990.99 | 1818.12 | 97.8
April 2025 |  |  | 650 | HOSPET-BELLARY-KARNATAKA AP BORDER | NHAI | N24000603 | 8-2016 | 3/2019 | 5/2025 | 5/2025 | 1167.42 |  | 1224.01 | 1028.39 | 86.35
April 2025 |  |  | 651 | WIDENING TO TWO LANE WITH PAVED SHOULDER FROM KM 544.200 TO KM 594.000 OF NH- 150A HOSMANE CROSS ? PA | MoRTH | N24001156 | 1-2017 | 9/2017 | 5/2023 | 5/2023 | 166.67 |  | 264.34 | 192.08 | 100
April 2025 |  |  | 652 | IMPROVEMENTS AND RECONSTRUCTION TO TWO LANE WITH PAVED SHOULDERS FROM KM 243.20 TO KM 290.20 OF NH | MoRTH | N24001157 | 8-2016 | 2/2017 | 7/2024 | 7/2024 | 175.5 |  | 241.6 | 178.73 | 90.1
April 2025 |  |  | 653 | RECONSTRUCTION TO TWO LANE WITH PAVED SHOULDERS FROM DS. CH. 442+180 (EX. KM 448.00) TO DS. CH.485+2 | MoRTH | N24001158 | 3-2018 | 6/2019 | 12/2023 | 12/2023 | 159.97 |  | 242.61 | 113.15 | 100
April 2025 |  |  | 654 | WIDENING TO TWO LANE WITH PAVED SHOULDERS FROM KM 20.150 TO KM 40.00 OF BC ROAD KOTTIGEHARA SECTION | MoRTH | N24001159 | 1-2018 | 7/2018 | N.A. | 3/2022 | 159.7 |  | 159.7 | 142.88 | 100
April 2025 |  |  | 655 | WIDENING TO TWO LANE WITH PAVED SHOULDER FROM KM 194.900 TO KM 243.200 OF NH- 234 BANAVARA-HULIYAR | MoRTH | N24001160 | 9-2017 | 10/2018 | 4/2022 | 4/2022 | 191.6 |  | 191.6 | 112.01 | 100
April 2025 |  |  | 656 | WIDENING TO TWO LANE WITH PAVED SHOULDERS FROM 24.600 TO 70.063 OF MUDIGERE TO KADUR SECTION OF NH- | MoRTH | N24001161 | 12-2017 | 1/2019 | 4/2022 | 4/2022 | 297.3 |  | 318.28 | 277.27 | 100
April 2025 |  |  | 657 | IMPROVEMENT AND RECONSTRUCTION TO TWO LANE WITH PAVED SHOULDERS FROM KM 489.845 (NEW KM.58.125) AN | MoRTH | N24001162 | 3-2018 | 10/2018 | 11/2022 | 11/2022 | 325.86 |  | 386.41 | 356.76 | 100
April 2025 |  |  | 658 | WIDENING TO 2 LANE WITH PAVED SHOULDERS FROM KM 0 TO 54 OF NH-50 UNDER EPC MODE IN THE STATE OF KARN | MoRTH | N24001164 | 10-2016 | 3/2017 | 7/2022 | 7/2022 | 396.96 |  | 396.96 | 329.58 | 100
April 2025 |  |  | 659 | WIDENING TO 2 LANE WITH PAVED SHOULDERS FROM KM 34.00 TO 70.900 OF NH-150 UNDER EPC MODE IN THE STAT | MoRTH | N24001165 | 11-2016 | 3/2017 | 10/2021 | 10/2021 | 314.9 |  | 314.9 | 233.95 | 100
April 2025 |  |  | 660 | WIDENING TWO LANE WITH PAVED SHOULDERS FROM FROM KM.56.00 TO 106.00 OF NH- 218 (218-KNT-2014-15-775) | MoRTH | N24001166 | 3-2015 | 1/2016 | N.A. | 7/2024 | 159.12 |  | 159.12 | 127.72 | 98.06
April 2025 |  |  | 661 | ESTIMATE FOR WIDENING TWO LANE TO FOUR LANE FROM FROM KM.129.00 TO 144.00 OF NH-63 ANKOLA-GOOTY SECT | MoRTH | N24001168 | 5-2018 | 5/2018 | 12/2023 | 12/2023 | 171.6 |  | 171.6 | 129.72 | 100
April 2025 |  |  | 662 | WIDENING TO TWO LANE WITH PAVED SHOULDER FROM KM 4.40 TO KM 56.00 OF NH-218 BIJAPURA-HUBLI SECTION U | MoRTH | N24001172 | 1-2017 | 8/2017 | N.A. | 6/2022 | 291.49 |  | 291.49 | 238.77 | 100
April 2025 |  |  | 663 | CONSTRUCTION OF MAJOR BRIDGE AT KM 180.865 ACROSS RIVER KRISHNA ON NH-167 HAGARI ? JADERCELA SECTION | MoRTH | N24001173 | 2-2017 | 5/2019 | N.A. | 10/2025 | 157.32 | 188 | 187.61 | 43.16 | 60
April 2025 |  |  | 664 | WIDENING TO 2-LANE WIH PAVED SHOULDER FROM KM. 544.20 TO 594.00 (HOSAMANE CROSS TO PANDAVAPURA) SECT | MoRTH | N24001387 | 1-2017 | 9/2017 | 5/2023 | 5/2023 | 264.34 |  | 264.34 | 201.07 | 100
April 2025 |  |  | 665 | CONSTRUCTION OF MAJOR BRIDGE ACROSS SHARAVATHI BACKWATERS AND APPROCHES BETWEEN AMBARGODU AND KALASA | MoRTH | N24001388 | 3-2019 | 12/2019 | 11/2024 | 11/2024 | 423.15 |  | 423.15 | 268.97 | 82
April 2025 |  |  | 666 | 4L OF ADDAHOLE TO BANTWAL CROSS SECTION INCLUDING FLYOVER AT KALLADKA TOWN | NHAI | N24001425 | 3-2021 | 11/2021 | 11/2025 | 11/2025 | 1100.88 | 1687.31 | 1687.31 | 1098.32 | 78.8
April 2025 |  |  | 667 | 4L OF ADDAHOLE TO BANTWAL CROSS SECTION | NHAI | N24001426 | 3-2021 | 10/2021 | 5/2025 | 5/2025 | 317.9 | 572.01 | 572.01 | 369.95 | 97.42
April 2025 |  |  | 668 | 6L FROM SANKESHWAR BYPASS TO MH KNT BORDER FROM KM. 555.017 TO KM. 592.853 OF NH- 48 (PKG II) | NHAI | N24001598 | 1-2022 | 4/2025 | 4/2025 | 4/2025 | 1388.7 | 1388.7 | 1388.7 | 438.61 | 62.5
April 2025 |  |  | 669 | BELAKERI PORT TO KUMTA - SIRSI ROAD FROM KM 0.00 - KM 4.265 OF BELEKERI PORT ROAD LINK RD. AND KM 4. | NHAI | N24001599 | 3-2018 | 12/2022 | 12/2022 | 11/2025 | 440.16 |  | 440.16 | 350.41 | 68.79
April 2025 |  |  | 670 | BANGALORE/TN BORDER TO HOSKOTE | NHAI | N24001674 | 2-2023 | 2/2025 | 9/2025 | 9/2025 | 1240.6 | 1240.6 | 1240.6 | 935.35 | 80.2
April 2025 |  |  | 671 | 6L OF MH/KN BORDER (NIMBAL VILLAGE) TO KN/TS BORDER (SINGNODI VILLAGE) FROM KM. 26.000 TO KM. 97.000 | NHAI | N24001676 | 12-2022 | 6/2025 | 3/2026 | 6/2025 | 2718.46 |  | 2718.46 | 438.9 | 52.2
April 2025 |  |  | 672 | BALANCE WORK OF 2L PS FROM KM 30.800 TO 70.800 AND 2L WITH RIGID CARRIAGEWAY FROM 70.800 TO KM 84.12 | NHAI | N24001677 | 11-2022 | 5/2024 | 5/2024 | 5/2024 | 226.76 | 226.76 | 226.76 | 86.76 | 68.7
April 2025 |  |  | 673 | 6L FROM BELGAUM TO SANKESHWAR BYPASS FROM KM 515.000 TO KM 555.017 OF NH 48 | NHAI | N24001679 | 10-2022 | 4/2025 | 4/2025 | 4/2025 | 1479.3 | 1479.3 | 1479.3 | 580.74 | 78.2
April 2025 |  |  | 674 | 4L OF SANNUR TO BIKARNAKATTE SECTION FROM KARKALA TO MANGALORE | NHAI | N24001680 | 3-2021 | 10/2024 | 1/2026 | 1/2026 | 1409.68 | 1808.12 | 1808.12 | 999.67 | 58.7
April 2025 |  |  | 675 | TUMKUR - NELAMANGALA(6L) | NHAI | N24001681 | 8-2022 | 8/2025 | 3/2026 | 3/2026 | 2032.15 | 2032.15 | 2032.15 | 182.43 | 51.58
April 2025 |  |  | 676 | UPGRADATION 2/4 LANE NH CONNECTIVITY UNDER SAGARMALA SCHEME SH 2 HAVERI YEKAMBI SH 69 YEKAMBI KUMTA | NHAI | N24001682 | 11-2021 | 3/2024 | 3/2024 | 12/2026 | 294.62 | 309.9 | 309.9 | 55.68 | 15.06
April 2025 |  |  | 677 | 4L OF CHANNARAYAPATNA BYPASS AND HASSAN BYPASS WITH STRUCTURES IN DEVIHALLI -HASSAN SECTION | NHAI | N24001684 | 9-2020 | 1/2023 | 9/2020 | 5/2025 | 688 | 602.09 | 688 | 514.23 | 80.02
April 2025 |  |  | 678 | FOUR LANING OF BETTADAHALLI TO SRIRAMPURA SECTION FROM KM. 166+100 (DESIGN KM. 170+415) TO KM. 217+0 | NHAI | N24001687 | 10-2021 | 10/2023 | 12/2025 | 12/2025 | 1331.77 | 2082.98 | 2082.98 | 470.87 | 76.06
April 2025 |  |  | 679 | BALANCE WORK OF CONTSRUCTION OF TWO/FOUR LANE WITH PAVED SHOULDER FROM KM. 54.370 TO KM. 101.400 (BI | MoRTH | N24001936 | 3-2021 | 3/2023 | 7/2024 | 7/2024 | 344.79 |  | 344.79 | 10 | 90
April 2025 |  |  | 680 | BALANCE WORK OF REHABILITATION AND UPGRADING TO 2LANE/2LANE WITH PAVED SHOULDER CONFIGURATION AND ST | MoRTH | N24001937 | 2-2023 | 2/2024 | 2/2025 | 2/2025 | 398.48 |  | 398.48 | 5 | 50
April 2025 |  |  | 681 | CONSTRUCTION OF ELEVATED CORRIDOR FROM KM. 135.650 TO 136.300 ON 63, FROM KM. 249 TO KM. 250.050 ON | MoRTH | N24001938 | 6-2021 | 6/2024 | 6/2025 | 6/2025 | 298 |  | 298 | 10.7 | 52
April 2025 |  |  | 682 | WIDENING TO 2 LANE WITH PAVED SHOULDERS FROM DESIGN KM 103.200 (EXISTING KM 103.200) TO DESIGN KM 11 | MoRTH | N24001940 | 1-2023 | 1/2026 | 9/2025 | 9/2025 | 166.58 |  | 166.58 | 3.54 | -
April 2025 |  |  | 683 | WIDENING TO 4 LANE FROM KM. 133.00 TO 158.04 (DESIGN CHAINAGE KM. 130.88 TO 155.145) (SHIRUR CROSS T | MoRTH | N24001941 | 1-2023 | 1/2025 | 1/2025 | 1/2025 | 350.69 |  | 350.69 | 10 | 56
April 2025 |  |  | 684 | WIDENING TO TWO LANE WITH PAVED SHOULDERS FROM KM. 33.13 TO KM. 40.23 AND KM. 52.00 TO KM. 71.00 (EX | MoRTH | N24001943 | 9-2022 | 3/2024 | 1/2025 | 1/2025 | 172.98 |  | 172.98 | 6.48 | 65
April 2025 |  |  | 685 | WIDENING TO INTERMEDIATE/TWO LANE TO 2 LANE WITH PAVED SHOULDER FROM EXISTING CHANAGES KM 112.750 TO | MoRTH | N24001944 | 1-2023 | 6/2024 | 7/2024 | 7/2024 | 255.88 |  | 255.88 | 60.99 | 78
April 2025 |  |  | 686 | WIDENING TO 2 LANE WITH PAVED SHOULDERS FROM KM 116.800 TO 149.070(DESIGN CHANGES) ON HOSADURGA HOL | MoRTH | N24001945 | 8-2022 | 2/2024 | 12/2024 | 12/2024 | 170.34 |  | 170.34 | 4.25 | 72
April 2025 |  |  | 687 | WIDENING TO 2 LANES WITH PAVED SHOULDERS FROM KM 24.400 TO 27.270, 40.500 TO 41.900, 84.300 TO 88.20 | MoRTH | N24001946 | 11-2022 | 11/2024 | 11/2024 | 11/2024 | 218.93 |  | 218.93 | 10 | 95
April 2025 |  |  | 688 | WIDENING TO EXISTING 2 LANE WITH PAVED SHOULDER TO 4 LANE WITH PAVED SHOULDER FROM DESIGN KM 153.00 | MoRTH | N24001947 | 2-2023 | 2/2025 | 2/2025 | 2/2025 | 177.94 |  | 177.94 | 6.66 | 47
April 2025 |  |  | 689 | WIDENING TO 4 LANE FROM KM 51.60 TO 76.20 (HEBRI TO PARKALA) AND FROM KM 85.20 TO 88.90 (KARAVALI JU | MoRTH | N24001948 | 10-2022 | 10/2024 | 12/2024 | 12/2024 | 355.72 |  | 355.72 | 11.32 | 60
April 2025 |  |  | 690 | FOUR LANING OF LEFT OVER WORKS OF HOSPET BELLARY KARNATAKA/ AP BORDER FROM KM.280.080 TO KM. 375.450 | NHAI | N24001989 | 3-2023 | 5/2025 | N.A. | 5/2025 | 830.28 |  | 830.28 | 634.76 | 73.64
April 2025 |  |  | 691 | DEVELOPMENT OF 6 LANE ACCESS CONTROLLED GREENFIELD HIGHWAY FROM KM. 97.000 TO KM. 162.500 MARADGI S | NHAI | N24001993 | 12-2022 | 10/2025 | N.A. | 10/2025 | 1589 |  | 1589 | 724.33 | 60.7
April 2025 |  |  | 692 | 4/6L OF BANGALORE - PUNE SECTION OF BYPASS CONNECTING DHARWAD - HUBLI FROM KM. 403.80 TO KM. 433.20 | NHAI | N24001994 | 5-2022 | 3/2023 | N.A. | 9/2025 | 1135.39 |  | 1135.39 | 339.37 | 66.12
April 2025 |  |  | 693 | BALANCE WORK OF CONSTRUCTION OF TWO/FOUR LANE WITH PAVED SHOULDER FROM KM 422.000 TO 523.600 ( CHITR | MoRTH | N24002011 | 12-2021 | 6/2024 | 12/2024 | 12/2024 | 516.96 |  | 516.96 | 19.93 | 70
April 2025 |  |  | 694 | WIDENING TO TWO LANE WITH PAVED SHOULDERS FROM KM 40.00 TO KM 75.00 (EXISTING CHAINAGES) OF MANGALOR | MoRTH | N24002012 | 3-2023 | 3/2025 | 3/2025 | 3/2025 | 718.52 |  | 718.52 | 24.81 | 23
April 2025 |  |  | 695 | CONSTRUCTION OF TWO LANE WITH PAVED SHOULDER FROM KM.0 TO KM. 80 ON NH 548B (VIJAYAPURA-SANKESWAR SE | MoRTH | N24002013 | 3-2021 | 2/2022 | 10/2024 | 10/2024 | 766.64 |  | 766.64 | 13.55 | 75
April 2025 |  |  | 696 | WIDENING TO 2 LANE WITH PAVED SHOULDERS FROM DESIGN KM 103.200 (EXISTING KM 103.200) TO DESIGN KM 11 | MoRTH | N24002186 | 3-2024 | 9/2025 | N.A. | 9/2025 | 166.58 |  | 166.58 | 3.62 | -
April 2025 |  |  | 697 | CONSTRUCTION OF 2 LANE WITH PAVED SHOULDER FROM KM 55.6 TO KM 90.7 (EXISTING CHAINAGES) OF NH-766C ( | MoRTH | N24002187 | 2-2024 | 2/2026 | N.A. | 2/2026 | 313.56 |  | 313.56 | 53.65 | -
April 2025 |  |  | 698 | WIDENING TO 2L+PS FROM KM 71.00 TO 104.00 (EXISTING CHAINAGES) (SARJAPUR TO PATTADKALLU) ON BHANAPUR | MoRTH | N24002188 | 3-2024 | 3/2026 | N.A. | 3/2026 | 445.62 |  | 445.62 | 33.24 | -
April 2025 |  |  | 699 | WIDENING TO TWO LANE WITH PAVED SHOULDERS FROM KM 0.00 (DESIGN CHAINAGE 0.00) TO KM 23.338 (DESIGN C | MoRTH | N24002189 | 9-2024 | 3/2026 | N.A. | 3/2026 | 196.05 |  | 196.05 | 2.34 | -
April 2025 |  | STEEL | 700 | SCREENING PLANT-II, DONIMALAI | NMDC | N12000136 | 9-2023 | 8/2026 | N.A. | 8/2026 | 1043.63 |  | 1043.63 | 176.3 | 11.27
April 2025 |  | URBAN DEVELOPMENT | 701 | BANGALORE METRO RAIL PROJECT PHASE-2 | BMRCL | N28000058 | 2-2014 | 2/2021 | N.A. | 3/2025 | 26405.14 |  | 26405.14 | 20936.29 | 89
April 2025 |  | URBAN DEVELOPMENT | 702 | BANGALORE METRO RAIL PROJECT LIMITED. PHASE. 2A AND 2B | BMRCL | N28000151 | 6-2021 | 6/2026 | N.A. | 6/2026 | 14788.1 |  | 14788.1 | 2424.04 | 30
April 2025 |  | CIVIL AVIATION | 703 | CALICUT AIRPORT - DEVELOPMENT OF ADDITIONAL RESA ON EITHER END ON RUNWAY 10-28 AT CALICUT AIRPORT | AAI | N04000111 | 6-2023 | 9/2025 | N.A. | 9/2025 | 484.57 |  | 323.98 | 54.09 | 16.5
April 2025 |  | DEPARTMENT OF HIGHER EDUCATION | 704 | C/O PERMANENT CAMPUS OF IIT PALAKKAD PHASE IA AT PUDESSERY VILLAGE,KANJIKODE WEST, DISTRICT PALAKKA | CPWD EDUCATION | N28000140 | 7-2019 | 3/2021 | N.A. | 11/2025 | 753.63 |  | 753.63 | 411.86 | 67
April 2025 |  | HEALTH AND FAMILY WELFARE | 705 | C/O NEW HOSPITAL BLOCK FOR SREE CHITRA TIRUNAL INSTITIUTE OF MEDICAL SCIENCE AND TECHNOLOGY (SCTIMST | CPWD FOR HEALTH | N28000112 | 9-2017 | 3/2020 | 5/2024 | 11/2024 | 150.29 |  | 162 | 146.95 | 100
April 2025 |  | PETROLEUM | 706 | REPLACEMENT AND EXTENSION OF JETTY PIPELINES AT KOCHI REFINERY | BPCL | N16000508 | 3-2023 | 3/2026 | N.A. | 3/2026 | 621.87 |  | 621.87 | 166.6 | 78.3
April 2025 |  | PETROLEUM | 707 | SETTING UP POLYPROPYLENE UNIT AT KOCHI REFINERY | BPCL | N16000530 | 12-2023 | 10/2027 | N.A. | 10/2027 | 4460 |  | 4460 | 214.4 | 9.6
April 2025 |  | PETROLEUM | 708 | TRIVANDRUM-KANYAKUMARI DOUBLING | SR | N22000399 | 2-2015 | 3/2024 | N.A. | 12/2027 | 1431.9 |  | 3785.45 | 3184.42 | 42.1
April 2025 |  | PETROLEUM | 709 | ERNAKULAM-KUMBALAM - PATCH DOUBLING (7.71 KM) | SR | N22000619 | 12-2010 | 3/2028 | N.A. | 12/2026 | 600.82 |  | 595.39 | 282.3 | 8
April 2025 |  |  | 710 | KUMBALAM-THURAVUR - PATCH DOUBLING (15.59 KM) | SR | N22000620 | 12-2011 | 3/2027 | N.A. | 12/2026 | 812.85 |  | 802.8 | 268.32 | 7
April 2025 |  |  | 711 | 4-LANNING OF THALSERRY - MAHE BYPASS | NHAI | N24000704 | 9-2017 | 5/2020 | 11/2023 | 2/2024 | 1124.11 | 1573.18 | 1573.18 | 1525.92 | 100
April 2025 |  |  | 712 | 6-LANING OF KOZHIKODE BYPASS (CALICUT BYPASS) (I.E. VENGALAM JN. TO RAMANATTUKARA JN.) SECTION OF NH | NHAI | N24000784 | 2-2018 | 2/2023 | 12/2024 | 6/2025 | 1424.77 | 2065.95 | 2065.95 | 901.96 | 93.63
April 2025 |  |  | 713 | WIDENING TO 2 LANES WITH PAVED SHOULDERS FROM KM.87/000 TO 133/720 (NATTUKAL TO THANAU JN. IN PALAKK | MoRTH | N24001369 | 2-2017 | 8/2017 | 3/2022 | 8/2024 | 294.28 | 296.53 | 296.53 | 286.8 | 98
April 2025 |  |  | 714 | WIDENING TO 2-LANE WITH PAVED SHOULDERS FROM KM 119/017 TO KM 161/300 ON NH 85 | OLD NH 49 | MoRTH | 2-2017 | 9/2017 | 1/2023 | 8/2024 | 380.76 | 372.87 | 372.87 | 347.04 | 100
April 2025 |  |  | 715 | CONSTRUCTION OF 6 LANE ELEVATED CORRIDOR ALONG WITH DEVELOPMENT OF EXISTING 4 LANE ROAD AT GROUND LE | NHAI | N24001648 | 8-2022 | 1/2026 | N.A. | 1/2026 | 2429.52 |  | 2429.52 | 1028.39 | 56.75
April 2025 |  |  | 716 | SIX LANING OF PARAVOOR(DESIGN KM. 417+000) TO KOTTUKULANGARA(DESIGN KM. 454+500) SECTION OF NEW NH-6 | NHAI | N24001649 | 12-2021 | 2/2025 | 2/2025 | 1/2026 | 3273.61 |  | 3273.61 | 740.3 | 58.51
April 2025 |  |  | 717 | SIX LANING OF KADAMBATTUKONAM TO KAZHAKKOOTTAM SECTION OF NH-66(OLD NH-47) FROM KM. 517+250 TO KM.54 | NHAI | N24001650 | 12-2021 | 1/2025 | 4/2026 | 4/2026 | 3635.64 |  | 3635.64 | 324.02 | 38.75
April 2025 |  |  | 718 | SIX LANING OF THURAVOOR (DESIGN KM. 378+612) TO PARAVOOR (DESIGN KM.417+000) SECTION OF NEW NH-66 (O | NHAI | N24001651 | 9-2021 | 9/2024 | 3/2026 | 9/2024 | 2878.97 |  | 2878.97 | 516.63 | 41.78
April 2025 |  |  | 719 | 6L MINOR BRIDGE (PALOLI PALAM) AT KM. 203.160 and MAJOR BRIDGE (MORAD) AT KM. 204.895 AND ALLIED WOR | NHAI | N24001652 | 3-2020 | 6/2022 | 2/2024 | 6/2024 | 210.37 | 216.94 | 216.94 | 198.1 | 100
April 2025 |  |  | 720 | SIX LANING FROM KODUNGALLUR TO EDAPALLY SECTION OF NH ?66 (OLD NH-17) FROM DESIGN CHAINAGE 397+750 ( | NHAI | N24001653 | 11-2021 | 4/2025 | N.A. | 4/2025 | 3565.82 |  | 3064.11 | 1997.3 | 60.14
April 2025 |  |  | 721 | SIX LANING OF START OF KOLLAM BYPASS (KM.486+000) KADAMBATTUKONAM (KM.517+250) SECTION OF NEW NH-66 | NHAI | N24001654 | 6-2021 | 3/2025 | 2/2026 | 2/2026 | 2641.37 |  | 2641.37 | 607.07 | 76.02
April 2025 |  |  | 722 | SIX LANING FROM KAPPIRIKKAD TO THALIKULAM SECTION OF NH ? 66 (OLD NH-17) FROM DESIGN CH. 335+850 (EX | NHAI | N24001655 | 6-2021 | 2/2025 | N.A. | 11/2025 | 3606 | 3946.56 | 3946.56 | 3120.23 | 70.41
April 2025 |  |  | 723 | SIX LANING FROM THALIKULAM TO KODUNGALLUR SECTION OF NH ? 66 (OLD NH-17) FROM DESIGN CH.369+015 (EX. | NHAI | N24001656 | 6-2021 | 3/2025 | N.A. | 12/2025 | 2595 |  | 4009.57 | 3044.77 | 62.75
April 2025 |  |  | 724 | SIX LANING OF KOTTUKULANGARA (DESIGN KM. 454+500) TO START OF KOLLAM BYPASS (DESIGN KM. 486+000) SEC | NHAI | N24001657 | 6-2021 | 10/2024 | 12/2025 | 12/2025 | 2842.14 |  | 2842.14 | 477.69 | 70.53
April 2025 |  |  | 725 | SIX LANING OF RAMANATTUKARA JUNCTION TO START OF VALANCHERY BYPASS SECTION OF NH-66 (OLD NH-17) FROM | NHAI | N24001658 | 1-2021 | 7/2024 | 3/2025 | 3/2025 | 4265.42 |  | 4728.4 | 3474.21 | 99.1
April 2025 |  |  | 726 | SIX LANING FROM START OF VALANCHERY BYPASS TO KAPPIRIKKAD-SECTION OF NH- 66(OLD NH-17) FROM DESIGN CH | NHAI | N24001659 | 2-2021 | 7/2024 | 3/2025 | 3/2025 | 3375.31 | 3824.07 | 3824.07 | 2351.43 | 98.3
April 2025 |  |  | 727 | SIX LANING OF THALIPARAMBHA- MUZHAPILANGAD SECTION FROM KM 137.900 TO KM. 170.600 OF NH-17 (NEW NH | NHAI | N24001660 | 8-2020 | 2/2024 | 8/2025 | 3/2026 | 2714.6 | 3557.65 | 2714.6 | 1898.58 | 71.15
April 2025 |  |  | 728 | 6L OF AZHIYUR-VENGALAM FROM KM. 189.200 TO KM. 230.400 OF NH-66 | NHAI | N24001661 | 10-2020 | 4/2024 | 5/2025 | 3/2026 | 3219.47 | 3898.46 | 3896.46 | 2295.2 | 56.58
April 2025 |  |  | 729 | SIX LANING OF KT/KL BORDER (THALAPPDY) TO CHENGALA SECTION OF NH17 (NEW NH-66) FROM CH. 17.200 TO CH | NHAI | N24001662 | 5-2020 | 5/2024 | 11/2021 | 5/2025 | 1981.07 | 2651.79 | 1981.07 | 1540.36 | 93.85
April 2025 |  |  | 730 | SIX LANING OF NEELESHWARAM TO THALIPARAMBHA SECTION FROM CH. 94+540 (EXISTING KM 96+450) TO CH. 134+ | NHAI | N24001663 | 6-2020 | 4/2024 | 10/2021 | 12/2025 | 3041.65 | 3867.66 | 3041.65 | 2387.89 | 80.6
April 2025 |  |  | 731 | SIX LANING OF CHENGALA TO NEELESHWARAM SECTION OF NH-17 (NEW NH-66) FROM CH. 56+200 (EXISTING KM 57+ | NHAI | N24001664 | 6-2020 | 4/2024 | 10/2021 | 11/2025 | 1746.45 | 2538.06 | 1746.45 | 1250.34 | 78.55
April 2025 |  |  | 732 | WIDENING/DEVELOPMENT OF EXISTING NH-85 FROM KM 0.000 TO KM 124.636 SECTION TO 2L/@L+PS SECTION IN TH | NHAI | N24002074 | 8-2022 | 6/2025 | N.A. | 6/2025 | 1231.74 |  | 1231.74 | 399.9 | 45.2
April 2025 |  | URBAN DEVELOPMENT | 733 | KOCHI METRO RAIL PROJECT PHASE II FROM JLN STADIUM TO INFOPARK VIA KAKKANAD | KMRCL | N28000158 | 7-2018 | 11/2026 | N.A. | 11/2026 | 1957.05 |  | 1957.05 | 244.8 | 7.4
April 2025 |  | URBAN DEVELOPMENT | 734 | KOCHI METRO RAIL PROJECT PHASE IB SECTION FROM S N JUNCTION TO THRIPUNITHURA | KMRCL | N28000159 | 6-2019 | 9/2023 | N.A. | 9/2023 | 355.7 | 448 | 448.33 | 1.64 | 100
April 2025 |  | CIVIL AVIATION | 735 | CONSTRUCTION OF TERMINAL BUILDING AND ASSOCIATED WORKS AT LEH AIRPORT | AAI | N04000078 | 7-2018 | 9/2021 | 10/2025 | 10/2025 | 480.33 |  | 640 | 407.93 | 63.2
April 2025 |  | CIVIL AVIATION | 736 | KARGIL-ZANSKR PACKAGE-1 | NHIDCL | N24001343 | 3-2021 | 1/2023 | 12/2024 | 11/2025 | 384.23 |  | 384.23 | 162.54 | 60.4
April 2025 |  | CIVIL AVIATION | 737 | KARGIL-ZANSKR PACKAGE-2 | NHIDCL | N24001344 | 3-2021 | 1/2023 | 2/2025 | 11/2025 | 404.89 |  | 404.89 | 244.21 | 64.36
April 2025 |  | CIVIL AVIATION | 738 | KARGIL-ZANSKR PACKAGE-3 | NHIDCL | N24001345 | 8-2020 | 1/2023 | 8/2025 | 8/2025 | 381.01 |  | 381.01 | 230.28 | 74.11
April 2025 |  |  | 739 | KARGIL-ZANSKR PACKAGE-8 | NHIDCL | N24001348 | 3-2021 | 1/2023 | 8/2025 | 8/2025 | 398.37 |  | 398.37 | 274.39 | 82.28
April 2025 |  |  | 740 | CONSTRUCTION OF REALIGNMENT BETWEEN PANDRASS- PASHKYUN (TOTAL LENGTH 27.10 KM) ON ROAD ZOZILA-KARGIL | BRO | N24001999 | 11-2021 | 6/2025 | N.A. | 6/2025 | 426.14 |  | 426.14 | 16.27 | 37
April 2025 |  | CIVIL AVIATION | 741 | UPGRADATION OF JABALPUR AIRPORT | AAI | N04000087 | 6-2016 | 6/2021 | 7/2024 | 7/2024 | 412.24 |  | 412.24 | 402.81 | 100
April 2025 |  | CIVIL AVIATION | 742 | DEVELOPMENT OF GWALIOR AIRPORT PHASE 01 | AAI | N04000098 | 10-2021 | 8/2023 | 8/2024 | 8/2024 | 446.12 | 455 | 455 | 451.41 | 100
April 2025 |  | CIVIL AVIATION | 743 | KANCHAN OC EXPANSION | SECL | N06000125 | 12-2014 | 3/2021 | 3/2026 | 3/2026 | 371.04 |  | 371.04 | 136.72 | 47
April 2025 |  | CIVIL AVIATION | 744 | AMADAND OPENCAST EXPANSION PROJECT | SECL | N06000148 | 3-2016 | 3/2021 | 3/2027 | 3/2027 | 869.44 |  | 869.44 | 271.74 | 73
April 2025 |  | CIVIL AVIATION | 745 | GANDHIGRAM UG MINE | WCL | N06000183 | 8-2019 | 3/2026 | N.A. | 3/2026 | 414.16 |  | 414.16 | 11.75 | 28
April 2025 |  | CIVIL AVIATION | 746 | BLOCK-B EXPANSION OPENCAST PROJECT | NCL | N06000184 | 7-2019 | 3/2023 | N.A. | 3/2027 | 998.71 |  | 998.71 | 431.21 | 29.48
April 2025 |  | CIVIL AVIATION | 747 | NIGAHI EXPANSION OCP (15 TO 25 MTPA) | NCL | N06000196 | 11-2020 | 3/2025 | N.A. | 3/2028 | 1729.68 |  | 1729.68 | 760.98 | 44
April 2025 |  |  | 748 | RAMPUR BATURA OC (4.0 MTY) | SECL | N06000233 | 7-2019 | 3/2026 | N.A. | 3/2026 | 1248.93 |  | 1248.93 | 487.87 | 44
April 2025 |  |  | 749 | TAWA III UG MINE | WCL | N06000250 | 12-2021 | 3/2027 | N.A. | 3/2027 | 314.09 |  | 324.25 | 0.56 | 9
April 2025 |  |  | 750 | AMALGAMATED DHANKASA JAMUNIA UG (1.84 MTY) | WCL | N06000257 | 9-2022 | 3/2027 | N.A. | 3/2027 | 399.2 |  | 497.01 | 64.13 | 42
April 2025 |  |  | 751 | VISHNUPURI UG TO OC | WCL | N06000260 | 11-2022 | 3/2029 | N.A. | 3/2029 | 220.62 |  | 227.65 | 0 | 7
April 2025 |  |  | 752 | URDHAN OC | WCL | N06000265 | 1-2023 | 3/2031 | N.A. | 3/2031 | 206.88 |  | 228.42 | 22.12 | 9
April 2025 |  |  | 753 | SHARDA UG | WCL | N06000266 | 9-2023 | 3/2028 | N.A. | 3/2028 | 166.25 |  | 200.16 | 1.69 | 11
April 2025 |  | PETROLEUM | 754 | ETHYLENE CRACKER PROJECT AT BINA REFINERY INCLUDING DOWNSTREAM PETROCHEMICAL PLANTS AND EXPANSION OF | BPCL | N16000518 | 5-2023 | 5/2028 | N.A. | 5/2028 | 43367 |  | 43367 | 1577 | 11.5
April 2025 |  | PETROLEUM | 755 | SHAJAPUR 325MW SOLAR PV PROJECT | NTPC | N18000348 | 6-2022 | 3/2024 | N.A. | 6/2025 | 1530.49 |  | 1530.49 | 1207.64 | 70
April 2025 |  |  | 756 | TS FOR EVACUATION POWER RAJASTHAN REZ PH-IV (PART- 2:5.5GW) (JAISALMER/BARMER COMPLEX): PART-C | PGCIL | N18000392 | 8-2024 | 8/2026 | N.A. | 8/2026 | 2708 |  | 2708 | 75 | 18.7
April 2025 |  |  | 757 | TRANSMISSION SYSTEM FOR EVACUATION OF POWER FROM RAJASTHAN REZ PH-IV [PART-2 5.5GW] [JAISALMER/BARME | PGCIL | N18000399 | 10-2024 | 10/2026 | N.A. | 10/2026 | 3674 |  | 3674 | 81 | 7
April 2025 |  |  | 758 | RAMGANJMUNDI-BHOPAL (NL),WCR | WCR | 220100314 | 4-2001 | 12/2025 | 12/2025 | 6/2026 | 3032 | 3032.46 | 5125.16 | 3423.9 | 69
April 2025 |  |  | 759 | RATLAM-MHOW-KHANDWA- AKOLA (GC) | WR | N22000120 | 4-2008 | 2/2027 | 2/2027 | 2/2027 | 5677.88 | 5677.8 | 6203.51 | 4271.4 | 80
April 2025 |  |  | 760 | KATNI - SINGRAULI DOUBLING PROJECT | WCR | N22000351 | 12-2015 | 12/2026 | 12/2027 | 12/2027 | 2445.29 | 2445.3 | 4353.5 | 3092.7 | 90
April 2025 |  |  | 761 | KATNI GRADE SEPARATOR/BYE PASS | WCR | N22000416 | 8-2016 | 9/2024 | 6/2025 | 9/2024 | 1247.64 | 1247.64 | 2300 | 1404.52 | 89
April 2025 |  |  | 762 | ANUPPUR-KATNI | SECR | N22000485 | 4-2015 | 12/2021 | 12/2023 | 3/2025 | 1860.94 | 1680 | 2311.02 | 1913.51 | 100
April 2025 |  |  | 763 | NIMACH BADI SADRI NEW LINE PROJECT | WR | N22000503 | 4-2017 | 3/2022 | N.A. | 3/2026 | 495.18 |  | 495.18 | 276.02 | 20
April 2025 |  |  | 764 | NIMACH-RATLAM (133 KM) | WR | N22000536 | 10-2021 | 10/2027 | 6/2025 | 6/2025 | 1095.88 | 1095.88 | 1095.88 | 1038.9 | 72
April 2025 |  |  | 765 | SATNA - REWA (50 KM) | WCR | N22000554 | 11-2015 | 3/2026 | N.A. | 3/2026 | 500 | 40 | 500 | 1.41 | 80
April 2025 |  |  | 766 | INDORE BUDNI (INDORE JABALPUR) | RVNL | N22000601 | 9-2018 | 9/2030 | N.A. | 9/2030 | 7474.01 |  | 7393.75 | 1004.86 | -
April 2025 |  |  | 767 | UMARIYA TO SHAHDOL SECTION OF NH-78 IN MADYA PRADESH KM 68/4 TO 142/200 | MoRTH | N24000513 | 3-2015 | 8/2017 | 12/2023 | 6/2025 | 511.83 |  | 511.83 | 478.84 | 93.06
April 2025 |  |  | 768 | BALANCE WORK FOR FOUR LANING OF ITARSI TO BETUL SECTION OF NH69 FROM KM 63.000 TO KM 137.00 (DESIGN | NHAI | N24000709 | 12-2017 | 2/2020 | 12/2024 | 12/2024 | 950.27 |  | 786.43 | 643.9 | 99.5
April 2025 |  |  | 769 | 4LBERKHEDI TO GODPEHRA NH- 44 | NHAI | N24001614 | 2-2022 | 11/2024 | N.A. | 11/2024 | 524.84 |  | 524.84 | 2423.91 | 50
April 2025 |  |  | 770 | 4L OF SAGAR - MOHARI FROM KM.8 TO KM.50 (PKG-I) | NHAI | N24001615 | 3-2021 | 4/2024 | 5/2024 | 8/2024 | 790.78 |  | 790.78 | 2139.29 | 75
April 2025 |  |  | 771 | 2L PS OF SATNA - MAIHAR SECTION OF NH-135BG FROM KM 80.800 TO KM 120.125 | NHAI | N24001616 | 1-2021 | 10/2023 | N.A. | 2/2025 | 428.04 |  | 428.04 | 351.97 | 100
April 2025 |  |  | 772 | KATNI BYPASS FROM KM. 359.50 TO KM. 378.50 | NHAI | N24001618 | 9-2019 | 9/2022 | N.A. | 2/2025 | 194.4 | 235 | 235 | 207.6 | 98.84
April 2025 |  |  | 773 | 4L OF CHANDESARA TO KHEDAKHAJURIYA FROM KM. 0.000 TO (-) 750 AND KM 0.000 TO KM 41.400 OF NH-752D | NHAI | N24001759 | 1-2020 | 6/2024 | 6/2025 | 6/2025 | 909.84 |  | 909.84 | 502.49 | 99
April 2025 |  |  | 774 | INDORE - HARDA (PKG-III) [NANASA TO PIDGAON SECTION FROM KM 95.000 TO KM 142.445] | NHAI | N24001762 | 10-2021 | 1/2024 | 12/2024 | 12/2024 | 1146.22 |  | 1146.22 | 662.24 | 91.21
April 2025 |  |  | 775 | ADDITIONAL WORKS (2VUPS, MR-10 JUNCTION FLYOVER AND UNDERPASS) IN SIX LANE INDORE-DEWAS SECTION OF N | NHAI | N24001765 | 8-2022 | 7/2024 | N.A. | 12/2025 | 207.77 |  | 207.77 | 65.02 | 49.28
April 2025 |  |  | 776 | INDORE - HARDA (PKG-I) [INDORE TO RAGHAV GARH FROM KM. 0.25 TO KM. 26.903] | NHAI | N24001766 | 1-2022 | 10/2024 | N.A. | 5/2025 | 1011.29 |  | 1011.29 | 284.8 | 62.1
April 2025 |  |  | 777 | 4L OF INDORE - BOREGAON (PKG-III) [BALWARA TO DHANGAON] FROM KM. 42.260 TO KM. 82.660 OF NH347BG AND | NHAI | N24001767 | 1-2021 | 4/2024 | N.A. | 4/2024 | 1001.69 |  | 1001.69 | 517 | 82.09
April 2025 |  |  | 778 | BALANCE WORK OF 4L OF INDORE-GUJARAT/MP BORDER FROM KM 106.210 TO KM 115.250 (START AND END POINT OF | NHAI | N24001768 | 8-2019 | 4/2023 | N.A. | 11/2023 | 323.51 |  | 323.51 | 51.96 | 100
April 2025 |  |  | 779 | 4L OF OBEDULLGANJ - BUDNI SECTION FROM KM. 8.400 TO KM. 20.700 IN RATANPANI WILDLIFE AREA OF NH - 69 | NHAI | N24001770 | 2-2022 | 3/2024 | 3/2025 | 5/2025 | 417.51 |  | 417.51 | 288.41 | 95.37
April 2025 |  |  | 780 | 2- LANE WITH PAVED SHOULDERS OF HINOTIYA TO MEHULWA FROM DESIGN KM 27+000 9OF EXISTING SH-19 KM 26+5 | NHAI | N24001921 | 8-2021 | 9/2025 | N.A. | 9/2025 | 581.65 | 592.03 | 581.65 | 186.33 | 39.53
April 2025 |  |  | 781 | CONSTRUCTION OF MIHONA BYPASS, LAHAR BYPASS, DABOH BYPASS and BHANDER BYPASS (TOTAL LENGTH 20.60 KM) | MoRTH | N24001962 | 3-2022 | 12/2024 | N.A. | 3/2025 | 179.19 |  | 179.19 | 47.91 | 96
April 2025 |  |  | 782 | UPGRADATION OF NASRULLAGANI-REHTI-BUDHNI SCCTION TO 2-LANE WITH PAVED SHOULDER FROM KM 0+150 TO KM | MoRTH | N24001963 | 12-2021 | 10/2024 | N.A. | 9/2025 | 305.12 |  | 305.12 | 71.47 | 34.46
April 2025 |  |  | 783 | UPGRADATION and WIDENING OF JHARKHEDA- BERASIA - DHOLKHEDI FROM DESIGN KM 0+000 TO KM 87+900 (DESIGN | MoRTH | N24001964 | 3-2022 | 5/2025 | N.A. | 5/2025 | 365.21 |  | 365.21 | 112.27 | 64
April 2025 |  |  | 784 | REHABILITATION AND UPGRADATION OF KURWAI?MUNGAOLI?CHANDERI ROAD SECTION OF NH-346, FROM DESIGN CHAIN | MoRTH | N24001965 | 3-2022 | 2/2025 | N.A. | 12/2025 | 386.49 |  | 386.49 | 77.42 | 48.77
April 2025 |  |  | 785 | BALANCE WORK FOR REHABILITATION AND UP- GRADATION OF SIDHI- SINGRAULI FROM KM 82.400 TO KM 187.993 SEC | MoRTH | N24001966 | 12-2020 | 4/2023 | N.A. | 6/2025 | 529.44 |  | 529.44 | 378.4 | 62
April 2025 |  |  | 786 | 4L GREENFIELD RUDHI TO DESHGAON (PKG V OF BETUL- KHANDWA/DESHGAON) - N/04015/06003/MP | NHAI | N24001967 | 11-2018 | 10/2025 | N.A. | 10/2025 | 521.21 |  | 521.21 | 98.23 | 39.8
April 2025 |  |  | 787 | REHABILITATION AND UPGRADATION TO 2-LANE WITH PAVED SHOULDER CONFIGURATION OF JIRAPUR- SUSNER-MP-RJ B | MoRTH | N24002018 | 1-2022 | 3/2025 | N.A. | 3/2025 | 239.72 | 232.22 | 232.22 | 73.4 | 100
April 2025 |  |  | 788 | UPGRADATION OF DINDORI- SAGARTOLA-KABICHABUTRA (MP-CG BORDER) SECTION OF NH -45 FROM KM 0+00(DESIGN) | MoRTH | N24002019 | 1-2022 | 9/2025 | N.A. | 9/2025 | 329.14 | 319.09 | 319.09 | 52.7 | 50.12
April 2025 |  |  | 789 | CONSTRUCTION OF KAITHI- PADARIA KALA BYPASS, PATNA- TAMOLI BYPASS, JASO BYPASS , NAGOD BYPASS (TOTAL L | MoRTH | N24002020 | 3-2022 | 10/2025 | N.A. | 10/2025 | 158.36 | 158 | 158.36 | 22.68 | 30
April 2025 |  |  | 790 | BALANCE WORK OF 4L OF NAURADEHI SANCTUARY DE- SCOPED STRETCH OF HIRAN RIVER TO SINDOOR RIVER FROM KM. | NHAI | N24002067 | 1-2021 | 7/2023 | N.A. | 4/2025 | 178.18 |  | 178.18 | 161.64 | 93.1
April 2025 |  |  | 791 | CONSTRUCTION OF 4-LANE FROM BARELA TO MANEGAON SECTION OF NH-30 FROM DESIGN CH. 2.900 TO DESIGN CH. | NHAI | N24002068 | 12-2022 | 3/2025 | N.A. | 12/2025 | 652.33 |  | 652.33 | 334.34 | 71.32
April 2025 |  |  | 792 | CONSTRUCTION OF ADDITIONAL 3 LANE WITH PAVED SHOULDER (DESIGN LENGTH 8.87 KM) AS REALIGNMENT OF BAKA | NHAI | N24002069 | 7-2022 | 12/2024 | N.A. | 12/2024 | 209.29 |  | 209.29 | 140.22 | 100
April 2025 |  |  | 793 | INDORE - EDLABAD (PKG-II) [TEJAJINAGAR TO BALWARA] | NHAI | N24002070 | 1-2022 | 1/2025 | N.A. | 1/2025 | 1162.8 |  | 1162.8 | 488.48 | 80
April 2025 |  |  | 794 | CONSTRUCTION OF (I) 4-LANE HIGHWAY FROM VIDISHA TO HINOTIYA FROM KM. 0.000 TO KM. 27.000 (LENGTH=27 | NHAI | N24002077 | 9-2022 | 12/2025 | N.A. | 12/2025 | 1000.63 |  | 1000.63 | 289.65 | 50.1
April 2025 |  |  | 795 | FOUR LANING OF RAGHOGARH (DESIGN CH.29.300/EXISTING CH. 29.555) TO NANASA (DESIGN CH.92.971/EXISTING | NHAI | N24002166 | 3-2024 | 3/2026 | 3/2026 | 3/2026 | 799.2 |  | 799.2 | 306.27 | 32.6
April 2025 |  |  | 796 | BALANCE WORKS OF 4 LANE DIVIDED CARRIAGEWAY OF MISSING LINK SECTION OF NH- 39 (REWA BYPASS) FROM JUNC | NHAI | N24002200 | 4-2024 | 4/2026 | N.A. | 4/2026 | 355.36 |  | 355.36 | 39.06 | 22.49
April 2025 |  | SOCIAL JUSTICE | 797 | CENTRE FOR DISABILITY SPORTS | CPWD | N38000001 | 2-2019 | 3/2024 | N.A. | 3/2024 | 170.99 |  | 170.99 | 73.8 | 74
April 2025 |  | URBAN DEVELOPMENT | 798 | BHOPAL METRO RAIL | MPMRCL | N28000124 | 11-2018 | 2/2023 | 6/2028 | 6/2028 | 6941.4 |  | 6941.4 | 2937.3 | 39.76
April 2025 |  | URBAN DEVELOPMENT | 799 | INDORE METRO RAIL | MPMRCL | N28000125 | 11-2018 | 2/2023 | 12/2028 | 12/2028 | 7500.8 |  | 7500.8 | 3677.77 | 52.18
April 2025 |  | CIVIL AVIATION | 800 | CONSTRUCTION OF NEW INTEGRATED TERMINAL BUILDING, RECONSTRUCTION OF OLD TERMINAL BUILDING, MODIFICAT | AAI | N04000079 | 3-2017 | 4/2021 | 12/2023 | 12/2023 | 475.39 |  | 520 | 532.88 | 100
April 2025 |  |  | 801 | EXTENSION OF RUNWAY WITH BLAST PAD, RESA, TAXIWAY, APRON, GSE AREA, ISOLATION BAY, NEW DOMESTIC TERM | AAI | N04000096 | 6-2017 | 12/2020 | N.A. | 4/2024 | 255.68 |  | 270 | 267.86 | 100
April 2025 |  |  | 802 | AMALGAMATED YEKONA-I YEKONA-II | WCL | N06000132 | 8-2015 | 3/2025 | N.A. | 3/2025 | 727.28 |  | 727.28 | 530.02 | 86
April 2025 |  |  | 803 | UKNI DEEP OC | WCL | N06000179 | 1-2019 | 3/2021 | 3/2025 | 3/2025 | 237.06 |  | 318.14 | 163.86 | 91
April 2025 |  |  | 804 | GHONSA EXPANSION DEEP OC | WCL | N06000205 | 3-2021 | 3/2028 | N.A. | 3/2029 | 184.71 |  | 241.72 | 9.25 | 6
April 2025 |  |  | 805 | SASTI EXPANSION OC | WCL | N06000206 | 8-2020 | 3/2026 | N.A. | 3/2026 | 319.04 |  | 371.59 | 68.64 | 24
April 2025 |  |  | 806 | DHUPTALA OC(SASTI UG TO OC) | WCL | N06000209 | 10-2021 | 3/2028 | N.A. | 3/2028 | 711 |  | 720.87 | 159.15 | 33
April 2025 |  |  | 807 | ADASA UG TO OC (1.50 MTY) | WCL | N06000219 | 11-2018 | 3/2024 | 3/2025 | 3/2025 | 316 |  | 333.43 | 208.2 | 78
April 2025 |  |  | 808 | DINESH (MAKARDHOKDA-III) OC | 8.0 MTY | WCL | 2-2020 | 3/2027 | N.A. | 3/2027 | 822.88 |  | 1184.33 | 578.89 | 48
April 2025 |  |  | 809 | AMALGAMATED INDER- KAMPTEE DEEP OC (3.20 MTY) | WCL | N06000226 | 9-2018 | 3/2024 | 3/2025 | 3/2025 | 235.9 |  | 313.34 | 116.46 | 87
April 2025 |  |  | 810 | SAONER UG MINE I EXPANSION | WCL | N06000251 | 1-2022 | 3/2028 | N.A. | 3/2028 | 228.64 |  | 253.51 | 118.34 | 27
April 2025 |  |  | 811 | SINGHORI DEEP OC | WCL | N06000252 | 5-2022 | 3/2029 | N.A. | 3/2029 | 335.75 |  | 421.84 | 22.01 | 16
April 2025 |  |  | 812 | MAKARDHOKDA I EXPANSION OC | WCL | N06000253 | 6-2022 | 3/2026 | N.A. | 3/2026 | 361.87 |  | 497.06 | 33.9 | 12
April 2025 |  |  | 813 | BHATADI EXPANSION OC | WCL | N06000254 | 5-2022 | 3/2028 | N.A. | 3/2028 | 580.6 |  | 729.86 | 61.33 | 17
April 2025 |  |  | 814 | NEW MAJARI UG TO OC (3.0 MTY) | WCL | N06000255 | 9-2022 | 3/2027 | N.A. | 3/2027 | 402.27 |  | 496.38 | 47.99 | 27
April 2025 |  |  | 815 | BHANEGAON OC (1.15MTY) | WCL | N06000256 | 9-2022 | 3/2028 | N.A. | 3/2028 | 405.2 |  | 494.6 | 10.21 | 7
April 2025 |  |  | 816 | GOKUL EXPANSION OC | WCL | N06000264 | 4-2021 | 3/2026 | N.A. | 3/2026 | 309.58 |  | 456.95 | 3.65 | 7
April 2025 |  |  | 817 | KOLGAON EXPANSION (DEEP) OC | WCL | N06000267 | 9-2023 | 3/2027 | N.A. | 3/2027 | 198.71 |  | 206.19 | 0.55 | 5
April 2025 |  |  | 818 | AMALGAMATED GAURI PAUNI EXPANSION OC | WCL | N06000271 | 3-2024 | 3/2030 | N.A. | 3/2030 | 1225.21 |  | 1428.25 | 52.83 | 17
April 2025 |  |  | 819 | GAURI CENTRAL OCM | WCL | N06000278 | 6-2024 | 3/2030 | N.A. | 3/2030 | 973.07 |  | 1015.07 | 0 | -
April 2025 |  |  | 820 | BALLARPUR NORTHWEST OC MINE | WCL | N06000282 | 12-2022 | 3/2029 | N.A. | 3/2029 | 360.18 |  | 360.18 | 0 | -
April 2025 |  |  | 821 | NORTHERN EXTENSION OF MUNGOLI NIRGUDA DEEP OC | WCL | N06000283 | 6-2024 | 3/2029 | N.A. | 3/2029 | 1024.91 |  | 1184.44 | 0 | -
April 2025 |  |  | 822 | AMALGAMATED GONDEGAON - GHATROHAN EXPANSION OCM | WCL | N06000284 | 9-2024 | 3/2029 | N.A. | 3/2029 | 668.54 |  | 871.59 | 0 | -
April 2025 |  | DEPARTMENT OF HIGHER EDUCATION | 823 | CONSTRUCTION OF IITB RESEARCH PARK AT IIT BOMBAY, POWAI, MUMBAI | CPWD EDUCATION | N28000117 | 1-2018 | 7/2020 | 11/2023 | 2/2024 | 223.37 | 275 | 230 | 141.16 | 100
April 2025 |  | HEALTH AND FAMILY WELFARE | 824 | 500 BEDDED HOSPITAL INCLUDING 50 SUPERSPECIALITY BEDS FOR ESIC AT PUNE | CPWD | N21000033 | 7-2022 | 9/2025 | N.A. | 9/2025 | 429.25 |  | 429.25 | 99.08 | -
April 2025 |  | HEALTH AND FAMILY WELFARE | 825 | LIFE EXTENSION OF WALL PLATFORMS OF MUMBAI HIGH AND HEERA FIELDS | ONGC | N16000213 | 12-2015 | 4/2018 | 12/2023 | 6/2025 | 3190.69 | 3375.9 | 3375.9 | 3006.09 | 88.4
April 2025 |  | HEALTH AND FAMILY WELFARE | 826 | SETTING UP 500KTPA PROPANE DEHYDROGENATION INTEGRATED WITH POLYPROPYLENE UNIT ALONG WITH OFFSITE AND | GAIL | N16000430 | 5-2019 | 4/2025 | 10/2025 | 10/2025 | 8797 | 11256 | 11256 | 6237.68 | 82.79
April 2025 |  |  | 827 | DEBOTTLENECKING AND AUGMENTATION OF CRYOGENIC FACILITIES AT URAN LPG IMPORT TERMINAL | BPCL | N16000442 | 4-2021 | 6/2024 | N.A. | 4/2025 | 1164.69 |  | 1164.69 | 827.81 | 79.3
April 2025 |  |  | 828 | EXPANSION OF CRYOGENICS GROUP BY SETTING UP NEW MANUFACTURING FACILITY | IOCL | N16000446 | 9-2021 | 10/2023 | 5/2024 | 5/2024 | 378 |  | 378 | 120.07 | 39.08
April 2025 |  |  | 829 | CONSTRUCTION OF LUBE OIL BLENDING AND FILLING PLANT AT RASAYANI | BPCL | N16000452 | 5-2022 | 3/2024 | N.A. | 9/2024 | 423.39 |  | 423.39 | 241.66 | 75.1
April 2025 |  |  | 830 | ATF PIPELINE FROM JAWAHARLAL NEHRU PORT TRUST (JNPT) TO NAVI MUMBAI INTERNATIONAL AIRPORT | NMIA | IOCL | 9-2022 | 8/2025 | N.A. | 3/2026 | 165 |  | 165 | 74.85 | 64.01
April 2025 |  |  | 831 | DAMAN UPSIDE DEVELOPMENT PROJECT (DUDP) IN TAPTI DAMAN BLOCK | ONGC | N16000470 | 6-2022 | 10/2025 | N.A. | 2/2026 | 4144.41 | 6406.9 | 6406.9 | 2782.76 | 77.1
April 2025 |  |  | 832 | CGD PROJECT AT BEED, JALGAON AND JALNA DISTRICTS | IOCL | N16000487 | 3-2022 | 3/2030 | N.A. | 9/2031 | 865 |  | 865 | 54.99 | 2.8
April 2025 |  |  | 833 | ANDHERI RESIDENTIAL TOWERS MUMBAI | IOCL | N16000503 | 6-2017 | 5/2025 | 6/2026 | 6/2026 | 281.35 | 389.67 | 389.67 | 216.88 | 49.5
April 2025 |  |  | 834 | CONSTRUCTION OF ADDITIONAL TANKAGES AND ALLIED FACILITIES AT JNPT TERMINAL | IOCL | N16000504 | 4-2022 | 10/2024 | 8/2026 | 8/2026 | 341.43 | 436.14 | 436.14 | 232.19 | 45.8
April 2025 |  |  | 835 | INSTALLATION OF INDEPENDENT DE- AROMATIZED SOLVENTS PRODUCTION FACILITIES AT MUMBAI REFINERY | BPCL | N16000507 | 3-2023 | 7/2025 | N.A. | 7/2025 | 405 |  | 405 | 174.12 | 75.7
April 2025 |  |  | 836 | PART REPLACEMENT PIPELINE PROJECT (PRPP) | ONGC | N16000515 | 11-2022 | 5/2024 | 12/2024 | 3/2025 | 1219.48 |  | 1145.1 | 678.96 | 84
April 2025 |  |  | 837 | POL AND LOBS INSTALLATIONS WITH RECEIPT PIPELINES AT RASAYANI | BPCL | N16000519 | 5-2023 | 5/2026 | N.A. | 5/2026 | 2585 |  | 2585 | 438.55 | 53
April 2025 |  |  | 838 | MHN TCPP PGC BGC PROJECT | MTPBP | ONGC | 2-2024 | 5/2026 | N.A. | 5/2026 | 2329.45 |  | 2354.23 | 500.96 | 37
April 2025 |  |  | 839 | PRP-VIII GROUP B (NH AND BS ASSET) | ONGC | N16000533 | 6-2024 | 5/2026 | N.A. | 2/2026 | 2379.84 |  | 2379.84 | 473.4 | 47.9
April 2025 |  |  | 840 | HP TDAE UNIT IN MUMBAI REFINERY | HPCL | N16000534 | 6-2024 | 4/2026 | N.A. | 4/2026 | 240 |  | 240 | 24.24 | 25.7
April 2025 |  |  | 841 | INTEGRATED DEVELOPMENT OF 4 CONTRACT AREAS UNDER DSF2 | ONGC | N16000537 | 5-2023 | 4/2027 | N.A. | 4/2027 | 6183.79 |  | 6183.79 | 0 | 11.2
April 2025 |  |  | 842 | LUBE MODERNIZATION AND BOTTOM UPGRADATION PROJECT | HPCL | N16000540 | 12-2024 | 3/2028 | N.A. | 3/2028 | 4679 |  | 4679 | 163.61 | 4.1
April 2025 |  | POWER | 843 | BIKANER SOLAR POWER PROJECT | SJVN | N18000335 | 4-2022 | 5/2024 | N.A. | 9/2025 | 5491.89 | 532 | 5491.89 | 3979.19 | 74
April 2025 |  | POWER | 844 | TS FOR EVACUATION OF 7GW RE INJECTION AT KHAVDA PS UNDER PHASE-IV PART E4 | PGCIL | N18000377 | 11-2023 | 7/2025 | N.A. | 9/2025 | 224 |  | 224 | 0 | 5
April 2025 |  | POWER | 845 | AHMEDNAGAR-PARLI VAIJNATH(NL) CR | CR | 220100181 | 2-1997 | 3/2026 | N.A. | 1/2026 | 2539 |  | 4957.27 | 4777.07 | 94
April 2025 |  | POWER | 846 | MUMBAI URBAN TRANSPORT PROJECT PHASE-II | MRTP | N22000092 | 4-2008 | 3/2014 | N.A. | 3/2014 | 8087.11 |  | 918.53 | 7110.54 | 77.3
April 2025 |  | POWER | 847 | WARDHA-NANDED MAHARASHTRA | CR | N22000231 | 4-2008 | 3/2027 | N.A. | 1/2026 | 3445.48 |  | 3445.34 | 3107.47 | 47
April 2025 |  | POWER | 848 | KALYAN-KASARA 3RD LINE | CR | N22000233 | 4-2011 | 12/2025 | N.A. | 12/2026 | 792.89 |  | 1395.79 | 868.61 | 50
April 2025 |  | POWER | 849 | WARDHA-SEWAGRAM NGP 3RD LINE | CR | N22000250 | 4-2012 | 12/2025 | N.A. | 2/2026 | 540.02 |  | 540.02 | 729.82 | 80
April 2025 |  |  | 850 | WARDHA-BALHARSHAH - 3RD LINE (132 KM) | CR | N22000356 | 2-2015 | 12/2025 | N.A. | 3/2026 | 1384.72 |  | 1384.72 | 1517.52 | 67
April 2025 |  |  | 851 | ITARSI-NAGPUR (BAL.) - 3RD LINE (267 KM) | CR | N22000358 | 2-2015 | 3/2027 | N.A. | 3/2027 | 2449.91 |  | 2449.91 | 1704.81 | 50
April 2025 |  |  | 852 | PUNE-MIRAJ-LONDA (467 KM) | CR | N22000359 | 2-2015 | 2/2025 | N.A. | 5/2025 | 3627.47 | 3627 | 7037.24 | 4584.11 | 84
April 2025 |  |  | 853 | DAUND - MANMAD (236 KM) | CR | N22000360 | 2-2016 | 12/2025 | N.A. | 1/2026 | 2081.27 |  | 2081.27 | 2670.38 | 88
April 2025 |  |  | 854 | MANMAD - JALGAON - 3RD LINE | 160 KM | CR | 2-2016 | 12/2024 | N.A. | 3/2026 | 1035.16 |  | 1558.75 | 1636.16 | 80
April 2025 |  |  | 855 | WARDHA - NAGPUR - 4TH LINE | 76 KM | CR | 2-2016 | 12/2025 | N.A. | 2/2026 | 638 |  | 637.95 | 941.27 | 80
April 2025 |  |  | 856 | RAJNANDGAON - NAGPUR - 3RD LINE (SECR) | SECR | N22000420 | 9-2016 | 12/2024 | N.A. | 12/2025 | 3544.92 |  | 3544.25 | 3023.12 | 95
April 2025 |  |  | 857 | MUMBAI CENTRAL VIRAR VADODARA AHMEDABAAD TRAIN PROTECTION SYSTEM 500 RKM | WR | N22000434 | 3-2010 | 10/2024 | N.A. | 3/2024 | 311 |  | 311.36 | 0 | -
April 2025 |  |  | 858 | WADSA-GADHCHIROLI NEW LINE (52.36 KM) | SECR | N22000480 | 6-2018 | 3/2027 | N.A. | 12/2026 | 1886.05 |  | 1880.61 | 740.67 | 25
April 2025 |  |  | 859 | PACHORA-JAMNER WITH EXTENSION UPTO MALKAPUR NG TO BG | CR | N22000511 | 8-2022 | 8/2027 | N.A. | 3/2029 | 955 |  | 2089.25 | 114.84 | -
April 2025 |  |  | 860 | SOLAPUR-TULJAPUR- OSMANABAD (UMBRELLA WORK) | CR | N22000513 | 1-2019 | 3/2028 | N.A. | 12/2027 | 904.92 |  | 2933.01 | 1130.01 | 7
April 2025 |  |  | 861 | DHULE (BORVIHIR)-NARDANA | UMBRELLA WORK | CR | 1-2019 | 12/2026 | N.A. | 3/2028 | 492.76 |  | 1158.99 | 198.13 | 5
April 2025 |  |  | 862 | KALYAN-MURBAD VIA ULHASNAGAR (UMBRELLA WORK) | CR | N22000515 | 2-2023 | 3/2027 | N.A. | 3/2027 | 836.12 |  | 836.12 | 9.23 | -
April 2025 |  |  | 863 | BARAMATI - LONAND | CR | N22000615 | 2-1999 | 3/2027 | N.A. | 3/2027 | 736.44 |  | 1843.9 | 663.53 | 50
April 2025 |  |  | 864 | MUMBAI URBAN TRANSPORT PROJECT IIIA | MRVC | N22000627 | 4-2019 | 12/2027 | N.A. | 12/2027 | 33690 |  | 33690 | 812.06 | -
April 2025 |  |  | 865 | NAGPUR- NAGBHIR RAILWAY LINE GAUGE CONVERSION PROJECT | MRIDC | N22000629 | 10-2019 | 6/2024 | N.A. | 10/2025 | 1400 |  | 2383 | 1739.7 | 85
April 2025 |  |  | 866 | REHABILITATION AND UPGRADATION OF END OF AHMEDNAGAR BYPASS TO KHARWANDI KASAR SECTION OF NH-222 FROM | MoRTH | N24000332 | 1-2015 | (N.A.) | {} |  | 225.81 |  | 225.81 | 167.96 | 96
April 2025 |  |  | 867 | CONSTRUCTION OF FLYOVER AT KM.544.650 INCLUDING ROB ,SERVICE ROADS ,FOOTPATH FOR RCC DRAINS ON URBAN | NHAI | N24000442 | 12-2015 | 3/2019 | 11/2023 | 5/2025 | 649.5 |  | 649.5 | 614.65 | 92.64
April 2025 |  |  | 868 | NAGPUR RING ROAD PACKAGE- 2 | NHAI | N24000560 | 3-2016 | 7/2019 | 3/2024 | 5/2025 | 591.66 |  | 591.66 | 632.4 | 98.73
April 2025 |  |  | 869 | 4-LANNING OF NH17 AND NEW NO. NH66 FROM KM 161/600 TO 205/400 UNDER HYBRID ANNUITY MODE | MoRTH | N24000584 | 3-2016 | (N.A.) | {12/2023} |  | 1142.62 | 1907.03 | 1142.62 | 1056.08 | 95.17
April 2025 |  |  | 870 | 4-LANNING OF NH17 AND NEW NO. NH66 FROM KM 241/300 TO 281/300 UNDER HYBRID ANNUITY MODE | MoRTH | N24000585 | 3-2016 | (N.A.) | {} |  | 1101.58 |  | 1101.58 | 608.53 | -
April 2025 |  |  | 871 | 4-LANNING OF BODHRE-DHULE SECTION(KM 390.000 TO 452.800) | NHAI | N24000656 | 3-2017 | 3/2020 | 7/2022 | 12/2025 | 744.64 |  | 1007 | 467.65 | 94.65
April 2025 |  |  | 872 | 4-LANNING OF WARANGA- MAHAGAON SECTION(KM 253.7000 TO 320.580) | NHAI | N24000659 | 3-2017 | 3/2017 | 5/2021 | 10/2024 | 1059.73 | 1071 | 1071 | 878.19 | 96.5
April 2025 |  |  | 873 | CONSTRUCTION OF 8 LANING OF EXISTING 4 LANE VADAPE TO THANE FROM KM 539.202 TO KM 563.000 SECTION OF | NHAI | N24000851 | 3-2018 | 7/2021 | N.A. | 6/2025 | 1162.92 | 1182.87 | 1182.87 | 412.38 | 59
April 2025 |  |  | 874 | SARSAM TO KOTHARI | MoRTH | N24001002 | 2-2016 | 7/2019 | N.A. | 12/2023 | 545.64 |  | 545.64 | 232.64 | 93.68
April 2025 |  |  | 875 | AKOLA TO AKOT | MoRTH | N24001003 | 1-2017 | 6/2019 | N.A. | 12/2023 | 313.95 |  | 313.95 | 270.26 | 99
April 2025 |  |  | 876 | DIGRAS DARWAH KARANJA | MoRTH | N24001013 | 1-2017 | 6/2019 | N.A. | 12/2023 | 391.06 | 391 | 391.06 | 287.6 | 92.76
April 2025 |  |  | 877 | DAHEGAON TO KUHI | MoRTH | N24001017 | 1-2017 | 6/2019 | N.A. | 12/2023 | 228.89 | 229 | 228.89 | 154.82 | 99
April 2025 |  |  | 878 | BHANDARA TO GHOTITOK | MoRTH | N24001018 | 1-2017 | 6/2019 | N.A. | 6/2019 | 392.83 | 393 | 392.83 | 274.75 | 100
April 2025 |  |  | 879 | AMDI TO SAONER | MoRTH | N24001021 | 1-2017 | 6/2019 | N.A. | 12/2023 | 396.91 | 397 | 396.91 | 289.79 | 98.69
April 2025 |  |  | 880 | WADI TO ASOLA | MoRTH | N24001022 | 1-2017 | 9/2019 | N.A. | 12/2023 | 363.82 | 364 | 363.82 | 154.65 | 93.15
April 2025 |  |  | 881 | RALEGAON TO RAMTIRTH | MoRTH | N24001046 | 1-2017 | 7/2019 | N.A. | 8/2023 | 210.81 |  | 210.81 | 210.81 | 96.5
April 2025 |  |  | 882 | VITA TO NAGAJ | MoRTH | N24001050 | 3-2018 | 12/2019 | N.A. | 12/2023 | 304.58 | 305 | 304.58 | 154.68 | 68.39
April 2025 |  |  | 883 | KARAD PATAN CHIPLUN GUHAGAR | MoRTH | N24001057 | 2-2017 | 6/2019 | N.A. | 10/2023 | 407.19 | 407 | 407.19 | 323.02 | 90
April 2025 |  |  | 884 | KARWANDI TO RAJURI | MoRTH | N24001058 | 3-2018 | 12/2019 | N.A. | 3/2024 | 276.95 | 277 | 276.95 | 160.94 | 92
April 2025 |  |  | 885 | PALPHATA TO PHULAMBARI | MoRTH | N24001060 | 3-2018 | 12/2019 | N.A. | 12/2023 | 227.19 | 227 | 227.19 | 141.92 | 95
April 2025 |  |  | 886 | NANDED TO JALKOT | MoRTH | N24001069 | 12-2017 | 9/2019 | N.A. | 9/2019 | 456.93 | 457 | 456.93 | 278.22 | 95
April 2025 |  |  | 887 | PUNE TO MALE VILLAGE | MoRTH | N24001078 | 3-2018 | 12/2019 | N.A. | 12/2023 | 228.31 |  | 228.31 | 100.97 | 93.83
April 2025 |  |  | 888 | ARDHAPUR TO HIMAYATNAGAR | MoRTH | N24001079 | 12-2017 | 6/2020 | N.A. | 12/2023 | 426.06 | 426 | 426.06 | 271.4 | 96.25
April 2025 |  |  | 889 | MALE VILLAGE TO PUNE RAIGARH DISTRICT BORDER | MoRTH | N24001080 | 3-2018 | 12/2019 | N.A. | 10/2023 | 256.15 |  | 256.15 | 126.62 | 98
April 2025 |  |  | 890 | PUNE RAIGARH DISTRICT BORDER TO MANGAON | MoRTH | N24001082 | 3-2018 | 12/2019 | N.A. | 12/2023 | 223.46 |  | 223.46 | 123.46 | 100
April 2025 |  |  | 891 | KOLDE TO KHETIYA | MoRTH | N24001090 | 1-2017 | 7/2019 | N.A. | 12/2023 | 509.18 |  | 509.18 | 283.13 | 94.81
April 2025 |  |  | 892 | SATARA TO MHASWAD | MoRTH | N24001092 | 1-2017 | 7/2019 | N.A. | 12/2023 | 653.46 |  | 653.46 | 369.62 | 77
April 2025 |  |  | 893 | MHASWAD TO TEMBHURNI | MoRTH | N24001099 | 1-2017 | 7/2019 | N.A. | 12/2023 | 488.6 |  | 488.6 | 279.42 | 76.5
April 2025 |  |  | 894 | KURUDWADI TO PANDHARPUR | MoRTH | N24001101 | 1-2017 | 7/2019 | N.A. | 11/2023 | 307.63 |  | 307.63 | 232.57 | 96.27
April 2025 |  |  | 895 | PANDHARPUR TO SANGOLA | MoRTH | N24001102 | 7-2017 | 7/2019 | N.A. | 12/2023 | 218.38 |  | 218.38 | 182.63 | 99.78
April 2025 |  |  | 896 | PEN TO KHOPOLI | MoRTH | N24001106 | 3-2018 | 3/2018 | N.A. | 1/2024 | 301.39 | 302 | 301.39 | 170.12 | 82.07
April 2025 |  |  | 897 | PANCHARAL TO MANDANGHAR | MoRTH | N24001107 | 7-2018 | 5/2020 | N.A. | 5/2020 | 381.08 | 302 | 381.08 | 45.66 | -
April 2025 |  |  | 898 | NASRATPUR TO BARASGAON | MoRTH | N24001112 | 7-2016 | 9/2019 | N.A. | 9/2019 | 406.54 | 407 | 406.54 | 274.3 | -
April 2025 |  |  | 899 | INDAPUR TO VADPALE | MoRTH | N24001114 | 1-2017 | 12/2019 | N.A. | 3/2024 | 1202.52 | 1656.94 | 1202.52 | 1450.82 | 61.42
April 2025 |  |  | 900 | PAITHAN TO SHIRUR | MoRTH | N24001122 | 3-2017 | 6/2019 | N.A. | 3/2024 | 341.8 |  | 341.8 | 226.19 | 78.6
April 2025 |  |  | 901 | SHIRUR TO KHARDA | MoRTH | N24001123 | 2-2017 | 6/2019 | N.A. | 12/2023 | 381.77 |  | 381.77 | 199.48 | 83.93
April 2025 |  |  | 902 | AURANGABAD TO SILLOD | MoRTH | N24001124 | 2-2017 | 6/2019 | N.A. | 12/2023 | 456.32 | 541.93 | 456.32 | 355.54 | 94
April 2025 |  |  | 903 | SILLOD TO FARDAPUR | MoRTH | N24001125 | 2-2017 | 6/2019 | N.A. | 12/2023 | 337.46 | 432.98 | 337.46 | 335.3 | 92
April 2025 |  |  | 904 | BHOGAN KHURD TO KASHEDI | MoRTH | N24001132 | 9-2017 | 6/2021 | N.A. | 12/2023 | 743.21 | 743 | 743.21 | 911.64 | 88.69
April 2025 |  |  | 905 | KANTE TO WAKED | MoRTH | N24001134 | 3-2016 | 11/2019 | N.A. | 12/2024 | 1230.02 | 1230 | 1230.02 | 791.8 | -
April 2025 |  |  | 906 | PARLI PIMPLA DAHIGUDA | MoRTH | N24001138 | 2-2017 | 6/2019 | N.A. | 8/2023 | 205.72 | 206 | 205.72 | 85.71 | 100
April 2025 |  |  | 907 | UPGRADATION OF ADHALGAON- JAMKHED SECTION OF NH-548 D FROM KM 132/600 TO KM 195/375 TO TWO LANE WITH | MoRTH | N24001448 | 11-2021 | 2/2022 | N.A. | 2/2022 | 223.35 |  | 223.35 | 209.36 | 87.88
April 2025 |  |  | 908 | REPANPALLI TO SIRONCHA | MoRTH | N24001468 | 3-2022 | 6/2022 | N.A. | 6/2024 | 282.07 |  | 282.07 | 34.65 | -
April 2025 |  |  | 909 | TUNNEL AT KHAMBATAKI GHAT SECTION AND ITS APPROACHES FROM EXISTING KM. 771.730 TO EXISTING KM. 782.0 | NHAI | N24001486 | 2-2019 | 2/2022 | 12/2024 | 8/2025 | 493 |  | 493 | 399.49 | 76.49
April 2025 |  |  | 910 | DHARAMPURI-LONAND FROM KM. 117.00 TO 166.40 (PKG-IV) ON MOHOL-ALANDI SECTION | NHAI | N24001488 | 9-2021 | 9/2023 | 12/2024 | 5/2025 | 618.45 |  | 618.45 | 639.23 | 96.2
April 2025 |  |  | 911 | 6L OF KAGAL-SATARA SECTION FROM KM 658.000 TO KM 725.000 OF NH-48 (PKG-II) | NHAI | N24001493 | 12-2022 | 12/2024 | N.A. | 11/2025 | 1749.86 |  | 1749.86 | 1838.16 | 65.41
April 2025 |  |  | 912 | 4L OF RATNAGIRI - KOLHAPUR SECTION OF NH-166 FROM KM 0.000 TO KM 19.769 AND KM 31.000 TO KM 67.140 ( | NHAI | N24001495 | 11-2022 | 11/2024 | N.A. | 9/2025 | 930 |  | 930 | 618.34 | 75.9
April 2025 |  |  | 913 | 4L OF BARAMATI TO INDAPUR (PKG-II) FROM KM. 41.400 TO KM. 84.550 OF NH-965G (SAINT TUKARAM MARG) | NHAI | N24001502 | 9-2021 | 9/2023 | 5/2025 | 5/2025 | 624.45 | 580.15 | 580.15 | 420.42 | 2
April 2025 |  |  | 914 | 4L OF INDAPUR TO TONDLE (PKG-III) FROM KM.84.550 TO KM. 131.00 OF NH-965G (SAINT TUKARAM MARG) | NHAI | N24001503 | 9-2021 | 9/2023 | 1/2025 | 3/2025 | 667.66 | 666.21 | 666.21 | 610.63 | 3
April 2025 |  |  | 915 | VADODARA MUMBAI EXPRESSWAY (PHASE II - PKG XI) [KM. 77.000 TO KM. 103.400] | GANJAD - TALSARI | NHAI | 5-2022 | 5/2024 | 6/2025 | 6/2025 | 1260 |  | 1260 | 665.73 | 96
April 2025 |  |  | 916 | VADODARA MUMBAI EXPRESSWAY (PHASE II - PKG XII) [KM. 50.700 TO KM. 77.000] | MASVAN - GANJAD | NHAI | 3-2022 | 3/2024 | 6/2025 | 6/2025 | 1549.02 |  | 1549.02 | 699 | 78.13
April 2025 |  |  | 917 | VADODARA MUMBAI EXPRESSWAY (PHASE II - PKG XIII) [KM. 26.582 TO KM. 50.700] | SHIRSAD - MASVAN | NHAI | 2-2022 | 2/2024 | 6/2025 | 6/2025 | 2747 |  | 2747 | 1125.16 | 77.05
April 2025 |  |  | 918 | VADODARA MUMBAI EXPRESSWAY (PHASE II - PKG XIV) [KM. 3.000 TO KM. 20.200 OF SPUR] (SHIRSAD - AKLOLI) | NHAI | N24001507 | 11-2022 | 5/2024 | 6/2025 | 6/2025 | 1124 |  | 1124 | 483.84 | 70.03
April 2025 |  |  | 919 | VADODARA MUMBAI EXPRESSWAY (PHASE II - PKG XVI) [KM. 43.000 TO KM. 69.800 OF SPUR] (AMNE - BHOJ) | NHAI | N24001508 | 11-2022 | 10/2024 | 6/2025 | 6/2025 | 1450 |  | 1450 | 718.65 | 82.05
April 2025 |  |  | 920 | VADODARA MUMBAI EXPRESSWAY (PHASE II - PKG XV) [KM. 20.200 TO KM. 43.000 OF SPUR] (AKLOLI - AMNE) | NHAI | N24001521 | 11-2022 | 10/2024 | 4/2025 | 4/2025 | 990 |  | 990 | 406.91 | 70.25
April 2025 |  |  | 921 | 6L OF KAGAL-SATARA SECTION FROM KM 592.240 TO KM 658.000 OF NH-48 (PKG-I) | NHAI | N24001546 | 1-2023 | 1/2025 | N.A. | 1/2025 | 1025.2 |  | 1025.2 | 446.14 | 43.52
April 2025 |  |  | 922 | BALANCE WORKS OF 4L PANVEL- INDAPUR SECTION OF NH-66 (OLD NH-17) FROM KM 42.300 (KASU) TO KM 84.600 ( | NHAI | N24001607 | 10-2022 | 5/2024 | 12/2025 | 12/2025 | 332 |  | 332 | 240.77 | 64.63
April 2025 |  |  | 923 | VADODARA MUMBAI EXPRESSWAY (PHASE II - PKG XVII) [KM. 69.800 TO KM. 79.783 OF SPUR] (BHOJ - MORBE) | NHAI | N24001608 | 9-2021 | 7/2025 | N.A. | 7/2025 | 2208.68 |  | 2208.68 | 565.2 | 73.73
April 2025 |  |  | 924 | BALANCE WORK OF 4 LANING OF PANVEL TO INDAPUR SECTION OF NH-66(OLD NH- 17) FROM KM 0.000 (PANVEL) TO | NHAI | N24001609 | 1-2023 | 12/2023 | 6/2025 | 6/2025 | 151.26 |  | 151.26 | 153.74 | 86.38
April 2025 |  |  | 925 | 4L OF EXISTING 2/4L STRETCH FROM LONAND TO DIVE GHAT (KM 166.400 TO KM 220.900 ) OF MOHOL ? ALANDI S | NHAI | N24001610 | 1-2022 | 5/2024 | 3/2025 | 5/2025 | 1833.73 |  | 1833.73 | 539.18 | 95.64
April 2025 |  |  | 926 | FOUR LANING OF AURANGABAD- PAITHAN SECTION OF NH-752E ON EPC MODE IN THE STATE OF MAHARASHTRA . | NHAI | N24001795 | 10-2022 | 7/2024 | 6/2025 | 12/2024 | 490.4 |  | 289 | 275.78 | 91
April 2025 |  |  | 927 | 4L OF RAJURA-KORPANA- ADILABAD ROAD UPTO M.S. BORDER FROM KM 32.910 TO KM 89.090 OF NH-353B | NHAI | N24001796 | 3-2022 | 10/2024 | 4/2025 | 4/2025 | 1013.33 | 1013.33 | 1111.33 | 355.07 | 62.01
April 2025 |  |  | 928 | 6L OF WAINGANGA BRIDGE - BHANDARA (INCLUDING BHANDARA BYPASS) SECTION FROM KM 485.000 TO KM 499.800 | NHAI | N24001797 | 10-2021 | 1/2024 | N.A. | 5/2025 | 815.77 |  | 815.77 | 732.7 | 100
April 2025 |  |  | 929 | 4L MITIGATION MEASURE STRUCTURES ON CH/MH BORDER TO WAINGANGA BRIDGE SECTION OF NH-53 | NHAI | N24001798 | 2-2021 | 11/2023 | N.A. | 5/2025 | 540.21 |  | 540.21 | 451.46 | 100
April 2025 |  |  | 930 | 4L OF NAGPUR-KATOL SECTION FROM KM. 13.00 TO KM. 62.900 OF NH-353J | NHAI | N24001799 | 2-2021 | 10/2023 | N.A. | 9/2025 | 1166.96 |  | 1251 | 1078.48 | 80.97
April 2025 |  |  | 931 | BAL. WORKS OF FAGNE (KM. 510.000) TO MAHARASHTRA/GUJARAT BORDER (KM. 650.794) | NHAI | N24001804 | 12-2019 | 9/2022 | 6/2024 | 11/2025 | 1654.07 |  | 980 | 835.19 | 95.75
April 2025 |  |  | 932 | 4L OF RATNAGIRI - KOLHAPUR SECTION FROM KM 67.140 TO KM 112.340 OF NH-166 (PKG ? II) | NHAI | N24001834 | 5-2023 | 5/2025 | N.A. | 5/2025 | 839 |  | 839 | 437.79 | 54
April 2025 |  |  | 933 | 4L OF RATNAGIRI - KOLHAPUR SECTION FROM KM 112.340 TO KM 145.300 OF NH-166 (PKG?III) | NHAI | N24001835 | 5-2023 | 5/2025 | N.A. | 5/2025 | 986 |  | 986 | 474.23 | 52.1
April 2025 |  |  | 934 | REHABILITATION AND UP- GRADATION TO 4 LANE ROAD WITH PAVED SHOULDER CONFIGURATION OF SECTION FROM UND | MoRTH | N24001880 | 3-2022 | 7/2025 | N.A. | 7/2025 | 778.18 |  | 778.18 | 135.78 | -
April 2025 |  |  | 935 | CONSTRUCTION OF NEW FOUR LANE BYPASS TO PARBHANI CITY (PARWA TO ASOLA) KM 463/265 TO KM 481/180 (DES | MoRTH | N24001882 | 3-2022 | 10/2024 | N.A. | 10/2024 | 496.64 |  | 496.64 | 0 | 8
April 2025 |  |  | 936 | CONSTRUCTION OF 4 LANE FLYOVER AT NAGPUR RTO CHOWK TO NAGPUR UNIVERSITY CAMPUS FROM CH 2/250 TO 5/10 | MoRTH | N24001883 | 3-2021 | 3/2024 | N.A. | 4/2024 | 478.83 |  | 478.83 | 233.48 | 65
April 2025 |  |  | 937 | REHABILITATION AND UPGRADATION OF SATANA TO MANGRUL (CHANDWAD) SECTION OF NH752 G DESIGN CH: KM 64.0 | MoRTH | N24001884 | 3-2023 | 5/2025 | N.A. | 5/2025 | 428.8 |  | 428.8 | 54.11 | 30.69
April 2025 |  |  | 938 | REHABILITATION AND UP- GRADATION OF JINTUR- SHIRAD SHAHAPUR SECTION KM 258.300 TO KM 306.300 [DESIGN | MoRTH | N24001885 | 2-2023 | 12/2024 | N.A. | 12/2024 | 414.81 |  | 414.81 | 0 | -
April 2025 |  |  | 939 | DEVELOPMENT/WIDENING OF TALEGAON ? CHAKAN ? SHIKRAPUR ? NHAVARA SECTION OF NH 548DG (NHAVARA TO CHOU | MoRTH | N24001886 | 10-2022 | 8/2024 | N.A. | 8/2024 | 304.68 |  | 304.68 | 97.09 | 58.78
April 2025 |  |  | 940 | REHABILITATION AND UPGRADATION OF BHOKARDAN TO KUMBHARI FATA DESIGN CH. (KM 13+500 TO 17+00) AND RAJ | MoRTH | N24001887 | 8-2022 | 6/2024 | N.A. | 6/2024 | 291.37 |  | 291.37 | 102.94 | 78.44
April 2025 |  |  | 941 | UP-GRADATION OF TIRORA- GONDIA, STATE HIGHWAY FROM EXISTING KM 163+213 (ON SH-335, TIRORA) TO KM 191+ | MoRTH | N24001888 | 8-2021 | 4/2023 | N.A. | 5/2024 | 288.14 |  | 288.14 | 63.01 | 46.31
April 2025 |  |  | 942 | 2 LANE + PS PIMPLNER TO SATANA -[DESIGN CHAINAGE KM 21.427 TO 64.00 ] OF NH- 752G] | MoRTH | N24001889 | 9-2019 | 7/2021 | N.A. | 12/2023 | 277.81 |  | 277.81 | 148.68 | 90
April 2025 |  |  | 943 | REHABILITATION AND UPGRADATION OF PARLI TO SIRSALA SECTION OF NH-361F (KM 136+700 TO 115+000) (LENGT | MoRTH | N24001890 | 2-2023 | 12/2024 | N.A. | 12/2024 | 261.82 |  | 261.82 | 70.59 | 46
April 2025 |  |  | 944 | BALANCE WORK OF REHABILITATION AND UP- GRADATION TO NH-166F FROM MAHAD JUNCTION (AT KM 123/400 ON NH- | MoRTH | N24001891 | 7-2021 | 11/2023 | N.A. | 3/2024 | 256.54 |  | 256.54 | 80.1 | 59.66
April 2025 |  |  | 945 | REHABILITATION AND UPGRADATION OF SHIRAPUR JUNCTION TO SHIVAJI CHOWK (DESIGN CHAINAGE KM. 130+00 TO | MoRTH | N24001892 | 2-2023 | 12/2024 | N.A. | 12/2024 | 245.61 |  | 245.61 | 43.39 | 32.5
April 2025 |  |  | 946 | 2 LANE + PS ASTHAMODE - TIVATYAL [DESIGN CH. KM 24.300 - 62.00] [KM 134.98-172.95 OF NH-63] | MoRTH | N24001894 | 9-2019 | 7/2021 | N.A. | 12/2023 | 228.82 |  | 228.82 | 144.54 | 95.44
April 2025 |  |  | 947 | REHABILATION AND UPGRADATION TO TWO LANES WITH PAVED SHOULDER CONFIGURATION FROM WATUR TO CHARTHANA | MoRTH | N24001895 | 11-2021 | 9/2023 | N.A. | 12/2023 | 228.01 |  | 228.01 | 103.01 | 99
April 2025 |  |  | 948 | UPGRADATIOBN AND REHABILITATION OF SECTION OF NH 361 F FROM PARLI (00/000) TO GANGAKHED (30/400) TO | MoRTH | N24001896 | 11-2021 | 9/2023 | N.A. | 4/2024 | 224.44 |  | 224.44 | 75.34 | 45.63
April 2025 |  |  | 949 | REHABILITATION AND UP- GRADATION OF SABALKHED TO ASHTI SECTION FROM KM 37+900 TO KM 55+100 AND CHINCH | MoRTH | N24001902 | 12-2022 | 9/2024 | N.A. | 9/2024 | 213.32 |  | 213.32 | 20 | 34
April 2025 |  |  | 950 | REHABILITATION AND UP- GRADATION OF MUDKHED TO NANDED SECTION FROM KM. 372+000 TO KM 388+400 OF NH 16 | MoRTH | N24001903 | 8-2022 | 4/2025 | N.A. | 4/2025 | 206.54 |  | 206.54 | 21.36 | -
April 2025 |  |  | 951 | KOPARGAON TO SAVALI VIHIR SECTION | MoRTH | N24001904 | 9-2022 | 7/2024 | N.A. | 7/2024 | 195.38 |  | 195.38 | 29.59 | 19.76
April 2025 |  |  | 952 | CONSTRUCTION OF MAJOR BRIDGE ACROSS MANJRA RIVER NEAR YESGI VILLAGE @ KM, 166/500 ON NH 63 TQ BILOLI | MoRTH | N24001905 | 10-2021 | 8/2023 | N.A. | 12/2023 | 188.69 |  | 188.69 | 111.26 | 95.8
April 2025 |  |  | 953 | UP-GRADATION TO 4 LANING OF DAULTABAD T-POINT TO MALIWADA [FROM DESIGN KM.0.000 TO KM 4.000] AND UPG | MoRTH | N24001906 | 8-2022 | 3/2024 | N.A. | 3/2024 | 185.59 |  | 185.59 | 63.56 | 48
April 2025 |  |  | 954 | CONSTRUCTION OF SIX LANE FLYOVER AT KATRAJ JUNCTION AT KM, 3/880 OF NH 548-DD (VADGAON - KATRAJ - KO | MoRTH | N24001907 | 6-2021 | 2/2024 | N.A. | 3/2024 | 169.15 |  | 169.15 | 36.94 | 35.96
April 2025 |  |  | 955 | UPGRADATION OF EXHISTING 2 LANE FLEXIBLE PAVEMENT TO 2 LANE PAVED SHOULDERS RIGID PAVEMENT FROM DESI | MoRTH | N24001908 | 12-2021 | 5/2024 | N.A. | 5/2024 | 167.97 |  | 167.97 | 35.28 | 36.76
April 2025 |  |  | 956 | STRENGTHING AND WIDINING OF EXISTING CARRIAGEWAY TO 10 M IN KM, 156/160 TO 229/160 (TEMBHURNI - KUSL | MoRTH | N24001909 | 11-2021 | 6/2024 | N.A. | 6/2024 | 157.72 |  | 157.72 | 55.38 | 90.41
April 2025 |  |  | 957 | REHABILITATION AND UPGRADATION OF JAMKHED TO SAUTADA SECTION OF NH548 D (FROM KM 195.375 TO KM 208.7 | MoRTH | N24001910 | 9-2022 | 7/2024 | N.A. | 7/2024 | 157.62 |  | 157.62 | 13.86 | 17.03
April 2025 |  |  | 958 | PANGAON TO DHARMAPURI AND PARALI TO INJEGAON 2L+PS | MoRTH | N24001911 | 3-2018 | 7/2024 | N.A. | 12/2023 | 152.03 |  | 152.03 | 81.35 | 97.57
April 2025 |  |  | 959 | 4L OF INDORA CHOWK TO PACHPAOLI AND AGRASEN CHOWK - ASHOKA CHOWK | NHAI | N24002071 | 3-2023 | 6/2026 | N.A. | 6/2026 | 998.27 |  | 998.27 | 318.58 | 42.12
April 2025 |  |  | 960 | IMPROVEMENT OF EXISTING ALIGNMENT OF PANDHARPUR TOWN PART BYPASSED SECTION FROM WAKHARI TO LORD VITT | NHAI | N24002072 | 7-2022 | 10/2025 | N.A. | 10/2025 | 150.21 | 150.21 | 150.21 | 24.66 | 2
April 2025 |  |  | 961 | STRENGTHENING OF 6-LANE PIMPALGAON-NASHIK-GONDE (KM. 380 - KM. 440) SECTION OF NH-3 IN MAHARASHTRA U | NHAI | N24002137 | 2-2024 | 3/2025 | N.A. | 3/2025 | 175 | 206.49 | 206.49 | 198.54 | 100
April 2025 |  |  | 962 | REHABILITATION/UPGRADATION OF EXISTING HIGHWAY TO 2L+PS/4 LANE OF DHAWALI TO RAJOLI FROM DESIGN KM.1 | MoRTH | N24002169 | 3-2022 | 9/2025 | N.A. | 9/2025 | 316.44 |  | 316.44 | 0 | -
April 2025 |  |  | 963 | REHABILITATION/ UPGRADATION OF EXISTING HIGHWAY TO FOUR LANE STANDARDS IN KURKHEDA TOWN FROM (KM.413 | MoRTH | N24002170 | 3-2022 | 5/2025 | N.A. | 5/2025 | 163.86 |  | 163.86 | 0 | -
April 2025 |  |  | 964 | REHABILITATION AND UP- GRADATION FOR TALERE A?? GAGANBAWDAA?? KOLHAPUR ROAD (NH-166G) STRETCHES START | MoRTH | N24002171 | 2-2023 | 4/2025 | N.A. | 4/2025 | 249.13 |  | 249.13 | 0 | -
April 2025 |  |  | 965 | UP-GRADATION TO 4 LANE CONFIGURATION FOR THE WORK OF PETH NAKA TO SANGLI ROAD, NH-166H, FROM KM 0+00 | MoRTH | N24002172 | 2-2023 | 12/2025 | N.A. | 12/2025 | 856.82 |  | 856.82 | 0 | -
April 2025 |  |  | 966 | REHABILITATION AND UP- GRADATION TO 2 LANE WITH PAVED SHOULDER CONFIGURATION OF MAHUD SANGOLA ROAD NH | MoRTH | N24002173 | 2-2023 | 4/2025 | N.A. | 4/2025 | 253.78 |  | 253.78 | 0 | -
April 2025 |  |  | 967 | UP-GRADATION TO FOUR LANE/ TWO LANE WITH PAVED SHOULDERS CONFIGURATION OF KALYAN - MURBAD - MALSHEJ | MoRTH | N24002174 | 2-2023 | 8/2026 | N.A. | 8/2026 | 984.07 |  | 984.07 | 0 | -
April 2025 |  |  | 968 | CONSTRUCTION OF FOUR-LANE CONCRETE ROAD FROM POLICE HEADQUARTER GONDIA CITY TO RAWANWADI VILLAGE (BI | MoRTH | N24002175 | 2-2023 | 8/2025 | N.A. | 8/2025 | 328.11 |  | 328.11 | 0 | -
April 2025 |  |  | 969 | REHABILITATION/UP GRADATION OF KARANJA ? KHERDA - MURTIZAPUR SECTION TO 4LANE+PAVED SHOULDER STANDA | MoRTH | N24002176 | 3-2023 | 2/2026 | N.A. | 2/2026 | 594.44 |  | 594.44 | 0 | -
April 2025 |  |  | 970 | REHABILITATION / UPGRADATION TO 4 LANE WITH PAVED SHOULDER OF EXISTING SECTION IN SILLOD TOWN WITH D | MoRTH | N24002177 | 3-2023 | 7/2025 | N.A. | 7/2025 | 153.79 |  | 153.79 | 0 | -
April 2025 |  |  | 971 | REHABILITATION, UPGRADATION AND WIDENING OF EXISTING HIGHWAY TO RIGID PAVEMENT 2 LANE WITH PAVED SHO | MoRTH | N24002178 | 2-2023 | 7/2026 | N.A. | 7/2026 | 723.13 |  | 723.13 | 0 | -
April 2025 |  |  | 972 | MUMBAI METRO LINE 3 (COLABA- BANDRA-SEEPZ) | MMRCL | N28000086 | 7-2013 | 3/2020 | 7/2025 | 7/2025 | 23136 |  | 37276 | 28615.78 | 95
April 2025 |  |  | 973 | PUNE METRO RAIL PROJECT | PHASE 1 | MMRC | 12-2016 | 11/2021 | 9/2024 | 9/2024 | 11420 | 13656.22 | 13656.22 | 13036.65 | 100
April 2025 |  |  | 974 | NAGPUR METRO RAIL PROJECT PHASE II | NMRCL | N28000155 | 12-2022 | 12/2027 | N.A. | 12/2027 | 6708 |  | 6708 | 768.34 | 21.6
April 2025 |  |  | 975 | PCMC NIGDI PROJECT EXTENSION OF CORRIDOR 1 OF PUNE METRO PHASE 1 | MMRC | N28000157 | 10-2023 | 1/2027 | N.A. | 1/2027 | 910.18 |  | 910.18 | 81.34 | 14.97
April 2025 |  |  | 976 | PUNE METRO PHASE-1 EXTENSION FROM SWARGATE TO KATRAJ | MMRC | N28000160 | 9-2024 | 3/2029 | N.A. | 3/2029 | 2954.53 |  | 2954.53 | 15.14 | 2
April 2025 |  | CIVIL AVIATION | 977 | CONSTRUCTION OF NEW INTEGRATED TERMINAL BUILDING, CONTROL TOWER CUM TECHNICAL BLOCK, APRON, LINK TAX | AAI | N04000100 | 11-2021 | 7/2024 | 3/2026 | 3/2026 | 499 |  | 499 | 154.47 | 39.4
April 2025 |  | RAILWAYS | 978 | JIRIBAM TO IMPHAL | TUPUI)(NL)(NEFR | NFR | 4-2003 | 12/2026 | 3/2028 | 3/2028 | 14322.79 | 12274.06 | 22234.6 | 15265.4 | 68.7
April 2025 |  | RAILWAYS | 979 | 2-LANING OF CHURACHANDPUR TUIVAI SECTION OF NH-102B | PKG- 2A | NHIDCL | 3-2020 | 6/2022 | 1/2025 | 9/2025 | 292.24 |  | 292.24 | 130.66 | 89.72
April 2025 |  | RAILWAYS | 980 | 2-LANING OF CHURACHANDPUR TUIVAI SECTION OF NH-102B | PKG- 2B | NHIDCL | 6-2020 | 8/2022 | 1/2025 | 10/2025 | 365.53 |  | 365.53 | 156.31 | 77.36
April 2025 |  |  | 981 | 2-LANING OF CHURACHANDPUR TUIVAI SECTION OF NH-102B | PKG- 4A | NHIDCL | 3-2020 | 6/2022 | 1/2025 | 5/2025 | 167.95 | 204.12 | 167.95 | 88.05 | 69.89
April 2025 |  |  | 982 | 2-LANING OF CHURACHANDPUR TUIVAI SECTION OF NH-102B | PKG- 4B | NHIDCL | 7-2020 | 8/2022 | 2/2025 | 5/2025 | 177.76 |  | 177.76 | 89.67 | 80.53
April 2025 |  |  | 983 | IMPROVEMENT/UPGRADATION OF EXISTING 2-LANE TO 4-LANE DIVIDED HIGHWAY FROM TAPHOU KUKI TO DAILI SECTI | NHIDCL | N24001274 | 8-2020 | 4/2022 | 6/2025 | 10/2025 | 379.39 |  | 379.39 | 214.93 | 67.72
April 2025 |  |  | 984 | MARIAM - PEREN PKG-1A | NHIDCL | N24001349 | 2-2021 | 12/2022 | 3/2025 | 7/2025 | 226.32 |  | 226.32 | 104.95 | 74.48
April 2025 |  |  | 985 | MARIAM - PEREN (PKG 1B) | NHIDCL | N24001350 | 2-2021 | 12/2022 | 10/2024 | 2/2025 | 188.36 |  | 188.36 | 126.71 | 100
April 2025 |  |  | 986 | IMPHAL - KHONGSANG PKG-2 | NHIDCL | N24001353 | 3-2021 | 12/2022 | 3/2025 | 3/2026 | 195.14 |  | 195.14 | 61.81 | 50.79
April 2025 |  |  | 987 | TAMENGLONG - MAHUR PKG-3 | NHIDCL | N24001354 | 3-2021 | 12/2022 | 9/2024 | 11/2025 | 234.08 |  | 234.08 | 139.45 | 91.85
April 2025 |  |  | 988 | SENAPATI- IMPHAL PKG-5B | NHIDCL | N24001400 | 3-2021 | 1/2023 | 5/2025 | 10/2025 | 211.7 |  | 211.7 | 83.79 | 68.65
April 2025 |  |  | 989 | IMPHAL - KHONGSANG PKG-3 | NHIDCL | N24001401 | 7-2021 | 3/2023 | 3/2025 | 10/2025 | 467 |  | 467 | 193.81 | 77.74
April 2025 |  |  | 990 | TAMENGLONG - MAHUR PKG-1 | NHIDCL | N24001402 | 7-2021 | 3/2023 | 1/2025 | 1/2025 | 185.8 |  | 185.8 | 117.78 | 100
April 2025 |  |  | 991 | TAMENGLONG - MAHUR PKG-2 | NHIDCL | N24001403 | 7-2021 | 3/2023 | 8/2024 | 12/2025 | 483.87 |  | 483.87 | 278.89 | 92.8
April 2025 |  |  | 992 | TAMENGLONG - MAHUR PKG-4 | NHIDCL | N24001404 | 7-2021 | 3/2023 | 2/2025 | 3/2025 | 198.77 |  | 198.77 | 127.86 | 100
April 2025 |  |  | 993 | CHURACHANPUR TUIVAI PKG-3 | NHIDCL | N24001405 | 7-2021 | 10/2023 | 3/2025 | 5/2025 | 673.27 |  | 673.27 | 377.12 | 78.46
April 2025 |  |  | 994 | TAMENGLONG - MAHUR PKG-5 | NHIDCL | N24001436 | 8-2021 | 5/2023 | 1/2025 | 1/2026 | 477.86 |  | 477.86 | 243.46 | 83.92
April 2025 |  |  | 995 | TAMENGLONG - MAHUR PKG-6 | NHIDCL | N24001437 | 9-2021 | 5/2023 | 11/2024 | 12/2025 | 311.18 |  | 311.18 | 186.15 | 81.65
April 2025 |  |  | 996 | MARAM - PEREN PKG-3 | NHIDCL | N24001439 | 8-2021 | 5/2023 | 10/2024 | 2/2025 | 467.41 |  | 467.41 | 264.83 | 100
April 2025 |  |  | 997 | IMPHAL - KHONGSANG PKG-4 | NHIDCL | N24001453 | 8-2021 | 12/2023 | 7/2025 | 12/2025 | 579.63 |  | 579.63 | 172.65 | 69.38
April 2025 |  |  | 998 | CONSTRUCTION OF 2-LANING WITH HARD SHOULDER ROAD OF UKHRUL - TOLOI - TADUBI SECTION OF NH-102A FROM | NHIDCL | N24001473 | 9-2021 | 2/2024 | 3/2025 | 5/2025 | 310.76 |  | 310.76 | 129.15 | 96.77
April 2025 |  |  | 999 | IMPHAL - KHONGSANG PKG-5 | NHIDCL | N24001538 | 12-2021 | 5/2024 | 2/2025 | 3/2026 | 410.68 |  | 410.68 | 147.81 | 67.64
April 2025 |  |  | 1000 | IMPHAL - KHONGSANG PKG-6 | NHIDCL | N24001539 | 12-2021 | 2/2025 | 9/2025 | 12/2025 | 504.76 |  | 504.76 | 183.15 | 74.23
April 2025 |  |  | 1001 | AKASH BRIDGE - JESSAMI SECTION PKG-2 | NHIDCL | N24001540 | 3-2022 | 2/2025 | 2/2025 | 3/2025 | 152.11 |  | 152.11 | 73.48 | 100
April 2025 |  |  | 1002 | CONSTRUCTION OF 2-LANING WITH HARD SHOULDER ROAD OF UKHRUL - TOLOI - TADUBI SECTION OF NH-102A FROM | NHIDCL | N24001974 | 9-2021 | 1/2025 | 1/2025 | 9/2025 | 315.56 |  | 315.56 | 121.49 | 79.4
April 2025 |  |  | 1003 | LMPHAL TO JIRIBAM PKG-7 | NHIDCL | N24002028 | 1-2023 | 12/2025 | 12/2025 | 3/2026 | 760.16 |  | 760.16 | 148.98 | 58.19
April 2025 |  |  | 1004 | UKHRUL TOLOI TADUBI PKG-2 | NHIDCL | N24002131 | 3-2023 | 2/2026 | 3/2026 | 3/2026 | 578.98 |  | 578.98 | 145.62 | 69.25
April 2025 |  |  | 1005 | MARREM KHULLEN TO JESSAMI SECTION IMPHAL- UKHRUL - JESSAMI PKG-6 (DESIGN CHAINAGE KM 95.700 TO KM 14 | NHIDCL | N24002202 | 3-2023 | 12/2026 | N.A. | 12/2026 | 554.66 |  | 554.66 | 11.64 | 9.21
April 2025 |  |  | 1006 | IMPHAL-KOHIMA ROAD PKG-4B | NHIDCL | N24002203 | 9-2020 | 6/2026 | N.A. | 6/2026 | 268.98 |  | 268.98 | 13.14 | 14.91
April 2025 |  |  | 1007 | JESSAMI TO LAYNEN BRIDGE UKHRUL - JESSAMI PKG-7 | NHIDCL | N24002227 | 3-2023 | 6/2026 | N.A. | 6/2026 | 164.89 |  | 164.89 | 1.46 | 3.28
April 2025 |  |  | 1008 | IMPHAL-KOHIMA ROAD PKG-5A | NHIDCL | N24002232 | 9-2020 | 8/2026 | N.A. | 8/2026 | 228.97 |  | 228.97 | 0 | 4.6
April 2025 |  | DEPARTMENT OF HIGHER EDUCATION | 1009 | CONSTRUCTION AND DEVELOPMENT OF NATINAL INSTITUTE OF TECHNOLOGY MEGHALAYA PERMANENT CAMPUS AT SOHRA | RITES OF HIGHER | N42000001 | 9-2013 | 9/2014 | 7/2025 | 7/2025 | 484.32 | 429.7 | 429.7 | 295.55 | 83
April 2025 |  | DEPARTMENT OF HIGHER EDUCATION | 1010 | WIDENING TO 2-LANE WITH GEOMETRIC IMPROVEMENTS OF TURA DALU ROAD UNDER JICA FUNDING FROM KM 85.000 T | NHIDCL | N24000771 | 4-2017 | 9/2021 | 3/2025 | 6/2025 | 553.51 | 610.09 | 553.51 | 419.49 | 84.94
April 2025 |  | DEPARTMENT OF HIGHER EDUCATION | 1011 | IMPROVEMENT/WIDENING TO 2- L WITH PAVED SHOULDER FROM (DESIGN KM 0.00 TO KM 10.670) / 4-LANING FROM ( | NHIDCL | N24001313 | 11-2020 | 12/2023 | 10/2025 | 10/2025 | 351.12 |  | 351.12 | 295.87 | 61.5
April 2025 |  | DEPARTMENT OF HIGHER EDUCATION | 1012 | IMPROVEMENT/WIDENING TO 2- LANE WITH PAVED SHOULDER FROM (DESIGN KM 10.670 TO KM 37.550) BETWEEN SHIL | NHIDCL | N24001314 | 11-2020 | 12/2023 | N.A. | 8/2026 | 525.68 |  | 525.68 | 425.76 | 31
April 2025 |  | DEPARTMENT OF HIGHER EDUCATION | 1013 | IMPROVEMENT/WIDENING TO 2- LANE WITH PAVED SHOULDER FROM (DESIGN KM 45.760 TO KM 63.530) BETWEEN SHIL | NHIDCL | N24001334 | 11-2020 | 12/2023 | N.A. | 4/2026 | 445.51 |  | 445.51 | 206.15 | 26
April 2025 |  |  | 1014 | IMPROVEMENT/WIDENING TO 2- LANE WITH PAVED SHOULDER / 4-LANING FROM (DESIGN KM 63.530 TO KM 71.520) B | NHIDCL | N24001335 | 11-2020 | 12/2023 | N.A. | 11/2026 | 284.21 |  | 284.21 | 100.93 | 23.1
April 2025 |  |  | 1015 | RANIKOR-MAHESHKHOLA- BAGHMARA (RMB) PKG-4 (KANAI- RONGARA) | NHIDCL | N24001339 | 10-2020 | 4/2022 | 6/2024 | 2/2025 | 157.86 | 146.92 | 157.86 | 152.95 | 100
April 2025 |  |  | 1016 | RANIKOR-MAHESHKHOLA- BAGHMARA (RMB) PKG-3 | NHIDCL | N24001360 | 3-2021 | 12/2022 | 6/2024 | 2/2025 | 260.21 |  | 260.21 | 239.35 | 100
April 2025 |  |  | 1017 | REHABILITATION AND UPGRADATION OF NONGSTOIN TO WAHKAJI SECTION OF PROJECT ROAD KM 0.000 TO KM 43.06 | MoRTH | N24001441 | 8-2020 | 2/2022 | 3/2025 | 3/2025 | 302.88 |  | 302.88 | 140.2 | 95
April 2025 |  |  | 1018 | REHABITITATION AND UP GRADATION OF NONGSTOIN- RAMBRAI-KYRSHAI ROAD UP TO MEGHALAYA-ASSAM BORDER FROM | NHIDCL | N24001474 | 9-2021 | 5/2024 | 12/2024 | 12/2025 | 359.86 |  | 359.86 | 232.55 | 89
April 2025 |  |  | 1019 | RANIKOR- MAHESHKHOLA- BAGHMARA PKG-2 | NHIDCL | N24001541 | 11-2021 | 6/2024 | 12/2024 | 5/2025 | 283.5 |  | 283.5 | 256.07 | 96.93
April 2025 |  |  | 1020 | CONSTRUCTION OF 2-LANE WITH PAVED SHOULDER OF SHILLONG WESTERN BYPASS STARTING FROM NH-06 NEAR LADUM | NHIDCL | N24002156 | 3-2023 | 9/2026 | N.A. | 9/2026 | 620.3 |  | 620.3 | 210.58 | 28
April 2025 |  |  | 1021 | SHILLONG WESTERN BYPASS PACKAGE-2 | NHIDCL | N24002157 | 3-2023 | 9/2026 | N.A. | 9/2026 | 686 |  | 686 | 281.9 | 23
April 2025 |  |  | 1022 | CONSTRUCTION OF 2-LANE WITH PAVED SHOULDERS OF SHILLONG WESTERN BYPASS STARTING FROM NH-06 NEAR LADU | NHIDCL | N24002158 | 3-2023 | 9/2026 | N.A. | 9/2026 | 562.48 |  | 562.48 | 297.79 | 24
April 2025 |  |  | 1023 | DAINADUBI-DARUGIRI PKG-1B | NHIDCL | N24002233 | 3-2023 | 3/2027 | N.A. | 3/2027 | 705.83 |  | 705.83 | 0.31 | -
April 2025 |  | RAILWAYS | 1024 | BHAIRABI SAIRONG, NL, NEFR | NFR | N22000100 | 4-2008 | 3/2025 | N.A. | 7/2025 | 6527.45 | 5021.45 | 8213.72 | 7948.91 | 96
April 2025 |  | RAILWAYS | 1025 | WIDENING AND UP-GRADATION TO 2-LANE WITH PAVED SHOULDER CONFIGURATION AND GEOMETRIC IMPROVEMENTS FRO | NHIDCL | N24000857 | 4-2017 | 4/2023 | N.A. | 6/2025 | 519.09 |  | 785.65 | 667.78 | 96.6
April 2025 |  | RAILWAYS | 1026 | WIDENING AND UP-GRADATION TO 2-LANE WITH PAVED SHOULDER CONFIGURATION AND GEOMETRIC IMPROVEMENTS FRO | NHIDCL | N24000858 | 4-2017 | 7/2023 | N.A. | 5/2024 | 640.07 |  | 1286.35 | 1192.26 | 98.9
April 2025 |  | RAILWAYS | 1027 | WIDENING AND UP-GRADATION TO 2-LANE WITH PAVED SHOULDER CONFIGURATION AND GEOMETRIC IMPROVEMENTS FRO | NHIDCL | N24000861 | 4-2017 | 4/2023 | N.A. | 6/2025 | 473.18 |  | 688.25 | 539.93 | 94.38
April 2025 |  |  | 1028 | WIDENING AND UP-GRADATION TO 2-LANE WITH PAVED SHOULDER CONFIGURATION AND GEOMETRIC IMPROVEMENTS FRO | NHIDCL | N24000862 | 4-2017 | 4/2023 | N.A. | 6/2025 | 537.82 |  | 789.05 | 768.85 | 96.82
April 2025 |  |  | 1029 | WIDENING AND UP-GRADATION TO 2-LANE WITH PAVED SHOULDER CONFIGURATION AND GEOMETRIC IMPROVEMENTS FRO | NHIDCL | N24000863 | 4-2017 | 6/2023 | N.A. | 5/2025 | 518.53 |  | 906.76 | 847.17 | 97.2
April 2025 |  |  | 1030 | WIDENING AND UP-GRADATION TO 2-LANE WITH PAVED SHOULDER CONFIGURATION AND GEOMETRIC IMPROVEMENTS FRO | NHIDCL | N24000864 | 4-2017 | 4/2024 | N.A. | 5/2025 | 404.29 |  | 750.32 | 654.75 | 97.71
April 2025 |  |  | 1031 | WIDENING AND UP-GRADATION TO 2-LANE WITH PAVED SHOULDER CONFIGURATION AND GEOMETRIC IMPROVEMENTS FRO | NHIDCL | N24000865 | 4-2017 | 9/2023 | N.A. | 5/2025 | 428.11 |  | 746.39 | 606.93 | 97.9
April 2025 |  |  | 1032 | CONSTRUCTION OF TWO LANE WITH PAVED SHOULDER OF SELLING-DULTE SECTION OF NH-06 (PKG-I) | NHIDCL | N24001278 | 3-2020 | 7/2022 | N.A. | 6/2024 | 206.88 |  | 219.33 | 265.18 | 100
April 2025 |  |  | 1033 | CONSTRUCTION OF TWO LANE WITH PAVED SHOULDER OF SELLING-DULTE SECTION OF NH-06 (PKG-III) | NHIDCL | N24001281 | 3-2020 | 7/2022 | N.A. | 6/2025 | 292.24 |  | 331.17 | 291.2 | 93.2
April 2025 |  |  | 1034 | DULTE- KWALKULH - CHAMPAI PKG.2 | NHIDCL | N24001356 | 3-2021 | 12/2022 | 4/2024 | 4/2024 | 233.25 |  | 233.25 | 172.09 | 100
April 2025 |  |  | 1035 | TLABUNG - LUNGLEI PKG-A | NHIDCL | N24001358 | 3-2021 | 12/2022 | N.A. | 3/2026 | 698.44 |  | 698.45 | 499.26 | 59.4
April 2025 |  |  | 1036 | TLABUNG - LUNGLEI PKG-B | NHIDCL | N24001359 | 3-2021 | 1/2023 | N.A. | 3/2026 | 740.58 |  | 740.58 | 362.71 | 57.4
April 2025 |  |  | 1037 | KEIFANG - TUVAI PKG-1 | NHIDCL | N24001440 | 9-2021 | 5/2023 | N.A. | 5/2024 | 492.94 |  | 492.94 | 354.89 | 90.5
April 2025 |  |  | 1038 | UP-GRADATION TO 2-LANE WITH PAVED SHOULDERS OF NGOPA - PAWLRANG SECTION OF NH 102B OF AIZAWL - IMPHA | NHIDCL | N24001975 | 9-2021 | 2/2025 | N.A. | 12/2025 | 523.78 |  | 523.78 | 643.63 | 78
April 2025 |  |  | 1039 | KEIFANG - TUVAI PKG-3 | NHIDCL | N24002027 | 12-2021 | 2/2025 | N.A. | 12/2025 | 500.88 |  | 500.88 | 250.46 | 65.1
April 2025 |  |  | 1040 | ZORINPUI- HMAWNGBU- LONGMASU (NH-502A) | NHIDCL | N24002204 | 2-2023 | 12/2026 | N.A. | 12/2026 | 781.85 |  | 781.85 | 67.12 | 1.12
April 2025 |  | COAL | 1041 | NILJAI EXPANSION (DEEP) OC | 3.5 MTY | WCL | 8-2016 | 3/2022 | 3/2025 | 3/2025 | 319.76 | 319.76 | 319.76 | 183.67 | 98
April 2025 |  | COAL | 1042 | BINA KAKRI AMALGAMATION OCP 14 MTPA | NCL | N06000192 | 8-2020 | 3/2024 | N.A. | 3/2027 | 836.42 |  | 836.42 | 768.64 | 58.2
April 2025 |  | DPIIT | 1043 | NATIONAL INDUSTRIAL CORRIDOR PROJECT | DMIC FOR DPIIT | N40000001 | 9-2011 | 3/2027 | 3/2032 | 3/2032 | 20084 | 26684 | 26684 | 4969.89 | 50.99
April 2025 |  | PETROLEUM | 1044 | KOCHI-KOOTTANAD- BANGALORE-MANGALORE PIPELINE PHASE-II | GAIL | N16000285 | 6-2009 | 12/2012 | 12/2025 | 12/2025 | 2915 | 5909 | 5909 | 4191.9 | 93.8
April 2025 |  | PETROLEUM | 1045 | SRIKAKULAM ANGUL PIPELINE PROJECT | GAIL | N16000388 | 9-2019 | 7/2022 | 6/2025 | 6/2025 | 2658.34 |  | 2658.34 | 2173.3 | 94.2
April 2025 |  | PETROLEUM | 1046 | DHAMRA HALDIA PIPELINE PROJECT | GAIL | N16000391 | 3-2020 | 11/2022 | 12/2025 | 12/2025 | 1030.65 |  | 1030.65 | 831.8 | 86.3
April 2025 |  | PETROLEUM | 1047 | MUMBAI NAGPUR JHARSUGUDA PIPELINE PROJECT | GAIL | N16000398 | 6-2020 | 5/2023 | 6/2025 | 6/2025 | 7844.25 |  | 7844.25 | 6266 | 93.8
April 2025 |  | PETROLEUM | 1048 | CGD PROJECT AT NAWADA AND KODERMA DISTRICTS | IOCL | N16000426 | 6-2019 | 12/2029 | 3/2030 | 3/2030 | 169 |  | 169 | 74.64 | 27.2
April 2025 |  | PETROLEUM | 1049 | NORTH EAST GAS GRID | IGGL | N16000439 | 11-2020 | 3/2024 | 7/2025 | 3/2027 | 9265 | 9265 | 9265 | 6270.19 | 84.51
April 2025 |  | PETROLEUM | 1050 | GURDASPUR JAMMU PIPELINE | GAIL | N16000531 | 7-2023 | 7/2026 | 7/2026 | 7/2026 | 521.92 | 521.92 | 521.92 | 121.5 | 33.56
April 2025 |  |  | 1051 | COMPREHENSIVE SCHEME FOR THE STRENGHTENING OF THE TRANSMISSION AND DISTRIBUTION SYSTEM IN A P | PGCIL | N18000249 | 12-2014 | 12/2018 | 3/2025 | 3/2029 | 4754.42 | 9129.32 | 9129.32 | 7602.44 | 81
April 2025 |  |  | 1052 | NORTH EASTERN REGION POWER SYSTEM IMPROVEMENT PROJECT (NERPSIP) FOR SIX (6) STATES | PGCIL | N18000250 | 12-2014 | 12/2018 | 3/2025 | 6/2025 | 5111.33 | 6700 | 6700 | 5276.39 | 95.8
April 2025 |  |  | 1053 | TS FOR EVACUATION OF POWER FROM PAKALDUL HEP IN CHENAB VALLEY HEPS - LTA SYSTEM | PGCIL | N18000328 | 2-2022 | 4/2025 | N.A. | 6/2025 | 318.12 |  | 318.12 | 169.75 | 95
April 2025 |  |  | 1054 | TRANSMISSION SYSTEM STRENGTHENING FOR SRINAGAR-LEH TRANSMISSION SYSTEM | PGCIL | N18000330 | 3-2022 | 12/2024 | N.A. | 7/2025 | 288.71 |  | 288.71 | 144.79 | 48
April 2025 |  |  | 1055 | TRANSMISSION SYSTEM STRENGTHENING SCHEME FOR EVACUATION OF POWER FROM SOLAR ENERGY ZONES IN RAJASTHA | PGCIL | N18000331 | 2-2022 | 9/2023 | N.A. | 6/2025 | 359.47 |  | 359.47 | 314.16 | 84
April 2025 |  |  | 1056 | TRANSMISSION SYSTEM STRENGTHENING SCHEME FOR EVACUATION OF POWER FROM SOLAR ENERGY ZONES IN RAJASTHA | PGCIL | N18000332 | 5-2022 | 11/2023 | N.A. | 8/2025 | 1666 |  | 1666 | 1490.62 | 90.3
April 2025 |  |  | 1057 | TRANSMISSION NETWORK EXPANSION IN GUJARAT TO INCREASE ATC FROM ISTS: PART B | PGCIL | N18000337 | 7-2022 | 6/2023 | N.A. | 9/2025 | 4546.26 |  | 4546.26 | 2785.35 | 91
April 2025 |  |  | 1058 | SYSTEM STRENGTHENING SCHEME FOR EASTERN AND NORTH EASTERN REGION | PGCIL | N18000343 | 10-2022 | 10/2025 | N.A. | 10/2025 | 307.87 |  | 307.87 | 184.31 | 89
April 2025 |  |  | 1059 | TRANSMISSION SYSTEM FOR KURNOOL WIND ENERGY ZONE SOLAR ENERGY ZONE (AP) PART-A PART B | PGCIL | N18000352 | 3-2023 | 11/2024 | N.A. | 8/2025 | 3546.94 |  | 3546.94 | 2202.14 | 89
April 2025 |  |  | 1060 | ER WR TRANSMISSION LIMITED | PGCIL | N18000353 | 3-2023 | 3/2025 | N.A. | 5/2025 | 281.16 |  | 281.16 | 162.14 | 91
April 2025 |  |  | 1061 | NANGALDAM-TALWARA(NL),NR | NR | 220100188 | 3-1981 | 12/2025 | 1/2027 | 6/2027 | 2018 | 603 | 2017.96 | 1579.04 | 75
April 2025 |  |  | 1062 | LALITPUR-SATNA-REWA- SINGRULI NL, (NCR) | WCR | 220100232 | 9-1998 | 3/2027 | N.A. | 3/2025 | 8913.94 | 63.57 | 8248.5 | 2520.04 | 43
April 2025 |  |  | 1063 | CHHAPRA-BALLIA UP | NER | N22000134 | 3-2013 | 2/2025 | N.A. | 12/2025 | 941.05 | 954 | 1045.82 | 1001.52 | 95.5
April 2025 |  |  | 1064 | CHOTTAUDEPUR-DHAR(NL) | WR | N22000138 | 4-2007 | 12/2026 | 12/2027 | 12/2027 | 1793.65 | 1793.63 | 1793.63 | 1619.35 | 59
April 2025 |  |  | 1065 | DAHOD-INDORE VIA SARDARPUR, JHABUA AND DHAR (NL) | WR | N22000139 | 4-2007 | 2/2027 | 2/2027 | 2/2027 | 1942 | 1873.1 | 2873.11 | 2913.16 | 59
April 2025 |  |  | 1066 | GWALIOR-SEOPURKALA WITH EXTENSION TO KOTA (GC) | NCR | N22000148 | 4-2011 | 3/2025 | N.A. | 12/2024 | 2912.96 |  | 3845.6 | 1024.32 | -
April 2025 |  |  | 1067 | DHOLPUR-SIRMUTTRA WITH EXTENSION TO GANGAPURCITY AND MOHARI-TANTPUR AND TANPUR-BANSI PAHARPUR | NCR | N22000158 | 4-2010 | 2/2019 | N.A. | 12/2026 | 746.83 |  | 746.83 | 389.88 | 30
April 2025 |  |  | 1068 | NEW BONGAIGAON-RANGIA- KAMAKGHYA DOUBLING | NFR | N22000183 | 4-2013 | 8/2024 | N.A. | 10/2024 | 2047.51 |  | 2832.35 | 3709.47 | 99.51
April 2025 |  |  | 1069 | NEW BG LINE FROM BALURGHAT TO HILLY NFR | NFR | N22000206 | 4-2010 | 3/2027 | N.A. | 3/2027 | 1208.67 |  | 1181.57 | 412.99 | 7
April 2025 |  |  | 1070 | NEW BG LINE FROM JAGBANI TO BIRATNAGAR | NFR | N22000207 | 4-2010 | 3/2022 | 12/2026 | 12/2026 | 401.65 | 485.96 | 485.96 | 361.33 | 86
April 2025 |  |  | 1071 | MURKONGSELEK-PASIGHAT NL | NFR | N22000208 | 4-2011 | 3/2025 | N.A. | 11/2025 | 435.06 |  | 1252.49 | 752.82 | 53
April 2025 |  |  | 1072 | PIRPAINTI-JASIDIH | ER | N22000219 | 4-2013 | 3/2028 | 3/2028 | 3/2028 | 2555.03 |  | 2610.84 | 1124.78 | 45
April 2025 |  |  | 1073 | KAZIPET-VIJAYAWADA 3RD LINE WITH ELECTRIFICATION | SCR | N22000261 | 4-2012 | 2/2025 | N.A. | 3/2025 | 1953 |  | 1952.68 | 1755.99 | -
April 2025 |  |  | 1074 | DEOBAND (MUZAFFARNAGAR)- ROORKEE NL | NR | N22000274 | 4-2007 | 3/2024 | N.A. | 3/2025 | 1053.23 |  | 1053 | 578.92 | 99
April 2025 |  |  | 1075 | RAYADURGA-TUMKUR NL | SWR | N22000279 | 4-2007 | 9/2015 | N.A. | 2/2028 | 2495.59 | 2495.59 | 2495.59 | 1645.12 | 60
April 2025 |  |  | 1076 | HOTGI-KUDGI-GADAG | SWR | N22000333 | 3-2015 | 12/2024 | N.A. | 2/2026 | 1877.81 | 1877.81 | 2458.87 | 2513.53 | 89
April 2025 |  |  | 1077 | KAZIPET-BALHRSHA | SCR | N22000367 | 4-2015 | 1/2025 | N.A. | 1/2025 | 2594.59 |  | 2909 | 2797.55 | -
April 2025 |  |  | 1078 | MUMBAI AHMEDABAD HIGH SPEED RAIL PROJECT | NHSRCL | N22000463 | 12-2015 | 8/2027 | N.A. | 8/2027 | 108000 |  | 108000 | 76441 | 51.5
April 2025 |  |  | 1079 | WESTERN DEDICATED FREIGHT CORRIDOR | DFCC | N22000464 | 11-2007 | 3/2022 | N.A. | 3/2020 | 51101 | 51101 | 51101 | 47476 | 83
April 2025 |  |  | 1080 | CHANDIGARH-BADDI | NR | N22000467 | 4-2007 | 6/2025 | 12/2026 | 12/2026 | 1540.13 | 1540.14 | 1540.14 | 941.19 | 28
April 2025 |  |  | 1081 | NARAYANGARH TO BHADRAK 3RD LINE (155 KM) | SER | N22000506 | 3-2019 | 12/2024 | N.A. | 6/2026 | 2400 |  | 1866.31 | 1979.58 | 58
April 2025 |  |  | 1082 | VARANASI-AURANGABAD KM.786 TO KM.978.40 | NHAI | N24000182 | 9-2011 | 3/2014 | N.A. | 6/2025 | 2848 |  | 3241.56 | 3901.66 | 90.02
April 2025 |  |  | 1083 | 4/6L OF SPUR TO HARIDWAR (GREENFIELD) FROM KM. 0.000 TO KM. 49.000 | NHAI | N24001628 | 11-2021 | 2/2025 | 8/2025 | 8/2025 | 2155.95 |  | 2155.95 | 1280.3 | 66.8
April 2025 |  |  | 1084 | 6L WITH ACCESS CONTROL PROVISION SAHARANPUR BYPASS TO GANESHPUR SECTION FROM 13.89 KM TO 41.820 KM O | NHAI | N24001629 | 4-2022 | 11/2024 | 5/2025 | 5/2025 | 796.65 |  | 796.65 | 417.88 | 83.55
April 2025 |  | SHIPPING AND PORTS | 1085 | JAL MARG VIKAS PROJECT | IWAI | N25000072 | 1-2018 | 3/2023 | 12/2025 | 12/2025 | 5369.18 | 5061.15 | 5061.15 | 3414.95 | 68.38
April 2025 |  | SHIPPING AND PORTS | 1086 | PHASE-I OF CONSOLIDATION OF EXISTING CDR DATA CENTERS AND NIB-P3 DATA CENTERS WITH STATE OF THE ART | BSNL | N26000114 | 3-2020 | 6/2021 | 11/2021 | 6/2025 | 461.42 | 461.42 | 461.42 | 166.02 | 81
April 2025 |  | SHIPPING AND PORTS | 1087 | SUPER EDGE ROUTERS FOR BSNL INTERNET PROTOCOL - MULTI PROTOCOL LEBEL SWITCHING (IPMPLS) NETWORK and | BSNL | N26000115 | 3-2023 | 3/2024 | 7/2024 | 3/2025 | 239.6 |  | 239.6 | 175.17 | 100
April 2025 |  | SHIPPING AND PORTS | 1088 | MPLS-IP BASED ACCESS AND AGGREGATION NETWORK (MAAN) IN BSNL ALONG WITH TEST AND MEASURING EQUIPMENT | BSNL | N26000116 | 5-2023 | 8/2024 | 11/2024 | 6/2025 | 645.13 |  | 645.13 | 346.27 | 86.89
April 2025 |  | SHIPPING AND PORTS | 1089 | PLANNIN ENGINEERING SUPPLY INSTALLATION TESTING COMMISSIONING INTEGARTION and ANNUAL MAINTENANCE OF | BSNL | N26000117 | 6-2023 | 6/2025 | N.A. | 6/2025 | 24556.35 | 24544.55 | 24544.55 | 7941 | 92.3
April 2025 |  |  | 1090 | OPTICAL TRANSPORT NETWORK (OTN) PH-4 IN BSNL | BSNL | N26000118 | 2-2024 | 8/2025 | N.A. | 8/2025 | 810.99 |  | 810.99 | 570 | 99.35
April 2025 |  | URBAN DEVELOPMENT | 1091 | DELHI GHAZIABAD MEERUT RRTS CORRIDOR | NCRTC | N28000134 | 3-2019 | 6/2025 | N.A. | 6/2025 | 30274 |  | 30274 | 25204.71 | 85.5
April 2025 |  | PETROLEUM | 1092 | AUGMENTATION OF DIMAPUR DEPOT, DIMAPUR | IOCL | N16000529 | 8-2023 | 11/2027 | N.A. | 11/2027 | 227.62 |  | 227.62 | 4.54 | 17.5
April 2025 |  | RAILWAYS | 1093 | NEW LINE FROM DIMAPUR TO ZUBZA(KOHIMA) NATIONAL PROJECT (NEFR) | NFR | N22000124 | 4-2006 | 3/2026 | N.A. | 12/2029 | 6663.2 | 6663.2 | 6663.2 | 4611.24 | 71
April 2025 |  | RAILWAYS | 1094 | FOUR LANING OF DIMAPUR KOHIMA ROAD FROM DESIGN KM 123.840 TO KM 138.775 (EXISTING KM 124.100 TO KM 1 | NHIDCL | N24000686 | 3-2016 | 9/2019 | 11/2022 | 5/2025 | 373.07 | 534.41 | 534.41 | 382.5 | 99.81
April 2025 |  | RAILWAYS | 1095 | FOUR LANING OF EXISTING DIMAPUR KOHIMA ROAD FROM DESIGN KM 152.490 TO KM 166.700 (EXISTING KM 156.00 | NHIDCL | N24000688 | 3-2016 | 8/2022 | 9/2025 | 9/2025 | 429.52 | 794.74 | 794.74 | 321.4 | 90.84
April 2025 |  | RAILWAYS | 1096 | (I) CONSTRUCTION OF FOUR/SIX LANING FROM KM 132.375 TO KM 158.058 (TOTAL NEW ALIGNMENT LENGTH OF 20. | NHIDCL | N24000752 | 2-2017 | 9/2020 | 2/2023 | 4/2025 | 387 | 688.12 | 688.12 | 389.81 | 100
April 2025 |  |  | 1097 | (II) CONSTRUCTION OF DIMAPUR BYPASS (ASSAM PORTION) OF 4/6 LANE PAVEMENT ON EPC BASIS FROM EXISTING | NHIDCL | N24000753 | 3-2018 | 11/2022 | 8/2024 | 4/2025 | 500.09 | 698.81 | 698.81 | 393.53 | 100
April 2025 |  |  | 1098 | CONSTRUCTION OF TWO LANE WITH HARD SHOULDERS OF MERANGKONG-TAMLU-MON ROAD FROM EXISTING KM 20.456 TO | NHIDCL | N24000763 | 3-2018 | 12/2021 | 8/2022 | 8/2025 | 215.79 |  | 215.79 | 127.85 | 77.1
April 2025 |  |  | 1099 | CONSTRUCTION OF TWO LANE WITH HARD SHOULDERS OF MERANGKONG-TAMLU-MON ROAD FROM EXISTING KM 60.345 TO | NHIDCL | N24000765 | 3-2018 | 9/2018 | 6/2023 | 9/2025 | 323.98 |  | 323.98 | 112.43 | 52.47
April 2025 |  |  | 1100 | CONSTRUCTION OF 2 LANE WITH PAVED SHOULDER FROM KM. 168 TO 183.783 (YESEMYONG TO UNGER) ON MOKOKCHUN | MoRTH | N24001179 | 3-2017 | 11/2020 | 2/2023 | 2/2023 | 217.35 |  | 217.35 | 214.18 | 100
April 2025 |  |  | 1101 | WIDENING OF EXISTING SINGLE/INTERMEDIATE LANE ROAD TO 2 LANE ROAD FROM KM. 83.00 TO KM 101.00 ON NH- | MoRTH | N24001180 | 3-2019 | 12/2022 | 1/2023 | 1/2023 | 237.51 |  | 237.51 | 215.47 | 100
April 2025 |  |  | 1102 | CONSTRUCTION OF 2-LANE WITH PAVED SHOULDER OF KOHIMA-BYPASS ROAD FROM DESIGN KM10.500 TO 21.00KM [D | NHIDCL | N24001255 | 9-2020 | 10/2022 | 9/2024 | 6/2026 | 277.44 |  | 277.44 | 168.88 | 66.12
April 2025 |  |  | 1103 | CONSTRUCTION OF 2-LANE WITH PAVED SHOULDER OF KOHIMA-BYPASS ROAD FROM DESIGN KM21.0 TO KM32.0 [DESIG | NHIDCL | N24001257 | 8-2020 | 10/2022 | 6/2025 | 6/2025 | 159.85 | 342.29 | 159.85 | 101.93 | 29.36
April 2025 |  |  | 1104 | CONSTRUCTION OF 2-LANE WITH PAVED SHOULDER OF KOHIMA-BYPASS ROAD FROM DSIGN KM32.0 TO KM43.454 [DES | NHIDCL | N24001258 | 8-2020 | 4/2022 | 4/2023 | 8/2025 | 202.36 |  | 202.36 | 75.17 | 30.8
April 2025 |  |  | 1105 | UPGRADATION OF EXISTING ROAD TO 2-LANE WITH PAVED SHOULDER FROM KOHIMA TO MAO FROM KM 185.540 TO KM | NHIDCL | N24001259 | 9-2020 | 4/2022 | 5/2024 | 12/2025 | 315.63 |  | 315.63 | 116.7 | 74.23
April 2025 |  |  | 1106 | 2 LANING OF KOHIMA - JESSAMI SECTION (PACKAGE II) | NHIDCL | N24001282 | 3-2020 | 6/2022 | N.A. | 1/2026 | 355.79 |  | 355.79 | 114.35 | 63.2
April 2025 |  |  | 1107 | 2-LANING OF CHANGTONGYA TO LONGLENG ROAD OF NH-702 | PKG-I | NHIDCL | 3-2020 | 6/2022 | 10/2022 | 6/2023 | 278.95 |  | 278.95 | 166.29 | 100
April 2025 |  |  | 1108 | 2 LANING OF KOHIMA - JESSAMI SECTION (PACKAGE V) | NHIDCL | N24001287 | 4-2020 | 12/2021 | 11/2025 | 11/2025 | 330.8 |  | 330.8 | 168.02 | 91.97
April 2025 |  |  | 1109 | CONSTRUCTION OF 2-LANE WITH PAVED SHOULDER OF KOHIMA-BYPASS ROAD FROM DESIGN KM 0.00 TO KM 10.500 [D | NHIDCL | N24001288 | 8-2020 | 4/2022 | 11/2026 | 11/2026 | 232.29 | 350.88 | 232.29 | 69.98 | 14.42
April 2025 |  |  | 1110 | CHANGTONGYA TO LONGLENG ROAD PKG-2 | NHIDCL | N24001389 | 3-2020 | 6/2022 | 9/2022 | 1/2025 | 206.53 |  | 206.53 | 119.25 | 99.4
April 2025 |  |  | 1111 | PEREN-DIMAPUR SECTION PKG- 2 | NHIDCL | N24001406 | 7-2021 | 3/2023 | 9/2025 | 9/2025 | 258.52 |  | 258.52 | 83.96 | 77.9
April 2025 |  |  | 1112 | MERANGKONG-TAMLU-MON (MTM) PKG-5 | NHIDCL | N24001438 | 7-2021 | 12/2023 | N.A. | 9/2025 | 161.73 |  | 161.73 | 62.08 | 66.76
April 2025 |  |  | 1113 | WIDENING OF EXISTING SINGLE LANE / INTERMEDIATE LANE ROAD TO 2 LANE FROM KM 101 TO KM 125 OF NH 61 I | MoRTH | N24001465 | 6-2020 | 9/2024 | 6/2026 | 6/2026 | 252.19 |  | 252.19 | 11.97 | 14.5
April 2025 |  |  | 1114 | WIDENING TO EXISTING SINGLE LANE /INTERMEDIATE LANE TO 2 LANE FROM KM185.00 TO KM 220.00 OF NH-61 (N | MoRTH | N24001466 | 3-2021 | 7/2024 | 6/2025 | 6/2025 | 297.24 |  | 297.24 | 137.57 | 76.2
April 2025 |  |  | 1115 | WIDENING TO EXISTING SINGRE/INTERMEDIATE RANE TO 2 LANE FROM KM 135 TO KM 147 AND FROM KM 156.00 TO | MoRTH | N24001467 | 3-2021 | 2/2024 | 3/2025 | 3/2025 | 226.44 |  | 226.44 | 140.24 | 100
April 2025 |  |  | 1116 | CONSTRUCTION OF 2 LANE WITH HARD SHOULDER FROM DESIGN CHAINAGE KM 283.000 TO KM 325.440 (5- LEGGED J | NHIDCL | N24001475 | 3-2022 | 12/2024 | N.A. | 1/2025 | 605.36 |  | 605.36 | 273.21 | 100
April 2025 |  |  | 1117 | WIDENING OF EXISTING SINGLE LANE ROAD TO INTERMEDIATE LANE ROAD FROM MOKOKCHUNG TO CHARE VIA DIKHU I | MoRTH | N24001855 | 2-2021 | 6/2025 | 6/2025 | 6/2025 | 192.93 |  | 192.93 | 103.62 | 88.6
April 2025 |  |  | 1118 | PEREN-DIMAPUR PKG-3 | NHIDCL | N24001912 | 2-2021 | 6/2025 | N.A. | 12/2025 | 177.77 | 199.02 | 199.02 | 43.33 | 61.13
April 2025 |  |  | 1119 | WIDENING TO 2 LANE WITH HARD SHOULDER OF AKEGWO- AVANGKHU SECTION OF NH- 202K FOR PACKAGE-I (DESIGN CH | NHIDCL | N24001976 | 12-2022 | 2/2026 | N.A. | 2/2026 | 430.24 |  | 430.24 | 92.24 | 49.95
April 2025 |  |  | 1120 | WIDENING TO 2 LANE WITH HARD SHOULDER OF AKEGWO- AVANGKHU SECTION OF NH- 202K FOR PACKAGE-II (DESIGN C | NHIDCL | N24001977 | 12-2022 | 2/2026 | N.A. | 2/2026 | 442.54 |  | 442.54 | 39.97 | 22.28
April 2025 |  |  | 1121 | WIDENING TO 2 LANE WITH HARD SHOULDER OF AKEGWO- AVANGKHU SECTION OF NH- 202K FOR PACKAGE-III (DESIGN | NHIDCL | N24001978 | 12-2022 | 2/2026 | N.A. | 2/2026 | 497.18 |  | 497.18 | 159.36 | 59.2
April 2025 |  |  | 1122 | BASUNDHARA (WEST) OC EXTN(7.00 MTY) | MCL | N06000112 | 5-2014 | 3/2019 | N.A. | 3/2027 | 479.15 |  | 479.15 | 267.1 | 63.04
April 2025 |  |  | 1123 | SIARMAL OCP (40.00MTY) | MCL | N06000113 | 2-2021 | 3/2029 | N.A. | 3/2029 | 5194.96 |  | 5194.96 | 3436.4 | 51.07
April 2025 |  |  | 1124 | INTEGRATED LAKHANPUR- BELPAHAR-LILARI OCP | MCL | N06000167 | 5-2018 | 3/2027 | N.A. | 3/2027 | 2434.75 |  | 2434.75 | 1749.33 | 60.87
April 2025 |  |  | 1125 | REORGANISATION OF BHARATPUR OCP EXPANSION | MCL | N06000171 | 11-2018 | 3/2029 | N.A. | 3/2029 | 2838.87 |  | 2838.87 | 1743.39 | 44.6
April 2025 |  |  | 1126 | TALABIRA II AND III OCP | NLC | N06000189 | 7-2017 | 1/2027 | N.A. | 1/2027 | 2401.07 |  | 2401.07 | 1626.71 | 62
April 2025 |  |  | 1127 | NAINI COAL MINE | SCCL | N06000203 | 3-2020 | 3/2024 | N.A. | 3/2027 | 494.3 |  | 494.3 | 491.33 | 80
April 2025 |  |  | 1128 | GOPALJI-KANIHA OCP | MCL | N06000229 | 4-2022 | 3/2028 | N.A. | 3/2028 | 6107.87 |  | 6107.87 | 1694.01 | 17.39
April 2025 |  |  | 1129 | BALARAM EXPANSION OCP | MCL | N06000230 | 8-2020 | 3/2029 | N.A. | 3/2029 | 3504.21 |  | 3504.21 | 1022.3 | 50.17
April 2025 |  |  | 1130 | SUBHADRA OCP | MCL | N06000249 | 5-2021 | 3/2029 | 3/2029 | 3/2029 | 1693.81 |  | 1693.81 | 1180.35 | 39.3
April 2025 |  |  | 1131 | NLC TALABIRA THERMAL POWER PROJECT (PHASE-1: 3 X 800 MW) | NLC | N06000270 | 1-2024 | 5/2029 | 3/2030 | 3/2030 | 27213 |  | 27213 | 1556.46 | 1.55
April 2025 |  |  | 1132 | RPR OF HINGULA EXPANSION OCP | MCL | N06000285 | 11-2022 | 3/2029 | N.A. | 3/2029 | 1561.85 |  | 1561.85 | 47.49 | 3.57
April 2025 |  |  | 1133 | BHUBANESWARI EXPANSION OCP | MCL | N06000286 | 3-2024 | 3/2031 | N.A. | 3/2031 | 5366.28 |  | 5366.28 | 0.82 | 3.39
April 2025 |  |  | 1134 | BALABHADRA OCP | MCL | N06000288 | 4-2023 | 3/2030 | N.A. | 3/2030 | 978.44 |  | 978.44 | 209.5 | 1.86
April 2025 |  |  | 1135 | INTEGRATED KULDA GARJANBAHAL OCP | MCL | N06000289 | 4-2023 | 3/2030 | N.A. | 3/2030 | 3563.5 |  | 3563.5 | 6.72 | 1
April 2025 |  | DEPARTMENT OF HIGHER EDUCATION | 1136 | INDIAN INSTITUTE OF SCIENCE EDUCATION AND RESEARCH BERHAMPUR | CPWD EDUCATION | N28000126 | 1-2019 | 3/2022 | N.A. | 6/2025 | 790.79 |  | 790.79 | 701.39 | 96
April 2025 |  | MINES | 1137 | 5TH STREAM ALUMINA REFINERY EXPANSION PROJECT | NALCO | N10000010 | 12-2014 | 4/2021 | 9/2025 | 9/2025 | 4103 | 5677.4 | 5677.4 | 3751.02 | 73.01
April 2025 |  | MINES | 1138 | UTKAL D AND E COAL BLOCK | NALCO | N10000011 | 5-2016 | 1/2020 | 11/2023 | 3/2024 | 534 |  | 1021.97 | 826.19 | 86.5
April 2025 |  | MINES | 1139 | CONVERSION OF FLAT BOTTOM SETTLERS AND WASHERS WITH A SINGLE TRAIN OF HRDS AND DCWS IN STREAMS 1 AND | NALCO | N10000012 | 12-2015 | 11/2020 | 9/2025 | 8/2027 | 355 | 581 | 581 | 163.55 | 12.6
April 2025 |  | MINES | 1140 | SOURCING OF BAUXITE ARRANGEMENT FOR 5TH STREAM ALUMINA REFINERY FROM SOUTH BLOCK MINING LEASE OF PAN | NALCO | N10000013 | 11-2017 | 4/2021 | 5/2025 | 5/2025 | 483 | 483 | 495 | 383.19 | 88.87
April 2025 |  | MINES | 1141 | POTTANGI BAUXITE MINES | NALCO | N10000016 | 5-2018 | 12/2024 | N.A. | 5/2025 | 1437 |  | 1381 | 649.96 | 50.9
April 2025 |  | MINES | 1142 | CONSTRUCTION OF RED MUD POND - II AT NALCO DAMANJODI ODISHA | NALCO | N10000017 | 9-2019 | 3/2023 | 5/2024 | 5/2024 | 225.79 |  | 270.66 | 5 | 100
April 2025 |  | MINES | 1143 | ADDITIONAL STORAGE TANKS AT PARADIP | IOCL | N16000361 | 11-2018 | 9/2021 | 12/2024 | 3/2025 | 462.3 | 552.44 | 552.44 | 493.72 | 100
April 2025 |  |  | 1144 | INTEGRATED PARA XYLENE (PX) AND PURIFIED TEREPHTHALIC ACID (PTA) PROJECT AT PARADIP REFINERY | IOCL | N16000396 | 7-2020 | 1/2024 | 4/2025 | 4/2026 | 13805 |  | 13805 | 7173.59 | 89.2
April 2025 |  | POWER | 1145 | EASTERN REGION EXPANSION SCHEME XXIX | PGCIL | N18000351 | 3-2023 | 11/2025 | N.A. | 11/2025 | 524.04 |  | 524.04 | 359.97 | 99
April 2025 |  | POWER | 1146 | TALCHER THERMAL POWER PROJECT STAGE III(2X660 MW) | NTPC | N18000364 | 8-2022 | 5/2027 | N.A. | 12/2027 | 11844 |  | 12539 | 3218.1 | 21.4
April 2025 |  | POWER | 1147 | KHURDA ROAD- BOLANGIR(NL)ECOR | ECOR | 220100284 | 4-1994 | 12/2026 | 12/2026 | 12/2026 | 3550 | 3791.66 | 5089.37 | 4690.64 | 84
April 2025 |  | POWER | 1148 | TALCHER- BIMALAGARH(NL)(ECOR) | ECOR | 220100328 | 4-2005 | 3/2025 | N.A. | 3/2026 | 1928.1 |  | 1928.07 | 1686.57 | 40
April 2025 |  | POWER | 1149 | BHADRAK - NERGUNDI 3RD LINE | ECOR | N22000316 | 3-2013 | 11/2024 | 1/2026 | 1/2026 | 1284.39 | 1284.39 | 1284.39 | 1257.23 | 80
April 2025 |  | POWER | 1150 | JAGADALPUR-KORAPUT DOUBLING | ECOR | N22000376 | 4-2015 | 3/2024 | N.A. | 3/2022 | 1547.38 |  | 1547.38 | 1273.36 | 93.5
April 2025 |  | POWER | 1151 | KORAPUT - SINGAPUR ROAD DOUBLING | ECOR | N22000379 | 4-2015 | 12/2027 | 3/2026 | 3/2026 | 2362 | 2361.74 | 2361.74 | 1752.26 | 78
April 2025 |  |  | 1152 | JARAPADA - BUDHAPANK WITH FLY OVER AT TALCHER ROAD 3RD AND 4TH LINE | ECOR | N22000380 | 4-2015 | 3/2027 | N.A. | 8/2026 | 820.61 |  | 810.02 | 573.95 | -
April 2025 |  |  | 1153 | BUDHAPANK - SALEGAON VIA RAJATGARH 3RD AND 4TH LINE. | ECOR | N22000381 | 4-2015 | 3/2026 | 11/2025 | 11/2025 | 1172.92 |  | 2022.75 | 1906.43 | 80
April 2025 |  |  | 1154 | VIZIANAGARAM -SAMABALPUR 3RD LINE | RVNL | N22000409 | 1-1991 | 12/2026 | N.A. | 12/2026 | 4803.16 |  | 4803.16 | 4691.52 | -
April 2025 |  |  | 1155 | EXECUTION OF RAIL CONNECTIVITY PROJECT FOR COAL TRANSPORTATION IN ODISHA FOR MCRL | IRCON | N22000418 | 4-2016 | 3/2020 | N.A. | 12/2025 | 5200 |  | 5200 | 0 | 17.4
April 2025 |  |  | 1156 | JEYPORE MALKANGIRI NEW LINE | ECOR | N22000516 | 2-2018 | 7/2033 | N.A. | 7/2033 | 2344 |  | 642.69 | 220.78 | 90
April 2025 |  |  | 1157 | JEYPORE NABARANGPUR NEWLINE | ECOR | N22000517 | 7-2017 | 7/2028 | N.A. | 7/2028 | 748 |  | 747.91 | 0 | -
April 2025 |  |  | 1158 | TALCHER - ANGUL NEW LINE WITH Y CONNECTION AT TALCHER | ECOR | N22000518 | 7-2018 | 12/2026 | N.A. | 12/2026 | 278.96 | 495 | 494.62 | 29.5 | -
April 2025 |  |  | 1159 | KODINGAMALI BAUXITE MINES TO SINGARAM RAILWAY STATION | ECOR | N22000519 | 8-2022 | 8/2027 | N.A. | 8/2027 | 190.9 |  | 190.9 | 10 | -
April 2025 |  |  | 1160 | GANDHAMARDAN IRON ORE MINES TO GOALDIH STATION | ECOR | N22000520 | 9-2022 | 9/2027 | N.A. | 3/2028 | 189.93 |  | 189.93 | 14.04 | -
April 2025 |  |  | 1161 | BRUNDAMAL-JHARSUGUDA- FLYOVER CONNECTION FOR JOINING DN LINE | ECOR | N22000521 | 12-2009 | 12/2026 | N.A. | 12/2026 | 296.51 |  | 297 | 302.5 | 10
April 2025 |  |  | 1162 | BAGHUAPAL FLY OVER (20 KM) | ECOR | N22000522 | 8-2019 | 8/2027 | 8/2027 | 8/2027 | 183 | 257.97 | 257.97 | 0.83 | -
April 2025 |  |  | 1163 | ROURKELA-BONDAMUNDA A- CABIN 5TH LINE (10 KM) (UMBRELLA WORK PB#57/2019- 20/NR) | SER | N22000571 | 9-2022 | 9/2026 | N.A. | 2/2026 | 209.75 |  | 244.99 | 59.29 | 10
April 2025 |  |  | 1164 | DEVELOPMENT OF FOUR LANNING OF ANGUL- SAMBALPUR SECTION OF NATIONAL HIGHWAY NH-42 (NEW NH-55 IN THE S | NHAI | N24000619 | 9-2016 | 8/2019 | N.A. | 5/2025 | 2510.04 |  | 2510.04 | 1181.34 | 99.38
April 2025 |  |  | 1165 | REHABILITATION AND UPGRADATION OF CUTTACK ANGUL SECTION OF NH-42 (NEW NH-55) TO 4 LANE (KM. 0+400 TO | NHAI | N24000715 | 12-2017 | 7/2020 | N.A. | 6/2025 | 686.65 | 565 | 686.65 | 574.26 | 97.65
April 2025 |  |  | 1166 | REHABILITATION AND UP- GRADATION OF EXISTING 2- LANE TO 4 LANE OF DUBURI (KM 388.376) TO CHANDIKHOLE ( | NHAI | N24000733 | 1-2018 | 8/2022 | N.A. | 12/2025 | 633.68 | 492.83 | 633.68 | 560.38 | 85.6
April 2025 |  |  | 1167 | REHABILITATION AND UP- GRADATION OF EXISTING 2- LANE TO FOUR LANE FROM TALCHAR TO END OF KAMAKHYANAG | NHAI | N24000734 | 1-2018 | 8/2021 | N.A. | 6/2025 | 614.48 | 503.3 | 757.12 | 664.48 | 100
April 2025 |  |  | 1168 | REHABILITATION AND UPGRADATION OF CUTTACK- ANGUL SECTION TO 4 LANE (KM 60.20) TO (KM 112.0) PKG II ON | NHAI | N24000736 | 1-2018 | 9/2020 | N.A. | 6/2025 | 686.65 | 504.09 | 1015.16 | 479.81 | 97.5
April 2025 |  |  | 1169 | REHABILITATION AND UPGRADATION OF SIX LANING OF BHADRAK BALESHWAR SECTION (KM 136.50) TO (KM 199.141 | NHAI | N24000738 | 1-2018 | 9/2021 | N.A. | 7/2025 | 999 | 1152.7 | 1152.7 | 498.82 | 80.58
April 2025 |  |  | 1170 | REHABILITATION AND UP- GRADATION TO 4-LANING OF RAJAMUNDA-BARKOTE SECTION OF NH-23 (NEW NH NO. 143) ( | NHAI | N24000739 | 1-2018 | 6/2021 | 5/2025 | 5/2025 | 503.88 | 609.03 | 609.03 | 536.89 | 99.5
April 2025 |  |  | 1171 | WIDENING TO 2LPS FROM 0/0 TO 119/0 OF NH-157 IN THE STATE OF ODISHA. | MoRTH | N24000912 | 8-2016 | 2/2017 | N.A. | 8/2025 | 287.7 |  | 293.66 | 275.42 | 98.66
April 2025 |  |  | 1172 | WIDENING TO 2LPS FROM 239/9 TO 294/3 OF NH-57 (NAYAGARH TO KHURDA) IN THE STATE OF ODISHA | MoRTH | N24000914 | 12-2016 | 8/2018 | N.A. | 9/2025 | 223.5 |  | 223.5 | 220.5 | 92
April 2025 |  |  | 1173 | WIDENING TO 2LPS FROM 269/30 TO 328/20 OF NH-49 IN THE STATE OF ODISHA | MoRTH | N24000917 | 3-2018 | 8/2018 | N.A. | 6/2025 | 199.16 |  | 199.16 | 155.1 | 98
April 2025 |  |  | 1174 | BALANCE WORK OF PANIKOILI RIMULI SECTION OF NEW NH-20 FROM KM 0.00 TO KM. 163.000 | NHAI | N24001647 | 8-2020 | 3/2022 | N.A. | 5/2025 | 200 | 154.73 | 154.73 | 150.38 | 99.62
April 2025 |  |  | 1175 | 6L GREENFIELD KANDILI - ALURU SECTION OF NH-130-CD ROAD FROM KM 342+500 TO KM 365+033 (PACKAGE-OD-8 | NHAI | N24001665 | 12-2021 | 10/2024 | N.A. | 12/2025 | 1592 | 1592 | 1592 | 1067.86 | 76.49
April 2025 |  |  | 1176 | 6L GREENFIELD BARAJA - KANDILI SECTION OF NH- 130- CD ROAD FROM KM 338+500 TO KM 342+500 (PACKAGE-OD | NHAI | N24001666 | 12-2021 | 9/2024 | N.A. | 8/2025 | 714 | 714 | 714 | 569.08 | 92.07
April 2025 |  |  | 1177 | 6L GREENFIELD KALIAGURA ? BAUNSAGUAR SECTION OF NH- 130-CD ROAD FROM KM 249+000 TO KM 293+000 (PACKAG | NHAI | N24001667 | 9-2021 | 5/2024 | N.A. | 10/2025 | 1734 | 1734 | 1734 | 1203.09 | 83.99
April 2025 |  |  | 1178 | 6L OF BADAKUMARI - KARKI SECTION FROM KM 179.000 TO KM 226.500 OF NH-130-CD | PACKAGE ? OD-3 | NHAI | 3-2021 | 4/2024 | N.A. | 6/2025 | 1249 |  | 1249 | 465.59 | 84.06
April 2025 |  |  | 1179 | 6L OF DHANARA - HATIBENA SECTION FROM KM 124.611 TO KM 146.50 OF NH-130-CD | PACKAGE ? OD-1 | NHAI | 2-2021 | 3/2024 | N.A. | 6/2025 | 586 |  | 586 | 240.33 | 87.6
April 2025 |  |  | 1180 | 6L OF KARKI ? KALIAGURA SECTION FROM KM 226.500 TO KM 249.000 OF NH-130-CD | PACKAGE ? OD-4 | NHAI | 2-2021 | 3/2024 | N.A. | 5/2025 | 593 |  | 593 | 282.15 | 93.6
April 2025 |  |  | 1181 | 6L OF HATIBENA - BADAKUMARI SECTION FROM KM 146.50 TO KM 179.00 OF NH-130-CD | PACKAGE ? OD-2 | NHAI | 2-2021 | 3/2024 | N.A. | 5/2025 | 925 |  | 925 | 460.47 | 97
April 2025 |  |  | 1182 | 6L GREENFIELD BAUNSAGUAR - BARAJA SECTION OF NH-130-CD ROAD FROM KM 293+000 TO KM 338+500 (PACKAGE ? | NHAI | N24001678 | 8-2021 | 6/2024 | N.A. | 12/2025 | 1460 | 1460 | 1460 | 947.94 | 87.92
April 2025 |  |  | 1183 | CONSTRUCTION OF ROAD FROM KM 0/0 TO 72/0 OF NH-26 SUCH AS 4 LANE FROM KM 0/0 TO 21/0 (BARGARH TO BAR | MoRTH | N24001857 | 6-2020 | 12/2023 | 8/2025 | 8/2025 | 414.24 |  | 414.24 | 307.52 | 97
April 2025 |  |  | 1184 | WIDENING AND STRENGTHENING TO 2L+PS INCLUDING LA OF KANDARPUR- BALIKUDA FROM KM 277/500 TO 318/970 OF | MoRTH | N24001858 | 3-2022 | 6/2025 | N.A. | 12/2025 | 499.79 |  | 499.79 | 280.32 | 36.83
April 2025 |  |  | 1185 | CONSTRUCTION OF BYPASS ON NH-59 FROM KM 336/350 TO 349/910 (13.56 KM) NEAR BERHAMPUR TOWN INCLUDING | MoRTH | N24001859 | 3-2021 | 3/2024 | N.A. | 8/2025 | 196.94 |  | 196.94 | 68.15 | 15
April 2025 |  |  | 1186 | CONSTRUCTION OF BYPASS TO NAYAGARH TOWN FROM KM 235.469 TO 252.482 OF NH-57 INCLUDING LAND ACQUISITI | MoRTH | N24001860 | 1-2022 | 4/2025 | N.A. | 8/2025 | 300.33 |  | 300.33 | 199.19 | 50
April 2025 |  |  | 1187 | CONSTRUCTION OF BYPASS TO KHORDHA TOWN FROM KM 294/000 TO 300/300 ON NH-57 INCLUDING LA IN THE STATE | MoRTH | N24001861 | 2-2022 | 11/2024 | 8/2025 | 8/2025 | 157.49 |  | 157.49 | 69 | 31.74
April 2025 |  |  | 1188 | CONSTRUCTION OF BYPASS ROAD TO BALANGIR TOWN FROM KM 72/400 (DESING KM 0/0) TO KM 79/800 (DESIGN KM | MoRTH | N24001862 | 2-2022 | 10/2025 | 11/2025 | 11/2025 | 238.78 |  | 238.78 | 39.26 | 28
April 2025 |  |  | 1189 | CONSTRUCTION OF 5 HL BRIDGES AT KM 379/000 (PANGAM), KM 439/400 (POTTERU), KM 444/237 | KONGURUKONDA | MoRTH | 3-2021 | 6/2024 | 10/2025 | 8/2025 | 154.05 |  | 154.05 | 47.47 | 30
April 2025 |  |  | 1190 | CONSTRUCTION OF FOUR LANE ROB AND ITS APPROACHES IN LIEU OF EXISTING LEVEL CROSSING NO. RV-71 AT KM | MoRTH | N24001864 | 11-2021 | 6/2025 | N.A. | 8/2025 | 154.49 |  | 154.49 | 59.92 | 32
April 2025 |  |  | 1191 | CONSTRUCTION OF 4 LANE ROB WITH APPROACHES IN LIEU OF LC NO. RV-172 AT KM 176.00 OF NH-201 (PRESENT | MoRTH | N24001865 | 12-2021 | 5/2025 | 8/2025 | 8/2025 | 324.09 |  | 324.09 | 103.11 | 35
April 2025 |  |  | 1192 | REHABILITATION AND UP GRADATION FROM 4 TO 8 LANING OF CHANDIKHOLE PARADIP SECTION OF NH 53 FROM KM. | NHAI | N24002078 | 12-2023 | 12/2025 | N.A. | 12/2025 | 711 |  | 711 | 111.9 | 47.8
April 2025 |  |  | 1193 | REHABILITATION AND UP GRADATION FROM 4 TO 8 LANING OF CHANDIKHOLE PARADIP SECTION OF NH 53 FROM KM | NHAI | N24002079 | 12-2023 | 12/2025 | N.A. | 12/2025 | 742.25 |  | 742.25 | 186.57 | 51.75
April 2025 |  |  | 1194 | REHABILITATION AND UP GRADATION FROM 4 TO 8 LANING OF CHANDIKHOLE PARADIP SECTION OF NH 53 FROM KM | NHAI | N24002080 | 12-2023 | 12/2025 | N.A. | 12/2025 | 762.75 |  | 762.75 | 152.76 | 51.5
April 2025 |  |  | 1195 | 3L MAJOR BRIDGE OVER RIVER BRAHMANI AT KM. 401.250 (DUBURI CHANDIKHOLE SECTION) OF NH 200 (NEW NH 5 | NHAI | N24002081 | 8-2022 | 1/2025 | N.A. | 12/2026 | 153.61 |  | 153.61 | 14.22 | 34.49
April 2025 |  |  | 1196 | WIDENING AND STRENGTHENLNG TO 2L+PS FROM KM 0.000 TO 40.000 (DHAUGAON- PODAMARI SECTION) OF NH 326 I | MoRTH | N24002135 | 3-2022 | 2/2026 | N.A. | 2/2026 | 186.52 |  | 186.52 | 45.9 | 35
April 2025 |  |  | 1197 | WIDENING AND STRENGTHENING TO 4L+PS/2L+PS FROM KM 0.000 TO 35.800 (KUAKHIA - MANGALPUR SECTION) OF N | MoRTH | N24002136 | 3-2022 | 2/2026 | N.A. | 2/2026 | 636.1 |  | 636.1 | 260.43 | 33.06
April 2025 |  |  | 1198 | REHABILITATION AND UP GRADATION FROM 4 TO 8 LANING OF CHANDIKHOLE ? PARADIP SECTION OF NH-53 (OLD NH | NHAI | N24002219 | 3-2024 | 10/2026 | N.A. | 10/2026 | 882.45 |  | 882.45 | 1.7 | 11.05
April 2025 |  | STEEL | 1199 | REBUILDING OF COKE OVEN BATTERY-2 ALONGWITH AUGMENTATION OF COKE HANDLING AND GAS HANDLING FACILITY | SAIL | N12000122 | 11-2020 | 5/2023 | 3/2025 | 3/2025 | 377.18 |  | 377.18 | 434.9
April 2025 |  | STEEL | 1200 | INSTALLATION OF 4TH SLAB CASTER ALONG WITH ITS AUXILIARIES AND A NEW LADLE FURNACE IN SMS-II AT RSP | SAIL | N12000125 | 1-2022 | 5/2025 | N.A. | 7/2025 | 970.18 |  | 970.18 | 664.38 | 89.4
April 2025 |  | DEPARTMENT OF HIGHER EDUCATION | 1201 | CONSTRUCTION OF PERMANENT CAMPUS OF INDIAN INSTITUTE OF MANAGEMENT (IIM) AMRITSAR, PUNJAB. | CPWD EDUCATION | N28000142 | 10-2019 | 5/2022 | N.A. | 7/2025 | 348.24 |  | 348.24 | 237.84 | 90
April 2025 |  | PETROLEUM | 1202 | SECOND GENERATION ETHANOL BIOREFINERY PROJECT, BATHINDA, PUNJAB | HPCL | N16000402 | 5-2020 | 2/2023 | 9/2024 | 12/2025 | 1421.46 |  | 1421.46 | 1153.95 | 95.6
April 2025 |  | PETROLEUM | 1203 | BHATINDA SANGRUR PIPELINE | HPCL | N16000440 | 11-2021 | 5/2024 | 2/2025 | 6/2025 | 367 | 397 | 397 | 329.59 | 89
April 2025 |  | PETROLEUM | 1204 | CGD PROJECT AT PATHANKOT DISTRICT | IOCL | N16000488 | 3-2022 | 3/2030 | 9/2033 | 9/2033 | 151 |  | 151 | 8.43 | 2
April 2025 |  | RAILWAYS | 1205 | MANSA-BHATINDA (PHASE-I), INCL. NEW MATERIAL MODIFICATION FOR RAMA MANDI (RAMAN) - SADA SINGHWALA VI | NR | N22000502 | 6-2009 | 8/2016 | N.A. | 8/2025 | 404 |  | 404 | 190 | 100
April 2025 |  | RAILWAYS | 1206 | 235 | NR | N22000589 | 9-2020 | 3/2025 | N.A. | 6/2025 | 235 |  | 235 | 3.88 | 98
April 2025 |  | RAILWAYS | 1207 | FEROZPUR - PATTI (25.72 KM) | NR | N22000614 | 4-2017 | 3/2027 | N.A. | 3/2027 | 299.74 |  | 781 | 0 | -
April 2025 |  | RAILWAYS | 1208 | WIDENING AND PAVED SHOULDER OF TOHANA (IN HARYANA) PUNJAB/HARYANA BORDER TO MOONAK-JAKHAL- BUDHLADA | MoRTH | N24000907 | 3-2018 | 8/2020 | N.A. | 7/2024 | 293.1 |  | 315 | 306.6 | 100
April 2025 |  |  | 1209 | JALANDHAR-HOSHIARPUR SECTION OF NH-70 [NEW NH NO. 3] FROM EXISTING KM 11.400 TO KM 49.200 | MoRTH | N24000909 | 10-2017 | 10/2019 | N.A. | 12/2025 | 1069.59 |  | 1069.59 | 739.08 | -
April 2025 |  |  | 1210 | REHABILITATION AND UP GRADATION TO 2 LANE WITH PAVED SHOULDER OF NH-703A FROM MAKHU (DESIGN CH 0 000 | MoRTH | N24000910 | 3-2018 | 11/2020 | N.A. | 6/2024 | 170.57 | 192.48 | 150 | 96.38 | 79
April 2025 |  |  | 1211 | DELHI-AMRITSAR-KATRA EXPRESSWAY FROM JUNCTION WITH PATIALA-BATHINDA ROAD (NH-7) NEAR BHAWANIGARH TO | NHAI | N24001415 | 12-2020 | 4/2024 | 7/2024 | 7/2024 | 881 |  | 881 | 882.83 | 89.33
April 2025 |  |  | 1212 | DELHI-AMRITSAR-KATRA EXPRESSWAY FROM JUNCTION WITH LUDHIANA-MALERKOTLA ROAD (SH-11) NEAR BHOGIWAL VI | NHAI | N24001416 | 12-2020 | 1/2024 | 3/2025 | 3/2025 | 989.66 |  | 989.66 | 324.77 | 31.08
April 2025 |  |  | 1213 | DELHI-AMRITSAR-KATRA EXPRESSWAY FROM JUNCTION WITH LUDHIANA-MOGA ROAD (NH-5) NEAR MULLANPUR DAKHA TO | NHAI | N24001417 | 12-2020 | 4/2024 | 9/2025 | 9/2025 | 1234.4 |  | 1234.4 | 792.35 | 57.84
April 2025 |  |  | 1214 | DELHI-AMRITSAR-KATRA EXPRESSWAY FROM CH.KM 303+900 TO KM 319+400 OF MAIN EXPRESSWAY) AND AMRITSAR CO | NHAI | N24001418 | 12-2020 | 4/2024 | 9/2025 | 9/2025 | 1094.46 |  | 1094.46 | 802.93 | 61.96
April 2025 |  |  | 1215 | DELHI-AMRITSAR-KATRA EXPRESSWAY (PHASE-I PKG-XI) FROM JUNCTION WITH JALANDHAR - KAPURTHALA ROAD (NH- | NHAI | N24001419 | 2-2021 | 4/2024 | 11/2024 | 11/2024 | 1269.96 |  | 1269.96 | 585.86 | 43.45
April 2025 |  |  | 1216 | DELHI-AMRITSAR-KATRA EXPRESSWAY (PHASE-I PKG-XII) FROM JUNCTION WITH AMRITSAR-MEHTA- SRIHARGOBINDPUR- | NHAI | N24001420 | 2-2021 | 4/2024 | 12/2025 | 12/2025 | 853.66 |  | 853.66 | 132.99 | 15.33
April 2025 |  |  | 1217 | 4/6L GREENFIELD LUDHIANA RUPNAGAR HIGHWAY FROM JUNCTION WITH NE 05 VILLAGR NEAR TO MANEWAL (LUDHIANA | NHAI | N24001630 | 7-2021 | 2/2025 | N.A. | 2/2025 | 1501.02 |  | 1501.02 | 372 | 71
April 2025 |  |  | 1218 | 6L OF IT CITY CHOWK TO KURALI CHANDIGARH ROAD | NHAI | N24001631 | 3-2021 | 10/2024 | N.A. | 10/2024 | 1525.31 |  | 1525.31 | 368 | 85
April 2025 |  |  | 1219 | CONSTRUCTION OF FOUR LANE GREENFIELD PROJECT OF DELHI-AMRITSAR-KATRA EXPRESSWAY (PHASE-I PKG-V) FROM | NHAI | N24001632 | 1-2021 | 5/2024 | 6/2025 | 8/2025 | 1741.86 | 2281.02 | 2281.02 | 1278 | 96
April 2025 |  |  | 1220 | CONSTRUCTION OF FOUR/SIX LANE GREENFIELD LUDHIANA ? RUPNAGAR NATIONAL HIGHWAY NO. NH-205K UNDER BHAR | NHAI | N24001636 | 5-2021 | 12/2024 | 10/2026 | 10/2026 | 1368.91 | 1368.91 | 1368.91 | 163.58 | 15.31
April 2025 |  |  | 1221 | DEVELOPMENT OF 6 LANE JALANDHAR BYPASS FROM KAHLWAN NATIONAL HIGHWAY 03 DESIGN KM 0.00 ENDING AT K | NHAI | N24001637 | 3-2021 | 1/2025 | N.A. | 1/2025 | 1754.84 |  | 1754.84 | 1082.62 | 34.7
April 2025 |  |  | 1222 | 4L GREENFIELD A. MALOUT BYPASS FROM CH. KM 44.500 TO CH. KM 35.500 ON NH-07 AND CH. KM 0.000 TO KM 6 | NHAI | N24001638 | 11-2021 | 7/2024 | 8/2025 | 8/2025 | 646.42 | 646.42 | 646.42 | 481.67 | 95
April 2025 |  |  | 1223 | FOUR LANING OF MOGA TO BAJAKHANA LAMBWALI SECTION OF 105B GREENFIELD ALIGNMENT FROM DESIGN CHAINAGE | NHAI | N24001639 | 5-2020 | 12/2024 | 8/2025 | 8/2025 | 864.23 | 864.23 | 864.23 | 434.88 | 61
April 2025 |  |  | 1224 | 6L AMRITSAR BATHINDA GREENFIELD SECTION FROM VILLAGE TIBA ON NE 5A TO JN. WITH MOGA JALANDHAR ROAD N | NHAI | N24001640 | 3-2021 | 11/2024 | N.A. | 11/2024 | 1229.38 |  | 1229.38 | 729.77 | 45.3
April 2025 |  |  | 1225 | DELHI AMRITSAR KATRA EXPRESSWAY PHASE I SPUR III FROM JUNCTION WITH AMRITSAR JALANDHAR ROAD NH3 NEAR | NHAI | N24001641 | 3-2021 | 10/2024 | 12/2025 | 12/2025 | 1641.75 |  | 1641.75 | 187.88 | 26.3
April 2025 |  |  | 1226 | FOUR LANING OF AMRITSAR BYPASS FROM NEW TARN TARAN ROAD TO AJNALA ROAD FROM DESIGN KM. 0.750 TO DESI | NHAI | N24001642 | 2-2021 | 8/2024 | 12/2025 | 12/2025 | 1474.77 |  | 1474.77 | 441.47 | 73.26
April 2025 |  |  | 1227 | 4L OF AMRITSAR GHOMAN TANDA UNA SECTION FROM KM 8.270 TO KM 54.000 OF NH 503A PACKAGE I | NHAI | N24001643 | 12-2020 | 6/2024 | 6/2025 | 6/2025 | 857.91 |  | 857.91 | 127.71 | 39.5
April 2025 |  |  | 1228 | AMRITSAR AIRPORT JUNCTION RAMDAS FROM KM. 100.835 TO KM. 139.813 PKG IV | NHAI | N24001644 | 12-2020 | 9/2023 | 9/2025 | 9/2025 | 524.88 | 416.58 | 416.58 | 157.14 | 73
April 2025 |  |  | 1229 | UP-GRADATION TO TWO LANE WITH PAVED SHOULDER CONFIGURATION OF NH-354 SECTION ARIFKES-FEROZEPUR- MUKTS | MoRTH | N24001960 | 3-2021 | 10/2023 | N.A. | 4/2025 | 263.19 |  | 220 | 22.48 | 42
April 2025 |  |  | 1230 | WORK OF WIDENING/UPGRADATION OF 2- LANE WITH PAVED SHOULDER OF SRI MUKTSAR SAHIB TO MALOUT ROAD FROM | MoRTH | N24001961 | 3-2022 | 10/2023 | N.A. | 4/2025 | 152.58 |  | 152.58 | 8.49 | 69
April 2025 |  |  | 1231 | 6L OF JODHPUR ROMANA (BATHINDA) - MANDI DABWALI (PUNJAB HARYANA BORDER) SECTION OF NH-54 FROM KM. 0. | NHAI | N24002075 | 12-2020 | 8/2025 | 8/2025 | 8/2025 | 757.13 | 757 | 757 | 246.51 | 97
April 2025 |  |  | 1232 | 6L AMRITSAR-BATHINDA GREENFIELD SECTION FROM JN. WITH BHAGTA BHAI KA- BHADAUR ROAD NEAR DYALPURA BHAI | NHAI | N24002076 | 3-2021 | 10/2025 | 6/2026 | 6/2026 | 2029.17 | 2029 | 2029 | 84.23 | 43
April 2025 |  |  | 1233 | 6L ACCESS CONTROLLED LUDHIANA-BATHINDA GREENFIELD HIGHWAY FROM JN. WITH AMRITSAR-BATHANDA GREENFIELD | NHAI | N24002091 | 6-2021 | 9/2025 | 3/2026 | 3/2026 | 906.51 | 906.51 | 906.51 | 221.31 | 48.4
April 2025 |  |  | 1234 | 6-LANE AMRITSAR-BATHINDA GREENFIELD SECTION OF NH- 754A FROM JUNCTION WITH MOGA JALANDHAR ROAD (NH-70 | NHAI | N24002092 | 3-2021 | 10/2025 | N.A. | 10/2025 | 1801.37 |  | 1801.37 | 1003.2 | 40.83
April 2025 |  |  | 1235 | 6L OF AMBALA-CHANDIGARH GREENFIELD SECTION FROM KM. 0.000 TO KM. 25.000 WITH 4L SPUR TO LALRU FROM K | NHAI | N24002098 | 3-2022 | 10/2025 | N.A. | 10/2025 | 1641.66 |  | 1641.66 | 154 | 45
April 2025 |  |  | 1236 | 4L OF EXISTING BEAS ? BABA BAKALA - DERA BABA NANAK SECTION FROM START OF BATALA BYPASS TILL INTERSE | NHAI | N24002100 | 10-2021 | 6/2025 | N.A. | 6/2025 | 1003.38 |  | 1003.38 | 275.45 | 68.59
April 2025 |  |  | 1237 | 4L OF BEAS-MEHTA-BATALA- DERA BABA NANAK FROM INTERSECTION WITH JALANDHAR-AMRITSAR HIGHWAY (NH-3) NEA | NHAI | N24002101 | 8-2021 | 6/2025 | 12/2025 | 12/2025 | 809.51 |  | 809.51 | 218.47 | 50.96
April 2025 |  |  | 1238 | DELHI-AMRITSAR-KATRA EXPRESSWAY (PHASE-I SPUR-I) FROM JN. WITH KAPURTHALA - SULTANPUR LODHI ROAD (NH | NHAI | N24002102 | 1-2020 | 4/2026 | N.A. | 4/2027 | 2165.23 |  | 2165.23 | 167.03 | 19.01
April 2025 |  | CIVIL AVIATION | 1239 | CONSTRUCTION OF NEW TERMINAL BUILDING AT JODHPUR AIRPORT | AAI | N04000101 | 5-2022 | 11/2024 | 10/2025 | 10/2025 | 480 |  | 480 | 217.2 | 60
April 2025 |  | CIVIL AVIATION | 1240 | UDAIPUR AIRPORT- CONSTRUCTION OF NEW INTEGRATED PASSENGER TERMINAL BUILDING | AAI | N04000104 | 6-2023 | 3/2026 | N.A. | 3/2026 | 887 |  | 887 | 300.51 | 59.14
April 2025 |  | COAL | 1241 | NLCIL 300 MW SOLAR POWER PROJECT (PART OF 510 MW CPSU SCHEME) | NLC | N06000269 | 3-2023 | 9/2024 | N.A. | 9/2025 | 1813 |  | 1813 | 579.82 | 65
April 2025 |  | COAL | 1242 | NEW MUNDRA-PANIPAT CRUDE OIL PIPELINE | IOCL | N16000435 | 12-2021 | 10/2024 | 12/2025 | 12/2025 | 9028 |  | 9028 | 6597.37 | 79.96
April 2025 |  |  | 1243 | CGD PROJECT IN TONK, SAWAI MADHOPUR, DAUSA, KARAULI | HPCL | N16000496 | 3-2022 | 3/2030 | N.A. | 3/2030 | 1751 |  | 1751 | 292.81 | 24.2
April 2025 |  |  | 1244 | SETTING UP OF PETROCHEMICAL EVACUATION MARKETING TERMINAL (PEMT) AT BARMER | HPCL | N16000512 | 12-2023 | 12/2026 | N.A. | 12/2026 | 461.05 |  | 461.05 | 77.86 | 40.6
April 2025 |  |  | 1245 | RAJASTHAN REFINERY PROJECT | HPCLRRL(JV) | N16000513 | 10-2017 | 10/2022 | 3/2025 | 12/2025 | 43129 | 72937 | 72937 | 56949.7 | 86.4
April 2025 |  |  | 1246 | CGD PROJECTS AT FAZILKA (EXCEPT AREA ALREADY AUTHORIZED) GANGANAGAR AND HANUMANGARH DISTRICTS | BPCL | N16000520 | 12-2022 | 6/2030 | N.A. | 6/2030 | 3207 |  | 3207 | 298.8 | 19.8
April 2025 |  |  | 1247 | SAMBHU KI BHURJ-II SOLAR 300MW | NTPC | N18000286 | 3-2020 | 9/2021 | N.A. | 3/2025 | 1782 | 12 | 1782 | 1369.88 | 95
April 2025 |  |  | 1248 | BHENSARA 320 MW | NTPC | N18000293 | 1-2021 | 7/2022 | N.A. | 3/2025 | 1221.73 | 1521 | 1221.73 | 1133.99 | -
April 2025 |  |  | 1249 | NOKH PLOT-1 SOLAR PV PROJECT 245MW | NTPC | N18000320 | 3-2022 | 8/2023 | N.A. | 6/2025 | 1352.71 |  | 1352.71 | 1057.36 | 45
April 2025 |  |  | 1250 | NOKH PLOT-2 SOLAR PV PROJECT 245MW | NTPC | N18000321 | 3-2022 | 8/2023 | N.A. | 3/2025 | 1409.52 |  | 1409.52 | 1403.89 | 95
April 2025 |  |  | 1251 | NOKH PLOT-3 SOLAR PV PROJECT 245MW | NTPC | N18000322 | 3-2022 | 8/2023 | N.A. | 5/2025 | 1426.94 |  | 1426.94 | 1170.29 | 80
April 2025 |  |  | 1252 | BHADLA-II 500MW SOLAR PV PROJECT | NTPC | N18000347 | 6-2022 | 3/2024 | N.A. | 9/2025 | 2598.92 |  | 2598.92 | 1705.7 | 12
April 2025 |  |  | 1253 | TRANSMISSION SYSTEM SCHEME FOR EVACUATION OF POWER FROM REZ RAJASTHAN (8.1 GW) UNDER PHASE-II PART | PGCIL | N18000356 | 3-2023 | 9/2024 | N.A. | 9/2025 | 1433.28 |  | 1433.28 | 956.47 | 90.7
April 2025 |  |  | 1254 | 300 MW SOLAR POWER PROJECT UNDER CPSU SCHEME | NHPC | N18000368 | 5-2022 | 11/2023 | N.A. | 8/2025 | 1677.12 |  | 1677.12 | 1036.45 | 85
April 2025 |  |  | 1255 | TS FOR EVACUATION OF POWER FROM REZ IN RAJASTHAN (20GW) UNDER PHASE-III, PART E1 | PGCIL | N18000373 | 8-2023 | 2/2025 | N.A. | 9/2025 | 688.74 |  | 688.74 | 411 | 91
April 2025 |  |  | 1256 | TS FOR EVACUATION POWER FROM REZ IN RAJASTHAN (20GW) UNDER PHASE-III PART H | PGCIL | N18000374 | 10-2023 | 4/2025 | N.A. | 8/2025 | 2211 |  | 2211 | 1227.63 | 57
April 2025 |  |  | 1257 | TS FOR EVACUATION POWER FROM REZ IN RAJASTHAN (20GW) UNDER PHASE-III PART C1 | PGCIL | N18000375 | 10-2023 | 4/2025 | 10/2025 | 10/2025 | 1796 |  | 1796 | 929.48 | 67
April 2025 |  |  | 1258 | TS FOR EVACUATION POWER FROM REZ IN RAJASTHAN (20GW) UNDER PHASE-III PART B1 | PGCIL | N18000376 | 9-2023 | 4/2025 | N.A. | 8/2025 | 2191 |  | 2191 | 1103.26 | 64
April 2025 |  |  | 1259 | TS FOR EVACUATION POWER FROM REZ IN RAJASTHAN (20GW) UNDER PHASE-III PART J | PGCIL | N18000378 | 12-2022 | 3/2025 | 4/2026 | 4/2026 | 331 |  | 331 | 8.66 | 26
April 2025 |  |  | 1260 | TS FOR EVACUATION POWER FROM REZ IN RAJASTHAN (20GW) UNDER PHASE-III PART E2 | PGCIL | N18000379 | 11-2023 | 6/2025 | N.A. | 9/2025 | 428 |  | 428 | 0 | 35
April 2025 |  |  | 1261 | TS FOR EVACUATION OF POWER FROM RAJASTHAN REZ PH-IV (PART-1) [BIKANER COMPLEX] PART A [BIKANER III N | PGCIL | N18000386 | 12-2023 | 12/2025 | N.A. | 12/2025 | 2998 |  | 2998 | 729.98 | 42.2
April 2025 |  |  | 1262 | TS FOR EVACUATION OF POWER FROM RAJASTHAN REZ PH-IV (PART-1) [BIKANER COMPLEX] PART D [NEEMRANA II B | PGCIL | N18000387 | 12-2023 | 12/2025 | N.A. | 12/2025 | 2056 |  | 2056 | 847 | 47
April 2025 |  |  | 1263 | TS FOR EVACUATION OF POWER FROM REZ IN RAJASTHAN (20GW) UNDER PH- III PART D [SIKAR KHETRI TRANSMISSI | PGCIL | N18000389 | 2-2024 | 8/2025 | N.A. | 8/2025 | 2000 |  | 2000 | 823 | 50.9
April 2025 |  |  | 1264 | TS FOR EVACUATION POWER FROM RAJASTHAN REZ PH-IV (PART-2:5.5GW) PART-B | JAISALMER/BARMER COMPLEX | PGCIL | 8-2024 | 8/2026 | N.A. | 8/2026 | 3279 |  | 3279 | 134 | 10.9
April 2025 |  |  | 1265 | TS FOR EVACUATION POWER FROM RAJASTHAN REZ PH-IV (PART-2:5.5GW) (JAISALMER/BARMER COMPLEX) PART-C | PGCIL | N18000393 | 8-2024 | 8/2026 | N.A. | 8/2026 | 2227 |  | 2227 | 123 | 13.5
April 2025 |  |  | 1266 | TS FOR EVACUATION POWER FROM RAJASTHAN REZ PH-IV (PART-2:5.5GW) (JAISALMER/BARMER COMPLEX) PART-E | PGCIL | N18000394 | 8-2024 | 8/2026 | N.A. | 8/2026 | 3251 |  | 3251 | 241 | 11.6
April 2025 |  |  | 1267 | ADDITIONAL TRANSMISSION SYSTEM FOR EVACUATION OF POWER FROM BHADLA-III PS AS PART OF RAJASTHAN REZ P | PGCIL | N18000396 | 8-2024 | 2/2026 | N.A. | 2/2026 | 369 |  | 369 | 0 | 1
April 2025 |  |  | 1268 | TRANSMISSION SYSTEM STRENGTHENING FOR INTERCONNECTIONS OF BHADLA-III AND BIKANER III COMPLEX [SPV NA | PGCIL | N18000397 | 8-2024 | 8/2026 | N.A. | 8/2026 | 1382 |  | 1382 | 0 | 1
April 2025 |  |  | 1269 | TRANSMISSION SYSTEM FOR EVACUATION OF POWER FROM RAJASTHAN REZ PH -IV [PART-2 5.5 GW] [JAISALMER/BAR | PGCIL | N18000401 | 11-2024 | 11/2026 | N.A. | 11/2026 | 2735 |  | 2735 | 0 | -
April 2025 |  |  | 1270 | TRANSMISSION SYSTEM FOR EVACUATION OF POWER FROM RAJASTHAN REZ PH-IV [PART-3 (6GW)] [BIKANER COMPLEX | PGCIL | N18000403 | 11-2024 | 11/2026 | N.A. | 11/2026 | 5969 |  | 5969 | 0 | -
April 2025 |  |  | 1271 | TRANSMISSION SYSTEM FOR EVACUATION OF POWER FROM RAJASTHAN REZ PH-IV [PART-3 (6 GW)] [BIKANER COMPLE | PGCIL | N18000404 | 11-2024 | 11/2026 | N.A. | 11/2026 | 5357 |  | 5357 | 0 | -
April 2025 |  |  | 1272 | RAJASTHAN REZ PH-V (PART-1: 4 GW) [SIROHI/NAGAUR] COMPLEX | PGCIL | N18000414 | 3-2025 | 3/2027 | N.A. | 3/2027 | 5028 |  | 5028 | 0 | -
April 2025 |  |  | 1273 | AUGMENTATION AT FATEHGARH-II PS, FATEHGARH- IV PS (SECTION-II) AND BARMER- I | PGCIL | N18000415 | 3-2025 | 12/2026 | N.A. | 12/2026 | 404 |  | 404 | 0 | -
April 2025 |  | RAILWAYS | 1274 | AGRA FORT-BANDIKUI | NCR | N22000553 | 6-2022 | 6/2027 | 5/2026 | 5/2026 | 1389.81 |  | 987.83 | 42.46 | 12
April 2025 |  | RAILWAYS | 1275 | GUDHA THATHANA MITHRI TEST TRACK FOR RDSO | NWR | N22000593 | 4-2019 | 3/2025 | N.A. | 6/2025 | 528.48 |  | 500.85 | 351.06 | 80
April 2025 |  | RAILWAYS | 1276 | DEDICATED TEST TRACK FOR RDSO (PHASE II) | NWR | N22000594 | 11-2021 | 11/2026 | N.A. | 12/2025 | 466.42 |  | 466.22 | 718.22 | 80
April 2025 |  | RAILWAYS | 1277 | DOUBLING BETWEEN CHURU- RATANGARH (42.81 KM) | NWR | N22000605 | 2-2023 | 2/2028 | N.A. | 6/2025 | 422.6 |  | 422.6 | 189.74 | 72
April 2025 |  | RAILWAYS | 1278 | SAWAIMADHOPUR - BYPASS LINE (6.98 KM) (UMBRELLA WORK PB#57/2019-20/NR) | NWR | N22000607 | 12-2022 | 6/2026 | N.A. | 1/2026 | 304 | 239.54 | 239.54 | 117.12 | 25
April 2025 |  | RAILWAYS | 1279 | GC OF NATHDWARA - DEVGARH MADARIYA (82.5KM) | NWR | N22000608 | 1-2023 | 6/2028 | N.A. | 12/2026 | 968.92 |  | 968.92 | 377.63 | 38
April 2025 |  |  | 1280 | CONSTRUCTION/ UP-GRATION OF FOUR/TWO LANE WITH PAVED SHOULDER OF NH68 FROM TANOT-RAMGARH BHADASAR-JA | NHAI | N24000795 | 2-2018 | 4/2021 | 5/2025 | 5/2025 | 741.86 | 649 | 649 | 672.53 | 99.21
April 2025 |  |  | 1281 | 4L+PS OF NH -58 FROM BEAWAR-GOMTI (OLD CH KM 58.245 TO KM. 108.600) PKG-I. | MoRTH | N24001411 | 12-2020 | 10/2023 | N.A. | 12/2025 | 379.23 |  | 379.23 | 263.62 | 96.1
April 2025 |  |  | 1282 | 2L+PS FOR WORK OF NH-325 (BALOTRA TO SANDERAO VIA JALORE) BY CONSTRUCTION OF BYPASSES:(1) ASOTRA- BR | MoRTH | N24001527 | 12-2021 | 5/2024 | 12/2025 | 12/2025 | 411.4 |  | 411.4 | 213.61 | 69
April 2025 |  |  | 1283 | WIDENING OF PACHPADRA- BAGUNDI SECTION TO 4 LANE FROM KM 73/60 TO 95/70 OF NH- 25 ON EPC MODE IN THE | MoRTH | N24001528 | 1-2022 | 12/2024 | 8/2025 | 8/2025 | 194.88 |  | 194.88 | 105.69 | 75.46
April 2025 |  |  | 1284 | 44 LANE DIVIDED CARRIAGEWAY OF BARMER BYPASS OF NH-15 (NEW NH-68) IN THE STATE OF RAJASTHAN ON EPC M | MoRTH | N24001529 | 12-2021 | 8/2024 | 5/2025 | 5/2025 | 451.66 |  | 451.66 | 401.78 | 99
April 2025 |  |  | 1285 | UPGRADATION TO TWO LANE PAVED SHOULDER OF KOTHUN- LALSOT-KAROLI-DHOLPUR ROAD NH-23 (OLD NH-11B) IN TH | MoRTH | N24001530 | 12-2021 | 9/2024 | N.A. | 8/2025 | 150.11 |  | 150.11 | 74.83 | 83
April 2025 |  |  | 1286 | 4L GREENFIELD SPUR FROM DELHI-VADODARA GREENFIELD EXPRESSWAY NEAR BANDIKUI TO JAIPUR | NHAI | N24001557 | 3-2022 | 11/2024 | 5/2025 | 5/2025 | 1636.15 |  | 1636.15 | 791.63 | 91.22
April 2025 |  |  | 1287 | 4L OF KARWAR (KM. 281.980 OF NH-62 NAGAUR ROAD) TO DANGIYAVAS OF JODHPUR RING ROAD (PKG-II) | NHAI | N24001558 | 11-2021 | 8/2024 | 5/2025 | 5/2025 | 736.75 |  | 736.75 | 253.43 | 93.25
April 2025 |  |  | 1288 | 2L PS SRIGANGANAGAR TO RAISINGHNAGAR (DESIGN CHAINAGE -0.500 KM TO DESIGN CHAINAGE 101.000 KM) (PACK | NHAI | N24001559 | 9-2021 | 6/2024 | 4/2025 | 4/2025 | 672.35 |  | 672.35 | 392.56 | 99.5
April 2025 |  |  | 1289 | DEOGARH (NEAR DHANDHANIYA)- RAJASTHAN/GUJARAT BORDER | PHASE-I) (AJ/DRGB-PACKAGE-6 | NHAI | 10-2019 | 8/2023 | 5/2025 | 5/2025 | 846.59 |  | 846.59 | 167.25 | 98
April 2025 |  |  | 1290 | DEOGARH (NEAR DHANDHANIYA)- RAJASTHAN/GUJARAT BORDER | PHASE-I) (AJ/DRGB-PACKAGE-7 | NHAI | 10-2019 | 7/2023 | 5/2025 | 5/2025 | 662.08 |  | 662.08 | 124.06 | 96.5
April 2025 |  |  | 1291 | DELHI-VADODARA GREENFIELD ALIGNMENT (NH-148N) (PKG-10) (CH. 292.950 TO CH. 319.400) [END OF INTERCHA | NHAI | N24001567 | 11-2019 | 10/2022 | 6/2025 | 6/2025 | 1272.97 |  | 1272.97 | 628.93 | 85.5
April 2025 |  |  | 1292 | DELHI-VADODARA GREENFIELD ALIGNMENT (NH-148N) (PKG-14) (CH. 388.420 TO CH. 419.000) [JUNCTION WITH N | NHAI | N24001568 | 11-2019 | 5/2023 | 4/2025 | 4/2025 | 1119.35 |  | 1119.35 | 1447.44 | 99.8
April 2025 |  |  | 1293 | DELHI-VADODARA GREENFIELD ALIGNMENT (NH-148N) (PKG-09) (CH. 247.310 TO CH. 292.950) [JUNCTION WITH M | NHAI | N24001573 | 11-2019 | 12/2022 | 4/2025 | 4/2025 | 1658.06 |  | 1658.06 | 180.53 | 99.9
April 2025 |  |  | 1294 | DELHI-VADODARA GREENFIELD ALIGNMENT (NH-148N) (PKG-15) (CH. 419.000 TO CH.427.300) [JUNCTION WITH NH | NHAI | N24001612 | 7-2020 | 1/2024 | 12/2025 | 12/2025 | 1788.69 |  | 1788.69 | 960.26 | 73.93
April 2025 |  |  | 1295 | CONSTRUCTION OF TWO LANE WITH PAVED SHOULDER FOR FATEHPUR BYPASS, MANDAWA BYPASS AND JHUNJHUNU BYPAS | MoRTH | N24001866 | 3-2022 | 8/2024 | N.A. | 6/2025 | 186.29 |  | 186.29 | 142.69 | 78
April 2025 |  |  | 1296 | UPGRADATION OF TWO LANE PAVED SHOULDER FROM SHAHPURA TO THANAGAZI OF NH-248A ON EPC MODE IN THE STAT | MoRTH | N24001867 | 3-2022 | 7/2024 | N.A. | 6/2025 | 174.34 |  | 174.34 | 111.08 | 88
April 2025 |  |  | 1297 | Sagwara Bypass and Garhi- Partapur Bypass of NH-927A in the State of Rajasthan. | MoRTH | N24001868 | 3-2022 | 8/2025 | N.A. | 6/2025 | 187.65 |  | 187.65 | 114.57 | 83
April 2025 |  |  | 1298 | UPGRADATION AND REHABILITATION TO TWO LANE WITH PAVED SHOULDER OF GHAGARIYA- MUNABAO SECTION FROM KM | MoRTH | N24001869 | 12-2022 | 8/2025 | N.A. | 8/2025 | 235.15 |  | 235.15 | 152.69 | 99
April 2025 |  |  | 1299 | UP-GRADATION TO 2 LANE WITH PAVED SHOULDER FROM CHARBHUJA AT DESIGN KM 0.00 (EXISTING KM 150.00) TO | MoRTH | N24001927 | 2-2022 | 9/2025 | N.A. | 9/2025 | 838.43 |  | 838.43 | 405.87 | 95
April 2025 |  |  | 1300 | CONSTRUCTION OF 2 LANE WITH PAVED SHOULDER NORTHERN BYPASS PHASE-II OF KOTA CITY FROM DESIGN CHAINAG | MoRTH | N24001928 | 3-2022 | 4/2025 | N.A. | 12/2025 | 317.74 |  | 317.74 | 136.23 | 12.5
April 2025 |  |  | 1301 | ADDITIONAL STRUCTURES ON 6LGURGAON-JAIPUR SECTION OF NH-48 BETWEEN KM 42.700 TO KM 273.00 | NHAI | N24002058 | 8-2022 | 6/2024 | 6/2025 | 6/2025 | 409.64 |  | 409.64 | 238.22 | 77.1
April 2025 |  |  | 1302 | UPGRADATION TO 2 LANE WITH PAVED SHOULDER OF HANUMANGARH TO KENCHIYAN OF NH 54 ON EPC MODE IN THE ST | MoRTH | N24002167 | 3-2024 | 10/2026 | N.A. | 10/2026 | 334.64 |  | 334.64 | 123 | 40
April 2025 |  |  | 1303 | UPGRADATION TO 2 LANE WITH PAVED SHOULDER FROM NEECHLI ODEN (NATHDWARA) AT DESIGN KM 88.800 TO BHATE | MoRTH | N24002168 | 3-2023 | 10/2026 | N.A. | 10/2026 | 606.61 |  | 606.61 | 116 | 15
April 2025 |  | CIVIL AVIATION | 1304 | PAKYONG AIRPORT- WIDENING OF BASIC STRIP AT WESTERN SIDE OF RUNWAY CHAINAGE 80M TO 920M I/C SLOPE ST | AAI | N04000110 | 11-2023 | 6/2026 | N.A. | 6/2026 | 323.26 |  | 323.26 | 24.98 | 9.9
April 2025 |  | DEPARTMENT OF HIGHER EDUCATION | 1305 | CONSTRUCTION OF SIKKIM UNIVERSITY CAMPUS PHASE-I, PACKAGE -II AT YANGANG SOUTH SIKKIM | Sikkim Universi | N44000002 | 8-2020 | 1/2025 | N.A. | 1/2025 | 314.06 |  | 303.55 | 157.24 | 76
April 2025 |  | POWER | 1306 | TEESTA VI HE PROJECT | NHPC | N18000325 | 3-2019 | 3/2024 | N.A. | 12/2027 | 5748.04 |  | 5748.04 | 4249.86 | 67.08
April 2025 |  | POWER | 1307 | RANGIT IV HE PROJECT | NHPC | N18000326 | 3-2021 | 5/2024 | N.A. | 12/2025 | 938.29 |  | 1828.11 | 1439.46 | 87.07
April 2025 |  | RAILWAYS | 1308 | SEVOK RANGPO, NEFR | NFR | N22000102 | 4-2008 | 5/2015 | 12/2027 | 12/2027 | 7876.92 | 11963.43 | 11963.43 | 8569.25 | 76.5
April 2025 |  |  | 1309 | CONSTRUCTION OF 2-LANE WITH PAVED SHOULDER INCLUDING GEOMETRIC IMPROVEMENT FROM KM 0.000 TO KM 16.00 | NHIDCL | N24000767 | 3-2017 | 4/2022 | 5/2022 | 12/2023 | 375.8 |  | 375.8 | 288.56 | 96.55
April 2025 |  |  | 1310 | CONSTRUCTION OF 2-LANE WITH PAVED SHOULDER INCLUDING GEOMETRIC IMPROVEMENT FROM KM 16.000 TO KM 32.5 | NHIDCL | N24000768 | 11-2017 | 10/2020 | 8/2023 | 4/2024 | 290.05 |  | 290.05 | 218.36 | 100
April 2025 |  |  | 1311 | CONSTUCTION/UPGRADATION OF EXISTING HIGHWAY TO 2 LANE WITH PAVED SHOULDER FROM KM 0.00 TO KM 13.00 N | NHIDCL | N24001251 | 3-2019 | 4/2022 | N.A. | 6/2025 | 402.94 |  | 402.94 | 247.12 | 76.54
April 2025 |  |  | 1312 | CONSTUCTION/UPGRADATION OF EXISTING HIGHWAY TO 2 LANE WITH PAVED SHOULDER FROM KM 13.00 TO KM 25.600 | NHIDCL | N24001252 | 8-2020 | 4/2023 | 11/2024 | 7/2025 | 295.97 |  | 295.97 | 248.39 | 95.22
April 2025 |  |  | 1313 | CONSTUCTION/UPGRADATION OF EXISTING HIGHWAY TO 2 LANE WITH PAVED SHOULDER FROM KM 26.10 TO KM 40.00 | NHIDCL | N24001254 | 3-2020 | 6/2022 | N.A. | 1/2024 | 242.97 |  | 244.45 | 246.91 | 100
April 2025 |  |  | 1314 | CONSTRUCTION AND UPGRADATION OFEXISTINGROAD TO 2-LANE WITH PAVED SHOULDER INCLUDING GEOMETRIC IMPROV | NHIDCL | N24001261 | 8-2020 | 4/2023 | N.A. | 4/2025 | 311 |  | 273.78 | 257.86 | 94.94
April 2025 |  |  | 1315 | CONSTRUCTION AND UPGRADATION OFEXISTINGROAD TO 2-LANE WITH PAVED SHOULDER INCLUDING GEOMETRIC IMPROV | NHIDCL | N24001262 | 7-2020 | 4/2023 | 8/2024 | 4/2025 | 345.38 | 395.59 | 395.59 | 362.61 | 90.82
April 2025 |  |  | 1316 | CONSTRUCTION OF 2-LANE ROAD WITH PAVED SHOULDER (GREENFIELD ALIGNMENT) OF EXISTING STRETCH BETWEEN L | NHIDCL | N24001322 | 9-2020 | 5/2022 | 10/2023 | 12/2025 | 183.31 | 439.56 | 439.56 | 355.31 | 51.85
April 2025 |  |  | 1317 | CONSTRUCTION OF 2-LANE SPECIFICATION ROAD WITH PAVED SHOULDER AS REALIGNMENT (GREENFIELD ALIGNMENT) | NHIDCL | N24001325 | 9-2020 | 5/2023 | 8/2024 | 12/2025 | 262.84 | 414.2 | 414.2 | 221.86 | 47.56
April 2025 |  |  | 1318 | REHABILITATION AND UPGRADATION OF EXISTING ROAD TO 2-LANE WITH PAVED SHOULDER INCLUDING GEOMETRIC IM | NHIDCL | N24001327 | 8-2020 | 5/2022 | 10/2023 | 12/2025 | 292.8 |  | 292.8 | 202.92 | 60.8
April 2025 |  |  | 1319 | CONSTRUCTION AND UPGRADATION OF EXISTING ROAD TO 2-LANE WITH PAVED SHOULDER FROM KM27.200 (END OF RO | NHIDCL | N24001336 | 8-2020 | 4/2023 | 10/2024 | 12/2025 | 230.45 | 244.91 | 244.91 | 206.95 | 82.32
April 2025 |  |  | 1320 | CONSTRUCTION AND UPGRADATION OF EXISTING ROAD TO 2-LANE WITH PAVED SHOULDER FROM NEW ROLEP BRIDGE AT | NHIDCL | N24001337 | 10-2020 | 11/2023 | 7/2025 | 3/2026 | 493.42 | 478.79 | 478.79 | 302.83 | 55.21
April 2025 |  |  | 1321 | CONSTRUCTION OF 2-LANE WITH PAVED SHOULDER OF NEW GREEN FIELD ALIGNMENT FROM CHOCHENPHERI AT KM 52.0 | NHIDCL | N24001338 | 10-2020 | 12/2023 | 6/2025 | 12/2026 | 816.79 | 786.6 | 786.6 | 326.82 | 50.6
April 2025 |  |  | 1322 | RISHI BORDER- ROLEP- MENLA PKG- 2A | NHIDCL | N24001361 | 1-2021 | 9/2023 | 4/2025 | 12/2025 | 332.2 | 348.92 | 348.92 | 149.38 | 41.04
April 2025 |  |  | 1323 | RISHI BORDER- ROLEP- MENLA PKG- 3B | NHIDCL | N24001362 | 12-2020 | 2/2024 | 4/2025 | 12/2025 | 410.6 | 379.3 | 379.3 | 234.27 | 73.22
April 2025 |  |  | 1324 | CONSTRUCTION OF 2-LANE WITH PAVED SHOULDER GANGTOK BYPASS ROAD FROM RANIPOOL TO BURTUK | L=23.316KM | MoRTH | 10-2021 | 5/2024 | 1/2026 | 1/2026 | 385.15 |  | 385.15 | 170.32 | 81.11
April 2025 |  | CIVIL AVIATION | 1325 | MODERNIZATION OF CHENNAI AIRPORT PHASE II, CHENNAI | AAI | N04000074 | 6-2018 | 2/2022 | 6/2026 | 6/2026 | 2467 |  | 2467 | 1586.75 | 70
April 2025 |  | CIVIL AVIATION | 1326 | DEVELOPMENT OF TUTICORIN AIRPORT | AAI | N04000090 | 6-2019 | 3/2022 | 4/2025 | 4/2025 | 380.87 | 451.74 | 451.74 | 358.88 | 100
April 2025 |  | COAL | 1327 | JAWAHAR KHANI OPENCAST (JK OC) MINE | SCCL | N06000259 | 12-2021 | 3/2025 | N.A. | 3/2026 | 297.88 |  | 297.88 | 46.37 | 20
April 2025 |  | COAL | 1328 | 50 MW SOLAR POWER PROJECT -NEYVELI MINED OUT AREA | NLC | N06000279 | 5-2023 | 6/2025 | N.A. | 6/2025 | 218.03 |  | 218.03 | 137.84 | 37
April 2025 |  | FINANCE | 1329 | CONSTRUCTION OF 726 Nos RESIDENTIAL QUARTERS CHENNAI | CPWD FOR FINANC | N28000109 | 11-2017 | 11/2021 | N.A. | 11/2022 | 348.77 |  | 348.77 | 223.39 | 100
April 2025 |  | MINES | 1330 | 25.5 MW WIND POWER PROJECT AT KAYATHAR IN TAMILNADU | NALCO | N10000014 | 9-2017 | 6/2019 | 3/2024 | 12/2024 | 166.62 | 163.17 | 163.17 | 135.63 | 65
April 2025 |  | PETROLEUM | 1331 | IRUGUR-DEVANGONTHI POL PIPELINE | BPCL | N16000234 | 11-2012 | 2/2017 | 10/2025 | 10/2025 | 678 | 1732 | 1732 | 600.83 | 56.7
April 2025 |  | PETROLEUM | 1332 | CBR 9 MMTPA PROJECT | CPCL | N16000434 | 1-2021 | 6/2025 | N.A. | 6/2025 | 31580 | 31580 | 36354 | 1321.7 | 10.2
April 2025 |  | PETROLEUM | 1333 | GRASS ROOT POL TERMINAL AT VALLUR, CHENNAI | IOCL | N16000438 | 1-2022 | 7/2024 | 6/2025 | 6/2025 | 827 | 887.71 | 887.71 | 568.48 | 84.79
April 2025 |  | PETROLEUM | 1334 | LAYING OF POL PIPELINES IN COMMON CORRIDOR FOR PROPOSED GRASS ROOT TERMINAL AT VALLUR | CHENNAI | IOCL | 1-2022 | 7/2024 | 5/2026 | 5/2026 | 829 |  | 829 | 245.35 | 58.7
April 2025 |  | PETROLEUM | 1335 | CGD PROJECT AT DHARMAPURI AND KRISHNAGIRI DISTRICTS | IOCL | N16000486 | 3-2022 | 3/2030 | N.A. | 12/2030 | 501 |  | 501 | 101.45 | 5.3
April 2025 |  | PETROLEUM | 1336 | CGD PROJECTS AT THE NILGIRIS AND ERODE DISTRICTS | BPCL | N16000521 | 12-2022 | 3/2030 | N.A. | 3/2030 | 3685 |  | 3685 | 193.42 | 10.4
April 2025 |  | POWER | 1337 | TRANSMISSION SYSTEM UNDER ISTS FOR EVACUATION OF POWER FROM KUDANKULAM UNIT - 3 & 4 (2X1000 MW) | PGCIL | N18000408 | 1-2025 | 7/2028 | N.A. | 7/2028 | 548 |  | 548 | 0 | -
April 2025 |  | POWER | 1338 | EXTENSION OF MRTS FROM VELACHERY TO STN. THOMAS, MTP | MRTP | N22000028 | 4-2006 | 7/2024 | 5/2025 | 5/2025 | 734.01 | 734.01 | 981.83 | 632.33 | 98
April 2025 |  |  | 1339 | TIDIVANAM-NAGARI (NL) | SR | N22000085 | 9-2006 | 9/2016 | 3/2028 | 3/2028 | 3631.34 | 3631.34 | 3631.34 | 854.85 | 14
April 2025 |  |  | 1340 | CHENNAI BEACH-CHENNAI EGMORE (4.3 KM) (UMBRELLA WORK PB#57/2019-20/NR) | SR | N22000568 | 3-2022 | 3/2026 | 2/2025 | 3/2025 | 359.6 | 274.2 | 274.2 | 264.96 | 95
April 2025 |  |  | 1341 | MORAPPUR-DHARMAPURI | SR | N22000618 | 2-2019 | 3/2028 | 3/2027 | 3/2027 | 358.95 |  | 358.95 | 39.07 | 1
April 2025 |  |  | 1342 | KARAIKAL PERALAM(23KM)-NEW LINE PROJECT | SR | N22000625 | 1-2019 | 3/2026 | 3/2025 | 6/2025 | 304.22 |  | 373.42 | 298.21 | 80
April 2025 |  |  | 1343 | NAGAPATTINAM THIRUTURAIPUNDI (38KM)- NEW LINE PROJECT | SR | N22000626 | 7-2008 | 3/2026 | 3/2027 | 3/2027 | 677.12 |  | 788.05 | 142.44 | 19
April 2025 |  |  | 1344 | FOUR LANNING OF CHOLOPURAM-THANJAVUR | NHAI | N24000697 | 8-2017 | 9/2020 | N.A. | 5/2025 | 1176.37 |  | 1176.37 | 1325.06 | 99.5
April 2025 |  |  | 1345 | 4-LANNING OF STHIYATHOPU- CHOLOPURAM | NHAI | N24000708 | 9-2017 | 8/2020 | 4/2025 | 4/2025 | 1227.87 |  | 1227.87 | 1406.21 | 96.1
April 2025 |  |  | 1346 | FOUR LANINIG OF CHETTIKULAM TO NATHAM SECTION OF NH-785 FROM CHETTIKULUM (KM 7.300) TO NATHAM (KM. 3 | NHAI | N24000826 | 3-2018 | 10/2022 | 5/2025 | 5/2025 | 505.35 |  | 837.69 | 376.61 | 99.75
April 2025 |  |  | 1347 | FOUR LANING OF VILUPPURAM TO PUDHUCHERRY (DESIGN CH. KM. 00/000 TO KM. 29/000) SECTION OF NH-45A ON | NHAI | N24001428 | 3-2018 | 11/2021 | 12/2024 | 12/2024 | 998.7 | 1358.32 | 1358.32 | 975.68 | 98.32
April 2025 |  |  | 1348 | FOUR LANING OF PUDUCHERRY (KM.29/000) TO POONDIYANKUPPAM (KM.67/000) SECTION OF NH-45A ON HAM UNDER | NHAI | N24001429 | 3-2018 | 11/2021 | 12/2024 | 12/2024 | 1294.47 | 1588.4 | 1588.4 | 865.37 | 98.68
April 2025 |  |  | 1349 | FOUR LANING OF POONDIYANKUPPAM (KM.67/000) TO SATTANATHAPOURAM (KM.123/800) SECTION OF NH- 45A ON HAM | NHAI | N24001430 | 3-2018 | 1/2022 | 12/2024 | 12/2024 | 2120.4 | 2565.63 | 2565.63 | 1588.17 | 99.8
April 2025 |  |  | 1350 | FOUR LANING OF SATTANATHAPURAM (KM.123/800) TO NAGAPATTINAM (KM.179/555) SECTION OF NH- 45A ON HAM UN | NHAI | N24001431 | 3-2018 | 10/2020 | 8/2025 | 8/2025 | 1872.68 | 2661.51 | 2756.09 | 1299.72 | 61.4
April 2025 |  |  | 1351 | CONSTRUCTION OF 4 LANE WITH PAVED SHOULDERS THIRUVAYARU BYPASS IN BETWEEN EXISTING KM.55/926 TO 62/6 | MoRTH | N24001455 | 2-2022 | 8/2022 | N.A. | 3/2025 | 191.33 | 207.97 | 207.97 | 100.42 | 100
April 2025 |  |  | 1352 | BALANCE WORK 2-LANE WITH PAVED SHOULDERS OF NAGAPATTINAM - THANJAVUR SECTION OF NH-67 (NEW NH-83) | NHAI | N24001600 | 10-2020 | 5/2023 | 5/2025 | 5/2025 | 434.12 |  | 434.12 | 268.92 | 100
April 2025 |  |  | 1353 | 4-LANING OF KAMALAPURAM - ODDANCHATRAM SECTION OF NH-209 | NHAI | N24001601 | 1-2019 | 1/2023 | 6/2025 | 6/2025 | 1051.69 |  | 1051.69 | 587.09 | 81.54
April 2025 |  |  | 1354 | 4-LANING OF MADATHUKULAM - POLLACHI SECTION OF NH-209 | NEW NH-83 | NHAI | 1-2019 | 12/2022 | 5/2025 | 5/2025 | 1409.38 |  | 1409.38 | 658.19 | 90.91
April 2025 |  |  | 1355 | 4-LANING OF ODDANCHATRAM - MADATHUKULAM SECTION OF NH-209 (NEW NH-83) | NHAI | N24001603 | 1-2019 | 10/2022 | 5/2025 | 5/2025 | 1518.53 |  | 1607.54 | 915.4 | 100
April 2025 |  |  | 1356 | 4-LANING OF MELUR - PILLAYARPATTI - KARAIKUDI SECTION OF NH-338, NH-36, NH- 383 | NHAI | N24001605 | 6-2018 | 3/2022 | N.A. | 6/2025 | 1103.86 |  | 1103.86 | 568.15 | 82
April 2025 |  |  | 1357 | 4-LANING OF VADIPPATTI - THAMARAIPATTI SECTION OF NH-744A (MADURAI RING ROAD) | NHAI | N24001606 | 12-2018 | 3/2022 | 8/2025 | 8/2025 | 854.94 |  | 854.94 | 400.13 | 74.72
April 2025 |  |  | 1358 | BALANCE WORKS OF FOUR LANE FROM KM 43+950 (THIRUVALLUR BYPASS) TO KM 61+470 (VEPPAMPATTU BYPASS) PAS | NHAI | N24001692 | 1-2022 | 9/2024 | 2/2025 | 6/2025 | 467.99 |  | 468 | 24.19 | 78.12
April 2025 |  |  | 1359 | FOUR LANING OF NERALURU TO THORAPALLI AGRAHARAM SECTION OF NH-844 (PKG-I) FROM KM.0+000 TO KM.23+350 | NHAI | N24001693 | 9-2021 | 10/2024 | N.A. | 10/2024 | 1751.18 |  | 1757.27 | 49.69 | -
April 2025 |  |  | 1360 | FOUR LANING OF THORAPALLI AGRAHARAM TO JITTANDAHALLI SECTION OF NH-844 (PKG-II) FROM KM.23+350 TO KM | NHAI | N24001694 | 2-2019 | 12/2023 | 12/2024 | 12/2024 | 1243.57 |  | 1243.57 | 171.63 | -
April 2025 |  |  | 1361 | FOUR LANING OF JITTANDAHALLI TO DHARMAPURI SECTION OF NH- 844 (PKG-III) FROM KM.60+100 TO KM.94+460 | NHAI | N24001696 | 2-2019 | 8/2023 | 12/2024 | 12/2024 | 1291.37 |  | 1291.37 | 215.02 | -
April 2025 |  |  | 1362 | THOPPUR METTUR BHAVANI ERODE SECTION OF NH 544H FOR A LENGTH OF 85 KM | NHAI | N24001716 | 7-2022 | 8/2023 | 12/2024 | 12/2024 | 186.5 | 242.4 | 242.4 | 17.15 | 100
April 2025 |  |  | 1363 | BANGALORE CHENNAI EXPRESSWAY PHASE-III PACKAGE III (ARAKKONAM TO KANCHEEPURAM) FROM KM 204.500 TO K | NHAI | N24001717 | 11-2020 | 8/2024 | N.A. | 3/2026 | 1155.49 | 1525.1 | 1525.1 | 489.94 | 53.45
April 2025 |  |  | 1364 | BANGALORE CHENNAI EXPRESSWAY PHASE-III PACKAGE II (WALAJAHPET TO ARAKKONAM) FROM KM 180.000 TO KM 2 | NHAI | N24001718 | 12-2020 | 7/2024 | N.A. | 8/2025 | 843.48 | 1077.4 | 1068.6 | 431.31 | 90.4
April 2025 |  |  | 1365 | 4L BANGALORE-CHENNAI EXPRESSWAY FROM KM. 230.000 TO KM. 261.705 OF KANCHEPURAM TO SRIPERUMBUDUR SECT | NHAI | N24001719 | 2-2021 | 7/2024 | N.A. | 10/2025 | 2948.31 | 3605.73 | 3605.73 | 808.77 | 73.8
April 2025 |  |  | 1366 | BANGALORE CHENNAI EXPRESSWAY PHASE-III ? PACKAGE I (GUDIPALA TO WALAJAJHPET) FROM KM 156.000 TO KM 1 | NHAI | N24001720 | 10-2020 | 5/2024 | N.A. | 8/2025 | 1023.91 | 1438.62 | 1438.62 | 635.04 | 83.57
April 2025 |  |  | 1367 | FOUR LANING OF MAMALLAPURAM TO MUGAIYUR SECTION OF NH332A FROM KM 0.000 TO KM 31.000 | NHAI | N24001721 | 2-2019 | 5/2024 | 8/2025 | 3/2026 | 1008.99 | 1360.53 | 1360.53 | 303.48 | 47.65
April 2025 |  |  | 1368 | 6L OF MADURAVOYAL TO SRIPERUMBUDUR SECTION FROM KM. 13.800 TO KM. 37.000 OF NH-4 THROUGH STATE HIGH | NHAI | N24001722 | 11-2021 | 2/2023 | N.A. | 12/2024 | 463.44 | 463.07 | 463.44 | 334.8 | 99
April 2025 |  |  | 1369 | KARAIPETTAI TO WALAJAPET FROM KM 71.015 TO 107.091 | NHAI | N24001723 | 10-2018 | 2/2021 | N.A. | 6/2025 | 707.9 | 766.51 | 766.51 | 526.39 | 88.95
April 2025 |  |  | 1370 | 6L OF SRIPERUMBUDUR TO KARAIPETTAI FROM KM 37.000 TO KM 71.015 OF NH 48 | NHAI | N24001725 | 1-2019 | 5/2021 | N.A. | 1/2025 | 819.89 | 1314.82 | 922.85 | 415.6 | 57.32
April 2025 |  |  | 1371 | CONSTRUCTION OF BYPASS TO GUDIYATHAM TOWN IN KM 23/100 ? 29/250 INCLUDING LA AND SHIFTING OF NH-234 | MoRTH | N24001828 | 1-2022 | 11/2024 | N.A. | 5/2025 | 221.03 | 243.95 | 243.95 | 176.5 | 85
April 2025 |  |  | 1372 | FOUR LANING OF OTTANCHATRAM TO PALANI SECTION FROM KM 30/700 TO KM 55/000 OF NH 209(NEW NH- 83) INCLU | MoRTH | N24001829 | 10-2022 | 11/2024 | N.A. | 5/2025 | 172.15 |  | 172.15 | 157.48 | 99
April 2025 |  |  | 1373 | CONSTRUCTION OF STRR (WEST SIDE)-NH948A- BALAGONDAPALLI (TAMIL NADU) TO KARNATAKA/TAMIL NADU BORDER F | NHAI | N24001968 | 4-2022 | 5/2025 | N.A. | 5/2025 | 1260.74 |  | 1260.74 | 487.46 | 44.95
April 2025 |  |  | 1374 | 4L OF THIRUMANGALAM TO VADUGAPATTI SECTION FROM KM 0.000 TO KM 36.000 OF NH- 744 | NHAI | N24002084 | 3-2022 | 2/2025 | N.A. | 8/2025 | 1076.97 |  | 1076.97 | 540.46 | 86.82
April 2025 |  |  | 1375 | CONSTRUCTION OF NEW DOUBLE TIER 4 LANE ELEVATED CORRIDOR FROM CHENNAI PORT TO MADURAVOYAL IN CHENNAI | NHAI | N24002107 | 3-2023 | 5/2026 | N.A. | 5/2026 | 1382 |  | 1382 | 0 | -
April 2025 |  |  | 1376 | CONSTRUCTION OF NEW DOUBLE TIER 4L ELEVATED CORRIDOR FROM CHENNAI PORT TO MADURAVOYAL IN CHENNAI DIS | NHAI | N24002108 | 3-2023 | 5/2026 | N.A. | 5/2026 | 1618.96 |  | 1618.96 | 0 | -
April 2025 |  |  | 1377 | CONSTRUCTION OF NEW DOUBLE TIER 4L ELEVATED CORRIDOR FROM CHENNAI PORT TO MADURAVOYAL IN CHENNAI DIS | NHAI | N24002109 | 3-2023 | 5/2026 | N.A. | 5/2026 | 1301.37 |  | 1301.37 | 0 | -
April 2025 |  |  | 1378 | CONSTRUCTION OF NEW DOUBLE TIER 4L ELEVATED CORRIDOR FROM CHENNAI PORT TO MADURAVOYAL IN CHENNAI DIS | NHAI | N24002110 | 3-2023 | 5/2026 | N.A. | 5/2026 | 1207.4 |  | 1207.4 | 0 | -
April 2025 |  |  | 1379 | FOUR LANING OF MUGAIYUR TO MARAKKANAM SECTION OF NH- 332A FROM KM 31.000 TO KM 62.000 | NHAI | N24002111 | 2-2019 | 12/2025 | 12/2025 | 12/2025 | 825.94 | 1116.13 | 1116.13 | 311.35 | 36.66
April 2025 |  |  | 1380 | SIX LANING OF TUTICORIN PORT ROAD SECTION OF NH-7A (NEW NH-138) FROM KM 0.000 TO KM 6.140 [EFFECTIVE | NHAI | N24002112 | 3-2023 | 7/2024 | N.A. | 6/2025 | 200.3 |  | 200.3 | 103.35 | 79.6
April 2025 |  |  | 1381 | 4L OF LEFT-OVER WORKS INCLUDING ADDITIONAL STRUCTURES FROM KERALA/TAMIL NADU BORDER TO KANYAKUMARI S | NHAI | N24002113 | 3-2023 | 8/2025 | N.A. | 8/2025 | 1141.78 |  | 1141.78 | 412.13 | 41.02
April 2025 |  |  | 1382 | 4L OF VADUGAPATTI TO THERKUVENGANALLUR (RAJAPALYAM) SECTION FROM KM 36.000 TO KM 71.600 OF NH744 UND | NHAI | N24002114 | 2-2022 | 4/2025 | N.A. | 10/2025 | 1097.59 |  | 1317.06 | 678.59 | 94.6
April 2025 |  |  | 1383 | WIDENING TO 4L/4L+PS AND STRENGTHENING IN SELECTED STRETCHES FROM KM 0/8 TO 50/570 OF NH 532 INCLUD | MoRTH | N24002151 | 3-2022 | 1/2024 | N.A. | 7/2025 | 257.14 | 294.7 | 294.7 | 228.36 | 82
April 2025 |  |  | 1384 | WIDENING FROM 2L+PS TO 4L/4L+PS AND IMPROVEMENTS THE SELECTED STRETHCES FROM KM 26/5 - 81/2 INCLU | MoRTH | N24002152 | 3-2023 | 11/2023 | N.A. | 11/2025 | 274.84 |  | 274.84 | 243.81 | 100
April 2025 |  |  | 1385 | STRENGTHENING OF 2L+PS FROM KM 17/8 ? 18/2, CONSTRUCTION OF 2L+PS FROM KM 18/2 TO KM 20/0 AND CONSTR | MoRTH | N24002153 | 3-2023 | 2/2024 | N.A. | 8/2025 | 169.68 |  | 169.68 | 112.18 | 70
April 2025 |  |  | 1386 | CONSTRUCTION OF BYPASS TO MADURAI - ACHAMBATHU - VIRATIPATHU IN KM 6/850 - 10/382 OF NH 49 EXTN. (NE | MoRTH | N24002165 | 3-2022 | 8/2026 | N.A. | 8/2026 | 238.97 | 260.07 | 260.07 | 95.44 | 44
April 2025 |  |  | 1387 | ACCESS CONTROLLED HIGHWAY OF 4 LANE WITH PAVED SHOULDERS FROM TIRUVALLUR (DESIGN CHAINAGE KM 17+56) | NHAI | N24002216 | 12-2024 | 12/2026 | N.A. | 12/2026 | 1376.1 |  | 1376.1 | 0 | 5.11
April 2025 |  | COAL | 1388 | KAKATIYAKHANI OPENCAST III PROJECT PHASE-1 | SCCL | N06000161 | 3-2017 | 3/2022 | N.A. | 3/2026 | 413.84 |  | 413.84 | 397.54 | 85
April 2025 |  | COAL | 1389 | GODAVARIKHANI COAL MINE | SCCL | N06000202 | 7-2019 | 3/2023 | N.A. | 3/2026 | 438.98 |  | 438.98 | 171.96 | 70
April 2025 |  | COAL | 1390 | VENKATESH KHANI COAL MINE | SCCL | N06000204 | 10-2020 | 3/2023 | N.A. | 3/2027 | 484.51 |  | 484.51 | 318.12 | 55
April 2025 |  | COAL | 1391 | RCE OF RAMAGUNDAM OPENCAST II EXTENSION PROJECT | SCCL | N06000210 | 11-2015 | 3/2023 | N.A. | 3/2026 | 489.62 |  | 489.62 | 405.54 | 70
April 2025 |  | COAL | 1392 | RCE OF INDARAM OPENCAST PROJECT | SCCL | N06000211 | 8-2017 | 3/2021 | N.A. | 3/2025 | 349.28 |  | 424.81 | 402.64 | 80
April 2025 |  | COAL | 1393 | RCE OF KALYANIKHANI OPENCAST PROJECT | SCCL | N06000213 | 3-2016 | 3/2020 | N.A. | 3/2026 | 384.32 |  | 384.32 | 255.02 | 75
April 2025 |  | COAL | 1394 | RCE OF KAKATHIYAKHANI OC - 2 PROJECT | SCCL | N06000214 | 8-2017 | 3/2020 | N.A. | 3/2026 | 442.42 |  | 442.42 | 203 | 63
April 2025 |  | COAL | 1395 | GOLETI OPENCAST MINE | SCCL | N06000258 | 7-2021 | 3/2026 | N.A. | 3/2026 | 345.6 |  | 345.6 | 68.47 | 20
April 2025 |  | HEALTH AND FAMILY WELFARE | 1396 | COMPREHENSIVE PLANNING, DESIGNING, EXECUTION OF ALL INDIA INSTITUTE OF MEDICAL SCIENCES AT BIBINAGAR | HITES | N21000031 | 12-2018 | 7/2024 | N.A. | 12/2025 | 1110.55 |  | 1110.55 | 734.9 | 81.62
April 2025 |  | HEALTH AND FAMILY WELFARE | 1397 | ESTABLISHMENT OF NATIONAL ANIMAL RESOURCE FACILITY FOR BIOMEDICAL RESEARCH AT HYDERABAD | CPWD FOR HEALTH | N28000098 | 10-2016 | 3/2020 | 1/2025 | 1/2025 | 209.84 | 281.05 | 281.05 | 253.13 | 98.5
April 2025 |  | RAILWAYS | 1398 | MANOHARABAD-KOTHPALL NEW LINE(SCR) | SCR | N22000032 | 4-2006 | 3/2027 | N.A. | 3/2025 | 1160 |  | 3014 | 1510.2 | -
April 2025 |  | RAILWAYS | 1399 | REHABILITATION AND UPGRADATION OF NH -565 FROM KM 1.00 TO 86.057 (NAKREKAL TO NAGARJUNSAGAR DAM SECT | MoRTH | N24000245 | 1-2014 | 3/2016 | 9/2019 | 9/2019 | 270 |  | 270 | 0 | 72.15
April 2025 |  | RAILWAYS | 1400 | REHABILITATION AND UPGRADATION OF NH-221 FROM KM 121/0 TO 165/00 (OF VIJAYAWADA-JAGDALPUR RUDRAMPUR | MoRTH | N24000247 | 10-2014 | 2/2017 | N.A. | 2/2017 | 295.47 |  | 295.47 | 224.42 | 99
April 2025 |  | RAILWAYS | 1401 | EPC- CORRIDOR APPROACH WORKS - NH (O): WIDENING EXISTING 2 LANE TO 2 LANE WITH PAVED SHOULDERS IN KM | MoRTH | N24000248 | 3-2015 | 1/2017 | N.A. | 1/2017 | 153.21 |  | 153.21 | 100.96 | 94
April 2025 |  | RAILWAYS | 1402 | WIDEINING TO TWO/FOUR LANE WITH PAVED SHOULDERS FROM EXISTING KM 182.120 TO KM 227.600 OF NH-167 ON | MoRTH | N24000980 | 10-2016 | 2/2019 | N.A. | 2/2019 | 298.32 |  | 298.32 | 178.47 | 98
April 2025 |  |  | 1403 | WIDEINING TO TWO/FOUR LANE WITH PAVED SHOULDERS FROM EXISTING KM 180.60 TO KM 223.00 OF NH-63 ON NIZ | MoRTH | N24000981 | 10-2016 | 3/2019 | N.A. | 3/2019 | 248.83 |  | 248.83 | 173.79 | 100
April 2025 |  |  | 1404 | WIDENING TO TWO LANE WITH PAVED SHOULDERS FROM KM 40/410 TO KM 84/037OF THIRUMALAGIRI TO SURYAPET SE | MoRTH | N24000982 | 1-2017 | 5/2019 | N.A. | 5/2019 | 244.54 |  | 244.54 | 174.35 | 99
April 2025 |  |  | 1405 | WIDENING TO TWO LANE WITH PAVED SHOULDERS FROM KM 0/970 TO KM 40/410 OF JANAGAON-THIRUMALAGIRI OF NH | MoRTH | N24000983 | 1-2017 | 10/2019 | N.A. | 10/2019 | 196.52 |  | 196.52 | 125.53 | 96
April 2025 |  |  | 1406 | WIDENING TO TWO LANE WITH PAVED SHOULDERS FROM KM 15.525 TO KM 62.880 OF JADCHERLA-KALWAKURTHY SECTI | MoRTH | N24000984 | 1-2017 | 12/2019 | N.A. | 12/2019 | 283 |  | 283 | 259.15 | 99
April 2025 |  |  | 1407 | WIDENING TO TWO LANE WITH PAVED SHOULDERS FROM KM 67.00 TO 114.425 OF KALWAKURTHY-MALLEPALLY SECTION | MoRTH | N24000986 | 1-2017 | 5/2019 | N.A. | 5/2019 | 300 |  | 300 | 239.93 | 96
April 2025 |  |  | 1408 | 6 LANING FROM KM 9.90 TO KM 19.948 (ARAMGARH-SAMSHABAD SECTION) OF HYDERABAD- SAMSHABAD SECTION OF NH | MoRTH | N24000987 | 1-2018 | 5/2020 | N.A. | 5/2020 | 283.15 |  | 283.15 | 270.01 | 93
April 2025 |  |  | 1409 | WIDENING AND STRENGTHENING OF EXISTING 2-LANE TO 2-LANE WITH PAVED SHOULDERS FROM KM.159/0 TO 165/4 | MoRTH | N24000988 | 1-2018 | 12/2019 | N.A. | 12/2019 | 230.03 |  | 230.03 | 231.31 | 100
April 2025 |  |  | 1410 | WIDENING AND STRENGTHENING OF EXISTING CARRIAGEWAY IN 2 LANE WITH PAVED SHOULDERS FROM KM.25/0 TO 59 | MoRTH | N24000989 | 2-2018 | 6/2020 | N.A. | 6/2020 | 206.13 |  | 206.13 | 190.94 | 98
April 2025 |  |  | 1411 | REHABILITATION AND UPGRADATION OF NH-167 FROM DESIGN KM.113.900 TO 154.479 (MALLEPALLY - HALIYA SECT | MoRTH | N24000990 | 2-2018 | 11/2019 | N.A. | 11/2019 | 294.13 |  | 294.13 | 198.75 | 87
April 2025 |  |  | 1412 | REHABILITATION AND UPGRADATION OF NH-167 FROM DESIGN KM.187.723 TO 234.434 (MIRYALAGUDA TO KODAD SEC | MoRTH | N24000993 | 3-2018 | 9/2020 | N.A. | 9/2020 | 322.81 |  | 322.81 | 315.23 | 98
April 2025 |  |  | 1413 | CONSTRUCTION OF SIX LANE ELEVATED CORRIDOR FROM KM.7.950 (UPPAL) TO KM.14.200 OF NH-163 TO DE-CONGES | MoRTH | N24000994 | 3-2018 | 7/2020 | N.A. | 2/2026 | 626.76 |  | 626.76 | 272.64 | 45
April 2025 |  |  | 1414 | REHABILITATION AND UP- GRADATION TO TWO LANE WITH PAVED SHOULDERS FROM KM 0/0 TO 72/6 OF NH-365 (NAKR | MoRTH | N24000996 | 1-2017 | 10/2019 | N.A. | 10/2019 | 605.08 |  | 605.08 | 413.37 | 100
April 2025 |  |  | 1415 | REHABILITATION AND UP GRADATION FROM KM. 121/0 TO 154/0 OF NAKAREKAL ? MALLAMPALLY SECTION OF NH- 365 | MoRTH | N24000997 | 3-2018 | 7/2019 | N.A. | 7/2019 | 192.67 |  | 192.67 | 176.37 | 92
April 2025 |  |  | 1416 | WIDENING AND STRENGTHENING/ RECONSTRUCTION OF EXISTING PAVEMENT TO FOUR ALNE WITH PAVED SHOULDERS FR | MoRTH | N24000998 | 1-2019 | (N.A.) | {} |  | 193.19 |  | 249.72 | 222.58 | 95
April 2025 |  |  | 1417 | KHAMMAM-DEVARAPALLE PKG I [4L ACCESS CONTROLLED (GREENFIELD) FROM THALLAMPADU VILLAGE TO SOMAVARAM | NHAI | N24001482 | 8-2022 | 10/2024 | N.A. | 10/2024 | 772.11 |  | 772.11 | 515.01 | 75.21
April 2025 |  |  | 1418 | KHAMMAM DEVARAPALLE PKG II 4L ACCESS CONTROLLED (GREENFIELD) FROM SOMAVARAM VILLAGE TO CHINTAGUDEM V | NHAI | N24001483 | 2-2022 | 9/2024 | N.A. | 9/2024 | 637.11 |  | 637.11 | 398.9 | 82
April 2025 |  |  | 1419 | KHAMMAM-DEVARAPALLE PKG III [4L ACCESS CONTROLLED (GREENFIELD) FROM CHINTAGUDEM VILLAGE TO RECHERLA | NHAI | N24001484 | 9-2022 | 2/2024 | 12/2024 | 12/2024 | 804.69 |  | 804.69 | 510.12 | 87
April 2025 |  |  | 1420 | 4L OF KODAD (DESIGN KM 0.00/EXISTING KM 185.00 OF NH- 65) TO KHAMMAM (DESIGN KM 31.800/EXISTING KM 29 | NHAI | N24001522 | 1-2021 | 1/2024 | 12/2024 | 12/2024 | 1307.95 |  | 1307.95 | 707.34 | 99.79
April 2025 |  |  | 1421 | 6 LANING OF EXISTING 4-LANE STRETCH FROM KALKALLU AT KM.454+000 TO GUNDLA POCHAMPALLY AT KM.471+000, | NHAI | N24001555 | 3-2022 | 1/2025 | N.A. | 1/2025 | 955.49 |  | 955.49 | 226.99 | 35.96
April 2025 |  |  | 1422 | 6L OF EXISTING 4L FROM GUNDLAPOCHAMPALLY TO BOWENPALLY FROM KM 471.300 TO KM 481.331 OF NH-44 | NHAI | N24001556 | 12-2021 | 7/2024 | N.A. | 7/2024 | 521.53 |  | 521.53 | 247.45 | 48.76
April 2025 |  |  | 1423 | 6L ACCESS CONTROLLED GREENFIELD HIGHWAY OF JULEKAL VILLAGE TO DINNEDEVARAPADU VILLAGE FROM KM 242.20 | NHAI | N24001625 | 1-2022 | 1/2025 | N.A. | 7/2025 | 1227.57 |  | 1227.57 | 288.58 | 46.5
April 2025 |  |  | 1424 | 6L ACCESS CONTROLLED GREENFIELD HIGHWAY OF NANDINNE VILLAGE TO JULEKAL VILLAGE FROM KM 202.900 TO KM | NHAI | N24001626 | 2-2022 | 1/2025 | N.A. | 1/2025 | 972.06 |  | 972.06 | 408.48 | 64.42
April 2025 |  |  | 1425 | WIDENING AND STRENGTHENING OF EXISTING 2 LANE WITH PAVED SHOULDER TO 4 LANE WITH PAVED SHOULDER FRO | MoRTH | N24002000 | 3-2021 | 7/2024 | N.A. | 7/2024 | 317.19 |  | 317.19 | 162.21 | 70
April 2025 |  |  | 1426 | WIDENING TO 2 LANE WITH PAVED SHOULDERS OF MEDAK - SIDDIPET SECTION FROM KM 0/0 TO KM 69/978 OF NH- | MoRTH | N24002001 | 1-2022 | 1/2025 | N.A. | 6/2025 | 882.18 |  | 882.18 | 206.02 | 71
April 2025 |  |  | 1427 | WIDENING AND IMPROVEMENT OF EXISTING CARRIAGE WAY TO 2 LANE WITH PAVED SHOULDERS FROM KM. 86/160 TO | MoRTH | N24002002 | 1-2022 | 12/2024 | N.A. | 12/2024 | 423.48 |  | 423.48 | 149.27 | 71
April 2025 |  |  | 1428 | REHABILITATION AND UP- GRADATION OF VALIGONDA TO THORRUR SECTION TO TWO LANE WITH PAVED SHOULDERS FRO | MoRTH | N24002003 | 1-2022 | 12/2024 | N.A. | 12/2024 | 549.28 |  | 549.28 | 103.51 | 70
April 2025 |  |  | 1429 | REHABILITATION AND UPGRADATION OF LB-NAGAR TO MALKAPUR SECTION TO 6- LANE MAIN CARRIAGEWAY WITH SERVI | MoRTH | N24002004 | 3-2021 | 7/2024 | N.A. | 6/2025 | 545.11 |  | 545.11 | 191.56 | 76
April 2025 |  |  | 1430 | WIDENING TO TWO LANE WITH PAVED SHOULDERS OF 'BODHAN BASAR BHAINSA ' SECTION FROM KM 38/900 TO 95/3 | MoRTH | N24002005 | 3-2022 | 3/2025 | N.A. | 6/2025 | 644.45 |  | 644.45 | 182.85 | 93
April 2025 |  |  | 1431 | ONSTRUCTION OF 4-LANE FLYOVER AT AMBERPET-X ROAD, HYDERABAD ON NH-202 IN THE STATE OF TELANGANA | MoRTH | N24002006 | 10-2017 | 6/2023 | N.A. | 6/2023 | 186.71 |  | 186.71 | 149.64 | 92
April 2025 |  |  | 1432 | WIDENING TO TWO LANE WITH PAVED SHOULDERS FROM KM 0/000 TO KM 79/300 OF KALWAKURTHY - KOLLAPUR SECTI | MoRTH | N24002007 | 3-2022 | 7/2025 | N.A. | 7/2025 | 886.69 |  | 886.69 | 90.46 | 59
April 2025 |  |  | 1433 | WIDENING TO 2 LANE WITH PAVED SHOULDERS OF SIDDIPET-ELKATHURTHY SECTION FROM KM 69/978 TO KM 133/6 | MoRTH | N24002008 | 1-2022 | 12/2024 | N.A. | 12/2024 | 578.85 |  | 578.85 | 172.76 | 79
April 2025 |  |  | 1434 | WIDENING AND STRENGTHENING TO 2/4 LANE WITH PAVED SHOULDERS OF MAHABUBNAGAR ? CHINCHOLI SECTION FROM | MoRTH | N24002009 | 1-2022 | 1/2025 | N.A. | 7/2025 | 703.68 |  | 703.68 | 193.39 | 61
April 2025 |  |  | 1435 | WIDENING AND STRENGTHENING TO 4 LANE / 2- LANE WITH PAVED SHOULDERS OF MAHABUBNAGAR- CHINCHOLI SECTION | MoRTH | N24002010 | 3-2022 | 3/2024 | N.A. | 10/2025 | 631.49 |  | 631.49 | 7.92 | 25
April 2025 |  |  | 1436 | IMPROVEMENT OF GEOMETRICS OF THONDUPALLY TO KOTHUR FROM KM 22.300 TO KM 34.14 OF NH-44-RCW | NHAI | N24002082 | 2-2022 | 9/2024 | N.A. | 1/2026 | 541.58 |  | 541.58 | 34.78 | -
April 2025 |  |  | 1437 | FOUR LANING OF KARIMNAGAR- WARANGAL SECTION OF NH-563 FROM DESIGN CH.48.860 KM NEAR SH-1 CH.170.400 K | NHAI | N24002083 | 3-2022 | 7/2025 | N.A. | 7/2025 | 2146.86 | 2413 | 2414.46 | 917.28 | 69.15
April 2025 |  |  | 1438 | CONSTRUCTION OF 4-LANE ACCESS CONTROLLED GREENFIELD HIGHWAY SECTION ON NH-163G | KHAMMAM-VIJAYAWADA | NHAI | 3-2023 | 8/2026 | N.A. | 8/2026 | 983 |  | 983 | 0 | 8.5
April 2025 |  |  | 1439 | CONSTRUCTION OF 4-LANE ACCESS CONTROLLED GREENFIELD HIGHWAY SECTION ON NH-163G (KHAMMAM - VIJAYAWADA | NHAI | N24002236 | 3-2023 | 3/2025 | N.A. | 3/2027 | 832.62 |  | 832.62 | 0 | -
April 2025 |  | PETROLEUM | 1440 | GRASS ROOT RAIL FED DEPOT AT SEKERKOTE, AGARTALA AS RESITEMENT OF EXISTING DHARMANAGAR DEPOT | IOCL | N16000495 | 6-2022 | 8/2025 | 9/2025 | 9/2025 | 656 |  | 656 | 395.18 | 81.15
April 2025 |  | PETROLEUM | 1441 | REHABILITATION AND UPGRADATION OF ROAD FROM KM 0.00 TO KM 18.600 OF KUMARGHAT-KAILASHAHAR SECTION | NHIDCL | N24001263 | 6-2020 | 1/2022 | 2/2024 | 12/2024 | 277.5 | 302.02 | 302.02 | 260.38 | 99.94
April 2025 |  | PETROLEUM | 1442 | KAILASHAHAR TO KHOWAI PKG- 4 | NHIDCL | N24001309 | 11-2020 | 6/2022 | 10/2023 | 11/2024 | 159.13 | 171.5 | 171.5 | 84.33 | 100
April 2025 |  |  | 1443 | 2-LANING FROM JOLAIBARI - BELONIA | NHIDCL | N24001317 | 6-2020 | 1/2022 | N.A. | 4/2025 | 201.99 |  | 287.47 | 148.22 | 100
April 2025 |  |  | 1444 | MANU-SIMLUNG ( PKG 4) | NHIDCL | N24001363 | 3-2021 | 12/2022 | N.A. | 12/2025 | 354.79 |  | 354.79 | 34.08 | -
April 2025 |  |  | 1445 | 2 LANING FROM MANU-SIMLUNG PKG-2 | NHIDCL | N24001542 | 2-2022 | 1/2025 | 5/2025 | 5/2025 | 456.88 |  | 456.88 | 122.23 | 49.17
April 2025 |  |  | 1446 | IMPROVEMENT AND WIDENING TO 2-LANE WITH EARTHEN PAVED SHOULDER FROM UDAIPUR TO SRIMANTAPUR | NHIDCL | N24001914 | 5-2023 | 11/2024 | N.A. | 11/2025 | 195.95 |  | 195.95 | 38.1 | 38.44
April 2025 |  |  | 1447 | 4 LANE WITH PAVED SHOULDER AGARTALA BYPASS (WESTERN SIDE) CONNECTING NH-8 | NHIDCL | N24002132 | 3-2023 | 3/2027 | N.A. | 3/2027 | 2026.05 |  | 2026.05 | 18.44 | 7.96
April 2025 |  |  | 1448 | REHABILITATION AND UP- GRADATION OF ROAD FROM DESIGN KM 25.250 TO KM 36.460 | TOTAL LENGH: 11.210 KM | NHIDCL | 2-2020 | 3/2026 | N.A. | 3/2026 | 174.43 |  | 174.43 | 7.56 | 16.61
April 2025 |  |  | 1449 | IMPROVEMENT AND WIDENING TO 2-LANE WITH PAVED SHOULDER OF ROAD FROM KM 101.300 TO KM 127.319 (TOTAL | NHIDCL | N24002160 | 1-2024 | 7/2026 | N.A. | 7/2026 | 431.78 |  | 431.78 | 46.6 | 31.45
April 2025 |  |  | 1450 | KHOWAI ?TELIAMURA-AMARPUR- HARINA-SABROOM PACKAGE-2 | NHIDCL | N24002161 | 1-2024 | 9/2026 | N.A. | 9/2026 | 657.21 |  | 657.21 | 11.96 | 27.5
April 2025 |  |  | 1451 | KHOWAI ?TELIAMURA-AMARPUR- HARINA-SABROOM PACKAGE-3 | NHIDCL | N24002162 | 1-2024 | 9/2026 | N.A. | 9/2026 | 670.9 |  | 670.9 | 0 | -
April 2025 |  |  | 1452 | CHAMPAK NAGAR TO KHAYERPUR SECTION (DESIGN KM 242+500 TO KM 261+610) | NHIDCL | N24002205 | 12-2023 | 9/2026 | N.A. | 9/2026 | 920.66 |  | 920.66 | 63.55 | 18.6
April 2025 |  |  | 1453 | KHOWAI ?TELIAMURA-AMARPUR- HARINA-SABROOM SECTION PKG-4 | NHIDCL | N24002228 | 1-2024 | 12/2026 | N.A. | 12/2026 | 726.9 |  | 726.9 | 0 | 2.25
April 2025 |  | CIVIL AVIATION | 1454 | CCS INTERNATIONAL AIRPORT , LUCKNOW | AAI | N04000077 | 6-2018 | 9/2021 | 10/2026 | 10/2026 | 1383 | 1938 | 3291.81 | 2631.82 | 79.95
April 2025 |  | CIVIL AVIATION | 1455 | DEVELOPMENT OF AYODHYA AIRPORT PHASE-01 | AAI | N04000094 | 3-2021 | 12/2022 | 5/2025 | 5/2025 | 242.14 | 328 | 358 | 344.58 | 99.9
April 2025 |  | CIVIL AVIATION | 1456 | PRAYAGRAJ AIRPORT - CONSTRUCTION OF NEW TERMINAL BUILDING, SECOND LINK TAXI TRACK, APRON EXPANSION, | AAI | N04000102 | 5-2023 | 11/2024 | 6/2025 | 6/2025 | 185.75 | 274.38 | 274.38 | 192.24 | 91
April 2025 |  | CIVIL AVIATION | 1457 | AGRA: DEVELOPMENT OF NEW CIVIL ENCLAVE AT AGRA AIRPORT. | AAI | N04000113 | 6-2024 | 7/2026 | N.A. | 7/2026 | 579 |  | 579 | 46.91 | 11
April 2025 |  | CIVIL AVIATION | 1458 | VARANASI: DEVELOPMENT OF LAL BAHADUR SHASTRI INTERNATIONAL AIRPORT, VARANASI. | AAI | N04000114 | 7-2024 | 7/2027 | N.A. | 7/2027 | 2869.65 |  | 2869.65 | 225.89 | 14
April 2025 |  | COAL | 1459 | NEYVELI UTTAR PRADESH POWER PROJECT LIMITED 1980 MW | NLC | N06000152 | 7-2016 | 11/2021 | 10/2025 | 10/2025 | 17237 | 21780.94 | 21780.94 | 19780.67 | 90.41
April 2025 |  | COAL | 1460 | KHADIA EXPANSION OCP | NCL | N06000208 | 6-2021 | 3/2025 | N.A. | 3/2027 | 491.67 |  | 491.67 | 163.58 | 13.12
April 2025 |  | HOME AFFAIRS | 1461 | CONSTRUCTION OF 683 VARIOUS TYPE FAMILY QUARTERS AT GROUP CENTRE CRPF CHANDAULI | CPWD FOR MHA | N45000003 | 5-2019 | 1/2022 | 3/2023 | 3/2023 | 199.31 |  | 199.31 | 86.49 | 85
April 2025 |  | PETROLEUM | 1462 | 60 KTA POLYPROPYLENE PROJECT | GAIL | N16000429 | 3-2019 | 4/2024 | 4/2024 | 6/2025 | 910.56 | 1299.02 | 1299.02 | 956 | 95.3
April 2025 |  | PETROLEUM | 1463 | AUGMENTATION OF FACILITIES AT MATHURA BITUMEN PLANT | IOCL | N16000505 | 4-2022 | 4/2025 | 12/2026 | 12/2026 | 260.12 |  | 260.12 | 1.03 | 25
April 2025 |  | PETROLEUM | 1464 | GRASS-ROOT TERMINAL AT MIRZAPUR UTTAR PRADESH | IOCL | N16000506 | 9-2022 | 6/2026 | N.A. | 11/2026 | 980.45 |  | 980.45 | 177.07 | 49.49
April 2025 |  | PETROLEUM | 1465 | CITY GAS DISTRIBUTION PROJECTS AT LAKHIMPUR KHERI , SITAPUR, BAHRAICH, SHRAVASTI,BALRAMPUR, | BPCL | N16000525 | 12-2022 | 6/2030 | N.A. | 6/2030 | 16654 |  | 16654 | 527.19 | 9.4
April 2025 |  | PETROLEUM | 1466 | KHURJA SUPER THERMAL POWER PROJECT | THDCIL | N18000272 | 3-2019 | 9/2023 | N.A. | 6/2025 | 11089.42 |  | 13276.16 | 12251.2 | 95.2
April 2025 |  |  | 1467 | SINGRAULI SUPER THERMAL POWER PROJECT, STAGE-III | 2X800 MW | NTPC | 3-2024 | 2/2030 | N.A. | 2/2030 | 17195.31 |  | 17195.31 | 1302.8 | 0.5
April 2025 |  |  | 1468 | TRANSMISSION SYSTEM FOR EVACUATION OF POWER FROM RAJASTHAN REZ PH-IV (PART-4: 3.5 GW): PART A | PGCIL | N18000407 | 12-2024 | 12/2026 | N.A. | 12/2026 | 5846 |  | 5846 | 0 | -
April 2025 |  |  | 1469 | VARANASI-MODHOSINGH- ALLAHABAD DOUBLING | RVNL | N22000401 | 4-2015 | 12/2024 | N.A. | 12/2024 | 2018.23 |  | 2018.23 | 1780.22 | -
April 2025 |  |  | 1470 | 2880.4 | ECR | N22000417 | 8-2015 | 8/2024 | N.A. | 1/2025 | 2880.4 | 2880.4 | 2880.4 | 3074.78 | 100
April 2025 |  |  | 1471 | KARAILA ROAD - SHAKTINAGAR DOUBLING | ECR | N22000419 | 8-2015 | 8/2024 | N.A. | 12/2024 | 762.97 | 762.97 | 762.97 | 808.96 | 100
April 2025 |  |  | 1472 | BURHWAL - GONDA - 3RD RUNNING LINE. | NER | N22000468 | 4-2016 | 3/2025 | N.A. | 9/2025 | 1015.59 |  | 1117.8 | 1092.11 | 48
April 2025 |  |  | 1473 | SHAHGANJ-BHATNI-PHEPHNA- INDARA, MAU-SHAHGANJ (EXCL. MAU-INDARA) PATCH DOUBLING. | NER | N22000470 | 4-2016 | 12/2024 | N.A. | 5/2025 | 1177.96 |  | 2050 | 2042.6 | 80.5
April 2025 |  |  | 1474 | JHANSI MANIKPUR AND KHAIRAR BHIMSEN DOUBLING | NCR | N22000495 | 3-2018 | 3/2026 | N.A. | 3/2027 | 4329.53 |  | 4329.53 | 1963.36 | 45
April 2025 |  |  | 1475 | JHANSI BINA DOUBLING | NCR | N22000496 | 9-2016 | 3/2022 | N.A. | 3/2027 | 2002 |  | 2001 | 1717.2 | 90
April 2025 |  |  | 1476 | MATHURA-JHANSI-3RD LINE | 273.80 KM | RVNL | 6-2016 | 12/2024 | N.A. | 12/2024 | 5323.39 |  | 5190.26 | 5046.07 | -
April 2025 |  |  | 1477 | SURFACE TRIANGLE LINE BETWEEN BHADURA STATION AND NEW CROSSING STN KARMA DOUBLING | ECR | N22000525 | 10-2022 | 10/2027 | N.A. | 10/2027 | 199.96 |  | 199.96 | 55.09 | -
April 2025 |  |  | 1478 | MUGHALSARAI - ALLAHABAD - 3RD LINE | NCR | N22000544 | 8-2019 | 12/2026 | N.A. | 12/2026 | 2649.44 |  | 2390 | 83.1 | 55
April 2025 |  |  | 1479 | ALIGARH-HARDUAGANJ FLYOVER (22 KM) | NCR | N22000545 | 4-2020 | 6/2026 | N.A. | 6/2026 | 1456.89 | 1244.13 | 1456.89 | 10.14 | 8.1
April 2025 |  |  | 1480 | LALITPUR - BIRARI WITH FLYOVER AT LALITPUR | NCR | N22000546 | 3-2017 | 12/2024 | N.A. | 6/2025 | 356.09 |  | 356 | 196.15 | 65
April 2025 |  |  | 1481 | ALIGARH-DAUD KHAN - 3RD LINE 6.9 KM AND CONSTRUCTION OF FLYOVER AT DAUD KHAN | NCR | N22000562 | 4-2019 | 12/2025 | N.A. | 12/2025 | 451.99 | 779.49 | 779.49 | 99.7 | 38.1
April 2025 |  |  | 1482 | ALLAHABAD-BAMHRAULI - 4TH LINE (10 KM) WITH FLY-OVER AT SUBEDARGANJ | NCR | N22000563 | 4-2019 | 3/2026 | N.A. | 3/2026 | 494.11 |  | 494.11 | 42.61 | 42
April 2025 |  |  | 1483 | BHANDAI - FLYOVER FOR ETAWAH BOUND DOWN TRAINS | NCR | N22000564 | 4-2019 | 12/2025 | N.A. | 3/2026 | 187.21 |  | 250.17 | 1.29 | 8
April 2025 |  |  | 1484 | SAHJANWA - DOHRIGHAT | NER | N22000565 | 8-2019 | 3/2029 | N.A. | 12/2027 | 371.77 |  | 1319.75 | 551.74 | 2.5
April 2025 |  |  | 1485 | BAHRAICH - NANPARA - NEPALGANJ (56.15 KM) | NER | N22000566 | 7-2020 | 12/2024 | N.A. | 6/2025 | 950 |  | 341.66 | 300.63 | 21.5
April 2025 |  |  | 1486 | BAHRAICH SRAVASTI BALRAMPUR (TULSIPUR) | NER | N22000569 | 10-2018 | 10/2030 | N.A. | 3/2028 | 4939.78 |  | 4939.78 | 1079.6 | 5
April 2025 |  |  | 1487 | JANGHAI PRATAPGARH AMETHI DOUBLING | NR | N22000583 | 11-2017 | 3/2025 | N.A. | 12/2025 | 721.72 |  | 1100 | 39.22 | 70
April 2025 |  |  | 1488 | BARABANKI MALHAUR 3RD AND 4TH LINE (32.84 KM) | NR | N22000590 | 1-2019 | 3/2025 | 1/2026 | 12/2025 | 323.85 |  | 407 | 5.17 | 58
April 2025 |  |  | 1489 | DOUBLING BETWEEN JAUNPUR JN-ZAFFARABAD (6.28 KM) | NR | N22000591 | 3-2023 | 12/2026 | N.A. | 12/2026 | 177.33 |  | 177.33 | 0.89 | 10
April 2025 |  |  | 1490 | JANGHAI-PHAPHAMAU - DOUBLING WITH ELECTRIFICATION (46.79 KM) | RVNL | N22000596 | 11-2018 | 3/2025 | N.A. | 3/2025 | 357.48 |  | 409.38 | 362.09 | -
April 2025 |  |  | 1491 | BHATNI - AUNRIHAR WITH ELECTRIFICATION (125 KM) (EXCL INDARA - MAU (116.95 KM)) | RVNL | N22000598 | 5-2018 | 12/2024 | N.A. | 2/2025 | 2529.46 |  | 2529.46 | 1636.33 | -
April 2025 |  |  | 1492 | MATHURA - VRINDAVAN (11 KM) | NCR | N22000612 | 8-2022 | 6/2025 | N.A. | 6/2025 | 402.88 |  | 402.88 | 0 | -
April 2025 |  |  | 1493 | DOMINGARH - GORAKHPUR - GORAKHPUR CANTT - KUSUMHI - 3RD RUNNING LINE (21.15 KM) | NER | N22000613 | 11-2016 | 2/2025 | N.A. | 7/2025 | 351.03 |  | 500.37 | 464.91 | 86
April 2025 |  |  | 1494 | CONSTRUCTION OF RING ROAD FOR RAEBARELI CITY (PHASE - I) ON EASTERN SIDE OF NH 24B | MoRTH | N24000331 | 12-2019 | 4/2022 | N.A. | 6/2025 | 282.41 |  | 319.96 | 276.35 | 88
April 2025 |  |  | 1495 | 4-LANNING OF HARIDWAR- NAGINA SECTION OF NH 74 FROM (KM 204.300 OF NH 58) TO KM 73.00 | NHAI | N24000564 | 3-2016 | 7/2020 | 6/2025 | 6/2025 | 1408 | 1659.12 | 1659.12 | 1319.36 | 88.01
April 2025 |  |  | 1496 | SIX LANING OF HAPUR BYPASS TO MORADABAD SECTION INCLUDING HAPUR BYPASS FROM KM 50.000 (DESIGN CHAINA | NHAI | N24000798 | 3-2018 | 11/2021 | N.A. | 6/2025 | 2140.93 |  | 2140.93 | 2067.09 | 98.9
April 2025 |  |  | 1497 | TWO / FOUR LANING OF RAEBARELI - JAGDISHPUR SECTION OF NH-330A FROM KM. 0.000 TO KM. 47.800 (DESIGN | NHAI | N24001306 | 10-2020 | 3/2023 | N.A. | 5/2024 | 724.6 |  | 724.6 | 569.96 | 96
April 2025 |  |  | 1498 | CONSTRUCTION OF 6 LANE BRIDGE ON GANGA ON NH-96 AND ITS APPROACHES IN PHAPHAMAU ALLAHABAD ON EPC MOD | MoRTH | N24001421 | 7-2018 | 2/2024 | N.A. | 8/2025 | 1948.25 |  | 1948.25 | 1082.99 | 77
April 2025 |  |  | 1499 | CONSTRUCTION OF FOUR-LANE ELEVATED VIADUCT FROM KM.4+634 TO KM.6+345 ON NH- 24A INCLUDING RETAINING W | MoRTH | N24001424 | 3-2021 | 9/2023 | N.A. | 1/2025 | 185.09 | 269.81 | 269.81 | 266.35 | 100
April 2025 |  |  | 1500 | REHABILITATION AND UPGRADATION TO 2 LANE WITH PS OF RADHAITA TO PILIBHIT SECTION OF 46.130 KM | MoRTH | N24001456 | 4-2020 | 2/2024 | N.A. | 1/2025 | 199.39 | 212.96 | 199.39 | 200.01 | 100
April 2025 |  |  | 1501 | REHABILITATION AND UPGRADATION TO 2 LANE WITH PS OF MIRANPUR KATRA TO RADHAITA SECTION OF NH-730C F | MoRTH | N24001457 | 4-2020 | 7/2024 | N.A. | 9/2025 | 172.5 | 169.56 | 172.5 | 106.04 | 73
April 2025 |  |  | 1502 | 2-LANE WITH PS OF BEWAR TO NEAR KARRI VILLAGE SECTION OF NH-92 FROM KM.0.00 TO 30.00 UNDER GNHCP | MoRTH | N24001461 | 4-2020 | 3/2024 | N.A. | 7/2025 | 236.47 |  | 236.47 | 145.81 | 87
April 2025 |  |  | 1503 | 2-LANE WITH PS OF NEAR KARRI VILLAGE TO ETAWAH SECTION OF NH-92 FROM KM.30.000 TO 57.346 UNDER GNHCP | MoRTH | N24001462 | 4-2020 | 7/2024 | N.A. | 7/2025 | 211.09 |  | 211.09 | 147.58 | 95
April 2025 |  |  | 1504 | PROJECTS- REHABILITATION AND UPGRADATION OF NH-731A FROM KM 0.00 TO KM.35.00 | MoRTH | N24001464 | 3-2021 | 8/2023 | N.A. | 5/2025 | 264.86 |  | 264.86 | 122.82 | 84
April 2025 |  |  | 1505 | IMPROVEMENT AND UPGRADATION TO TWO LANE WITH PAVED SHOULDER CONFIGURATION FROM EXISTING KM 55.00 TO | MoRTH | N24001469 | 11-2021 | 5/2024 | N.A. | 7/2025 | 307.11 |  | 307.11 | 199.38 | 88
April 2025 |  |  | 1506 | R/U TO 2-LANE WITH PS OF BEWAR TO ALLAHGANJ SECTION OF NH-730C FROM KM.0.00 TO 52.770 UNDER GNHCP | MoRTH | N24001471 | 4-2020 | 11/2024 | N.A. | 6/2025 | 325.24 | 340.16 | 325.24 | 284.33 | 96
April 2025 |  |  | 1507 | WIDENING AND UPGRADATION TO FOUR LANE CONFIGURATION FROM KM.34.900 (BHADOHI) TO KM.73.134 (JAUNPUR) | MoRTH | N24001479 | 3-2021 | 5/2024 | N.A. | 6/2025 | 395.62 | 392.03 | 395.62 | 281.93 | 72
April 2025 |  |  | 1508 | WIDENING AND STRENGTHENING FROM KM 0.00 TO KM 15.089 OF NH-334A (PURKAJI-LAKSAR-HARIDWAR ROAD) TO TW | MoRTH | N24001480 | 10-2021 | 4/2024 | N.A. | 3/2025 | 227.06 |  | 227.06 | 141.89 | 100
April 2025 |  |  | 1509 | 6L ACCESS-CONTROLLED HIGHWAY FROM (GANESHPUR) TO(NEAR MOHAND) OF GANESHPUR ? DEHRADUN SECTION FROM K | NHAI | N24001523 | 3-2021 | 10/2023 | 5/2025 | 5/2025 | 836.24 |  | 836.24 | 792.55 | 98.85
April 2025 |  |  | 1510 | 6L OF ACCESS-CONTROLLED HIGHWAY FROM MOHAND TO DAAT KALI TUNNEL OF GANESHPUR ? DEHRADUN SECTION FROM | NHAI | N24001524 | 3-2021 | 10/2023 | 5/2025 | 5/2025 | 990.28 |  | 990.28 | 997.62 | 98.78
April 2025 |  |  | 1511 | WIDENING AND STRENGTHENING OF SECTION FROM BHARTHANA CHOWK TO KODARKOOT (KM. 0.00 TO KM. 40.00) OF | MoRTH | N24001587 | 3-2020 | 9/2024 | N.A. | 6/2025 | 262.37 | 343.77 | 343.77 | 278.9 | 84
April 2025 |  |  | 1512 | 4L SPUR OF SHAMLI- MUZZAFARNAGAR CONNECTING NH-709AD (PANIPAT-SHAMLI- MUZAFFARNAGAR) AND NH-58 (MEERUT | NHAI | N24001726 | 1-2023 | 8/2024 | N.A. | 8/2024 | 391.26 |  | 391.26 | 14.12 | 80.3
April 2025 |  |  | 1513 | IMPROVEMENT AND UP- GRADATION OF EXISTING ROAD TO 2/4L PS FROM KM 40.000 TO 88.750, START OF KHUTAR B | NHAI | N24001727 | 3-2022 | 2/2025 | N.A. | 2/2025 | 762.62 |  | 762.62 | 557.37 | 92.85
April 2025 |  |  | 1514 | 4L SPUR OF PANIPAT - SHAMLI CONNECTING NH-709AD (PANIPAT ? SHAMLI ? MUZAFFARNAGAR) AND NH- 709A (KARN | NHAI | N24001729 | 8-2022 | 4/2024 | N.A. | 7/2025 | 326.79 |  | 329.79 | 109.08 | 96
April 2025 |  |  | 1515 | 4L FROM GAJU VILLAGE AT KM 32.982 TO DEVINAGAR BYPASS (END) AT KM 208.000 OF NH 530B (PKG 1C) | NHAI | N24001730 | 12-2021 | 1/2025 | N.A. | 3/2025 | 1384.79 |  | 1384.79 | 657.94 | 97.98
April 2025 |  |  | 1516 | 6L GREENFIELD KANPUR - LUCKNOW (EXPRESSWAY) PKG II FROM KM. 28.500 TO KM. 73.744 | NHAI | N24001731 | 12-2021 | 5/2025 | 5/2025 | 5/2025 | 2470.64 |  | 2335 | 691.28 | 85.7
April 2025 |  |  | 1517 | IMPROVEMENT AND UP- GRADATION OF EXISTING ROAD TO 4L PS FROM KM 229.070 TO 260.800, END OF HARDOI DIS | NHAI | N24001732 | 12-2021 | 10/2024 | N.A. | 7/2025 | 540.97 |  | 540.97 | 270.14 | 88.09
April 2025 |  |  | 1518 | 6L ACCESS CONTROLLED GREENFIELD HIGHWAY OF JUNCTION OF EPE (VILL.- MAVIKALAN) TO VILL.-LOHADDA FROM K | NHAI | N24001733 | 3-2022 | 8/2024 | N.A. | 7/2025 | 1602.48 |  | 1602.48 | 432.16 | 90
April 2025 |  |  | 1519 | 6L ACCESS CONTROL GREENFIELD HIGHWAY OF VILL- LOHADDA TO VILL-KARAUNDA MAHAJAN FROM KM. 27.000 TO KM. | NHAI | N24001734 | 3-2022 | 8/2024 | N.A. | 7/2025 | 1335.45 |  | 1335.45 | 449.57 | 77
April 2025 |  |  | 1520 | 6L ACCESS CONTROL GREENFIELD HIGHWAY OF VILL- KHYAWARI TO VILL-LATIFPUR AT SAHARANPUR BYPASS FROM KM | NHAI | N24001735 | 3-2022 | 8/2024 | N.A. | 7/2025 | 1428.19 |  | 1428.19 | 510.01 | 83
April 2025 |  |  | 1521 | 6L ACCESS CONTROL GREENFIELD HIGHWAY OF VILL- KARAUNDA MAHAJAN TO VILL- KHYAWARI FROM KM. 56.500 TO K | NHAI | N24001736 | 1-2022 | 8/2024 | N.A. | 7/2025 | 1159.96 |  | 1159.96 | 515.16 | 98.69
April 2025 |  |  | 1522 | 4LPS OF MUZAFFARNAGAR TO MIRANPUR SECTION OF NH- 709AD, PKG-III | NHAI | N24001737 | 11-2021 | 4/2024 | N.A. | 4/2024 | 923.15 |  | 923.15 | 455.61 | 100
April 2025 |  |  | 1523 | 2LPS OF BIJNOR TO KOTAWALI SECTION OF NH-709AD, PKG-IV | NHAI | N24001738 | 9-2021 | 10/2023 | 12/2024 | 12/2024 | 300.79 |  | 300.79 | 122.56 | 74.53
April 2025 |  |  | 1524 | REHABILITATION and UPGRADATION FROM 2 LANE TO 4 LANE OF NH STRETCH UNDER BHARATMALA PARIYOJANA FOR U | NHAI | N24001739 | 10-2019 | 11/2023 | 12/2024 | 12/2024 | 1779.83 |  | 2200 | 1066 | 99.8
April 2025 |  |  | 1525 | 4L OF SHAMLI BYAPSS- SAHARANPUR FROM KM 92.2 TO KM 155.025 SECTION OF NH- 709B, PKG-II | NHAI | N24001744 | 5-2019 | 11/2022 | N.A. | 7/2025 | 779.17 |  | 779.17 | 64.1 | 96.45
April 2025 |  |  | 1526 | KANPUR LUCKNOW EXPRESSWAY PKG-1 CONSTRUCTION OF 6-LANE TO EIGHT LANE OF KANPUR LUCKNOW EXPRESSWAY (N | NHAI | N24001745 | 12-2021 | 7/2025 | 7/2025 | 7/2025 | 1972.1 |  | 1936 | 466.64 | 61.53
April 2025 |  |  | 1527 | 2-LANE EXISTING RAMPUR BYPASS OF RAMPUR TO BE DEVELOPED TO 4-LANE ON EPC MODE IN THE STATE OF UTTAR | NHAI | N24001746 | 3-2021 | 4/2024 | 6/2025 | 6/2025 | 364.47 |  | 364.47 | 202.47 | 90.72
April 2025 |  |  | 1528 | 4 LANING OF NAJIBABAD BYPASS OF NH-119 FROM KM. 105.423 TO KM. 118.373 (EXCLUDING 2.45 KM. OF NH-74 | NHAI | N24001753 | 2-2022 | 6/2024 | 4/2025 | 4/2025 | 570.98 | 578.02 | 578.02 | 400.1 | 95.1
April 2025 |  |  | 1529 | SPUR OF MEERUT-GARH- MUKTESHWAR SECTION(NH- 709A) CONNECTING NH-119 AND NH-58 BYPASSING MEERUT TOWN | NHAI | N24001754 | 1-2022 | 10/2024 | N.A. | 10/2024 | 953.79 |  | 953.79 | 384.66 | 66.29
April 2025 |  |  | 1530 | 4-LANING OF MEERUT NAJIBABAD SECTION FROM KM. 11.500 TO KM 39.250 AND KM 86.590 TO KM. 112.545.IN TH | NHAI | N24001755 | 10-2019 | 3/2023 | 12/2024 | 12/2024 | 1936.68 |  | 2458.03 | 1380.9 | 100
April 2025 |  |  | 1531 | 4 LANE CONNECTOR FROM DELHI MEERUT EXPRESSWAY KM 50.000 TO KM 8.520 OF NH 235 IN THE STATE OF UTTAR | NHAI | N24001772 | 8-2021 | 3/2024 | 12/2024 | 12/2024 | 1147.26 |  | 1147.26 | 81.34 | 60
April 2025 |  |  | 1532 | 4L BYPASSES FOR JAGATPUR, B4ABUGANJ, UNCHAHAR, ALAPUR BYPASS, AND SAI RIVER BRIDGE OF RAEBARELI- PRA | NHAI | N24001815 | 12-2022 | 11/2024 | N.A. | 11/2024 | 1699 | 1078 | 1699 | 64.39 | 100
April 2025 |  |  | 1533 | VARANASI RING ROAD (PKG-II) CONNECTING SANDAHA VILLAGE (KM 11.70 / NH-29) WITH REVASA VILLAGE (KM 81 | NHAI | N24001826 | 2-2019 | 2/2022 | 6/2025 | 12/2025 | 927.77 |  | 1603 | 1202.77 | 91.25
April 2025 |  |  | 1534 | SIX LANE ACCESS CONTROLLED OF DELHI SAHARANPUR HIGHWAY FROM DELHI UP BORDER TO EPE JUNCTION CH.14.75 | NHAI | N24001830 | 6-2020 | 11/2023 | 12/2024 | 12/2024 | 2002.79 |  | 2002.79 | 1989.85 | 99
April 2025 |  |  | 1535 | 4L FROM MATHURA BYPASS (START) AT EXISTING KM. 154.20 OF NH-44 TO GAJU VILLAGE AT KM 32.982 OF NH-53 | NHAI | N24001851 | 1-2022 | 3/2025 | N.A. | 3/2025 | 1738.2 |  | 1738.2 | 742.13 | 65
April 2025 |  |  | 1536 | 6L OF AGRA BYPASS (NORTHERN) CONNECTING KM. 174.500 OF NH-2 (NEW NH-19) TO KM. 141.000 OF YAMUNA EXP | NHAI | N24001852 | 10-2021 | 2/2025 | N.A. | 2/2025 | 957.62 |  | 957.62 | 832.8 | 86
April 2025 |  |  | 1537 | CONSTRUCTION OF LEFT OUT PORTION OF AGRA INNER RING ROAD CONNECTING VILLAGE DEORI TO NH-44 VILLAGE B | NHAI | N24001853 | 10-2021 | 9/2024 | 3/2025 | 3/2025 | 772.05 |  | 772.05 | 593.39 | 67.5
April 2025 |  |  | 1538 | CONSTRUCTION OF 4-LANE GREEN FIELD HIGHWAY FROM KM. 35.000 TO KM. 49.155 OF NH- 731A WITH PAVED SHOUL | MoRTH | N24001929 | 1-2022 | 10/2025 | N.A. | 10/2025 | 697.66 |  | 697.66 | 318.74 | 93
April 2025 |  |  | 1539 | BALANCE WORKS OF 4-LANNING OF RAMPUR-KATHGODAM SECTION OF NH-87 (NEW NH NO. 09) FROM KM. 0.000 (KM 1 | NHAI | N24001992 | 8-2022 | 2/2024 | 5/2025 | 5/2025 | 199.31 | 199.38 | 199.38 | 204.84 | 89.46
April 2025 |  |  | 1540 | CONSTRUCTION OF TWO LANE WITH PAVED SHOULDER HIGHWAY FROM DESIGN CH.0.000 TO CH.49.2OO OF NH- 731B ON | MoRTH | N24001996 | 3-2022 | 11/2025 | N.A. | 11/2025 | 640.18 | 602.76 | 602.76 | 468.29 | 77
April 2025 |  |  | 1541 | CONSTRUCTION OF SHOHRATGARH BYPASS ON NH- 730 UNDER EPC MODE IN THE STATE OF UTTAR PRADESH | MoRTH | N24001997 | 10-2022 | 5/2025 | N.A. | 8/2025 | 189.31 |  | 189.31 | 56.13 | 20
April 2025 |  |  | 1542 | IMPROVEMENT AND UPGRADATION TO TWO LANE WITH PAVED SHOULDER CONFIGURATION FROM EXISTING KM 90.00 TO | MoRTH | N24002015 | 11-2021 | 6/2025 | N.A. | 6/2025 | 403.36 | 328.49 | 403.36 | 130.45 | 63
April 2025 |  |  | 1543 | CONSTRUCTION OF PRATAPGARH BYPASS (EXTENSION) CONNECTING NH- 31 TO NH-330 | MoRTH | N24002016 | 10-2022 | 6/2025 | N.A. | 8/2025 | 225.17 |  | 225.17 | 95.68 | 54
April 2025 |  |  | 1544 | WIDENING TO FOUR LANE WITH PAVED SHOULDER FROM DESIGN KM.49.200 TO KM.89.285 OF NH-731B ON EPC MODE | MoRTH | N24002029 | 3-2022 | 1/2026 | N.A. | 1/2026 | 917.91 | 956.3 | 917.91 | 583.55 | 44
April 2025 |  |  | 1545 | CONSTRUCTION OF TWO LANE WITH PAVED SHOULDER FROM EXISTING KM.0.000 TO KM.55.610 (DESIGN KM. 0.000 T | MoRTH | N24002031 | 12-2021 | 2/2026 | N.A. | 2/2026 | 840.93 | 773.58 | 840.93 | 492.26 | 38
April 2025 |  |  | 1546 | CONSTRUCTION OF 4-LANE HIGHWAY WITH PAVED SHOULDERS FROM KM 49.155 TO KM 74.700 OF NH-731A ON HYBRID | MoRTH | N24002032 | 1-2022 | 1/2026 | N.A. | 1/2026 | 1156.72 |  | 1156.72 | 365.74 | 55
April 2025 |  |  | 1547 | DEVELOPMENT OF SIX-LANE ACCESS CONTROLLED HIGHWAY FROM GOGWAN JALALPUR (SHAMLI DISTRICT) TO RANIPUR | NHAI | N24002036 | 4-2022 | 5/2025 | N.A. | 5/2025 | 1843.59 |  | 1843.59 | 843.83 | 49
April 2025 |  |  | 1548 | GARHMUKTESHWAR (KM. 83.200 OF NH-24) TO MEERUT (KM. 9.860 OF NH-235) INCLUDING CONNECTOR TO NH-119 | NHAI | N24002073 | 10-2019 | 10/2023 | N.A. | 6/2025 | 2068.99 | 2171 | 2171 | 209.6 | 53.08
April 2025 |  |  | 1549 | WIDENING OF RAEBARELI TO PRAYAGRAJ SECTION FROM KM. 82.650 TO KM. 161.450 OF NH-30 AND LINK ROAD FRO | NHAI | N24002085 | 11-2023 | 3/2025 | N.A. | 3/2025 | 1470.93 |  | 1470.93 | 69.56 | 100
April 2025 |  |  | 1550 | CONSTRUCTION OF FOUR LANE HIGHWAY FORM GHAZIPUR BALLIA UP BIHAR STATE BORDER (GREENFIELD) SECTION OF | NHAI | N24002086 | 10-2022 | 7/2025 | N.A. | 7/2025 | 1706.47 |  | 1706.47 | 719.13 | 71.1
April 2025 |  |  | 1551 | CONSTRUCTION OF FOUR LANE HIGHWAY FROM GHAZIPUR BALLIA UP BIHAR STATE BORDER (GREENFIELD) SECTION OF | NHAI | N24002087 | 10-2022 | 10/2025 | N.A. | 10/2025 | 1493.14 |  | 1493.14 | 93.3 | 59.87
April 2025 |  |  | 1552 | CONSTRUCTION OF FOUR LANE HIGHWAY FROM GHAZIPUR BALLIA UP BIHAR STATE BORDER (GREENFIELD) SECTION OF | NHAI | N24002088 | 10-2022 | 8/2025 | N.A. | 8/2025 | 1493.5 |  | 1493.5 | 492.86 | 52
April 2025 |  |  | 1553 | CONSTRUCTION OF FOUR LANE HIGHWAY FROM GHAZIPUR BALLIA UP BIHAR STATE BORDER GREENFIELD SECTION OF N | NHAI | N24002089 | 10-2022 | 6/2025 | N.A. | 6/2025 | 617.87 |  | 617.88 | 106.2 | 67.6
April 2025 |  |  | 1554 | CONSTRUCTION OF FOUR-LANE ?WESTERN SIDE SPUR OF RAMPUR-RUDRAPUR SECTION CONNECTING NH-24 TO NH-87 BY | NHAI | N24002090 | 3-2021 | 11/2024 | 8/2025 | 8/2025 | 646.27 |  | 646.27 | 69.11 | 42.88
April 2025 |  |  | 1555 | IMPROVEMENT , UP-GRADATION OF NH-734 SECTION OF MORADABAD - THAKURDWARA - KASHIPUR: ?PACKAGE-I: MORA | NHAI | N24002093 | 10-2022 | 9/2025 | N.A. | 9/2025 | 1841.92 |  | 1841.92 | 384.31 | 48.05
April 2025 |  |  | 1556 | IMPROVEMENT AND UP- GRADATION OF EXISTING ROAD TO 4L PS FROM KM 123.650 TO 175.080, FROM START OF SHA | NHAI | N24002094 | 9-2022 | 11/2025 | N.A. | 11/2025 | 1212.26 |  | 1212.26 | 329.52 | 29.08
April 2025 |  |  | 1557 | FOUR LANING OF SONAULI GORAKHPUR SECTION OF NH 29E (NEW NH 24) FROM DESIGN CH. 0.000 TO DESIGN CH. 7 | NHAI | N24002095 | 12-2021 | 3/2025 | N.A. | 3/2025 | 2555.5 |  | 2555.5 | 951.47 | 56.97
April 2025 |  |  | 1558 | CONSTRUCTION OF 4 LANE GREEN FIELD NORTHERN EAST SIDE GORAKHPUR BYPASS (26.616 KMS) STARTING FROM NH | NHAI | N24002096 | 2-2023 | 1/2026 | N.A. | 1/2026 | 1973.98 |  | 1973.98 | 736.14 | 46.76
April 2025 |  |  | 1559 | STRENGTHENING OF EXISTING 4L AYODHYA BYPASS SECTION FROM DESIGN KM.121.600 TO KM. 144.020 OF NH 28 ( | NHAI | N24002097 | 2-2023 | 9/2025 | N.A. | 8/2025 | 526.45 |  | 526.45 | 228.37 | 83
April 2025 |  |  | 1560 | CONSTRUCTION OF RING ROAD AROUND KANPUR FROM KM.000 TO KM. 23.325 (CHACHENDI SACHENDI I TO MAHARAJPU | NHAI | N24002104 | 1-2023 | 6/2026 | N.A. | 6/2026 | 1754 |  | 1754 | 326.84 | 31.5
April 2025 |  |  | 1561 | CONSTRUCTION OF NEW 4 LANE PRAYAGRAJ SOUTHERN BYPASS (PHASE-I) FROM DESIGN KM 43+200 (AT MAHUWARI VI | NHAI | N24002105 | 8-2023 | 6/2026 | N.A. | 6/2026 | 1378.36 |  | 739 | 192.88 | 25.1
April 2025 |  |  | 1562 | CONSTRUCTION OF NEW 4 LANE PRAYAGRAJ SOUTHERN BYPASS FROM DESIGN KM 50.860 (NABABA URF NIBI KALA UPA | NHAI | N24002106 | 8-2023 | 3/2025 | N.A. | 6/2025 | 993.77 |  | 349.48 | 354.88 | 90.2
April 2025 |  |  | 1563 | CONSTRUCTION OF MARIAHU BYPASS WITH FOUR LANE PAVED SHOULDER CONFIGURATION (KM.53.540 TO KM.59.200) | MoRTH | N24002115 | 3-2023 | 8/2025 | N.A. | 2/2026 | 438.24 | 362.39 | 438.24 | 202.3 | 31
April 2025 |  |  | 1564 | REHABILITATION AND UPGRADATION FROM KM 51.600 TO KM 75.700 OF NH-321G (NUHKHAS TO ETAH SECTION) TO T | MoRTH | N24002116 | 1-2022 | 8/2025 | N.A. | 8/2025 | 343.54 |  | 343.54 | 66.01 | 34
April 2025 |  |  | 1565 | CONSTRUCTION OF JASRA BYPASS WITH FOUR LANE PAVED SHOULDER CONFIGURATION FROM KM. 379.670 ON NH-76 ( | MoRTH | N24002120 | 2-2023 | 9/2025 | N.A. | 9/2025 | 274.06 |  | 274.06 | 122.34 | 84
April 2025 |  |  | 1566 | IMPROVEMENT AND UP- GRADATION TO TWO LANE WITH PAVED SHOULDER CONFIGURATION FROM EXISTING KM. 420.00 | MoRTH | N24002121 | 1-2022 | 9/2025 | N.A. | 2/2026 | 509.65 |  | 509.65 | 174.67 | 21
April 2025 |  |  | 1567 | REHABILITATION AND UP- GRADATION FROM KM. 0.000 TO KM. 40.390 OF NH-730S (MAHARAJGANJ ? NICHLOUL ? TH | MoRTH | N24002134 | 3-2023 | 12/2025 | N.A. | 12/2025 | 809.25 |  | 809.25 | 243.96 | 25
April 2025 |  |  | 1568 | CONSTRUCTION OF FOUR LANE HIGHWAY WITH PAVED SHOULDER FROM KM.74.700 TO KM.112.950 OF NH-731A (I/C Y | MoRTH | N24002138 | 3-2022 | 6/2026 | N.A. | 6/2026 | 1141.67 |  | 1141.67 | 386.39 | 40
April 2025 |  |  | 1569 | CONSTRUCTION OF BALRAMPUR BYPASS WITH 2L FLEXIBLE PAVEMENT CONFIGURATION FROM KM.223.000 OF NH-330 T | MoRTH | N24002150 | 12-2022 | 2/2026 | N.A. | 2/2026 | 515.69 |  | 515.69 | 171.73 | 28
April 2025 |  |  | 1570 | WIDENING TO 4L RIGID PAVEMENT CONFIGURATION FROM KM 90.00 TO KM 100.800 OF NH-96 (KM 42.O TO KM 53.3 | MoRTH | N24002199 | 12-2022 | 11/2026 | N.A. | 11/2026 | 309.63 |  | 309.63 | 6.79 | 15
April 2025 |  |  | 1571 | IMPROVEMENT AND UP- GRADATION TO TWO LANE WITH PAVED SHOULDER/FOUR LANE CONFIGURATION FROM EXISTING K | MoRTH | N24002201 | 1-2022 | 5/2027 | N.A. | 5/2027 | 974.19 |  | 974.19 | 586.49 | 6
April 2025 |  |  | 1572 | REHABILITATION AND UPGRADATION TO FOUR LANE ROAD FROM KM 70.500 TO KM 78.600 OF NH-92 UNDER EPC MODE | MoRTH | N24002211 | 1-2022 | 1/2027 | N.A. | 1/2027 | 296.02 |  | 296.02 | 27.68 | -
April 2025 |  |  | 1573 | WIDENING AND STRENGTHENING FROM DESIGN KM. 67.280 TO KM. 88.622 OF NH-727A (SALEMPUR- MAIRWA ROAD) TO | MoRTH | N24002212 | 3-2023 | 7/2026 | N.A. | 7/2026 | 371.89 |  | 371.89 | 126.17 | -
April 2025 |  |  | 1574 | REHABILITATION and UP- GRADATION TO 2L+PS FROM KM. 0.0 TO KM. 7.80 AND KM. 35.400 TO KM. 52.345 (DESI | MoRTH | N24002213 | 3-2023 | 7/2026 | N.A. | 7/2026 | 701.02 |  | 701.02 | 242.64 | -
April 2025 |  |  | 1575 | CONSTRUCTION OF AMETHI BYPASS (PART-II) AT KM.30.050 OF NH-931 UNDER EPC MODE IN THE STATE OF UTTAR | MoRTH | N24002214 | 12-2022 | 2/2027 | N.A. | 2/2027 | 283.86 |  | 283.86 | 58.89 | -
April 2025 |  |  | 1576 | WIDENING TO 4L FROM KM.108.50 TO 139.00 OF NH-135A PKG-II (JAUNPUR TO AKBARPUR SECTION) ON HAM IN TH | MoRTH | N24002234 | 3-2023 | 3/2027 | N.A. | 3/2027 | 1511.57 |  | 1511.57 | 124.06 | -
April 2025 |  |  | 1577 | CONSTRUCTION OF RAEBARELI RING ROAD (PHASE-2) WITH FOUR LANE CONFIGURATION FOR RAEBARELI CITY IN THE | MoRTH | N24002235 | 3-2022 | 5/2027 | N.A. | 5/2027 | 1273.72 |  | 1273.72 | 330.12 | -
April 2025 |  | URBAN DEVELOPMENT | 1578 | KANPUR METRO RAIL PROJECT | LMRCL | N28000144 | 5-2019 | 3/2024 | N.A. | 12/2026 | 11076.48 |  | 11076.48 | 8651.58 | 72
April 2025 |  | URBAN DEVELOPMENT | 1579 | AGRA METRO RAIL PROJECT | LMRCL | N28000145 | 5-2019 | 3/2024 | N.A. | 12/2026 | 8379.62 |  | 8379.62 | 4902.53 | 53.4
April 2025 |  | URBAN DEVELOPMENT | 1580 | INTERCEPTION AND DIVERSION WORKS AND STP AT MUZAFFARNAGAR UTTAR PRADESH | UPJalNigam | N30000021 | 1-2019 | 12/2021 | 1/2020 | 3/2025 | 231.79 | 234.03 | 234.03 | 141.79 | 100
April 2025 |  |  | 1581 | SEWERAGE SCHEME INTERCEPTION AND DIVERSION WITH STP WORKS AT MEERUT UTTAR PRADESH | UPJalNigam | N30000024 | 2-2019 | 6/2022 | N.A. | 12/2025 | 681.78 |  | 690.71 | 13.34 | 22
April 2025 |  | CIVIL AVIATION | 1582 | CONSTRUCTION OF DOMESTIC PASSENGER TERMINAL BUILDING AT DEHRADUN AIRPORT, DEHRADUN | AAI | N04000085 | 7-2018 | 9/2020 | 9/2024 | 9/2024 | 456.86 | 500 | 500 | 483.86 | 100
April 2025 |  | POWER | 1583 | TEHRI PUMPED STORAGE PLANT(1000MW) | THDCIL | N18000010 | 7-2006 | 7/2010 | 6/2022 | 9/2025 | 1657 | 4825.6 | 7877.81 | 7854.76 | 98.1
April 2025 |  | POWER | 1584 | TAPOVAN-VISHNUGAD HEP | 4X130MW | NTPC | 11-2006 | 3/2013 | 12/2021 | 4/2029 | 2978.48 |  | 10907 | 6736.09 | 72.4
April 2025 |  | POWER | 1585 | VISHNUGAD PIPALKOTI HYDRO ELECTRIC PROJECT | THDCIL | N18000042 | 8-2008 | 6/2013 | N.A. | 3/2027 | 2491.58 | 3860.35 | 6630.6 | 4652.11 | 70
April 2025 |  | POWER | 1586 | LATA-TAPOVAN HYDRO ELECTRIC POWER PROJECT 3X57 MW | NTPC | N18000142 | 7-2012 | 8/2017 | N.A. | 8/2017 | 1527 |  | 1527 | 149.93 | -
April 2025 |  | RAILWAYS | 1587 | RISHIKESH - KARNAPRAYAG NEW LINE | RVNL | N22000406 | 4-2011 | 12/2025 | N.A. | 3/2025 | 38953.15 |  | 24659 | 18820.04 | -
April 2025 |  | RAILWAYS | 1588 | 4-LANING OF KASHIPUR- SITARGANJ SECTION | AMR | N24000465 | 11-2012 | 8/2016 | N.A. | 8/2016 | 605.84 |  | 605.84 | 0 | -
April 2025 |  |  | 1589 | CONSTRUCTION AND UPGRADATION OF EXISTING ROAD TO 2 LANE WITH PAVED SHOULDER FROM KM 368.00 TO KM 399 | NHIDCL | N24000741 | 3-2018 | 11/2020 | 3/2024 | 3/2024 | 274.31 |  | 274.31 | 505.22 | 97.31
April 2025 |  |  | 1590 | 2 LANE WITH PAVED SHOULDER FROM KM 399.00 TO KM 430.00 OF KARANPARYAG TO CHAMOLI UNDER CHARDHAM PARI | NHIDCL | N24000742 | 3-2018 | 11/2020 | N.A. | 3/2024 | 403.36 |  | 403.36 | 678.04 | 98.93
April 2025 |  |  | 1591 | 2 LANE WITH PAVED SHOULDER FROM KM 430.00 TO KM 468.00 OF CHAMOLI TO PAINI UNDER CHARDHAM PARIYOJNA | NHIDCL | N24000743 | 3-2018 | 11/2020 | N.A. | 3/2024 | 417.24 |  | 417.24 | 688.4 | 99.88
April 2025 |  |  | 1592 | RECONSTRUCTION WITH GEOMETRIC IMPROVEMENT OF EXISTING 2 LANE/INTERMEDIATE LANE TO 2LANE WITH PAVED S | MoRTH | N24000772 | 12-2017 | 12/2019 | N.A. | 12/2019 | 257.34 |  | 257.34 | 232.69 | 100
April 2025 |  |  | 1593 | RECONSTRUCTION WITH GEOMETRIC IMPROVEMENT OF EXISTING 2 LANE/INTERMEDIATE LANE TO 2LANE WITH PAVED S | MoRTH | N24000773 | 12-2017 | 12/2019 | N.A. | 12/2019 | 200.34 | 253.43 | 200.34 | 227.98 | 100
April 2025 |  |  | 1594 | WIDENING OF EXISTING SINGLE LANE ROAD TO TWO LANE WITH PAVED SHOULDERS CONFIGURATION FROM KM. 235.00 | MoRTH | N24000774 | 12-2017 | 12/2019 | N.A. | 12/2019 | 248.22 |  | 248.22 | 236.8 | 100
April 2025 |  |  | 1595 | RECONSTRUCTION WITH GEOMETRIC IMPROVEMENT OF EXISTING 2 LANE/INTERMEDIATE LANE TO 2LANE WITH PAVED S | MoRTH | N24000775 | 6-2017 | 6/2019 | 3/2023 | 3/2023 | 282.08 |  | 282.08 | 234.97 | 100
April 2025 |  |  | 1596 | RECONSTRUCTION WITH GEOMETIC IMPROVEMENT OF EXISTING TWO LANE TO 2- LANE WITH PAVED SHOULDERS CONFIG | MoRTH | N24000776 | 11-2017 | 11/2019 | N.A. | 11/2019 | 232.81 |  | 232.81 | 201.58 | 100
April 2025 |  |  | 1597 | RECONSTRUCTION WITH GEOMETIC IMPROVEMENT OF SINGLE LANE TO 2- LANE WITH PAVED SHOULDER CONFIGURATION | MoRTH | N24000777 | 11-2017 | 11/2019 | N.A. | 11/2019 | 283.51 |  | 283.51 | 278.51 | 100
April 2025 |  |  | 1598 | RECONSTRUCTION WITH GEOMETRIC IMPROVEMENT OF EXISTING SINGLE/INTERMEDIATE LANE TO 2LANE WITH PAVED S | MoRTH | N24000778 | 11-2017 | 11/2019 | N.A. | 11/2019 | 266.52 |  | 266.52 | 250.34 | 100
April 2025 |  |  | 1599 | RECONSTRUCTION WITH GEOMETRIC IMPROVEMENT OF EXISTING SINGLE/INTERMEDIATE LANE TO 2 LANE WITH EAR | MoRTH | N24000779 | 2-2018 | 2/2020 | 3/2023 | 3/2023 | 418.88 |  | 418.88 | 339.71 | 94
April 2025 |  |  | 1600 | REHABILITATION AND UP GRADATION OF 2 LANE/ 2 LANE WITH PAVED SHOULDER FROM EXISTING KM. 172.900 TO K | MoRTH | N24000780 | 2-2018 | (4/2023) | {4/2023} |  | 293.68 |  | 293.68 | 244.25 | 100
April 2025 |  |  | 1601 | CONSTRUCTION OF KUND BYPASS FROM EXISTING KM 33+130 TO KM 41+260 (EXISTING LENGTH: 8.130 KM); DESIGN | MoRTH | N24000781 | 5-2018 | 5/2020 | 12/2023 | 12/2023 | 248 |  | 248 | 120.5 | 65.56
April 2025 |  |  | 1602 | REHABILITATION AND UPGRADATION OF 2 LANE WITH PAVED SHOULDER FROM EXISTING KM. 195.175 TO KM. 220.00 | MoRTH | N24000782 | 3-2018 | (N.A.) | {} |  | 460.73 |  | 461 | 0 | -
April 2025 |  |  | 1603 | CONSTRUCTION OF 4.5 KM LONG SILKYARA TUNNEL BETWEEN KM 25.40 TO 50.25 KM | TUNNEL WORK | NHIDCL | 3-2018 | 7/2022 | N.A. | 9/2026 | 1383.78 |  | 1383.78 | 1391 | 63.61
April 2025 |  |  | 1604 | RECONSTRUCTION WITH GEOMETRIC IMPROVMENT OF EXISTING INTERMEDIATE LANE TO 2 LANE WITH PAVED SHOULDER | MoRTH | N24001130 | 8-2016 | 12/2017 | N.A. | 12/2017 | 234.88 | 273.49 | 234.88 | 237.19 | 100
April 2025 |  |  | 1605 | 6L ACCESS-CONTROLLED HIGHWAY OF DAAT KALI TUNNEL - DEHRADUN OF GANESHPUR ? DEHRADUN SECTION FROM KM. | NHAI | N24001525 | 3-2021 | 3/2024 | 5/2025 | 5/2025 | 169.08 |  | 169.08 | 105.77 | 99.99
April 2025 |  |  | 1606 | UPGRADATION AND 4L OF HARIDWAR BYPASS FROM KM 0.000 (KM 188.100 OF NH-58) TO KM. 15.100 (KM 5.100 OF | NHAI | N24001526 | 8-2021 | 10/2024 | 8/2025 | 8/2025 | 1377.79 | 1384.11 | 1377.79 | 679.1 | 53.05
April 2025 |  |  | 1607 | 4L MEDINIPUR TO BALLUPUR FROM KM. 458.65 TO KM. 487.65 OF NH-07(PKG-2) | NHAI | N24001553 | 3-2022 | 2/2025 | 7/2025 | 7/2025 | 1092.9 | 1092.9 | 1092.9 | 463.92 | 81.2
April 2025 |  |  | 1608 | 4L POANTA SAHEB?MEDNIPUR FROM KM. 435.65 TO KM. 458.65 OF NH-07(PKG-1) | NHAI | N24001990 | 6-2022 | 5/2025 | 6/2025 | 6/2025 | 524.54 | 683.26 | 683.26 | 91.94 | 73.37
April 2025 |  |  | 1609 | ACCESS ROAD/BRIDGE CONNECTIVITY FROM NH-09 AT KM.40 NEAR JAGBUDA BRIDGE (INDIA) TO BOUNDARY PILLAR | NHAI | N24001991 | 5-2022 | 9/2024 | 11/2026 | 11/2026 | 314.31 |  | 314.31 | 229.7 | 68.16
April 2025 |  |  | 1610 | CONSTRUCTION FOR MITIGATION MEASURES KM 368.00-UTTARAKHAND-TO KM 433.00 ON NH-07-PKG-1 | NHIDCL | N24002163 | 12-2023 | 12/2025 | N.A. | 12/2025 | 216.88 |  | 216.88 | 76.07 | 73
April 2025 |  |  | 1611 | CONSTRUCTION FOR MITIGATION MEASURES KM 450.00-UTTARAKHAND-TO KM 468.00 ON NH-07-PKG-3 | NHIDCL | N24002164 | 12-2023 | 12/2025 | N.A. | 12/2025 | 250.33 |  | 250.33 | 57.1 | 48
April 2025 |  |  | 1612 | CONSTRUCTION FOR MITIGATION MEASURES PKG-2 | NHIDCL | N24002206 | 12-2023 | 6/2026 | N.A. | 6/2026 | 259.64 |  | 259.64 | 4.16 | 20
April 2025 |  | CIVIL AVIATION | 1613 | CONSTRUCTION OF ATC TOWER AND TECHNICAL BLOCK AT NSCBI AIRPORT KOLKATA | AAI | N04000080 | 1-2016 | 3/2020 | 12/2023 | 12/2023 | 458 |  | 458 | 251.64 | 100
April 2025 |  | CIVIL AVIATION | 1614 | AIRSIDE CAPACITY ENHANCEMENT OF NSBI AIRPORT, KOLKATA | AAI | N04000081 | 1-2019 | 11/2021 | 5/2023 | 5/2023 | 389.71 |  | 397 | 396.61 | 100
April 2025 |  |  | 1615 | NSCBI AIRPORT KOLKATA: RE- CONSTRUCTION OF RIGID POSITIONS OF SECONDARY RUNWAY, 'K' AND 'A' TAXIWAY | AAI | N04000109 | 4-2023 | 10/2025 | N.A. | 10/2025 | 328.3 |  | 328.3 | 79.39 | 36
April 2025 |  |  | 1616 | BAGDOGRA AIRPORT: DEVELOPMENT OF NEW CIVIL ENCLAVE AT BAGDOGRA AIRPORT. SUB-HEAD : CONSTRUCTION OF N | AAI | N04000115 | 8-2024 | 3/2027 | N.A. | 3/2027 | 1549 |  | 1549 | 181.32 | 8
April 2025 |  |  | 1617 | RANIGANJ MASTER PLAN | ECL | N06000163 | 8-2009 | 8/2019 | N.A. | 8/2019 | 2661.73 |  | 5146.48 | 779.5 | 42
April 2025 |  |  | 1618 | SIDULI MINE (OC AND UG) | ECL | N06000165 | 5-2018 | 3/2027 | N.A. | 3/2027 | 535.18 |  | 535.17 | 4.75 | 14
April 2025 |  |  | 1619 | NAKRAKONDA KUMARDIH B OCP | ECL | N06000170 | 8-2018 | 3/2029 | N.A. | 3/2029 | 502.68 |  | 502.67 | 70.02 | 25.5
April 2025 |  |  | 1620 | SHYAMSUNDARPUR UG INCLUDING SAPI UNIT | ECL | N06000191 | 4-2020 | 3/2026 | 3/2026 | 3/2026 | 483.65 |  | 483.65 | 54.87 | 12
April 2025 |  |  | 1621 | 2.0 MTPA BHOJUDIH NLW WASHERY | BCCL | N06000195 | 12-2015 | 9/2020 | N.A. | 5/2025 | 384.57 |  | 384.57 | 347.98 | 97
April 2025 |  |  | 1622 | SONEPUR BAZARI EXPANSION OC | ECL | N06000220 | 7-2021 | 3/2029 | N.A. | 3/2029 | 5365.88 | 5366 | 5365.88 | 550.61 | 17
April 2025 |  |  | 1623 | EXPANSION PR OF JHANJRA UG | 5.00 MTY | ECL | 4-2020 | 3/2029 | N.A. | 3/2029 | 1210.12 |  | 1210.12 | 478.77 | 38
April 2025 |  |  | 1624 | MOHANPUR EXPANSION OC PHASE II | ECL | N06000236 | 11-2020 | 3/2026 | N.A. | 3/2026 | 888.99 |  | 888.99 | 73.31 | 30
April 2025 |  |  | 1625 | BONJEMEHARI EXPANSION OCP | ECL | N06000244 | 8-2021 | 3/2026 | 3/2026 | 3/2026 | 570.12 |  | 570.11 | 81.09 | 16
April 2025 |  |  | 1626 | ITAPARA OC | ECL | N06000272 | 12-2023 | 3/2030 | N.A. | 3/2030 | 929.1 |  | 929.1 | 63.74 | 7
April 2025 |  |  | 1627 | UCE OF TILABONI UG | ECL | N06000276 | 1-2023 | 3/2029 | N.A. | 3/2029 | 749.07 |  | 749.07 | 51.59 | 10
April 2025 |  |  | 1628 | UCE OF PARASEA BELBAID REORGANISATION UG | ECL | N06000277 | 1-2023 | 3/2029 | 3/2028 | 3/2028 | 389.1 |  | 389.1 | 130.56 | 16
April 2025 |  |  | 1629 | PARASCOLE JAMBAD OCP | ECL | N06000281 | 11-2024 | 3/2037 | N.A. | 3/2037 | 1193.55 |  | 1193.55 | 0 | -
April 2025 |  | DEPARTMENT OF HIGHER EDUCATION | 1630 | CONSTRUCTION OF TWO NOS GIRLS HOSTELS AND ONE NO BOYS HOSTEL OF 500 CAPACITY EACH G PLUS 8 STOREYED | CPWD EDUCATION | N28000146 | 3-2020 | 6/2020 | N.A. | 5/2024 | 193.83 |  | 193.83 | 207.35 | -
April 2025 |  | HOME AFFAIRS | 1631 | NSG AT KOLKATA | CPWD FOR MHA | N28000104 | 10-2014 | 4/2018 | N.A. | 8/2025 | 162.88 | 210.83 | 210.83 | 193.91 | 92.5
April 2025 |  | MINES | 1632 | CONSTRUCTION OF BASEMENTG FLOOR10 STORIES BUILDING FOR THE STATE OF THE ART, DG, GSI AT SECTOR-V, SA | CPWD | N10000015 | 4-2019 | 4/2022 | N.A. | 8/2026 | 255.37 |  | 255.37 | 68.66 | 36
April 2025 |  | PETROLEUM | 1633 | DURGAPUR-HALDIA PIPELINE PROJECT | GAIL | N16000275 | 3-2017 | 12/2020 | 12/2025 | 12/2025 | 1740 | 2433.15 | 2433.15 | 2182.2 | 89.5
April 2025 |  | PETROLEUM | 1634 | CITY GAS DISTRIBUTION IN WEST BENGAL | HPCL | N16000392 | 3-2019 | 3/2031 | 3/2031 | 3/2031 | 5830.2 |  | 5830.2 | 875.27 | 32.52
April 2025 |  | PETROLEUM | 1635 | HALDIA PANAGARH PIPELINE PROJECT | HPCL | N16000478 | 11-2022 | 11/2025 | N.A. | 11/2025 | 1010 |  | 1010 | 526.55 | 76.78
April 2025 |  | PETROLEUM | 1636 | CGD PROJECT AT EAST MEDNIPORE, WEST MEDNIPORE AND JHARGRAM DISTRICTS | IOCL | N16000491 | 3-2022 | 3/2030 | N.A. | 6/2031 | 609 |  | 609 | 60.43 | 2.1
April 2025 |  | PETROLEUM | 1637 | CGD PROJECT IN WEST BENGAL 11TH ROUND | HPCL | N16000498 | 6-2022 | 6/2030 | N.A. | 6/2030 | 2628 |  | 2628 | 308.32 | 21.7
April 2025 |  | PETROLEUM | 1638 | CITY GAS DISTRIBUTION PROJECTS AT ALIPURDUAR AND COOCH BEHAR | BPCL | N16000522 | 12-2022 | 3/2030 | N.A. | 3/2030 | 1017 |  | 1017 | 158.78 | 29.8
April 2025 |  | POWER | 1639 | RAMMAM-III HEPP (3X40 MW) | NTPC | N18000178 | 9-2014 | 9/2019 | 12/2024 | 3/2029 | 1381.84 |  | 1803 | 1302.76 | 43.68
April 2025 |  |  | 1640 | TARAKESWAR - BISHNUPUR NEW BG LINE (NL), ER | ER | 220100272 | 4-2000 | 3/2019 | 2/2026 | 2/2026 | 1188.91 |  | 2582.49 | 1247.41 | 75
April 2025 |  |  | 1641 | NEW WORK FOR CONSTRUCTION OF METRO RAILWAY FROM NOAPARA- BARASAI VIA BIMANBANDER | MTP | KOMRCL | 4-2010 | 8/2026 | N.A. | 3/2016 | 4829.6 |  | 2397.72 | 197.2 | 17
April 2025 |  |  | 1642 | NEW WORK FOR CONSTRUCTION OF METRO RAILWAY FROM BARANAGAR TO BARRACKPORE AND DAKSHINESHWAR (MTP) | RVNL | N22000109 | 4-2010 | 12/2026 | N.A. | 12/2025 | 2298.42 |  | 2733.86 | 392.98 | -
April 2025 |  |  | 1643 | NEW WORK FOR CONSTRUCTION OF METRO RAILWAY FROM NSCB AIRPORT TO NEW GARIA VIA RAJARHAT | MTP | RVNL | 4-2010 | 12/2025 | N.A. | 3/2026 | 8964.35 |  | 8964.35 | 7387.4 | -
April 2025 |  |  | 1644 | NEW WORK FOR CONSTRUCTION OF METRO RAILWAY FROM JOKA TO BINOY BADAL DINESH BAGH. | RVNL | N22000111 | 4-2010 | 12/2026 | N.A. | 12/2026 | 4834.54 |  | 4834.54 | 3918.86 | -
April 2025 |  |  | 1645 | PURULIA TO KOTSHILA DOUBLING (39.1 KM) | SER | N22000510 | 4-2018 | 12/2024 | N.A. | 3/2025 | 393.83 |  | 393.83 | 302.8 | 100
April 2025 |  |  | 1646 | AZIMGANJ-MURSHIDABAD (JIYAGANJ) INCL. RLY. BRIDGE OVER RIVER BHAGIRATHI | ER | N22000609 | 10-2001 | 2/2024 | N.A. | 2/2024 | 164.33 |  | 187.05 | 160.82 | 100
April 2025 |  |  | 1647 | NAHATI - RANAGHAT 3RD LINE (MM OF KALINARAYANPUR - KRISHNANAGAR) | ER | N22000624 | 7-2015 | 3/2025 | N.A. | 3/2025 | 1000 |  | 283.54 | 165.74 | 44
April 2025 |  |  | 1648 | EAST WEST METRO CORRIDOR KOLKATA | KOMRCL | N22000628 | 2-2009 | 9/2016 | N.A. | 9/2016 | 4874.58 | 8575 | 10442.41 | 0 | -
April 2025 |  |  | 1649 | KALIPAHARI - BAKHTARNAGAR 5TH LINE (17.61 KM) | ER | N22000630 | 4-2024 | 6/2027 | N.A. | 6/2027 | 350.46 |  | 350.46 | 0 | -
April 2025 |  |  | 1650 | SITARAMPUR BYE - PASS LINE | 6.59 KM | ER | 2-2023 | 3/2027 | N.A. | 3/2027 | 461.64 |  | 461.64 | 24.54 | -
April 2025 |  |  | 1651 | 4 LANING OF NH-31D FROM GHOSHPUKUR - SALSALABARI ( KM 0.00 TO KM . 83.785) | NHAI | N24000463 | 12-2015 | 6/2018 | 5/2024 | 8/2023 | 1083 | 1414.01 | 1414.01 | 1080.05 | 100
April 2025 |  |  | 1652 | SIX-LANING OF BARWA ADDA- PANAGARH | NHAI | N24000515 | 4-2014 | 9/2016 | N.A. | 3/2025 | 1665 |  | 4972.99 | 4972.99 | 100
April 2025 |  |  | 1653 | REHABILITATION AND UP GRADATION OF EXISTING ROAD TO 2-LANE WITH PAVED SHOULDER CONFIGURATION IN PURU | NHAI | N24000788 | 3-2018 | 9/2022 | 12/2022 | 12/2025 | 841.57 | 708.3 | 708.3 | 11121.3 | 95.78
April 2025 |  |  | 1654 | CONSTRUCTION OF NEW ROAD AT THE MISSING LINK PORTION OF NH-81 ALONG THE APPROVED ALIGNMENT BETWEEN H | MoRTH | N24000874 | 3-2016 | 11/2018 | 12/2023 | 7/2025 | 271.17 | 291.2 | 291.2 | 199.72 | 82.34
April 2025 |  |  | 1655 | UPGRADATION OF NH-81 WITH A MINIMUM OF 2-LANE WITH PAVED SHOULDER CONFIGURATION STARTING FROM KM 19. | MoRTH | N24000880 | 2-2018 | 9/2020 | 1/2024 | 2/2025 | 426.18 | 426.18 | 426.18 | 364.92 | 100
April 2025 |  |  | 1656 | SIX LANE OF PALSIT TO DANKUNI SECTION FROM 588.870 TO KM. 652.700 | NHAI | N24001747 | 3-2020 | 9/2024 | N.A. | 9/2024 | 2193.23 | 2314 | 2314 | 2085 | 97.5
April 2025 |  |  | 1657 | SIX LANING OF NATIONAL CORRIDOR NH19 FROM PANAGARH TO PALSIT IN THE STATE OF WEST BENGAL UNDER BHARA | NHAI | N24001748 | 3-2021 | 9/2024 | N.A. | 9/2025 | 2200.93 |  | 2621.41 | 2621.41 | 96.83
April 2025 |  |  | 1658 | FOUR LANING OF PURULIYA BYPASS SECTION OF NH 32 IN THE STATE OF WEST BENGAL ON EPC MODE | NHAI | N24001749 | 8-2021 | 8/2023 | N.A. | 6/2025 | 557.55 |  | 567.31 | 473.25 | 91.41
April 2025 |  |  | 1659 | CONSTRUCTION OF NEW 4 LANE BRIDGE OVER RIVER GANGA AT DOWNSTREAM OF FARAKKA BARRAGE INCLUDING APPROA | NHAI | N24001750 | 8-2018 | 12/2021 | N.A. | 7/2025 | 622.04 |  | 622.04 | 565.4 | 91.34
April 2025 |  |  | 1660 | DEVELOPMENT TO 4/6-LANNING OF NH-31 (NEW NH-10) WITH BOTH SIDE SERVICE ROADS FROM KM 569.258 TO KM 5 | MoRTH | N24001850 | 3-2022 | 9/2025 | 9/2025 | 9/2025 | 995.04 | 995.04 | 995.04 | 383.34 | 47.9
April 2025 |  |  | 1661 | CONSTRUCTION OR 4 LANE RANIGANJ BYPASS OF LENGTH 5 261 KM ON NH 60 NEW NH 14 FROM KM 273 00 OF NH | MoRTH | N24002184 | 3-2023 | 3/2026 | 3/2026 | 3/2026 | 410.83 |  | 410.83 | 152.32 | 28.99
April 2025 |  |  | 1662 | CONSTRUCTION OF ROB AND ITS APPROACHES IN LIEU OF LEVEL CROSSING NO 10 B T AT KM 307 050 OF NH 60 B | MoRTH | N24002191 | 3-2016 | 8/2025 | N.A. | 8/2025 | 155.87 |  | 155.87 | 21.68 | 9.49
April 2025 |  | STEEL | 1663 | REBUILDING OF COKE OVEN BATTERY NO.4 OF DURGAPUR STEEL PLANT | SAIL | N12000132 | 11-2023 | 12/2026 | N.A. | 12/2026 | 916.78 |  | 916.78 | 86.34 | 4.85
April 2025 |  | STEEL | 1664 | INSTALLATION OF NEW BAR MILL AT DURGAPUR STEEL PLANT | SAIL | N12000138 | 9-2024 | 6/2027 | N.A. | 6/2027 | 2115.44 |  | 2115.44 | 61.67 | 4.5
April 2025 |  | STEEL | 1665 | UP-GRADATION OF BLAST FURNACE NO. 3 AT DURGAPUR STEEL PLANT | SAIL | N12000139 | 9-2024 | 6/2026 | N.A. | 6/2026 | 758.09 |  | 758.09 | 0 | 1.8
April 2025 |  | STEEL | 1666 | REVAMPING OF AIR POLLUTION CONTROL SYSTEMS OF SP-1 AT DURGAPUR STEEL PLANT | SAIL | N12000140 | 11-2024 | 5/2026 | N.A. | 5/2026 | 196.4 |  | 196.4 | 0.19 | 0.8
April 2025 |  | STEEL | 1667 | THIRD LADLE FURNACE IN SECONDARY REFINERY UNIT AT IISCO STEEL PLANT | SAIL | N12000141 | 11-2024 | 7/2026 | N.A. | 7/2026 | 227.96 |  | 227.96 | 2.58 | 18.98
April 2025 |  | STEEL | 1668 | INTERCEPTION AND DIVERSION WITH STP AT MAHESHTALA | KMDA | N30000032 | 5-2018 | 2/2022 | N.A. | 8/2025 | 198.43 | 224.69 | 286.97 | 75.88 | 95
April 2025 |  | STEEL | 1669 | INTERCEPTION DIVERSION TREATMENT WORKS AT TOLLYS NULLAH ADI GANGA | KMDA | N30000034 | 8-2017 | 9/2022 | 1/2023 | 12/2026 | 307.12 |  | 653.67 | 0 | -
April 2025 |  |  | 1670 | INTERCEPTION AND DIVERSION WITH STP AT HUGHLY- CHINSURAH | KMDA | N30000042 | 5-2018 | 2/2022 | 9/2020 | 3/2025 | 160 | 154.73 | 154.73 | 87.35 | 90
May 2025 | ANDAMAN AND NICOBAR ISLANDS | CIVIL AVIATION | 1 | CONSTRUCTION OF NEW INTEGRATED TERMINAL BUILDING AT VSI AIRPORT, PORTBLAIR | AAI | N04000073 | 10-2013 | 9/2018 | Jun-2023 | 6/2023 | 417.23 | 707.73 | 707.73 | 698.8 | 100
May 2025 | ANDAMAN AND NICOBAR ISLANDS | RAILWAYS | 2 | LUDHIANA KILA RAIPUR (19 KMS) WITH FREIGHT LINE AT GILL STATION ON LDH- JHL SECTION | NR | N22000584 | 3-2019 | 3/2025 | Dec-2025 | 1/2026 | 235.72 |  | 235.72 | 55.79 | 55
May 2025 | ANDAMAN AND NICOBAR ISLANDS | ROAD TRANSPORT AND HIGHWAYS | 3 | 2 LANE WITH HARD SHOLDER , REHABILITATION AND UP GRADATION OF SECTION FROM KM 242.0 TO KM 298.0 OF N | NHIDCL | N24000745 | 3-2017 | 12/2019 | Mar-2023 | 6/2025 | 409.85 |  | 409.85 | 214.23 | 95.1
May 2025 | ANDAMAN AND NICOBAR ISLANDS | ROAD TRANSPORT AND HIGHWAYS | 4 | REHABILITATION AND UP GRADATION OF SECTION FROM KM 206.00 TO KM 242.00 (NIMBUTALA TO AUSTIN CREEK) O | NHIDCL | N24000749 | 3-2018 | 9/2020 | Nov-2022 | 7/2025 | 234.27 |  | 234.27 | 126.5 | 82.97
May 2025 | ANDAMAN AND NICOBAR ISLANDS | ROAD TRANSPORT AND HIGHWAYS | 5 | Rehabilitation and up gradation to 2 lane with paved shoulder configuration from existing km. 122.00 | MoRTH | N24000820 | 11-2017 | 11/2019 | N.A. | 11/2019 | 237.8 |  | 238 | 222.13 | 98
May 2025 | ANDAMAN AND NICOBAR ISLANDS | ROAD TRANSPORT AND HIGHWAYS | 6 | RECONSTRUCTION WITH GEOMETRIC IMPROVEMENT OF EXISTING 2 LANE/INTERMEDIATE LANE TO 2LANE WITH PAVED S | MoRTH | N24000821 | 11-2017 | 11/2019 | N.A. | 11/2019 | 257.34 |  | 238 | 214.9 | 100
May 2025 | ANDAMAN AND NICOBAR ISLANDS | ROAD TRANSPORT AND HIGHWAYS | 7 | AJANTHA TO BULDHANA | MoRTH | N24001008 | 2-2017 | 7/2019 | N.A. | 12/2023 | 401 | 401 | 401 | 260.08 | 97
May 2025 | ANDAMAN AND NICOBAR ISLANDS | ROAD TRANSPORT AND HIGHWAYS | 8 | MAJOR BRIDGE OVER MIDDLE STRAIT CREEK | NHIDCL | N24002207 | 12-2024 | 2/2026 | N.A. | 2/2026 | 371.8 | 207.99 | 207.99 | 0 | 4.68
May 2025 | ANDAMAN AND NICOBAR ISLANDS | ROAD TRANSPORT AND HIGHWAYS | 9 | PACKAGE-3A | NHIDCL | N24002208 | 2-2018 | 9/2025 | Mar-2024 | 9/2025 | 207.54 | 154.01 | 154.01 | 16.21 | 39.27
May 2025 | ANDAMAN AND NICOBAR ISLANDS | ROAD TRANSPORT AND HIGHWAYS | 10 | PACKAGE-3B | NHIDCL | N24002209 | 2-2018 | 11/2025 | N.A. | 11/2025 | 183.47 |  | 183.47 | 17.36 | 32.38
May 2025 | ANDAMAN AND NICOBAR ISLANDS | ROAD TRANSPORT AND HIGHWAYS | 11 | C/O OF NITB AND ASSOCIATED WORK AT VIJAYAWADA AIRPORT | AAI | N04000091 | 4-2020 | 3/2023 | Aug-2025 | 8/2025 | 611.8 |  | 611.8 | 444.75 | 74
May 2025 |  |  | 12 | RAJAHMUNDRY AIRPORT: CONSTRUCTION OF NEW DOMESTIC TERMINAL BUILDING AND MISCELLANEOUS WORKS INCLUD | AAI | N04000103 | 12-2022 | 8/2025 | N.A. | 8/2025 | 347.15 | 347.15 | 347.15 | 75.17 | 44.5
May 2025 |  |  | 13 | KADAPPA AIRPORT- CONSTRUCTION OF NEW DOMESTIC TERMINAL BUILDING AND MISCELLANEOUS WORKS INCLUDING MA | AAI | N04000106 | 3-2023 | 1/2026 | Jan-2026 | 1/2026 | 265.91 | 265.91 | 265.91 | 39.49 | 27
May 2025 |  | DEPARTMENT OF HIGHER EDUCATION | 14 | CONSTRUCTION OF PERMANENT CAMPUS FOR INDIAN INSTITUTE OF TECHNOLOGY TIRUPATI AT MERLAPAKA VILLAGE YE | CPWD EDUCATION | N42000005 | 2-2019 | 6/2020 | N.A. | 6/2020 | 655.34 |  | 655.34 | 366.21 | 95
May 2025 |  | DEPARTMENT OF HIGHER EDUCATION | 15 | CONSTRUCTION OF PERMANENT CAMPUS FOR IISER AT JANGALAPALLI VILLAGE, YERPEDU MANDAL, CHITTOOR DISTRIC | CPWD EDUCATION | N42000007 | 9-2019 | 9/2022 | N.A. | 6/2024 | 588.72 | 656.39 | 656.39 | 630.55 | 100
May 2025 |  | DEPARTMENT OF HIGHER EDUCATION | 16 | KG-DWN-98-2 CLUSTER II DEVELOPMENT PROJECT | ONGC | N16000247 | 3-2016 | 6/2020 | Mar-2025 | 6/2025 | 34012 |  | 34012 | 33149.29 | 96.4
May 2025 |  | DEPARTMENT OF HIGHER EDUCATION | 17 | HP CRUDE TO OLEFINS AND AROMATICS TECHNOLOGY DEMO UNIT AT VISAKH REFINERY | HPCL | N16000432 | 9-2021 | 6/2024 | Mar-2026 | 3/2026 | 160 | 220 | 220 | 50.04 | 58.3
May 2025 |  | DEPARTMENT OF HIGHER EDUCATION | 18 | CGD PROJECT AT KURNOOL, GUNTUR AND PRAKASAM DISTRICTS | IOCL | N16000485 | 3-2022 | 3/2030 | N.A. | 3/2030 | 1420 |  | 1420 | 152.86 | 6.1
May 2025 |  | DEPARTMENT OF HIGHER EDUCATION | 19 | MULTI-PRODUCT PIPELINE FROM KRISHNAPATNAM COASTAL INSTALLATION TO THE PROPOSED INSTALLATION AT HYDER | BPCL | N16000499 | 9-2019 | 3/2025 | N.A. | 10/2025 | 1932 |  | 1932 | 1491.65 | 92.6
May 2025 |  | DEPARTMENT OF HIGHER EDUCATION | 20 | HP TRIJET UNIT IN VR | HPCL | N16000535 | 7-2024 | 7/2027 | N.A. | 7/2027 | 193 |  | 193 | 0.38 | 23
May 2025 |  | DEPARTMENT OF HIGHER EDUCATION | 21 | CONSTRUCTION OF AVIATION FUEL FARM FACILITIES AT BHOGAPURAM AIRPORT | HPCL | N16000538 | 8-2024 | 3/2026 | N.A. | 3/2026 | 240 |  | 240 | 19.32 | 35.3
May 2025 |  |  | 22 | VISAKHA RAIPUR PIPELINE PROJECT | HPCL | N16000539 | 9-2024 | 9/2027 | N.A. | 9/2027 | 2212 |  | 2212 | 4.32 | 4.73
May 2025 |  | POWER | 23 | TRANSMISSION SCHEME FOR SOLAR ENERGY ZONE IN ANANTHPURAM (2500MW) AND KURNOOL (1000MW) | PGCIL | N18000380 | 9-2023 | 3/2025 | N.A. | 9/2025 | 1249 |  | 1249 | 568.7 | 56.7
May 2025 |  | POWER | 24 | AUGMENTATION OF 1500MVA 3RD 765/400KV TRANSFORMATION CAPACITY AT KURNOOL NEW SUBSTATION | PGCIL | N18000395 | 5-2023 | 9/2025 | N.A. | 9/2025 | 164 |  | 164 | 60 | 21
May 2025 |  | POWER | 25 | TRANSMISSION SYSTEM FOR INTEGRATION OF KURNOOL-IV REZ PHASE- I (FOR 4.5 GW) | PGCIL | N18000413 | 3-2025 | 3/2027 | N.A. | 3/2027 | 5000 |  | 5000 | 0
May 2025 |  | POWER | 26 | TRANSMISSION SYSTEM STRENGTHENING AT KURNOOL- III PS FOR INTEGRATION OF ADDITIONAL RE GENERATION PRO | PGCIL | N18000416 | 3-2025 | 3/2027 | N.A. | 3/2027 | 2886 |  | 2886 | 0
May 2025 |  | POWER | 27 | KOTLPALLI-NARASAPUR (NL) (SCR) | SCR | 220100265 | 12-2001 | 3/2028 | N.A. | 3/2027 | 2500.98 |  | 2500.98 | 1141.44 | 18
May 2025 |  | POWER | 28 | NADIKUDE-SRI KALAHASTI | SCR | N22000286 | 4-2011 | 5/2027 | N.A. | 5/2027 | 2312 |  | 3122.35 | 1935.77 | 35
May 2025 |  | POWER | 29 | GUNTUR-GUNTAKAL | SCR | N22000368 | 4-2016 | 12/2025 | N.A. | 12/2025 | 3733.37 |  | 3887.48 | 3534.39
May 2025 |  | POWER | 30 | VIJAYAWADA-GUDUR | RVNL | N22000369 | 4-2015 | 11/2024 | N.A. | 12/2024 | 6654 |  | 6238.67 | 5883.89
May 2025 |  | POWER | 31 | KOTTAVALSA - KORAPUT DOUBLING | ECOR | N22000377 | 4-2015 | 3/2022 | N.A. | 3/2022 | 2499.71 |  | 2499.71 | 1950.16 | 70
May 2025 |  | POWER | 32 | PENUKONDA-DHARMAVARAM, EXCL. DHARMAVARAM (41.5 KM) | SWR | N22000555 | 4-2019 | 3/2026 | N.A. | 12/2025 | 294.67 | 307.66 | 307.66 | 206.8 | 60
May 2025 |  | POWER | 33 | MALUGUR-PALASAMUDRAM (17.98 KM) | PB#29/NR/2022-23 | SWR | 9-2022 | 12/2025 | N.A. | 12/2026 | 323.14 | 342.41 | 342.41 | 46.89 | 12
May 2025 |  |  | 34 | DOUBLING BETWEEN GOOTY-PENDAKALLU | 29.225 | SCR | 3-2023 | 3/2027 | N.A. | 3/2027 | 351.83 |  | 351.83 | 0
May 2025 |  |  | 35 | VIJAYAWADA KAZIPET BYEPASS LINE | SCR | N22000586 | 4-2016 | 12/2025 | N.A. | 12/2025 | 647.37 |  | 226.72 | 242.64
May 2025 |  |  | 36 | RENIGUNTA WADI GOOTY - BYPASS | SCR | N22000587 | 4-2016 | 12/2025 | N.A. | 12/2025 | 302 |  | 302 | 219.08 | 50
May 2025 |  |  | 37 | REHABILITATION AND UPGRADATION OF NH-219 FROM KM 58-600 TO KM 140-750 IN THE STATE OF ANDHRA PRADES | MoRTH | N24000301 | 3-2015 | 10/2015 | May-2021 | 5/2021 | 271.45 |  | 271.45 | 238.23 | 100
May 2025 |  |  | 38 | CONSTRUCTION OF SIX LANING OF DEDICATED PORT ROAD TO KRISHNAPATNAM PORT (PACKAGE-I) KM 0+000 TO KM 1 | NHAI | N24000811 | 3-2018 | 12/2020 | Dec-2022 | 12/2024 | 314.43 |  | 348.72 | 85.61 | 69.64
May 2025 |  |  | 39 | REHABILITATION AND UPGRADATION OF EXISTING NH-167 FROM KM 14.900 TO KM 70.00 (DESIGN CH.14.900 TO 69 | MoRTH | N24000931 | 11-2016 | 5/2017 | N.A. | 11/2024 | 290.15 |  | 236.16 | 205.02 | 90
May 2025 |  |  | 40 | REHABILITATION AND UPGRADATION OF NEW NH-544DD FROM DESIGN CHAINAGE KM 56.00 TO 102.20 OF KALYANDURG | MoRTH | N24000937 | 3-2018 | 8/2018 | N.A. | 11/2024 | 289.67 | 290 | 285.29 | 254.19 | 98.5
May 2025 |  |  | 41 | CONSTRUCTION OF TIMMAPURAM TO GURJANAPALLE SECTION FROM KM 26.150 TO 41.161 OF NH-214(NH216)(KAKINAD | MoRTH | N24000964 | 8-2016 | 1/2017 | N.A. | 5/2025 | 350.61 |  | 411.18 | 407.92 | 98.2
May 2025 |  |  | 42 | CONSTRUCTION OF 2L+PS FROM PASARLAPUDI-DHINDI (105/700 TO 127.500 OF NH-214) OF NH-216 | MoRTH | N24000969 | 1-2017 | 9/2017 | N.A. | 6/2025 | 263.45 |  | 263.45 | 208.15 | 85
May 2025 |  |  | 43 | 6-LANING OF VIJAYAWADA BYPASS FROM GOLLAPUDI (DESIGN CH. 30+000) TO CHINNAKAKANI (DESIGN CH. 47+881) | NHAI | N24001301 | 11-2019 | 1/2024 | N.A. | 7/2024 | 1601.1 |  | 1601.1 | 1425.64 | 91.05
May 2025 |  |  | 44 | REHABILITATION AND UPGRADATION TO 2- LANE WITH PAVED SHOULDERS CONFIGURATION OF PADERU-GONDIGUDA SECT | MoRTH | N24001386 | 8-2020 | 3/2021 | N.A. | 6/2025 | 222.61 |  | 222.61 | 120.46 | 95
May 2025 |  |  | 45 | CONSTRUCTION OF 4 LANE ACCESS CONTROLLED NEW GREENFIELD HIGHWAY SECTION OF NH 365BG FROM RECHARLA VI | NHAI | N24001476 | 9-2021 | 9/2022 | Sep-2024 | 6/2025 | 517.05 |  | 655.06 | 520.94 | 91.97
May 2025 |  |  | 46 | CONSTRUCTION OF 4 LANE ACCESS CONTROLLED NEW GREENFIELD HIGHWAY SECTION OF NH-365BG (KHAMMAM- DEVARAP | NHAI | N24001477 | 9-2021 | 9/2022 | Sep-2024 | 6/2025 | 622 |  | 817.91 | 541.73 | 75.96
May 2025 |  |  | 47 | 6L OF CHILKARARUPET BYPASS FROM KM. 357.400 TO KM. 371.920 OF NH-16 | NHAI | N24001817 | 2-2019 | 3/2023 | Oct-2024 | 10/2024 | 757.45 |  | 757.45 | 607.76 | 99.41
May 2025 |  |  | 48 | 6L OF PONDAVAKKAM TO KANNIGAIPAIR FROM KM 96.040 TO KM 116.100 OF NH 716B | PKG-IV | NHAI | 2-2021 | 1/2025 | N.A. | 1/2025 | 818.73 |  | 1105 | 563.32 | 24.92
May 2025 |  |  | 49 | 6L OF VEERA KAVERI RAJA PURAM TO PONDAVAKKAM FROM KM 61.380 TO KM 96.040 OF NH 716B (PKG-III) | NHAI | N24001819 | 3-2021 | 1/2025 | N.A. | 1/2025 | 1102.63 |  | 1303 | 1107.66 | 94.17
May 2025 |  |  | 50 | 6L OF VARADHARAJULA TO KUMARAJAPET FROM KM 0.000 TO KM 43.800 OF NH-716B | PKG-I | NHAI | 2-2021 | 12/2024 | N.A. | 12/2024 | 1484.83 |  | 1768 | 1523.09 | 91.85
May 2025 |  |  | 51 | BANGALORE CHENNAI EXPRESSWAY (PHASE-II PKG-III) FROM KM.127.000 TO KM 156.000 (BANGARUPALEM TO GUDIP | NHAI | N24001821 | 11-2020 | 10/2024 | N.A. | 10/2024 | 1137.74 |  | 1289 | 1256.44 | 97.1
May 2025 |  |  | 52 | BANGALORE CHENNAI EXPRESSWAY (PHASE-II PKG-I) FROM KM.71.000 TO KM 96.000 (BETHAMANGALA IN THE STATE | NHAI | N24001822 | 12-2020 | 10/2024 | N.A. | 10/2024 | 1075.27 |  | 1307 | 1100.55 | 84.8
May 2025 |  |  | 53 | 4L OF MADANAPALLE TO PILERU SECTION FROM KM 0.000 TO KM 55.900 OF NH- 71(PACKAGE-I) - N/05060/01002/A | NHAI | N24001823 | 1-2022 | 1/2025 | Jan-2023 | 1/2025 | 1852.12 |  | 1787 | 777.18 | 90
May 2025 |  |  | 54 | RENIGUNTA - POYYA - NAIDUPETA KM 124.60 TO KM 183.4 OF NH 71 - N/04027/06001/AP | NHAI | N24001824 | 3-2020 | 1/2024 | Dec-2024 | 12/2024 | 1863.09 |  | 2238 | 1227.61 | 98.76
May 2025 |  |  | 55 | 6L KANTAKAPALLE ? SABBAVARAM SECTION OF NH-130CD ROAD FROM KM 445.100 TO KM 464.662 (PKG-4) | NHAI | N24001836 | 2-2021 | 10/2024 | N.A. | 3/2026 | 824.29 |  | 924 | 514.33 | 75.54
May 2025 |  |  | 56 | 6L JAKKUVA ? KORLAM SECTION OF NH- 130CD ROAD FROM KM 396.800 TO KM 421.100 (PKG 2) | NHAI | N24001837 | 2-2021 | 3/2024 | Jul-2024 | 12/2025 | 663.6 |  | 768 | 463.08 | 98.8
May 2025 |  |  | 57 | 6L ALURU - JAKKUVA SECTION OF NH- 130CD ROAD FROM KM 365.033 TO KM 396.800 (PKG. 1) | NHAI | N24001838 | 2-2021 | 3/2024 | N.A. | 12/2025 | 922.5 |  | 1128.68 | 534.48 | 84.03
May 2025 |  |  | 58 | 6L ACCESS CONTROLLED GREENFIELD HIGHWAY FROM KODUR 0.000 KMS TO VANAVOLU 24.300 KMS OF NH 544G PACKA | NHAI | N24001841 | 12-2022 | 9/2025 | N.A. | 2/2026 | 912.94 |  | 912.94 | 238.71 | 57.4
May 2025 |  |  | 59 | 6L ACCESS CONTROLLED GREENFIELD HIGHWAY FROM VANAVOLU 24.300 KM. TO VANKARAKUNTA 45.700 KM. OF NH 5 | NHAI | N24001842 | 12-2022 | 11/2025 | N.A. | 11/2025 | 750.81 |  | 750.81 | 145.15 | 49.1
May 2025 |  |  | 60 | 6L ACCESS CONTROLLED GREENFIELD HIGHWAY FROM VANKARAKUNTA 45.700 KM. TO ODULAPALLE 72.000 KM. OF NH | NHAI | N24001843 | 12-2022 | 11/2025 | N.A. | 11/2025 | 992.89 |  | 992.89 | 197.36 | 43.9
May 2025 |  |  | 61 | 6L ACCESS CONTROLLED GREENFIELD HIGHWAY FROM ODULAPALLE 72.000 KM. TO NALLACHERUVUPALLI 96.300 KM. | NHAI | N24001844 | 12-2022 | 10/2025 | N.A. | 10/2025 | 1058.9 |  | 1058.9 | 249.94 | 45.04
May 2025 |  |  | 62 | 6L ACCESS CONTROLLED GREENFIELD HIGHWAY FROM NALLACHERUVU PALLI 96.300 KM. TO YERRAGUDIPADU 129.000 | NHAI | N24001845 | 2-2023 | 10/2025 | N.A. | 10/2025 | 1253.24 |  | 1253.24 | 156.38 | 20.09
May 2025 |  |  | 63 | 6L ACCESS CONTROLLED GREENFIELD HIGHWAY FROM YERRAGUDIPADU 129.000 KM. TO AUDIREDDIPALLE 160.000 KM. | NHAI | N24001846 | 2-2023 | 10/2025 | N.A. | 10/2025 | 1200.42 |  | 1200.42 | 98.18 | 7.2
May 2025 |  |  | 64 | 6L ACCESS CONTROLLED GREENFIELD HIGHWAY FROM AUDIREDDIPALLE 160.000 KM. TO MALLAPALLE 176.000 KM. PA | NHAI | N24001847 | 1-2023 | 11/2025 | N.A. | 11/2025 | 956.14 |  | 956.14 | 215.17 | 40.2
May 2025 |  |  | 65 | 6L ACCESS CONTROLLED GREENFIELD HIGHWAY FROM MALLAPALLE 176.000 KM. TO KAVULAKUNTLA 196.000 KM. PACK | NHAI | N24001848 | 2-2023 | 10/2025 | N.A. | 10/2025 | 909.02 |  | 909.02 | 129.52 | 18.1
May 2025 |  |  | 66 | 4L PS MYDUKUR BADVEL FROM KM 585.820 TO KM 630.960 SECTION OF NH 67 | NHAI | N24001849 | 5-2022 | 7/2025 | N.A. | 9/2025 | 1063.72 |  | 1063.72 | 467.74 | 77.09
May 2025 |  |  | 67 | CONSTRUCTION OF 4-LANE HIGHWAY FROM SAMARLAKOTA TO ACHAMPETA JUNCTION (FROM KM. 0.000 TO KM. 12.250 | NHAI | N24001856 | 5-2023 | 8/2025 | N.A. | 8/2025 | 648.75 |  | 648.75 | 240.26 | 60.74
May 2025 |  |  | 68 | 2L+PS FROM KM. 0+000 TO KM. 32+000 (MUDIGUBBA TO PUTTAPARTHI) OF NH-342 | MoRTH | N24001932 | 3-2022 | 9/2024 | N.A. | 6/2025 | 401.72 |  | 401.72 | 139.07 | 80
May 2025 |  |  | 69 | NH440 RAYACHOTY TOVEMPALLI 2LPS | MoRTH | N24001934 | 12-2021 | 5/2024 | N.A. | 7/2025 | 439.82 |  | 439.82 | 119.72 | 26.73
May 2025 |  |  | 70 | 4 LANE WITH PAVED SHOULDER FROM KM 0.000 TO KM 51.119 OF TADIPATRI TO MUDDANUR OF NH67 | MoRTH | N24001935 | 3-2022 | 8/2025 | N.A. | 8/2025 | 724.17 |  | 724.17 | 229.73 | 97.38
May 2025 |  |  | 71 | NH165 FROM KM 0.000 TO KM 64.020 PAMARRU TO AKIVEEDU SECTION TO TWO LANE WITH PAVED SHOULDERS | MoRTH | N24001939 | 3-2020 | 9/2023 | N.A. | 12/2025 | 529.24 |  | 529.24 | 224.81 | 51.78
May 2025 |  |  | 72 | 2LPS FROM KM36.400 TO KM. 107.224 OF NH167BG FROM DUTTALUR TO KAVALI SECTION | MoRTH | N24001942 | 3-2021 | 7/2024 | N.A. | 3/2025 | 423.67 |  | 423.67 | 145.72 | 60.53
May 2025 |  |  | 73 | NH167AD FROM MACHERLA TO DACHEPALLI FROM KM.0.000 TO 43.659 TO 2LPS | MoRTH | N24001951 | 1-2022 | 1/2025 | N.A. | 1/2025 | 403.22 |  | 403.22 | 201.69 | 97
May 2025 |  |  | 74 | NH 167 B KADAPA NELLORE BORDER TO CSPURAM I.E. FROM KM 58.635 TO KM 99.409 | MoRTH | N24001952 | 3-2022 | 8/2025 | N.A. | 8/2025 | 285.5 |  | 285.5 | 204.29 | 95
May 2025 |  |  | 75 | NH-30-BHADRACHALAM TO KONTA SECTION 2LPS | MoRTH | N24001953 | 12-2021 | 9/2024 | N.A. | 3/2025 | 388.71 |  | 388.71 | 159.29 | 80
May 2025 |  |  | 76 | WIDENING TO 2LPS OF RAMPACHODAVARAM - KOYYURU SECTION OF NH516E FROM KM.43.700 TO KM 113.820 | MoRTH | N24001954 | 3-2022 | 1/2025 | N.A. | 1/2025 | 568.12 |  | 568.12 | 215.09 | 91.05
May 2025 |  |  | 77 | GUDIWADA TOWN 2 LANE ROB AND ROAD IMPROVEMENT OF NH165 IN REPLACEMENT OF LC NO 3ESPL3 AT KM 231.700 | MoRTH | N24001955 | 3-2022 | 5/2025 | N.A. | 5/2025 | 317.22 |  | 317.22 | 84.57 | 80
May 2025 |  |  | 78 | 2LPS FROM GONDIGUDA TO ARAKU BHALLAGUDA KM 27.480 TO KM 51.772 SECTION OF NH 516E | MoRTH | N24001956 | 8-2020 | 9/2023 | N.A. | 12/2024 | 296.66 |  | 296.66 | 190.3 | 87.49
May 2025 |  |  | 79 | 2LPS OF KOYYURU TO CHAPRATHIPALEM SECTION OF NH 516E | MoRTH | N24001957 | 8-2020 | 7/2024 | N.A. | 6/2025 | 349.29 |  | 349.29 | 114.53 | 76
May 2025 |  |  | 80 | 2LPS OF CHAPRATHIPALEM TO LAMBASINGI SECTION OF NH 516E | MoRTH | N24001958 | 8-2020 | 10/2024 | N.A. | 6/2025 | 311.22 |  | 311.22 | 85.45 | 72
May 2025 |  |  | 81 | 4 LANE FROM KM 56.400 TO KM 120.300 FROM B.KOTHAPALLI JUNCTION TO GORANTLA OF NH 716G | MoRTH | N24001959 | 3-2022 | 9/2025 | N.A. | 9/2025 | 839.98 |  | 839.98 | 146.12 | 67
May 2025 |  |  | 82 | 4L GREENFIELD ROAD CONNECTING NORTH AND SOUTH INDUSTRIAL CLUSTER OF KHANDALERU CREEK NEAR KRISHNAPAT | NHAI | N24001979 | 8-2022 | 9/2025 | N.A. | 9/2025 | 609.43 |  | 609.43 | 25.24 | 52.45
May 2025 |  |  | 83 | 4 LANING OF NH 544D FROM EXISTING KM 346.300 OF NH 44 (DESIGN CHAINAGE KM 0.000) TO KM 39.380 (DESIG | NHAI | N24001980 | 10-2022 | 7/2025 | N.A. | 7/2025 | 907.76 |  | 907.76 | 388.4 | 81.35
May 2025 |  |  | 84 | CONSTRUCTION OF SIX LANING OF NAIDUPETA JUNCTION - TURPUKANUPUR SECTION FROM KM.57+046 TO KM.91+927 | NHAI | N24001981 | 7-2022 | 10/2025 | N.A. | 10/2025 | 1398.84 |  | 1398.84 | 58.68 | 16
May 2025 |  |  | 85 | 4L PS FROM KURNOOL (EXISTING KM. 5.400 OF NH-40/DESIGN KM.0.000) TO MANDLEM (EXISTING KM.38.000/DESI | NHAI | N24001982 | 3-2023 | 10/2025 | N.A. | 10/2025 | 827.39 |  | 827.39 | 333.74 | 99.15
May 2025 |  |  | 86 | 4 LANING FROM EXISTING KM 39.380 (DESIGN CH. 37.000) TO KM 74.450 (DESIGN CH. 69.000) OF MUCHUKOTA ? | NHAI | N24001983 | 10-2022 | 8/2025 | N.A. | 8/2025 | 972.63 |  | 1055.23 | 309.39 | 53.38
May 2025 |  |  | 87 | 4L PS FROM MANDLEM (EXISTING KM. 38.000/DESIGN KM.30.600) TO ATMAKUR (EXISTING KM.73.000/DESIGN KM 6 | NHAI | N24001984 | 3-2023 | 10/2025 | N.A. | 10/2025 | 887.28 |  | 887.28 | 293.88 | 84.5
May 2025 |  |  | 88 | BANGALORE CHENNAI EXPRESSWAY (PHASE-II PKG-II) FROM KM.96.000 TO KM 127.000 (BAIREDDYPALLE TO BANGAR | NHAI | N24001985 | 3-2021 | 6/2025 | N.A. | 6/2025 | 1942.94 | 2171 | 2171 | 1694.18 | 61.25
May 2025 |  |  | 89 | 4L OF PILERU TO KALUR SECTION FROM KM 55.900 TO KM 92.800 AND KM 94.500 TO KM 95.717 | NHAI | N24001986 | 10-2023 | 4/2025 | N.A. | 4/2025 | 1047.32 |  | 1047.32 | 301.2 | 88
May 2025 |  |  | 90 | CONSTRUCTION OF 1 NOS ROB, 2 NOS VUPS, SERVICE ROADS, PROVISION OF LIGHTING AND CONSTRUCTION OF OTHE | NHAI | N24001987 | 6-2023 | 12/2024 | N.A. | 12/2024 | 152.05 |  | 152.05 | 136.12 | 76.63
May 2025 |  |  | 91 | 6L OF CHITTOOR TO THATCHUR FROM KUMARAJAPET TO VEERA KAVERI RAJA PURAM FROM KM 43.800 TO KM 61.380 O | NHAI | N24001988 | 2-2021 | 10/2025 | N.A. | 10/2025 | 591.99 | 703 | 703 | 496.65 | 65.28
May 2025 |  |  | 92 | CONSTRUCTION OF 4 LANE ACCESS CONTROLLED HIGHWAY FROM CHILLAKURU CROSS ROAD TO TURPUKANUPUR KM 0+000 | NHAI | N24002033 | 7-2022 | 12/2025 | N.A. | 12/2025 | 909.47 |  | 909.47 | 97.03 | 30.4
May 2025 |  |  | 93 | COMPLETION OF BALANCE WORKS PENDING IN BIT AND PIECES (INCOMPLETE STRETCH AT 7 LOCATIONS) AND LISTED | NHAI | N24002103 | 9-2022 | 1/2025 | N.A. | 6/2025 | 166.52 |  | 166.52 | 57.29 | 98
May 2025 |  |  | 94 | 6L ACCESS CONTROLLED GREENFIELD HIGHWAY FROM NARAYANMPET (CH. 203+500) TO CHANDRASEKHARPURAM (CH. 22 | NHAI | N24002122 | 2-2024 | 2/2026 | N.A. | 2/2026 | 813.66 |  | 813.66 | 91.7 | 22.17
May 2025 |  |  | 95 | 6L ACCESS CONTROLLED GREENFIELD HIGHWAY FROM CHANDRASEKHARAPURAM (CH. 228+000) TO POLAVARAM (CH. 260 | NHAI | N24002123 | 2-2024 | 2/2026 | N.A. | 2/2026 | 1292.65 |  | 1292.65 | 135.26 | 16
May 2025 |  |  | 96 | 6L ACCESS CONTROLLED GREENFIELD HIGHWAY FROM POLAVARAM (CH. 260+000) TO MARRIPUDI (CH. 285+500) OF [ | NHAI | N24002124 | 2-2024 | 2/2026 | N.A. | 2/2026 | 747.29 |  | 747.29 | 142.64 | 30.8
May 2025 |  |  | 97 | 6L ACCESS CONTROLLED GREENFIELD HIGHWAY FROM MARRIPUDI (CH. 285+500) TO SOMAVARAPPADU (CH. 314+600) | NHAI | N24002125 | 2-2024 | 2/2026 | N.A. | 2/2026 | 976.4 |  | 976.4 | 229.68 | 41
May 2025 |  |  | 98 | 6L ACCESS CONTROLLED GREENFIELD HIGHWAY FROM SOMAVARAPPADU (CH.314.600) TO MUPPAVARAM (CH.343+240) O | NHAI | N24002126 | 2-2024 | 2/2026 | N.A. | 2/2026 | 1103.89 |  | 1103.89 | 133.88 | 14.5
May 2025 |  |  | 99 | 4-LANE WITH PAVED SHOULDERS FROM KM 32/0 TO KM 79/650 (DESIGN CHAINAGE KM 32+000 TO KM 78+760) PUTTA | MoRTH | N24002139 | 3-2023 | 12/2025 | N.A. | 11/2025 | 1318.57 |  | 1318.57 | 201 | 56
May 2025 |  |  | 100 | SOMAYAJULAPALLI ? DHONE SECTION OF NH ? 340B FROM KM.0/0 TO 56/200 [DESIGN CH. KM 0/00 TO KM 53/33] | MoRTH | N24002140 | 4-2023 | 12/2025 | N.A. | 12/2025 | 629.73 |  | 629.73 | 103 | 62
May 2025 |  |  | 101 | 2-LANE WITH PAVED SHOULDER CONFIGURATION OF LAMBASINGI TO PADERU SECTION (KM 205+000 TO KM 253+974) | MoRTH | N24002142 | 8-2023 | 11/2025 | N.A. | 11/2025 | 361.24 |  | 361.24 | 7 | 26
May 2025 |  |  | 102 | BYPASS ROAD TO ADONI TOWN CONNECTING NH-167 (HAGARI - JADCHARLA ROAD) FROM KM.62/700 TO 71/400 IN KU | MoRTH | N24002143 | 8-2023 | 2/2026 | N.A. | 2/2026 | 361.24 |  | 361.24 | 109.65 | 56
May 2025 |  |  | 103 | VODAREVU-CHILAKALURIPET SECTION (DESIGN CHAINAGE 0+00 TO 47+000) OF NH- 167A (PACKAGE-I) | MoRTH | N24002144 | 8-2023 | 2/2026 | N.A. | 2/2026 | 1064.24 |  | 1064.24 | 80 | 60
May 2025 |  |  | 104 | TADIPATRI BYPASS (KM 0+000 TO KM 6+285) OF 4-LANE ON NH-67 IN ANANTAPURAMU | MoRTH | N24002145 | 11-2023 | 3/2026 | N.A. | 3/2026 | 159.66 |  | 159.66 | 11.95 | 63.5
May 2025 |  |  | 105 | KURNOOL/KADAPA BORDER- JAMMALAMADUGU SECTION OF NH-167K I.E. DESIGN CH. KM 248+010 TO KM 269+900 | MoRTH | N24002146 | 11-2023 | 11/2025 | N.A. | 11/2025 | 292.63 |  | 292.63 | 61.36 | 20
May 2025 |  |  | 106 | DORNALA TO KUNTA JUNCTION FROM DESIGN CHAINAGE KM 244+000 TO 267+990 SECTION OF NH-765 (PACKAGE-2) | MoRTH | N24002147 | 12-2022 | 1/2024 | N.A. | 3/2026 | 244.83 |  | 244.83 | 104.32 | 74
May 2025 |  |  | 107 | PADERU BYPASS (KM 0+000 TO KM 13+000) OF 2- LANE WITH PAVED SHOULDER ON NH- 516E | MoRTH | N24002148 | 3-2023 | 3/2024 | N.A. | 2/2026 | 244.43 |  | 244.43 | 22.77
May 2025 |  |  | 108 | DAVUALAPALLY TO MALLAPALEM SECTION {DESIGN CH. KM 133+922 TO KM 154+216 (EXISTING CH. KM 133+922 TO | MoRTH | N24002149 | 1-2024 | 2/2024 | N.A. | 2/2026 | 393.61 |  | 393.61 | 40 | 24
May 2025 |  |  | 109 | DEVELOPMENT OF SIX LANE ACCESS CONTROLLED GREEN FIELD HIGHWAY FROM KAVULAKUNTLA (KM.196+000) TO NARA | NHAI | N24002215 | 2-2023 | 2/2027 | N.A. | 2/2027 | 1092.18 |  | 1092.18 | 0.14
May 2025 |  |  | 110 | ACCESS CONTROLLED HIGHWAY OF 4 LANE WITH PAVED SHOULDERS FROM TN/AP BORDER (DESIGN CHAINAGE KM 61+51 | NHAI | N24002217 | 12-2024 | 12/2026 | N.A. | 12/2026 | 1346.82 |  | 1346.82 | 37.35 | 7.4
May 2025 |  | WATER RESOURCES | 111 | POLAVARAM IRRIGATION PROJECT | PPA | N30000002 | 2-2009 | 3/2020 | Mar-2027 | 12/2027 | 10151.04 |  | 55548.87 | 23775.68 | 76
May 2025 |  | CIVIL AVIATION | 112 | CONSTRUCTION OF NEW GREEN FIELD AIRPORT AT HOLLONGI ITANAGAR ARUNACHAL PRADESH | AAI | N04000092 | 2-2019 | 8/2022 | Jun-2025 | 6/2025 | 645.63 | 732 | 732 | 693.71 | 99.72
May 2025 |  | POWER | 113 | SUBANSIRI LOWER H.E.P (8X250 MW) | NHPC | NHPC | 9-2003 | 9/2010 | N.A. | 5/2026 | 6285.33 |  | 26075.54 | 24213.84 | 96.49
May 2025 |  | POWER | 114 | DIBANG MULTIPURPOSE PROJECT 2880 MW ARUNACHAL PRADESH | NHPC | N18000362 | 2-2023 | 2/2032 | N.A. | 2/2032 | 31876.39 |  | 31876.39 | 3306.4 | 15.74
May 2025 |  |  | 115 | TWO LANING OF JORAM KOLORIANG ROAD (NH 713) ON EPC BASIS FROM DESIGN KM. 138+000 TO KM. 154+036 [EX | NHIDCL | N24000683 | 2-2017 | 11/2023 | Mar-2024 | 12/2024 | 180.57 | 244.1 | 180.57 | 160.46 | 96.62
May 2025 |  |  | 116 | CONSTRUCTION OF 2-LANE ROAD WITH PAVED SHOULDERS FROM KM16.00 OF ROING-HUNLI SECTION TO KM 21.500 OF | NHIDCL | N24000946 | 3-2017 | 3/2022 | Jun-2025 | 12/2025 | 1718.59 | 1718.59 | 1718.59 | 728.21 | 73.64
May 2025 |  |  | 117 | TWO-LANING OF HAYULIANG? HAWAI BYPASS ROAD ON EPC BASIS FROM DESIGN KM. 51.825 TO KM. 63.131 EXISTI | NHIDCL | N24000979 | 1-2017 | 5/2023 | May-2023 | 3/2025 | 256.66 |  | 256.66 | 0 | 63.59
May 2025 |  |  | 118 | CONSTRUCTION OF 2-LANING WITH HARD SHOULDERS OF ARROWA-KHUPA- HAYULIANG SECTION OF NH-113 FROM CH.68. | NHIDCL | N24001244 | 8-2020 | 4/2022 | Feb-2025 | 2/2025 | 301.06 |  | 301.06 | 198.22 | 81.06
May 2025 |  |  | 119 | CONSTRUCTION OF 2 LANE ROAD OF POTIN TO PANGIN SECTION OF NH 13 FROM KM 163.59 TO KM 206.66 (PACKAGE | MoRTH | N24001297 | 3-2019 | 3/2027 | N.A. | 3/2027 | 450.65 |  | 450.65 | 398.18 | 95.84
May 2025 |  |  | 120 | 4 LANING OF ITANAGAR TO BANDARDEWA SECTION OF NH-415 FROM KM 40+430 TO KM 51+735 (PACKAGE B) ON EPC | MoRTH | N24001375 | 6-2020 | 3/2027 | N.A. | 3/2027 | 496.47 |  | 496.47 | 194.62 | 42.69
May 2025 |  |  | 121 | JORAM ? KOLORIANG ROAD FROM EXISTING KM 50.050 TO KM 70.00 (PKG-3) | NHIDCL | N24001390 | 8-2020 | 4/2022 | Aug-2024 | 9/2024 | 228.71 |  | 228.71 | 98.86 | 99.52
May 2025 |  |  | 122 | JORAM ? KOLORIANG ROAD FROM EXISTING KM122.600 TO KM138.00 (PKG-7) | NHIDCL | N24001393 | 8-2020 | 4/2022 | Feb-2024 | 6/2025 | 184.88 |  | 184.88 | 99.32 | 97.42
May 2025 |  |  | 123 | HUNLI TO HAYULIANG PKG-1 | NHIDCL | N24002222 | 2-2024 | 2/2028 | N.A. | 2/2028 | 1262.43 |  | 1262.43 | 12.12 | 2.35
May 2025 |  |  | 124 | HUNLI TO ITHUN BRIDGE SECTION | NHIDCL | N24002223 | 2-2024 | 1/2027 | N.A. | 1/2027 | 275.5 |  | 275.5 | 7.61 | 6.01
May 2025 |  |  | 125 | PANGO TO JORGING ROAD PKG-1 | NHIDCL | N24002224 | 1-2024 | 7/2027 | N.A. | 7/2027 | 898.19 |  | 898.19 | 7.08 | 4.06
May 2025 |  | CIVIL AVIATION | 126 | CONSTRUCTION OF NEW INTEGRATED TERMINAL BUILDING AT LGBI AIRPORT GUWAHATI | AAI | N04000083 | 12-2016 | 3/2021 | Aug-2025 | 8/2025 | 1142 |  | 2333 | 1884.13 | 87.93
May 2025 |  | COAL | 127 | TIKAK EXTENSION OCP - 0.2 MTY | CIL | N06000290 | 7-2022 | 11/2030 | N.A. | 11/2030 | 159.77 |  | 159.77 | 81.45
May 2025 |  | COAL | 128 | TIRAP OCP | CIL | N06000291 | 11-2022 | 11/2027 | N.A. | 11/2027 | 289.46 |  | 289.46 | 105.59
May 2025 |  | HEALTH AND FAMILY WELFARE | 129 | ALL INDIA INSTITUTE OF MEDICAL SCIENCE AT GUWAHATI, ASSAM | HITES | N21000027 | 5-2017 | 5/2021 | Apr-2023 | 6/2025 | 875 | 873.92 | 860 | 787.9 | 99.52
May 2025 |  | HEALTH AND FAMILY WELFARE | 130 | DEVELOPMENT OF SURFACE FACILITIES FOR PRODUCTION AND EVACUATION OF CRUDE OIL AND NATURAL GAS FROM NA | OIL | N16000331 | 1-2018 | 2/2020 | Dec-2024 | 6/2025 | 543.91 | 726.93 | 726.93 | 491.56 | 93.95
May 2025 |  | HEALTH AND FAMILY WELFARE | 131 | NUMALIGARH REFINERY EXPANSION PROJECT 6 MMTPA REFINARY | NRL | N16000379 | 1-2019 | 10/2024 | N.A. | 12/2025 | 12366 |  | 18968 | 16013.82 | 74.01
May 2025 |  | HEALTH AND FAMILY WELFARE | 132 | NUMALIGARH REFINERY EXPANSION PROJECT COIT AND PIPELINES | NRL | N16000394 | 1-2019 | 10/2024 | N.A. | 9/2025 | 10228 |  | 9058 | 9447.83 | 85.06
May 2025 |  | HEALTH AND FAMILY WELFARE | 133 | EXPANSION OF GUWAHATI REFINERY FROM 1 TO 1.2 MMTPA ALONG WITH INSTALLATION OF CATALYTIC REFORMING UN | IOCL | N16000414 | 5-2021 | 10/2023 | May-2026 | 5/2026 | 412 | 595.2 | 595.2 | 396.08 | 82.8
May 2025 |  | HEALTH AND FAMILY WELFARE | 134 | REVAMPING OF FACILITIES AT EXISTING GUWAHATI TERMINAL, ASSAM | IOCL | N16000441 | 3-2022 | 7/2026 | Sep-2026 | 9/2026 | 277 |  | 277 | 180.17 | 66.4
May 2025 |  |  | 135 | UPGRADATION OF FACILITIES OF NUMALIGARH-SILIGURI PRODUCT PIPELINE (NSPL) FOR TRANSPORTATION OF ADDIT | OIL | N16000449 | 6-2021 | 12/2024 | Apr-2025 | 7/2025 | 860 |  | 860 | 535.46 | 96.5
May 2025 |  |  | 136 | PROJECT TO CONSTRUCT A FIELD GAS GATHERING STATION AT BAGHJAN AREA FOR COLLECTION,PROCESSING | OIL | N16000450 | 12-2020 | 7/2024 | Mar-2024 | 6/2025 | 430.76 |  | 430.76 | 319.86 | 83.66
May 2025 |  |  | 137 | CAPACITY EXPANSION OF DIGBOI REFINERY FROM 0.65 TO 1.0 MMTPA | IOCL | N16000457 | 6-2022 | 10/2025 | N.A. | 3/2026 | 768 |  | 768 | 86.75 | 33.1
May 2025 |  |  | 138 | CONSTRUCTION OF LPG FACILITIES AT KAMARDANGA, ASSAM | HPCL | N16000484 | 3-2023 | 7/2027 | Jul-2027 | 7/2027 | 156.36 | 156.36 | 156.36 | 41.02 | 31.5
May 2025 |  |  | 139 | SETTING UP OF NEW RAIL FED POL FACILITY AT KAMARDANGA, ASSAM | HPCL | N16000494 | 3-2023 | 7/2027 | Jul-2027 | 7/2027 | 384.04 |  | 384.04 | 94 | 34.4
May 2025 |  |  | 140 | POWER RECOVERY TURBINE IN PFCCU | NRL | N16000510 | 3-2023 | 7/2025 | N.A. | 7/2025 | 293.5 |  | 293.5 | 97.22 | 91
May 2025 |  |  | 141 | DCU REVAMP PROJECT | NRL | N16000511 | 8-2021 | 3/2025 | N.A. | 10/2025 | 370 |  | 370 | 255.51 | 56.1
May 2025 |  |  | 142 | PIPELINE NETWORK PROJECT RUDRASAGAR | ONGC | N16000528 | 1-2023 | 4/2026 | N.A. | 4/2026 | 344.99 |  | 344.99 | 172.04 | 45.3
May 2025 |  |  | 143 | BORHOLLA GGS LIFE EXTENSION PROJECT | ONGC | N16000532 | 9-2023 | 5/2026 | N.A. | 5/2026 | 198.7 |  | 198.7 | 99.52 | 23.8
May 2025 |  | RAILWAYS | 144 | BONGAIGAON-GOALPARA-GUWAHATI (176 KM) | NFR | N22000388 | 4-2015 | 3/2026 | N.A. | 3/2027 | 4059.65 |  | 4983.94 | 3652.94 | 92.31
May 2025 |  | RAILWAYS | 145 | 4 LANING OF JORHAT TO JHANJI SECTION FROM KM. 453.00 TO KM. 491.08 (DESIGN KM 403.200 TO KM 454.240) | NHIDCL | N24000319 | 6-2015 | 8/2023 | N.A. | 6/2025 | 437.39 |  | 437.39 | 574.56 | 96.95
May 2025 |  |  | 146 | FOUR LANING OF JHANJHI JN TO DEMOW SECTION FROM KM. 491.050 TO KM. 535.250(DESIGN KM 490.800 TO KM 5 | NHIDCL | N24000320 | 6-2015 | 3/2024 | N.A. | 10/2025 | 463.49 |  | 463.49 | 515.52 | 76.95
May 2025 |  |  | 147 | 4 LANING FROM JAMUGURI TO BISWANATH CHARIALI FROM KM 182 TO KM 208 OF NH- 52 | NHIDCL | N24000431 | 1-1991 | 6/2019 | Jun-2019 | 7/2025 | 520.01 |  | 520.01 | 305.76 | 97.9
May 2025 |  |  | 148 | 4 LANING FROM RANGAGARA TO KALIABHOR TINALI FROM KM 297.00 TO KM 315.315 OF NH-37 ON EPC BASIS. | NHIDCL | N24000438 | 12-2015 | 12/2018 | Jul-2021 | 12/2025 | 289.99 |  | 289.99 | 233.23 | 88.03
May 2025 |  |  | 149 | 4 LANING OF NH-37 SECTION BETWEEN DEMOW TO END OF MORAN BYPASS (FROM KM. 534.800 TO KM. 561.700) O | NHIDCL | N24000582 | 1-2016 | 1/2016 | N.A. | 7/2025 | 294.17 |  | 294.17 | 389.75 | 97.88
May 2025 |  |  | 150 | 4 LANING OF NH 37 SECTION BETWEEN END OF MORAN BYPASS TO BOGIBEEL JUNCTION NEAR LAPETKETA (KM. 561 | NHIDCL | N24000583 | 1-2016 | 12/2021 | N.A. | 7/2025 | 252 |  | 330.3 | 219.65 | 91.31
May 2025 |  |  | 151 | 4-LANING OF HAPACHARA - TULUNGIA SECTION | NHIDCL | N24001246 | 3-2020 | 12/2022 | N.A. | 6/2024 | 220.2 |  | 220.2 | 217.18 | 97.76
May 2025 |  |  | 152 | 2-LANING OF CHURACHANDPUR TUIVAI SECTION OF NH-102B (PKG- IB) | NHIDCL | N24001269 | 3-2020 | 3/2022 | Jun-2025 | 8/2025 | 216.49 | 241.52 | 216.49 | 111.59 | 85.83
May 2025 |  |  | 153 | 4-L DHUBRI PHULBARI BRIDGE WITH APPROACH ROAD | NHIDCL | N24001326 | 11-2020 | 9/2028 | N.A. | 9/2028 | 4997.04 |  | 4997.04 | 2408.8 | 62.1
May 2025 |  |  | 154 | 2-LANING FROM YAINGANGPOKPI TO FINCH CORNER (PKG-I) | NHIDCL | N24001331 | 3-2020 | 6/2022 | May-2025 | 12/2025 | 261.13 |  | 261.13 | 68.75 | 57.42
May 2025 |  |  | 155 | 2-LANING FROM YAINGANGPOKPI TO FINCH CORNER (PKG-II) | NHIDCL | N24001332 | 3-2020 | 6/2022 | Apr-2025 | 12/2025 | 217.5 |  | 217.5 | 88.99 | 68.03
May 2025 |  |  | 156 | DABOKA KATHKATI PACKAGE-5 | NHIDCL | N24001366 | 3-2021 | 1/2023 | N.A. | 11/2024 | 288.85 |  | 288.85 | 247.76 | 100
May 2025 |  |  | 157 | TULUNGIA-JOGIGHOPA-PAIKAN ROAD PKG- 7 | NHIDCL | N24001368 | 3-2021 | 1/2024 | N.A. | 10/2025 | 286.72 |  | 286.72 | 158.15 | 81.63
May 2025 |  |  | 158 | CONSTRUCTION OF 2-LANE MAJOR BRIDGE INCLUDING APPROACHESOVER BRAHMAPUTRA BETWEEN MAJULI ON NORTH BAN | MoRTH | N24001408 | 2-2021 | 7/2025 | N.A. | 7/2025 | 925.47 | 1019.17 | 925.47 | 192.5 | 30.65
May 2025 |  |  | 159 | JOGIGHOPA BRIDGE | NHIDCL | N24001434 | 8-2021 | 11/2024 | N.A. | 12/2026 | 746.76 |  | 746.76 | 335.2 | 66.96
May 2025 |  |  | 160 | DABOKA KATHKATI PACKAGE-6 | NHIDCL | N24001450 | 9-2021 | 7/2024 | N.A. | 5/2025 | 625.64 |  | 625.64 | 556.44 | 100
May 2025 |  |  | 161 | DABOKA KATHKATI PACKAGE-7 | NHIDCL | N24001537 | 11-2021 | 7/2024 | N.A. | 7/2025 | 204.1 |  | 204.1 | 143.45 | 96.02
May 2025 |  |  | 162 | FOUR LANING OF SRIRAMPUR-DHUBRI PKG- 2 | NHIDCL | N24001544 | 3-2022 | 1/2025 | N.A. | 6/2025 | 909.02 |  | 909.02 | 532.44 | 98.92
May 2025 |  |  | 163 | 6L STANDALONE FLYOVERS AT RAHA, DEMOW, BORGHAT, KATHIATALI JUNCTIONS AND ROB AT JAGIROAD ON STRETCHE | NHAI | N24001545 | 8-2022 | 12/2022 | Sep-2024 | 6/2024 | 175 |  | 175 | 200.8 | 100
May 2025 |  |  | 164 | BALANCE WORK OF 4L OF NARIMBANGLO?JATINGA JUNCTION- HARANGAJO ROAD SECTION FROM KM 0.000 TO KM 49.23 | NHAI | N24001547 | 3-2022 | 1/2026 | N.A. | 1/2026 | 1909.98 |  | 1909.98 | 654.6 | 77.1
May 2025 |  |  | 165 | 6L STANDALONE FLYOVERS AT BONGAIGAON, CHAPAGURI, PATHSALA, SIMLAGURI CHOWK AND BAIHATA BYPASS JUNCTI | NHAI | N24001548 | 3-2022 | 6/2024 | N.A. | 5/2025 | 457.72 |  | 457.72 | 366.34 | 100
May 2025 |  |  | 166 | SRIRAMPUR - DHUBRI PKG-1 | NHIDCL | N24001831 | 3-2022 | 2/2025 | N.A. | 11/2026 | 613.89 |  | 613.89 | 110.76 | 35.7
May 2025 |  |  | 167 | DIBRUGARH-LAHOAL-CHABUA BYPASS PACKAGE-3 | NHIDCL | N24001832 | 1-2023 | 5/2025 | N.A. | 7/2025 | 458.59 |  | 458.59 | 198.15 | 65.62
May 2025 |  |  | 168 | CONSTRUCTION OF MANGALDOI BYPASS (NH-15) STARTING AT CH 26+400 AND TERMINATING AT CH 41+505 UNDER RA | MoRTH | N24001840 | 3-2022 | 4/2025 | N.A. | 3/2026 | 535.03 |  | 535.03 | 102.23 | 34.15
May 2025 |  |  | 169 | WIDENING AND UPGRADATION TO TWO LANES WITH PAVED SHOULDERS ROAD FROM TAMENGLONG TO MAHUR (NH-137) I | NHIDCL | N24001969 | 3-2023 | 8/2025 | N.A. | 8/2025 | 904.04 |  | 904.04 | 409.15 | 67.3
May 2025 |  |  | 170 | WIDENING AND UPGRADATION TO TWO LANES WITH PAVED SHOULDERS ROAD FROM TAMENGLONG TO MAHUR (NH-137) IN | NHIDCL | N24001970 | 3-2023 | 8/2025 | N.A. | 8/2025 | 860.37 |  | 860.37 | 393.82 | 65.95
May 2025 |  |  | 171 | WIDENING AND UPGRADATION TO TWO LANES WITH PAVED SHOULDERS ROAD FROM TAMENGLONG TO MAHUR (NH-137) IN | NHIDCL | N24001971 | 3-2023 | 8/2025 | N.A. | 8/2025 | 890.33 |  | 890.33 | 454.34 | 63.7
May 2025 |  |  | 172 | WIDENING/IMPROVEMENT TO 4-LANE WITH PAVED SHOULDER FROM KM 0+800 (KANDULIJAN GAON) TO KM 27+701 (SI | NHIDCL | N24001972 | 3-2023 | 4/2026 | N.A. | 4/2026 | 609.16 |  | 609.16 | 305.73 | 94.97
May 2025 |  |  | 173 | WIDENING/IMPROVEMENT TO 4-LANE WITH PAVED SHOULDER FROM KM 27+701 (SIMEN CHAPORI) TO KM 55+000 (NAG | NHIDCL | N24001973 | 3-2023 | 2/2026 | N.A. | 2/2026 | 562.05 |  | 562.05 | 290.2 | 95.71
May 2025 |  |  | 174 | BILASIPURA-GUWAHATI ROAD PKG-8 | NHIDCL | N24002021 | 3-2023 | 12/2026 | N.A. | 12/2026 | 1457.59 |  | 1457.59 | 537.09 | 46.78
May 2025 |  |  | 175 | BILASIPURA-GUWAHATI ROAD PKG-9 | NHIDCL | N24002022 | 3-2023 | 6/2026 | N.A. | 6/2026 | 1000.27 |  | 1000.27 | 304.61 | 27.07
May 2025 |  |  | 176 | BILASIPURA-GUWAHATI ROAD PKG-10 | NHIDCL | N24002023 | 3-2023 | 6/2026 | N.A. | 6/2026 | 1264.9 |  | 1264.9 | 422.31 | 25.57
May 2025 |  |  | 177 | DABOKA BYPASS OF DABOKA - PAROKHAOWA PKG -1 | NHIDCL | N24002024 | 1-2023 | 11/2025 | N.A. | 11/2025 | 516.88 |  | 516.88 | 242.91 | 73.5
May 2025 |  |  | 178 | 2 LANE WITH PAVED SHOULDER FROM KM 16+900 (BOGAPANI) TO KM 27+150 (GOLAI GAON) ON EXISTING DIBRUGARH | NHIDCL | N24002025 | 1-2023 | 12/2025 | N.A. | 12/2026 | 356.65 |  | 356.65 | 129.18 | 16.28
May 2025 |  |  | 179 | DEVELOPMENT OF EXTERNAL TRUNK CONNECTIVITY AND INTERNAL INFRASTRUCTURE WORKS AT MULTI MODEL LOGISTIC | NHIDCL | N24002030 | 2-2020 | 3/2022 | N.A. | 9/2024 | 592.06 |  | 592.06 | 308.87 | 100
May 2025 |  |  | 180 | SILCHAR VAIRENGTE SAIRANG ROAD PKG- 1 | NHIDCL | N24002127 | 2-2023 | 7/2026 | N.A. | 7/2026 | 1256.9 |  | 1256.9 | 537.26 | 38.6
May 2025 |  |  | 181 | SILCHAR VAIRENGTE SAIRANG ROAD PKG- 2 | NHIDCL | N24002128 | 3-2023 | 8/2026 | N.A. | 8/2026 | 1716.21 |  | 1716.21 | 983.58 | 64.03
May 2025 |  |  | 182 | FOUR LANNING OF BADARPUR BYPASS FROM DESIGN CHAINAGE KM 27+300 AT CROSSING WITH NH-6 | NHIDCL | N24002129 | 2-2023 | 8/2026 | N.A. | 8/2026 | 574.26 |  | 574.26 | 297.5 | 54.88
May 2025 |  |  | 183 | TAMENGLONG- MAHUR ROAD PKG-7 | NHIDCL | N24002130 | 12-2023 | 3/2026 | N.A. | 3/2026 | 846.82 |  | 846.82 | 404.51 | 68.8
May 2025 |  |  | 184 | CONSTRUCTION OF 4-LANE PANCHGRAM BYPASS FROM DESIGN CHAINAGE KM 15+500 ON NH-37 (OLD NH-53) AT KALIN | NHIDCL | N24002154 | 3-2023 | 2/2027 | N.A. | 2/2027 | 728.97 |  | 728.97 | 279.87 | 42.68
May 2025 |  |  | 185 | WIDENING/IMPROVEMENT TO 4-LANE WITH PAVED SHOULDER FROM KM 55+000 (NAGABANG GAMSUK) TO KM 82+514 (OY | NHIDCL | N24002155 | 3-2023 | 3/2027 | N.A. | 3/2027 | 665.47 |  | 665.47 | 183.63 | 45.53
May 2025 |  |  | 186 | BILASIPURA- GUWAHATI ROAD PKG-1 | NHIDCL | N24002225 | 2-2024 | 8/2027 | N.A. | 8/2027 | 1081.15 |  | 1081.15 | 33.93 | 2.76
May 2025 |  |  | 187 | SILCHAR-JIRIBAM PKG-1 | NHIDCL | N24002226 | 1-2024 | 1/2028 | N.A. | 1/2028 | 957.95 |  | 957.95 | 0 | 16.25
May 2025 |  |  | 188 | BILASIPURA- GUWAHATI ROAD PKG-2 | NHIDCL | N24002229 | 11-2023 | 6/2027 | N.A. | 6/2027 | 1338.61 |  | 1338.61 | 0.5
May 2025 |  |  | 189 | BADARPUR ? CHURAIBARI PKG-6 | NHIDCL | N24002230 | 3-2024 | 3/2027 | N.A. | 3/2027 | 870 |  | 870 | 0
May 2025 |  |  | 190 | KARIMGANI - SUTARKANDI SECTION ON SILCHAR-CHURAIBARI PKG-7 | NHIDCL | N24002231 | 2-2024 | 2/2027 | N.A. | 2/2027 | 791.79 |  | 791.79 | 0
May 2025 |  |  | 191 | CONSTRUCTION OF 4 LANE GAURIPUR BYPASS ON NH-17 IN THE STATE OF ASSAM | MoRTH | N24002237 | 3-2024 | 10/2026 | N.A. | 10/2026 | 421.15 |  | 421.15 | 0
May 2025 |  |  | 192 | CONSTRUCTION OF 2 LANE BARPETA BYPASS FROM KM 77+900(BARADI) TO KM 86+150( DEURIKUCHI) (LENGTH=8.25K | MoRTH | N24002238 | 3-2023 | 8/2026 | N.A. | 8/2026 | 173.65 |  | 173.65 | 0
May 2025 |  |  | 193 | SILCHAR- CHURAIBARI PKG-5 | NHIDCL | N24002243 | 2-2024 | 10/2027 | N.A. | 10/2027 | 1258.13 |  | 1258.13 | 0
May 2025 |  | CIVIL AVIATION | 194 | CONSTRUCTION OF NEW DORNESTIC TERMINAL BUILDING AND OTHER STRUCTURES, PHASE I AND II | AAI | N04000082 | 5-2018 | 10/2022 | Jun-2025 | 6/2025 | 1216.9 |  | 1216.9 | 1008.79 | 89.66
May 2025 |  | CIVIL AVIATION | 195 | DARBHANGA:DEVELOPMENT OF NEW CIVIL ENCLAVE AT DARBHANGA, BIHAR. SH- CONSTRUCTION OF NEW TERMINAL BUI | AAI | N04000112 | 7-2024 | 7/2026 | N.A. | 7/2026 | 911.66 |  | 911.66 | 122.51 | 18
May 2025 |  | DEPARTMENT OF HIGHER EDUCATION | 196 | CONSTRUCTION OF ACADEMIC AND RESIDENTIAL COMPLEX UNDER PHASE-II FOR THE CAMPUS OF IIT PATNA | CPWD EDUCATION | N28000100 | 2-2016 | 6/2017 | N.A. | 1/2024 | 496.18 | 496 | 460 | 390.15 | 100
May 2025 |  | DEPARTMENT OF HIGHER EDUCATION | 197 | PERMANENT CAMPUS FOR IIM BODH GAYA | CPWD EDUCATION | N42000009 | 9-2018 | 9/2020 | N.A. | 3/2025 | 375 |  | 375 | 342.18 | 100
May 2025 |  | DEPARTMENT OF HIGHER EDUCATION | 198 | BARAUNI REFINERY CAPACITY EXPANSION FROM 6.0 TO 9.0 MMTPA | IOCL | N16000386 | 1-2020 | 4/2023 | Aug-2026 | 8/2026 | 14810 | 18113 | 18113 | 10898.63 | 85.7
May 2025 |  | DEPARTMENT OF HIGHER EDUCATION | 199 | CGD PROJECT AT KHAGARIA, SAHARSA AND MADHEPURA | IOCL | N16000423 | 6-2019 | 12/2029 | Mar-2030 | 3/2030 | 163 |  | 163 | 95.19 | 40.1
May 2025 |  |  | 200 | INSTALLATION OF BITUMEN MANUFACTURING UNIT ALONG WITH ALLIED FACILITIES AT BARAUNI | IOCL | N16000453 | 1-2022 | 4/2025 | N.A. | 5/2026 | 389 |  | 389 | 36.61 | 33.7
May 2025 |  |  | 201 | CITY GAS DISTRIBUTION PROJECTS AT GOPALGANJ SIWAN WEST CHAMPARAN EAST CHAMPARAN AND DEORIA DISTRICTS | BPCL | N16000523 | 12-2022 | 6/2030 | N.A. | 6/2030 | 3919 |  | 3919 | 376.96 | 13.3
May 2025 |  |  | 202 | CITY GAS DISTRIBUTION PROJECTS AT DARBHANGA, MADHUBANI, SUPAUL, SITAMARHI AND SHEOHAR DISTRICTS | BPCL | N16000524 | 12-2022 | 3/2030 | N.A. | 3/2030 | 3638 |  | 3638 | 381.17 | 19.7
May 2025 |  | POWER | 203 | BARH STPP(3X660MW) NTPC | NTPC | 180100242 | 2-2005 | 10/2011 | Jul-2023 | 3/2025 | 8692.97 | 21312.11 | 21312.11 | 22290.14 | 95
May 2025 |  | POWER | 204 | BUXAR THERMAL POWER PLANT (1320 MW) | SJVN | N18000194 | 3-2019 | 1/2024 | N.A. | 10/2025 | 10439.09 |  | 14390.09 | 11676 | 90.92
May 2025 |  | POWER | 205 | EASTERN REGION EXPANSION SCHEME: 43 [ERES: 43] | PGCIL | N18000421 | 5-2025 | 5/2026 | N.A. | 5/2026 | 343 |  | 343 | 0
May 2025 |  | POWER | 206 | EASTERN REGION EXPANSION SCHEME: 44 [ERES: 44] | PGCIL | N18000422 | 5-2025 | 5/2026 | N.A. | 5/2026 | 409 |  | 409 | 0
May 2025 |  | POWER | 207 | KHAGARIA-KUSHESHWAR ASTHAN (NL) | ECR | ECR | 4-1997 | 12/2024 | N.A. | 3/2027 | 614.45 | 614.45 | 614.45 | 483.35 | 52
May 2025 |  | POWER | 208 | HAJIPUR-SUGAULI VIA VAISHALI (NL), ECR | ECR | 220100303 | 4-2003 | 12/2014 | N.A. | 12/2026 | 2066.78 | 2087.36 | 2087.36 | 2334.96 | 73
May 2025 |  | POWER | 209 | NEW B.G. LINE FROM ARARIA TO GALGALIA (THAKURGUNG), NEFR | NFR | N22000087 | 9-2006 | 12/2024 | N.A. | 6/2025 | 2650 | 2132.03 | 4412.25 | 3917.04 | 90
May 2025 |  | POWER | 210 | SAKRI-HASANPUR ROAD (NL) | ECR | N22000171 | 4-1999 | (N.A.) | {3/2027} |  | 325 | 735.2 | 735.2 | 603.44 | 78
May 2025 |  | POWER | 211 | ARARIA-SUPAUL (NL) | ECR | N22000177 | 4-2008 | 3/2024 | N.A. | 5/2025 | 1605.17 | 1605.17 | 1605.17 | 1697.58 | 65
May 2025 |  |  | 212 | JAYNAGAR-BIJALPURA INCLUDING EXTENSION BIJALPURA-BARDIBAS(NEPAL) GC | ECR | N22000181 | 4-2009 | 3/2022 | N.A. | 3/2026 | 819 | 548 | 783.83 | 544.31 | 75
May 2025 |  |  | 213 | SAMASTIPUR-DARBANGHA | ECR | N22000329 | 5-2015 | 3/2025 | N.A. | 10/2025 | 519.33 | 519.33 | 519.33 | 640.68 | 80
May 2025 |  |  | 214 | KIUL - GAYA DOUBLING PROJECT | ECR | N22000349 | 12-2015 | 9/2024 | N.A. | 2/2025 | 2462.11 | 1200.2 | 1771.07 | 1866.29 | 99
May 2025 |  |  | 215 | RAMPUR DUMRA - TAL - RAJENDRAPUL DOUBLING INCLUDING GANGA BRIDGE | ECR | N22000350 | 12-2015 | 12/2024 | N.A. | 12/2025 | 2373.64 | 1491.47 | 1600 | 1763.21 | 77
May 2025 |  |  | 216 | SAGAULI VALMIKINAGAR DOUBLING 109.7 KM | ECR | N22000472 | 4-2016 | 12/2024 | N.A. | 6/2025 | 1215.54 | 1215.54 | 1215.54 | 1577.26 | 91
May 2025 |  |  | 217 | MUZAFFARPUR SAGAULI DOUBLING 100.60 KM | ECR | N22000473 | 4-2016 | 6/2024 | N.A. | 5/2025 | 1586.22 | 1185.73 | 1300 | 1477.91 | 96
May 2025 |  |  | 218 | FATUHA-ISLAMPUR INCL. MM FOR EXTENSION OF NEW LINE FORM BIHARSHARIF-BARBIGHA, DANIYAWAN- BIHARSHARIF, | ECR | N22000476 | 4-1991 | 3/2023 | N.A. | 5/2025 | 1473.3 | 803.09 | 2722.16 | 2786.29 | 90
May 2025 |  |  | 219 | BARAUNI- BACHWARA 3RD AND 4TH LINE | ECR | N22000524 | 7-2022 | 7/2027 | N.A. | 12/2025 | 486 |  | 486 | 128.43 | 33
May 2025 |  |  | 220 | JHAJHA - BATIA (UMBRELLA WORK PB#23/2018-19/NR) | ECR | N22000526 | 2-2019 | 6/2028 | N.A. | 12/2026 | 496.47 |  | 496.47 | 22.53
May 2025 |  |  | 221 | SONENAGAR BYE PASS LINE FROM CHIRALAPOTHU TO BAGHA BISHUNPUR | ECR | N22000528 | 10-2022 | 10/2027 | N.A. | 12/2026 | 234 | 223.69 | 223.69 | 22.57
May 2025 |  |  | 222 | KATIHAR-KUMEDPUR AND KATIHAR- MUKURIA (64.5 KM) (UMBRELLA WORK PB#57/2019-20/NR) | NFR | N22000570 | 8-2022 | 8/2027 | N.A. | 8/2026 | 745 |  | 942.64 | 336.83 | 35
May 2025 |  |  | 223 | PATNA-MUZZAFFARPUR | NHAI | N24000165 | 8-2010 | 2/2013 | N.A. | 6/2025 | 671.3 |  | 671.3 | 1830.13 | 98.87
May 2025 |  |  | 224 | 4-LANNING OF CHAPRA-HAJIPUR | NHAI | N24000187 | 1-2011 | 7/2013 | Jan-2026 | 1/2026 | 575 |  | 575 | 573.48 | 89.81
May 2025 |  |  | 225 | REHABILITATION AND UPGRADING TO 2 LANES/2 LANE WITH PAVED SHOULDERS CONFIGURATION OF BIRPUR - BIHPUR | MoRTH | N24000382 | 1-2014 | 10/2019 | Jun-2025 | 6/2025 | 675 |  | 780.77 | 764.69 | 96
May 2025 |  |  | 226 | FOUR OF SIMARIA - KHAGARIA SECTION OF NH-31 | NHAI | N24000480 | 12-2015 | 4/2019 | Mar-2025 | 7/2025 | 1041.1 | 567 | 639.58 | 553.73 | 97.58
May 2025 |  |  | 227 | FOUR LANING OF BAKHTIYARPUR - MOKAMA SECTION OF NH-31 | NHAI | N24000507 | 12-2015 | 12/2019 | N.A. | 8/2025 | 1167.45 |  | 1182.94 | 753.72 | 99.43
May 2025 |  |  | 228 | REHABILITATION AND UPGRADING TO 2 LANES/2 LANE WITH PAVED SHOULDERS (KM 40 TO KM 219.945) OF NH-104 | MoRTH | N24000531 | 2-2016 | 11/2018 | N.A. | 5/2025 | 319.68 |  | 503.28 | 453 | 99
May 2025 |  |  | 229 | CONSTRUCTION OF REHABILITATION AND UPGRADING TO 2 LANES/2 LANE(FOR LOT-I- KM 40.00 TO KM 65.400 AND K | MoRTH | N24000576 | 2-2016 | 5/2016 | N.A. | 5/2025 | 178.85 |  | 278.54 | 232.61 | 98
May 2025 |  |  | 230 | PROCUREMENT, AND CONSTRUCTION OF REHABILITATION AND UPGRADING TO 2 LANES/2 LANE(FOR LOT-III-KM 156.5 | MoRTH | N24000578 | 2-2016 | 5/2016 | N.A. | 5/2025 | 553.3 |  | 706.39 | 712.38 | 98
May 2025 |  |  | 231 | FOUR LANING OF GAYA-HISUA-RAJGIRI- NALANDA-BIHARSHARIF SECTION (KM0.00 TO 92.935) ON NH-82 IN BIHAR | MoRTH | N24000579 | 1-2014 | 10/2016 | Jun-2025 | 6/2025 | 1408.85 |  | 2138.16 | 1738.55 | 97
May 2025 |  |  | 232 | TWO-LANNING WITH PAVED SHOULDER OF MAHSHKUNT-SAHARSA-PURNEA SECTION FROM EXISTING KM.89.020 (DESIGN | NHAI | N24000665 | 3-2017 | 3/2020 | Dec-2025 | 12/2025 | 672.89 | 893.92 | 893.92 | 714.74 | 86.71
May 2025 |  |  | 233 | SIX LANNING OF AUNTA-SIMARIA(GANGA BRIDGE WITH APPROACH ROADS) SECTION OF NH-31 | NHAI | N24000696 | 8-2017 | 2/2022 | Oct-2024 | 6/2025 | 950.64 | 1161 | 1168.33 | 1156.29 | 99.53
May 2025 |  |  | 234 | CONSTRUCTION OF NEW LINK (NH-133B) FROM KM 0/00 (KM 200/87 OF SAHIBANJ BYPASS) IN JHARKHAND TO KM 15 | NHAI | N24000714 | 12-2017 | 10/2024 | Apr-2025 | 12/2026 | 2598 |  | 1978.01 | 1410.14 | 77.46
May 2025 |  |  | 235 | REHABILITATION AND UPGRADATION OF TWO LANING OF MAHESHKHUNT - SAHARSA - PURNEA SECTION PKG - I | NHAI | N24000723 | 1-2018 | 12/2021 | Aug-2025 | 12/2025 | 573.7 | 644.5 | 726.99 | 492.33 | 82.27
May 2025 |  |  | 236 | DEVELOPMENT OF NEWLY DECLARED NH- 527C FROM MAJHAULI TO CHAROUT SECTION TO 2 LANE WITH PAVED SHOULDER | NHAI | N24000813 | 3-2018 | 11/2021 | Dec-2024 | 8/2025 | 496.2 | 470.18 | 470.18 | 399.41 | 98.25
May 2025 |  |  | 237 | CONSTRUCTION OF A NEW 4 LANE MAJOR BRIDGE ACROSS RIVER KOSI AT PHULAUT INCLUDING RHABILITATION AND | MoRTH | N24000943 | 9-2018 | 6/2024 | May-2026 | 5/2026 | 1478.4 |  | 1478.4 | 941.27 | 70
May 2025 |  |  | 238 | CONSTRUCTION OF A NEW 4 LANE BRIDGE PARALLEL TO EXISTING MG SETU WITH ITS APPROACHES FROM KM 0.00 | MoRTH | N24001201 | 2-2019 | 9/2024 | N.A. | 9/2026 | 2926.42 |  | 2926.42 | 1300.42 | 56
May 2025 |  |  | 239 | BALANCE WORK OF 4- LANING OF PATNA- GAYA-DOBHI SECTION (KM. 0.00 TO KM. 127.217) OF NH-83 IN THE STAT | NHAI | N24001303 | 10-2013 | 12/2020 | Dec-2024 | 12/2024 | 649.9 |  | 750 | 711.53 | 98.3
May 2025 |  |  | 240 | BALANCE WORK OF 4- LANING OF PATNA- GAYA-DOBHI SECTION (KM. 39.00 TO KM. 83.00) OF NH-83 IN THE STATE | NHAI | N24001304 | 10-2013 | 11/2020 | Dec-2024 | 12/2024 | 446.97 | 598.48 | 740.5 | 638.8 | 96.3
May 2025 |  |  | 241 | BALANCE WORK OF 4- L ANING OF PATNA- GAYA-DOBHI SECTION (KM.83.00 TO KM. 127.217) OF NH-83 IN THE STA | NHAI | N24001305 | 10-2013 | 11/2020 | Dec-2024 | 12/2024 | 464.09 | 605.53 | 765.12 | 698.25 | 97.3
May 2025 |  |  | 242 | CONSTRUCTION OF 2 LANE BRIDGE ACROSS RIVER KOSI WITH APPROACH ROAD FROM BHEJA TO BAKAUR SECTION OF N | NHAI | N24001371 | 10-2019 | 8/2023 | Apr-2026 | 4/2026 | 1101.99 |  | 1101.99 | 874.95 | 77.4
May 2025 |  |  | 243 | 4L GREENFIELD ALIGNMENT FROM KALYANAPUR TO TAL DASHRAHA OF NH- 119D (PKG-III) | NHAI | N24001697 | 2-2023 | 2/2025 | N.A. | 12/2025 | 1358 |  | 1358 | 188.08 | 19.06
May 2025 |  |  | 244 | FOUR LANING OF MUNGER TO MIRZACHAUKI (NH-80) SECTION FROM NEAR RASULPUR TO MIRZACHAUKI (DESIGN CH | NHAI | N24001698 | 8-2022 | 8/2024 | Dec-2025 | 12/2025 | 1198.02 |  | 1198.02 | 14.85
May 2025 |  |  | 245 | CONSTRUCTION OF 4 LANE ELEVATED SECTION AND AT- GRADE IMPROVEMENTS AT BEGUSARAI TOWN SECTION OF NH-3 | NHAI | N24001699 | 3-2022 | 12/2024 | Dec-2025 | 12/2025 | 312.58 |  | 312.58 | 196.82 | 82.06
May 2025 |  |  | 246 | SIX LANNING OF AURANGABAD TO BIHAR/JHARKHAND BORDER SECTION OF NH-19 (OLD NH-2) FROM KM. 209.827 TO | NHAI | N24001700 | 12-2021 | 3/2024 | Dec-2024 | 12/2024 | 552.55 | 553 | 553 | 378.25 | 86.6
May 2025 |  |  | 247 | FOUR LANING OF MUNGER TO MIRZACHAUKI (NH-80) SECTION FROM START OF EXISTING BHAGALPUR BYPASS TO RASU | NHAI | N24001701 | 4-2022 | 4/2024 | Sep-2025 | 9/2025 | 1769.5 |  | 1769.5 | 51.61
May 2025 |  |  | 248 | CONSTRUCTION OF 4 LANE ELEVATED HIGHWAY AND AT-GRADE IMPROVEMENTS AT GOPALGANJ TOWN FROM DESIGN CH: | NHAI | N24001702 | 12-2021 | 9/2024 | N.A. | 6/2025 | 184.9 | 185 | 185 | 164.63 | 99.78
May 2025 |  |  | 249 | 6 L OF AURANGABAD TO BIHAR- JHARKHAND BORDER (CHORDAHA) SECTION FROM KM. 180.000 TO KM. 209.827 OF N | NHAI | N24001703 | 2-2022 | 5/2025 | N.A. | 5/2025 | 786.81 | 787 | 787 | 0 | 8.3
May 2025 |  |  | 250 | FOUR LANING OF MUNGER TO MIRZACHAUKI (NH-80) SECTION FROM KHARIA VILLAGE JUNCTION TO START OF EXISTI | NHAI | N24001704 | 3-2021 | 3/2024 | Sep-2025 | 9/2025 | 1020.84 |  | 1020.84 | 118.96
May 2025 |  |  | 251 | FOUR LANING OF MUNGER TO MIRZACHAUKI (NH-80) SECTION FROM MUNGER TO KHARIA VILLAGE JUNCTION DESIGN C | NHAI | N24001705 | 3-2022 | 3/2024 | Dec-2025 | 12/2025 | 1485.66 |  | 1485.66 | 35.16
May 2025 |  |  | 252 | BAKHTIYARPUR RAJAULI PKG-II FROM KM 54.405 TO KM 101.630 NH20 | NHAI | N24001709 | 9-2020 | 4/2023 | Dec-2024 | 12/2024 | 897.45 |  | 1090 | 1037.63 | 97.85
May 2025 |  |  | 253 | FOUR LANING OF PARARIA TO MOHANIA SECTION OF NH 319 (OLD NH 30) FROM KM. 54+530 (DESIGN CHAINAGE) TO | NHAI | N24001712 | 8-2020 | 7/2023 | May-2025 | 5/2025 | 690 |  | 690 | 770.73 | 98.8
May 2025 |  |  | 254 | BALANCE WORK OF TWO LANING WITH PAVED SHOULDER OF PIPRAKOTHI?MOTIHARI- RAXAUL SECTION OF NH-28A FRO | NHAI | N24001715 | 12-2018 | 10/2020 | N.A. | 1/2024 | 333.6 | 466.59 | 461.41 | 460.38 | 100
May 2025 |  |  | 255 | IMPROVEMENT TO TWO LANE WITH PAVED SHOULDERS OF NH 122B FROM KM 29.730 TO KM 72.348 IN STATE OF BIH | MoRTH | N24001870 | 2-2022 | 11/2024 | N.A. | 11/2025 | 624.43 |  | 624.43 | 280.98 | 82
May 2025 |  |  | 256 | WIDENING AND STRENTHENING FROM KM 70.15 TO KM 121.025 OF NH-80 | MoRTH | N24001875 | 3-2021 | 1/2025 | N.A. | 6/2025 | 477.54 |  | 477.54 | 334.36 | 90
May 2025 |  |  | 257 | WIDENING and STRENTHENING FROM KM132.895 TO KM 190.15 NH-80 | MoRTH | N24001876 | 3-2021 | 3/2024 | N.A. | 9/2025 | 566.15 |  | 566.15 | 239.2 | 56
May 2025 |  |  | 258 | CONSTRUCTION OF NEW 4-LANE BRIDGE (PARALLEL TO EXISTING VIKRAMASHILA SETU)FROM KM 8+920 TO KM 13+375 | MoRTH | N24001877 | 7-2020 | 5/2027 | N.A. | 5/2027 | 1110.23 |  | 1110.23 | 425.49 | 40
May 2025 |  |  | 259 | IMPROVEMENT TO TWO LANE WITH PAVED SHOULDERS OF NH-319A FROM KM 0 TO KM 45 IN STATE OF BIHAR UNDER | MoRTH | N24001878 | 2-2022 | 12/2024 | N.A. | 7/2025 | 427.29 |  | 427.29 | 197.04 | 78
May 2025 |  |  | 260 | CONSTRUCTION OF PROPOSED 4_LANE REVELGUNJ BYPASS NH-19 IN THE STATE OF BIHAR ON EPC MODE CONNECTING | MoRTH | N24001879 | 3-2022 | 7/2025 | N.A. | 7/2025 | 295.24 |  | 295.24 | 77.05 | 53
May 2025 |  |  | 261 | CONSTRUCTION OF 6- LANE BRIDGE AND ITS APPROACHES ACROSS RIVER GANGA AS PART OF PATNA RING ROAD (NH- | NHAI | N24002062 | 3-2023 | 9/2027 | N.A. | 9/2027 | 3012.27 |  | 3012.27 | 263.36 | 9.12
May 2025 |  |  | 262 | BALANCE WORK - WB-10 (GANDAK BRIDGE) KM 402.00 TO KM 440.00 (DEVANPUR - KOTWA) | NHAI | N24002063 | 12-2021 | 1/2024 | N.A. | 3/2026 | 210.05 |  | 210.05 | 104.35 | 69
May 2025 |  |  | 263 | PERMANENT RECTIFICATION OF 3 NOS. OF BLACK SPOTS IN PROJECT HIGHWAY NH-27 OF U.P BORDER - DEWAPUR - | NHAI | N24002064 | 12-2022 | 12/2025 | N.A. | 12/2025 | 381.8 |  | 381.8 | 115.37 | 48
May 2025 |  |  | 264 | 4L GREENFIELD ALIGNMENT OF AMAS TO SHIVRAMPUR FROM 0.000 KM. TO 55.002 KM. OF NH 119 D (PKG-I) | NHAI | N24002065 | 2-2022 | 3/2025 | N.A. | 3/2025 | 1390.92 |  | 1390.92 | 17.54 | 22.56
May 2025 |  |  | 265 | 4L GREENFIELD ALIGNMENT OF SHIVRAMPUR TO RAMNAGAR FROM KM. 55.002 TO KM. 109.300 OF NH 119 D (PKG-I | NHAI | N24002066 | 2-2022 | 7/2025 | N.A. | 7/2025 | 1494.31 |  | 1494.31 | 38.28 | 4.59
May 2025 |  |  | 266 | IMPROVEMENT OF 2 LANE WITH PAVED SHOULDER OF STRETCH FROM BIKRAMGANJ DAWATH MELAYABAGH NAWANAGR -DUM | MoRTH | N24002133 | 3-2021 | 3/2025 | N.A. | 6/2025 | 178.63 |  | 178.63 | 116.16 | 91
May 2025 |  |  | 267 | CONSTRUCTION OF 4 LANE ROB AND ITS APPROACHES AT THE LEVEL OF CROSSING (L C NO. 29-B) OF KM 29 (EKAN | MoRTH | N24002193 | 3-2023 | 7/2026 | N.A. | 7/2026 | 201.08 |  | 201.08 | 25.42 | 25
May 2025 |  |  | 268 | CONSTRUCTION OF 6-LANE ELEVATED / EXTRA DOSE CABLE BRIDGE ON RIVER GANGA PARALLEL TO AND WESTERN SID | MoRTH | N24002194 | 1-2024 | 11/2027 | N.A. | 11/2027 | 3064.45 |  | 3064.45 | 78.87 | 2
May 2025 |  |  | 269 | ESTIMATE FOR IMPROVEMENT TO TWO LANE WITH PAVED SHOULDER FROM RAMNAGAR TO ROSEDA FROM (KM 3.500 TO 4 | MoRTH | N24002195 | 1-2022 | 4/2026 | N.A. | 4/2026 | 495.16 |  | 495.16 | 129.17 | 10
May 2025 |  |  | 270 | CONSTRUCTION OF BHABHUA BYPASS FROM CH. 10+800(DESIGN CH. 10+800) TO CH. 19+860 (DESIGN CH. 18+150) | MoRTH | N24002196 | 2-2022 | 3/2026 | N.A. | 7/2026 | 179.86 |  | 179.86 | 25.07 | 0.03
May 2025 |  |  | 271 | IMPROVEMENT TO TWO LANE WITH PAVED SHOULDER FROM JUNCTION OF NH-22 NEAR HAJIPUR TO JUNCTION OF NH-12 | MoRTH | N24002197 | 2-2024 | 2/2026 | N.A. | 2/2026 | 226.15 |  | 226.15 | 9.77 | 13
May 2025 |  |  | 272 | IMPROVEMENT TO TWO LANE WITH PAVED SHOULDERS OF BH/WBBORDER-AMDABAD- MANIHARI SECTION FROM DESIGN KM | MoRTH | N24002198 | 1-2022 | 3/2026 | N.A. | 3/2026 | 353.27 |  | 353.27 | 25.33
May 2025 |  |  | 273 | PERMANENT RECTIFICATION OF 4 NOS. OF BLACKSPOTS ON NH 27 OF KOTWA MEHSI MUZAFFARPUR SECTION FROM | NHAI | N24002220 | 12-2022 | 11/2026 | N.A. | 11/2026 | 410.75 |  | 410.75 | 35.27 | 25.07
May 2025 |  |  | 274 | 4L OF GREENFIELD ALIGNMENT FROM KM. 47.000 TO KM. 89.210 OF BALBHADARPUR TO BELA NAWDA SECTION OF NH | NHAI | N24002221 | 2-2022 | 3/2026 | N.A. | 3/2026 | 2185.75 |  | 2185.75 | 513.47 | 11.48
May 2025 |  | URBAN DEVELOPMENT | 275 | PATNA METRO RAIL CORPORATION LIMITED | PATNA METRO RAI | N28000148 | 2-2019 | 6/2024 | N.A. | 9/2024 | 13365.77 |  | 13925.5 | 3158.18 | 44
May 2025 |  | WATER RESOURCES | 276 | SEWER NETWORK SPS AND STP BEGUSARAI | BUIDCO | N30000026 | 3-2018 | 7/2021 | Dec-2019 | 4/2025 | 230.06 |  | 230.06 | 261.47 | 97
May 2025 |  | WATER RESOURCES | 277 | I AND D AND STP WORKS FOR BHAGALPUR | BUIDCO | N30000027 | 10-2017 | 9/2020 | Nov-2020 | 4/2025 | 254.13 | 413.29 | 413.29 | 126.67 | 90
May 2025 |  | WATER RESOURCES | 278 | SEWER NETWORKS SPS AND STP HAJIPUR | BUIDCO | N30000035 | 3-2018 | 8/2021 | Mar-2018 | 6/2025 | 305.19 |  | 305.19 | 346.46 | 95
May 2025 |  | WATER RESOURCES | 279 | SEWER NETWORKS, SPS AND STP, MUNGER | BUIDCO | N30000036 | 3-2018 | 10/2021 | Mar-2018 | 6/2024 | 294.02 | 350.79 | 522.85 | 428.7 | 100
May 2025 |  | WATER RESOURCES | 280 | SAIDPUR SEWER NETWORK PATNA | BUIDCO | N30000039 | 4-2015 | 1/2021 | N.A. | 6/2022 | 268.63 |  | 493.85 | 491.13 | 100
May 2025 |  | WATER RESOURCES | 281 | SEWERAGE SYSTEM WITH SEWER NETWORK PATNA KARMALICHAK | BUIDCO | N30000044 | 3-2017 | 5/2021 | Mar-2017 | 2/2023 | 277.42 | 253.98 | 277.42 | 355.31 | 100
May 2025 |  | WATER RESOURCES | 282 | SEWERAGE SYSTEM AND STP FOR KANKARBAG ZONE PATNA | BUIDCO | N30000050 | 8-2017 | 6/2022 | N.A. | 12/2025 | 578.89 | 453.83 | 578.89 | 164.87 | 52
May 2025 |  | WATER RESOURCES | 283 | SEWERAGE SYSTEM AND STP FOR DIGHA ZONE, PATNA | BUIDCO | N30000051 | 8-2017 | 6/2022 | N.A. | 12/2025 | 824 | 734.09 | 824 | 384.17 | 55
May 2025 |  | WATER RESOURCES | 284 | GEVRA EXPANSION OCP (SECL) (35-70) MTY | SECL | 060100093 | 6-2010 | 3/2023 | Mar-2026 | 3/2026 | 11816.4 |  | 11816.4 | 6596.25 | 77.2
May 2025 |  | WATER RESOURCES | 285 | PELMA OCP(15.00MTY) | SECL | N06000045 | 10-2022 | 3/2023 | N.A. | 3/2033 | 1624.59 |  | 1725.04 | 15.53 | 17
May 2025 |  | WATER RESOURCES | 286 | CHHAL OC SEAM -III (6.00 MTY) | SECL | N06000104 | 12-2013 | 3/2022 | Jun-2025 | 6/2025 | 610.63 |  | 610.63 | 576.24 | 85
May 2025 |  |  | 287 | AMERA OC RCE | SECL | N06000123 | 2-2015 | 3/2018 | Mar-2026 | 3/2026 | 335.97 |  | 335.97 | 86.98 | 42
May 2025 |  |  | 288 | AMGAON OPENCAST PROJECT RCE | SECL | N06000135 | 7-2015 | 3/2020 | Mar-2026 | 3/2026 | 316.1 |  | 316.1 | 188.33 | 71
May 2025 |  |  | 289 | MAHAMAYA OPENCAST PROJECT | SECL | N06000164 | 5-2018 | 3/2026 | N.A. | 3/2026 | 410.26 |  | 410.26 | 180.18 | 38
May 2025 |  |  | 290 | JHIRIA WEST OPENCAST PROJECT | SECL | N06000166 | 1-2024 | 3/2029 | N.A. | 3/2029 | 366.94 |  | 366.94 | 33.37 | 41
May 2025 |  |  | 291 | BAROUD OC EXPANSION (3-10 MTY) | SECL | N06000197 | 8-2020 | 3/2029 | N.A. | 3/2029 | 2309.8 |  | 2309.8 | 911.51 | 41
May 2025 |  |  | 292 | JAMPALI OCP RCE | SECL | N06000198 | 5-2020 | 3/2024 | Mar-2025 | 6/2025 | 278.64 |  | 278.64 | 209.34 | 82
May 2025 |  |  | 293 | PORDA CHIMTAPANI OCP (10 MTY) | SECL | N06000199 | 12-2020 | 3/2029 | N.A. | 3/2029 | 2310.12 |  | 2310.12 | 47.65 | 10
May 2025 |  |  | 294 | DIPKA OC EXPANSION 40 MTY | SECL | N06000200 | 12-2020 | 3/2029 | N.A. | 3/2029 | 5241.4 |  | 5241.4 | 2820.23 | 37.3
May 2025 |  |  | 295 | JAGANNATHPUR OC RCE (3.0 MTY) | SECL | N06000232 | 7-2016 | 3/2020 | Mar-2026 | 3/2026 | 459.49 |  | 459.49 | 263.51 | 92
May 2025 |  |  | 296 | KATKONA RO UG PROJECT (1.74 MTY) | SECL | N06000274 | 1-2023 | 3/2029 | N.A. | 3/2029 | 329.22 |  | 329.22 | 60.38 | 2
May 2025 |  | DEPARTMENT OF HIGHER EDUCATION | 297 | C/O PERMANENT CAMPUS OF IIT BHILAI AT KUTHELABHATA, DURG CHHATTISGARH, STAGE I PHASE I. | CPWD EDUCATION | N28000141 | 3-2020 | 7/2022 | Feb-2024 | 3/2024 | 808.62 | 879.22 | 808.62 | 640.7 | 100
May 2025 |  | POWER | 298 | WESTERN REGION EXPANSION SCHEME XXV | PGCIL | N18000350 | 2-2023 | 11/2023 | N.A. | 6/2025 | 385.84 |  | 385.84 | 369.79 | 93
May 2025 |  | POWER | 299 | LARA SUPER THERMAL POWER PROJECT, STAGE-II (2X800 MW) | NTPC | N18000381 | 8-2023 | 6/2028 | N.A. | 6/2028 | 15530 |  | 15530 | 1636.45 | 6.5
May 2025 |  | POWER | 300 | KIRANDUL - JAGDALPUR DOUBLING | ECOR | N22000318 | 12-2012 | 3/2020 | N.A. | 3/2024 | 1588.7 |  | 1553.11 | 1526.84 | 94.8
May 2025 |  | POWER | 301 | JHARSUGUDA-BILASPUR 4TH LINE | SECR | N22000484 | 4-2015 | 10/2024 | Dec-2023 | 12/2025 | 2140.34 | 2135.34 | 2135.34 | 2280.8 | 88
May 2025 |  |  | 302 | KHARSIA DHARAMJAIGARH WITH SPUR LINE EAST CORRIDOR-PHASE I | IRCON | N22000489 | 4-2013 | 9/2018 | N.A. | 3/2026 | 3055 |  | 3438.39 | 3117.24 | 92.8
May 2025 |  |  | 303 | Gauge conversion of Raipur(Kendri)-Dhamtari and Abhanpur-Rajim branch (67.20 km) | SECR | N22000572 | 7-2011 | 10/2024 | N.A. | 6/2025 | 1171.3 |  | 1171.3 | 617.69 | 82
May 2025 |  |  | 304 | NIPANIA-BHATAPRA (14.4 KM) 4TH LINE | PB#72/NR/2022-23 | SECR | 9-2022 | 12/2026 | N.A. | 12/2026 | 170.49 |  | 170.49 | 0.13 | 2
May 2025 |  |  | 305 | 4TH LINE - BHATAPARA-HATHBAND (8.8 KM) | PB#72/NR/2022-23 | SECR | 12-2022 | 12/2026 | N.A. | 12/2026 | 177.03 |  | 177.03 | 6.23 | 2
May 2025 |  |  | 306 | 4TH LINE - BHILAI-BHILAI NAGAR (8.8 KM) | PB#72/NR/2022-23 | SECR | 9-2022 | 9/2026 | N.A. | 9/2026 | 169.06 |  | 177.34 | 1.72 | 2
May 2025 |  |  | 307 | 4TH LINE - DADHAPARA-BELHA (9.2 KM) | PB#72/NR/2022-23 | SECR | 9-2022 | 9/2026 | N.A. | 9/2026 | 169.06 |  | 169.06 | 15.66 | 30
May 2025 |  |  | 308 | 4TH LINE - RAJNANDGAON-DONGARHGARH | 31.2 KM) (PB#72/NR/2022-23 | SECR | 9-2022 | 9/2026 | N.A. | 9/2026 | 328.34 |  | 328.34 | 36.65 | 20
May 2025 |  |  | 309 | 3RD AND 4TH LINE - SARAGBUNDIA AND MADWARANI | SECR | N22000579 | 9-2022 | 9/2026 | N.A. | 9/2026 | 167.64 |  | 167.64 | 0
May 2025 |  |  | 310 | DOUBLING OF BORIDAND - AMBIKAPUR ( SURAJPUR) | SECR | N22000580 | 6-2022 | 6/2030 | N.A. | 3/2027 | 1376.2 | 1242.94 | 1242.94 | 193.79 | 12
May 2025 |  |  | 311 | DALLIRAJHARA - ROWGHAT (95 KM) {PART OF DALLIRAJHARA-JAGDALPUR (235 KM)} | RVNL | N22000602 | 3-2008 | 6/2025 | N.A. | 6/2025 | 1627.56 |  | 1627.56 | 1349.09
May 2025 |  |  | 312 | CHIRIMIRI-NAGPUR HALT | SECR | N22000616 | 10-2018 | 6/2030 | N.A. | 6/2030 | 241 |  | 241 | 0
May 2025 |  |  | 313 | REHABILITATION AND UPGRADATION OF NH 43 KANKER TO BEDMA SECTION KM. 130 TO 180 | MoRTH | N24001217 | 1-2016 | 8/2016 | N.A. | 6/2025 | 497.14 | 572.66 | 572.66 | 385.27 | 60
May 2025 |  |  | 314 | REHABILITATION AND UPGRADATION OF NH 78 FROM KM 373.505 TO 469.300 AMBIKAPUR TO PATHALGAON SECTION | MoRTH | N24001221 | 1-2016 | 10/2016 | N.A. | 3/2025 | 624.98 |  | 731.5 | 620.67 | 100
May 2025 |  |  | 315 | REHABILITATION AND UPGRADATION OF NH 78 FROM KM 469.000 TO 531.000 PATTHALGAON TO KUNKURI | MoRTH | N24001222 | 3-2016 | 7/2016 | N.A. | 12/2025 | 452.94 |  | 435.61 | 322.59 | 70
May 2025 |  |  | 316 | CONSTRUCTION OF 4 NOS GRADE SEPARATOR BETWEEN KM. 281.000 TO KM 307.600 KM. 286.400 KUMHARI KM. 299. | MoRTH | N24001227 | 3-2018 | 1/2019 | N.A. | 5/2025 | 349.03 |  | 349.03 | 316.52 | 98
May 2025 |  |  | 317 | UPGRADATION AND WIDENING OF BILASPUR TO MUNGELI SECTION NH-130A | MoRTH | N24001228 | 11-2017 | 5/2019 | N.A. | 5/2025 | 188.8 |  | 188.8 | 136.81 | 97
May 2025 |  |  | 318 | DEVELOPMENT OF SIX LANE SARGI- BASANWAHI OF NH 130 CD FROM KM.42+800 TO 99+500 UNDER RAIPUR VISAKHAPA | NHAI | N24001588 | 12-2021 | 1/2025 | N.A. | 12/2025 | 1470.73 |  | 1470.73 | 646.79 | 79
May 2025 |  |  | 319 | DEVELOPMENT OF SIX LANE JHANKI SARGI OF NH 130 CD FROM KM.0+000 TO 42+800 UNDER RAIPUR VISAKHAPATTNA | NHAI | N24001593 | 11-2021 | 9/2024 | N.A. | 4/2026 | 1368.19 |  | 1368.19 | 896.51 | 96.4
May 2025 |  |  | 320 | 4 LANE OF BILASPUR TO URGA PROJECT (KM 0.00 TO KM 70.2) OF NH-130A | NHAI | N24001611 | 4-2020 | 3/2024 | N.A. | 12/2025 | 1855.59 | 2523.86 | 2523.86 | 594.46 | 93.03
May 2025 |  |  | 321 | UP GRADATION OF NH 930 SHERPAR TO KOHKA FROM KM 67.880 TO KM 114.860 TO TWO LANE WITH PAVED SHOULDER | MoRTH | N24001917 | 3-2020 | 5/2024 | N.A. | 6/2025 | 278.97 |  | 278.97 | 206.61 | 87
May 2025 |  |  | 322 | UP GRADATION OF NH 130C ABHANPUR TO PAUND FROM NK KM 0.000 TO KM. 40.380 TO TWO LANE WITH PAVED SHOU | MoRTH | N24001919 | 12-2020 | 9/2023 | Feb-2025 | 6/2025 | 193.16 |  | 193.16 | 103.83 | 81
May 2025 |  |  | 323 | UPGRADATION OF NH 130A MUNGELI TO PONDI FROM NH KM. 51.600 TO KM. 77.870 KM. 80.970 TO 96.970 TO 2 | MoRTH | N24001920 | 3-2021 | 9/2024 | N.A. | 5/2025 | 218.57 |  | 218.57 | 136.26 | 89
May 2025 |  |  | 324 | DEVELOPMENT OF SIX LANE BASANWAHI- MARANGPURI OF NH 130 CD FROM KM.99+500 TO 124+661 UNDER RAIPUR VIS | NHAI | N24002017 | 3-2022 | 10/2025 | N.A. | 9/2026 | 1307.16 |  | 1307.16 | 252.68 | 33.05
May 2025 |  |  | 325 | CONSTRUCTION OF 6 LANE DURG RAIPUR ARANG BYPASS PKG 1 SECTION OF NH 53 FROM CH 0.000 TO CH 44.50 | NHAI | N24002045 | 6-2022 | 7/2025 | N.A. | 7/2025 | 1828 |  | 1828 | 543.14 | 44.72
May 2025 |  |  | 326 | CONSTRUCTION OF 6 LANE DURG RAIPUR ARANG BYPASS PKG 2 SECTION OF NH 53 FROM CH 44+500 TO CH.92+230 I | NHAI | N24002046 | 6-2022 | 5/2025 | N.A. | 5/2025 | 1958.94 | 1959 | 1958.94 | 690.46 | 40.01
May 2025 |  |  | 327 | NMDC SLURRY PIPE LINE PROJECT - PHASE-1 | NMDC | N12000124 | 11-2015 | 6/2023 | Jul-2024 | 12/2025 | 2907 | 5427.06 | 5427.06 | 2926.87 | 79.2
May 2025 |  |  | 328 | SCREENING PLANT-III AT KIRANDUL | NMDC | N12000127 | 3-2021 | 8/2024 | N.A. | 1/2026 | 2092.97 | 2718.84 | 2718.84 | 1491.2 | 70.81
May 2025 |  |  | 329 | CONSTRUCTION OF RESIDENTIAL TOWERS AT BIOM KIRANDUL COMPLEX | NMDC | N12000130 | 7-2021 | 11/2024 | N.A. | 12/2025 | 282.44 | 349.75 | 349.75 | 232.34 | 80.66
May 2025 |  |  | 330 | REPLACEMENT OF CONVERTER VESSELS, TRUNNION RINGS, SUPPORT SYSTEM AND INSTALLATION OF SECONDARY EMISS | SAIL | N12000131 | 10-2023 | 6/2026 | N.A. | 6/2026 | 471.83 |  | 471.83 | 92.37 | 24.87
May 2025 |  |  | 331 | REBUILDING OF COKE OVEN BATTERY NO.7 AND 8 OF BHILAI STEEL PLANT | SAIL | N12000134 | 11-2023 | 10/2025 | N.A. | 10/2025 | 884.1 |  | 884.1 | 394.99 | 69.46
May 2025 |  |  | 332 | REPLACEMENT OF HOT LEVELLER-1 OF PLATE MILL AT BHILAI STEEL PLANT | SAIL | N12000137 | 7-2024 | 7/2026 | N.A. | 7/2026 | 198.62 |  | 198.62 | 0 | 5.74
May 2025 |  | URBAN DEVELOPMENT | 333 | CONSTRUCTION729 QUARTERS (TYPE II- 180 TYPE III-364 TYPE IV-112 TYPE V-68 TYPE-VI-5 SHOPS COMMUNI | CPWD | N28000149 | 5-2019 | 9/2020 | Oct-2024 | 10/2024 | 299.97 | 299.97 | 299.97 | 272.05 | 92
May 2025 |  | CIVIL AVIATION | 334 | CONSTRUCTION OF COMBINED OPERATIONAL OFFICES FOR DGCA, BCAS, AAIB, AERA AND AAI AT SAFDARJUNG AIRPOR | AAI | N04000076 | 11-2016 | 4/2020 | Apr-2024 | 4/2024 | 303.8 | 374.98 | 351.21 | 344.65 | 100
May 2025 |  | DPIIT | 335 | INDIA INTERNATIONAL CONVENTION AND EXPO CENTRE | IICC FOR DPIIT | N40000002 | 11-2017 | 12/2019 | N.A. | 4/2025 | 4773 |  | 5401 | 4969.89 | 100
May 2025 |  | FINANCE | 336 | C/O RESIDENTIAL COMPLEX BUILDING FOR CENTRAL BOARD OF INDIRECT TAXES AND CUSTOMS AT SECTOR-9, DWARKA | NPCC | N07000001 | 7-2018 | 4/2022 | N.A. | 4/2022 | 228.5 |  | 220.27 | 176.28 | 85
May 2025 |  | HOME AFFAIRS | 337 | ESTABLISHMENT OF CENTRAL ARMED POLICE FORCE INSTITUTE OF MEDICAL SCIENCES(CAPFIMS) AT NEW DELHI | CPWD FOR MHA | N28000071 | 10-2013 | 10/2019 | N.A. | 9/2024 | 1219.21 | 2091.53 | 2091.53 | 1947.12 | 100
May 2025 |  | HOME AFFAIRS | 338 | CONSTRUCTION OF HEADQUARTER BUILDING OF CRPF AT LODHI ROAD NEW DELHI | CPWD FOR MHA | N45000002 | 6-2019 | 7/2022 | N.A. | 9/2025 | 277.35 |  | 277.35 | 107 | 64
May 2025 |  | RAILWAYS | 339 | ANAND VIHAR-TILAK BRIDGE 3RD AND 4TH LINE | NR | N22000281 | 4-2012 | 3/2023 | N.A. | 6/2026 | 586.36 |  | 699 | 174.22 | 45
May 2025 |  | RAILWAYS | 340 | SIX LANE ACCESS CONTROLLED OF DELHI SAHARANPUR HIGHWAY FROM AKSHARDHAM NH 9 JUNCTION TO DELHI UP BOR | NHAI | N24001771 | 6-2020 | 12/2024 | N.A. | 12/2024 | 1479.22 |  | 1479.22 | 1491.26 | 99
May 2025 |  |  | 341 | 6L ACCESS CONTROLLED HIGHWAY FROM DND MAHARANI BAGH JN. WITH JAITPUR PUSHTA ROAD OF NH 148NA FROM | NHAI | N24001773 | 5-2020 | 7/2024 | N.A. | 9/2025 | 1467.44 |  | 1942.89 | 1189.56 | 90.39
May 2025 |  |  | 342 | DEVELOPMENT OF 6L UER-II (PACKAGE-I) (NH-1 NEAR BAKOLI TILL KARALA KANJHAWALA ROAD) FROM KM. (-)0.70 | NHAI | N24001777 | 7-2020 | 10/2023 | N.A. | 6/2025 | 2171.8 |  | 2171.8 | 958.13 | 99.99
May 2025 |  |  | 343 | DWARKA EXPRESSWAY FROM KM -0.600 TO KM 5.300 - PKG-I (SHIVMURTI CHOWK-RUB NEAR DWARKA SECTOR 21) | NHAI | N24001779 | 3-2018 | 9/2022 | N.A. | 9/2025 | 2507 |  | 3030.73 | 1155.7 | 95.01
May 2025 |  |  | 344 | 8L OF DWARKA EXPRESSWAY PKG-II (RUB NEAR DWARKA SECTOR 21-DL/HR BORDER) FROM 5.300 KM.TO 9.500 KM. O | NHAI | N24001781 | 1-2018 | 10/2021 | N.A. | 6/2025 | 2067.67 |  | 2160 | 1496.49 | 99.35
May 2025 |  |  | 345 | DEVELOPMENT OF 6L UER II [PACKAGE - II] (KARALA KANJHAWALA ROAD TILL NANGLOI - NAJAFGARH ROAD) FROM | NHAI | N24001825 | 7-2020 | 10/2023 | N.A. | 7/2025 | 1894.96 |  | 1894.96 | 741.88 | 94.65
May 2025 |  | TELECOMMUNICATIONS | 346 | SETTING UP PHYSICAL INFRASTRUCTURE FOR THE NATIONAL INSTITUTE OF COMMUNICATION FINANCE(NICF) AT GHIT | CPWD FOR TELECO | N28000115 | 10-2014 | 3/2018 | N.A. | 10/2025 | 248.2 |  | 248.2 | 236.27 | 98
May 2025 |  | TELECOMMUNICATIONS | 347 | DELHI MRTS PHASE-III | DMRC | N28000056 | 9-2011 | 3/2016 | Aug-2021 | 8/2021 | 38585 | 43095.35 | 40180.91 | 40614.9 | 100
May 2025 |  | TELECOMMUNICATIONS | 348 | REDEVELOPMENT OF GPRA COLONY AT NAUROJI NAGAR | NBCC | N28000105 | 7-2016 | (N.A.) | {} |  | 2694 |  | 2694 | 2247.61
May 2025 |  | TELECOMMUNICATIONS | 349 | REDEVELOPMENT OF GENERAL POOL RESIDENTIAL COLONY AT SRINIWASPURI NEW DELHI PHASE-I | CPWD | N28000128 | 10-2016 | 7/2021 | N.A. | 6/2024 | 1180 |  | 1100.8 | 36.69 | 2
May 2025 |  |  | 350 | REDEVELOPMENT OF GPRA AT KASTURBA NAGAR PHASE I | CPWD | N28000129 | 10-2016 | 3/2022 | N.A. | 6/2024 | 1128 |  | 1128 | 709.96 | 66
May 2025 |  |  | 351 | DELHI METRO PHASE IV THREE PRIORITY CORRIDORS | DMRC | N28000135 | 7-2019 | 3/2025 | N.A. | 3/2026 | 24948.65 |  | 24948.65 | 16065.03 | 65.67
May 2025 |  |  | 352 | CONSTRUCTION OF 184 MULTI STORIED FLATS FOR HON'BLE MPS AT BKS MARG, NEW DELHI | CPWD | N28000153 | 1-2022 | 11/2024 | May-2025 | 5/2025 | 646.52 |  | 646.52 | 489.53 | 93
May 2025 |  |  | 353 | REDEVELOPMENT OF GPRA AT NETAJI NAGAR NEW DELHI PACKAGE 2 | NBCC | N28000156 | 10-2016 | 3/2024 | Jun-2025 | 3/2025 | 1536.72 |  | 1536.72 | 491.35 | 90
May 2025 |  | WATER RESOURCES | 354 | CONSTRUCTION OF 564 MLD 124 MGD WASTE WATER TREATMENT PLANT WITH EFFLUENT STANDARDS OF BOD ? 10MG/L | DJB | N30000014 | 3-2017 | 12/2022 | N.A. | 3/2025 | 665.78 |  | 665.78 | 782.51 | 100
May 2025 | GOA | CIVIL AVIATION | 355 | EXTENSION OF EXISTING INTEGRATED TERMINAL BUILDING AND ALLIED WORKS AT GOA AIRPORT. | AAI | N04000095 | 11-2017 | 9/2021 | Aug-2025 | 8/2025 | 255.69 | 255.69 | 255.69 | 119.89 | 85
May 2025 | GOA | DEPARTMENT OF HIGHER EDUCATION | 356 | CONSTRUCTION OF PERMANENT CAMPUS FOR NATIONAL INSTITUTE OF TECHNOLOGY GOA AT CUNCOLIM, GOA. | CPWD EDUCATION | N42000002 | 5-2019 | 8/2021 | N.A. | 12/2024 | 303.9 |  | 390.4 | 360 | 99.3
May 2025 | GOA | ROAD TRANSPORT AND HIGHWAYS | 357 | CONSTRUCTION OF SIX LANE ELEVATED CORRIDOR FROM KM. 508.000 TO KM. 513.150 INCLUDING APPROACHES ON N | MoRTH | N24002181 | 4-2023 | 4/2026 | N.A. | 4/2026 | 641.46 |  | 641.46 | 0
May 2025 | GOA | ROAD TRANSPORT AND HIGHWAYS | 358 | C/O NEW GREENFIELD AIRPORT AT HISSAR, RAJKOT, GUJARAT | AAI | N04000088 | 1-2018 | 8/2022 | Dec-2024 | 12/2024 | 1405 |  | 1405 | 1304.42 | 100
May 2025 | GOA | ROAD TRANSPORT AND HIGHWAYS | 359 | EXTENSION OF TERMINAL BUILDING, PTT, APRON AND CAR PARK AT SURAT AIRPORT. | AAI | N04000093 | 8-2018 | 2/2021 | Mar-2025 | 3/2025 | 353.25 |  | 353.25 | 348.78 | 100
May 2025 |  |  | 360 | DEVELOPMENT OF NEW GREENFIELD AIRPORT AT DHOLERA, AHMEDABAD (GUJARAT). PHASE-1. | AAI | N04000099 | 6-2022 | 12/2025 | N.A. | 12/2025 | 1305 | 1143.95 | 1143.95 | 604.5 | 57
May 2025 |  | COAL | 361 | 50 MW WIND POWER PROJECT PART OF 150 MW SECI HYBRID | NLC | N06000292 | 7-2022 | 6/2025 | Jan-2026 | 1/2026 | 383.84 |  | 383.84 | 303.5 | 41
May 2025 |  | COAL | 362 | REDEVELOPMENT OF SANTHAL FIELD | ONGC | N16000279 | 2-2017 | 3/2026 | N.A. | 3/2026 | 1162.56 |  | 1162.56 | 1156.83 | 94.1
May 2025 |  | COAL | 363 | ACRYLICS OR OXO-ALCOHOL PROJECT AT GUJARAT REFINERY | IOCL | N16000382 | 11-2019 | 5/2023 | Mar-2024 | 6/2025 | 5251 | 5894 | 5894 | 4682.5 | 99.6
May 2025 |  | COAL | 364 | PETROCHEMICAL AND LUBE INTEGRATION PROJECT AT GUJARAT REFINERY | IOCL | N16000409 | 9-2020 | 8/2024 | Dec-2025 | 12/2025 | 18936 |  | 18936 | 10871.57 | 81.9
May 2025 |  | COAL | 365 | AUGUMENTATION OF SALAYA MATHURA CRUDE OIL PIPELINE SYSTEM | IOCL | N16000411 | 10-2020 | 8/2023 | Jun-2025 | 6/2025 | 1614 |  | 1614 | 1117.38 | 96.21
May 2025 |  | COAL | 366 | REDEVELOPMENT OF LINCH FIELD | ONGC | N16000428 | 4-2021 | 3/2025 | N.A. | 7/2025 | 631.03 | 860.04 | 860.04 | 399.66 | 75.8
May 2025 |  | COAL | 367 | REDEVELOPMENT OF SOBHASAN COMPLEX | ONGC | N16000431 | 8-2021 | 2/2026 | N.A. | 2/2026 | 885.63 | 1286.67 | 1286.67 | 584.23 | 71.4
May 2025 |  | COAL | 368 | COMMERCIAL POLYMER FLOODING PROJECT IN BECHRAJI FIELD | ONGC | N16000444 | 1-2022 | 11/2024 | N.A. | 11/2025 | 621.4 |  | 621.4 | 137.69 | 21.4
May 2025 |  | COAL | 369 | INSTALLATION OF NEW BITUMEN UNIT ALONG WITH ALLIED FACILITIES AT GUJARAT | IOCL | N16000454 | 1-2022 | 9/2024 | N.A. | 5/2026 | 328 |  | 328 | 97.01 | 47.4
May 2025 |  | COAL | 370 | RESTORATION OF GAS TERMINAL, PHASE-I (PART-A), HAZIRA PLANT | ONGC | N16000477 | 5-2022 | 2/2025 | N.A. | 9/2025 | 249.43 |  | 249.43 | 209.4 | 93
May 2025 |  | COAL | 371 | KALOL REDEVELOPMENT PROJECT | ONGC | N16000481 | 8-2022 | 3/2027 | N.A. | 3/2027 | 1487.41 |  | 1487.41 | 952 | 60
May 2025 |  |  | 372 | OLD PIPE LINE REPLACEMENT (OPRP) GROUP-A | ONGC | N16000483 | 7-2021 | 7/2025 | N.A. | 7/2025 | 173.03 |  | 169.84 | 140.45 | 84
May 2025 |  |  | 373 | REVAMPING OF SV STATIONS, GAS TERMINAL AND KRIBHCO TERMINAL | ONGC | N16000514 | 11-2022 | 8/2026 | N.A. | 8/2026 | 837.34 |  | 837.34 | 183.33 | 45.1
May 2025 |  |  | 374 | GUJARAT 200 MW (GUVNL TENDER) | NTPC | N18000295 | 1-2021 | 7/2022 | Mar-2026 | 3/2026 | 842.27 | 1049.61 | 1049.61 | 769.67 | 65.1
May 2025 |  |  | 375 | 150 MW SOLAR PV PROJECT IN GUJARAT | LIMBDI, MESANKA AND RADHANPUR | NTPC | 5-2021 | 9/2022 | Apr-2025 | 4/2025 | 674.92 | 726.79 | 726.79 | 572.53 | 100
May 2025 |  |  | 376 | Bagodara Solar Power Project | SJVN | N18000297 | 5-2021 | 10/2022 | N.A. | 12/2025 | 339.35 |  | 339.35 | 317.59 | 51.22
May 2025 |  |  | 377 | DAYAPAR WIND ENERGY PROJECT 150MW | NTPC | N18000319 | 11-2021 | 5/2023 | Jun-2025 | 6/2025 | 937.8 |  | 937.8 | 800.11 | 100
May 2025 |  |  | 378 | DAYAPAR WIND ENERGY PROJECT 200MW | NTPC | N18000345 | 7-2022 | 3/2025 | Jan-2026 | 1/2026 | 1316.02 |  | 1316.02 | 324.36 | 26
May 2025 |  |  | 379 | KHAWDA 1255MW SOLAR PROJECT | KHAWDA SOLAR PARK | NTPC | 9-2022 | 9/2024 | Feb-2026 | 2/2026 | 7179.54 |  | 7179.54 | 5017.87 | 85
May 2025 |  |  | 380 | BHUJ SOLAR 300MW (TRANCHE-IV WIND SOLAR HYBRID) | NTPC | N18000349 | 11-2022 | 3/2024 | Mar-2026 | 3/2026 | 1442.6 |  | 1442.6 | 793.56 | 2
May 2025 |  |  | 381 | ESTABLISHMENT OF KHAVDA POOLING STATION 3 (KPS3) IN KHAVDA RE PARK | PGCIL | N18000357 | 3-2023 | 12/2024 | N.A. | 6/2025 | 922.3 |  | 922.3 | 823.07 | 88.7
May 2025 |  |  | 382 | TRANSMISSION NETWORK EXPANSION IN GUJARAT ASSOCIATED WITH INTEGRATION OF RE PROJECTS FROM KHAVDA POT | PGCIL | N18000358 | 3-2023 | 3/2025 | N.A. | 6/2025 | 815.12 |  | 815.12 | 738.03 | 94.6
May 2025 |  |  | 383 | KHAVDA-2, GUJARAT- ESTABLISHMENT OF KHAVDA POOLING STATION-2 (KPS2) IN KHAVDA RE PARK | PGCIL | N18000359 | 3-2023 | 12/2024 | N.A. | 6/2025 | 966.79 |  | 966.79 | 859 | 93.6
May 2025 |  |  | 384 | KHAVDA PHASE-II-PART B, GUJARAT- TRANSMISSION SCHEME FOR EVACUATION OF 4.5 GW RE INJECTION AT KHAVDA | PGCIL | N18000360 | 3-2023 | 3/2025 | N.A. | 9/2025 | 1167.55 |  | 1167.55 | 950 | 86.1
May 2025 |  |  | 385 | KHAVDA PHASE-II-PART C, GUJARAT- TRANSMISSION SCHEME FOR EVACUATION OF 4.5 GW RE INJECTION AT KHAVDA | PGCIL | N18000361 | 3-2023 | 3/2025 | N.A. | 9/2025 | 2820.99 |  | 2820.99 | 2418 | 76.5
May 2025 |  |  | 386 | KHAVDA 1200MW (4X300MW) IN KHAVDA RE PARK | NTPC | N18000365 | 6-2023 | 12/2024 | Jan-2026 | 1/2026 | 6283.81 |  | 6283.81 | 1752.69 | 40
May 2025 |  |  | 387 | DAYAPAR WIND- III (HYBRID TRANCHE-V) | NTPC | N18000366 | 5-2023 | 1/2025 | Mar-2026 | 3/2026 | 1095.01 |  | 1095.01 | 345.26 | 16
May 2025 |  |  | 388 | TS FOR EVACUATION OF POWER FROM POTENTIAL RE ZONE IN KHAVDA AREA OF GUJARAT UNDER PH-IV PART E3 | PGCIL | N18000383 | 7-2023 | 7/2025 | N.A. | 8/2025 | 334 |  | 334 | 33.54 | 18
May 2025 |  |  | 389 | TS FOR EVACUATION OF ADDITIONAL 7GW RE POWER FROM KHAVDA RE PARK UNDER PHASE-III PART B [VATAMAN TRA | PGCIL | N18000384 | 12-2023 | 12/2025 | N.A. | 6/2026 | 3752 |  | 3752 | 1365.02 | 13.9
May 2025 |  |  | 390 | TS FOR EVACUATION OF POWER FROM 7GW REZ IN KHAVDA AREA UNDER PHASE- IV PART E2 | PGCIL | N18000390 | 5-2024 | 5/2026 | N.A. | 5/2026 | 679 |  | 679 | 47.74 | 15
May 2025 |  |  | 391 | AUGMENTATION OF TRANSFORMATION CAPACITY AT JAM KHAMBHALIYA PS [GIS] [SPV NAME POWERGRID JAM KHAMBHAL | PGCIL | N18000398 | 10-2024 | 7/2026 | N.A. | 7/2026 | 329 |  | 329 | 0 | 1
May 2025 |  |  | 392 | TRANSMISSION SYSTEM FOR EVACUATION OF POWER FROM POTENTIAL RENEWABLE ENERGY ZONE IN KHAVDA AREA OF G | PGCIL | N18000400 | 10-2024 | 10/2026 | N.A. | 10/2026 | 4766 |  | 4766 | 280.03 | 4.2
May 2025 |  |  | 393 | PROVISION OF DYNAMIC REACTIVE COMPENSATION AT KHAVDA POOLING STATION 1 [KPS1] AND KHAVDA POOLING STA | PGCIL | N18000402 | 11-2024 | 11/2026 | N.A. | 11/2026 | 501 |  | 501 | 0 | 1
May 2025 |  |  | 394 | TRANSMISSION SYSTEM FOR EVACUATION OF POWER FROM POTENTIAL RENEWABLE ENERGY ZONE IN KHAVDA AREA OF G | PGCIL | N18000405 | 11-2024 | 5/2029 | N.A. | 5/2029 | 24819 |  | 24819 | 1454.4 | 1
May 2025 |  |  | 395 | 600 MW SOLAR POWER PROJECT UNDER CPSU SCHEME | NHPC | N18000406 | 4-2022 | 3/2026 | N.A. | 3/2026 | 4100.45 |  | 4100.45 | 10.36 | 9
May 2025 |  |  | 396 | AUGMENTATION OF TRANSFORMATION CAPACITY AT KPS2 AND KPS2 | PGCIL | N18000411 | 3-2025 | 3/2027 | N.A. | 3/2027 | 466 |  | 466 | 0
May 2025 |  |  | 397 | AUGMENTATION OF BANASKANTHA | RAGHANESDA) PS (GIS | PGCIL | 3-2025 | 3/2027 | N.A. | 3/2027 | 172 |  | 172 | 0
May 2025 |  |  | 398 | MIYAGAM-KARJAN-DABHOI-SAMLAYA (GC) | WR | N22000142 | 4-2011 | 3/2021 | Oct-2026 | 10/2026 | 844.1 | 844.1 | 844.1 | 599.22 | 41
May 2025 |  |  | 399 | ANAND GODHRA DOUBLING PROJECT 79 KMS | WR | N22000504 | 4-2017 | 12/2024 | Jun-2025 | 6/2025 | 692.26 | 692.26 | 692.26 | 683.44 | 99
May 2025 |  |  | 400 | 4TH LINE BETWEEN BAREJADI NANDEJ (GERATPUR)- SANAND (38.20 KM) (AHMEDABAD BYPASS). | WR | N22000532 | 2-2023 | 3/2027 | Feb-2027 | 2/2027 | 961.67 | 961.67 | 961.67 | 103.14 | 16
May 2025 |  |  | 401 | QUADRUPLING BETWEEN GANDHIDHAM - ADIPUR WITH Y CONNECTION AT ADIPUR FOR PROVIDING DIRECT ENTRY TOWAR | WR | N22000533 | 2-2023 | 12/2025 | Dec-2025 | 12/2025 | 152.44 | 152.44 | 152.44 | 19.5 | 60
May 2025 |  |  | 402 | RAJKOT-KANALUS (111.20 KM) | WR | N22000535 | 10-2021 | 10/2026 | Jun-2026 | 6/2026 | 1080.58 | 1080.58 | 1080.58 | 304.58 | 70
May 2025 |  |  | 403 | HIMMATNAGAR-KHEDBRAHMA (54.83 KM) | WR | N22000537 | 6-2022 | 2/2030 | Jun-2025 | 6/2025 | 354.99 | 482.42 | 482.42 | 309.75 | 91
May 2025 |  |  | 404 | PETLAD-BHADRAN (22.5 KM) | WR | N22000538 | 5-2022 | 5/2030 | Dec-2025 | 12/2025 | 202.5 | 307.12 | 307.12 | 81.12 | 8
May 2025 |  |  | 405 | NADIAD-PETLAD (37.26 KM) | WR | N22000539 | 5-2022 | 6/2030 | N.A. | 12/2025 | 335.34 | 461.91 | 461.91 | 74.11 | 7
May 2025 |  |  | 406 | SAMLAYA-TIMBA ROAD (53.53 KM) | WR | N22000540 | 2-2023 | 3/2030 | Jul-2026 | 7/2026 | 670 | 670.17 | 670.17 | 101.79 | 12
May 2025 |  |  | 407 | SAMNI-JAMBUSAR (24.08 KM) | WR | N22000541 | 5-2022 | 3/2030 | Dec-2025 | 12/2025 | 216.72 | 349.93 | 349.93 | 86.46 | 25
May 2025 |  |  | 408 | VIJAPUR-AMBLIYASAN (41.53 KM) | WR | N22000547 | 5-2022 | 3/2030 | Jul-2025 | 7/2025 | 309.81 | 415.38 | 415.38 | 240.08 | 85
May 2025 |  |  | 409 | ADRAJ MOTI-VIAJAPUR (39.75 KM) | WR | N22000548 | 5-2022 | 5/2030 | Jul-2025 | 5/2030 | 296.54 |  | 296.54 | 164.47 | 80
May 2025 |  |  | 410 | NEW BG LINE BETWEEN NALIYA-JAKHAU PORT | WR | N22000550 | 2-2023 | 1/2028 | Dec-2026 | 12/2026 | 410.46 | 410.46 | 410.46 | 5.89 | 2
May 2025 |  |  | 411 | NEW BG LINE INTERSECTION (5 NOS) BETWEEN GERATPUR-SANAND AND BOTAD- AHMEDABAD (16.51 KM) (PB29/NR/20 | WR | N22000551 | 10-2022 | 10/2027 | Feb-2027 | 10/2027 | 437.21 |  | 437.21 | 30.05
May 2025 |  |  | 412 | TARANGA HILL ABU ROAD VIA AMBAJI NEW LINE | NWR | N22000592 | 7-2022 | 7/2030 | N.A. | 12/2026 | 2798.16 |  | 2798.16 | 1063.09 | 12
May 2025 |  |  | 413 | JUNAGARH -VISAVADAR (42.28) KM | RVNL | N22000600 | 6-2022 | 9/2028 | N.A. | 12/2026 | 493 |  | 492.83 | 0
May 2025 |  |  | 414 | MODASA- SHAMLAJI NEW LINE ( MM OF AHMEDABAD-HIMMATNAGAR-UDAIPUR | 299.2 KM) | WR | 9-2012 | 3/2027 | Feb-2026 | 2/2026 | 261.68 | 261.68 | 261.68 | 191.87 | 55
May 2025 |  |  | 415 | FOUR LANING OF KAGAVADAR - UNA SECTION OF NH-8E FROM KM 139.915 TO KM 180.478 (PACKAGE-IV) IN THE ST | NHAI | N24000569 | 5-2016 | 9/2019 | May-2024 | 6/2025 | 723.64 |  | 723.64 | 562.31 | 97
May 2025 |  |  | 416 | 4-LANNING OF KODINAR TO VERAVAL SECTION OF NH-8E FROM KM 221.610 TO KM 263.000 | NHAI | N24000592 | 7-2016 | 7/2020 | N.A. | 5/2025 | 829.97 |  | 829.97 | 486.93 | 96.63
May 2025 |  |  | 417 | SIX LANNING FROM KM. 401.200 TO 494.410 OF NH-8 ON HYBRID ANNUITY MODE UNDER NHDP-V(PKG VI)REG. | NHAI | N24000649 | 1-2017 | 12/2020 | Oct-2025 | 10/2025 | 1251.11 | 1527.75 | 1527.75 | 685.11 | 90.41
May 2025 |  |  | 418 | CONSTRUCTION OF EIGHT LANE VADODARA KIM EXPRESSWAY FROM KM 254.430 TO KM 279.000 (KIM TO ANKLESHWAR | NHAI | N24000834 | 3-2018 | 10/2021 | May-2025 | 7/2025 | 1161.39 | 1738.03 | 1404 | 683.24 | 83
May 2025 |  |  | 419 | CONSTRUCTION OF MISSING LINKS (SINGLE LANE) IN LAKHPAT GADULI HAJIPIR ODMA KHAVDA DHOLAVIRA MAUVANA | MoRTH | N24000925 | 10-2018 | 11/2020 | Sep-2024 | 9/2024 | 400.76 | 394.44 | 394.44 | 287.04 | 87
May 2025 |  |  | 420 | CONSTRUCTION OF ROB WITH APPROACHES IN LIEU OF L C NO 165 OF AHMEDABAD PALANPUR BETWEEN RAILWAY STAT | MoRTH | N24001427 | 6-2020 | 4/2023 | Sep-2024 | 9/2024 | 166.21 |  | 166.21 | 97.12 | 93
May 2025 |  |  | 421 | CONSTRUCTION OF FOUR LANE EXPRESSWAY FROM START OF SARDAR PATEL RING ROAD TO SINDHREJ VILLAGE (CH. 0 | NHAI | N24001443 | 5-2020 | 3/2024 | Jun-2025 | 6/2025 | 690.3 | 929.95 | 929.95 | 841.05 | 93.9
May 2025 |  |  | 422 | CONSTRUCTION OF FOUR LANE EXPRESSWAY FROM START OF SINDHREJ VILLAGE (CH. 22.00 TO CH. 48.52) SECTION | NHAI | N24001444 | 5-2020 | 1/2024 | Jun-2025 | 6/2025 | 882 | 1229.37 | 1229.37 | 996.88 | 89.28
May 2025 |  |  | 423 | CONSTRUCTION OF FOUR LANE EXPRESSWAY FROM START OF VEJALLKA VILLAGE TO START OF DSIR ZONE OF AHMEDAB | NHAI | N24001445 | 5-2020 | 7/2023 | May-2025 | 5/2025 | 691.52 | 903.85 | 903.85 | 872.33 | 99.1
May 2025 |  |  | 424 | CONSTRUCTION OF FOUR LANE EXPRESSWAY FROM START OF DSIR ZONE OF AHMEDABAD DISTRICT TO ADHELAI VILLAG | NHAI | N24001446 | 5-2020 | 12/2023 | May-2025 | 5/2025 | 894 | 1261.58 | 1261.58 | 1156.84 | 96.77
May 2025 |  |  | 425 | DELHI VADODARA GREENFIELD ALIGNMENT SECTION OF NH 148N PACKAGE 26 | NHAI | N24001515 | 9-2020 | 2/2024 | N.A. | 3/2026 | 1542.02 |  | 1542.02 | 969.47 | 68.35
May 2025 |  |  | 426 | DELHI VADODARA GREENFIELD ALIGNMENT SECTION OF NH 148N PACKAGE 27 | NHAI | N24001516 | 9-2020 | 2/2024 | Aug-2025 | 8/2025 | 1185.69 |  | 1185.69 | 980.16 | 93.52
May 2025 |  |  | 427 | DELHI VADODARA GREENFIELD ALIGNMENT SECTION OF NH 148N PACKAGE 30 | NHAI | N24001518 | 11-2019 | 9/2023 | N.A. | 8/2025 | 1669.56 |  | 1669.56 | 1066.35 | 96.9
May 2025 |  |  | 428 | DELHI VADODARA GREENFIELD ALIGNMENT SECTION OF NH 148N PACKAGE 28 | NHAI | N24001519 | 9-2020 | 11/2023 | N.A. | 7/2025 | 1198.55 |  | 1198.55 | 911.13 | 95.78
May 2025 |  |  | 429 | DELHI VADODARA GREENFIELD ALIGNMENT SECTION OF NH 148N PACKAGE 31 | NHAI | N24001520 | 11-2019 | 5/2024 | N.A. | 8/2025 | 1604.06 |  | 1604.06 | 1241.4 | 95.73
May 2025 |  |  | 430 | UP-GRADATION TO 4-LANE WITH PAVED SHOULDER OF BHIMASAR JUNCTION OF NH-41 TO ANJAR BHUJ UPTO AIRPORT | NHAI | N24001785 | 3-2022 | 6/2025 | N.A. | 6/2025 | 1373.06 | 1085 | 1373.06 | 656.62 | 87.3
May 2025 |  |  | 431 | CONSTRUCTION OF EIGHT LANE ACCESS CONTROLLED EXPRESSWAY FROM KM 103.400 TO KM 128.000 OF VADODARA MU | NHAI | N24001786 | 3-2021 | 3/2024 | N.A. | 3/2026 | 1259 | 2652.24 | 1910 | 278.29 | 34.08
May 2025 |  |  | 432 | CONSTRUCTION OF EIGHT LANE EXPRESSWAY FROM KM 190.000 TO KM 217.500 GANDEVA TO ENA SECTION OF VADODA | NHAI | N24001789 | 7-2020 | 8/2023 | N.A. | 4/2025 | 1710.3 | 2665.08 | 1927 | 900.19 | 90.56
May 2025 |  |  | 433 | SANCHORE - SANTALPUR FROM KM 67.000- KM 99.000 OF NH-754K (AJ-RGBS-PACKAGE- 3) | NHAI | N24001790 | 2-2020 | 8/2023 | Dec-2024 | 12/2024 | 752.3 |  | 766.2 | 452.13 | 98.14
May 2025 |  |  | 434 | 4L OF BAL WORKS OF TALAJA - MAHUVA FROM 54.990 KM. TO 100.450 KM. OF OLD NH-8E (PACKAGE-II) | NHAI | N24001792 | 3-2021 | 9/2022 | N.A. | 1/2025 | 536.03 |  | 536.03 | 480.77 | 100
May 2025 |  |  | 435 | 4L OF BAL WORKS OF MAHUVA TO KAGVADAR FROM 100.450 KM. TO 140.470 KM. OF NH-8E (PKG- III) | NHAI | N24001793 | 3-2021 | 9/2022 | N.A. | 5/2025 | 485.75 |  | 485.75 | 393.88 | 99.57
May 2025 |  |  | 436 | SANCHORE - SANTALPUR FROM KM 99.000- KM 130.073 OF NH-754K (AJ-RGBS-PACKAGE- 4) | NHAI | N24001794 | 2-2020 | 3/2023 | Dec-2024 | 12/2024 | 778.15 |  | 785.67 | 547.22 | 99.7
May 2025 |  |  | 437 | 4L KODINAR - VERAVAL (PACKAGE VI) FROM KM. 222.400 TO KM. 230.00 (KODINAR BYPASS) OF NH-8E (NH 51 NE | NHAI | N24001827 | 3-2022 | 3/2023 | N.A. | 4/2025 | 162.73 |  | 162.73 | 131.79 | 100
May 2025 |  |  | 438 | UPGRADATION AND STRENGTHENING TO 2 LANE PS FROM KM 95/500 TO KM 129/775 OF NH 168 G IDAR BHILODA SA | MoRTH | N24002014 | 9-2022 | 12/2023 | Dec-2025 | 12/2025 | 237.28 |  | 237.28 | 0.34
May 2025 |  |  | 439 | UPGRADATION TO 4L PS DIVIDED CARRIAGEWAY FROM PATAN (NEAR RAJPUR) TO GOJARIYA FROM KM 52.000 TO KM 1 | NHAI | N24002034 | 12-2021 | 3/2025 | N.A. | 3/2025 | 1181.34 | 1181 | 1181.34 | 534.24 | 77.6
May 2025 |  |  | 440 | WIDENING TO 6L OF EXISTING 4L JETPUR - GONDAL - RAJKOT SECTION FROM KM. 117.600 TO KM. 185.00 ON NH- | NHAI | N24002035 | 9-2023 | 9/2025 | N.A. | 9/2025 | 2070.44 |  | 2070.44 | 485.44 | 36.96
May 2025 |  |  | 441 | UPGRADATION OF DHORAJI JAMKANDORNA KALAVAD SECTION OF NH 927D FROM DESIGN CHAINAGE KM 00 TO KM 58.11 | MoRTH | N24002117 | 10-2022 | 2/2024 | Feb-2026 | 2/2026 | 246.6 | 291 | 291 | 27.57 | 15
May 2025 |  |  | 442 | UPGRADATION TO TWO LANE WITH PAVED SHULDER CONFIGUARATION FROM KM 00 TO 47 OF NH 351 MAHUVA TO BADHA | MoRTH | N24002118 | 12-2022 | 2/2024 | Aug-2025 | 8/2025 | 173.06 |  | 219 | 0.15
May 2025 |  |  | 443 | WORK OF DEVELOPMENT AND CONSTRUCTION OF ELEVATED CORRIDORFROM KM 38/660 TO KM 42/690 (ISCON JUNCTION | MoRTH | N24002182 | 3-2023 | 3/2026 | N.A. | 3/2026 | 530.2 |  | 530.2 | 0
May 2025 |  |  | 444 | WIDENING 2 LANE TO 4-LANE FROM KM 92/320 TO KM 115/320 (VAV CHOKDI- SATLASANA TO TO VRUNDAVAN CHOKDI, | MoRTH | N24002183 | 3-2022 | 3/2026 | N.A. | 3/2026 | 151.13 |  | 171 | 0
May 2025 |  | URBAN DEVELOPMENT | 445 | AHMEDABAD METRO RAIL PROJECT PHASE 1 | AMR | N28000122 | 11-2014 | 12/2018 | N.A. | 8/2025 | 10773 |  | 12924.55 | 12484.89 | 99.89
May 2025 |  | URBAN DEVELOPMENT | 446 | AHMEDABAD METRO RAIL PROJECT PHASE II | AMR | N28000137 | 3-2019 | 3/2024 | N.A. | 12/2025 | 5384.17 |  | 5384.17 | 4032.54 | 85.77
May 2025 |  | URBAN DEVELOPMENT | 447 | SURAT METRO RAIL PROJECT | AMR | N28000138 | 3-2019 | 3/2024 | N.A. | 6/2026 | 12020.32 |  | 12020.32 | 6882.87 | 66.05
May 2025 |  | HEALTH AND FAMILY WELFARE | 448 | ALL INDIA INSTITUTE OF MEDICAL SCIENCES AT MANETHI, HARYANA. | HITES | N21000032 | 3-2019 | 3/2023 | Mar-2026 | 3/2026 | 1294.34 | 1294.34 | 1294.34 | 269.2 | 23.2
May 2025 |  | HOME AFFAIRS | 449 | C/o separate family accommodation (Phase-I) on EPC basis for SSB at Faridabad (Haryana)" | CPWD FOR MHA | N28000147 | 1-2020 | 10/2023 | Mar-2025 | 7/2025 | 166.98 | 170.23 | 170.23 | 139.66 | 97
May 2025 |  | HOME AFFAIRS | 450 | R and D CAMPUS II AT FARIDABAD | IOCL | N16000375 | 6-2019 | 12/2022 | Jul-2025 | 3/2026 | 2281.94 | 3219.94 | 3219.94 | 1705.85 | 63
May 2025 |  | HOME AFFAIRS | 451 | CAPACITY EXPANSION OF PANIPAT REFINERY FROM 15 TO 25 MMTPA | IOCL | N16000412 | 2-2021 | 9/2024 | Dec-2025 | 12/2025 | 34627 | 38231 | 38231 | 20878.96 | 86.5
May 2025 |  |  | 452 | POLY BUTADIENE RUBBER PLANT AT PANIPAT | IOCL | N16000458 | 3-2022 | 3/2025 | Jun-2026 | 6/2026 | 1459 | 2948.62 | 2948.62 | 913.92 | 65.6
May 2025 |  | POWER | 453 | IMPLEMENTATION OF LILO OF BOTH CIRCUITS OF 400KV VIDHYACHAL PS TO SASAN D/C LINE AT HINDALCO SWITCHY | PGCIL | N18000420 | 2-2025 | 12/2026 | N.A. | 12/2026 | 370 |  | 370 | 0
May 2025 |  | RAILWAYS | 454 | DOUBLING BETWEEN BHIWANI-DOBH BAHALI | NWR | N22000604 | 2-2023 | 2/2028 | N.A. | 12/2025 | 471.06 |  | 471.06 | 111.4 | 44
May 2025 |  | RAILWAYS | 455 | DOUBLING BETWEEN REWARI-KATHUWAS | 27.73 KM | NWR | 2-2023 | 6/2027 | N.A. | 12/2025 | 352.41 |  | 352.41 | 169.66 | 51
May 2025 |  | RAILWAYS | 456 | 4-LANING OF GOHANA-SONIPAT (PKG-2) SECTION FROM KM 40.601 TO KM 78.837 (LENGTH = 38.236KM) OF NH-352 | NHAI | N24001535 | 7-2020 | 7/2022 | May-2024 | 8/2025 | 899 | 1882.46 | 1882.46 | 1123.98 | 97.3
May 2025 |  | RAILWAYS | 457 | CONSTRUCTION OF FOUR LANE GREENFIELD PROJECT OF DELHI- AMRITSAR-KATRA EXPRESSWAY (PHASE-I PKG-III) F | NHAI | N24001633 | 12-2020 | 12/2023 | Mar-2024 | 6/2025 | 1430.88 | 1813.91 | 1813.91 | 1190.24 | 99.9
May 2025 |  | RAILWAYS | 458 | CONSTRUCTION OF FOUR LANE GREENFIELD PROJECT OF DELHI- AMRITSAR-KATRA EXPRESSWAY (PHASE-I PKG-IV) FRO | NHAI | N24001634 | 1-2021 | 12/2023 | Mar-2024 | 6/2025 | 1306.95 | 1564.14 | 1564.14 | 942.71 | 99.97
May 2025 |  | RAILWAYS | 459 | 4 LANING OF JAGADHRI TAJEWALA ROAD SECTION OF NH 907 (OLD NH 73A) UNDER NH(O) (PKG 1) IN THE STATE O | NHAI | N24001635 | 3-2022 | 2/2025 | N.A. | 2/2025 | 1269.5 |  | 1269.5 | 151 | 52
May 2025 |  | RAILWAYS | 460 | 4- LANING OF ROHTAK-JIND SECTION FROM KM. 307+000 TO KM. 347+800 OF NH- 71 AND CONNECTING LINK FROM K | NHAI | N24001673 | 3-2020 | 3/2023 | Nov-2024 | 6/2025 | 510.97 |  | 510.97 | 529 | 96.75
May 2025 |  |  | 461 | CONSTRUCTION OF GURGAON - PATAUDI - REWARI SECTION OF NH-352W (DESIGN LENGTH 46.11 KM) AS FEEDER ROU | NHAI | N24001774 | 12-2020 | 11/2023 | N.A. | 6/2024 | 1524.03 |  | 1524.03 | 1105.08 | 65.54
May 2025 |  |  | 462 | CONSTRUCTION OF PROPOSED REWARI BYPASS (DESIGN LENGTH 14.4 KM) NH-11 AS A FEEDER ROUTE IN THE STATE | NHAI | N24001775 | 2-2020 | 1/2023 | Dec-2024 | 12/2024 | 808.31 |  | 958 | 917.55 | 100
May 2025 |  |  | 463 | UPGRADATION OF EXISTING 4 LANE ISMAILABAD-AMBALA SECTION (KM. 0+000 TO KM 42+500) (PART OF AMBALA-KO | NHAI | N24002037 | 1-2023 | 12/2025 | N.A. | 3/2026 | 609.32 | 609 | 609 | 187.47 | 47.3
May 2025 |  |  | 464 | CONSTRUCTION OF 6-LANE GREENFIELD KARNAL RING ROAD STARTING FROM NH- 44 NEAR VILLAGE SHAMGARH (DESIGN | NHAI | N24002038 | 11-2022 | 8/2025 | N.A. | 8/2025 | 1691.45 | 1998 | 1998 | 649.71 | 58.76
May 2025 |  |  | 465 | CONSTRUCTION OF 6-LANE GREENFIELD AMBALA RING ROAD STARTING FROM JUNCTION WITH SHAMLI-AMBALA SECTION | NHAI | N24002039 | 2-2023 | 10/2025 | N.A. | 10/2025 | 1088.64 | 1178 | 1178 | 425.85 | 53.55
May 2025 |  |  | 466 | DEVELOPMENT OF SIX-LANE ACCESS CONTROLLED HIGHWAY FROM RANIPUR BARSI (SAHARANPUR DISTRICT) TO ADHOYA | NHAI | N24002040 | 4-2022 | 5/2025 | N.A. | 5/2028 | 1554.21 |  | 1554.21 | 522.92 | 54
May 2025 |  |  | 467 | DEVELOPMENT OF SIX-LANE ACCESS CONTROLLED HIGHWAY FROM ADHOYA MUSALMANA (AMBALA DISTRICT) TO SADOPUR | NHAI | N24002041 | 4-2022 | 5/2025 | N.A. | 5/2025 | 1491.71 |  | 1491.71 | 706.26 | 49.7
May 2025 |  |  | 468 | CONSTRUCTION OF 4-LANING OF BHIWANI HANSI ROAD SECTION OF NH 148B (DESIGN LENGTH 42.934 KM) UNDER BH | NHAI | N24002042 | 11-2022 | 12/2025 | N.A. | 12/2025 | 1322.13 |  | 1322.13 | 354.56 | 91.01
May 2025 |  |  | 469 | CONSTRUCTION OF 4-LANE GREENFIELD JALBEHRA - SHAHBAD SECTION OF NH ? 152G FROM KM 0+000 TO KM 22+850 | NHAI | N24002043 | 3-2022 | 6/2025 | N.A. | 6/2025 | 927.22 | 1173.66 | 1173.66 | 493.79 | 80.5
May 2025 |  |  | 470 | 4L AMBALA - KALAAMB FROM KM. -0.800 TO KM. 33.015 OF OLD NH-72 | NHAI | N24002044 | 6-2023 | 6/2025 | N.A. | 6/2025 | 629.16 |  | 629.16 | 94 | 95
May 2025 |  |  | 471 | CONSTRUCTION OF GREENFIELD CONNECTIVITY TO JEWAR INTERNATIONAL AIRPORT FROM DND FARIDABAD BALLABHGAR | NHAI | N24002048 | 7-2022 | 6/2025 | N.A. | 3/2026 | 2414.67 | 2898 | 2898 | 1229.9 | 47.2
May 2025 |  | DEPARTMENT OF HIGHER EDUCATION | 472 | ESTABLISHMENT OF PERMANENT CAMPUS PHASE 1 OF IIM SIRMAUR | CPWD EDUCATION | N42000008 | 9-2018 | 6/2022 | Dec-2024 | 8/2025 | 392.51 |  | 446.43 | 316.16 | 91.5
May 2025 |  | DEPARTMENT OF HIGHER EDUCATION | 473 | CONSTRUCTION OF PERMANENT CAMPUSES OF CENTRAL UNIVERSITY OF HIMACHAL PRADESH AT DEHRA AND DHARAMSHAL | CPWD | N42000011 | 3-2021 | 11/2024 | Jul-2025 | 7/2025 | 512.37 | 300.45 | 300.45 | 157.12 | 72
May 2025 |  | POWER | 474 | LUHRI HYDROELECTRIC PROJECT | STAGE1 | SJVN | 11-2020 | 1/2026 | N.A. | 12/2028 | 1810.56 |  | 3584.53 | 1715.33 | 51.32
May 2025 |  | POWER | 475 | DHAULASIDH HYDROELECTRIC PROJECT | 66 MW | SJVN | 10-2020 | 11/2025 | N.A. | 3/2027 | 687.97 |  | 1511.87 | 874.54 | 66.91
May 2025 |  | POWER | 476 | SUNNI DAM HYDRO ELECTRIC PROJECT | SJVN | N18000344 | 1-2023 | 4/2028 | N.A. | 12/2028 | 2614.51 |  | 4540.71 | 942.36 | 29.08
May 2025 |  | RAILWAYS | 477 | BHANUPALI-BILASPUR BERI NL | RVNL | N22000273 | 4-2008 | 12/2026 | N.A. | 3/2025 | 13370.29 |  | 6753.42 | 5369.57
May 2025 |  | RAILWAYS | 478 | FOUR LANNING OF NERCHOWK-PANDOH BYPASS SECTION OF NH-21(PACKAGE-I KM 190.000 TO KM 221.305) UNDER NH | NHAI | N24000613 | 9-2016 | 7/2020 | N.A. | 3/2025 | 1273.71 |  | 1478.61 | 1439.49 | 97.26
May 2025 |  |  | 479 | FOUR LANING OF SOLAN-KAITHLIGHAT SECTION OF NH-22 (NOW NH-5) FROM KM 106.139 TO KM 129.050, ON EPC M | NHAI | N24000852 | 3-2018 | 5/2021 | Dec-2024 | 12/2024 | 478.74 |  | 1514.46 | 1349.59 | 83
May 2025 |  |  | 480 | REHABILITATION AND UPGRADATION TO 2- LANE/2-LANE WITH PAVED SHOULDERS/4- LANE CONFIGURATION OF PAONTA | MoRTH | N24001381 | 8-2020 | 4/2021 | N.A. | 4/2021 | 272.98 |  | 272.98 | 140.69 | 100
May 2025 |  |  | 481 | REHABILITATION AND UPGRADATION TO 2- LANE CONFIGURATION OF HEWNA- ASHYARI SECTION (KM 25.000 TO KM 50. | MoRTH | N24001382 | 8-2020 | 3/2021 | N.A. | 7/2024 | 242.8 |  | 242.8 | 96.76 | 92.44
May 2025 |  |  | 482 | REHABILITATION AND UPGRADATION TO INTERMEDIATE LANE CONFIGURATION OF SHRI KYARI-GUMMA SECTION (KM 75 | MoRTH | N24001383 | 8-2020 | 4/2021 | N.A. | 4/2021 | 349.2 |  | 349.2 | 239.34 | 100
May 2025 |  |  | 483 | REHABILITATION AND UPGRADATION TO 2- LANE CONFIGURATION OF ASHYARI-SHRI KYARI SECTION (KM 50.000 TO K | MoRTH | N24001422 | 2-2021 | 9/2021 | N.A. | 7/2024 | 345.89 |  | 345.89 | 162.23 | 91.75
May 2025 |  |  | 484 | REHABILITATION AND UPGRADATION TO 2- LANE CONFIGURATION OF HAMIRPUR- KARNOHAL SECTION (KM 141.000 TO K | MoRTH | N24001447 | 8-2020 | 12/2024 | N.A. | 12/2024 | 371.93 |  | 371.93 | 154.04 | 81
May 2025 |  |  | 485 | REHABILITATION AND UPGRADATION TO 2- LANE CONFIGURATION OF KALWAHAN- MANDI SECTION (KM 208.950 TO KM 2 | MoRTH | N24001470 | 8-2020 | 4/2025 | N.A. | 4/2025 | 314.32 |  | 314.32 | 49.26 | 45
May 2025 |  |  | 486 | REHABILITATION AND UPGRADING FROM 2 L TO 4 L FROM BHANGBAR(NEAR RANITAL) TO KANGRA BYPASS SECTION OF | NHAI | N24001808 | 3-2021 | 12/2024 | Dec-2024 | 12/2024 | 1322.95 | 1442.47 | 1442.47 | 888.51 | 96.61
May 2025 |  |  | 487 | CONVERSION OF PARTIALLY EXCAVATED ESCAPE TUNNEL TO UNIDIRECTIONAL TWO LANE TUNNEL (INCLUDING CONSTRU | NHAI | N24001809 | 5-2022 | 3/2024 | Dec-2024 | 12/2024 | 469.95 |  | 280 | 302.91 | 98.3
May 2025 |  |  | 488 | 4L SUNDER NAGAR BYPASS FROM KM173.900 TO KM 179.600 OF NH-21 IN THE STATE OF HP | NHAI | N24001810 | 2-2022 | 6/2024 | N.A. | 6/2024 | 190.6 |  | 163 | 103.48 | 100
May 2025 |  |  | 489 | 4L OF MO - SIHUNI FROM KM. 42.00 TO KM. 51.00 OF OLD NH-20 (NEW NH-154) | PACKAGE-IB | NHAI | 4-2021 | 6/2024 | N.A. | 5/2025 | 583.93 | 770 | 770 | 173.6 | 100
May 2025 |  |  | 490 | 4L OF HP/PUNJAB BO4L OF HP/PUNJAB BORDER - MO FROM KM. 11.00 TO KM. 42.00 OF OLD NH-20 (NEW NH-154) | NHAI | N24001812 | 3-2021 | 5/2024 | N.A. | 12/2025 | 1002.11 | 1361.79 | 1361.76 | 190.22 | 46.54
May 2025 |  |  | 491 | 4L OF END OF PINJORE BYPASS - BADDI - NALAGARH SECTION (KM. 4.200 TO KM. 35.370) OF NH21A | NHAI | N24001813 | 7-2021 | 9/2024 | N.A. | 9/2024 | 1692.05 |  | 1692.05 | 942.14 | 21.6
May 2025 |  |  | 492 | IMPROVEMENT/CONSTRUCTION OF EXISTING CLASS-5 ROAD TO NH INTERMEDIATE LANE SPECIFICATION WITH HARD SH | BRO | N24001915 | 3-2021 | 6/2026 | N.A. | 6/2026 | 230.54 |  | 230.54 | 20.16 | 28
May 2025 |  |  | 493 | IMPROVEMENT/CONSTRUCTION OF EXISTING CLASS 5 ROAD TO NH INTERMEDIATE LANE SPECIFICATION WITH HARD SH | BRO | N24001916 | 3-2021 | 5/2026 | N.A. | 5/2026 | 314.67 |  | 314.67 | 76.05 | 47
May 2025 |  |  | 494 | PKG NAME: 4L OF KATHLIGHAT TO SHAKRAL VILLAGE FROM KM 128.835 TO KM 146.300 OF NH- 5 (SHIMLA BYPASS | NHAI | N24002049 | 3-2022 | 4/2026 | N.A. | 4/2026 | 1703.48 | 2278 | 2278 | 651.98 | 14.5
May 2025 |  |  | 495 | REHABILITATION AND UPGRADATION TO 4L CONFIGURATION and STRENGTHENING OF SIHUNI TO RAJOL FROM KM 51.0 | NHAI | N24002050 | 2-2022 | 9/2025 | N.A. | 9/2025 | 696.65 | 698.46 | 698.46 | 367.62 | 64.8
May 2025 |  |  | 496 | CONSTRUCTION OF NEW 2 LANE WITH PAVED SHOULDER OF HAMIRPUR BYPASS (PACKAGE IVA) OF NH-88 (NEW NH-103 | NHAI | N24002051 | 7-2022 | 10/2025 | N.A. | 10/2025 | 739.39 |  | 739.39 | 328.46 | 78
May 2025 |  |  | 497 | REHABILITATION AND UP-GRADATION OF EXISTING ROAD TO 2L PS FROM END OF HAMIRPUR BYPASS (NEAR CHILBAHA | NHAI | N24002052 | 2-2022 | 4/2025 | N.A. | 4/2025 | 1146.19 |  | 1146.19 | 918.84 | 69.27
May 2025 |  |  | 498 | REHABILITATION AND UP-GRADATION TO 4L CONFIGURATION AND STRENGTHENING OF THANPURI TO PAROR SECTION F | NHAI | N24002192 | 6-2022 | 12/2025 | N.A. | 12/2025 | 815.69 | 815.69 | 815.69 | 392.01 | 29.2
May 2025 |  | URBAN DEVELOPMENT | 499 | CONSTRUCTION OF PERMANENT CAMPUS OF CENTRAL UNIVERSITY OF HIMACHAL PRADESH AT DEHRA AND JADRANGAL (D | CPWD | N28000154 | 4-2022 | 11/2024 | N.A. | 11/2024 | 512.34 |  | 512.34 | 0
May 2025 |  | CIVIL AVIATION | 500 | JAMMU - CONSTRUCTION OF NEW CIVIL ENCLAVE | AAI | N04000107 | 7-2022 | 6/2026 | N.A. | 6/2026 | 861.37 |  | 861.37 | 144.65 | 30
May 2025 |  | DEPARTMENT OF HIGHER EDUCATION | 501 | CONSTRUCTION OF PERMANENT CAMPUS OF IIM JAMMU (PHASE 1) | CPWD EDUCATION | N28000130 | 3-2019 | 7/2022 | Jan-2025 | 1/2025 | 424.93 |  | 500.91 | 448.15 | 96
May 2025 |  | DEPARTMENT OF HIGHER EDUCATION | 502 | CONSTRUCTION OF PERMANENT CAMPUS IIT JAMMU (PHASE 1C) | CPWD EDUCATION | N28000131 | 1-2018 | 4/2023 | Apr-2025 | 4/2025 | 676 | 1144.68 | 1144.68 | 54.75 | 100
May 2025 |  | HEALTH AND FAMILY WELFARE | 503 | CONSTRUCTION OF AIIMS AT JAMMU VIJAYPUR, SAMBA JAMMU AND KASHMIR | CPWD FOR HEALTH | N21000029 | 3-2019 | 9/2023 | May-2025 | 5/2025 | 1404 | 1642 | 1642 | 1461.68 | 100
May 2025 |  | HEALTH AND FAMILY WELFARE | 504 | C/O AIIMS AT AWANTIPORA (KASHMIR) JAMMU AND KASHMIR | CPWD FOR HEALTH | N28000150 | 3-2019 | 9/2025 | N.A. | 11/2025 | 1828 |  | 1577 | 1285.4 | 64.1
May 2025 |  | HEALTH AND FAMILY WELFARE | 505 | SETTING UP A COMMON USER PETROLEUM TERMINAL AT JAMMU FOR RE-SITEMENT OF EXISTING DEPOTS OF PSU OMCS | BPCL | N16000500 | 4-2021 | 3/2025 | N.A. | 3/2025 | 676.89 |  | 676.89 | 495.3 | 75
May 2025 |  |  | 506 | CGD PROJECT AT JAMMU DISTRICTS | IOCL | N16000527 | 3-2022 | 3/2032 | Sep-2034 | 9/2034 | 538 |  | 538 | 4.09 | 0.6
May 2025 |  | POWER | 507 | PAKAL DUL HYDRO ELECTRIC PROJECT | 1000 MW | CVPPPL | 10-2014 | 4/2020 | Jul-2025 | 9/2026 | 8112.12 |  | 12727.76 | 6561.65 | 69.35
May 2025 |  | POWER | 508 | KIRU HYDRO ELECTRIC PROJECT | CVPPPL | N18000278 | 3-2019 | 8/2024 | N.A. | 9/2026 | 4287.59 |  | 5409 | 2599.24 | 61.38
May 2025 |  | POWER | 509 | RATLE HE PROJECT | NHPC | N18000324 | 2-2021 | 2/2026 | N.A. | 8/2028 | 5281.94 |  | 5281.94 | 968.19 | 23.01
May 2025 |  | POWER | 510 | KWAR HE PROJECT | CVPPPL | N18000363 | 5-2022 | 11/2026 | N.A. | 12/2027 | 4526.12 |  | 4526.12 | 1119.97 | 21.45
May 2025 |  | POWER | 511 | TRANSMISSION SCHEME FOR EVACUATION OF POWER FROM RATLE HEP (850 MW) AND KIRU (624 MW): PART B | PGCIL | N18000417 | 3-2025 | 3/2027 | N.A. | 3/2027 | 219 |  | 219 | 0
May 2025 |  | POWER | 512 | FOUR LANING OF UDHAMBUR - RAMBAN SECTION OF NH-1A | NHAI | N24000488 | 12-2015 | 12/2018 | Jun-2025 | 6/2025 | 2136.97 | 2644 | 2644 | 2386.51 | 99.5
May 2025 |  | POWER | 513 | CONSTRUCTION OF STAND ALONE RING ROAD/ BYPASS AROUND JAMMU CITY IN THE STATE OF J AND K ON EPC MODE | NHAI | N24000717 | 12-2017 | 7/2021 | Jun-2025 | 6/2025 | 1471.75 | 1471.75 | 1903.98 | 1716.22 | 98.8
May 2025 |  | POWER | 514 | UP-GRADATION TO 4-LANE WITH PAVED SHOULDER OF JAMMU-AKHNOOR ROAD SECTION OF NH-144A FROM GANESH VIHA | NHIDCL | N24000868 | 3-2018 | 7/2021 | Aug-2023 | 10/2025 | 253.44 |  | 253.44 | 189.72 | 82.35
May 2025 |  | POWER | 515 | CONSTRUCTION OF (I) CONNECTING ROAD FROM Z-MORH TUNNEL TO ZOJILA TUNNEL AND (II) 14.150 KM LONG BI-D | NHIDCL | N24001256 | 8-2020 | 9/2026 | N.A. | 9/2026 | 6808.69 |  | 6808.69 | 3013.84 | 49.92
May 2025 |  | POWER | 516 | UP-GRADATION TO 2-LANE WITH PAVED SHOULDER FROM KM 12.850 TO KM20.300 OF 7.450KM LENGTH ON GOHA-KHEL | NHIDCL | N24001264 | 7-2020 | 4/2022 | Oct-2024 | 10/2026 | 228.39 |  | 228.39 | 69.32 | 87.85
May 2025 |  |  | 517 | UP-GRADATION TO 2-LANE WITH PAVED SHOULDER FROM KM 20.300 TO KM 29.030 OF 8.730 KM LENGTH ON GOHA-K | NHIDCL | N24001266 | 7-2020 | 4/2022 | Nov-2023 | 7/2025 | 210.79 |  | 210.79 | 71 | 90.4
May 2025 |  |  | 518 | KHELLANI-KHANABAL PKG-1 | NHIDCL | N24001323 | 3-2021 | 9/2022 | Oct-2024 | 10/2024 | 486.45 |  | 486.45 | 126.73 | 96.58
May 2025 |  |  | 519 | KHELLANI-KHANABAL PKG-3 | NHIDCL | N24001341 | 3-2021 | 12/2022 | Oct-2024 | 5/2025 | 398.51 |  | 398.51 | 80.64 | 98.36
May 2025 |  |  | 520 | KHELLANI-KHANABAL PKG-2 | NHIDCL | N24001394 | 7-2021 | 2/2023 | Jun-2025 | 6/2026 | 512.43 |  | 512.43 | 71.65 | 51.52
May 2025 |  |  | 521 | KHELLANI-KHANABAL PKG-4 | NHIDCL | N24001395 | 7-2021 | 8/2023 | Dec-2025 | 6/2026 | 859.67 |  | 859.67 | 190.91 | 44.02
May 2025 |  |  | 522 | KHELLANI-KHANABAL PKG-5 | NHIDCL | N24001396 | 7-2021 | 2/2023 | Mar-2025 | 8/2025 | 497.09 |  | 497.09 | 172.85 | 88.04
May 2025 |  |  | 523 | GOHA-KHELLANI PKG-3 | NHIDCL | N24001397 | 2-2021 | 3/2023 | Feb-2025 | 3/2025 | 431.28 | 433.08 | 431.28 | 372.31 | 100
May 2025 |  |  | 524 | BALANCE WORKS OF FOUR LANING FROM RAMBAN KM 151.00 TO BANIHAL KM 187.00 OF NH-1A (NOW NH-44) WITH VA | NHAI | N24001472 | 9-2021 | 12/2023 | Jun-2024 | 6/2024 | 811.19 |  | 811.19 | 848.57 | 99
May 2025 |  |  | 525 | CONSTRUCTION OF FOUR LANE RINGROAD BYPASS SRINAGAR CITY | NHAI | N24001511 | 3-2021 | 2/2024 | Oct-2025 | 10/2025 | 2919.96 |  | 2919.96 | 2317.82 | 70
May 2025 |  |  | 526 | FOUR LANING OF JAMMU-AKHNOOR PKG-1 | NHIDCL | N24001543 | 7-2022 | 1/2025 | N.A. | 10/2025 | 245.34 |  | 245.34 | 57.03 | 38.48
May 2025 |  |  | 527 | DELHI-AMRITSAR-KATRA EXPRESSWAY (PHASE-II PKG-XVI) EXISTING JAKH (VIJAYPUR)-KUNJWANI SECTION OF NH-4 | NHAI | N24001550 | 9-2021 | 9/2024 | Dec-2025 | 12/2025 | 1821.72 | 1917.32 | 1917.32 | 1005.35 | 83.21
May 2025 |  |  | 528 | DELHI-AMRITSAR-KATRA EXPRESSWAY (PHASE-II PKG-XIV) FROM JUNCTION WITH PATHANKOT-GURDASPUR ROAD (NH-5 | NHAI | N24001551 | 10-2021 | 9/2024 | Dec-2025 | 12/2025 | 3044.02 | 3044.02 | 3044.02 | 1586.31 | 70.95
May 2025 |  |  | 529 | DELHI-AMRITSAR-KATRA EXPRESSWAY (PHASE-II PKG-XV) [JUNCTION WITH HIRANAGAR ROAD NEAR VILLAGE GURHA B | NHAI | N24001552 | 10-2021 | 9/2024 | Feb-2026 | 2/2026 | 2714.95 | 2714.95 | 2714.95 | 1642.02 | 85.37
May 2025 |  |  | 530 | CORRIDOR EFFICIENCY IMPROVEMENT INCLUDING REMOVAL OF BLACK SPOTS IN LAKHANPUR - SAMBA SECTION OF NH- | NHAI | N24001619 | 8-2022 | 6/2024 | Jun-2025 | 6/2025 | 200.05 | 200.05 | 208.92 | 153.05 | 58.6
May 2025 |  |  | 531 | CONSTRUCTION OF TUNNELS/VIADUCTS AT IDENTIFIED SLIDING/SLIP ZONES AT KM 130.550 TO KM.130.750; KM. | NHAI | N24001620 | 9-2021 | 10/2023 | Dec-2025 | 12/2025 | 442.14 |  | 442.14 | 341.75 | 19.88
May 2025 |  |  | 532 | 4L OF KM.165.092 TO KM.171.855 (NORTH BOUND) AND FROM KM.166.895 TO KM.173.638 (SOUTH BOUND), EXCL. | NHAI | N24001621 | 7-2021 | 8/2024 | Jun-2025 | 6/2025 | 614.48 |  | 614.48 | 187.59 | 7
May 2025 |  |  | 533 | 4L TWIN TUBE TUNNEL INCLUDING APPROACHES FROM DIGDOL TO KHUNI NALLAH (NORTH BOUND CONNECTING WITH EX | NHAI | N24001622 | 7-2021 | 6/2024 | Jun-2025 | 6/2025 | 1401.87 |  | 1401.87 | 734.56
May 2025 |  |  | 534 | BANIHAL BYPASS (DELINKED FROM SRINAGAR - BANIHAL) FROM KM. 187.00 TO KM. 189.350 | NHAI | N24001623 | 1-2020 | 1/2024 | Feb-2025 | 2/2025 | 336.01 |  | 336.01 | 222.97 | 34
May 2025 |  |  | 535 | CONSTRUCTION OF EMERGENCY LANDING FACILITY FROM KM. 246.60 TO KM. 249.70 ON SRINAGAR - BANIHAL SECTI | NHAI | N24001624 | 7-2019 | 10/2020 | Apr-2023 | 9/2024 | 157.05 |  | 157.05 | 139.54 | 100
May 2025 |  |  | 536 | 4L OF TWIN TUBE TUNNEL CONFIGURATION INCLUDING APPROACHES FROM MAROG TO DIGDOL (FROM KM.154.210 TO K | NHAI | N24001627 | 7-2021 | 2/2025 | May-2026 | 5/2026 | 1912.17 |  | 1912.17 | 129.05
May 2025 |  |  | 537 | JAMMU - AKHNOOR SECTION OF NH 144A PKG-3B | NHIDCL | N24001833 | 7-2022 | 3/2025 | N.A. | 8/2025 | 198.28 |  | 198.28 | 85.39 | 71.09
May 2025 |  |  | 538 | REHABILITATION AND UPGRADATION TO 2 LANE WITH PAVED SHOULDER FROM EXISTING CHAINAGE KM 102 TO KM 13 | BRO | N24001897 | 3-2021 | 7/2024 | Mar-2025 | 3/2024 | 642.24 |  | 642.24 | 345.14 | 95
May 2025 |  |  | 539 | REHABILITATION AND UPGRADATION TO 2 LANE WITH PAVED SHOULDER FROM EXISTING CHAINAGE KM 30.000 TO K | BRO | N24001898 | 7-2020 | 11/2024 | N.A. | 11/2024 | 272.49 |  | 272.49 | 133.66 | 87.24
May 2025 |  |  | 540 | REHABILITATION AND UPGRADATION TO 2 LANE WITH PAVED SHOULDER FROM EXISTING CHAINAGE KM 134.95 TO KM | BRO | N24001899 | 2-2021 | 7/2024 | N.A. | 3/2025 | 395.25 |  | 395.25 | 140.42 | 64
May 2025 |  |  | 541 | REHABILITATION AND UPGRADATION TO 2 LANE WITH PAVED SHOULDER FROM EXISTING CHAINAGE KM 49.150 TO KM | BRO | N24001900 | 3-2020 | 8/2024 | N.A. | 3/2025 | 796.97 |  | 796.97 | 323.85 | 79
May 2025 |  |  | 542 | REHABILITATION AND UPGRADATION TO 2 LANE WITH PAVED SHOULDER FROM EXISTING CHAINAGE KM 64.535 TO K | BRO | N24001901 | 3-2020 | 9/2023 | N.A. | 3/2025 | 152.93 |  | 152.93 | 90.3 | 78.27
May 2025 |  |  | 543 | CONSTRUCTION OF TWIN TUBE TUNNELS ON JAMMU KASHMIR RING ROAD (NH-244A) BETWEEN DESIGN CH. 50+600 TO | NHAI | N24001926 | 3-2023 | 6/2025 | N.A. | 3/2026 | 939.86 |  | 939.86 | 475.07 | 64.93
May 2025 |  |  | 544 | CONSTRUCTION OF 4 LANE WITH PAVED SHOULDER FROM (DESIGN CH. 14+200 TO 24+400), (DESIGN CH. 35+300 TO | BRO | N24001998 | 6-2022 | 8/2025 | N.A. | 8/2025 | 832.46 |  | 823.46 | 227.5 | 46
May 2025 |  |  | 545 | 2L NH-1 FROM KM 8.660 TO KM 33.775 (SUMBAL TO WAYUL) TO 4L DUAL CARRIAGEWAY NH STANDARD AS PART OF S | NHAI | N24002059 | 9-2022 | 6/2026 | Jun-2026 | 12/2026 | 1183.6 |  | 1183.6 | 185.45 | 12.62
May 2025 |  |  | 546 | DELHI AMRITSAR KATRA EXPRESSWAY (PHASE-II PKG XVIII) DEVELOPMENT AND UPGRADATION OF FOUR LANE ACCESS | NHAI | N24002060 | 3-2023 | 11/2025 | N.A. | 3/2026 | 1107 |  | 975.38 | 338.69 | 38.38
May 2025 |  |  | 547 | 4/6L ACCESS CONTROL EXPRESSWAY FROM DESIGN CHAINAGE KM 515.000 TO 528.300 (KUNJWANI TO SIDHRA SECTIO | NHAI | N24002061 | 8-2022 | 6/2025 | N.A. | 2/2026 | 2474.47 |  | 2894.74 | 923.64 | 38.2
May 2025 |  |  | 548 | REHABILITATION AND UPGRADATION TO 2 LANE WITH PAVED SHOULDER FROM DESIGN CHAINAGE KM 162.800 TO KM | BRO | N24002119 | 10-2022 | 1/2026 | N.A. | 1/2026 | 562.45 |  | 562.45 | 99.06 | 25
May 2025 |  |  | 549 | CONSTRUCTION OF 4 LANE WITH PAVED SHOULDER (PATTAN BYPASS) GREENFIELD BYPASS FROM EXISTING CH. KM 24 | BRO | N24002179 | 3-2023 | 7/2026 | N.A. | 7/2026 | 980.21 |  | 980.21 | 300.02 | 8
May 2025 |  |  | 550 | REHABILITATION AND UPGRADATION TO 2 LANE WITH PAVED SHOULDER FROM EXISTING CHAINAGE KM 166.100 TO KM | BRO | N24002180 | 9-2021 | 7/2026 | N.A. | 7/2026 | 734.64 |  | 734.64 | 19.6 | 8
May 2025 |  |  | 551 | CONSTRUCTION OF 2 LANE WITH PAVED SHOULDERS (BARAMULLA BYPASS) GREENFIELD BYPASS FROM EXISTING CH. K | BRO | N24002185 | 3-2023 | 9/2026 | N.A. | 9/2026 | 992.43 |  | 992.43 | 338.33
May 2025 |  |  | 552 | WIDENING AND STRENGTHENING OF RAFIABAD-KUPWARA-CHOWKIBAL- TANGDHAR-CHAMKOT (NH-701) ROAD FROM DESIGN | BRO | N24002210 | 3-2024 | 5/2027 | N.A. | 5/2027 | 1404.94 |  | 1404.94 | 0
May 2025 |  |  | 553 | RAJRAPPA RCE OCP ( 3.0 MTY) | CCL | N06000087 | 12-2009 | 3/2016 | N.A. | 3/2027 | 510.85 |  | 510.85 | 488.57 | 75
May 2025 |  |  | 554 | MURAIDIH UG TURN-KEY PROJECT | BCCL | N06000096 | 2-2011 | 4/2014 | N.A. | 1/2026 | 339.88 |  | 339.88 | 190.48 | 70
May 2025 |  |  | 555 | MOONIDIH XV SEAM UG | BCCL | N06000098 | 8-2011 | 3/2019 | N.A. | 5/2026 | 1230.27 |  | 1230.27 | 605.99 | 81
May 2025 |  |  | 556 | CHITRA EAST (RCE) OCP | ECL | N06000169 | 8-2018 | 3/2026 | Mar-2026 | 3/2026 | 513.98 |  | 513.98 | 227.74 | 51
May 2025 |  |  | 557 | TETARIAKHAR EXPANSION OCP | CCL | N06000186 | 11-2019 | 3/2023 | N.A. | 3/2027 | 243.52 |  | 243.52 | 44.64 | 24
May 2025 |  |  | 558 | PACHWARA SOUTH COAL BLOCK | NLC | N06000193 | 7-2013 | 9/2028 | N.A. | 9/2028 | 2242.92 | 2242.9 | 2242.9 | 687.46 | 54
May 2025 |  |  | 559 | PATHERDIH 2.5 NLW COAL WASHERY | BCCL | N06000194 | 10-2015 | 4/2018 | N.A. | 3/2026 | 334.27 |  | 334.27 | 135.86 | 45.05
May 2025 |  |  | 560 | REVISED PROJECT REPORT MAGADH EXPANSION OCP | CCL | N06000216 | 8-2020 | 3/2028 | N.A. | 3/2028 | 7254.37 |  | 7254.37 | 1500.33 | 38
May 2025 |  |  | 561 | EXPANSION PROJECT AMRAPALI OCP | CCL | N06000217 | 8-2020 | 3/2028 | N.A. | 3/2028 | 5136.15 |  | 5136.15 | 1082.09 | 41
May 2025 |  |  | 562 | UCE OF EPR OF NORTH URIMARI OCP | CCL | N06000218 | 7-2021 | 3/2029 | N.A. | 3/2029 | 778.8 |  | 778.8 | 694.11 | 75
May 2025 |  |  | 563 | KOTRE BASANTPUR PACHMO OCP | CCL | N06000237 | 8-2020 | 3/2032 | N.A. | 3/2032 | 625.4 | 625.4 | 625.4 | 441.24 | 41
May 2025 |  |  | 564 | CHANDRAGUPT OCP | CCL | N06000238 | 8-2020 | 3/2032 | N.A. | 3/2032 | 973.5 |  | 973.5 | 339.32 | 12.4
May 2025 |  |  | 565 | SIRKA OCP | CCL | N06000239 | 5-2020 | 3/2028 | N.A. | 3/2028 | 222.82 |  | 222.82 | 139.31 | 60
May 2025 |  |  | 566 | JHARKHAND LAIYO OCP | CCL | N06000240 | 8-2020 | 3/2031 | N.A. | 3/2031 | 764.57 |  | 764.57 | 145.8 | 28
May 2025 |  |  | 567 | EPR TAPIN SOUTH OCP | CCL | N06000241 | 11-2020 | 3/2028 | N.A. | 3/2028 | 230.41 |  | 230.41 | 21.12 | 18.3
May 2025 |  |  | 568 | EPR PUNDI OCP | CCL | N06000242 | 11-2020 | 3/2027 | N.A. | 3/2027 | 713.35 |  | 713.35 | 236.57 | 21
May 2025 |  |  | 569 | EPR ROHINI KARKATA OCP | CCL | N06000243 | 1-2021 | 3/2028 | N.A. | 3/2028 | 1020.42 |  | 1020.42 | 83.44 | 11.7
May 2025 |  |  | 570 | EXPANSION OF KONAR OCP | CCL | N06000245 | 1-2022 | 3/2032 | N.A. | 3/2032 | 799.34 |  | 799.34 | 416.73 | 32
May 2025 |  |  | 571 | EXPANSION OF KARO OCP | CCL | N06000246 | 1-2022 | 3/2029 | N.A. | 3/2029 | 908.47 |  | 908.47 | 217.68 | 21
May 2025 |  |  | 572 | EXPANSION OF ASHOK OCP | CCL | N06000247 | 5-2021 | 3/2028 | N.A. | 3/2028 | 2898.28 |  | 2898.28 | 176.5 | 20
May 2025 |  |  | 573 | AMALGAMATED NTST KUJAMA OCP 8.5 MTY | BCCL | N06000273 | 1-2023 | 3/2030 | N.A. | 3/2030 | 4011.85 |  | 4011.85 | 397.65 | 25
May 2025 |  |  | 574 | HURA C OC | ECL | N06000275 | 8-2022 | 3/2029 | N.A. | 3/2029 | 859.41 |  | 859.41 | 448.6 | 62
May 2025 |  |  | 575 | CHUPERBHITA- SIMLONG OCP | ECL | N06000280 | 12-2023 | 3/2037 | Mar-2037 | 3/2037 | 979.08 |  | 979.08 | 0
May 2025 |  |  | 576 | BLOCK-E OCP (15 MTY) | BCCL | N06000287 | 3-2024 | 3/2029 | N.A. | 3/2029 | 5850.83 |  | 5850.83 | 5.85 | 2
May 2025 |  | DEPARTMENT OF HIGHER EDUCATION | 577 | 2000 BOYS HOSTEL(1000 DOUBLE BEDDED ROOM) AT ISM DHANBAD | CPWD EDUCATION | N28000067 | 9-2012 | 3/2016 | N.A. | 3/2016 | 171.86 |  | 171.86 | 174.48
May 2025 |  | PETROLEUM | 578 | DEVELOPMENT OF JHARIA CBM BLOCK | PHASE-1 | ONGC | 11-2019 | 1/2024 | Mar-2025 | 6/2025 | 431 |  | 431 | 194.4 | 57.9
May 2025 |  | PETROLEUM | 579 | LAYING OF NATURAL GAS PIPELINE FROM HAZARIBAGH TO RANCHI | IOCL | N16000480 | 3-2023 | 2/2026 | N.A. | 2/2026 | 202.07 |  | 202.07 | 52.94 | 42.91
May 2025 |  | PETROLEUM | 580 | CGD PROJECT IN BIHAR JHARKHAND | HPCL | N16000497 | 6-2022 | 6/2030 | N.A. | 6/2030 | 1377 |  | 1377 | 277.81 | 22.6
May 2025 |  | POWER | 581 | NORTH KARANPURA STPP (3X660 MW) | NTPC | N18000177 | 2-2014 | 6/2019 | Oct-2022 | 3/2025 | 16242.9 |  | 16242.9 | 16745.68 | 98
May 2025 |  | POWER | 582 | PATRATU STPP-I (3X800MW) | NTPC | N18000275 | 11-2017 | 3/2023 | N.A. | 3/2026 | 17112 |  | 17112 | 16305.18 | 81
May 2025 |  | POWER | 583 | BADAM COAL MINING PROJECT | NTPC | N18000367 | 2-2019 | 10/2024 | Apr-2027 | 4/2027 | 501.79 | 784.39 | 501.79 | 305.97 | 59.79
May 2025 |  | POWER | 584 | KERANDARI COAL MINING PROJECT | NTPC | N18000370 | 9-2015 | 11/2019 | Mar-2025 | 3/2025 | 1553 | 2896.64 | 2896.64 | 2086.52 | 64
May 2025 |  | POWER | 585 | KODERMA-TILAIYA (NL), ECR | ECR | 220100305 | 4-2002 | 3/2023 | N.A. | 12/2025 | 1625.87 | 1625.87 | 1700 | 2013.59 | 80
May 2025 |  | POWER | 586 | BONDAMUNDA RANCHI DOUBLING | SER | N22000396 | 3-2016 | 6/2024 | N.A. | 6/2026 | 3029.04 | 3029.04 | 3029.04 | 2390.21 | 84
May 2025 |  |  | 587 | LODHMA TO PISKA LINK LINE BY PASSING HATIA/RANCHI WITH Y CONNECTION (17.2 KM) | SER | N22000508 | 4-2018 | 6/2026 | N.A. | 6/2026 | 501.52 |  | 472.5 | 275.86 | 4
May 2025 |  |  | 588 | DOUBLING OF PRADHANKHUNTA JN - PATHERDIH BAZAR-BHOJUDIH | ECR | N22000529 | 11-2022 | 11/2027 | N.A. | 3/2026 | 202 | 349.22 | 349.22 | 64.1 | 2
May 2025 |  |  | 589 | KHARAGPUR-ADITYAPUR - 3RD LINE (132 KM) | RVNL | N22000595 | 12-2015 | 3/2025 | N.A. | 3/2025 | 3249.98 |  | 3270.07 | 2899.45
May 2025 |  |  | 590 | 3RD LINE BETWEEN DHANBAD SONNAGAR | RVNL | N22000599 | 11-2016 | 3/2026 | N.A. | 3/2026 | 8975 |  | 7906.38 | 4705.38
May 2025 |  |  | 591 | GARHWA ROAD - RAIL OVER RAIL | ECR | N22000610 | 3-2017 | 6/2024 | N.A. | 2/2026 | 262.71 |  | 262.71 | 226.43 | 70
May 2025 |  |  | 592 | GOMOH - FLYOVER FOR DOWN TRAINS | ECR | N22000611 | 1-2018 | 3/2023 | N.A. | 3/2026 | 686.03 |  | 487.73 | 399.45 | 45
May 2025 |  |  | 593 | SIX LANING OF BIHAR - JHARKHAND BORDER (CHORDAHA) TO GORHAR SECTION | NHAI | N24000726 | 1-2018 | 11/2021 | May-2026 | 5/2026 | 1155.16 |  | 950.49 | 657.82 | 73
May 2025 |  |  | 594 | WIDENING TO 2 LANE WITH PAVED SHOULDERS AND GEOMETRIC IMPROVEMENT OF NH-114A FROM KM 141 TO KM 184 I | MoRTH | N24001216 | 12-2016 | 9/2021 | N.A. | 12/2024 | 196 |  | 196 | 164.21 | 90.1
May 2025 |  |  | 595 | HARIHARGANJ TO PARWA MODE SECTION FROM KM 23.284 TO KM 57.049 OF NH-98 | NHAI | N24001589 | 9-2020 | 3/2024 | Dec-2024 | 4/2025 | 755.26 |  | 1039 | 624.66 | 87
May 2025 |  |  | 596 | 4L FROM KM 196.87 (SANKHA) TO KM 219.6 (KHAJURI) ON NH-75 [REHLA / GARHWA BYPASS] | NHAI | N24001590 | 9-2020 | 10/2023 | Dec-2024 | 1/2025 | 748.99 |  | 903 | 831.75 | 100
May 2025 |  |  | 597 | ELEVATED CORRIDOR IN RANCHI CITY FROM KM 0.00 TO KM 3.260 OF NH-75 INCLUDING DOWN RAMP ON NH-23 FROM | NHAI | N24001594 | 2-2022 | 1/2025 | Mar-2025 | 3/2025 | 534.73 |  | 534.73 | 205.31 | 98
May 2025 |  |  | 598 | 4L OF PALMA TO GUMLA SECTION OF NH23 FROM KM. 26.00 TO KM. 89.170 ON HAM MODE IN THE STATE OF JHARKH | NHAI | N24001595 | 8-2020 | 3/2024 | Jun-2025 | 6/2025 | 1034 | 1879.55 | 1879.55 | 41.5 | 96.61
May 2025 |  |  | 599 | 4L OF MIRZA CHAUKI TO FARKKA SECTION OF NH80 FROM KM 215.00 TO KM 260.00 ON HAM MODE IN THE STATE OF | NHAI | N24001596 | 11-2021 | 7/2023 | Jun-2025 | 6/2025 | 1302.72 | 1504.8 | 1504.8 | 875.97 | 71.4
May 2025 |  |  | 600 | FOUR LANING WITH PAVED SHOULDER OF SECTION FROM KM 53.600 (GOLA ON NH- 320) TO KM 81.446 (ORMANJHI ON | NHAI | N24001854 | 6-2023 | 6/2025 | N.A. | 6/2025 | 1214.93 | 1324.95 | 1462 | 808.69 | 73
May 2025 |  |  | 601 | WIDENING TO 2-LANE WITH PAVED SHOULDER FROM KM 0.00 TO 44.00 (KURU- GHAGHRA SECTION) OF NH-143A INCLU | MoRTH | N24001922 | 2-2020 | 8/2023 | N.A. | 12/2024 | 153.01 |  | 153.01 | 83.63 | 96.23
May 2025 |  |  | 602 | WIDENING AND STRENGTHENING OF EXISTING PAVEEMNT TO TWO LANE WITH PAVED SHOULDERS FROM KM 116.00 TO K | MoRTH | N24001923 | 1-2022 | 7/2024 | N.A. | 12/2024 | 315.21 |  | 315.21 | 117.26 | 80
May 2025 |  |  | 603 | WIDENING AND STRENGTHENING TO TWO LANE WITH PAVED SHOULDER/TWO LANE+ PAVED SHOULDER WITH SERVICE ROA | MoRTH | N24001924 | 3-2022 | 8/2025 | N.A. | 8/2025 | 514.22 |  | 514.22 | 15.19 | 6.1
May 2025 |  |  | 604 | WIDENING AND STRENGTHENING/RECONSTRUCTION TO TWO LANE WITH PAVED SHOULDER/ TWO LANE WITH PAVED SHOUL | MoRTH | N24001925 | 3-2022 | 8/2025 | N.A. | 8/2025 | 423.18 |  | 423.18 | 0.11
May 2025 |  |  | 605 | FOUR LANING OF KHAJURI TO WYNDHAMGANJ FROM KM 219.600 TO KM 260.483 ON NH-75 PKG SEC-V ON HAM | NHAI | N24002053 | 4-2022 | 9/2025 | N.A. | 9/2025 | 1232 | 1343 | 1400 | 606.6 | 78.5
May 2025 |  |  | 606 | FOUR LANING OF BHOGU TO SANKHA FROM KM 147.450 TO KM 196.870 ON NH-75 PKG SEC-III | NHAI | N24002054 | 10-2022 | 11/2025 | N.A. | 11/2025 | 1390.77 | 1391 | 1600 | 303 | 70
May 2025 |  |  | 607 | FOUR LANING OF BASUKINATH-DEOGHAR SECTION OF NH-114A FROM KM 85.081 TO KM 130.240 UNDER NHDP PHASE-I | NHAI | N24002055 | 3-2023 | 12/2025 | N.A. | 12/2025 | 1444.94 |  | 1444.94 | 0
May 2025 |  |  | 608 | BHARATMALA PARIYOJANA OF BOKARO JAINA MORE - GOLA SECTION OF NH-320 FROM KM. 21.110 TO KM. 53.600 IN | NHAI | N24002056 | 6-2020 | 6/2025 | N.A. | 6/2025 | 964.64 |  | 964.64 | 432.7 | 60.24
May 2025 |  |  | 609 | FOUR LANING OF MEHGAMA HANSDIHA SECTION OF NH-33 FROM EXISTING KM 41.900 TO 93.000 IN THE STATE OF J | NHAI | N24002057 | 12-2022 | 5/2025 | N.A. | 5/2025 | 1443.77 |  | 1443.77 | 0
May 2025 |  |  | 610 | NEW SINTER PLANT AT BOKARO STEEL PLANT | SAIL | N12000095 | 3-2015 | 10/2017 | Nov-2026 | 11/2026 | 1034.01 | 1752.3 | 1752.3 | 874.75 | 51.75
May 2025 |  |  | 611 | REVAMPING OF OLD SUB SYSTEM OF BLAST FURNACE 3 AT BOKARO STEEL PLANT | SAIL | N12000129 | 9-2023 | 7/2025 | Nov-2025 | 11/2025 | 513.82 |  | 513.82 | 179.29 | 64
May 2025 |  |  | 612 | REBUILDING OF COKE OVEN BATTERY NO.6 OF BOKARO STEEL PLANT | SAIL | N12000133 | 11-2023 | 11/2026 | N.A. | 11/2026 | 627.31 |  | 627.31 | 84.56 | 33
May 2025 |  |  | 613 | REPLACEMENT OF REMAINING 04 NOS. OF BATTERY CYCLONES WITH 04 NOS. OF ESPS IN SINTER PLANT-1 AT BSL | SAIL | N12000135 | 3-2024 | 6/2026 | N.A. | 6/2026 | 260.37 |  | 260.37 | 42.86 | 12
May 2025 |  |  | 614 | REPLACEMENT OF EXISTING GRINDERS IN CRM-I & II AT BOKARO STEEL PLANT | SAIL | N12000142 | 1-2025 | 1/2027 | N.A. | 1/2027 | 211.94 |  | 211.94 | 0
May 2025 |  |  | 615 | SECONDARY EMISSION CONTROL IN CONVERTERS OF SMS-II AT BOKARO STEEL PLANT | SAIL | N12000143 | 1-2025 | 10/2026 | N.A. | 10/2026 | 207.13 |  | 207.13 | 0 | 1
May 2025 |  | CIVIL AVIATION | 616 | BELAGAVI AIRPORT- EXPANSION OF TERMINAL BUILDING AND ASSOCIATED WORKS | AAI | N04000105 | 6-2023 | 2/2026 | N.A. | 2/2026 | 322.45 |  | 322.45 | 95.91 | 40
May 2025 |  | CIVIL AVIATION | 617 | HUBBALI AIRPORT - CONSTRUCTION OF NEW DOMESTIC TERMINAL BUILDING AND MISCELLANEOUS WORKS | AAI | N04000108 | 6-2023 | 2/2026 | N.A. | 2/2026 | 320.47 |  | 320.47 | 50.51 | 27.5
May 2025 |  | DEPARTMENT OF HIGHER EDUCATION | 618 | CONSTRUCTION OF PERMANENT CAMPUS FOR INDIAN INSTITUTE OF TECHNOLOGY, DHARWAD (PHASE 1A) | CPWD EDUCATION | N42000006 | 7-2019 | 3/2022 | Jun-2025 | 11/2025 | 851 | 930.36 | 930.36 | 918.06 | 99
May 2025 |  | DEPARTMENT OF HIGHER EDUCATION | 619 | ADDITIONAL INFRASTRUCTURE AT IISC BANGALORE SH RCC MONOLITHIC FOR MEN WOMEN HOSTEL | CPWD | N42000010 | 8-2021 | 2/2024 | Nov-2024 | 11/2024 | 316.25 |  | 316.25 | 281.32 | 91
May 2025 |  | PETROLEUM | 620 | CONSTRUCTION OF 80000MT LPG CAVERN AT MANGALORE | HPCL | N16000369 | 12-2018 | 12/2022 | Aug-2025 | 8/2025 | 854 | 854 | 854 | 696.35 | 99.5
May 2025 |  | PETROLEUM | 621 | REVAMPING, AUGMENTATION OF FACILITIES AT EXISTING PORT TERMINAL AT MANGALORE | IOCL | N16000437 | 1-2022 | 7/2025 | Dec-2025 | 12/2025 | 463 | 500.62 | 500.62 | 241.69 | 71.1
May 2025 |  | PETROLEUM | 622 | POWER SYSTEM UPGRADATION PROJECT | MANGALORE REFIN | N16000509 | 10-2023 | 2/2026 | N.A. | 2/2026 | 385 |  | 385 | 122.13 | 56.88
May 2025 |  | PETROLEUM | 623 | DEMO PLANT FOR PRODUCTION OF BIO- ATF | MANGALORE REFIN | N16000536 | 3-2024 | 3/2027 | N.A. | 3/2027 | 364 |  | 364 | 16.85 | 6.6
May 2025 |  | PETROLEUM | 624 | TS FOR INTRGRATION OF RE ZONE (PHASE II) IN KOPPAL II (PHASE A and B) AND GADAG II (PHASE A) IN KARN | PGCIL | N18000385 | 12-2023 | 12/2025 | N.A. | 12/2025 | 2889 |  | 2889 | 891.98 | 28.5
May 2025 |  |  | 625 | TS FOR SOLAR ENERGY ZONE IN BIDAR (2500MW), KARNATAKA [BIDAR TRANSMISSION LTD] | PGCIL | N18000388 | 2-2024 | 2/2026 | N.A. | 2/2026 | 2148 |  | 2148 | 846.6 | 43.8
May 2025 |  |  | 626 | SYSTEM STRENGTHENING AT KOPPAL-II AND GADAG-II FOR INTEGRATION OF RE GENERATION PROJECTS | PGCIL | N18000409 | 1-2025 | 1/2027 | N.A. | 1/2027 | 1354 |  | 1354 | 0
May 2025 |  |  | 627 | AUGMENTATION OF TRANSFORMATION CAPACITY AT BIDAR PS | PGCIL | N18000410 | 2-2025 | 2/2027 | N.A. | 2/2027 | 288 |  | 288 | 0
May 2025 |  |  | 628 | TRANSMISSION SCHEME FOR INTEGRATION OF DAVANAGERE / CHITRADURGA AND BELLARY REZ IN KARNATAKA | PGCIL | N18000419 | 3-2025 | 3/2027 | N.A. | 3/2027 | 3453 |  | 3453 | 0
May 2025 |  |  | 629 | TUMKUR-CHITRADURGA-DAVENGERE NL | SWR | N22000256 | 4-2011 | 3/2019 | N.A. | 12/2027 | 1876 |  | 1801.01 | 498.03 | 12
May 2025 |  |  | 630 | BAGALKOT-KUDACHI NL | SWR | N22000258 | 4-2010 | 3/2027 | N.A. | 3/2027 | 1378 | 1378 | 1378 | 643.99 | 34
May 2025 |  |  | 631 | HOSPET-HUBLI-LONDA-VASCODAGAMA DL | RVNL | N22000297 | 4-2010 | 3/2027 | N.A. | 12/2026 | 5060.36 |  | 3692.6 | 3505.49
May 2025 |  |  | 632 | GADAG-WADI NL | SWR | N22000299 | 4-2013 | 3/2027 | N.A. | 3/2028 | 2841.84 |  | 2841.84 | 1306.74 | 29
May 2025 |  |  | 633 | MARIKUPPAM - KUPPAM | SWR | N22000308 | 4-2012 | 3/2016 | N.A. | 12/2027 | 279.54 | 296.72 | 296.72 | 121.12 | 14
May 2025 |  |  | 634 | KADUR CHIKMAGALUR SAKLESHPUR NEW LINE (93 KM) | SWR | N22000486 | 3-1996 | 6/2025 | N.A. | 3/2026 | 825.31 | 825.31 | 825.31 | 687.05 | 83
May 2025 |  |  | 635 | BAIYYAPPANAHALLI-HOSUR (48 KM) | NCRTC | N22000542 | 4-2019 | 3/2026 | N.A. | 3/2026 | 375.67 |  | 375.67 | 0
May 2025 |  |  | 636 | YESHVANTHPUR-CHANNASANDRA (21.7 KM) | NCRTC | N22000543 | 4-2019 | 3/2026 | N.A. | 3/2026 | 169.65 |  | 169.65 | 71.75
May 2025 |  |  | 637 | BELGAUM-DHARWAD VIA KITTUR (73.10 KM) | UMBRELLA WORK PB#22/2019-20/NR | SWR | 9-2020 | 12/2027 | N.A. | 3/2029 | 1590.8 | 927.42 | 927.42 | 0.75
May 2025 |  |  | 638 | HASSAN (ALUR) - BELUR (32 KM) | UMBRELLA WORK PB#23/2018-19/NR | SWR | 6-2019 | 4/2028 | N.A. | 3/2028 | 748.86 | 748.85 | 748.85 | 0.88 | 1
May 2025 |  |  | 639 | SHIMOGA-SHIKARIPURA-RANEBENNUR | UMBRELLA WORK PB#23/2018-19/NR | SWR | 9-2019 | 12/2027 | N.A. | 12/2028 | 1453.73 | 994.47 | 994.47 | 80.24 | 7
May 2025 |  |  | 640 | BANGALORE-WHITEFIELD-BANGALORE CITY-KRISHNARAJAPURAM QUADRUPLING | SWR | N22000621 | 3-2018 | 6/2025 | N.A. | 2/2026 | 492.87 | 492.87 | 492.87 | 251.52 | 75
May 2025 |  |  | 641 | STRENGTHENING AND WIDENING TO TWO LANE WITH PAVED SHOULDERS FROM KM.106.00 TO 153.00 OF NH-218 BIJAP | MoRTH | N24000334 | 3-2015 | 11/2015 | Aug-2024 | 8/2024 | 165.67 |  | 165.67 | 126.47 | 98.99
May 2025 |  |  | 642 | 4-LANING OF GOA/KARNATAKA BORDER- KUNDAPUR SECTION | NHAI | N24000462 | 7-2012 | 8/2016 | Jan-2020 | 6/2025 | 1655.01 | 1990.99 | 1990.99 | 1818.5 | 97.8
May 2025 |  |  | 643 | WIDENING TO TWO LANE WITH PAVED SHOULDER FROM KM 544.200 TO KM 594.000 OF NH-150A HOSMANE CROSS ? PA | MoRTH | N24001156 | 1-2017 | 9/2017 | May-2023 | 5/2023 | 166.67 |  | 264.34 | 192.08 | 100
May 2025 |  |  | 644 | IMPROVEMENTS AND RECONSTRUCTION TO TWO LANE WITH PAVED SHOULDERS FROM KM 243.20 TO KM 290.20 OF NH | MoRTH | N24001157 | 8-2016 | 2/2017 | Jul-2024 | 7/2024 | 175.5 |  | 241.6 | 178.73 | 90.01
May 2025 |  |  | 645 | RECONSTRUCTION TO TWO LANE WITH PAVED SHOULDERS FROM DS. CH. 442+180 (EX. KM 448.00) TO DS. CH.485+2 | MoRTH | N24001158 | 3-2018 | 6/2019 | Dec-2023 | 12/2023 | 159.97 |  | 242.61 | 113.15 | 100
May 2025 |  |  | 646 | WIDENING TO TWO LANE WITH PAVED SHOULDERS FROM KM 20.150 TO KM 40.00 OF BC ROAD KOTTIGEHARA SECTION | MoRTH | N24001159 | 1-2018 | 7/2018 | N.A. | 3/2022 | 159.7 |  | 159.7 | 142.88 | 100
May 2025 |  |  | 647 | WIDENING TO TWO LANE WITH PAVED SHOULDER FROM KM 194.900 TO KM 243.200 OF NH-234 BANAVARA-HULIYAR | MoRTH | N24001160 | 9-2017 | 10/2018 | Apr-2022 | 4/2022 | 191.6 |  | 191.6 | 112.01 | 100
May 2025 |  |  | 648 | WIDENING TO TWO LANE WITH PAVED SHOULDERS FROM 24.600 TO 70.063 OF MUDIGERE TO KADUR SECTION OF NH- | MoRTH | N24001161 | 12-2017 | 1/2019 | Apr-2022 | 4/2022 | 297.3 |  | 318.28 | 277.27 | 100
May 2025 |  |  | 649 | IMPROVEMENT AND RECONSTRUCTION TO TWO LANE WITH PAVED SHOULDERS FROM KM 489.845 (NEW KM.58.125) AN | MoRTH | N24001162 | 3-2018 | 10/2018 | Nov-2022 | 11/2022 | 325.86 |  | 386.41 | 356.76 | 100
May 2025 |  |  | 650 | WIDENING TO 2 LANE WITH PAVED SHOULDERS FROM KM 0 TO 54 OF NH-50 UNDER EPC MODE IN THE STATE OF KARN | MoRTH | N24001164 | 10-2016 | 3/2017 | Jul-2022 | 7/2022 | 396.96 |  | 396.96 | 329.58 | 100
May 2025 |  |  | 651 | WIDENING TO 2 LANE WITH PAVED SHOULDERS FROM KM 34.00 TO 70.900 OF NH-150 UNDER EPC MODE IN THE STAT | MoRTH | N24001165 | 11-2016 | 3/2017 | Oct-2021 | 10/2021 | 314.9 |  | 314.9 | 233.95 | 100
May 2025 |  |  | 652 | WIDENING TWO LANE WITH PAVED SHOULDERS FROM FROM KM.56.00 TO 106.00 OF NH-218 (218-KNT-2014-15-775) | MoRTH | N24001166 | 3-2015 | 1/2016 | N.A. | 7/2024 | 159.12 |  | 159.12 | 127.72 | 98
May 2025 |  |  | 653 | ESTIMATE FOR WIDENING TWO LANE TO FOUR LANE FROM FROM KM.129.00 TO 144.00 OF NH-63 ANKOLA-GOOTY SECT | MoRTH | N24001168 | 5-2018 | 5/2018 | Dec-2023 | 12/2023 | 171.6 |  | 171.6 | 129.72 | 100
May 2025 |  |  | 654 | WIDENING TO TWO LANE WITH PAVED SHOULDER FROM KM 4.40 TO KM 56.00 OF NH-218 BIJAPURA-HUBLI SECTION U | MoRTH | N24001172 | 1-2017 | 8/2017 | N.A. | 6/2022 | 291.49 |  | 291.49 | 238.77 | 100
May 2025 |  |  | 655 | CONSTRUCTION OF MAJOR BRIDGE AT KM 180.865 ACROSS RIVER KRISHNA ON NH- 167 HAGARI ? JADERCELA SECTION | MoRTH | N24001173 | 2-2017 | 5/2019 | N.A. | 10/2025 | 157.32 | 188 | 187.61 | 43.16 | 60
May 2025 |  |  | 656 | WIDENING TO 2-LANE WIH PAVED SHOULDER FROM KM. 544.20 TO 594.00 (HOSAMANE CROSS TO PANDAVAPURA) SECT | MoRTH | N24001387 | 1-2017 | 9/2017 | May-2023 | 5/2023 | 264.34 |  | 264.34 | 201.07 | 100
May 2025 |  |  | 657 | CONSTRUCTION OF MAJOR BRIDGE ACROSS SHARAVATHI BACKWATERS AND APPROCHES BETWEEN AMBARGODU AND KALASA | MoRTH | N24001388 | 3-2019 | 12/2019 | Nov-2024 | 11/2024 | 423.15 |  | 423.15 | 268.97 | 82
May 2025 |  |  | 658 | 4L OF ADDAHOLE TO BANTWAL CROSS SECTION INCLUDING FLYOVER AT KALLADKA TOWN | NHAI | N24001425 | 3-2021 | 11/2021 | Nov-2025 | 11/2025 | 1100.88 | 1687.31 | 1687.31 | 1149.04 | 80.28
May 2025 |  |  | 659 | 4L OF ADDAHOLE TO BANTWAL CROSS SECTION | NHAI | N24001426 | 3-2021 | 10/2021 | Jun-2025 | 6/2025 | 317.9 | 572.01 | 572.01 | 370.84 | 98
May 2025 |  |  | 660 | 6L FROM SANKESHWAR BYPASS TO MH KNT BORDER FROM KM. 555.017 TO KM. 592.853 OF NH-48 (PKG II) | NHAI | N24001598 | 1-2022 | 4/2025 | Apr-2025 | 4/2025 | 1388.7 | 1388.7 | 1388.7 | 438.61 | 62.5
May 2025 |  |  | 661 | BELAKERI PORT TO KUMTA - SIRSI ROAD FROM KM 0.00 - KM 4.265 OF BELEKERI PORT ROAD LINK RD. AND KM 4. | NHAI | N24001599 | 3-2018 | 12/2022 | Dec-2022 | 12/2025 | 440.16 |  | 440.16 | 355.11 | 69.73
May 2025 |  |  | 662 | BANGALORE/TN BORDER TO HOSKOTE | NHAI | N24001674 | 2-2023 | 2/2025 | Sep-2025 | 9/2025 | 1240.6 | 1181.68 | 1181.68 | 942.92 | 81.52
May 2025 |  |  | 663 | 6L OF MH/KN BORDER (NIMBAL VILLAGE) TO KN/TS BORDER (SINGNODI VILLAGE) FROM KM. 26.000 TO KM. 97.000 | NHAI | N24001676 | 12-2022 | 6/2025 | Mar-2026 | 6/2025 | 2718.46 |  | 2718.46 | 438.9 | 53.72
May 2025 |  |  | 664 | BALANCE WORK OF 2L PS FROM KM 30.800 TO 70.800 AND 2L WITH RIGID CARRIAGEWAY FROM 70.800 TO KM 84.12 | NHAI | N24001677 | 11-2022 | 5/2024 | Apr-2025 | 4/2025 | 226.76 | 226.76 | 226.76 | 86.76 | 71.87
May 2025 |  |  | 665 | 6L FROM BELGAUM TO SANKESHWAR BYPASS FROM KM 515.000 TO KM 555.017 OF NH 48 | NHAI | N24001679 | 10-2022 | 4/2025 | Dec-2025 | 12/2025 | 1479.3 | 1479.3 | 1479.3 | 676.61 | 93.1
May 2025 |  |  | 666 | 4L OF SANNUR TO BIKARNAKATTE SECTION FROM KARKALA TO MANGALORE | NHAI | N24001680 | 3-2021 | 10/2024 | Jan-2026 | 1/2026 | 1409.68 | 1808.12 | 1808.12 | 1032.44 | 59
May 2025 |  |  | 667 | TUMKUR - NELAMANGALA(6L) | NHAI | N24001681 | 8-2022 | 8/2025 | Mar-2026 | 3/2026 | 2032.15 | 2032.15 | 2032.15 | 184.86 | 52.08
May 2025 |  |  | 668 | UPGRADATION 2/4 LANE NH CONNECTIVITY UNDER SAGARMALA SCHEME SH 2 HAVERI YEKAMBI SH 69 YEKAMBI KUMTA | NHAI | N24001682 | 11-2021 | 3/2024 | Mar-2024 | 12/2026 | 294.62 | 309.9 | 309.9 | 55.68 | 15.06
May 2025 |  |  | 669 | 4L OF CHANNARAYAPATNA BYPASS AND HASSAN BYPASS WITH STRUCTURES IN DEVIHALLI -HASSAN SECTION | NHAI | N24001684 | 9-2020 | 1/2023 | Sep-2020 | 5/2025 | 688 | 602.09 | 688 | 514.23 | 80.02
May 2025 |  |  | 670 | FOUR LANING OF BETTADAHALLI TO SRIRAMPURA SECTION FROM KM. 166+100 (DESIGN KM. 170+415) TO KM. 217+0 | NHAI | N24001687 | 10-2021 | 10/2023 | Dec-2025 | 12/2025 | 1331.77 | 2082.98 | 2082.98 | 477.33 | 76.52
May 2025 |  |  | 671 | BALANCE WORK OF CONTSRUCTION OF TWO/FOUR LANE WITH PAVED SHOULDER FROM KM. 54.370 TO KM. 101.400 (BI | MoRTH | N24001936 | 3-2021 | 3/2023 | Jul-2024 | 7/2024 | 344.79 |  | 344.79 | 10 | 90
May 2025 |  |  | 672 | BALANCE WORK OF REHABILITATION AND UPGRADING TO 2LANE/2LANE WITH PAVED SHOULDER CONFIGURATION AND ST | MoRTH | N24001937 | 2-2023 | 2/2024 | Feb-2025 | 2/2025 | 398.48 |  | 398.48 | 5 | 50
May 2025 |  |  | 673 | CONSTRUCTION OF ELEVATED CORRIDOR FROM KM. 135.650 TO 136.300 ON 63, FROM KM. 249 TO KM. 250.050 ON | MoRTH | N24001938 | 6-2021 | 6/2024 | Jun-2025 | 6/2025 | 298 |  | 298 | 10.7 | 52
May 2025 |  |  | 674 | WIDENING TO 2 LANE WITH PAVED SHOULDERS FROM DESIGN KM 103.200 (EXISTING KM 103.200) TO DESIGN KM 11 | MoRTH | N24001940 | 1-2023 | 1/2026 | Sep-2025 | 9/2025 | 166.58 |  | 166.58 | 3.54
May 2025 |  |  | 675 | WIDENING TO 4 LANE FROM KM. 133.00 TO 158.04 (DESIGN CHAINAGE KM. 130.88 TO 155.145) (SHIRUR CROSS T | MoRTH | N24001941 | 1-2023 | 1/2025 | Jan-2025 | 1/2025 | 350.69 |  | 350.69 | 10 | 56
May 2025 |  |  | 676 | WIDENING TO TWO LANE WITH PAVED SHOULDERS FROM KM. 33.13 TO KM. 40.23 AND KM. 52.00 TO KM. 71.00 (EX | MoRTH | N24001943 | 9-2022 | 3/2024 | Jan-2025 | 1/2025 | 172.98 |  | 172.98 | 6.48 | 65
May 2025 |  |  | 677 | WIDENING TO INTERMEDIATE/TWO LANE TO 2 LANE WITH PAVED SHOULDER FROM EXISTING CHANAGES KM 112.750 TO | MoRTH | N24001944 | 1-2023 | 6/2024 | Jul-2024 | 7/2024 | 255.88 |  | 255.88 | 60.99 | 78.24
May 2025 |  |  | 678 | WIDENING TO 2 LANE WITH PAVED SHOULDERS FROM KM 116.800 TO 149.070(DESIGN CHANGES) ON HOSADURGA HOL | MoRTH | N24001945 | 8-2022 | 2/2024 | Dec-2024 | 12/2024 | 170.34 |  | 170.34 | 4.25 | 72
May 2025 |  |  | 679 | WIDENING TO 2 LANES WITH PAVED SHOULDERS FROM KM 24.400 TO 27.270, 40.500 TO 41.900, 84.300 TO 88.20 | MoRTH | N24001946 | 11-2022 | 11/2024 | Nov-2024 | 11/2024 | 218.93 |  | 218.93 | 10 | 95.25
May 2025 |  |  | 680 | WIDENING TO EXISTING 2 LANE WITH PAVED SHOULDER TO 4 LANE WITH PAVED SHOULDER FROM DESIGN KM 153.00 | MoRTH | N24001947 | 2-2023 | 2/2025 | Feb-2025 | 2/2025 | 177.94 |  | 177.94 | 6.66 | 47
May 2025 |  |  | 681 | WIDENING TO 4 LANE FROM KM 51.60 TO 76.20 (HEBRI TO PARKALA) AND FROM KM 85.20 TO 88.90 (KARAVALI JU | MoRTH | N24001948 | 10-2022 | 10/2024 | Dec-2024 | 12/2024 | 355.72 |  | 355.72 | 11.32 | 60
May 2025 |  |  | 682 | FOUR LANING OF LEFT OVER WORKS OF HOSPET BELLARY KARNATAKA/ AP BORDER FROM KM.280.080 TO KM. 375.450 | NHAI | N24001989 | 3-2023 | 5/2025 | N.A. | 5/2025 | 830.28 |  | 830.28 | 652.09 | 75.3
May 2025 |  |  | 683 | DEVELOPMENT OF 6 LANE ACCESS CONTROLLED GREENFIELD HIGHWAY FROM KM. 97.000 TO KM. 162.500 MARADGI S | NHAI | N24001993 | 12-2022 | 10/2025 | N.A. | 10/2025 | 1589 |  | 1589 | 725.46 | 60.7
May 2025 |  |  | 684 | 4/6L OF BANGALORE - PUNE SECTION OF BYPASS CONNECTING DHARWAD - HUBLI FROM KM. 403.80 TO KM. 433.20 | NHAI | N24001994 | 5-2022 | 3/2023 | Sep-2025 | 9/2025 | 1135.39 |  | 1135.39 | 396.27 | 69.6
May 2025 |  |  | 685 | BALANCE WORK OF CONSTRUCTION OF TWO/FOUR LANE WITH PAVED SHOULDER FROM KM 422.000 TO 523.600 ( CHITR | MoRTH | N24002011 | 12-2021 | 6/2024 | Dec-2024 | 12/2024 | 516.96 |  | 516.96 | 19.93 | 75
May 2025 |  |  | 686 | WIDENING TO TWO LANE WITH PAVED SHOULDERS FROM KM 40.00 TO KM 75.00 (EXISTING CHAINAGES) OF MANGALOR | MoRTH | N24002012 | 3-2023 | 3/2025 | Mar-2025 | 3/2025 | 718.52 |  | 718.52 | 24.81 | 23
May 2025 |  |  | 687 | CONSTRUCTION OF TWO LANE WITH PAVED SHOULDER FROM KM.0 TO KM. 80 ON NH 548B (VIJAYAPURA-SANKESWAR SE | MoRTH | N24002013 | 3-2021 | 2/2022 | Oct-2024 | 10/2024 | 766.64 |  | 766.64 | 13.55 | 75
May 2025 |  |  | 688 | WIDENING TO 2 LANE WITH PAVED SHOULDERS FROM DESIGN KM 103.200 (EXISTING KM 103.200) TO DESIGN KM 11 | MoRTH | N24002186 | 3-2024 | 9/2025 | N.A. | 9/2025 | 166.58 |  | 166.58 | 3.62
May 2025 |  |  | 689 | CONSTRUCTION OF 2 LANE WITH PAVED SHOULDER FROM KM 55.6 TO KM 90.7 (EXISTING CHAINAGES) OF NH-766C ( | MoRTH | N24002187 | 2-2024 | 2/2026 | N.A. | 2/2026 | 313.56 |  | 313.56 | 53.65
May 2025 |  |  | 690 | WIDENING TO 2L+PS FROM KM 71.00 TO 104.00 (EXISTING CHAINAGES) (SARJAPUR TO PATTADKALLU) ON BHANAPUR | MoRTH | N24002188 | 3-2024 | 3/2026 | N.A. | 3/2026 | 445.62 |  | 445.62 | 33.24
May 2025 |  |  | 691 | WIDENING TO TWO LANE WITH PAVED SHOULDERS FROM KM 0.00 (DESIGN CHAINAGE 0.00) TO KM 23.338 (DESIGN C | MoRTH | N24002189 | 9-2024 | 3/2026 | N.A. | 3/2026 | 196.05 |  | 196.05 | 2.34
May 2025 |  | STEEL | 692 | SCREENING PLANT-II, DONIMALAI | NMDC | N12000136 | 9-2023 | 8/2026 | N.A. | 8/2026 | 1043.63 |  | 1043.63 | 181.21 | 13.61
May 2025 |  | URBAN DEVELOPMENT | 693 | BANGALORE METRO RAIL PROJECT PHASE- 2 | BMRCL | N28000058 | 2-2014 | 2/2021 | N.A. | 3/2025 | 26405.14 |  | 26405.14 | 20936.29
May 2025 |  | URBAN DEVELOPMENT | 694 | BANGALORE METRO RAIL PROJECT LIMITED. PHASE. 2A AND 2B | BMRCL | N28000151 | 6-2021 | 6/2026 | N.A. | 6/2026 | 14788.1 |  | 14788.1 | 2424.04
May 2025 |  | CIVIL AVIATION | 695 | CALICUT AIRPORT - DEVELOPMENT OF ADDITIONAL RESA ON EITHER END ON RUNWAY 10-28 AT CALICUT AIRPORT | AAI | N04000111 | 6-2023 | 9/2025 | N.A. | 9/2025 | 484.57 | 323.98 | 323.98 | 74.41 | 18
May 2025 |  | DEPARTMENT OF HIGHER EDUCATION | 696 | C/O PERMANENT CAMPUS OF IIT PALAKKAD PHASE IA AT PUDESSERY VILLAGE,KANJIKODE WEST, DISTRICT PALAKKA | CPWD EDUCATION | N28000140 | 7-2019 | 3/2021 | N.A. | 11/2025 | 753.63 |  | 753.63 | 411.86 | 67
May 2025 |  | PETROLEUM | 697 | REPLACEMENT AND EXTENSION OF JETTY PIPELINES AT KOCHI REFINERY | BPCL | N16000508 | 3-2023 | 3/2026 | N.A. | 3/2026 | 621.87 |  | 621.87 | 168.5 | 81.5
May 2025 |  | PETROLEUM | 698 | SETTING UP POLYPROPYLENE UNIT AT KOCHI REFINERY | BPCL | N16000530 | 12-2023 | 10/2027 | N.A. | 10/2027 | 4460 |  | 4460 | 223.5 | 10.1
May 2025 |  | RAILWAYS | 699 | TRIVANDRUM-KANYAKUMARI DOUBLING | SR | N22000399 | 2-2015 | 3/2024 | N.A. | 12/2027 | 1431.9 |  | 3785.45 | 3184.42 | 42.1
May 2025 |  | RAILWAYS | 700 | ERNAKULAM-KUMBALAM - PATCH DOUBLING (7.71 KM) | SR | N22000619 | 12-2010 | 3/2028 | N.A. | 12/2026 | 600.82 |  | 595.39 | 282.48 | 8
May 2025 |  | RAILWAYS | 701 | KUMBALAM-THURAVUR - PATCH DOUBLING | 15.59 KM | SR | 12-2011 | 3/2027 | N.A. | 12/2026 | 812.85 |  | 802.8 | 280.39 | 7
May 2025 |  | RAILWAYS | 702 | 4-LANNING OF THALSERRY -MAHE BYPASS | NHAI | N24000704 | 9-2017 | 5/2020 | Nov-2023 | 2/2024 | 1124.11 | 1573.18 | 1573.18 | 1525.92 | 100
May 2025 |  | RAILWAYS | 703 | 6-LANING OF KOZHIKODE BYPASS (CALICUT BYPASS) (I.E. VENGALAM JN. TO RAMANATTUKARA JN.) SECTION OF NH | NHAI | N24000784 | 2-2018 | 2/2023 | Dec-2024 | 6/2025 | 1424.77 | 2065.95 | 2065.95 | 901.96 | 95.01
May 2025 |  | RAILWAYS | 704 | WIDENING TO 2 LANES WITH PAVED SHOULDERS FROM KM.87/000 TO 133/720 (NATTUKAL TO THANAU JN. IN PALAKK | MoRTH | N24001369 | 2-2017 | 8/2017 | Mar-2022 | 8/2024 | 294.28 | 296.53 | 296.53 | 286.8 | 98
May 2025 |  | RAILWAYS | 705 | WIDENING TO 2-LANE WITH PAVED SHOULDERS FROM KM 119/017 TO KM 161/300 ON NH 85 (OLD NH 49) | MoRTH | N24001370 | 2-2017 | 9/2017 | Jan-2023 | 8/2024 | 380.76 | 372.87 | 372.87 | 347.04 | 100
May 2025 |  | RAILWAYS | 706 | CONSTRUCTION OF 6 LANE ELEVATED CORRIDOR ALONG WITH DEVELOPMENT OF EXISTING 4 LANE ROAD AT GROUND LE | NHAI | N24001648 | 8-2022 | 1/2026 | N.A. | 1/2026 | 2429.52 |  | 2429.52 | 1088.32 | 59.9
May 2025 |  |  | 707 | SIX LANING OF PARAVOOR(DESIGN KM. 417+000) TO KOTTUKULANGARA(DESIGN KM. 454+500) SECTION OF NEW NH-6 | NHAI | N24001649 | 12-2021 | 2/2025 | Feb-2025 | 1/2026 | 3273.61 |  | 3273.61 | 777.99 | 61.01
May 2025 |  |  | 708 | SIX LANING OF KADAMBATTUKONAM TO KAZHAKKOOTTAM SECTION OF NH-66(OLD NH-47) FROM KM. 517+250 TO KM.54 | NHAI | N24001650 | 12-2021 | 1/2025 | Apr-2026 | 4/2026 | 3635.64 |  | 3635.64 | 324.02 | 38.97
May 2025 |  |  | 709 | SIX LANING OF THURAVOOR (DESIGN KM. 378+612) TO PARAVOOR (DESIGN KM.417+000) SECTION OF NEW NH-66 (O | NHAI | N24001651 | 9-2021 | 9/2024 | Mar-2026 | 9/2024 | 2878.97 |  | 2878.97 | 565.38 | 43.79
May 2025 |  |  | 710 | 6L MINOR BRIDGE (PALOLI PALAM) AT KM. 203.160 and MAJOR BRIDGE (MORAD) AT KM. 204.895 AND ALLIED WOR | NHAI | N24001652 | 3-2020 | 6/2022 | Feb-2024 | 6/2024 | 210.37 | 216.94 | 216.94 | 198.1 | 100
May 2025 |  |  | 711 | SIX LANING FROM KODUNGALLUR TO EDAPALLY SECTION OF NH ?66 (OLD NH-17) FROM DESIGN CHAINAGE 397+750 ( | NHAI | N24001653 | 11-2021 | 4/2025 | N.A. | 4/2025 | 3565.82 |  | 3064.11 | 1997.54 | 61.99
May 2025 |  |  | 712 | SIX LANING OF START OF KOLLAM BYPASS (KM.486+000) KADAMBATTUKONAM (KM.517+250) SECTION OF NEW NH-66 | NHAI | N24001654 | 6-2021 | 3/2025 | Feb-2026 | 2/2026 | 2641.37 |  | 2641.37 | 607.07 | 76.05
May 2025 |  |  | 713 | SIX LANING FROM KAPPIRIKKAD TO THALIKULAM SECTION OF NH ? 66 (OLD NH- 17) FROM DESIGN CH. 335+850 (EX | NHAI | N24001655 | 6-2021 | 2/2025 | N.A. | 11/2025 | 3606 | 3946.56 | 3946.56 | 3120.31 | 71.59
May 2025 |  |  | 714 | SIX LANING FROM THALIKULAM TO KODUNGALLUR SECTION OF NH ? 66 (OLD NH-17) FROM DESIGN CH.369+015 (EX. | NHAI | N24001656 | 6-2021 | 3/2025 | N.A. | 12/2025 | 2595 |  | 4009.57 | 3044.86 | 64.07
May 2025 |  |  | 715 | SIX LANING OF KOTTUKULANGARA (DESIGN KM. 454+500) TO START OF KOLLAM BYPASS (DESIGN KM. 486+000) SEC | NHAI | N24001657 | 6-2021 | 10/2024 | Dec-2025 | 12/2025 | 2842.14 |  | 2842.14 | 477.69 | 70.95
May 2025 |  |  | 716 | SIX LANING OF RAMANATTUKARA JUNCTION TO START OF VALANCHERY BYPASS SECTION OF NH-66 (OLD NH-17) FROM | NHAI | N24001658 | 1-2021 | 7/2024 | Mar-2025 | 3/2025 | 4265.42 |  | 4728.4 | 3474.3 | 99.1
May 2025 |  |  | 717 | SIX LANING FROM START OF VALANCHERY BYPASS TO KAPPIRIKKAD-SECTION OF NH- 66(OLD NH-17) FROM DESIGN CH | NHAI | N24001659 | 2-2021 | 7/2024 | Mar-2025 | 3/2025 | 3375.31 | 3824.07 | 3824.07 | 2351.49 | 98.3
May 2025 |  |  | 718 | SIX LANING OF THALIPARAMBHA- MUZHAPILANGAD SECTION FROM KM 137.900 TO KM. 170.600 OF NH-17 (NEW NH | NHAI | N24001660 | 8-2020 | 2/2024 | Aug-2025 | 3/2026 | 2714.6 | 3557.65 | 2714.6 | 1903.94 | 73
May 2025 |  |  | 719 | 6L OF AZHIYUR-VENGALAM FROM KM. 189.200 TO KM. 230.400 OF NH-66 | NHAI | N24001661 | 10-2020 | 4/2024 | May-2025 | 3/2026 | 3219.47 | 3898.46 | 3896.46 | 2295.21 | 57.9
May 2025 |  |  | 720 | SIX LANING OF KT/KL BORDER (THALAPPDY) TO CHENGALA SECTION OF NH17 (NEW NH-66) FROM CH. 17.200 TO CH | NHAI | N24001662 | 5-2020 | 5/2024 | Nov-2021 | 7/2025 | 1981.07 | 2651.79 | 1981.07 | 1540.46 | 96.4
May 2025 |  |  | 721 | SIX LANING OF NEELESHWARAM TO THALIPARAMBHA SECTION FROM CH. 94+540 (EXISTING KM 96+450) TO CH. 134+ | NHAI | N24001663 | 6-2020 | 4/2024 | Oct-2021 | 3/2026 | 3041.65 | 3867.66 | 3041.65 | 2406.4 | 82.1
May 2025 |  |  | 722 | SIX LANING OF CHENGALA TO NEELESHWARAM SECTION OF NH-17 (NEW NH-66) FROM CH. 56+200 (EXISTING KM 57+ | NHAI | N24001664 | 6-2020 | 4/2024 | Oct-2021 | 3/2026 | 1746.45 | 2538.06 | 1746.45 | 1262.05 | 82
May 2025 |  |  | 723 | WIDENING/DEVELOPMENT OF EXISTING NH- 85 FROM KM 0.000 TO KM 124.636 SECTION TO 2L/@L+PS SECTION IN TH | NHAI | N24002074 | 8-2022 | 6/2025 | N.A. | 6/2025 | 1231.74 |  | 1231.74 | 452.6 | 48.2
May 2025 |  | URBAN DEVELOPMENT | 724 | KOCHI METRO RAIL PROJECT PHASE II FROM JLN STADIUM TO INFOPARK VIA KAKKANAD | KMRCL | N28000158 | 7-2018 | 11/2026 | N.A. | 11/2026 | 1957.05 |  | 1957.05 | 250.63 | 7.4
May 2025 |  | URBAN DEVELOPMENT | 725 | KOCHI METRO RAIL PROJECT PHASE IB SECTION FROM S N JUNCTION TO THRIPUNITHURA | KMRCL | N28000159 | 6-2019 | 9/2023 | N.A. | 9/2023 | 355.7 | 448 | 448.33 | 448.39 | 100
May 2025 | LADAKH | CIVIL AVIATION | 726 | CONSTRUCTION OF TERMINAL BUILDING AND ASSOCIATED WORKS AT LEH AIRPORT | AAI | N04000078 | 7-2018 | 9/2021 | Oct-2025 | 10/2025 | 480.33 | 640 | 640 | 409.08 | 63.67
May 2025 | LADAKH | ROAD TRANSPORT AND HIGHWAYS | 727 | KARGIL-ZANSKR PACKAGE-1 | NHIDCL | N24001343 | 3-2021 | 1/2023 | Dec-2024 | 11/2025 | 384.23 |  | 384.23 | 162.54 | 60.4
May 2025 | LADAKH | ROAD TRANSPORT AND HIGHWAYS | 728 | KARGIL-ZANSKR PACKAGE-2 | NHIDCL | N24001344 | 3-2021 | 1/2023 | Feb-2025 | 11/2025 | 404.89 |  | 404.89 | 244.21 | 65.54
May 2025 | LADAKH | ROAD TRANSPORT AND HIGHWAYS | 729 | KARGIL-ZANSKR PACKAGE-3 | NHIDCL | N24001345 | 8-2020 | 1/2023 | Aug-2025 | 8/2025 | 381.01 |  | 381.01 | 230.28 | 74.72
May 2025 | LADAKH | ROAD TRANSPORT AND HIGHWAYS | 730 | KARGIL-ZANSKR PACKAGE-8 | NHIDCL | N24001348 | 3-2021 | 1/2023 | Aug-2025 | 8/2025 | 398.37 |  | 398.37 | 274.39 | 82.28
May 2025 | LADAKH | ROAD TRANSPORT AND HIGHWAYS | 731 | CONSTRUCTION OF REALIGNMENT BETWEEN PANDRASS- PASHKYUN (TOTAL LENGTH 27.10 KM) ON ROAD ZOZILA- KARGIL | BRO | N24001999 | 11-2021 | 6/2025 | N.A. | 6/2025 | 426.14 |  | 426.14 | 16.27 | 37
May 2025 | LADAKH | CIVIL AVIATION | 732 | UPGRADATION OF JABALPUR AIRPORT | AAI | N04000087 | 6-2016 | 6/2021 | Jul-2024 | 7/2024 | 412.24 |  | 412.24 | 402.81 | 100
May 2025 | LADAKH | CIVIL AVIATION | 733 | DEVELOPMENT OF GWALIOR AIRPORT PHASE 01 | AAI | N04000098 | 10-2021 | 8/2023 | Aug-2024 | 8/2024 | 446.12 | 455 | 455 | 451.55 | 100
May 2025 | LADAKH | CIVIL AVIATION | 734 | KANCHAN OC EXPANSION | SECL | N06000125 | 12-2014 | 3/2021 | Mar-2026 | 3/2026 | 371.04 |  | 371.04 | 137.2 | 47
May 2025 |  |  | 735 | AMADAND OPENCAST EXPANSION PROJECT | SECL | N06000148 | 3-2016 | 3/2021 | Mar-2027 | 3/2027 | 869.44 |  | 869.44 | 272.09 | 75
May 2025 |  |  | 736 | GANDHIGRAM UG MINE | WCL | N06000183 | 8-2019 | 3/2026 | N.A. | 3/2026 | 414.16 |  | 414.16 | 11.75 | 28
May 2025 |  |  | 737 | BLOCK-B EXPANSION OPENCAST PROJECT | NCL | N06000184 | 7-2019 | 3/2023 | N.A. | 3/2027 | 998.71 |  | 998.71 | 438.64 | 42.57
May 2025 |  |  | 738 | NIGAHI EXPANSION OCP (15 TO 25 MTPA) | NCL | N06000196 | 11-2020 | 3/2025 | N.A. | 3/2028 | 1729.68 |  | 1729.68 | 766.06 | 44.29
May 2025 |  |  | 739 | RAMPUR BATURA OC (4.0 MTY) | SECL | N06000233 | 7-2019 | 3/2026 | N.A. | 3/2026 | 1248.93 |  | 1248.93 | 488.6 | 44
May 2025 |  |  | 740 | TAWA III UG MINE | WCL | N06000250 | 12-2021 | 3/2027 | N.A. | 3/2027 | 314.09 |  | 324.25 | 0.56 | 9
May 2025 |  |  | 741 | AMALGAMATED DHANKASA JAMUNIA UG | 1.84 MTY | WCL | 9-2022 | 3/2027 | N.A. | 3/2027 | 399.2 |  | 497.01 | 64.13 | 42
May 2025 |  |  | 742 | VISHNUPURI UG TO OC | WCL | N06000260 | 11-2022 | 3/2029 | N.A. | 3/2029 | 220.62 |  | 227.65 | 0 | 7
May 2025 |  |  | 743 | URDHAN OC | WCL | N06000265 | 1-2023 | 3/2031 | N.A. | 3/2031 | 206.88 |  | 228.42 | 22.12 | 9
May 2025 |  |  | 744 | SHARDA UG | WCL | N06000266 | 9-2023 | 3/2028 | N.A. | 3/2028 | 166.25 |  | 200.16 | 1.69 | 11
May 2025 |  | PETROLEUM | 745 | ETHYLENE CRACKER PROJECT AT BINA REFINERY INCLUDING DOWNSTREAM PETROCHEMICAL PLANTS AND EXPANSION OF | BPCL | N16000518 | 5-2023 | 5/2028 | N.A. | 5/2028 | 43367 |  | 43367 | 1594.9 | 12.2
May 2025 |  | PETROLEUM | 746 | SHAJAPUR 325MW SOLAR PV PROJECT | NTPC | N18000348 | 6-2022 | 3/2024 | Jun-2025 | 6/2025 | 1530.49 |  | 1578.34 | 1210.05 | 90
May 2025 |  | PETROLEUM | 747 | TS FOR EVACUATION POWER RAJASTHAN REZ PH-IV (PART-2:5.5GW) (JAISALMER/BARMER COMPLEX): PART-C | PGCIL | N18000392 | 8-2024 | 8/2026 | N.A. | 8/2026 | 2708 |  | 2708 | 189.9 | 21.7
May 2025 |  |  | 748 | TRANSMISSION SYSTEM FOR EVACUATION OF POWER FROM RAJASTHAN REZ PH-IV [PART-2 5.5GW] [JAISALMER/BARME | PGCIL | N18000399 | 10-2024 | 10/2026 | N.A. | 10/2026 | 3674 |  | 3674 | 234.57 | 10.3
May 2025 |  | RAILWAYS | 749 | RAMGANJMUNDI-BHOPAL (NL),WCR | WCR | 220100314 | 4-2001 | 12/2025 | Dec-2025 | 6/2026 | 3032 | 3032.46 | 5125.16 | 3423.9 | 69
May 2025 |  | RAILWAYS | 750 | RATLAM-MHOW-KHANDWA-AKOLA (GC) | WR | N22000120 | 4-2008 | 2/2027 | Feb-2027 | 2/2027 | 5677.88 | 5677.8 | 6203.51 | 4284.8 | 80
May 2025 |  | RAILWAYS | 751 | KATNI - SINGRAULI DOUBLING PROJECT | WCR | N22000351 | 12-2015 | 12/2026 | Dec-2027 | 12/2027 | 2445.29 | 2445.3 | 4353.5 | 3099.24 | 91
May 2025 |  | RAILWAYS | 752 | KATNI GRADE SEPARATOR/BYE PASS | WCR | N22000416 | 8-2016 | 9/2024 | Jun-2025 | 9/2024 | 1247.64 | 1247.64 | 2300 | 1427.58 | 89
May 2025 |  | RAILWAYS | 753 | ANUPPUR-KATNI | SECR | N22000485 | 4-2015 | 12/2021 | Dec-2023 | 3/2025 | 1860.94 | 1680 | 2311.02 | 1929.51 | 100
May 2025 |  | RAILWAYS | 754 | NIMACH BADI SADRI NEW LINE PROJECT | WR | N22000503 | 4-2017 | 3/2022 | N.A. | 3/2026 | 495.18 |  | 495.18 | 289.65 | 45
May 2025 |  | RAILWAYS | 755 | NIMACH-RATLAM (133 KM) | WR | N22000536 | 10-2021 | 10/2027 | Dec-2025 | 12/2025 | 1095.88 | 1095.88 | 1095.88 | 1048.6 | 72
May 2025 |  | RAILWAYS | 756 | SATNA - REWA (50 KM) | WCR | N22000554 | 11-2015 | 3/2026 | N.A. | 3/2026 | 500 | 40 | 500 | 1.41 | 80
May 2025 |  | RAILWAYS | 757 | INDORE BUDNI (INDORE JABALPUR) | RVNL | N22000601 | 9-2018 | 9/2030 | N.A. | 9/2030 | 7474.01 |  | 7393.75 | 1004.86
May 2025 |  | RAILWAYS | 758 | UMARIYA TO SHAHDOL SECTION OF NH-78 IN MADYA PRADESH KM 68/4 TO 142/200 | MoRTH | N24000513 | 3-2015 | 8/2017 | Dec-2023 | 6/2025 | 511.83 |  | 511.83 | 478.84 | 93.06
May 2025 |  | RAILWAYS | 759 | 4LBERKHEDI TO GODPEHRA NH-44 | NHAI | N24001614 | 2-2022 | 11/2024 | N.A. | 12/2025 | 524.84 |  | 524.84 | 2434.64 | 60
May 2025 |  | RAILWAYS | 760 | 4L OF SAGAR - MOHARI FROM KM.8 TO KM.50 (PKG-I) | NHAI | N24001615 | 3-2021 | 4/2024 | Jun-2025 | 6/2025 | 790.78 |  | 790.78 | 2139.45 | 77.02
May 2025 |  |  | 761 | KATNI BYPASS FROM KM. 359.50 TO KM. 378.50 | NHAI | N24001618 | 9-2019 | 9/2022 | N.A. | 2/2025 | 194.4 | 235 | 235 | 208.32 | 98.84
May 2025 |  |  | 762 | 4L OF CHANDESARA TO KHEDAKHAJURIYA FROM KM. 0.000 TO (-) 750 AND KM 0.000 TO KM 41.400 OF NH-752D | NHAI | N24001759 | 1-2020 | 6/2024 | Jun-2025 | 6/2025 | 909.84 |  | 909.84 | 502.49 | 99
May 2025 |  |  | 763 | INDORE - HARDA (PKG-III) [NANASA TO PIDGAON SECTION FROM KM 95.000 TO KM 142.445] | NHAI | N24001762 | 10-2021 | 1/2024 | Dec-2025 | 12/2025 | 1146.22 |  | 1146.22 | 662.3 | 91.31
May 2025 |  |  | 764 | INDORE - HARDA (PKG-I) [INDORE TO RAGHAV GARH FROM KM. 0.25 TO KM. 26.903] | NHAI | N24001766 | 1-2022 | 10/2024 | N.A. | 12/2025 | 1011.29 |  | 1011.29 | 284.8 | 70.02
May 2025 |  |  | 765 | 4L OF INDORE - BOREGAON (PKG-III) [BALWARA TO DHANGAON] FROM KM. 42.260 TO KM. 82.660 OF NH347BG AND | NHAI | N24001767 | 1-2021 | 4/2024 | N.A. | 12/2025 | 1001.69 |  | 1001.69 | 517.31 | 82.11
May 2025 |  |  | 766 | 4L OF OBEDULLGANJ - BUDNI SECTION FROM KM. 8.400 TO KM. 20.700 IN RATANPANI WILDLIFE AREA OF NH - 69 | NHAI | N24001770 | 2-2022 | 3/2024 | Mar-2025 | 5/2025 | 417.51 |  | 417.51 | 312.94 | 100
May 2025 |  |  | 767 | 2- LANE WITH PAVED SHOULDERS OF HINOTIYA TO MEHULWA FROM DESIGN KM 27+000 9OF EXISTING SH-19 KM 26+5 | NHAI | N24001921 | 8-2021 | 9/2025 | N.A. | 9/2025 | 581.65 | 592.03 | 581.65 | 125.56 | 43.79
May 2025 |  |  | 768 | CONSTRUCTION OF MIHONA BYPASS, LAHAR BYPASS, DABOH BYPASS and BHANDER BYPASS (TOTAL LENGTH 20.60 KM) | MoRTH | N24001962 | 3-2022 | 12/2024 | N.A. | 3/2025 | 179.19 |  | 179.19 | 47.91 | 96
May 2025 |  |  | 769 | UPGRADATION OF NASRULLAGANI-REHTI- BUDHNI SCCTION TO 2-LANE WITH PAVED SHOULDER FROM KM 0+150 TO KM | MoRTH | N24001963 | 12-2021 | 10/2024 | N.A. | 9/2025 | 305.12 |  | 305.12 | 71.47 | 34.46
May 2025 |  |  | 770 | UPGRADATION and WIDENING OF JHARKHEDA- BERASIA - DHOLKHEDI FROM DESIGN KM 0+000 TO KM 87+900 (DESIGN | MoRTH | N24001964 | 3-2022 | 5/2025 | N.A. | 5/2025 | 365.21 |  | 365.21 | 112.27 | 64
May 2025 |  |  | 771 | REHABILITATION AND UPGRADATION OF KURWAI?MUNGAOLI?CHANDERI ROAD SECTION OF NH-346, FROM DESIGN CHAIN | MoRTH | N24001965 | 3-2022 | 2/2025 | N.A. | 12/2025 | 386.49 |  | 386.49 | 77.42 | 48.77
May 2025 |  |  | 772 | BALANCE WORK FOR REHABILITATION AND UP-GRADATION OF SIDHI-SINGRAULI FROM KM 82.400 TO KM 187.993 SEC | MoRTH | N24001966 | 12-2020 | 4/2023 | N.A. | 6/2025 | 529.44 |  | 529.44 | 378.4 | 62
May 2025 |  |  | 773 | 4L GREENFIELD RUDHI TO DESHGAON (PKG V OF BETUL-KHANDWA/DESHGAON) - N/04015/06003/MP | NHAI | N24001967 | 11-2018 | 10/2025 | N.A. | 10/2025 | 521.21 |  | 521.21 | 98.23 | 39.8
May 2025 |  |  | 774 | REHABILITATION AND UPGRADATION TO 2- LANE WITH PAVED SHOULDER CONFIGURATION OF JIRAPUR-SUSNER-MP- RJ B | MoRTH | N24002018 | 1-2022 | 3/2025 | N.A. | 3/2025 | 239.72 | 232.22 | 232.22 | 73.4 | 100
May 2025 |  |  | 775 | UPGRADATION OF DINDORI-SAGARTOLA- KABICHABUTRA (MP-CG BORDER) SECTION OF NH -45 FROM KM 0+00(DESIGN) | MoRTH | N24002019 | 1-2022 | 9/2025 | N.A. | 9/2025 | 329.14 | 319.09 | 319.09 | 52.7 | 50.12
May 2025 |  |  | 776 | CONSTRUCTION OF KAITHI-PADARIA KALA BYPASS, PATNA-TAMOLI BYPASS, JASO BYPASS , NAGOD BYPASS (TOTAL L | MoRTH | N24002020 | 3-2022 | 10/2025 | N.A. | 10/2025 | 158.36 | 158 | 158.36 | 22.68 | 30
May 2025 |  |  | 777 | BALANCE WORK OF 4L OF NAURADEHI SANCTUARY DE-SCOPED STRETCH OF HIRAN RIVER TO SINDOOR RIVER FROM KM. | NHAI | N24002067 | 1-2021 | 7/2023 | N.A. | 4/2025 | 178.18 |  | 178.18 | 161.64 | 94.65
May 2025 |  |  | 778 | CONSTRUCTION OF 4-LANE FROM BARELA TO MANEGAON SECTION OF NH-30 FROM DESIGN CH. 2.900 TO DESIGN CH. | NHAI | N24002068 | 12-2022 | 3/2025 | N.A. | 12/2025 | 652.33 |  | 652.33 | 334.34 | 73.16
May 2025 |  |  | 779 | CONSTRUCTION OF ADDITIONAL 3 LANE WITH PAVED SHOULDER (DESIGN LENGTH 8.87 KM) AS REALIGNMENT OF BAKA | NHAI | N24002069 | 7-2022 | 12/2024 | N.A. | 12/2024 | 209.29 |  | 209.29 | 140.22 | 100
May 2025 |  |  | 780 | INDORE - EDLABAD (PKG-II) [TEJAJINAGAR TO BALWARA] | NHAI | N24002070 | 1-2022 | 1/2025 | N.A. | 1/2026 | 1162.8 |  | 1162.8 | 493.76 | 80
May 2025 |  |  | 781 | CONSTRUCTION OF (I) 4-LANE HIGHWAY FROM VIDISHA TO HINOTIYA FROM KM. 0.000 TO KM. 27.000 (LENGTH=27 | NHAI | N24002077 | 9-2022 | 12/2025 | N.A. | 12/2025 | 1000.63 |  | 1000.63 | 210.15 | 50.72
May 2025 |  |  | 782 | FOUR LANING OF RAGHOGARH (DESIGN CH.29.300/EXISTING CH. 29.555) TO NANASA (DESIGN CH.92.971/EXISTING | NHAI | N24002166 | 3-2024 | 3/2026 | Mar-2026 | 3/2026 | 799.2 |  | 799.2 | 306.27 | 35.04
May 2025 |  |  | 783 | BALANCE WORKS OF 4 LANE DIVIDED CARRIAGEWAY OF MISSING LINK SECTION OF NH-39 (REWA BYPASS) FROM JUNC | NHAI | N24002200 | 4-2024 | 4/2026 | N.A. | 4/2026 | 355.36 |  | 355.36 | 39.06 | 34.4
May 2025 |  | SOCIAL JUSTICE | 784 | CENTRE FOR DISABILITY SPORTS | CPWD | N38000001 | 2-2019 | 3/2024 | N.A. | 3/2024 | 170.99 |  | 170.99 | 73.8 | 74
May 2025 |  | URBAN DEVELOPMENT | 785 | BHOPAL METRO RAIL | MPMRCL | N28000124 | 11-2018 | 2/2023 | Jun-2028 | 6/2028 | 6941.4 |  | 6941.4 | 2970.09 | 40.9
May 2025 |  | URBAN DEVELOPMENT | 786 | INDORE METRO RAIL | MPMRCL | N28000125 | 11-2018 | 2/2023 | Dec-2028 | 12/2028 | 7500.8 |  | 7500.8 | 3724.27 | 52.99
May 2025 |  | URBAN DEVELOPMENT | 787 | CONSTRUCTION OF NEW INTEGRATED TERMINAL BUILDING, RECONSTRUCTION OF OLD TERMINAL BUILDING, MODIFICAT | AAI | N04000079 | 3-2017 | 4/2021 | Dec-2023 | 12/2023 | 475.39 |  | 520 | 532.99 | 100
May 2025 |  |  | 788 | EXTENSION OF RUNWAY WITH BLAST PAD, RESA, TAXIWAY, APRON, GSE AREA, ISOLATION BAY, NEW DOMESTIC TERM | AAI | N04000096 | 6-2017 | 12/2020 | Apr-2024 | 4/2024 | 255.68 | 270 | 270 | 267.86 | 100
May 2025 |  |  | 789 | AMALGAMATED YEKONA-I YEKONA-II | WCL | N06000132 | 8-2015 | 3/2025 | N.A. | 3/2025 | 727.28 |  | 727.28 | 530.02 | 86
May 2025 |  |  | 790 | UKNI DEEP OC | WCL | N06000179 | 1-2019 | 3/2021 | Mar-2025 | 3/2025 | 237.06 |  | 318.14 | 163.86 | 91
May 2025 |  |  | 791 | GHONSA EXPANSION DEEP OC | WCL | N06000205 | 3-2021 | 3/2028 | N.A. | 3/2029 | 184.71 |  | 241.72 | 9.25 | 6
May 2025 |  |  | 792 | SASTI EXPANSION OC | WCL | N06000206 | 8-2020 | 3/2026 | N.A. | 3/2026 | 319.04 |  | 371.59 | 68.64 | 24
May 2025 |  |  | 793 | DHUPTALA OC(SASTI UG TO OC) | WCL | N06000209 | 10-2021 | 3/2028 | N.A. | 3/2028 | 711 |  | 720.87 | 159.15 | 33
May 2025 |  |  | 794 | ADASA UG TO OC (1.50 MTY) | WCL | N06000219 | 11-2018 | 3/2024 | Mar-2025 | 3/2025 | 316 |  | 333.43 | 208.2 | 78
May 2025 |  |  | 795 | DINESH (MAKARDHOKDA-III) OC (8.0 MTY) | WCL | N06000222 | 2-2020 | 3/2027 | N.A. | 3/2027 | 822.88 |  | 1184.33 | 578.89 | 48
May 2025 |  |  | 796 | AMALGAMATED INDER-KAMPTEE DEEP OC | 3.20 MTY | WCL | 9-2018 | 3/2024 | Mar-2025 | 3/2025 | 235.9 |  | 313.34 | 116.46 | 87
May 2025 |  |  | 797 | SAONER UG MINE I EXPANSION | WCL | N06000251 | 1-2022 | 3/2028 | N.A. | 3/2028 | 228.64 |  | 253.51 | 118.34 | 27
May 2025 |  |  | 798 | SINGHORI DEEP OC | WCL | N06000252 | 5-2022 | 3/2029 | N.A. | 3/2029 | 335.75 |  | 421.84 | 22.01 | 16
May 2025 |  |  | 799 | MAKARDHOKDA I EXPANSION OC | WCL | N06000253 | 6-2022 | 3/2026 | N.A. | 3/2026 | 361.87 |  | 497.06 | 33.9 | 12
May 2025 |  |  | 800 | BHATADI EXPANSION OC | WCL | N06000254 | 5-2022 | 3/2028 | N.A. | 3/2028 | 580.6 |  | 729.86 | 61.33 | 17
May 2025 |  |  | 801 | NEW MAJARI UG TO OC (3.0 MTY) | WCL | N06000255 | 9-2022 | 3/2027 | N.A. | 3/2027 | 402.27 |  | 496.38 | 47.99 | 27
May 2025 |  |  | 802 | BHANEGAON OC (1.15MTY) | WCL | N06000256 | 9-2022 | 3/2028 | N.A. | 3/2028 | 405.2 |  | 494.6 | 10.21 | 7
May 2025 |  |  | 803 | GOKUL EXPANSION OC | WCL | N06000264 | 4-2021 | 3/2026 | N.A. | 3/2026 | 309.58 |  | 456.95 | 3.65 | 7
May 2025 |  |  | 804 | KOLGAON EXPANSION (DEEP) OC | WCL | N06000267 | 9-2023 | 3/2027 | N.A. | 3/2027 | 198.71 |  | 206.19 | 0.55 | 5
May 2025 |  |  | 805 | AMALGAMATED GAURI PAUNI EXPANSION OC | WCL | N06000271 | 3-2024 | 3/2030 | N.A. | 3/2030 | 1225.21 |  | 1428.25 | 52.83 | 17
May 2025 |  |  | 806 | GAURI CENTRAL OCM | WCL | N06000278 | 6-2024 | 3/2030 | N.A. | 3/2030 | 973.07 |  | 1015.07 | 0
May 2025 |  |  | 807 | BALLARPUR NORTHWEST OC MINE | WCL | N06000282 | 12-2022 | 3/2029 | N.A. | 3/2029 | 360.18 |  | 360.18 | 0
May 2025 |  |  | 808 | NORTHERN EXTENSION OF MUNGOLI NIRGUDA DEEP OC | WCL | N06000283 | 6-2024 | 3/2029 | N.A. | 3/2029 | 1024.91 |  | 1184.44 | 0
May 2025 |  |  | 809 | AMALGAMATED GONDEGAON - GHATROHAN EXPANSION OCM | WCL | N06000284 | 9-2024 | 3/2029 | N.A. | 3/2029 | 668.54 |  | 871.59 | 0
May 2025 |  | DEPARTMENT OF HIGHER EDUCATION | 810 | CONSTRUCTION OF IITB RESEARCH PARK AT IIT BOMBAY, POWAI, MUMBAI | CPWD EDUCATION | N28000117 | 1-2018 | 7/2020 | Nov-2023 | 2/2024 | 223.37 | 275 | 230 | 141.16 | 100
May 2025 |  | HEALTH AND FAMILY WELFARE | 811 | 500 BEDDED HOSPITAL INCLUDING 50 SUPERSPECIALITY BEDS FOR ESIC AT PUNE | CPWD | N21000033 | 7-2022 | 9/2025 | N.A. | 9/2025 | 429.25 |  | 429.25 | 99.08
May 2025 |  | HEALTH AND FAMILY WELFARE | 812 | LIFE EXTENSION OF WALL PLATFORMS OF MUMBAI HIGH AND HEERA FIELDS | ONGC | N16000213 | 12-2015 | 4/2018 | Dec-2023 | 6/2025 | 3190.69 | 3375.9 | 3375.9 | 3023.97 | 89
May 2025 |  | HEALTH AND FAMILY WELFARE | 813 | SETTING UP 500KTPA PROPANE DEHYDROGENATION INTEGRATED WITH POLYPROPYLENE UNIT ALONG WITH OFFSITE AND | GAIL | N16000430 | 5-2019 | 4/2025 | Oct-2025 | 10/2025 | 8797 | 11256 | 11256 | 6367.78 | 83.78
May 2025 |  | HEALTH AND FAMILY WELFARE | 814 | DEBOTTLENECKING AND AUGMENTATION OF CRYOGENIC FACILITIES AT URAN LPG IMPORT TERMINAL | BPCL | N16000442 | 4-2021 | 6/2024 | N.A. | 4/2025 | 1164.69 |  | 1164.69 | 873.03 | 82.2
May 2025 |  |  | 815 | EXPANSION OF CRYOGENICS GROUP BY SETTING UP NEW MANUFACTURING FACILITY | IOCL | N16000446 | 9-2021 | 10/2023 | Jun-2025 | 6/2025 | 378 |  | 378 | 142.31 | 90.6
May 2025 |  |  | 816 | CONSTRUCTION OF LUBE OIL BLENDING AND FILLING PLANT AT RASAYANI | BPCL | N16000452 | 5-2022 | 3/2024 | N.A. | 9/2024 | 423.39 |  | 423.39 | 253.13 | 75.5
May 2025 |  |  | 817 | ATF PIPELINE FROM JAWAHARLAL NEHRU PORT TRUST (JNPT) TO NAVI MUMBAI INTERNATIONAL AIRPORT (NMIA) | IOCL | N16000456 | 9-2022 | 8/2025 | N.A. | 3/2026 | 165 |  | 165 | 78.6 | 65.93
May 2025 |  |  | 818 | DAMAN UPSIDE DEVELOPMENT PROJECT (DUDP) IN TAPTI DAMAN BLOCK | ONGC | N16000470 | 6-2022 | 10/2025 | N.A. | 2/2026 | 4144.41 | 6406.9 | 6406.9 | 3203.26 | 80.5
May 2025 |  |  | 819 | CGD PROJECT AT BEED, JALGAON AND JALNA DISTRICTS | IOCL | N16000487 | 3-2022 | 3/2030 | N.A. | 9/2031 | 865 |  | 865 | 63.81 | 2.8
May 2025 |  |  | 820 | ANDHERI RESIDENTIAL TOWERS MUMBAI | IOCL | N16000503 | 6-2017 | 5/2025 | Jun-2026 | 6/2026 | 281.35 | 389.67 | 389.67 | 216.88 | 50.5
May 2025 |  |  | 821 | CONSTRUCTION OF ADDITIONAL TANKAGES AND ALLIED FACILITIES AT JNPT TERMINAL | IOCL | N16000504 | 4-2022 | 10/2024 | Aug-2026 | 8/2026 | 341.43 | 436.14 | 436.14 | 239.13 | 47.52
May 2025 |  |  | 822 | INSTALLATION OF INDEPENDENT DE- AROMATIZED SOLVENTS PRODUCTION FACILITIES AT MUMBAI REFINERY | BPCL | N16000507 | 3-2023 | 7/2025 | N.A. | 7/2025 | 405 |  | 405 | 181 | 78.2
May 2025 |  |  | 823 | PART REPLACEMENT PIPELINE PROJECT | PRPP | ONGC | 11-2022 | 5/2024 | Dec-2024 | 11/2025 | 1219.48 |  | 1145.1 | 678.98 | 87
May 2025 |  |  | 824 | POL AND LOBS INSTALLATIONS WITH RECEIPT PIPELINES AT RASAYANI | BPCL | N16000519 | 5-2023 | 5/2026 | N.A. | 5/2026 | 2585 |  | 2585 | 463.12 | 53.8
May 2025 |  |  | 825 | MHN TCPP PGC BGC PROJECT (MTPBP) | ONGC | N16000526 | 2-2024 | 5/2026 | N.A. | 5/2026 | 2329.45 |  | 2354.23 | 523 | 40.5
May 2025 |  |  | 826 | PRP-VIII GROUP B (NH AND BS ASSET) | ONGC | N16000533 | 6-2024 | 5/2026 | N.A. | 2/2026 | 2379.84 |  | 2379.84 | 1362.62 | 57.8
May 2025 |  |  | 827 | HP TDAE UNIT IN MUMBAI REFINERY | HPCL | N16000534 | 6-2024 | 4/2026 | N.A. | 4/2026 | 240 |  | 240 | 26.53 | 26.3
May 2025 |  |  | 828 | INTEGRATED DEVELOPMENT OF 4 CONTRACT AREAS UNDER DSF2 | ONGC | N16000537 | 5-2023 | 4/2027 | N.A. | 4/2027 | 6183.79 |  | 6183.79 | 0 | 12.6
May 2025 |  |  | 829 | LUBE MODERNIZATION AND BOTTOM UPGRADATION PROJECT | HPCL | N16000540 | 12-2024 | 3/2028 | N.A. | 3/2028 | 4679 |  | 4679 | 171.65 | 4.2
May 2025 |  | POWER | 830 | BIKANER SOLAR POWER PROJECT | SJVN | N18000335 | 4-2022 | 5/2024 | N.A. | 9/2025 | 5491.89 | 532 | 5491.89 | 4229.4 | 76
May 2025 |  | POWER | 831 | TS FOR EVACUATION OF 7GW RE INJECTION AT KHAVDA PS UNDER PHASE- IV PART E4 | PGCIL | N18000377 | 11-2023 | 7/2025 | N.A. | 9/2025 | 224 |  | 224 | 2.64 | 6
May 2025 |  | POWER | 832 | AHMEDNAGAR-PARLI VAIJNATH(NL) CR | CR | 220100181 | 2-1997 | 3/2026 | N.A. | 1/2026 | 2539 |  | 4957.27 | 4858.62 | 97
May 2025 |  | POWER | 833 | MUMBAI URBAN TRANSPORT PROJECT PHASE-II | MRTP | N22000092 | 4-2008 | 3/2014 | N.A. | 3/2014 | 8087.11 |  | 918.53 | 7110.54 | 77.3
May 2025 |  | POWER | 834 | WARDHA-NANDED MAHARASHTRA | CR | N22000231 | 4-2008 | 3/2027 | N.A. | 1/2026 | 3445.48 |  | 3445.34 | 3121.26 | 47
May 2025 |  | POWER | 835 | KALYAN-KASARA 3RD LINE | CR | N22000233 | 4-2011 | 12/2025 | N.A. | 12/2026 | 792.89 |  | 1395.79 | 876.77 | 50
May 2025 |  | POWER | 836 | WARDHA-SEWAGRAM NGP 3RD LINE | CR | N22000250 | 4-2012 | 12/2025 | N.A. | 2/2026 | 540.02 |  | 540.02 | 733.95 | 80
May 2025 |  | POWER | 837 | WARDHA-BALHARSHAH - 3RD LINE (132 KM) | CR | N22000356 | 2-2015 | 12/2025 | N.A. | 3/2026 | 1384.72 |  | 1384.72 | 1580.25 | 67
May 2025 |  | POWER | 838 | ITARSI-NAGPUR (BAL.) - 3RD LINE (267 KM) | CR | N22000358 | 2-2015 | 3/2027 | N.A. | 3/2027 | 2449.91 |  | 2449.91 | 1732.39 | 50
May 2025 |  |  | 839 | PUNE-MIRAJ-LONDA (467 KM) | CR | N22000359 | 2-2015 | 2/2025 | N.A. | 5/2025 | 3627.47 | 3627 | 7037.24 | 4624.86 | 84
May 2025 |  |  | 840 | DAUND - MANMAD (236 KM) | CR | N22000360 | 2-2016 | 12/2025 | N.A. | 1/2026 | 2081.27 |  | 2081.27 | 2723.05 | 88
May 2025 |  |  | 841 | MANMAD - JALGAON - 3RD LINE (160 KM) | CR | N22000361 | 2-2016 | 12/2024 | N.A. | 3/2026 | 1035.16 |  | 1558.75 | 1675.57 | 80
May 2025 |  |  | 842 | WARDHA - NAGPUR - 4TH LINE (76 KM) | CR | N22000362 | 2-2016 | 12/2025 | N.A. | 2/2026 | 638 |  | 637.95 | 962.97 | 80
May 2025 |  |  | 843 | RAJNANDGAON - NAGPUR - 3RD LINE | SECR | SECR | 9-2016 | 12/2024 | N.A. | 12/2026 | 3544.92 |  | 3544.25 | 3041.12 | 95
May 2025 |  |  | 844 | MUMBAI CENTRAL VIRAR VADODARA AHMEDABAAD TRAIN PROTECTION SYSTEM 500 RKM | WR | N22000434 | 3-2010 | 10/2024 | N.A. | 3/2024 | 311 |  | 311.36 | 0
May 2025 |  |  | 845 | WADSA-GADHCHIROLI NEW LINE (52.36 KM) | SECR | N22000480 | 6-2018 | 3/2027 | N.A. | 12/2026 | 1886.05 |  | 1880.61 | 778.67 | 25
May 2025 |  |  | 846 | PACHORA-JAMNER WITH EXTENSION UPTO MALKAPUR NG TO BG | CR | N22000511 | 8-2022 | 8/2027 | N.A. | 3/2029 | 955 |  | 2089.25 | 117.54
May 2025 |  |  | 847 | SOLAPUR-TULJAPUR-OSMANABAD | UMBRELLA WORK | CR | 1-2019 | 3/2028 | N.A. | 12/2027 | 904.92 |  | 2933.01 | 1139.92 | 10
May 2025 |  |  | 848 | DHULE (BORVIHIR)-NARDANA (UMBRELLA WORK) | CR | N22000514 | 1-2019 | 12/2026 | N.A. | 3/2028 | 492.76 |  | 1158.99 | 198.74 | 5
May 2025 |  |  | 849 | KALYAN-MURBAD VIA ULHASNAGAR | UMBRELLA WORK | CR | 2-2023 | 3/2027 | N.A. | 3/2027 | 836.12 |  | 836.12 | 9.29
May 2025 |  |  | 850 | BARAMATI - LONAND | CR | N22000615 | 2-1999 | 3/2027 | N.A. | 3/2027 | 736.44 |  | 1843.9 | 692.52 | 50
May 2025 |  |  | 851 | MUMBAI URBAN TRANSPORT PROJECT IIIA | MRVC | N22000627 | 4-2019 | 12/2027 | N.A. | 12/2027 | 33690 |  | 33690 | 812.06
May 2025 |  |  | 852 | NAGPUR- NAGBHIR RAILWAY LINE GAUGE CONVERSION PROJECT | MRIDC | N22000629 | 10-2019 | 6/2024 | N.A. | 10/2025 | 1400 |  | 2383 | 1774.9 | 86
May 2025 |  |  | 853 | REHABILITATION AND UPGRADATION OF END OF AHMEDNAGAR BYPASS TO KHARWANDI KASAR SECTION OF NH-222 FROM | MoRTH | N24000332 | 1-2015 | (N.A.) | {} |  | 225.81 |  | 225.81 | 167.96 | 96
May 2025 |  |  | 854 | CONSTRUCTION OF FLYOVER AT KM.544.650 INCLUDING ROB ,SERVICE ROADS ,FOOTPATH FOR RCC DRAINS ON URBAN | NHAI | N24000442 | 12-2015 | 3/2019 | Nov-2023 | 7/2025 | 649.5 |  | 649.5 | 623.65 | 93.43
May 2025 |  |  | 855 | NAGPUR RING ROAD PACKAGE-2 | NHAI | N24000560 | 3-2016 | 7/2019 | Mar-2024 | 5/2025 | 591.66 |  | 591.66 | 632.92 | 99.99
May 2025 |  |  | 856 | 4-LANNING OF NH17 AND NEW NO. NH66 FROM KM 161/600 TO 205/400 UNDER HYBRID ANNUITY MODE | MoRTH | N24000584 | 3-2016 | (N.A.) | {12/2023} |  | 1142.62 | 1907.03 | 1142.62 | 1056.08 | 95.17
May 2025 |  |  | 857 | 4-LANNING OF NH17 AND NEW NO. NH66 FROM KM 241/300 TO 281/300 UNDER HYBRID ANNUITY MODE | MoRTH | N24000585 | 3-2016 | (N.A.) | {} |  | 1101.58 |  | 1101.58 | 608.53
May 2025 |  |  | 858 | 4-LANNING OF BODHRE-DHULE SECTION(KM 390.000 TO 452.800) | NHAI | N24000656 | 3-2017 | 3/2020 | Jul-2022 | 12/2025 | 744.64 |  | 1007 | 467.65 | 95.2
May 2025 |  |  | 859 | 4-LANNING OF WARANGA-MAHAGAON SECTION(KM 253.7000 TO 320.580) | NHAI | N24000659 | 3-2017 | 3/2017 | May-2021 | 5/2025 | 1059.73 | 1071 | 1071 | 928.19 | 97.25
May 2025 |  |  | 860 | CONSTRUCTION OF 8 LANING OF EXISTING 4 LANE VADAPE TO THANE FROM KM 539.202 TO KM 563.000 SECTION OF | NHAI | N24000851 | 3-2018 | 7/2021 | N.A. | 12/2025 | 1162.92 | 1182.87 | 1182.87 | 412.38 | 59
May 2025 |  |  | 861 | SARSAM TO KOTHARI | MoRTH | N24001002 | 2-2016 | 7/2019 | N.A. | 12/2023 | 545.64 |  | 545.64 | 232.64 | 93.68
May 2025 |  |  | 862 | AKOLA TO AKOT | MoRTH | N24001003 | 1-2017 | 6/2019 | N.A. | 12/2023 | 313.95 |  | 313.95 | 270.26 | 99
May 2025 |  |  | 863 | DIGRAS DARWAH KARANJA | MoRTH | N24001013 | 1-2017 | 6/2019 | N.A. | 12/2023 | 391.06 | 391 | 391.06 | 287.6 | 92.76
May 2025 |  |  | 864 | DAHEGAON TO KUHI | MoRTH | N24001017 | 1-2017 | 6/2019 | N.A. | 12/2023 | 228.89 | 229 | 228.89 | 154.82 | 99
May 2025 |  |  | 865 | BHANDARA TO GHOTITOK | MoRTH | N24001018 | 1-2017 | 6/2019 | N.A. | 6/2019 | 392.83 | 393 | 392.83 | 274.75 | 100
May 2025 |  |  | 866 | AMDI TO SAONER | MoRTH | N24001021 | 1-2017 | 6/2019 | N.A. | 12/2023 | 396.91 | 397 | 396.91 | 289.79 | 98.69
May 2025 |  |  | 867 | WADI TO ASOLA | MoRTH | N24001022 | 1-2017 | 9/2019 | N.A. | 12/2023 | 363.82 | 364 | 363.82 | 154.65 | 93.15
May 2025 |  |  | 868 | RALEGAON TO RAMTIRTH | MoRTH | N24001046 | 1-2017 | 7/2019 | N.A. | 8/2023 | 210.81 |  | 210.81 | 210.81 | 96.5
May 2025 |  |  | 869 | VITA TO NAGAJ | MoRTH | N24001050 | 3-2018 | 12/2019 | N.A. | 12/2023 | 304.58 | 305 | 304.58 | 154.68 | 68.39
May 2025 |  |  | 870 | KARAD PATAN CHIPLUN GUHAGAR | MoRTH | N24001057 | 2-2017 | 6/2019 | N.A. | 10/2023 | 407.19 | 407 | 407.19 | 323.02 | 90
May 2025 |  |  | 871 | KARWANDI TO RAJURI | MoRTH | N24001058 | 3-2018 | 12/2019 | N.A. | 3/2024 | 276.95 | 277 | 276.95 | 160.94 | 92.06
May 2025 |  |  | 872 | PALPHATA TO PHULAMBARI | MoRTH | N24001060 | 3-2018 | 12/2019 | N.A. | 12/2023 | 227.19 | 227 | 227.19 | 141.92 | 95
May 2025 |  |  | 873 | NANDED TO JALKOT | MoRTH | N24001069 | 12-2017 | 9/2019 | N.A. | 9/2019 | 456.93 | 457 | 456.93 | 278.22 | 95
May 2025 |  |  | 874 | PUNE TO MALE VILLAGE | MoRTH | N24001078 | 3-2018 | 12/2019 | N.A. | 12/2023 | 228.31 |  | 228.31 | 100.97 | 93.83
May 2025 |  |  | 875 | ARDHAPUR TO HIMAYATNAGAR | MoRTH | N24001079 | 12-2017 | 6/2020 | N.A. | 12/2023 | 426.06 | 426 | 426.06 | 271.4 | 96.25
May 2025 |  |  | 876 | MALE VILLAGE TO PUNE RAIGARH DISTRICT BORDER | MoRTH | N24001080 | 3-2018 | 12/2019 | N.A. | 10/2023 | 256.15 |  | 256.15 | 126.62 | 98
May 2025 |  |  | 877 | PUNE RAIGARH DISTRICT BORDER TO MANGAON | MoRTH | N24001082 | 3-2018 | 12/2019 | N.A. | 12/2023 | 223.46 |  | 223.46 | 123.46 | 100
May 2025 |  |  | 878 | KOLDE TO KHETIYA | MoRTH | N24001090 | 1-2017 | 7/2019 | N.A. | 12/2023 | 509.18 |  | 509.18 | 283.13 | 94.81
May 2025 |  |  | 879 | SATARA TO MHASWAD | MoRTH | N24001092 | 1-2017 | 7/2019 | N.A. | 12/2023 | 653.46 |  | 653.46 | 369.62
May 2025 |  |  | 880 | MHASWAD TO TEMBHURNI | MoRTH | N24001099 | 1-2017 | 7/2019 | N.A. | 12/2023 | 488.6 |  | 488.6 | 279.42 | 76.5
May 2025 |  |  | 881 | KURUDWADI TO PANDHARPUR | MoRTH | N24001101 | 1-2017 | 7/2019 | N.A. | 11/2023 | 307.63 |  | 307.63 | 232.57 | 96.27
May 2025 |  |  | 882 | PANDHARPUR TO SANGOLA | MoRTH | N24001102 | 7-2017 | 7/2019 | N.A. | 12/2023 | 218.38 |  | 218.38 | 182.63 | 99.78
May 2025 |  |  | 883 | PEN TO KHOPOLI | MoRTH | N24001106 | 3-2018 | 3/2018 | N.A. | 1/2024 | 301.39 | 302 | 301.39 | 170.12 | 82.07
May 2025 |  |  | 884 | PANCHARAL TO MANDANGHAR | MoRTH | N24001107 | 7-2018 | 5/2020 | N.A. | 5/2020 | 381.08 | 302 | 381.08 | 45.66
May 2025 |  |  | 885 | NASRATPUR TO BARASGAON | MoRTH | N24001112 | 7-2016 | 9/2019 | N.A. | 9/2019 | 406.54 | 407 | 406.54 | 274.3
May 2025 |  |  | 886 | INDAPUR TO VADPALE | MoRTH | N24001114 | 1-2017 | 12/2019 | N.A. | 3/2024 | 1202.52 | 1656.94 | 1202.52 | 1450.82 | 61.42
May 2025 |  |  | 887 | PAITHAN TO SHIRUR | MoRTH | N24001122 | 3-2017 | 6/2019 | N.A. | 3/2024 | 341.8 |  | 341.8 | 226.19 | 78.6
May 2025 |  |  | 888 | SHIRUR TO KHARDA | MoRTH | N24001123 | 2-2017 | 6/2019 | N.A. | 12/2023 | 381.77 |  | 381.77 | 199.48 | 83.93
May 2025 |  |  | 889 | AURANGABAD TO SILLOD | MoRTH | N24001124 | 2-2017 | 6/2019 | N.A. | 12/2023 | 456.32 | 541.93 | 456.32 | 355.54 | 94.07
May 2025 |  |  | 890 | SILLOD TO FARDAPUR | MoRTH | N24001125 | 2-2017 | 6/2019 | N.A. | 12/2023 | 337.46 | 432.98 | 337.46 | 335.3 | 91.56
May 2025 |  |  | 891 | BHOGAN KHURD TO KASHEDI | MoRTH | N24001132 | 9-2017 | 6/2021 | N.A. | 12/2023 | 743.21 | 743 | 743.21 | 911.64 | 88.69
May 2025 |  |  | 892 | KANTE TO WAKED | MoRTH | N24001134 | 3-2016 | 11/2019 | N.A. | 12/2024 | 1230.02 | 1230 | 1230.02 | 791.8
May 2025 |  |  | 893 | PARLI PIMPLA DAHIGUDA | MoRTH | N24001138 | 2-2017 | 6/2019 | N.A. | 8/2023 | 205.72 | 206 | 205.72 | 85.71 | 100
May 2025 |  |  | 894 | UPGRADATION OF ADHALGAON-JAMKHED SECTION OF NH-548 D FROM KM 132/600 TO KM 195/375 TO TWO LANE WITH | MoRTH | N24001448 | 11-2021 | 2/2022 | N.A. | 2/2022 | 223.35 |  | 223.35 | 209.36 | 87.88
May 2025 |  |  | 895 | REPANPALLI TO SIRONCHA | MoRTH | N24001468 | 3-2022 | 6/2022 | N.A. | 6/2024 | 282.07 |  | 282.07 | 34.65
May 2025 |  |  | 896 | TUNNEL AT KHAMBATAKI GHAT SECTION AND ITS APPROACHES FROM EXISTING KM. 771.730 TO EXISTING KM. 782.0 | NHAI | N24001486 | 2-2019 | 2/2022 | Dec-2024 | 8/2025 | 493 |  | 493 | 399.49 | 76.49
May 2025 |  |  | 897 | DHARAMPURI-LONAND FROM KM. 117.00 TO 166.40 (PKG-IV) ON MOHOL-ALANDI SECTION | NHAI | N24001488 | 9-2021 | 9/2023 | Dec-2024 | 5/2025 | 618.45 |  | 618.45 | 639.23 | 96.2
May 2025 |  |  | 898 | 6L OF KAGAL-SATARA SECTION FROM KM 658.000 TO KM 725.000 OF NH-48 (PKG-II) | NHAI | N24001493 | 12-2022 | 12/2024 | N.A. | 11/2025 | 1749.86 |  | 1749.86 | 1848.81 | 68.18
May 2025 |  |  | 899 | 4L OF RATNAGIRI - KOLHAPUR SECTION OF NH-166 FROM KM 0.000 TO KM 19.769 AND KM 31.000 TO KM 67.140 ( | NHAI | N24001495 | 11-2022 | 11/2024 | N.A. | 9/2025 | 930 |  | 930 | 620.6 | 76.5
May 2025 |  |  | 900 | 4L OF BARAMATI TO INDAPUR (PKG-II) FROM KM. 41.400 TO KM. 84.550 OF NH- 965G (SAINT TUKARAM MARG) | NHAI | N24001502 | 9-2021 | 9/2023 | Jun-2025 | 6/2025 | 624.45 | 580.15 | 580.15 | 420.42 | 0.5
May 2025 |  |  | 901 | 4L OF INDAPUR TO TONDLE (PKG-III) FROM KM.84.550 TO KM. 131.00 OF NH-965G | SAINT TUKARAM MARG | NHAI | 9-2021 | 9/2023 | Jan-2025 | 3/2025 | 667.66 | 666.21 | 666.21 | 610.63 | 3
May 2025 |  |  | 902 | VADODARA MUMBAI EXPRESSWAY (PHASE II - PKG XI) [KM. 77.000 TO KM. 103.400] | GANJAD - TALSARI | NHAI | 5-2022 | 5/2024 | Jun-2025 | 6/2025 | 1260 |  | 1260 | 665.73 | 97
May 2025 |  |  | 903 | VADODARA MUMBAI EXPRESSWAY (PHASE II - PKG XII) [KM. 50.700 TO KM. 77.000] | MASVAN - GANJAD | NHAI | 3-2022 | 3/2024 | Jun-2025 | 6/2025 | 1549.02 |  | 1549.02 | 699 | 82.91
May 2025 |  |  | 904 | VADODARA MUMBAI EXPRESSWAY (PHASE II - PKG XIII) [KM. 26.582 TO KM. 50.700] | SHIRSAD - MASVAN | NHAI | 2-2022 | 2/2024 | Jun-2025 | 6/2025 | 2747 |  | 2747 | 1125.16 | 80.02
May 2025 |  |  | 905 | VADODARA MUMBAI EXPRESSWAY (PHASE II - PKG XIV) [KM. 3.000 TO KM. 20.200 OF SPUR] (SHIRSAD - AKLOLI) | NHAI | N24001507 | 11-2022 | 5/2024 | Jun-2025 | 6/2025 | 1124 |  | 1124 | 483.84 | 73.13
May 2025 |  |  | 906 | VADODARA MUMBAI EXPRESSWAY (PHASE II - PKG XVI) [KM. 43.000 TO KM. 69.800 OF SPUR] (AMNE - BHOJ) | NHAI | N24001508 | 11-2022 | 10/2024 | Jun-2025 | 6/2025 | 1450 |  | 1450 | 718.65 | 84.05
May 2025 |  |  | 907 | VADODARA MUMBAI EXPRESSWAY (PHASE II - PKG XV) [KM. 20.200 TO KM. 43.000 OF SPUR] (AKLOLI - AMNE) | NHAI | N24001521 | 11-2022 | 10/2024 | Jul-2025 | 7/2025 | 990 |  | 990 | 406.91 | 73
May 2025 |  |  | 908 | 6L OF KAGAL-SATARA SECTION FROM KM 592.240 TO KM 658.000 OF NH-48 (PKG-I) | NHAI | N24001546 | 1-2023 | 1/2025 | N.A. | 1/2025 | 1025.2 |  | 1025.2 | 453.39 | 44.22
May 2025 |  |  | 909 | BALANCE WORKS OF 4L PANVEL-INDAPUR SECTION OF NH-66 (OLD NH-17) FROM KM 42.300 (KASU) TO KM 84.600 ( | NHAI | N24001607 | 10-2022 | 5/2024 | Dec-2025 | 12/2025 | 332 |  | 332 | 273.33 | 64.63
May 2025 |  |  | 910 | VADODARA MUMBAI EXPRESSWAY (PHASE II - PKG XVII) [KM. 69.800 TO KM. 79.783 OF SPUR] (BHOJ - MORBE) | NHAI | N24001608 | 9-2021 | 7/2025 | N.A. | 7/2025 | 2208.68 |  | 2208.68 | 565.2 | 74.5
May 2025 |  |  | 911 | BALANCE WORK OF 4 LANING OF PANVEL TO INDAPUR SECTION OF NH-66(OLD NH- 17) FROM KM 0.000 (PANVEL) TO | NHAI | N24001609 | 1-2023 | 12/2023 | Jun-2025 | 6/2025 | 151.26 |  | 151.26 | 153.77 | 86.38
May 2025 |  |  | 912 | 4L OF EXISTING 2/4L STRETCH FROM LONAND TO DIVE GHAT (KM 166.400 TO KM 220.900 ) OF MOHOL ? ALANDI S | NHAI | N24001610 | 1-2022 | 5/2024 | Mar-2025 | 5/2025 | 1833.73 |  | 1833.73 | 539.18 | 95.64
May 2025 |  |  | 913 | FOUR LANING OF AURANGABAD-PAITHAN SECTION OF NH-752E ON EPC MODE IN THE STATE OF MAHARASHTRA . | NHAI | N24001795 | 10-2022 | 7/2024 | Jun-2025 | 12/2024 | 490.4 |  | 289 | 275.78 | 95
May 2025 |  |  | 914 | 4L OF RAJURA-KORPANA-ADILABAD ROAD UPTO M.S. BORDER FROM KM 32.910 TO KM 89.090 OF NH-353B | NHAI | N24001796 | 3-2022 | 10/2024 | Apr-2025 | 4/2025 | 1013.33 | 1013.33 | 1111.33 | 355.07 | 62.01
May 2025 |  |  | 915 | 6L OF WAINGANGA BRIDGE - BHANDARA (INCLUDING BHANDARA BYPASS) SECTION FROM KM 485.000 TO KM 499.800 | NHAI | N24001797 | 10-2021 | 1/2024 | N.A. | 5/2025 | 815.77 |  | 815.77 | 732.7 | 100
May 2025 |  |  | 916 | 4L MITIGATION MEASURE STRUCTURES ON CH/MH BORDER TO WAINGANGA BRIDGE SECTION OF NH-53 | NHAI | N24001798 | 2-2021 | 11/2023 | N.A. | 5/2025 | 540.21 |  | 540.21 | 457.05 | 100
May 2025 |  |  | 917 | 4L OF NAGPUR-KATOL SECTION FROM KM. 13.00 TO KM. 62.900 OF NH-353J | NHAI | N24001799 | 2-2021 | 10/2023 | N.A. | 10/2025 | 1166.96 |  | 1251 | 1078.65 | 81
May 2025 |  |  | 918 | BAL. WORKS OF FAGNE (KM. 510.000) TO MAHARASHTRA/GUJARAT BORDER (KM. 650.794) | NHAI | N24001804 | 12-2019 | 9/2022 | Jun-2024 | 12/2025 | 1654.07 |  | 980 | 887.38 | 95.75
May 2025 |  |  | 919 | 4L OF RATNAGIRI - KOLHAPUR SECTION FROM KM 67.140 TO KM 112.340 OF NH-166 | PKG ? II | NHAI | 5-2023 | 5/2025 | N.A. | 5/2025 | 839 |  | 839 | 441.05 | 56.5
May 2025 |  |  | 920 | 4L OF RATNAGIRI - KOLHAPUR SECTION FROM KM 112.340 TO KM 145.300 OF NH-166 | PKG?III | NHAI | 5-2023 | 5/2025 | N.A. | 5/2025 | 986 |  | 986 | 508.04 | 54.6
May 2025 |  |  | 921 | REHABILITATION AND UP-GRADATION TO 4 LANE ROAD WITH PAVED SHOULDER CONFIGURATION OF SECTION FROM UND | MoRTH | N24001880 | 3-2022 | 7/2025 | N.A. | 7/2025 | 778.18 |  | 778.18 | 135.78
May 2025 |  |  | 922 | CONSTRUCTION OF NEW FOUR LANE BYPASS TO PARBHANI CITY (PARWA TO ASOLA) KM 463/265 TO KM 481/180 (DES | MoRTH | N24001882 | 3-2022 | 10/2024 | N.A. | 10/2024 | 496.64 |  | 496.64 | 0 | 8
May 2025 |  |  | 923 | CONSTRUCTION OF 4 LANE FLYOVER AT NAGPUR RTO CHOWK TO NAGPUR UNIVERSITY CAMPUS FROM CH 2/250 TO 5/10 | MoRTH | N24001883 | 3-2021 | 3/2024 | N.A. | 4/2024 | 478.83 |  | 478.83 | 233.48 | 65
May 2025 |  |  | 924 | REHABILITATION AND UPGRADATION OF SATANA TO MANGRUL (CHANDWAD) SECTION OF NH752 G DESIGN CH: KM 64.0 | MoRTH | N24001884 | 3-2023 | 5/2025 | N.A. | 5/2025 | 428.8 |  | 428.8 | 54.11 | 30.69
May 2025 |  |  | 925 | REHABILITATION AND UP-GRADATION OF JINTUR- SHIRAD SHAHAPUR SECTION KM 258.300 TO KM 306.300 [DESIGN | MoRTH | N24001885 | 2-2023 | 12/2024 | N.A. | 12/2024 | 414.81 |  | 414.81 | 0
May 2025 |  |  | 926 | DEVELOPMENT/WIDENING OF TALEGAON ? CHAKAN ? SHIKRAPUR ? NHAVARA SECTION OF NH 548DG (NHAVARA TO CHOU | MoRTH | N24001886 | 10-2022 | 8/2024 | N.A. | 8/2024 | 304.68 |  | 304.68 | 97.09 | 59
May 2025 |  |  | 927 | REHABILITATION AND UPGRADATION OF BHOKARDAN TO KUMBHARI FATA DESIGN CH. (KM 13+500 TO 17+00) AND RAJ | MoRTH | N24001887 | 8-2022 | 6/2024 | N.A. | 6/2024 | 291.37 |  | 291.37 | 102.94 | 78.44
May 2025 |  |  | 928 | UP-GRADATION OF TIRORA-GONDIA, STATE HIGHWAY FROM EXISTING KM 163+213 (ON SH-335, TIRORA) TO KM 191+ | MoRTH | N24001888 | 8-2021 | 4/2023 | N.A. | 5/2024 | 288.14 |  | 288.14 | 63.01 | 46.31
May 2025 |  |  | 929 | 2 LANE + PS PIMPLNER TO SATANA - [DESIGN CHAINAGE KM 21.427 TO 64.00 ] OF NH-752G] | MoRTH | N24001889 | 9-2019 | 7/2021 | N.A. | 12/2023 | 277.81 |  | 277.81 | 148.68 | 90
May 2025 |  |  | 930 | REHABILITATION AND UPGRADATION OF PARLI TO SIRSALA SECTION OF NH-361F (KM 136+700 TO 115+000) (LENGT | MoRTH | N24001890 | 2-2023 | 12/2024 | N.A. | 12/2024 | 261.82 |  | 261.82 | 70.59 | 46
May 2025 |  |  | 931 | BALANCE WORK OF REHABILITATION AND UP-GRADATION TO NH-166F FROM MAHAD JUNCTION (AT KM 123/400 ON NH- | MoRTH | N24001891 | 7-2021 | 11/2023 | N.A. | 3/2024 | 256.54 |  | 256.54 | 80.1 | 60
May 2025 |  |  | 932 | REHABILITATION AND UPGRADATION OF SHIRAPUR JUNCTION TO SHIVAJI CHOWK (DESIGN CHAINAGE KM. 130+00 TO | MoRTH | N24001892 | 2-2023 | 12/2024 | N.A. | 12/2024 | 245.61 |  | 245.61 | 43.39 | 33
May 2025 |  |  | 933 | 2 LANE + PS ASTHAMODE - TIVATYAL [DESIGN CH. KM 24.300 - 62.00] [KM 134.98- 172.95 OF NH-63] | MoRTH | N24001894 | 9-2019 | 7/2021 | N.A. | 12/2023 | 228.82 |  | 228.82 | 144.54 | 95.44
May 2025 |  |  | 934 | REHABILATION AND UPGRADATION TO TWO LANES WITH PAVED SHOULDER CONFIGURATION FROM WATUR TO CHARTHANA | MoRTH | N24001895 | 11-2021 | 9/2023 | N.A. | 12/2023 | 228.01 |  | 228.01 | 103.01 | 99
May 2025 |  |  | 935 | UPGRADATIOBN AND REHABILITATION OF SECTION OF NH 361 F FROM PARLI (00/000) TO GANGAKHED (30/400) TO | MoRTH | N24001896 | 11-2021 | 9/2023 | N.A. | 4/2024 | 224.44 |  | 224.44 | 75.34 | 45.63
May 2025 |  |  | 936 | REHABILITATION AND UP-GRADATION OF SABALKHED TO ASHTI SECTION FROM KM 37+900 TO KM 55+100 AND CHINCH | MoRTH | N24001902 | 12-2022 | 9/2024 | N.A. | 9/2024 | 213.32 |  | 213.32 | 20 | 34
May 2025 |  |  | 937 | REHABILITATION AND UP-GRADATION OF MUDKHED TO NANDED SECTION FROM KM. 372+000 TO KM 388+400 OF NH 16 | MoRTH | N24001903 | 8-2022 | 4/2025 | N.A. | 4/2025 | 206.54 |  | 206.54 | 21.36
May 2025 |  |  | 938 | KOPARGAON TO SAVALI VIHIR SECTION | MoRTH | N24001904 | 9-2022 | 7/2024 | N.A. | 7/2024 | 195.38 |  | 195.38 | 29.59 | 19.76
May 2025 |  |  | 939 | CONSTRUCTION OF MAJOR BRIDGE ACROSS MANJRA RIVER NEAR YESGI VILLAGE @ KM, 166/500 ON NH 63 TQ BILOLI | MoRTH | N24001905 | 10-2021 | 8/2023 | N.A. | 12/2023 | 188.69 |  | 188.69 | 111.26 | 95.8
May 2025 |  |  | 940 | UP-GRADATION TO 4 LANING OF DAULTABAD T-POINT TO MALIWADA [FROM DESIGN KM.0.000 TO KM 4.000] AND UPG | MoRTH | N24001906 | 8-2022 | 3/2024 | N.A. | 3/2024 | 185.59 |  | 185.59 | 63.56 | 48
May 2025 |  |  | 941 | CONSTRUCTION OF SIX LANE FLYOVER AT KATRAJ JUNCTION AT KM, 3/880 OF NH 548- DD (VADGAON - KATRAJ - KO | MoRTH | N24001907 | 6-2021 | 2/2024 | N.A. | 3/2024 | 169.15 |  | 169.15 | 36.94 | 35.96
May 2025 |  |  | 942 | UPGRADATION OF EXHISTING 2 LANE FLEXIBLE PAVEMENT TO 2 LANE PAVED SHOULDERS RIGID PAVEMENT FROM DESI | MoRTH | N24001908 | 12-2021 | 5/2024 | N.A. | 5/2024 | 167.97 |  | 167.97 | 35.28 | 36.76
May 2025 |  |  | 943 | STRENGTHING AND WIDINING OF EXISTING CARRIAGEWAY TO 10 M IN KM, 156/160 TO 229/160 (TEMBHURNI - KUSL | MoRTH | N24001909 | 11-2021 | 6/2024 | N.A. | 6/2024 | 157.72 |  | 157.72 | 55.38 | 90.41
May 2025 |  |  | 944 | REHABILITATION AND UPGRADATION OF JAMKHED TO SAUTADA SECTION OF NH548 D (FROM KM 195.375 TO KM 208.7 | MoRTH | N24001910 | 9-2022 | 7/2024 | N.A. | 7/2024 | 157.62 |  | 157.62 | 13.86 | 17.03
May 2025 |  |  | 945 | PANGAON TO DHARMAPURI AND PARALI TO INJEGAON 2L+PS | MoRTH | N24001911 | 3-2018 | 7/2024 | N.A. | 12/2023 | 152.03 |  | 152.03 | 81.35 | 97.57
May 2025 |  |  | 946 | 4L OF INDORA CHOWK TO PACHPAOLI AND AGRASEN CHOWK - ASHOKA CHOWK | NHAI | N24002071 | 3-2023 | 6/2026 | N.A. | 6/2026 | 998.27 |  | 998.27 | 347.53 | 45.52
May 2025 |  |  | 947 | IMPROVEMENT OF EXISTING ALIGNMENT OF PANDHARPUR TOWN PART BYPASSED SECTION FROM WAKHARI TO LORD VITT | NHAI | N24002072 | 7-2022 | 10/2025 | N.A. | 10/2025 | 150.21 | 150.21 | 150.21 | 31.57 | 6
May 2025 |  |  | 948 | STRENGTHENING OF 6-LANE PIMPALGAON- NASHIK-GONDE (KM. 380 - KM. 440) SECTION OF NH-3 IN MAHARASHTRA U | NHAI | N24002137 | 2-2024 | 3/2025 | N.A. | 3/2025 | 175 | 206.49 | 206.49 | 198.54 | 100
May 2025 |  |  | 949 | REHABILITATION/UPGRADATION OF EXISTING HIGHWAY TO 2L+PS/4 LANE OF DHAWALI TO RAJOLI FROM DESIGN KM.1 | MoRTH | N24002169 | 3-2022 | 9/2025 | N.A. | 9/2025 | 316.44 |  | 316.44 | 0
May 2025 |  |  | 950 | REHABILITATION/ UPGRADATION OF EXISTING HIGHWAY TO FOUR LANE STANDARDS IN KURKHEDA TOWN FROM (KM.413 | MoRTH | N24002170 | 3-2022 | 5/2025 | N.A. | 5/2025 | 163.86 |  | 163.86 | 0
May 2025 |  |  | 951 | REHABILITATION AND UP-GRADATION FOR TALERE A?? GAGANBAWDAA?? KOLHAPUR ROAD (NH-166G) STRETCHES START | MoRTH | N24002171 | 2-2023 | 4/2025 | N.A. | 4/2025 | 249.13 |  | 249.13 | 0
May 2025 |  |  | 952 | UP-GRADATION TO 4 LANE CONFIGURATION FOR THE WORK OF PETH NAKA TO SANGLI ROAD, NH-166H, FROM KM 0+00 | MoRTH | N24002172 | 2-2023 | 12/2025 | N.A. | 12/2025 | 856.82 |  | 856.82 | 0
May 2025 |  |  | 953 | REHABILITATION AND UP-GRADATION TO 2 LANE WITH PAVED SHOULDER CONFIGURATION OF MAHUD SANGOLA ROAD NH | MoRTH | N24002173 | 2-2023 | 4/2025 | N.A. | 4/2025 | 253.78 |  | 253.78 | 0
May 2025 |  |  | 954 | UP-GRADATION TO FOUR LANE/ TWO LANE WITH PAVED SHOULDERS CONFIGURATION OF KALYAN - MURBAD - MALSHEJ | MoRTH | N24002174 | 2-2023 | 8/2026 | N.A. | 8/2026 | 984.07 |  | 984.07 | 0
May 2025 |  |  | 955 | CONSTRUCTION OF FOUR-LANE CONCRETE ROAD FROM POLICE HEADQUARTER GONDIA CITY TO RAWANWADI VILLAGE (BI | MoRTH | N24002175 | 2-2023 | 8/2025 | N.A. | 8/2025 | 328.11 |  | 328.11 | 0
May 2025 |  |  | 956 | REHABILITATION/UP GRADATION OF KARANJA ? KHERDA - MURTIZAPUR SECTION TO 4LANE+PAVED SHOULDER STANDA | MoRTH | N24002176 | 3-2023 | 2/2026 | N.A. | 2/2026 | 594.44 |  | 594.44 | 0
May 2025 |  |  | 957 | REHABILITATION / UPGRADATION TO 4 LANE WITH PAVED SHOULDER OF EXISTING SECTION IN SILLOD TOWN WITH D | MoRTH | N24002177 | 3-2023 | 7/2025 | N.A. | 7/2025 | 153.79 |  | 153.79 | 0
May 2025 |  |  | 958 | REHABILITATION, UPGRADATION AND WIDENING OF EXISTING HIGHWAY TO RIGID PAVEMENT 2 LANE WITH PAVED SHO | MoRTH | N24002178 | 2-2023 | 7/2026 | N.A. | 7/2026 | 723.13 |  | 723.13 | 0
May 2025 |  | URBAN DEVELOPMENT | 959 | MUMBAI METRO LINE 3 (COLABA-BANDRA- SEEPZ) | MMRCL | N28000086 | 7-2013 | 3/2020 | Jul-2025 | 7/2025 | 23136 |  | 37276 | 28615.78 | 94.77
May 2025 |  | URBAN DEVELOPMENT | 960 | PUNE METRO RAIL PROJECT (PHASE 1) | MMRC | N28000121 | 12-2016 | 11/2021 | Sep-2024 | 9/2024 | 11420 | 13656.22 | 13656.22 | 13049.54 | 100
May 2025 |  | URBAN DEVELOPMENT | 961 | NAGPUR METRO RAIL PROJECT PHASE II | NMRCL | N28000155 | 12-2022 | 12/2027 | N.A. | 12/2027 | 6708 |  | 6708 | 809.32 | 22.68
May 2025 |  | URBAN DEVELOPMENT | 962 | PCMC NIGDI PROJECT EXTENSION OF CORRIDOR 1 OF PUNE METRO PHASE 1 | MMRC | N28000157 | 10-2023 | 1/2027 | N.A. | 1/2027 | 910.18 |  | 910.18 | 91.03 | 16.99
May 2025 |  | URBAN DEVELOPMENT | 963 | PUNE METRO PHASE-1 EXTENSION FROM SWARGATE TO KATRAJ | MMRC | N28000160 | 9-2024 | 3/2029 | N.A. | 3/2029 | 2954.53 |  | 2954.53 | 16.38 | 2.15
May 2025 |  | CIVIL AVIATION | 964 | CONSTRUCTION OF NEW INTEGRATED TERMINAL BUILDING, CONTROL TOWER CUM TECHNICAL BLOCK, APRON, LINK TAX | AAI | N04000100 | 11-2021 | 7/2024 | Mar-2026 | 3/2026 | 499 |  | 499 | 154.47 | 40.36
May 2025 |  | RAILWAYS | 965 | JIRIBAM TO IMPHAL (TUPUI)(NL)(NEFR) | NFR | 220100288 | 4-2003 | 12/2026 | Mar-2028 | 3/2028 | 14322.79 | 12274.06 | 22234.6 | 15338.76 | 69
May 2025 |  | RAILWAYS | 966 | 2-LANING OF CHURACHANDPUR TUIVAI SECTION OF NH-102B (PKG- 2A) | NHIDCL | N24001270 | 3-2020 | 6/2022 | Jun-2025 | 9/2025 | 292.24 |  | 292.24 | 130.66 | 89.88
May 2025 |  |  | 967 | 2-LANING OF CHURACHANDPUR TUIVAI SECTION OF NH-102B (PKG- 2B) | NHIDCL | N24001271 | 6-2020 | 8/2022 | Jun-2025 | 10/2025 | 365.53 |  | 365.53 | 156.31 | 77.36
May 2025 |  |  | 968 | 2-LANING OF CHURACHANDPUR TUIVAI SECTION OF NH-102B (PKG- 4A) | NHIDCL | N24001272 | 3-2020 | 6/2022 | Jan-2025 | 6/2025 | 167.95 | 204.12 | 167.95 | 88.05 | 69.89
May 2025 |  |  | 969 | 2-LANING OF CHURACHANDPUR TUIVAI SECTION OF NH-102B (PKG- 4B) | NHIDCL | N24001273 | 7-2020 | 8/2022 | Feb-2025 | 6/2025 | 177.76 |  | 177.76 | 89.67 | 80.53
May 2025 |  |  | 970 | IMPROVEMENT/UPGRADATION OF EXISTING 2-LANE TO 4-LANE DIVIDED HIGHWAY FROM TAPHOU KUKI TO DAILI SECTI | NHIDCL | N24001274 | 8-2020 | 4/2022 | Jun-2025 | 12/2025 | 379.39 |  | 379.39 | 218.03 | 70.31
May 2025 |  |  | 971 | MARIAM - PEREN PKG-1A | NHIDCL | N24001349 | 2-2021 | 12/2022 | Mar-2025 | 12/2025 | 226.32 |  | 226.32 | 105.78 | 74.48
May 2025 |  |  | 972 | MARIAM - PEREN (PKG 1B) | NHIDCL | N24001350 | 2-2021 | 12/2022 | Jan-2025 | 9/2025 | 188.36 |  | 188.36 | 126.71 | 100
May 2025 |  |  | 973 | TAMENGLONG - MAHUR PKG-3 | NHIDCL | N24001354 | 3-2021 | 12/2022 | Sep-2024 | 11/2025 | 234.08 |  | 234.08 | 139.45 | 92.82
May 2025 |  |  | 974 | SENAPATI- IMPHAL PKG-5B | NHIDCL | N24001400 | 3-2021 | 1/2023 | May-2025 | 10/2025 | 211.7 |  | 211.7 | 83.79 | 70.72
May 2025 |  |  | 975 | IMPHAL - KHONGSANG PKG-3 | NHIDCL | N24001401 | 7-2021 | 3/2023 | Mar-2025 | 10/2025 | 467 |  | 467 | 193.81 | 77.8
May 2025 |  |  | 976 | TAMENGLONG - MAHUR PKG-1 | NHIDCL | N24001402 | 7-2021 | 3/2023 | Jan-2025 | 1/2025 | 185.8 |  | 185.8 | 117.78 | 100
May 2025 |  |  | 977 | TAMENGLONG - MAHUR PKG-2 | NHIDCL | N24001403 | 7-2021 | 3/2023 | Jan-2025 | 12/2025 | 483.87 |  | 483.87 | 278.89 | 92.94
May 2025 |  |  | 978 | TAMENGLONG - MAHUR PKG-4 | NHIDCL | N24001404 | 7-2021 | 3/2023 | Feb-2025 | 3/2025 | 198.77 |  | 198.77 | 127.86 | 100
May 2025 |  |  | 979 | CHURACHANPUR TUIVAI PKG-3 | NHIDCL | N24001405 | 7-2021 | 10/2023 | Mar-2025 | 12/2025 | 673.27 |  | 673.27 | 382.37 | 79.47
May 2025 |  |  | 980 | TAMENGLONG - MAHUR PKG-5 | NHIDCL | N24001436 | 8-2021 | 5/2023 | Jan-2025 | 1/2026 | 477.86 |  | 477.86 | 246.09 | 84.6
May 2025 |  |  | 981 | TAMENGLONG - MAHUR PKG-6 | NHIDCL | N24001437 | 9-2021 | 5/2023 | Nov-2024 | 12/2025 | 311.18 |  | 311.18 | 190.96 | 83.5
May 2025 |  |  | 982 | MARAM - PEREN PKG-3 | NHIDCL | N24001439 | 8-2021 | 5/2023 | Oct-2024 | 2/2025 | 467.41 |  | 467.41 | 264.83 | 100
May 2025 |  |  | 983 | IMPHAL - KHONGSANG PKG-4 | NHIDCL | N24001453 | 8-2021 | 12/2023 | Jul-2025 | 12/2025 | 579.63 |  | 579.63 | 172.65 | 72
May 2025 |  |  | 984 | CONSTRUCTION OF 2-LANING WITH HARD SHOULDER ROAD OF UKHRUL - TOLOI - TADUBI SECTION OF NH-102A FROM | NHIDCL | N24001473 | 9-2021 | 2/2024 | Mar-2025 | 6/2025 | 310.76 |  | 310.76 | 129.15 | 96.77
May 2025 |  |  | 985 | IMPHAL - KHONGSANG PKG-5 | NHIDCL | N24001538 | 12-2021 | 5/2024 | Jan-2026 | 3/2026 | 410.68 |  | 410.68 | 147.81 | 68.79
May 2025 |  |  | 986 | IMPHAL - KHONGSANG PKG-6 | NHIDCL | N24001539 | 12-2021 | 2/2025 | Sep-2025 | 12/2025 | 504.76 |  | 504.76 | 183.15 | 76.52
May 2025 |  |  | 987 | AKASH BRIDGE - JESSAMI SECTION PKG-2 | NHIDCL | N24001540 | 3-2022 | 2/2025 | Feb-2025 | 3/2025 | 152.11 |  | 152.11 | 73.48 | 100
May 2025 |  |  | 988 | CONSTRUCTION OF 2-LANING WITH HARD SHOULDER ROAD OF UKHRUL - TOLOI - TADUBI SECTION OF NH-102A FROM | NHIDCL | N24001974 | 9-2021 | 1/2025 | Aug-2025 | 8/2025 | 315.56 |  | 315.56 | 137.81 | 88.54
May 2025 |  |  | 989 | LMPHAL TO JIRIBAM PKG-7 | NHIDCL | N24002028 | 1-2023 | 12/2025 | Dec-2025 | 3/2026 | 760.16 |  | 760.16 | 148.98 | 60.6
May 2025 |  |  | 990 | UKHRUL TOLOI TADUBI PKG-2 | NHIDCL | N24002131 | 3-2023 | 2/2026 | Mar-2026 | 3/2026 | 578.98 |  | 578.98 | 153.92 | 71.25
May 2025 |  |  | 991 | MARREM KHULLEN TO JESSAMI SECTION IMPHAL- UKHRUL - JESSAMI PKG-6 (DESIGN CHAINAGE KM 95.700 TO KM 14 | NHIDCL | N24002202 | 3-2023 | 12/2026 | N.A. | 12/2026 | 554.66 |  | 554.66 | 17.79 | 11.93
May 2025 |  |  | 992 | IMPHAL-KOHIMA ROAD PKG-4B | NHIDCL | N24002203 | 9-2020 | 6/2026 | N.A. | 6/2026 | 268.98 |  | 268.98 | 13.14 | 15.9
May 2025 |  |  | 993 | JESSAMI TO LAYNEN BRIDGE UKHRUL - JESSAMI PKG-7 | NHIDCL | N24002227 | 3-2023 | 6/2026 | N.A. | 6/2026 | 164.89 |  | 164.89 | 1.46 | 6.5
May 2025 |  |  | 994 | IMPHAL-KOHIMA ROAD PKG-5A | NHIDCL | N24002232 | 9-2020 | 8/2026 | N.A. | 8/2026 | 228.97 |  | 228.97 | 0 | 5.96
May 2025 |  |  | 995 | CHOITHAR TO MARREM KHULLEN SECTION IMPHAL- UKHRUL - JESSAMI PKG-5 | NHIDCL | N24002242 | 3-2023 | 3/2027 | N.A. | 3/2027 | 564.05 |  | 564.05 | 0
May 2025 |  |  | 996 | IMPHAL - KHONGSANG - JIRIBAM PKG-2 | NHIDCL | N24002244 | 3-2021 | 3/2026 | N.A. | 3/2026 | 195.14 |  | 195.14 | 0 | 7.19
May 2025 |  | DEPARTMENT OF HIGHER EDUCATION | 997 | CONSTRUCTION AND DEVELOPMENT OF NATINAL INSTITUTE OF TECHNOLOGY MEGHALAYA PERMANENT CAMPUS AT SOHRA | RITES OF HIGHER | N42000001 | 9-2013 | 9/2014 | Jul-2025 | 7/2025 | 484.32 | 429.7 | 494.52 | 270.55 | 84
May 2025 |  | DEPARTMENT OF HIGHER EDUCATION | 998 | WIDENING TO 2-LANE WITH GEOMETRIC IMPROVEMENTS OF TURA DALU ROAD UNDER JICA FUNDING FROM KM 85.000 T | NHIDCL | N24000771 | 4-2017 | 9/2021 | Mar-2025 | 6/2025 | 553.51 | 610.09 | 553.51 | 432.78 | 92.01
May 2025 |  | DEPARTMENT OF HIGHER EDUCATION | 999 | IMPROVEMENT/WIDENING TO 2-L WITH PAVED SHOULDER FROM (DESIGN KM 0.00 TO KM 10.670) / 4-LANING FROM ( | NHIDCL | N24001313 | 11-2020 | 12/2023 | Oct-2025 | 10/2025 | 351.12 |  | 351.12 | 295.88 | 62.5
May 2025 |  | DEPARTMENT OF HIGHER EDUCATION | 1000 | IMPROVEMENT/WIDENING TO 2-LANE WITH PAVED SHOULDER FROM (DESIGN KM 10.670 TO KM 37.550) BETWEEN SHIL | NHIDCL | N24001314 | 11-2020 | 12/2023 | N.A. | 8/2026 | 525.68 |  | 525.68 | 434.11 | 31
May 2025 |  | DEPARTMENT OF HIGHER EDUCATION | 1001 | IMPROVEMENT/WIDENING TO 2-LANE WITH PAVED SHOULDER FROM (DESIGN KM 45.760 TO KM 63.530) BETWEEN SHIL | NHIDCL | N24001334 | 11-2020 | 12/2023 | N.A. | 4/2026 | 445.51 |  | 445.51 | 207.2 | 26
May 2025 |  | DEPARTMENT OF HIGHER EDUCATION | 1002 | IMPROVEMENT/WIDENING TO 2-LANE WITH PAVED SHOULDER / 4-LANING FROM (DESIGN KM 63.530 TO KM 71.520) B | NHIDCL | N24001335 | 11-2020 | 12/2023 | N.A. | 11/2026 | 284.21 |  | 284.21 | 101.98 | 24
May 2025 |  |  | 1003 | RANIKOR-MAHESHKHOLA- BAGHMARA | RMB) PKG-4 (KANAI-RONGARA | NHIDCL | 10-2020 | 4/2022 | Jun-2024 | 2/2025 | 157.86 | 146.92 | 157.86 | 152.95 | 100
May 2025 |  |  | 1004 | REHABILITATION AND UPGRADATION OF NONGSTOIN TO WAHKAJI SECTION OF PROJECT ROAD KM 0.000 TO KM 43.06 | MoRTH | N24001441 | 8-2020 | 2/2022 | N.A. | 3/2025 | 302.88 |  | 302.88 | 228.68 | 96
May 2025 |  |  | 1005 | REHABITITATION AND UP GRADATION OF NONGSTOIN-RAMBRAI-KYRSHAI ROAD UP TO MEGHALAYA-ASSAM BORDER FROM | NHIDCL | N24001474 | 9-2021 | 5/2024 | Dec-2024 | 5/2026 | 359.86 |  | 359.86 | 233.26 | 87
May 2025 |  |  | 1006 | RANIKOR- MAHESHKHOLA- BAGHMARA PKG- 2 | NHIDCL | N24001541 | 11-2021 | 6/2024 | Dec-2024 | 5/2025 | 283.5 |  | 283.5 | 257.26 | 100
May 2025 |  |  | 1007 | CONSTRUCTION OF 2-LANE WITH PAVED SHOULDER OF SHILLONG WESTERN BYPASS STARTING FROM NH-06 NEAR LADUM | NHIDCL | N24002156 | 3-2023 | 9/2026 | N.A. | 9/2026 | 620.3 |  | 620.3 | 221.86 | 28
May 2025 |  |  | 1008 | SHILLONG WESTERN BYPASS PACKAGE-2 | NHIDCL | N24002157 | 3-2023 | 9/2026 | N.A. | 9/2026 | 686 |  | 686 | 292.69 | 25.52
May 2025 |  |  | 1009 | CONSTRUCTION OF 2-LANE WITH PAVED SHOULDERS OF SHILLONG WESTERN BYPASS STARTING FROM NH-06 NEAR LADU | NHIDCL | N24002158 | 3-2023 | 9/2026 | N.A. | 9/2026 | 562.48 |  | 562.48 | 297.79 | 24
May 2025 |  |  | 1010 | DAINADUBI-DARUGIRI PKG-1B | NHIDCL | N24002233 | 3-2023 | 3/2027 | N.A. | 3/2027 | 705.83 |  | 705.83 | 0.31 | 1.55
May 2025 |  |  | 1011 | IMPROVEMENT AND WIDENING TWO LANNIG WITH PAVED SHOULDER OF NATIONAL HIGHWAY 127B FROM KM 31.500 (GOE | MoRTH | N24002239 | 12-2023 | 5/2027 | N.A. | 5/2027 | 504 |  | 504 | 0
May 2025 |  | RAILWAYS | 1012 | BHAIRABI SAIRONG, NL, NEFR | NFR | N22000100 | 4-2008 | 3/2025 | N.A. | 6/2025 | 6527.45 | 5021.45 | 8213.72 | 8001.88 | 97
May 2025 |  |  | 1013 | WIDENING AND UP-GRADATION TO 2-LANE WITH PAVED SHOULDER CONFIGURATION AND GEOMETRIC IMPROVEMENTS FRO | NHIDCL | N24000857 | 4-2017 | 4/2023 | N.A. | 4/2025 | 519.09 |  | 785.65 | 670.91 | 97.51
May 2025 |  |  | 1014 | WIDENING AND UP-GRADATION TO 2-LANE WITH PAVED SHOULDER CONFIGURATION AND GEOMETRIC IMPROVEMENTS FRO | NHIDCL | N24000858 | 4-2017 | 7/2023 | N.A. | 5/2024 | 640.07 |  | 1286.35 | 1195.84 | 98.9
May 2025 |  |  | 1015 | WIDENING AND UP-GRADATION TO 2-LANE WITH PAVED SHOULDER CONFIGURATION AND GEOMETRIC IMPROVEMENTS FRO | NHIDCL | N24000861 | 4-2017 | 4/2023 | N.A. | 4/2025 | 473.18 |  | 688.25 | 541.04 | 94.7
May 2025 |  |  | 1016 | WIDENING AND UP-GRADATION TO 2-LANE WITH PAVED SHOULDER CONFIGURATION AND GEOMETRIC IMPROVEMENTS FRO | NHIDCL | N24000862 | 4-2017 | 4/2023 | N.A. | 5/2025 | 537.82 |  | 789.05 | 778.16 | 99.82
May 2025 |  |  | 1017 | WIDENING AND UP-GRADATION TO 2-LANE WITH PAVED SHOULDER CONFIGURATION AND GEOMETRIC IMPROVEMENTS FRO | NHIDCL | N24000863 | 4-2017 | 6/2023 | N.A. | 5/2025 | 518.53 |  | 906.76 | 849.68 | 97.9
May 2025 |  |  | 1018 | WIDENING AND UP-GRADATION TO 2-LANE WITH PAVED SHOULDER CONFIGURATION AND GEOMETRIC IMPROVEMENTS FRO | NHIDCL | N24000864 | 4-2017 | 4/2024 | N.A. | 5/2025 | 404.29 |  | 750.32 | 666.58 | 100
May 2025 |  |  | 1019 | WIDENING AND UP-GRADATION TO 2-LANE WITH PAVED SHOULDER CONFIGURATION AND GEOMETRIC IMPROVEMENTS FRO | NHIDCL | N24000865 | 4-2017 | 9/2023 | N.A. | 5/2025 | 428.11 |  | 746.39 | 613.69 | 98.7
May 2025 |  |  | 1020 | CONSTRUCTION OF TWO LANE WITH PAVED SHOULDER OF SELLING-DULTE SECTION OF NH-06 (PKG-I) | NHIDCL | N24001278 | 3-2020 | 7/2022 | N.A. | 6/2024 | 206.88 |  | 219.33 | 265.34 | 100
May 2025 |  |  | 1021 | CONSTRUCTION OF TWO LANE WITH PAVED SHOULDER OF SELLING-DULTE SECTION OF NH-06 (PKG-III) | NHIDCL | N24001281 | 3-2020 | 7/2022 | N.A. | 10/2024 | 292.24 |  | 331.17 | 294.6 | 93.2
May 2025 |  |  | 1022 | DULTE- KWALKULH - CHAMPAI PKG.2 | NHIDCL | N24001356 | 3-2021 | 12/2022 | Apr-2024 | 4/2024 | 233.25 |  | 233.25 | 172.09 | 100
May 2025 |  |  | 1023 | TLABUNG - LUNGLEI PKG-A | NHIDCL | N24001358 | 3-2021 | 12/2022 | N.A. | 3/2026 | 698.44 |  | 698.45 | 496.84 | 59.4
May 2025 |  |  | 1024 | TLABUNG - LUNGLEI PKG-B | NHIDCL | N24001359 | 3-2021 | 1/2023 | N.A. | 3/2026 | 740.58 |  | 740.58 | 364.34 | 57.4
May 2025 |  |  | 1025 | KEIFANG - TUVAI PKG-1 | NHIDCL | N24001440 | 9-2021 | 5/2023 | N.A. | 5/2024 | 492.94 |  | 492.94 | 365.86 | 90.5
May 2025 |  |  | 1026 | UP-GRADATION TO 2-LANE WITH PAVED SHOULDERS OF NGOPA - PAWLRANG SECTION OF NH 102B OF AIZAWL - IMPHA | NHIDCL | N24001975 | 9-2021 | 2/2025 | N.A. | 12/2025 | 523.78 |  | 523.78 | 366.81 | 80.51
May 2025 |  |  | 1027 | KEIFANG - TUVAI PKG-3 | NHIDCL | N24002027 | 12-2021 | 2/2025 | N.A. | 12/2025 | 500.88 |  | 500.88 | 263.48 | 68.8
May 2025 |  |  | 1028 | ZORINPUI- HMAWNGBU-LONGMASU (NH- 502A) | NHIDCL | N24002204 | 2-2023 | 12/2026 | N.A. | 12/2026 | 781.85 |  | 781.85 | 33.56 | 3
May 2025 |  | COAL | 1029 | NILJAI EXPANSION (DEEP) OC (3.5 MTY) | WCL | N06000154 | 8-2016 | 3/2022 | Mar-2025 | 3/2025 | 319.76 | 319.76 | 319.76 | 183.67 | 98
May 2025 |  | COAL | 1030 | BINA KAKRI AMALGAMATION OCP 14 MTPA | NCL | N06000192 | 8-2020 | 3/2024 | N.A. | 3/2027 | 836.42 |  | 836.42 | 769.27 | 85.95
May 2025 |  | DPIIT | 1031 | NATIONAL INDUSTRIAL CORRIDOR PROJECT | DMIC FOR DPIIT | N40000001 | 9-2011 | 3/2027 | Mar-2032 | 3/2032 | 20084 | 26684 | 26684 | 11262.06 | 50.99
May 2025 |  | DPIIT | 1032 | KOCHI-KOOTTANAD-BANGALORE- MANGALORE PIPELINE PHASE-II | GAIL | N16000285 | 6-2009 | 12/2012 | Dec-2025 | 12/2025 | 2915 | 5909 | 5909 | 4294.8 | 94
May 2025 |  | DPIIT | 1033 | SRIKAKULAM ANGUL PIPELINE PROJECT | GAIL | N16000388 | 9-2019 | 7/2022 | Jun-2025 | 12/2025 | 2658.34 |  | 2658.34 | 2173.3 | 94.4
May 2025 |  |  | 1034 | DHAMRA HALDIA PIPELINE PROJECT | GAIL | N16000391 | 3-2020 | 11/2022 | Dec-2025 | 12/2025 | 1030.65 |  | 1030.65 | 835.9 | 86.5
May 2025 |  |  | 1035 | MUMBAI NAGPUR JHARSUGUDA PIPELINE PROJECT | GAIL | N16000398 | 6-2020 | 5/2023 | Jun-2025 | 9/2025 | 7844.25 |  | 7844.25 | 6349.9 | 94.5
May 2025 |  |  | 1036 | CGD PROJECT AT NAWADA AND KODERMA DISTRICTS | IOCL | N16000426 | 6-2019 | 12/2029 | Mar-2030 | 3/2030 | 169 |  | 169 | 71 | 27.2
May 2025 |  |  | 1037 | NORTH EAST GAS GRID | IGGL | N16000439 | 11-2020 | 3/2024 | Jul-2025 | 3/2027 | 9265 | 9265 | 9265 | 6270.19 | 84.51
May 2025 |  |  | 1038 | GURDASPUR JAMMU PIPELINE | GAIL | N16000531 | 7-2023 | 7/2026 | Jul-2026 | 7/2026 | 521.92 | 521.92 | 521.92 | 133.3 | 34.9
May 2025 |  |  | 1039 | COMPREHENSIVE SCHEME FOR THE STRENGHTENING OF THE TRANSMISSION AND DISTRIBUTION SYSTEM IN A P | PGCIL | N18000249 | 12-2014 | 12/2018 | Mar-2025 | 3/2027 | 4754.42 | 9129.32 | 9129.32 | 7602.44 | 81.5
May 2025 |  |  | 1040 | NORTH EASTERN REGION POWER SYSTEM IMPROVEMENT PROJECT (NERPSIP) FOR SIX (6) STATES | PGCIL | N18000250 | 12-2014 | 12/2018 | Mar-2025 | 9/2025 | 5111.33 | 6700 | 6700 | 5276.39 | 95.9
May 2025 |  |  | 1041 | TS FOR EVACUATION OF POWER FROM PAKALDUL HEP IN CHENAB VALLEY HEPS - LTA SYSTEM | PGCIL | N18000328 | 2-2022 | 4/2025 | N.A. | 6/2025 | 318.12 |  | 318.12 | 169.75 | 98
May 2025 |  |  | 1042 | TRANSMISSION SYSTEM STRENGTHENING FOR SRINAGAR-LEH TRANSMISSION SYSTEM | PGCIL | N18000330 | 3-2022 | 12/2024 | N.A. | 7/2025 | 288.71 |  | 288.71 | 149.79 | 48
May 2025 |  |  | 1043 | TRANSMISSION SYSTEM STRENGTHENING SCHEME FOR EVACUATION OF POWER FROM SOLAR ENERGY ZONES IN RAJASTHA | PGCIL | N18000331 | 2-2022 | 9/2023 | N.A. | 7/2025 | 359.47 |  | 359.47 | 319.16 | 90
May 2025 |  |  | 1044 | TRANSMISSION SYSTEM STRENGTHENING SCHEME FOR EVACUATION OF POWER FROM SOLAR ENERGY ZONES IN RAJASTHA | PGCIL | N18000332 | 5-2022 | 11/2023 | N.A. | 8/2025 | 1666 | 2218 | 2218 | 1511.62 | 92.7
May 2025 |  |  | 1045 | TRANSMISSION NETWORK EXPANSION IN GUJARAT TO INCREASE ATC FROM ISTS: PART B | PGCIL | N18000337 | 7-2022 | 6/2023 | N.A. | 9/2025 | 4546.26 |  | 4546.26 | 3969.34 | 92
May 2025 |  |  | 1046 | SYSTEM STRENGTHENING SCHEME FOR EASTERN AND NORTH EASTERN REGION | PGCIL | N18000343 | 10-2022 | 10/2025 | N.A. | 6/2025 | 307.87 |  | 307.87 | 234.9 | 99.9
May 2025 |  |  | 1047 | TRANSMISSION SYSTEM FOR KURNOOL WIND ENERGY ZONE SOLAR ENERGY ZONE (AP) PART-A PART B | PGCIL | N18000352 | 3-2023 | 11/2024 | N.A. | 8/2025 | 3546.94 |  | 3546.94 | 2759 | 97
May 2025 |  |  | 1048 | ER WR TRANSMISSION LIMITED | PGCIL | N18000353 | 3-2023 | 3/2025 | N.A. | 6/2025 | 281.16 |  | 281.16 | 217.88 | 98.8
May 2025 |  |  | 1049 | NANGALDAM-TALWARA(NL),NR | NR | 220100188 | 3-1981 | 12/2025 | Jan-2027 | 6/2027 | 2018 | 603 | 2017.96 | 1604.43 | 75
May 2025 |  |  | 1050 | LALITPUR-SATNA-REWA-SINGRULI NL, | NCR | WCR | 9-1998 | 3/2027 | N.A. | 3/2025 | 8913.94 | 63.57 | 8248.5 | 2500.34 | 43
May 2025 |  |  | 1051 | CHHAPRA-BALLIA UP | NER | N22000134 | 3-2013 | 2/2025 | N.A. | 12/2025 | 941.05 | 954 | 1045.82 | 1004.58 | 95.5
May 2025 |  |  | 1052 | CHOTTAUDEPUR-DHAR(NL) | WR | N22000138 | 4-2007 | 12/2026 | Dec-2027 | 12/2027 | 1793.65 | 1793.63 | 1793.63 | 1626.42 | 59
May 2025 |  |  | 1053 | DAHOD-INDORE VIA SARDARPUR, JHABUA AND DHAR (NL) | WR | N22000139 | 4-2007 | 2/2027 | Feb-2027 | 2/2027 | 1942 | 1873.1 | 2873.11 | 2971.25 | 59
May 2025 |  |  | 1054 | GWALIOR-SEOPURKALA WITH EXTENSION TO KOTA (GC) | NCR | N22000148 | 4-2011 | 3/2025 | N.A. | 12/2024 | 2912.96 |  | 3845.6 | 1024.32
May 2025 |  |  | 1055 | DHOLPUR-SIRMUTTRA WITH EXTENSION TO GANGAPURCITY AND MOHARI-TANTPUR AND TANPUR-BANSI PAHARPUR | NCR | N22000158 | 4-2010 | 2/2019 | N.A. | 12/2026 | 746.83 |  | 746.83 | 391.89 | 39
May 2025 |  |  | 1056 | NEW BG LINE FROM BALURGHAT TO HILLY NFR | NFR | N22000206 | 4-2010 | 3/2027 | N.A. | 3/2027 | 1208.67 |  | 1181.57 | 418.79 | 8
May 2025 |  |  | 1057 | NEW BG LINE FROM JAGBANI TO BIRATNAGAR | NFR | N22000207 | 4-2010 | 3/2022 | Dec-2026 | 12/2026 | 401.65 | 485.96 | 485.96 | 361.33 | 86
May 2025 |  |  | 1058 | MURKONGSELEK-PASIGHAT NL | NFR | N22000208 | 4-2011 | 3/2025 | N.A. | 2/2026 | 435.06 |  | 1249.35 | 795.68 | 53.5
May 2025 |  |  | 1059 | PIRPAINTI-JASIDIH | ER | N22000219 | 4-2013 | 3/2028 | Mar-2028 | 3/2028 | 2555.03 |  | 2610.84 | 1129.76 | 45
May 2025 |  |  | 1060 | KAZIPET-VIJAYAWADA 3RD LINE WITH ELECTRIFICATION | SCR | N22000261 | 4-2012 | 2/2025 | N.A. | 3/2025 | 1953 |  | 1952.68 | 1798.38
May 2025 |  |  | 1061 | DEOBAND (MUZAFFARNAGAR)- ROORKEE NL | NR | N22000274 | 4-2007 | 3/2024 | N.A. | 3/2025 | 1053.23 |  | 1053 | 588.8 | 99
May 2025 |  |  | 1062 | RAYADURGA-TUMKUR NL | SWR | N22000279 | 4-2007 | 9/2015 | N.A. | 2/2028 | 2495.59 | 2495.86 | 2495.86 | 1653.85 | 65
May 2025 |  |  | 1063 | HOTGI-KUDGI-GADAG | SWR | N22000333 | 3-2015 | 12/2024 | N.A. | 2/2026 | 1877.81 | 1877.81 | 2458.87 | 2539.04 | 89
May 2025 |  |  | 1064 | KAZIPET-BALHRSHA | SCR | N22000367 | 4-2015 | 1/2025 | N.A. | 1/2025 | 2594.59 |  | 2909 | 2797.55 | 75
May 2025 |  |  | 1065 | MUMBAI AHMEDABAD HIGH SPEED RAIL PROJECT | NHSRCL | N22000463 | 12-2015 | 8/2027 | N.A. | 8/2027 | 108000 |  | 108000 | 76441 | 52
May 2025 |  |  | 1066 | WESTERN DEDICATED FREIGHT CORRIDOR | DFCC | N22000464 | 11-2007 | 3/2022 | N.A. | 3/2020 | 51101 | 51101 | 51101 | 47476 | 83
May 2025 |  |  | 1067 | CHANDIGARH-BADDI | NR | N22000467 | 4-2007 | 6/2025 | Dec-2026 | 12/2026 | 1540.13 | 1540.14 | 1540.14 | 941.19 | 29
May 2025 |  |  | 1068 | NARAYANGARH TO BHADRAK 3RD LINE | 155 KM | SER | 3-2019 | 12/2024 | N.A. | 6/2026 | 2400 |  | 1866.31 | 2048.31 | 60
May 2025 |  |  | 1069 | VARANASI-AURANGABAD KM.786 TO KM.978.40 | NHAI | N24000182 | 9-2011 | 3/2014 | N.A. | 6/2025 | 2848 |  | 3241.56 | 3901.66 | 90.02
May 2025 |  |  | 1070 | 4/6L OF SPUR TO HARIDWAR (GREENFIELD) FROM KM. 0.000 TO KM. 49.000 | NHAI | N24001628 | 11-2021 | 2/2025 | Aug-2025 | 8/2025 | 2155.95 |  | 2155.95 | 1359.81 | 67.42
May 2025 |  |  | 1071 | 6L WITH ACCESS CONTROL PROVISION SAHARANPUR BYPASS TO GANESHPUR SECTION FROM 13.89 KM TO 41.820 KM O | NHAI | N24001629 | 4-2022 | 11/2024 | Jun-2025 | 6/2025 | 796.65 |  | 796.65 | 432.84 | 87.5
May 2025 |  | SHIPPING AND PORTS | 1072 | JAL MARG VIKAS PROJECT | IWAI | N25000072 | 1-2018 | 3/2023 | Dec-2025 | 12/2025 | 5369.18 | 5061.15 | 5061.15 | 3441.55 | 68.86
May 2025 |  | TELECOMMUNICATIONS | 1073 | PHASE-I OF CONSOLIDATION OF EXISTING CDR DATA CENTERS AND NIB-P3 DATA CENTERS WITH STATE OF THE ART | BSNL | N26000114 | 3-2020 | 6/2021 | Nov-2021 | 12/2025 | 461.42 | 461.42 | 461.42 | 166.02 | 81
May 2025 |  | TELECOMMUNICATIONS | 1074 | SUPER EDGE ROUTERS FOR BSNL INTERNET PROTOCOL - MULTI PROTOCOL LEBEL SWITCHING (IPMPLS) NETWORK and | BSNL | N26000115 | 3-2023 | 3/2024 | Jul-2024 | 3/2025 | 239.6 |  | 239.6 | 179.43 | 100
May 2025 |  | TELECOMMUNICATIONS | 1075 | MPLS-IP BASED ACCESS AND AGGREGATION NETWORK (MAAN) IN BSNL ALONG WITH TEST AND MEASURING EQUIPMENT | BSNL | N26000116 | 5-2023 | 8/2024 | Nov-2024 | 6/2025 | 645.13 |  | 645.13 | 346.69 | 89.15
May 2025 |  | TELECOMMUNICATIONS | 1076 | PLANNIN ENGINEERING SUPPLY INSTALLATION TESTING COMMISSIONING INTEGARTION and ANNUAL MAINTENANCE OF | BSNL | N26000117 | 6-2023 | 6/2025 | N.A. | 6/2025 | 24556.35 | 24544.55 | 24544.55 | 8087.14 | 94.09
May 2025 |  | TELECOMMUNICATIONS | 1077 | OPTICAL TRANSPORT NETWORK (OTN) PH- 4 IN BSNL | BSNL | N26000118 | 2-2024 | 8/2025 | N.A. | 8/2025 | 810.99 |  | 810.99 | 635.37 | 100
May 2025 |  | URBAN DEVELOPMENT | 1078 | DELHI GHAZIABAD MEERUT RRTS CORRIDOR | NCRTC | N28000134 | 3-2019 | 6/2025 | N.A. | 6/2025 | 30274 |  | 30274 | 25673.23 | 86.3
May 2025 |  | PETROLEUM | 1079 | AUGMENTATION OF DIMAPUR DEPOT, DIMAPUR | IOCL | N16000529 | 8-2023 | 11/2027 | N.A. | 11/2027 | 227.62 |  | 227.62 | 6.12 | 18
May 2025 |  | RAILWAYS | 1080 | NEW LINE FROM DIMAPUR TO ZUBZA(KOHIMA) NATIONAL PROJECT | NEFR | NFR | 4-2006 | 3/2026 | N.A. | 12/2029 | 6663.2 | 6663.2 | 6663.2 | 4789.15 | 73
May 2025 |  |  | 1081 | FOUR LANING OF DIMAPUR KOHIMA ROAD FROM DESIGN KM 123.840 TO KM 138.775 (EXISTING KM 124.100 TO KM 1 | NHIDCL | N24000686 | 3-2016 | 9/2019 | Nov-2022 | 5/2025 | 373.07 | 534.41 | 534.41 | 382.5 | 99.81
May 2025 |  |  | 1082 | FOUR LANING OF EXISTING DIMAPUR KOHIMA ROAD FROM DESIGN KM 152.490 TO KM 166.700 (EXISTING KM 156.00 | NHIDCL | N24000688 | 3-2016 | 8/2022 | Sep-2025 | 9/2025 | 429.52 | 794.74 | 794.74 | 321.4 | 91.49
May 2025 |  |  | 1083 | (I) CONSTRUCTION OF FOUR/SIX LANING FROM KM 132.375 TO KM 158.058 (TOTAL NEW ALIGNMENT LENGTH OF 20. | NHIDCL | N24000752 | 2-2017 | 9/2020 | Feb-2023 | 4/2025 | 387 | 688.12 | 688.12 | 392.01 | 100
May 2025 |  |  | 1084 | (II) CONSTRUCTION OF DIMAPUR BYPASS (ASSAM PORTION) OF 4/6 LANE PAVEMENT ON EPC BASIS FROM EXISTING | NHIDCL | N24000753 | 3-2018 | 11/2022 | Aug-2024 | 4/2025 | 500.09 | 698.81 | 698.81 | 393.53 | 100
May 2025 |  |  | 1085 | CONSTRUCTION OF TWO LANE WITH HARD SHOULDERS OF MERANGKONG-TAMLU- MON ROAD FROM EXISTING KM 20.456 TO | NHIDCL | N24000763 | 3-2018 | 12/2021 | Aug-2022 | 8/2025 | 215.79 |  | 215.79 | 130.2 | 79.58
May 2025 |  |  | 1086 | CONSTRUCTION OF TWO LANE WITH HARD SHOULDERS OF MERANGKONG-TAMLU- MON ROAD FROM EXISTING KM 60.345 TO | NHIDCL | N24000765 | 3-2018 | 9/2018 | Jun-2023 | 9/2025 | 323.98 |  | 323.98 | 119.94 | 59.68
May 2025 |  |  | 1087 | CONSTRUCTION OF 2-LANE WITH PAVED SHOULDER OF KOHIMA-BYPASS ROAD FROM DESIGN KM10.500 TO 21.00KM [D | NHIDCL | N24001255 | 9-2020 | 10/2022 | Sep-2024 | 6/2026 | 277.44 |  | 277.44 | 168.88 | 67.81
May 2025 |  |  | 1088 | CONSTRUCTION OF 2-LANE WITH PAVED SHOULDER OF KOHIMA-BYPASS ROAD FROM DESIGN KM21.0 TO KM32.0 [DESIG | NHIDCL | N24001257 | 8-2020 | 10/2022 | Jun-2025 | 12/2025 | 159.85 | 342.29 | 159.85 | 103.95 | 29.9
May 2025 |  |  | 1089 | CONSTRUCTION OF 2-LANE WITH PAVED SHOULDER OF KOHIMA-BYPASS ROAD FROM DSIGN KM32.0 TO KM43.454 [DES | NHIDCL | N24001258 | 8-2020 | 4/2022 | Apr-2023 | 8/2025 | 202.36 |  | 202.36 | 75.39 | 31.02
May 2025 |  |  | 1090 | 2 LANING OF KOHIMA - JESSAMI SECTION | PACKAGE II | NHIDCL | 3-2020 | 6/2022 | N.A. | 1/2026 | 355.79 |  | 355.79 | 119.2 | 65.06
May 2025 |  |  | 1091 | 2-LANING OF CHANGTONGYA TO LONGLENG ROAD OF NH-702 (PKG-I) | NHIDCL | N24001286 | 3-2020 | 6/2022 | Oct-2022 | 6/2023 | 278.95 |  | 278.95 | 166.29 | 100
May 2025 |  |  | 1092 | 2 LANING OF KOHIMA - JESSAMI SECTION | PACKAGE V | NHIDCL | 4-2020 | 12/2021 | Nov-2025 | 11/2025 | 330.8 |  | 330.8 | 171.89 | 92.44
May 2025 |  |  | 1093 | CONSTRUCTION OF 2-LANE WITH PAVED SHOULDER OF KOHIMA-BYPASS ROAD FROM DESIGN KM 0.00 TO KM 10.500 [D | NHIDCL | N24001288 | 8-2020 | 4/2022 | Nov-2026 | 11/2026 | 232.29 | 350.88 | 232.29 | 70.9 | 14.7
May 2025 |  |  | 1094 | PEREN-DIMAPUR SECTION PKG-2 | NHIDCL | N24001406 | 7-2021 | 3/2023 | Sep-2025 | 9/2025 | 258.52 |  | 258.52 | 89.46 | 79.7
May 2025 |  |  | 1095 | MERANGKONG-TAMLU-MON (MTM) PKG-5 | NHIDCL | N24001438 | 7-2021 | 12/2023 | N.A. | 9/2025 | 161.73 |  | 161.73 | 62.08 | 67.82
May 2025 |  |  | 1096 | WIDENING OF EXISTING SINGLE LANE / INTERMEDIATE LANE ROAD TO 2 LANE FROM KM 101 TO KM 125 OF NH 61 I | MoRTH | N24001465 | 6-2020 | 9/2024 | Jun-2026 | 6/2026 | 252.19 |  | 252.19 | 14.25 | 17.9
May 2025 |  |  | 1097 | WIDENING TO EXISTING SINGLE LANE /INTERMEDIATE LANE TO 2 LANE FROM KM185.00 TO KM 220.00 OF NH-61 (N | MoRTH | N24001466 | 3-2021 | 7/2024 | Dec-2025 | 12/2025 | 297.24 |  | 297.24 | 137.76 | 79.47
May 2025 |  |  | 1098 | WIDENING TO EXISTING SINGRE/INTERMEDIATE RANE TO 2 LANE FROM KM 135 TO KM 147 AND FROM KM 156.00 TO | MoRTH | N24001467 | 3-2021 | 2/2024 | Mar-2025 | 3/2025 | 226.44 |  | 226.44 | 140.24 | 100
May 2025 |  |  | 1099 | WIDENING OF EXISTING SINGLE LANE ROAD TO INTERMEDIATE LANE ROAD FROM MOKOKCHUNG TO CHARE VIA DIKHU I | MoRTH | N24001855 | 2-2021 | 6/2025 | Sep-2025 | 9/2025 | 192.93 |  | 192.93 | 105.41 | 92.82
May 2025 |  |  | 1100 | PEREN-DIMAPUR PKG-3 | NHIDCL | N24001912 | 2-2021 | 6/2025 | N.A. | 12/2025 | 177.77 | 199.02 | 199.02 | 46.94 | 61.25
May 2025 |  |  | 1101 | WIDENING TO 2 LANE WITH HARD SHOULDER OF AKEGWO-AVANGKHU SECTION OF NH-202K FOR PACKAGE-I (DESIGN CH | NHIDCL | N24001976 | 12-2022 | 2/2026 | N.A. | 2/2026 | 430.24 |  | 430.24 | 100.51 | 54.28
May 2025 |  |  | 1102 | WIDENING TO 2 LANE WITH HARD SHOULDER OF AKEGWO-AVANGKHU SECTION OF NH-202K FOR PACKAGE-II (DESIGN C | NHIDCL | N24001977 | 12-2022 | 2/2026 | N.A. | 2/2026 | 442.54 |  | 442.54 | 50.6 | 26.58
May 2025 |  |  | 1103 | WIDENING TO 2 LANE WITH HARD SHOULDER OF AKEGWO-AVANGKHU SECTION OF NH-202K FOR PACKAGE-III (DESIGN | NHIDCL | N24001978 | 12-2022 | 2/2026 | N.A. | 2/2026 | 497.18 |  | 497.18 | 163.84 | 62.02
May 2025 |  |  | 1104 | BASUNDHARA (WEST) OC EXTN(7.00 MTY) | MCL | N06000112 | 5-2014 | 3/2019 | N.A. | 3/2028 | 479.15 |  | 479.15 | 267.2 | 63.04
May 2025 |  |  | 1105 | SIARMAL OCP (40.00MTY) | MCL | N06000113 | 2-2021 | 3/2029 | N.A. | 3/2029 | 5194.96 |  | 5194.96 | 3436.4 | 51.94
May 2025 |  |  | 1106 | INTEGRATED LAKHANPUR-BELPAHAR- LILARI OCP | MCL | N06000167 | 5-2018 | 3/2027 | N.A. | 3/2027 | 2434.75 |  | 2434.75 | 1760.96 | 60.87
May 2025 |  |  | 1107 | REORGANISATION OF BHARATPUR OCP EXPANSION | MCL | N06000171 | 11-2018 | 3/2029 | N.A. | 3/2029 | 2838.87 |  | 2838.87 | 1835.56 | 44.62
May 2025 |  |  | 1108 | NAINI COAL MINE | SCCL | N06000203 | 3-2020 | 3/2024 | N.A. | 3/2027 | 494.3 |  | 494.3 | 491.33 | 80
May 2025 |  |  | 1109 | GOPALJI-KANIHA OCP | MCL | N06000229 | 4-2022 | 3/2028 | N.A. | 3/2028 | 6107.87 |  | 6107.87 | 1703.67 | 17.39
May 2025 |  |  | 1110 | BALARAM EXPANSION OCP | MCL | N06000230 | 8-2020 | 3/2029 | N.A. | 3/2029 | 3504.21 |  | 3504.21 | 1024.91 | 50.17
May 2025 |  |  | 1111 | SUBHADRA OCP | MCL | N06000249 | 5-2021 | 3/2029 | Mar-2029 | 3/2029 | 1693.81 |  | 1693.81 | 1181.97 | 39.3
May 2025 |  |  | 1112 | NLC TALABIRA THERMAL POWER PROJECT | PHASE-1: 3 X 800 MW | NLC | 1-2024 | 5/2029 | Mar-2030 | 3/2030 | 27213 |  | 27213 | 1883.39 | 1.55
May 2025 |  |  | 1113 | RPR OF HINGULA EXPANSION OCP | MCL | N06000285 | 11-2022 | 3/2029 | N.A. | 3/2029 | 1561.85 |  | 1561.85 | 49.1 | 3.57
May 2025 |  |  | 1114 | BHUBANESWARI EXPANSION OCP | MCL | N06000286 | 3-2024 | 3/2031 | N.A. | 3/2031 | 5366.28 |  | 5366.28 | 3.95 | 8.33
May 2025 |  |  | 1115 | BALABHADRA OCP | MCL | N06000288 | 4-2023 | 3/2030 | N.A. | 3/2030 | 978.44 |  | 978.44 | 209.5 | 1.86
May 2025 |  |  | 1116 | INTEGRATED KULDA GARJANBAHAL OCP | MCL | N06000289 | 4-2023 | 3/2030 | N.A. | 3/2030 | 3563.5 |  | 3563.5 | 496.87 | 3.58
May 2025 |  | DEPARTMENT OF HIGHER EDUCATION | 1117 | INDIAN INSTITUTE OF SCIENCE EDUCATION AND RESEARCH BERHAMPUR | CPWD EDUCATION | N28000126 | 1-2019 | 3/2022 | N.A. | 10/2025 | 790.79 |  | 790.79 | 706.39 | 96
May 2025 |  | MINES | 1118 | 5TH STREAM ALUMINA REFINERY EXPANSION PROJECT | NALCO | N10000010 | 12-2014 | 4/2021 | Sep-2025 | 9/2025 | 4103 | 5677.4 | 5677.4 | 3799.56 | 73.74
May 2025 |  | MINES | 1119 | UTKAL D AND E COAL BLOCK | NALCO | N10000011 | 5-2016 | 1/2020 | Nov-2023 | 3/2024 | 534 |  | 1021.97 | 826.94 | 87.5
May 2025 |  | MINES | 1120 | CONVERSION OF FLAT BOTTOM SETTLERS AND WASHERS WITH A SINGLE TRAIN OF HRDS AND DCWS IN STREAMS 1 AND | NALCO | N10000012 | 12-2015 | 11/2020 | Sep-2025 | 8/2027 | 355 | 581 | 581 | 163.55 | 12.6
May 2025 |  | MINES | 1121 | SOURCING OF BAUXITE ARRANGEMENT FOR 5TH STREAM ALUMINA REFINERY FROM SOUTH BLOCK MINING LEASE OF PAN | NALCO | N10000013 | 11-2017 | 4/2021 | May-2026 | 5/2026 | 483 | 483 | 495 | 385.2 | 89.3
May 2025 |  | MINES | 1122 | POTTANGI BAUXITE MINES | NALCO | N10000016 | 5-2018 | 12/2024 | N.A. | 5/2025 | 1437 |  | 1381 | 650.05 | 51
May 2025 |  | MINES | 1123 | CONSTRUCTION OF RED MUD POND - II AT NALCO DAMANJODI ODISHA | NALCO | N10000017 | 9-2019 | 3/2023 | May-2024 | 5/2024 | 225.79 |  | 270.66 | 5 | 100
May 2025 |  | PETROLEUM | 1124 | INTEGRATED PARA XYLENE (PX) AND PURIFIED TEREPHTHALIC ACID (PTA) PROJECT AT PARADIP REFINERY | IOCL | N16000396 | 7-2020 | 1/2024 | Apr-2025 | 4/2026 | 13805 |  | 13805 | 7531.48 | 89.7
May 2025 |  | POWER | 1125 | EASTERN REGION EXPANSION SCHEME XXIX | PGCIL | N18000351 | 3-2023 | 11/2025 | N.A. | 6/2025 | 524.04 |  | 524.04 | 359.97 | 99
May 2025 |  | POWER | 1126 | TALCHER THERMAL POWER PROJECT STAGE III(2X660 MW) | NTPC | N18000364 | 8-2022 | 5/2027 | N.A. | 12/2027 | 11844 |  | 12539 | 3218.1 | 21.4
May 2025 |  | POWER | 1127 | KHURDA ROAD-BOLANGIR(NL)ECOR | ECOR | 220100284 | 4-1994 | 12/2026 | Dec-2026 | 12/2026 | 3550 | 3791.66 | 5089.37 | 4840.22 | 85
May 2025 |  | POWER | 1128 | TALCHER-BIMALAGARH(NL)(ECOR) | ECOR | 220100328 | 4-2005 | 3/2025 | N.A. | 3/2026 | 1928.1 |  | 1928.07 | 1726.15 | 40
May 2025 |  | POWER | 1129 | BHADRAK - NERGUNDI 3RD LINE | ECOR | N22000316 | 3-2013 | 11/2024 | Jan-2026 | 6/2026 | 1284.39 | 1284.39 | 1284.39 | 1288.97 | 80
May 2025 |  | POWER | 1130 | JAGADALPUR-KORAPUT DOUBLING | ECOR | N22000376 | 4-2015 | 3/2024 | N.A. | 3/2022 | 1547.38 |  | 1547.38 | 1291.3 | 93.6
May 2025 |  | POWER | 1131 | KORAPUT - SINGAPUR ROAD DOUBLING | ECOR | N22000379 | 4-2015 | 12/2027 | Mar-2026 | 3/2026 | 2362 | 2361.74 | 2361.74 | 1794.64 | 79
May 2025 |  | POWER | 1132 | JARAPADA - BUDHAPANK WITH FLY OVER AT TALCHER ROAD 3RD AND 4TH LINE | ECOR | N22000380 | 4-2015 | 3/2027 | N.A. | 8/2026 | 820.61 |  | 810.02 | 580.59
May 2025 |  | POWER | 1133 | BUDHAPANK - SALEGAON VIA RAJATGARH 3RD AND 4TH LINE. | ECOR | N22000381 | 4-2015 | 3/2026 | Nov-2025 | 11/2025 | 1172.92 |  | 2022.75 | 1949.32 | 80
May 2025 |  | POWER | 1134 | VIZIANAGARAM -SAMABALPUR 3RD LINE | RVNL | N22000409 | 1-1991 | 12/2026 | N.A. | 12/2026 | 4803.16 |  | 4803.16 | 4691.52
May 2025 |  | POWER | 1135 | JEYPORE MALKANGIRI NEW LINE | ECOR | N22000516 | 2-2018 | 7/2033 | N.A. | 7/2033 | 2344 |  | 642.69 | 220.78 | 90.1
May 2025 |  | POWER | 1136 | JEYPORE NABARANGPUR NEWLINE | ECOR | N22000517 | 7-2017 | 7/2028 | Dec-2029 | 12/2029 | 748 |  | 747.91 | 0
May 2025 |  |  | 1137 | TALCHER - ANGUL NEW LINE WITH Y CONNECTION AT TALCHER | ECOR | N22000518 | 7-2018 | 12/2026 | N.A. | 12/2026 | 278.96 | 495 | 494.62 | 29.5
May 2025 |  |  | 1138 | KODINGAMALI BAUXITE MINES TO SINGARAM RAILWAY STATION | ECOR | N22000519 | 8-2022 | 8/2027 | N.A. | 8/2027 | 190.9 |  | 190.9 | 10
May 2025 |  |  | 1139 | GANDHAMARDAN IRON ORE MINES TO GOALDIH STATION | ECOR | N22000520 | 9-2022 | 9/2027 | N.A. | 3/2028 | 189.93 |  | 189.93 | 14.04
May 2025 |  |  | 1140 | BRUNDAMAL-JHARSUGUDA- FLYOVER CONNECTION FOR JOINING DN LINE | ECOR | N22000521 | 12-2009 | 12/2026 | N.A. | 12/2026 | 296.51 |  | 297 | 171.98 | 10
May 2025 |  |  | 1141 | BAGHUAPAL FLY OVER (20 KM) | ECOR | N22000522 | 8-2019 | 8/2027 | Aug-2027 | 8/2027 | 183 | 257.97 | 257.97 | 0.83
May 2025 |  |  | 1142 | ROURKELA-BONDAMUNDA A-CABIN 5TH LINE (10 KM) (UMBRELLA WORK PB#57/2019- 20/NR) | SER | N22000571 | 9-2022 | 9/2026 | N.A. | 2/2026 | 209.75 |  | 244.99 | 76.22 | 30
May 2025 |  |  | 1143 | DEVELOPMENT OF FOUR LANNING OF ANGUL-SAMBALPUR SECTION OF NATIONAL HIGHWAY NH-42 (NEW NH-55 IN THE S | NHAI | N24000619 | 9-2016 | 8/2019 | N.A. | 6/2025 | 2510.04 |  | 2510.04 | 1181.34 | 99.38
May 2025 |  |  | 1144 | REHABILITATION AND UPGRADATION OF CUTTACK ANGUL SECTION OF NH-42 (NEW NH-55) TO 4 LANE (KM. 0+400 TO | NHAI | N24000715 | 12-2017 | 7/2020 | N.A. | 7/2025 | 686.65 | 565 | 686.65 | 574.26 | 97.8
May 2025 |  |  | 1145 | REHABILITATION AND UP-GRADATION OF EXISTING 2-LANE TO 4 LANE OF DUBURI (KM 388.376) TO CHANDIKHOLE ( | NHAI | N24000733 | 1-2018 | 8/2022 | N.A. | 12/2025 | 633.68 | 492.83 | 633.68 | 560.38 | 86
May 2025 |  |  | 1146 | REHABILITATION AND UP-GRADATION OF EXISTING 2-LANE TO FOUR LANE FROM TALCHAR TO END OF KAMAKHYANAG | NHAI | N24000734 | 1-2018 | 8/2021 | N.A. | 6/2025 | 614.48 | 503.3 | 757.12 | 664.48 | 100
May 2025 |  |  | 1147 | REHABILITATION AND UPGRADATION OF CUTTACK-ANGUL SECTION TO 4 LANE (KM 60.20) TO (KM 112.0) PKG II ON | NHAI | N24000736 | 1-2018 | 9/2020 | N.A. | 7/2025 | 686.65 | 504.09 | 1015.16 | 488.98 | 97.98
May 2025 |  |  | 1148 | REHABILITATION AND UPGRADATION OF SIX LANING OF BHADRAK BALESHWAR SECTION (KM 136.50) TO (KM 199.141 | NHAI | N24000738 | 1-2018 | 9/2021 | N.A. | 7/2025 | 999 | 1152.7 | 1152.7 | 540.1 | 82.01
May 2025 |  |  | 1149 | REHABILITATION AND UP-GRADATION TO 4- LANING OF RAJAMUNDA-BARKOTE SECTION OF NH-23 (NEW NH NO. 143) ( | NHAI | N24000739 | 1-2018 | 6/2021 | Jun-2025 | 6/2025 | 503.88 | 609.03 | 609.03 | 536.89 | 98.5
May 2025 |  |  | 1150 | WIDENING TO 2LPS FROM 0/0 TO 119/0 OF NH-157 IN THE STATE OF ODISHA. | MoRTH | N24000912 | 8-2016 | 2/2017 | N.A. | 12/2025 | 287.7 |  | 293.66 | 275.42 | 98.66
May 2025 |  |  | 1151 | WIDENING TO 2LPS FROM 239/9 TO 294/3 OF NH-57 (NAYAGARH TO KHURDA) IN THE STATE OF ODISHA | MoRTH | N24000914 | 12-2016 | 8/2018 | N.A. | 9/2025 | 223.5 |  | 223.5 | 220.5 | 92
May 2025 |  |  | 1152 | WIDENING TO 2LPS FROM 269/30 TO 328/20 OF NH-49 IN THE STATE OF ODISHA | MoRTH | N24000917 | 3-2018 | 8/2018 | N.A. | 6/2025 | 199.16 |  | 199.16 | 158.73 | 100
May 2025 |  |  | 1153 | BALANCE WORK OF PANIKOILI RIMULI SECTION OF NEW NH-20 FROM KM 0.00 TO KM. 163.000 | NHAI | N24001647 | 8-2020 | 3/2022 | N.A. | 6/2025 | 200 | 154.73 | 154.73 | 150.38 | 100
May 2025 |  |  | 1154 | 6L GREENFIELD KANDILI - ALURU SECTION OF NH-130-CD ROAD FROM KM 342+500 TO KM 365+033 (PACKAGE-OD-8 | NHAI | N24001665 | 12-2021 | 10/2024 | N.A. | 12/2025 | 1592 | 1592 | 1592 | 1083.78 | 78.13
May 2025 |  |  | 1155 | 6L GREENFIELD BARAJA - KANDILI SECTION OF NH- 130-CD ROAD FROM KM 338+500 TO KM 342+500 (PACKAGE-OD | NHAI | N24001666 | 12-2021 | 9/2024 | N.A. | 8/2025 | 714 | 714 | 714 | 580.51 | 94.92
May 2025 |  |  | 1156 | 6L GREENFIELD KALIAGURA ? BAUNSAGUAR SECTION OF NH-130-CD ROAD FROM KM 249+000 TO KM 293+000 (PACKAG | NHAI | N24001667 | 9-2021 | 5/2024 | N.A. | 12/2025 | 1734 | 1734 | 1734 | 1222.14 | 86
May 2025 |  |  | 1157 | 6L OF BADAKUMARI - KARKI SECTION FROM KM 179.000 TO KM 226.500 OF NH-130- CD (PACKAGE ? OD-3) | NHAI | N24001668 | 3-2021 | 4/2024 | N.A. | 11/2025 | 1249 |  | 1249 | 465.59 | 85.6
May 2025 |  |  | 1158 | 6L OF DHANARA - HATIBENA SECTION FROM KM 124.611 TO KM 146.50 OF NH-130- CD (PACKAGE ? OD-1) | NHAI | N24001669 | 2-2021 | 3/2024 | N.A. | 6/2025 | 586 |  | 586 | 240.33 | 88.9
May 2025 |  |  | 1159 | 6L OF KARKI ? KALIAGURA SECTION FROM KM 226.500 TO KM 249.000 OF NH-130-CD | PACKAGE ? OD-4 | NHAI | 2-2021 | 3/2024 | N.A. | 6/2025 | 593 |  | 593 | 282.15 | 94.46
May 2025 |  |  | 1160 | 6L OF HATIBENA - BADAKUMARI SECTION FROM KM 146.50 TO KM 179.00 OF NH-130- CD (PACKAGE ? OD-2) | NHAI | N24001671 | 2-2021 | 3/2024 | N.A. | 6/2025 | 925 |  | 925 | 460.47 | 97
May 2025 |  |  | 1161 | 6L GREENFIELD BAUNSAGUAR - BARAJA SECTION OF NH-130-CD ROAD FROM KM 293+000 TO KM 338+500 (PACKAGE ? | NHAI | N24001678 | 8-2021 | 6/2024 | N.A. | 12/2025 | 1460 | 1460 | 1460 | 978.88 | 91
May 2025 |  |  | 1162 | CONSTRUCTION OF ROAD FROM KM 0/0 TO 72/0 OF NH-26 SUCH AS 4 LANE FROM KM 0/0 TO 21/0 (BARGARH TO BAR | MoRTH | N24001857 | 6-2020 | 12/2023 | Aug-2025 | 8/2025 | 414.24 |  | 414.24 | 307.52 | 98
May 2025 |  |  | 1163 | WIDENING AND STRENGTHENING TO 2L+PS INCLUDING LA OF KANDARPUR-BALIKUDA FROM KM 277/500 TO 318/970 OF | MoRTH | N24001858 | 3-2022 | 6/2025 | N.A. | 12/2025 | 499.79 |  | 499.79 | 285.58 | 45
May 2025 |  |  | 1164 | CONSTRUCTION OF BYPASS ON NH-59 FROM KM 336/350 TO 349/910 (13.56 KM) NEAR BERHAMPUR TOWN INCLUDING | MoRTH | N24001859 | 3-2021 | 3/2024 | N.A. | 8/2025 | 196.94 |  | 196.94 | 71.55 | 56
May 2025 |  |  | 1165 | CONSTRUCTION OF BYPASS TO NAYAGARH TOWN FROM KM 235.469 TO 252.482 OF NH-57 INCLUDING LAND ACQUISITI | MoRTH | N24001860 | 1-2022 | 4/2025 | N.A. | 8/2025 | 300.33 |  | 300.33 | 203.81 | 70
May 2025 |  |  | 1166 | CONSTRUCTION OF BYPASS TO KHORDHA TOWN FROM KM 294/000 TO 300/300 ON NH- 57 INCLUDING LA IN THE STATE | MoRTH | N24001861 | 2-2022 | 11/2024 | Aug-2025 | 8/2025 | 157.49 |  | 157.49 | 72.57 | 54
May 2025 |  |  | 1167 | CONSTRUCTION OF BYPASS ROAD TO BALANGIR TOWN FROM KM 72/400 (DESING KM 0/0) TO KM 79/800 (DESIGN KM | MoRTH | N24001862 | 2-2022 | 10/2025 | Nov-2025 | 11/2025 | 238.78 |  | 238.78 | 50.39 | 35
May 2025 |  |  | 1168 | CONSTRUCTION OF 5 HL BRIDGES AT KM 379/000 (PANGAM), KM 439/400 (POTTERU), KM 444/237 (KONGURUKONDA) | MoRTH | N24001863 | 3-2021 | 6/2024 | Oct-2025 | 8/2025 | 154.05 |  | 154.05 | 47.47 | 30
May 2025 |  |  | 1169 | CONSTRUCTION OF FOUR LANE ROB AND ITS APPROACHES IN LIEU OF EXISTING LEVEL CROSSING NO. RV-71 AT KM | MoRTH | N24001864 | 11-2021 | 6/2025 | N.A. | 8/2025 | 154.49 |  | 154.49 | 59.92 | 45
May 2025 |  |  | 1170 | CONSTRUCTION OF 4 LANE ROB WITH APPROACHES IN LIEU OF LC NO. RV-172 AT KM 176.00 OF NH-201 (PRESENT | MoRTH | N24001865 | 12-2021 | 5/2025 | Aug-2025 | 8/2025 | 324.09 |  | 324.09 | 110.76 | 35
May 2025 |  |  | 1171 | REHABILITATION AND UP GRADATION FROM 4 TO 8 LANING OF CHANDIKHOLE PARADIP SECTION OF NH 53 FROM KM. | NHAI | N24002078 | 12-2023 | 12/2025 | N.A. | 12/2025 | 711 |  | 711 | 182.54 | 52.3
May 2025 |  |  | 1172 | REHABILITATION AND UP GRADATION FROM 4 TO 8 LANING OF CHANDIKHOLE PARADIP SECTION OF NH 53 FROM KM | NHAI | N24002079 | 12-2023 | 12/2025 | N.A. | 12/2025 | 742.25 |  | 742.25 | 223.42 | 52.89
May 2025 |  |  | 1173 | REHABILITATION AND UP GRADATION FROM 4 TO 8 LANING OF CHANDIKHOLE PARADIP SECTION OF NH 53 FROM KM | NHAI | N24002080 | 12-2023 | 12/2025 | N.A. | 12/2025 | 762.75 |  | 762.75 | 228.86 | 52.78
May 2025 |  |  | 1174 | 3L MAJOR BRIDGE OVER RIVER BRAHMANI AT KM. 401.250 (DUBURI CHANDIKHOLE SECTION) OF NH 200 (NEW NH 5 | NHAI | N24002081 | 8-2022 | 1/2025 | N.A. | 12/2026 | 153.61 |  | 153.61 | 14.22 | 34.49
May 2025 |  |  | 1175 | WIDENING AND STRENGTHENLNG TO 2L+PS FROM KM 0.000 TO 40.000 (DHAUGAON- PODAMARI SECTION) OF NH 326 I | MoRTH | N24002135 | 3-2022 | 2/2026 | N.A. | 2/2026 | 186.52 |  | 186.52 | 45.93 | 35
May 2025 |  |  | 1176 | WIDENING AND STRENGTHENING TO 4L+PS/2L+PS FROM KM 0.000 TO 35.800 (KUAKHIA - MANGALPUR SECTION) OF N | MoRTH | N24002136 | 3-2022 | 2/2026 | N.A. | 2/2026 | 636.1 |  | 636.1 | 264.02 | 36
May 2025 |  |  | 1177 | REHABILITATION AND UP GRADATION FROM 4 TO 8 LANING OF CHANDIKHOLE ? PARADIP SECTION OF NH-53 (OLD NH | NHAI | N24002219 | 3-2024 | 10/2026 | N.A. | 10/2026 | 882.45 |  | 882.45 | 81.9 | 12.73
May 2025 |  | STEEL | 1178 | REBUILDING OF COKE OVEN BATTERY-2 ALONGWITH AUGMENTATION OF COKE HANDLING AND GAS HANDLING FACILITY | SAIL | N12000122 | 11-2020 | 5/2023 | Mar-2025 | 3/2025 | 377.18 |  | 377.18 | 434.9
May 2025 |  | STEEL | 1179 | INSTALLATION OF 4TH SLAB CASTER ALONG WITH ITS AUXILIARIES AND A NEW LADLE FURNACE IN SMS-II AT RSP | SAIL | N12000125 | 1-2022 | 5/2025 | N.A. | 7/2025 | 970.18 |  | 970.18 | 689.07 | 93.76
May 2025 |  | DEPARTMENT OF HIGHER EDUCATION | 1180 | CONSTRUCTION OF PERMANENT CAMPUS OF INDIAN INSTITUTE OF MANAGEMENT (IIM) AMRITSAR, PUNJAB. | CPWD EDUCATION | N28000142 | 10-2019 | 5/2022 | N.A. | 7/2025 | 348.24 |  | 348.24 | 237.84 | 90.2
May 2025 |  | PETROLEUM | 1181 | SECOND GENERATION ETHANOL BIOREFINERY PROJECT, BATHINDA, PUNJAB | HPCL | N16000402 | 5-2020 | 2/2023 | Sep-2024 | 12/2025 | 1421.46 |  | 1421.46 | 1156.45 | 95.62
May 2025 |  | PETROLEUM | 1182 | BHATINDA SANGRUR PIPELINE | HPCL | N16000440 | 11-2021 | 5/2024 | Feb-2025 | 7/2025 | 367 | 397 | 397 | 329.81 | 90.3
May 2025 |  | PETROLEUM | 1183 | CGD PROJECT AT PATHANKOT DISTRICT | IOCL | N16000488 | 3-2022 | 3/2030 | Sep-2033 | 9/2033 | 151 |  | 151 | 8.73 | 2
May 2025 |  | RAILWAYS | 1184 | 235 | NR | N22000589 | 9-2020 | 3/2025 | N.A. | 7/2025 | 235 |  | 235 | 5.12 | 98
May 2025 |  | RAILWAYS | 1185 | FEROZPUR - PATTI (25.72 KM) | NR | N22000614 | 4-2017 | 3/2027 | N.A. | 3/2027 | 299.74 |  | 781 | 0
May 2025 |  | RAILWAYS | 1186 | WIDENING AND PAVED SHOULDER OF TOHANA (IN HARYANA) PUNJAB/HARYANA BORDER TO MOONAK-JAKHAL-BUDHLADA | MoRTH | N24000907 | 3-2018 | 8/2020 | N.A. | 6/2025 | 293.1 |  | 315 | 318.24 | 99.75
May 2025 |  | RAILWAYS | 1187 | JALANDHAR-HOSHIARPUR SECTION OF NH- 70 [NEW NH NO. 3] FROM EXISTING KM 11.400 TO KM 49.200 | MoRTH | N24000909 | 10-2017 | 10/2019 | N.A. | 12/2025 | 1069.59 |  | 1069.59 | 739.08 | 44
May 2025 |  | RAILWAYS | 1188 | REHABILITATION AND UP GRADATION TO 2 LANE WITH PAVED SHOULDER OF NH-703A FROM MAKHU (DESIGN CH 0 000 | MoRTH | N24000910 | 3-2018 | 11/2020 | N.A. | 6/2026 | 170.57 |  | 150 | 135 | 79
May 2025 |  | RAILWAYS | 1189 | DELHI-AMRITSAR-KATRA EXPRESSWAY FROM JUNCTION WITH PATIALA-BATHINDA ROAD (NH-7) NEAR BHAWANIGARH TO | NHAI | N24001415 | 12-2020 | 4/2024 | Jul-2024 | 7/2024 | 881 |  | 881 | 932.64 | 90.64
May 2025 |  | RAILWAYS | 1190 | DELHI-AMRITSAR-KATRA EXPRESSWAY FROM JUNCTION WITH LUDHIANA- MALERKOTLA ROAD (SH-11) NEAR BHOGIWAL VI | NHAI | N24001416 | 12-2020 | 1/2024 | Mar-2025 | 3/2025 | 989.66 |  | 989.66 | 324.77 | 31.08
May 2025 |  |  | 1191 | DELHI-AMRITSAR-KATRA EXPRESSWAY FROM JUNCTION WITH LUDHIANA-MOGA ROAD (NH-5) NEAR MULLANPUR DAKHA TO | NHAI | N24001417 | 12-2020 | 4/2024 | Sep-2025 | 9/2025 | 1234.4 |  | 1234.4 | 792.35 | 63.09
May 2025 |  |  | 1192 | DELHI-AMRITSAR-KATRA EXPRESSWAY FROM CH.KM 303+900 TO KM 319+400 OF MAIN EXPRESSWAY) AND AMRITSAR CO | NHAI | N24001418 | 12-2020 | 4/2024 | Sep-2025 | 9/2025 | 1094.46 |  | 1094.46 | 802.93 | 62.99
May 2025 |  |  | 1193 | DELHI-AMRITSAR-KATRA EXPRESSWAY (PHASE-I PKG-XI) FROM JUNCTION WITH JALANDHAR - KAPURTHALA ROAD (NH- | NHAI | N24001419 | 2-2021 | 4/2024 | Nov-2024 | 11/2024 | 1269.96 |  | 1269.96 | 585.86 | 43.45
May 2025 |  |  | 1194 | DELHI-AMRITSAR-KATRA EXPRESSWAY (PHASE-I PKG-XII) FROM JUNCTION WITH AMRITSAR-MEHTA-SRIHARGOBINDPUR- | NHAI | N24001420 | 2-2021 | 4/2024 | Dec-2025 | 12/2025 | 853.66 |  | 853.66 | 132.99 | 15.33
May 2025 |  |  | 1195 | 4/6L GREENFIELD LUDHIANA RUPNAGAR HIGHWAY FROM JUNCTION WITH NE 05 VILLAGR NEAR TO MANEWAL (LUDHIANA | NHAI | N24001630 | 7-2021 | 2/2025 | N.A. | 2/2025 | 1501.02 |  | 1501.02 | 237 | 73
May 2025 |  |  | 1196 | 6L OF IT CITY CHOWK TO KURALI CHANDIGARH ROAD | NHAI | N24001631 | 3-2021 | 10/2024 | N.A. | 10/2024 | 1525.31 |  | 1525.31 | 245 | 88.7
May 2025 |  |  | 1197 | CONSTRUCTION OF FOUR LANE GREENFIELD PROJECT OF DELHI- AMRITSAR-KATRA EXPRESSWAY (PHASE-I PKG-V) FROM | NHAI | N24001632 | 1-2021 | 5/2024 | Jun-2025 | 8/2025 | 1741.86 | 2281.02 | 2281.02 | 1278 | 96
May 2025 |  |  | 1198 | CONSTRUCTION OF FOUR/SIX LANE GREENFIELD LUDHIANA ? RUPNAGAR NATIONAL HIGHWAY NO. NH-205K UNDER BHAR | NHAI | N24001636 | 5-2021 | 12/2024 | Oct-2026 | 10/2026 | 1368.91 | 1368.91 | 1368.91 | 163.58 | 15.31
May 2025 |  |  | 1199 | DEVELOPMENT OF 6 LANE JALANDHAR BYPASS FROM KAHLWAN NATIONAL HIGHWAY 03 DESIGN KM 0.00 ENDING AT K | NHAI | N24001637 | 3-2021 | 1/2025 | N.A. | 1/2025 | 1754.84 |  | 1754.84 | 1082.62 | 35.08
May 2025 |  |  | 1200 | 4L GREENFIELD A. MALOUT BYPASS FROM CH. KM 44.500 TO CH. KM 35.500 ON NH-07 AND CH. KM 0.000 TO KM 6 | NHAI | N24001638 | 11-2021 | 7/2024 | Aug-2025 | 8/2025 | 646.42 | 646.42 | 646.42 | 481.67 | 96
May 2025 |  |  | 1201 | FOUR LANING OF MOGA TO BAJAKHANA LAMBWALI SECTION OF 105B GREENFIELD ALIGNMENT FROM DESIGN CHAINAGE | NHAI | N24001639 | 5-2020 | 12/2024 | Aug-2025 | 8/2025 | 864.23 | 864.23 | 864.23 | 434.88 | 63
May 2025 |  |  | 1202 | 6L AMRITSAR BATHINDA GREENFIELD SECTION FROM VILLAGE TIBA ON NE 5A TO JN. WITH MOGA JALANDHAR ROAD N | NHAI | N24001640 | 3-2021 | 11/2024 | N.A. | 11/2024 | 1229.38 |  | 1229.38 | 729.77 | 47.8
May 2025 |  |  | 1203 | DELHI AMRITSAR KATRA EXPRESSWAY PHASE I SPUR III FROM JUNCTION WITH AMRITSAR JALANDHAR ROAD NH3 NEAR | NHAI | N24001641 | 3-2021 | 10/2024 | Dec-2025 | 12/2025 | 1641.75 |  | 1641.75 | 188.55 | 29.45
May 2025 |  |  | 1204 | FOUR LANING OF AMRITSAR BYPASS FROM NEW TARN TARAN ROAD TO AJNALA ROAD FROM DESIGN KM. 0.750 TO DESI | NHAI | N24001642 | 2-2021 | 8/2024 | Dec-2025 | 12/2025 | 1474.77 |  | 1474.77 | 471.06 | 73.72
May 2025 |  |  | 1205 | 4L OF AMRITSAR GHOMAN TANDA UNA SECTION FROM KM 8.270 TO KM 54.000 OF NH 503A PACKAGE I | NHAI | N24001643 | 12-2020 | 6/2024 | Jun-2025 | 6/2025 | 857.91 |  | 857.91 | 127.71 | 40
May 2025 |  |  | 1206 | AMRITSAR AIRPORT JUNCTION RAMDAS FROM KM. 100.835 TO KM. 139.813 PKG IV | NHAI | N24001644 | 12-2020 | 9/2023 | Sep-2025 | 9/2025 | 524.88 | 416.58 | 416.58 | 157.14 | 73
May 2025 |  |  | 1207 | UP-GRADATION TO TWO LANE WITH PAVED SHOULDER CONFIGURATION OF NH-354 SECTION ARIFKES-FEROZEPUR-MUKTS | MoRTH | N24001960 | 3-2021 | 10/2023 | N.A. | 10/2025 | 263.19 |  | 220 | 119.5 | 61
May 2025 |  |  | 1208 | WORK OF WIDENING/UPGRADATION OF 2- LANE WITH PAVED SHOULDER OF SRI MUKTSAR SAHIB TO MALOUT ROAD FROM | MoRTH | N24001961 | 3-2022 | 10/2023 | N.A. | 7/2025 | 152.58 |  | 152.58 | 97 | 85
May 2025 |  |  | 1209 | 6L OF JODHPUR ROMANA (BATHINDA) - MANDI DABWALI (PUNJAB HARYANA BORDER) SECTION OF NH-54 FROM KM. 0. | NHAI | N24002075 | 12-2020 | 8/2025 | Aug-2025 | 8/2025 | 757.13 | 757 | 757 | 246.51 | 98
May 2025 |  |  | 1210 | 6L AMRITSAR-BATHINDA GREENFIELD SECTION FROM JN. WITH BHAGTA BHAI KA- BHADAUR ROAD NEAR DYALPURA BHAI | NHAI | N24002076 | 3-2021 | 10/2025 | Jun-2026 | 6/2026 | 2029.17 | 2029 | 2029 | 84.23 | 46
May 2025 |  |  | 1211 | 6L ACCESS CONTROLLED LUDHIANA- BATHINDA GREENFIELD HIGHWAY FROM JN. WITH AMRITSAR-BATHANDA GREENFIELD | NHAI | N24002091 | 6-2021 | 9/2025 | Mar-2026 | 3/2026 | 906.51 | 906.51 | 906.51 | 134.05 | 49.8
May 2025 |  |  | 1212 | 6-LANE AMRITSAR-BATHINDA GREENFIELD SECTION OF NH-754A FROM JUNCTION WITH MOGA JALANDHAR ROAD (NH-70 | NHAI | N24002092 | 3-2021 | 10/2025 | N.A. | 10/2025 | 1801.37 |  | 1801.37 | 1074.27 | 44.15
May 2025 |  |  | 1213 | 6L OF AMBALA-CHANDIGARH GREENFIELD SECTION FROM KM. 0.000 TO KM. 25.000 WITH 4L SPUR TO LALRU FROM K | NHAI | N24002098 | 3-2022 | 10/2025 | N.A. | 10/2025 | 1641.66 |  | 1641.66 | 60 | 52
May 2025 |  |  | 1214 | 4L OF EXISTING BEAS ? BABA BAKALA - DERA BABA NANAK SECTION FROM START OF BATALA BYPASS TILL INTERSE | NHAI | N24002100 | 10-2021 | 6/2025 | N.A. | 6/2025 | 1003.38 |  | 1003.38 | 275.45 | 69.19
May 2025 |  |  | 1215 | 4L OF BEAS-MEHTA-BATALA-DERA BABA NANAK FROM INTERSECTION WITH JALANDHAR-AMRITSAR HIGHWAY (NH-3) NEA | NHAI | N24002101 | 8-2021 | 6/2025 | Dec-2025 | 12/2025 | 809.51 |  | 809.51 | 218.47 | 51.91
May 2025 |  |  | 1216 | DELHI-AMRITSAR-KATRA EXPRESSWAY (PHASE-I SPUR-I) FROM JN. WITH KAPURTHALA - SULTANPUR LODHI ROAD (NH | NHAI | N24002102 | 1-2020 | 4/2026 | N.A. | 4/2027 | 2165.23 |  | 2165.23 | 174.63 | 19.6
May 2025 |  | CIVIL AVIATION | 1217 | CONSTRUCTION OF NEW TERMINAL BUILDING AT JODHPUR AIRPORT | AAI | N04000101 | 5-2022 | 11/2024 | Oct-2025 | 10/2025 | 480 |  | 480 | 246.67 | 70
May 2025 |  | CIVIL AVIATION | 1218 | UDAIPUR AIRPORT- CONSTRUCTION OF NEW INTEGRATED PASSENGER TERMINAL BUILDING | AAI | N04000104 | 6-2023 | 3/2026 | N.A. | 3/2026 | 887 |  | 887 | 300.51 | 62
May 2025 |  | COAL | 1219 | NLCIL 300 MW SOLAR POWER PROJECT | PART OF 510 MW CPSU SCHEME | NLC | 3-2023 | 9/2024 | N.A. | 9/2025 | 1813 |  | 1813 | 654.94 | 66
May 2025 |  | PETROLEUM | 1220 | NEW MUNDRA-PANIPAT CRUDE OIL PIPELINE | IOCL | N16000435 | 12-2021 | 10/2024 | Dec-2025 | 12/2025 | 9028 |  | 9028 | 6662.44 | 81.86
May 2025 |  | PETROLEUM | 1221 | CGD PROJECT IN TONK, SAWAI MADHOPUR, DAUSA, KARAULI | HPCL | N16000496 | 3-2022 | 3/2030 | N.A. | 3/2030 | 1751 |  | 1751 | 296.16 | 24.7
May 2025 |  | PETROLEUM | 1222 | SETTING UP OF PETROCHEMICAL EVACUATION MARKETING TERMINAL (PEMT) AT BARMER | HPCL | N16000512 | 12-2023 | 12/2026 | N.A. | 12/2026 | 461.05 |  | 461.05 | 90.93 | 44.3
May 2025 |  | PETROLEUM | 1223 | RAJASTHAN REFINERY PROJECT | HPCLRRL(JV) | N16000513 | 10-2017 | 10/2022 | Mar-2025 | 12/2025 | 43129 | 72937 | 72937 | 57717.81 | 86.9
May 2025 |  | PETROLEUM | 1224 | CGD PROJECTS AT FAZILKA (EXCEPT AREA ALREADY AUTHORIZED) GANGANAGAR AND HANUMANGARH DISTRICTS | BPCL | N16000520 | 12-2022 | 6/2030 | N.A. | 6/2030 | 3207 |  | 3207 | 316.65 | 20.6
May 2025 |  | PETROLEUM | 1225 | SAMBHU KI BHURJ-II SOLAR 300MW | NTPC | N18000286 | 3-2020 | 9/2021 | Mar-2025 | 3/2025 | 1782 |  | 1782 | 1369.88 | 100
May 2025 |  |  | 1226 | BHENSARA 320 MW | NTPC | N18000293 | 1-2021 | 7/2022 | Mar-2025 | 3/2025 | 1221.73 | 1533.38 | 1533.38 | 1139.42 | 100
May 2025 |  |  | 1227 | BHADLA-II 500MW SOLAR PV PROJECT | NTPC | N18000347 | 6-2022 | 3/2024 | Sep-2025 | 9/2025 | 2598.92 |  | 2598.92 | 1758.06 | 55
May 2025 |  |  | 1228 | TRANSMISSION SYSTEM SCHEME FOR EVACUATION OF POWER FROM REZ RAJASTHAN (8.1 GW) UNDER PHASE-II PART | PGCIL | N18000356 | 3-2023 | 9/2024 | N.A. | 9/2025 | 1433.28 |  | 1433.28 | 1281.27 | 91.9
May 2025 |  |  | 1229 | 300 MW SOLAR POWER PROJECT UNDER CPSU SCHEME | NHPC | N18000368 | 5-2022 | 11/2023 | N.A. | 8/2025 | 1677.12 |  | 1677.12 | 1066.01 | 87
May 2025 |  |  | 1230 | TS FOR EVACUATION OF POWER FROM REZ IN RAJASTHAN (20GW) UNDER PHASE- III, PART E1 | PGCIL | N18000373 | 8-2023 | 2/2025 | N.A. | 9/2025 | 688.74 |  | 688.74 | 507 | 92
May 2025 |  |  | 1231 | TS FOR EVACUATION POWER FROM REZ IN RAJASTHAN (20GW) UNDER PHASE-III PART H | PGCIL | N18000374 | 10-2023 | 4/2025 | N.A. | 8/2025 | 2211 |  | 2211 | 1551.8 | 60.9
May 2025 |  |  | 1232 | TS FOR EVACUATION POWER FROM REZ IN RAJASTHAN (20GW) UNDER PHASE-III PART C1 | PGCIL | N18000375 | 10-2023 | 4/2025 | Oct-2025 | 10/2025 | 1796 |  | 1796 | 1069 | 73.6
May 2025 |  |  | 1233 | TS FOR EVACUATION POWER FROM REZ IN RAJASTHAN (20GW) UNDER PHASE-III PART B1 | PGCIL | N18000376 | 9-2023 | 4/2025 | N.A. | 8/2025 | 2191 |  | 2191 | 1440.66 | 67.9
May 2025 |  |  | 1234 | TS FOR EVACUATION POWER FROM REZ IN RAJASTHAN (20GW) UNDER PHASE-III PART J | PGCIL | N18000378 | 12-2022 | 3/2025 | Apr-2026 | 4/2026 | 331 |  | 331 | 8.66 | 26
May 2025 |  |  | 1235 | TS FOR EVACUATION POWER FROM REZ IN RAJASTHAN (20GW) UNDER PHASE-III PART E2 | PGCIL | N18000379 | 11-2023 | 6/2025 | N.A. | 9/2025 | 428 |  | 428 | 51.42 | 42
May 2025 |  |  | 1236 | TS FOR EVACUATION OF POWER FROM RAJASTHAN REZ PH-IV (PART-1) [BIKANER COMPLEX] PART A [BIKANER III N | PGCIL | N18000386 | 12-2023 | 12/2025 | N.A. | 12/2025 | 2998 |  | 2998 | 1112.98 | 45.3
May 2025 |  |  | 1237 | TS FOR EVACUATION OF POWER FROM RAJASTHAN REZ PH-IV (PART-1) [BIKANER COMPLEX] PART D [NEEMRANA II B | PGCIL | N18000387 | 12-2023 | 12/2025 | N.A. | 12/2025 | 2056 |  | 2056 | 1318.23 | 50.7
May 2025 |  |  | 1238 | TS FOR EVACUATION OF POWER FROM REZ IN RAJASTHAN (20GW) UNDER PH-III PART D [SIKAR KHETRI TRANSMISSI | PGCIL | N18000389 | 2-2024 | 8/2025 | N.A. | 8/2025 | 2000 |  | 2000 | 823 | 51
May 2025 |  |  | 1239 | TS FOR EVACUATION POWER FROM RAJASTHAN REZ PH-IV (PART-2:5.5GW) PART-B (JAISALMER/BARMER COMPLEX) | PGCIL | N18000391 | 8-2024 | 8/2026 | N.A. | 8/2026 | 3279 |  | 3279 | 293.9 | 16.4
May 2025 |  |  | 1240 | TS FOR EVACUATION POWER FROM RAJASTHAN REZ PH-IV (PART-2:5.5GW) (JAISALMER/BARMER COMPLEX) PART-C | PGCIL | N18000393 | 8-2024 | 8/2026 | N.A. | 8/2026 | 2227 |  | 2227 | 292.59 | 16.4
May 2025 |  |  | 1241 | TS FOR EVACUATION POWER FROM RAJASTHAN REZ PH-IV (PART-2:5.5GW) (JAISALMER/BARMER COMPLEX) PART-E | PGCIL | N18000394 | 8-2024 | 8/2026 | N.A. | 8/2026 | 3251 |  | 3251 | 426.6 | 13.4
May 2025 |  |  | 1242 | ADDITIONAL TRANSMISSION SYSTEM FOR EVACUATION OF POWER FROM BHADLA-III PS AS PART OF RAJASTHAN REZ P | PGCIL | N18000396 | 8-2024 | 2/2026 | N.A. | 2/2026 | 369 |  | 369 | 0 | 1
May 2025 |  |  | 1243 | TRANSMISSION SYSTEM STRENGTHENING FOR INTERCONNECTIONS OF BHADLA-III AND BIKANER III COMPLEX [SPV NA | PGCIL | N18000397 | 8-2024 | 8/2026 | N.A. | 8/2026 | 1382 |  | 1382 | 0 | 1
May 2025 |  |  | 1244 | TRANSMISSION SYSTEM FOR EVACUATION OF POWER FROM RAJASTHAN REZ PH -IV [PART-2 5.5 GW] [JAISALMER/BAR | PGCIL | N18000401 | 11-2024 | 11/2026 | N.A. | 11/2026 | 2735 |  | 2735 | 0 | 0.7
May 2025 |  |  | 1245 | TRANSMISSION SYSTEM FOR EVACUATION OF POWER FROM RAJASTHAN REZ PH-IV [PART-3 (6GW)] [BIKANER COMPLEX | PGCIL | N18000403 | 11-2024 | 11/2026 | N.A. | 11/2026 | 5969 |  | 5969 | 0
May 2025 |  |  | 1246 | TRANSMISSION SYSTEM FOR EVACUATION OF POWER FROM RAJASTHAN REZ PH-IV [PART-3 (6 GW)] [BIKANER COMPLE | PGCIL | N18000404 | 11-2024 | 11/2026 | N.A. | 11/2026 | 5357 |  | 5357 | 67.82 | 3.7
May 2025 |  |  | 1247 | RAJASTHAN REZ PH-V (PART-1: 4 GW) [SIROHI/NAGAUR] COMPLEX | PGCIL | N18000414 | 3-2025 | 3/2027 | N.A. | 3/2027 | 5028 |  | 5028 | 0
May 2025 |  |  | 1248 | AUGMENTATION AT FATEHGARH-II PS, FATEHGARH-IV PS (SECTION-II) AND BARMER-I | PGCIL | N18000415 | 3-2025 | 12/2026 | N.A. | 12/2026 | 404 |  | 428 | 0
May 2025 |  |  | 1249 | NOKH SOLAR PV PROJECT 735 MW | NTPC | N18000418 | 3-2022 | 4/2024 | Jul-2025 | 7/2025 | 4189.17 | 4378.17 | 4378.17 | 151.79 | 95
May 2025 |  |  | 1250 | AGRA FORT-BANDIKUI | NCR | N22000553 | 6-2022 | 6/2027 | May-2026 | 5/2026 | 1389.81 |  | 987.83 | 42.46 | 12
May 2025 |  |  | 1251 | GUDHA THATHANA MITHRI TEST TRACK FOR RDSO | NWR | N22000593 | 4-2019 | 3/2025 | N.A. | 6/2025 | 528.48 |  | 500.85 | 354.2 | 95
May 2025 |  |  | 1252 | DEDICATED TEST TRACK FOR RDSO | PHASE II | NWR | 11-2021 | 11/2026 | N.A. | 12/2025 | 466.42 |  | 466.22 | 737.27 | 82
May 2025 |  |  | 1253 | DOUBLING BETWEEN CHURU-RATANGARH | 42.81 KM | NWR | 2-2023 | 2/2028 | N.A. | 6/2025 | 422.6 |  | 422.6 | 209.8 | 90
May 2025 |  |  | 1254 | SAWAIMADHOPUR - BYPASS LINE (6.98 KM) | UMBRELLA WORK PB#57/2019-20/NR | NWR | 12-2022 | 6/2026 | N.A. | 1/2026 | 304 | 239.54 | 239.54 | 124.6 | 30
May 2025 |  |  | 1255 | GC OF NATHDWARA - DEVGARH MADARIYA | 82.5KM | NWR | 1-2023 | 6/2028 | N.A. | 12/2026 | 968.92 |  | 968.92 | 400.31 | 40
May 2025 |  |  | 1256 | CONSTRUCTION/ UP-GRATION OF FOUR/TWO LANE WITH PAVED SHOULDER OF NH68 FROM TANOT-RAMGARH BHADASAR-JA | NHAI | N24000795 | 2-2018 | 4/2021 | Jun-2025 | 6/2025 | 741.86 | 649 | 649 | 663.37 | 99.99
May 2025 |  |  | 1257 | 4L+PS OF NH -58 FROM BEAWAR-GOMTI (OLD CH KM 58.245 TO KM. 108.600) PKG-I. | MoRTH | N24001411 | 12-2020 | 10/2023 | N.A. | 12/2025 | 379.23 |  | 379.23 | 268.62 | 96.1
May 2025 |  |  | 1258 | 2L+PS FOR WORK OF NH-325 (BALOTRA TO SANDERAO VIA JALORE) BY CONSTRUCTION OF BYPASSES:(1) ASOTRA- BR | MoRTH | N24001527 | 12-2021 | 5/2024 | Dec-2025 | 12/2025 | 411.4 |  | 411.4 | 219.61 | 71.63
May 2025 |  |  | 1259 | WIDENING OF PACHPADRA-BAGUNDI SECTION TO 4 LANE FROM KM 73/60 TO 95/70 OF NH-25 ON EPC MODE IN THE | MoRTH | N24001528 | 1-2022 | 12/2024 | Aug-2025 | 8/2025 | 194.88 |  | 194.88 | 105.69 | 83
May 2025 |  |  | 1260 | 44 LANE DIVIDED CARRIAGEWAY OF BARMER BYPASS OF NH-15 (NEW NH-68) IN THE STATE OF RAJASTHAN ON EPC M | MoRTH | N24001529 | 12-2021 | 8/2024 | May-2025 | 5/2025 | 451.66 |  | 451.66 | 401.78 | 99
May 2025 |  |  | 1261 | UPGRADATION TO TWO LANE PAVED SHOULDER OF KOTHUN-LALSOT-KAROLI- DHOLPUR ROAD NH-23 (OLD NH-11B) IN TH | MoRTH | N24001530 | 12-2021 | 9/2024 | N.A. | 8/2025 | 150.11 |  | 150.11 | 82.83 | 88
May 2025 |  |  | 1262 | 4L GREENFIELD SPUR FROM DELHI- VADODARA GREENFIELD EXPRESSWAY NEAR BANDIKUI TO JAIPUR | NHAI | N24001557 | 3-2022 | 11/2024 | Jun-2025 | 6/2025 | 1636.15 |  | 1636.15 | 553.96 | 95.26
May 2025 |  |  | 1263 | 4L OF KARWAR (KM. 281.980 OF NH-62 NAGAUR ROAD) TO DANGIYAVAS OF JODHPUR RING ROAD (PKG-II) | NHAI | N24001558 | 11-2021 | 8/2024 | Jun-2025 | 6/2025 | 736.75 |  | 736.75 | 253.43 | 97
May 2025 |  |  | 1264 | 2L PS SRIGANGANAGAR TO RAISINGHNAGAR (DESIGN CHAINAGE -0.500 KM TO DESIGN CHAINAGE 101.000 KM) (PACK | NHAI | N24001559 | 9-2021 | 6/2024 | May-2025 | 5/2025 | 672.35 |  | 672.35 | 328.24 | 99.5
May 2025 |  |  | 1265 | DEOGARH (NEAR DHANDHANIYA)- RAJASTHAN/GUJARAT BORDER (PHASE-I) | AJ/DRGB-PACKAGE-6 | NHAI | 10-2019 | 8/2023 | Jun-2025 | 6/2025 | 846.59 |  | 846.59 | 167.25 | 99.25
May 2025 |  |  | 1266 | DEOGARH (NEAR DHANDHANIYA)- RAJASTHAN/GUJARAT BORDER (PHASE-I) | AJ/DRGB-PACKAGE-7 | NHAI | 10-2019 | 7/2023 | Jun-2025 | 6/2025 | 662.08 |  | 662.08 | 124.06 | 96.5
May 2025 |  |  | 1267 | DELHI-VADODARA GREENFIELD ALIGNMENT (NH-148N) (PKG-10) (CH. 292.950 TO CH. 319.400) [END OF INTERCHA | NHAI | N24001567 | 11-2019 | 10/2022 | Jun-2025 | 6/2025 | 1272.97 |  | 1272.97 | 512.05 | 86.81
May 2025 |  |  | 1268 | DELHI-VADODARA GREENFIELD ALIGNMENT (NH-148N) (PKG-14) (CH. 388.420 TO CH. 419.000) [JUNCTION WITH N | NHAI | N24001568 | 11-2019 | 5/2023 | Jun-2025 | 6/2025 | 1119.35 |  | 1119.35 | 1447.44 | 99.8
May 2025 |  |  | 1269 | DELHI-VADODARA GREENFIELD ALIGNMENT (NH-148N) (PKG-09) (CH. 247.310 TO CH. 292.950) [JUNCTION WITH M | NHAI | N24001573 | 11-2019 | 12/2022 | Jun-2025 | 6/2025 | 1658.06 |  | 1658.06 | 157.39 | 99.9
May 2025 |  |  | 1270 | DELHI-VADODARA GREENFIELD ALIGNMENT (NH-148N) (PKG-15) (CH. 419.000 TO CH.427.300) [JUNCTION WITH NH | NHAI | N24001612 | 7-2020 | 1/2024 | Dec-2025 | 12/2025 | 1788.69 |  | 1788.69 | 960.26 | 76.81
May 2025 |  |  | 1271 | CONSTRUCTION OF TWO LANE WITH PAVED SHOULDER FOR FATEHPUR BYPASS, MANDAWA BYPASS AND JHUNJHUNU BYPAS | MoRTH | N24001866 | 3-2022 | 8/2024 | N.A. | 6/2025 | 186.29 |  | 186.29 | 142.69 | 90
May 2025 |  |  | 1272 | UPGRADATION OF TWO LANE PAVED SHOULDER FROM SHAHPURA TO THANAGAZI OF NH-248A ON EPC MODE IN THE STAT | MoRTH | N24001867 | 3-2022 | 7/2024 | N.A. | 8/2025 | 174.34 |  | 174.34 | 118.08 | 90
May 2025 |  |  | 1273 | Sagwara Bypass and Garhi- Partapur Bypass of NH-927A in the State of Rajasthan. | MoRTH | N24001868 | 3-2022 | 8/2025 | N.A. | 8/2025 | 187.65 |  | 187.65 | 117.57 | 90
May 2025 |  |  | 1274 | UP-GRADATION TO 2 LANE WITH PAVED SHOULDER FROM CHARBHUJA AT DESIGN KM 0.00 (EXISTING KM 150.00) TO | MoRTH | N24001927 | 2-2022 | 9/2025 | N.A. | 9/2025 | 838.43 |  | 838.43 | 455.87 | 99
May 2025 |  |  | 1275 | CONSTRUCTION OF 2 LANE WITH PAVED SHOULDER NORTHERN BYPASS PHASE-II OF KOTA CITY FROM DESIGN CHAINAG | MoRTH | N24001928 | 3-2022 | 4/2025 | N.A. | 12/2025 | 317.74 |  | 317.74 | 136.23 | 12.5
May 2025 |  |  | 1276 | ADDITIONAL STRUCTURES ON 6LGURGAON- JAIPUR SECTION OF NH-48 BETWEEN KM 42.700 TO KM 273.00 | NHAI | N24002058 | 8-2022 | 6/2024 | Jun-2025 | 6/2025 | 409.64 |  | 409.64 | 238.22 | 77.1
May 2025 |  |  | 1277 | UPGRADATION TO 2 LANE WITH PAVED SHOULDER OF HANUMANGARH TO KENCHIYAN OF NH 54 ON EPC MODE IN THE ST | MoRTH | N24002167 | 3-2024 | 10/2026 | N.A. | 10/2026 | 334.64 |  | 334.64 | 128 | 50
May 2025 |  |  | 1278 | UPGRADATION TO 2 LANE WITH PAVED SHOULDER FROM NEECHLI ODEN (NATHDWARA) AT DESIGN KM 88.800 TO BHATE | MoRTH | N24002168 | 3-2023 | 10/2026 | N.A. | 10/2026 | 606.61 |  | 606.61 | 118 | 20
May 2025 |  | CIVIL AVIATION | 1279 | PAKYONG AIRPORT- WIDENING OF BASIC STRIP AT WESTERN SIDE OF RUNWAY CHAINAGE 80M TO 920M I/C SLOPE ST | AAI | N04000110 | 11-2023 | 6/2026 | N.A. | 6/2026 | 323.26 |  | 323.26 | 24.99 | 12
May 2025 |  | DEPARTMENT OF HIGHER EDUCATION | 1280 | CONSTRUCTION OF SIKKIM UNIVERSITY CAMPUS PHASE-I, PACKAGE -II AT YANGANG SOUTH SIKKIM | Sikkim Universi | N44000002 | 8-2020 | 1/2025 | N.A. | 1/2025 | 314.06 |  | 303.55 | 157.24 | 80
May 2025 |  | POWER | 1281 | TEESTA VI HE PROJECT | NHPC | N18000325 | 3-2019 | 3/2024 | N.A. | 12/2027 | 5748.04 |  | 5748.04 | 4341.5 | 67.67
May 2025 |  | POWER | 1282 | RANGIT IV HE PROJECT | NHPC | N18000326 | 3-2021 | 5/2024 | N.A. | 12/2025 | 938.29 |  | 1828.11 | 1486.3 | 88.51
May 2025 |  | RAILWAYS | 1283 | SEVOK RANGPO, NEFR | NFR | N22000102 | 4-2008 | 5/2015 | Dec-2027 | 12/2027 | 7876.92 | 11963.43 | 11963.43 | 8569.25 | 80
May 2025 |  | RAILWAYS | 1284 | CONSTRUCTION OF 2-LANE WITH PAVED SHOULDER INCLUDING GEOMETRIC IMPROVEMENT FROM KM 0.000 TO KM 16.00 | NHIDCL | N24000767 | 3-2017 | 4/2022 | May-2022 | 12/2023 | 375.8 |  | 375.8 | 288.56 | 96.55
May 2025 |  | RAILWAYS | 1285 | CONSTRUCTION OF 2-LANE WITH PAVED SHOULDER INCLUDING GEOMETRIC IMPROVEMENT FROM KM 16.000 TO KM 32.5 | NHIDCL | N24000768 | 11-2017 | 10/2020 | Aug-2023 | 4/2024 | 290.05 |  | 290.05 | 218.36 | 100
May 2025 |  | RAILWAYS | 1286 | CONSTUCTION/UPGRADATION OF EXISTING HIGHWAY TO 2 LANE WITH PAVED SHOULDER FROM KM 0.00 TO KM 13.00 N | NHIDCL | N24001251 | 3-2019 | 4/2022 | N.A. | 6/2025 | 402.94 |  | 402.94 | 247.12 | 76.54
May 2025 |  | RAILWAYS | 1287 | CONSTUCTION/UPGRADATION OF EXISTING HIGHWAY TO 2 LANE WITH PAVED SHOULDER FROM KM 13.00 TO KM 25.600 | NHIDCL | N24001252 | 8-2020 | 4/2023 | Nov-2024 | 7/2025 | 295.97 |  | 295.97 | 249.8 | 95.66
May 2025 |  | RAILWAYS | 1288 | CONSTUCTION/UPGRADATION OF EXISTING HIGHWAY TO 2 LANE WITH PAVED SHOULDER FROM KM 26.10 TO KM 40.00 | NHIDCL | N24001254 | 3-2020 | 6/2022 | N.A. | 1/2024 | 242.97 |  | 244.45 | 246.91 | 100
May 2025 |  | RAILWAYS | 1289 | CONSTRUCTION AND UPGRADATION OFEXISTINGROAD TO 2-LANE WITH PAVED SHOULDER INCLUDING GEOMETRIC IMPROV | NHIDCL | N24001261 | 8-2020 | 4/2023 | N.A. | 4/2025 | 311 |  | 273.78 | 257.86 | 95.12
May 2025 |  |  | 1290 | CONSTRUCTION AND UPGRADATION OFEXISTINGROAD TO 2-LANE WITH PAVED SHOULDER INCLUDING GEOMETRIC IMPROV | NHIDCL | N24001262 | 7-2020 | 4/2023 | Aug-2024 | 10/2025 | 345.38 | 395.59 | 395.59 | 362.61 | 91.24
May 2025 |  |  | 1291 | CONSTRUCTION OF 2-LANE ROAD WITH PAVED SHOULDER (GREENFIELD ALIGNMENT) OF EXISTING STRETCH BETWEEN L | NHIDCL | N24001322 | 9-2020 | 5/2022 | Oct-2023 | 12/2025 | 183.31 | 439.56 | 439.56 | 355.31 | 51.19
May 2025 |  |  | 1292 | CONSTRUCTION OF 2-LANE SPECIFICATION ROAD WITH PAVED SHOULDER AS REALIGNMENT (GREENFIELD ALIGNMENT) | NHIDCL | N24001325 | 9-2020 | 5/2023 | Aug-2024 | 12/2025 | 262.84 | 414.2 | 414.2 | 221.86 | 47.57
May 2025 |  |  | 1293 | REHABILITATION AND UPGRADATION OF EXISTING ROAD TO 2-LANE WITH PAVED SHOULDER INCLUDING GEOMETRIC IM | NHIDCL | N24001327 | 8-2020 | 5/2022 | Oct-2023 | 12/2025 | 292.8 |  | 292.8 | 202.92 | 60.9
May 2025 |  |  | 1294 | CONSTRUCTION AND UPGRADATION OF EXISTING ROAD TO 2-LANE WITH PAVED SHOULDER FROM KM27.200 (END OF RO | NHIDCL | N24001336 | 8-2020 | 4/2023 | Oct-2024 | 12/2025 | 230.45 | 244.91 | 244.91 | 206.95 | 82.32
May 2025 |  |  | 1295 | CONSTRUCTION AND UPGRADATION OF EXISTING ROAD TO 2-LANE WITH PAVED SHOULDER FROM NEW ROLEP BRIDGE AT | NHIDCL | N24001337 | 10-2020 | 11/2023 | Jul-2025 | 3/2026 | 493.42 | 478.79 | 478.79 | 305.2 | 58.28
May 2025 |  |  | 1296 | CONSTRUCTION OF 2-LANE WITH PAVED SHOULDER OF NEW GREEN FIELD ALIGNMENT FROM CHOCHENPHERI AT KM 52.0 | NHIDCL | N24001338 | 10-2020 | 12/2023 | Jun-2025 | 12/2026 | 816.79 | 786.6 | 786.6 | 332.24 | 51.45
May 2025 |  |  | 1297 | RISHI BORDER- ROLEP- MENLA PKG- 3B | NHIDCL | N24001362 | 12-2020 | 2/2024 | Apr-2025 | 12/2025 | 410.6 | 379.3 | 379.3 | 234.98 | 74.58
May 2025 |  |  | 1298 | CONSTRUCTION OF 2-LANE WITH PAVED SHOULDER GANGTOK BYPASS ROAD FROM RANIPOOL TO BURTUK (L=23.316KM) | MoRTH | N24001442 | 10-2021 | 5/2024 | Jan-2026 | 1/2026 | 385.15 |  | 385.15 | 170.32 | 81.3
May 2025 |  | CIVIL AVIATION | 1299 | MODERNIZATION OF CHENNAI AIRPORT PHASE II, CHENNAI | AAI | N04000074 | 6-2018 | 2/2022 | Jun-2026 | 6/2026 | 2467 |  | 2467 | 1601.6 | 71
May 2025 |  | CIVIL AVIATION | 1300 | DEVELOPMENT OF TUTICORIN AIRPORT | AAI | N04000090 | 6-2019 | 3/2022 | Apr-2025 | 4/2025 | 380.87 | 451.74 | 451.74 | 361.57 | 100
May 2025 |  | COAL | 1301 | JAWAHAR KHANI OPENCAST (JK OC) MINE | SCCL | N06000259 | 12-2021 | 3/2025 | N.A. | 3/2026 | 297.88 |  | 297.88 | 46.37 | 20
May 2025 |  | COAL | 1302 | 50 MW SOLAR POWER PROJECT -NEYVELI MINED OUT AREA | NLC | N06000279 | 5-2023 | 6/2025 | N.A. | 9/2025 | 218.03 |  | 218.03 | 147.99 | 38
May 2025 |  | FINANCE | 1303 | CONSTRUCTION OF 726 Nos RESIDENTIAL QUARTERS CHENNAI | CPWD FOR FINANC | N28000109 | 11-2017 | 11/2021 | N.A. | 11/2022 | 348.77 |  | 348.77 | 223.39 | 100
May 2025 |  | MINES | 1304 | 25.5 MW WIND POWER PROJECT AT KAYATHAR IN TAMILNADU | NALCO | N10000014 | 9-2017 | 6/2019 | Mar-2024 | 12/2024 | 166.62 | 163.17 | 163.17 | 135.63 | 65
May 2025 |  | MINES | 1305 | IRUGUR-DEVANGONTHI POL PIPELINE | BPCL | N16000234 | 11-2012 | 2/2017 | Oct-2025 | 10/2025 | 678 | 1732 | 1732 | 615.48 | 59
May 2025 |  | MINES | 1306 | CBR 9 MMTPA PROJECT | CPCL | N16000434 | 1-2021 | 6/2025 | N.A. | 6/2025 | 31580 | 31580 | 36354 | 1326.17 | 10.2
May 2025 |  | MINES | 1307 | GRASS ROOT POL TERMINAL AT VALLUR, CHENNAI | IOCL | N16000438 | 1-2022 | 7/2024 | Jun-2025 | 12/2025 | 827 | 887.71 | 887.71 | 576.63 | 85.4
May 2025 |  | MINES | 1308 | LAYING OF POL PIPELINES IN COMMON CORRIDOR FOR PROPOSED GRASS ROOT TERMINAL AT VALLUR (CHENNAI) | IOCL | N16000455 | 1-2022 | 7/2024 | May-2026 | 5/2026 | 829 |  | 829 | 257.54 | 59.44
May 2025 |  | MINES | 1309 | CGD PROJECT AT DHARMAPURI AND KRISHNAGIRI DISTRICTS | IOCL | N16000486 | 3-2022 | 3/2030 | N.A. | 12/2030 | 501 |  | 501 | 107.21 | 5.3
May 2025 |  |  | 1310 | CGD PROJECTS AT THE NILGIRIS AND ERODE DISTRICTS | BPCL | N16000521 | 12-2022 | 3/2030 | N.A. | 3/2030 | 3685 |  | 3685 | 205.14 | 10.8
May 2025 |  | POWER | 1311 | TRANSMISSION SYSTEM UNDER ISTS FOR EVACUATION OF POWER FROM KUDANKULAM UNIT - 3 AND 4 (2X1000 MW) | PGCIL | N18000408 | 1-2025 | 7/2028 | N.A. | 7/2028 | 548 |  | 548 | 0
May 2025 |  | RAILWAYS | 1312 | EXTENSION OF MRTS FROM VELACHERY TO STN. THOMAS, MTP | MRTP | N22000028 | 4-2006 | 7/2024 | May-2025 | 5/2025 | 734.01 | 734.01 | 981.83 | 632.33 | 98
May 2025 |  | RAILWAYS | 1313 | TIDIVANAM-NAGARI (NL) | SR | N22000085 | 9-2006 | 9/2016 | Mar-2028 | 3/2028 | 3631.34 | 3631.34 | 3631.34 | 873.31 | 15
May 2025 |  | RAILWAYS | 1314 | CHENNAI BEACH-CHENNAI EGMORE (4.3 KM) (UMBRELLA WORK PB#57/2019-20/NR) | SR | N22000568 | 3-2022 | 3/2026 | Feb-2025 | 3/2025 | 359.6 | 274.2 | 310 | 302.11 | 95
May 2025 |  | RAILWAYS | 1315 | MORAPPUR-DHARMAPURI | SR | N22000618 | 2-2019 | 3/2028 | Mar-2028 | 3/2028 | 358.95 |  | 358.95 | 40.09 | 1
May 2025 |  | RAILWAYS | 1316 | KARAIKAL PERALAM(23KM)-NEW LINE PROJECT | SR | N22000625 | 1-2019 | 3/2026 | Mar-2025 | 6/2025 | 304.22 |  | 373.42 | 282.58 | 97
May 2025 |  | RAILWAYS | 1317 | NAGAPATTINAM THIRUTURAIPUNDI (38KM)- NEW LINE PROJECT | SR | N22000626 | 7-2008 | 3/2026 | Mar-2027 | 3/2027 | 677.12 |  | 788.05 | 144.28 | 19
May 2025 |  | RAILWAYS | 1318 | FOUR LANNING OF CHOLOPURAM- THANJAVUR | NHAI | N24000697 | 8-2017 | 9/2020 | N.A. | 6/2025 | 1176.37 |  | 1176.37 | 1325.06 | 99.5
May 2025 |  | RAILWAYS | 1319 | 4-LANNING OF STHIYATHOPU- CHOLOPURAM | NHAI | N24000708 | 9-2017 | 8/2020 | May-2025 | 5/2025 | 1227.87 |  | 1227.87 | 1436.16 | 98.12
May 2025 |  | RAILWAYS | 1320 | FOUR LANINIG OF CHETTIKULAM TO NATHAM SECTION OF NH-785 FROM CHETTIKULUM (KM 7.300) TO NATHAM (KM. 3 | NHAI | N24000826 | 3-2018 | 10/2022 | Jun-2025 | 6/2025 | 505.35 |  | 837.69 | 376.61 | 99.75
May 2025 |  |  | 1321 | FOUR LANING OF PUDUCHERRY (KM.29/000) TO POONDIYANKUPPAM (KM.67/000) SECTION OF NH-45A ON HAM UNDER | NHAI | N24001429 | 3-2018 | 11/2021 | Jun-2025 | 6/2025 | 1294.47 | 1588.4 | 1588.4 | 865.95 | 98.72
May 2025 |  |  | 1322 | FOUR LANING OF SATTANATHAPURAM (KM.123/800) TO NAGAPATTINAM (KM.179/555) SECTION OF NH-45A ON HAM UN | NHAI | N24001431 | 3-2018 | 10/2020 | Jan-2026 | 1/2026 | 1872.68 | 2899.77 | 2899.77 | 1301.78 | 63.5
May 2025 |  |  | 1323 | CONSTRUCTION OF 4 LANE WITH PAVED SHOULDERS THIRUVAYARU BYPASS IN BETWEEN EXISTING KM.55/926 TO 62/6 | MoRTH | N24001455 | 2-2022 | 8/2022 | N.A. | 3/2025 | 191.33 | 207.97 | 207.97 | 100.42 | 100
May 2025 |  |  | 1324 | BALANCE WORK 2-LANE WITH PAVED SHOULDERS OF NAGAPATTINAM - THANJAVUR SECTION OF NH-67 (NEW NH- 83) | NHAI | N24001600 | 10-2020 | 5/2023 | Jun-2025 | 6/2025 | 434.12 |  | 434.12 | 268.92 | 100
May 2025 |  |  | 1325 | 4-LANING OF KAMALAPURAM - ODDANCHATRAM SECTION OF NH-209 | NHAI | N24001601 | 1-2019 | 1/2023 | Jun-2025 | 6/2025 | 1051.69 |  | 1051.69 | 588.17 | 81.69
May 2025 |  |  | 1326 | 4-LANING OF MADATHUKULAM - POLLACHI SECTION OF NH-209 (NEW NH-83) | NHAI | N24001602 | 1-2019 | 12/2022 | Nov-2025 | 11/2025 | 1409.38 |  | 1409.38 | 659.5 | 91.09
May 2025 |  |  | 1327 | 4-LANING OF ODDANCHATRAM - MADATHUKULAM SECTION OF NH-209 (NEW NH-83) | NHAI | N24001603 | 1-2019 | 10/2022 | Jun-2025 | 6/2025 | 1518.53 |  | 1607.54 | 915.4 | 100
May 2025 |  |  | 1328 | 4-LANING OF MELUR - PILLAYARPATTI - KARAIKUDI SECTION OF NH-338, NH-36, NH- 383 | NHAI | N24001605 | 6-2018 | 3/2022 | N.A. | 8/2025 | 1103.86 |  | 1103.86 | 568.15 | 84.25
May 2025 |  |  | 1329 | 4-LANING OF VADIPPATTI - THAMARAIPATTI SECTION OF NH-744A (MADURAI RING ROAD) | NHAI | N24001606 | 12-2018 | 3/2022 | Sep-2025 | 9/2025 | 854.94 |  | 854.94 | 400.13 | 77.21
May 2025 |  |  | 1330 | BALANCE WORKS OF FOUR LANE FROM KM 43+950 (THIRUVALLUR BYPASS) TO KM 61+470 (VEPPAMPATTU BYPASS) PAS | NHAI | N24001692 | 1-2022 | 9/2024 | Feb-2025 | 7/2025 | 467.99 |  | 468 | 71.05 | 80.92
May 2025 |  |  | 1331 | FOUR LANING OF NERALURU TO THORAPALLI AGRAHARAM SECTION OF NH- 844 (PKG-I) FROM KM.0+000 TO KM.23+350 | NHAI | N24001693 | 9-2021 | 10/2024 | N.A. | 10/2024 | 1751.18 |  | 1757.27 | 49.69
May 2025 |  |  | 1332 | FOUR LANING OF THORAPALLI AGRAHARAM TO JITTANDAHALLI SECTION OF NH-844 (PKG-II) FROM KM.23+350 TO KM | NHAI | N24001694 | 2-2019 | 12/2023 | Dec-2024 | 12/2024 | 1243.57 |  | 1243.57 | 171.63
May 2025 |  |  | 1333 | FOUR LANING OF JITTANDAHALLI TO DHARMAPURI SECTION OF NH-844 (PKG-III) FROM KM.60+100 TO KM.94+460 | NHAI | N24001696 | 2-2019 | 8/2023 | Dec-2024 | 12/2024 | 1291.37 |  | 1291.37 | 215.02
May 2025 |  |  | 1334 | THOPPUR METTUR BHAVANI ERODE SECTION OF NH 544H FOR A LENGTH OF 85 KM | NHAI | N24001716 | 7-2022 | 8/2023 | Dec-2024 | 12/2024 | 186.5 | 242.4 | 242.4 | 17.15 | 100
May 2025 |  |  | 1335 | BANGALORE CHENNAI EXPRESSWAY PHASE-III PACKAGE III (ARAKKONAM TO KANCHEEPURAM) FROM KM 204.500 TO K | NHAI | N24001717 | 11-2020 | 8/2024 | N.A. | 3/2026 | 1155.49 | 1525.1 | 1525.1 | 489.94 | 53.56
May 2025 |  |  | 1336 | BANGALORE CHENNAI EXPRESSWAY PHASE-III PACKAGE II (WALAJAHPET TO ARAKKONAM) FROM KM 180.000 TO KM 2 | NHAI | N24001718 | 12-2020 | 7/2024 | N.A. | 8/2025 | 843.48 | 1077.4 | 1068.6 | 434.49 | 90.62
May 2025 |  |  | 1337 | 4L BANGALORE-CHENNAI EXPRESSWAY FROM KM. 230.000 TO KM. 261.705 OF KANCHEPURAM TO SRIPERUMBUDUR SECT | NHAI | N24001719 | 2-2021 | 7/2024 | N.A. | 10/2025 | 2948.31 | 3605.73 | 3605.73 | 813.96 | 76.32
May 2025 |  |  | 1338 | BANGALORE CHENNAI EXPRESSWAY PHASE-III ? PACKAGE I (GUDIPALA TO WALAJAJHPET) FROM KM 156.000 TO KM 1 | NHAI | N24001720 | 10-2020 | 5/2024 | N.A. | 8/2025 | 1023.91 | 1438.62 | 1438.62 | 635.04 | 84.49
May 2025 |  |  | 1339 | FOUR LANING OF MAMALLAPURAM TO MUGAIYUR SECTION OF NH332A FROM KM 0.000 TO KM 31.000 | NHAI | N24001721 | 2-2019 | 5/2024 | Aug-2025 | 3/2026 | 1008.99 | 1360.53 | 1360.53 | 324.81 | 48.1
May 2025 |  |  | 1340 | 6L OF MADURAVOYAL TO SRIPERUMBUDUR SECTION FROM KM. 13.800 TO KM. 37.000 OF NH-4 THROUGH STATE HIGH | NHAI | N24001722 | 11-2021 | 2/2023 | N.A. | 12/2024 | 463.44 | 463.07 | 463.44 | 334.8 | 99
May 2025 |  |  | 1341 | KARAIPETTAI TO WALAJAPET FROM KM 71.015 TO 107.091 | NHAI | N24001723 | 10-2018 | 2/2021 | N.A. | 6/2025 | 707.9 | 766.51 | 766.51 | 526.39 | 90.06
May 2025 |  |  | 1342 | 6L OF SRIPERUMBUDUR TO KARAIPETTAI FROM KM 37.000 TO KM 71.015 OF NH 48 | NHAI | N24001725 | 1-2019 | 5/2021 | N.A. | 1/2025 | 819.89 | 1314.82 | 922.85 | 415.6 | 57.32
May 2025 |  |  | 1343 | CONSTRUCTION OF BYPASS TO GUDIYATHAM TOWN IN KM 23/100 ? 29/250 INCLUDING LA AND SHIFTING OF NH-234 | MoRTH | N24001828 | 1-2022 | 11/2024 | N.A. | 5/2025 | 221.03 | 243.95 | 243.95 | 176.5 | 100
May 2025 |  |  | 1344 | FOUR LANING OF OTTANCHATRAM TO PALANI SECTION FROM KM 30/700 TO KM 55/000 OF NH 209(NEW NH-83) INCLU | MoRTH | N24001829 | 10-2022 | 11/2024 | N.A. | 5/2025 | 172.15 |  | 172.15 | 157.48 | 100
May 2025 |  |  | 1345 | CONSTRUCTION OF STRR (WEST SIDE)- NH948A-BALAGONDAPALLI (TAMIL NADU) TO KARNATAKA/TAMIL NADU BORDER F | NHAI | N24001968 | 4-2022 | 5/2025 | N.A. | 5/2025 | 1260.74 |  | 1260.74 | 487.46 | 44.95
May 2025 |  |  | 1346 | 4L OF THIRUMANGALAM TO VADUGAPATTI SECTION FROM KM 0.000 TO KM 36.000 OF NH-744 | NHAI | N24002084 | 3-2022 | 2/2025 | N.A. | 9/2025 | 1076.97 |  | 1076.97 | 540.46 | 87.3
May 2025 |  |  | 1347 | CONSTRUCTION OF NEW DOUBLE TIER 4 LANE ELEVATED CORRIDOR FROM CHENNAI PORT TO MADURAVOYAL IN CHENNAI | NHAI | N24002107 | 3-2023 | 5/2026 | N.A. | 5/2026 | 1382 |  | 1382 | 0
May 2025 |  |  | 1348 | CONSTRUCTION OF NEW DOUBLE TIER 4L ELEVATED CORRIDOR FROM CHENNAI PORT TO MADURAVOYAL IN CHENNAI DIS | NHAI | N24002108 | 3-2023 | 5/2026 | N.A. | 5/2026 | 1618.96 |  | 1618.96 | 0
May 2025 |  |  | 1349 | CONSTRUCTION OF NEW DOUBLE TIER 4L ELEVATED CORRIDOR FROM CHENNAI PORT TO MADURAVOYAL IN CHENNAI DIS | NHAI | N24002109 | 3-2023 | 5/2026 | N.A. | 5/2026 | 1301.37 |  | 1301.37 | 0
May 2025 |  |  | 1350 | CONSTRUCTION OF NEW DOUBLE TIER 4L ELEVATED CORRIDOR FROM CHENNAI PORT TO MADURAVOYAL IN CHENNAI DIS | NHAI | N24002110 | 3-2023 | 5/2026 | N.A. | 5/2026 | 1207.4 |  | 1207.4 | 0
May 2025 |  |  | 1351 | FOUR LANING OF MUGAIYUR TO MARAKKANAM SECTION OF NH-332A FROM KM 31.000 TO KM 62.000 | NHAI | N24002111 | 2-2019 | 12/2025 | May-2026 | 5/2026 | 825.94 | 1116.13 | 1116.13 | 327.75 | 38.39
May 2025 |  |  | 1352 | SIX LANING OF TUTICORIN PORT ROAD SECTION OF NH-7A (NEW NH-138) FROM KM 0.000 TO KM 6.140 [EFFECTIVE | NHAI | N24002112 | 3-2023 | 7/2024 | N.A. | 6/2025 | 200.3 |  | 200.3 | 109.38 | 83.35
May 2025 |  |  | 1353 | 4L OF LEFT-OVER WORKS INCLUDING ADDITIONAL STRUCTURES FROM KERALA/TAMIL NADU BORDER TO KANYAKUMARI S | NHAI | N24002113 | 3-2023 | 8/2025 | N.A. | 8/2025 | 1141.78 |  | 1141.78 | 439.12 | 44.75
May 2025 |  |  | 1354 | 4L OF VADUGAPATTI TO THERKUVENGANALLUR (RAJAPALYAM) SECTION FROM KM 36.000 TO KM 71.600 OF NH744 UND | NHAI | N24002114 | 2-2022 | 4/2025 | N.A. | 10/2025 | 1097.59 |  | 1317.06 | 689.69 | 96
May 2025 |  |  | 1355 | WIDENING TO 4L/4L+PS AND STRENGTHENING IN SELECTED STRETCHES FROM KM 0/8 TO 50/570 OF NH 532 INCLUD | MoRTH | N24002151 | 3-2022 | 1/2024 | N.A. | 7/2025 | 257.14 | 294.7 | 294.7 | 251.25 | 90
May 2025 |  |  | 1356 | WIDENING FROM 2L+PS TO 4L/4L+PS AND IMPROVEMENTS THE SELECTED STRETHCES FROM KM 26/5 - 81/2 INCLU | MoRTH | N24002152 | 3-2023 | 11/2023 | N.A. | 11/2025 | 274.84 |  | 274.84 | 243.81 | 100
May 2025 |  |  | 1357 | STRENGTHENING OF 2L+PS FROM KM 17/8 ? 18/2, CONSTRUCTION OF 2L+PS FROM KM 18/2 TO KM 20/0 AND CONSTR | MoRTH | N24002153 | 3-2023 | 2/2024 | N.A. | 8/2025 | 169.68 |  | 169.68 | 112.18 | 79
May 2025 |  |  | 1358 | CONSTRUCTION OF BYPASS TO MADURAI - ACHAMBATHU - VIRATIPATHU IN KM 6/850 - 10/382 OF NH 49 EXTN. (NE | MoRTH | N24002165 | 3-2022 | 8/2026 | N.A. | 8/2026 | 238.97 | 260.07 | 260.07 | 108.95 | 48
May 2025 |  |  | 1359 | ACCESS CONTROLLED HIGHWAY OF 4 LANE WITH PAVED SHOULDERS FROM TIRUVALLUR (DESIGN CHAINAGE KM 17+56) | NHAI | N24002216 | 12-2024 | 12/2026 | N.A. | 12/2026 | 1376.1 |  | 1376.1 | 0 | 7.03
May 2025 |  |  | 1360 | KAKATIYAKHANI OPENCAST III PROJECT PHASE-1 | SCCL | N06000161 | 3-2017 | 3/2022 | N.A. | 3/2026 | 413.84 |  | 413.84 | 397.54 | 85
May 2025 |  |  | 1361 | GODAVARIKHANI COAL MINE | SCCL | N06000202 | 7-2019 | 3/2023 | N.A. | 3/2026 | 438.98 |  | 438.98 | 171.96 | 70
May 2025 |  |  | 1362 | VENKATESH KHANI COAL MINE | SCCL | N06000204 | 10-2020 | 3/2023 | N.A. | 3/2027 | 484.51 |  | 484.51 | 318.12 | 55
May 2025 |  |  | 1363 | RCE OF RAMAGUNDAM OPENCAST II EXTENSION PROJECT | SCCL | N06000210 | 11-2015 | 3/2023 | N.A. | 3/2026 | 489.62 |  | 489.62 | 405.54 | 70
May 2025 |  |  | 1364 | RCE OF INDARAM OPENCAST PROJECT | SCCL | N06000211 | 8-2017 | 3/2021 | N.A. | 3/2025 | 349.28 |  | 424.81 | 402.64 | 80
May 2025 |  |  | 1365 | RCE OF KALYANIKHANI OPENCAST PROJECT | SCCL | N06000213 | 3-2016 | 3/2020 | N.A. | 3/2026 | 384.32 |  | 384.32 | 260.96 | 75
May 2025 |  |  | 1366 | RCE OF KAKATHIYAKHANI OC - 2 PROJECT | SCCL | N06000214 | 8-2017 | 3/2020 | N.A. | 3/2026 | 442.42 |  | 442.42 | 203 | 63
May 2025 |  |  | 1367 | GOLETI OPENCAST MINE | SCCL | N06000258 | 7-2021 | 3/2026 | N.A. | 3/2026 | 345.6 |  | 345.6 | 68.47 | 20
May 2025 |  | HEALTH AND FAMILY WELFARE | 1368 | COMPREHENSIVE PLANNING, DESIGNING, EXECUTION OF ALL INDIA INSTITUTE OF MEDICAL SCIENCES AT BIBINAGAR | HITES | N21000031 | 12-2018 | 7/2024 | N.A. | 12/2025 | 1110.55 |  | 1110.55 | 743.76 | 82.04
May 2025 |  | HEALTH AND FAMILY WELFARE | 1369 | ESTABLISHMENT OF NATIONAL ANIMAL RESOURCE FACILITY FOR BIOMEDICAL RESEARCH AT HYDERABAD | CPWD FOR HEALTH | N28000098 | 10-2016 | 3/2020 | Jan-2025 | 1/2025 | 209.84 | 281.05 | 281.05 | 253.13 | 98.5
May 2025 |  | RAILWAYS | 1370 | MANOHARABAD-KOTHPALL NEW LINE(SCR) | SCR | N22000032 | 4-2006 | 3/2027 | N.A. | 3/2025 | 1160 |  | 3014 | 1535.65
May 2025 |  | RAILWAYS | 1371 | REHABILITATION AND UPGRADATION OF NH -565 FROM KM 1.00 TO 86.057 (NAKREKAL TO NAGARJUNSAGAR DAM SECT | MoRTH | N24000245 | 1-2014 | 3/2016 | Sep-2019 | 9/2019 | 270 |  | 270 | 0 | 72.15
May 2025 |  | RAILWAYS | 1372 | REHABILITATION AND UPGRADATION OF NH-221 FROM KM 121/0 TO 165/00 (OF VIJAYAWADA-JAGDALPUR RUDRAMPUR | MoRTH | N24000247 | 10-2014 | 2/2017 | N.A. | 2/2017 | 295.47 |  | 295.47 | 224.42 | 98.15
May 2025 |  | RAILWAYS | 1373 | EPC- CORRIDOR APPROACH WORKS - NH (O): WIDENING EXISTING 2 LANE TO 2 LANE WITH PAVED SHOULDERS IN KM | MoRTH | N24000248 | 3-2015 | 1/2017 | N.A. | 1/2017 | 153.21 |  | 153.21 | 100.96 | 93.81
May 2025 |  | RAILWAYS | 1374 | WIDEINING TO TWO/FOUR LANE WITH PAVED SHOULDERS FROM EXISTING KM 182.120 TO KM 227.600 OF NH-167 ON | MoRTH | N24000980 | 10-2016 | 2/2019 | N.A. | 2/2019 | 298.32 |  | 298.32 | 178.47 | 98
May 2025 |  |  | 1375 | WIDEINING TO TWO/FOUR LANE WITH PAVED SHOULDERS FROM EXISTING KM 180.60 TO KM 223.00 OF NH-63 ON NIZ | MoRTH | N24000981 | 10-2016 | 3/2019 | N.A. | 3/2019 | 248.83 |  | 248.83 | 173.79 | 100
May 2025 |  |  | 1376 | WIDENING TO TWO LANE WITH PAVED SHOULDERS FROM KM 40/410 TO KM 84/037OF THIRUMALAGIRI TO SURYAPET SE | MoRTH | N24000982 | 1-2017 | 5/2019 | N.A. | 5/2019 | 244.54 |  | 244.54 | 174.35 | 100
May 2025 |  |  | 1377 | WIDENING TO TWO LANE WITH PAVED SHOULDERS FROM KM 0/970 TO KM 40/410 OF JANAGAON-THIRUMALAGIRI OF NH | MoRTH | N24000983 | 1-2017 | 10/2019 | N.A. | 10/2019 | 196.52 |  | 196.52 | 125.53 | 100
May 2025 |  |  | 1378 | WIDENING TO TWO LANE WITH PAVED SHOULDERS FROM KM 15.525 TO KM 62.880 OF JADCHERLA-KALWAKURTHY SECTI | MoRTH | N24000984 | 1-2017 | 12/2019 | N.A. | 12/2019 | 283 |  | 283 | 259.15 | 100
May 2025 |  |  | 1379 | WIDENING TO TWO LANE WITH PAVED SHOULDERS FROM KM 67.00 TO 114.425 OF KALWAKURTHY-MALLEPALLY SECTION | MoRTH | N24000986 | 1-2017 | 5/2019 | N.A. | 5/2019 | 300 |  | 300 | 239.93 | 96.05
May 2025 |  |  | 1380 | 6 LANING FROM KM 9.90 TO KM 19.948 (ARAMGARH-SAMSHABAD SECTION) OF HYDERABAD-SAMSHABAD SECTION OF NH | MoRTH | N24000987 | 1-2018 | 5/2020 | N.A. | 5/2020 | 283.15 |  | 283.15 | 270.01 | 92.59
May 2025 |  |  | 1381 | WIDENING AND STRENGTHENING OF EXISTING 2-LANE TO 2-LANE WITH PAVED SHOULDERS FROM KM.159/0 TO 165/4 | MoRTH | N24000988 | 1-2018 | 12/2019 | N.A. | 12/2019 | 230.03 |  | 230.03 | 231.31 | 99.9
May 2025 |  |  | 1382 | WIDENING AND STRENGTHENING OF EXISTING CARRIAGEWAY IN 2 LANE WITH PAVED SHOULDERS FROM KM.25/0 TO 59 | MoRTH | N24000989 | 2-2018 | 6/2020 | N.A. | 6/2020 | 206.13 |  | 206.13 | 190.94 | 98.36
May 2025 |  |  | 1383 | REHABILITATION AND UPGRADATION OF NH-167 FROM DESIGN KM.113.900 TO 154.479 (MALLEPALLY - HALIYA SECT | MoRTH | N24000990 | 2-2018 | 11/2019 | N.A. | 11/2019 | 294.13 |  | 294.13 | 198.75 | 87.44
May 2025 |  |  | 1384 | REHABILITATION AND UPGRADATION OF NH-167 FROM DESIGN KM.187.723 TO 234.434 (MIRYALAGUDA TO KODAD SEC | MoRTH | N24000993 | 3-2018 | 9/2020 | N.A. | 9/2020 | 322.81 |  | 322.81 | 315.23 | 98.09
May 2025 |  |  | 1385 | CONSTRUCTION OF SIX LANE ELEVATED CORRIDOR FROM KM.7.950 (UPPAL) TO KM.14.200 OF NH-163 TO DE-CONGES | MoRTH | N24000994 | 3-2018 | 7/2020 | N.A. | 2/2026 | 626.76 |  | 626.76 | 272.64 | 45.3
May 2025 |  |  | 1386 | REHABILITATION AND UP-GRADATION TO TWO LANE WITH PAVED SHOULDERS FROM KM 0/0 TO 72/6 OF NH-365 (NAKR | MoRTH | N24000996 | 1-2017 | 10/2019 | N.A. | 10/2019 | 605.08 |  | 605.08 | 413.37 | 99.84
May 2025 |  |  | 1387 | REHABILITATION AND UP GRADATION FROM KM. 121/0 TO 154/0 OF NAKAREKAL ? MALLAMPALLY SECTION OF NH-365 | MoRTH | N24000997 | 3-2018 | 7/2019 | N.A. | 7/2019 | 192.67 |  | 192.67 | 176.37 | 92
May 2025 |  |  | 1388 | WIDENING AND STRENGTHENING/ RECONSTRUCTION OF EXISTING PAVEMENT TO FOUR ALNE WITH PAVED SHOULDERS FR | MoRTH | N24000998 | 1-2019 | (N.A.) | {} |  | 193.19 |  | 249.72 | 222.58 | 95
May 2025 |  |  | 1389 | KHAMMAM-DEVARAPALLE PKG I [4L ACCESS CONTROLLED (GREENFIELD) FROM THALLAMPADU VILLAGE TO SOMAVARAM | NHAI | N24001482 | 8-2022 | 10/2024 | Aug-2022 | 12/2025 | 772.11 |  | 772.11 | 519.84 | 78
May 2025 |  |  | 1390 | KHAMMAM DEVARAPALLE PKG II 4L ACCESS CONTROLLED (GREENFIELD) FROM SOMAVARAM VILLAGE TO CHINTAGUDEM V | NHAI | N24001483 | 2-2022 | 9/2024 | Feb-2022 | 9/2025 | 637.11 |  | 637.11 | 415.97 | 84.71
May 2025 |  |  | 1391 | KHAMMAM-DEVARAPALLE PKG III [4L ACCESS CONTROLLED (GREENFIELD) FROM CHINTAGUDEM VILLAGE TO RECHERLA | NHAI | N24001484 | 9-2022 | 2/2024 | Sep-2022 | 9/2025 | 804.69 |  | 804.69 | 514.29 | 89.75
May 2025 |  |  | 1392 | 4L OF KODAD (DESIGN KM 0.00/EXISTING KM 185.00 OF NH-65) TO KHAMMAM (DESIGN KM 31.800/EXISTING KM 29 | NHAI | N24001522 | 1-2021 | 1/2024 | Jan-2021 | 7/2025 | 1307.95 |  | 1307.95 | 707.34 | 99.79
May 2025 |  |  | 1393 | 6 LANING OF EXISTING 4-LANE STRETCH FROM KALKALLU AT KM.454+000 TO GUNDLA POCHAMPALLY AT KM.471+000, | NHAI | N24001555 | 3-2022 | 1/2025 | N.A. | 1/2025 | 955.49 |  | 955.49 | 233.46 | 35.96
May 2025 |  |  | 1394 | 6L OF EXISTING 4L FROM GUNDLAPOCHAMPALLY TO BOWENPALLY FROM KM 471.300 TO KM 481.331 OF NH-44 | NHAI | N24001556 | 12-2021 | 7/2024 | N.A. | 7/2024 | 521.53 |  | 521.53 | 250.7 | 48.76
May 2025 |  |  | 1395 | 6L ACCESS CONTROLLED GREENFIELD HIGHWAY OF JULEKAL VILLAGE TO DINNEDEVARAPADU VILLAGE FROM KM 242.20 | NHAI | N24001625 | 1-2022 | 1/2025 | N.A. | 7/2025 | 1227.57 |  | 1227.57 | 288.58 | 44.49
May 2025 |  |  | 1396 | 6L ACCESS CONTROLLED GREENFIELD HIGHWAY OF NANDINNE VILLAGE TO JULEKAL VILLAGE FROM KM 202.900 TO KM | NHAI | N24001626 | 2-2022 | 1/2025 | N.A. | 1/2025 | 972.06 |  | 972.06 | 408.48 | 66.81
May 2025 |  |  | 1397 | WIDENING AND STRENGTHENING OF EXISTING 2 LANE WITH PAVED SHOULDER TO 4 LANE WITH PAVED SHOULDER FRO | MoRTH | N24002000 | 3-2021 | 7/2024 | N.A. | 7/2024 | 317.19 |  | 317.19 | 162.21 | 70
May 2025 |  |  | 1398 | WIDENING TO 2 LANE WITH PAVED SHOULDERS OF MEDAK - SIDDIPET SECTION FROM KM 0/0 TO KM 69/978 OF NH- | MoRTH | N24002001 | 1-2022 | 1/2025 | N.A. | 6/2025 | 882.18 |  | 882.18 | 206.02 | 71
May 2025 |  |  | 1399 | WIDENING AND IMPROVEMENT OF EXISTING CARRIAGE WAY TO 2 LANE WITH PAVED SHOULDERS FROM KM. 86/160 TO | MoRTH | N24002002 | 1-2022 | 12/2024 | N.A. | 12/2024 | 423.48 |  | 423.48 | 149.27 | 71.08
May 2025 |  |  | 1400 | REHABILITATION AND UP-GRADATION OF VALIGONDA TO THORRUR SECTION TO TWO LANE WITH PAVED SHOULDERS FRO | MoRTH | N24002003 | 1-2022 | 12/2024 | N.A. | 12/2024 | 549.28 |  | 549.28 | 103.51 | 70
May 2025 |  |  | 1401 | REHABILITATION AND UPGRADATION OF LB- NAGAR TO MALKAPUR SECTION TO 6-LANE MAIN CARRIAGEWAY WITH SERVI | MoRTH | N24002004 | 3-2021 | 7/2024 | N.A. | 6/2025 | 545.11 |  | 545.11 | 191.56 | 75.92
May 2025 |  |  | 1402 | WIDENING TO TWO LANE WITH PAVED SHOULDERS OF 'BODHAN BASAR BHAINSA ' SECTION FROM KM 38/900 TO 95/3 | MoRTH | N24002005 | 3-2022 | 3/2025 | N.A. | 6/2025 | 644.45 |  | 644.45 | 182.85 | 92.5
May 2025 |  |  | 1403 | ONSTRUCTION OF 4-LANE FLYOVER AT AMBERPET-X ROAD, HYDERABAD ON NH- 202 IN THE STATE OF TELANGANA | MoRTH | N24002006 | 10-2017 | 6/2023 | N.A. | 6/2023 | 186.71 |  | 186.71 | 149.64 | 91.5
May 2025 |  |  | 1404 | WIDENING TO TWO LANE WITH PAVED SHOULDERS FROM KM 0/000 TO KM 79/300 OF KALWAKURTHY - KOLLAPUR SECTI | MoRTH | N24002007 | 3-2022 | 7/2025 | N.A. | 7/2025 | 886.69 |  | 886.69 | 90.46 | 59.29
May 2025 |  |  | 1405 | WIDENING TO 2 LANE WITH PAVED SHOULDERS OF SIDDIPET-ELKATHURTHY SECTION FROM KM 69/978 TO KM 133/6 | MoRTH | N24002008 | 1-2022 | 12/2024 | N.A. | 12/2024 | 578.85 |  | 578.85 | 172.76 | 79.25
May 2025 |  |  | 1406 | WIDENING AND STRENGTHENING TO 2/4 LANE WITH PAVED SHOULDERS OF MAHABUBNAGAR ? CHINCHOLI SECTION FROM | MoRTH | N24002009 | 1-2022 | 1/2025 | N.A. | 7/2025 | 703.68 |  | 703.68 | 193.39 | 61
May 2025 |  |  | 1407 | WIDENING AND STRENGTHENING TO 4 LANE / 2-LANE WITH PAVED SHOULDERS OF MAHABUBNAGAR-CHINCHOLI SECTION | MoRTH | N24002010 | 3-2022 | 3/2024 | N.A. | 10/2025 | 631.49 |  | 631.49 | 7.92 | 25
May 2025 |  |  | 1408 | IMPROVEMENT OF GEOMETRICS OF THONDUPALLY TO KOTHUR FROM KM 22.300 TO KM 34.14 OF NH-44-RCW | NHAI | N24002082 | 2-2022 | 9/2024 | N.A. | 1/2026 | 541.58 |  | 541.58 | 34.89
May 2025 |  |  | 1409 | FOUR LANING OF KARIMNAGAR- WARANGAL SECTION OF NH-563 FROM DESIGN CH.48.860 KM NEAR SH-1 CH.170.400 K | NHAI | N24002083 | 3-2022 | 7/2025 | N.A. | 7/2025 | 2146.86 | 2413 | 2414.46 | 999.41 | 71.83
May 2025 |  |  | 1410 | CONSTRUCTION OF 4-LANE ACCESS CONTROLLED GREENFIELD HIGHWAY SECTION ON NH-163G (KHAMMAM- VIJAYAWADA) | NHAI | N24002190 | 3-2023 | 8/2026 | N.A. | 8/2026 | 983 |  | 983 | 0 | 8.5
May 2025 |  |  | 1411 | CONSTRUCTION OF 4-LANE ACCESS CONTROLLED GREENFIELD HIGHWAY SECTION ON NH-163G (KHAMMAM - VIJAYAWADA | NHAI | N24002236 | 3-2023 | 3/2025 | N.A. | 3/2027 | 832.62 |  | 832.62 | 0
May 2025 |  | PETROLEUM | 1412 | GRASS ROOT RAIL FED DEPOT AT SEKERKOTE, AGARTALA AS RESITEMENT OF EXISTING DHARMANAGAR DEPOT | IOCL | N16000495 | 6-2022 | 8/2025 | Sep-2025 | 9/2025 | 656 |  | 656 | 415.86 | 82.2
May 2025 |  | PETROLEUM | 1413 | REHABILITATION AND UPGRADATION OF ROAD FROM KM 0.00 TO KM 18.600 OF KUMARGHAT-KAILASHAHAR SECTION | NHIDCL | N24001263 | 6-2020 | 1/2022 | Feb-2024 | 12/2024 | 277.5 | 302.02 | 302.02 | 260.38 | 99.94
May 2025 |  | PETROLEUM | 1414 | KAILASHAHAR TO KHOWAI PKG-4 | NHIDCL | N24001309 | 11-2020 | 6/2022 | Oct-2023 | 11/2024 | 159.13 | 171.5 | 171.5 | 84.33 | 100
May 2025 |  | PETROLEUM | 1415 | 2-LANING FROM JOLAIBARI - BELONIA | NHIDCL | N24001317 | 6-2020 | 1/2022 | N.A. | 4/2025 | 201.99 |  | 287.47 | 148.22 | 100
May 2025 |  | PETROLEUM | 1416 | MANU-SIMLUNG ( PKG 4) | NHIDCL | N24001363 | 3-2021 | 12/2022 | N.A. | 12/2025 | 354.79 |  | 354.79 | 34.08
May 2025 |  |  | 1417 | 2 LANING FROM MANU-SIMLUNG PKG-2 | NHIDCL | N24001542 | 2-2022 | 1/2025 | May-2025 | 5/2025 | 456.88 |  | 456.88 | 122.23 | 49.88
May 2025 |  |  | 1418 | IMPROVEMENT AND WIDENING TO 2-LANE WITH EARTHEN PAVED SHOULDER FROM UDAIPUR TO SRIMANTAPUR | NHIDCL | N24001914 | 5-2023 | 11/2024 | N.A. | 12/2025 | 195.95 |  | 195.95 | 38.1 | 45.3
May 2025 |  |  | 1419 | 4 LANE WITH PAVED SHOULDER AGARTALA BYPASS (WESTERN SIDE) CONNECTING NH- 8 | NHIDCL | N24002132 | 3-2023 | 3/2027 | N.A. | 3/2027 | 2026.05 |  | 2026.05 | 26.34 | 8.38
May 2025 |  |  | 1420 | REHABILITATION AND UP-GRADATION OF ROAD FROM DESIGN KM 25.250 TO KM 36.460 (TOTAL LENGH: 11.210 KM) | NHIDCL | N24002159 | 2-2020 | 3/2026 | N.A. | 3/2026 | 174.43 |  | 174.43 | 9.34 | 16.61
May 2025 |  |  | 1421 | IMPROVEMENT AND WIDENING TO 2-LANE WITH PAVED SHOULDER OF ROAD FROM KM 101.300 TO KM 127.319 (TOTAL | NHIDCL | N24002160 | 1-2024 | 7/2026 | N.A. | 7/2026 | 431.78 |  | 431.78 | 52.82 | 34.61
May 2025 |  |  | 1422 | KHOWAI ?TELIAMURA-AMARPUR-HARINA- SABROOM PACKAGE-2 | NHIDCL | N24002161 | 1-2024 | 9/2026 | N.A. | 9/2026 | 657.21 |  | 657.21 | 26.37 | 31.5
May 2025 |  |  | 1423 | KHOWAI ?TELIAMURA-AMARPUR-HARINA- SABROOM PACKAGE-3 | NHIDCL | N24002162 | 1-2024 | 9/2026 | N.A. | 9/2026 | 670.9 |  | 670.9 | 0 | 2
May 2025 |  |  | 1424 | CHAMPAK NAGAR TO KHAYERPUR SECTION (DESIGN KM 242+500 TO KM 261+610) | NHIDCL | N24002205 | 12-2023 | 9/2026 | N.A. | 9/2026 | 920.66 |  | 920.66 | 73.41 | 22
May 2025 |  |  | 1425 | KHOWAI ?TELIAMURA-AMARPUR-HARINA- SABROOM SECTION PKG-4 | NHIDCL | N24002228 | 1-2024 | 12/2026 | N.A. | 12/2026 | 726.9 |  | 726.9 | 0 | 3.1
May 2025 |  |  | 1426 | CCS INTERNATIONAL AIRPORT , LUCKNOW | AAI | N04000077 | 6-2018 | 9/2021 | Oct-2026 | 10/2026 | 1383 | 1938 | 3291.81 | 2645.52 | 80.37
May 2025 |  |  | 1427 | DEVELOPMENT OF AYODHYA AIRPORT PHASE-01 | AAI | N04000094 | 3-2021 | 12/2022 | Jun-2025 | 6/2025 | 242.14 | 328 | 358 | 344.58 | 99.9
May 2025 |  |  | 1428 | PRAYAGRAJ AIRPORT - CONSTRUCTION OF NEW TERMINAL BUILDING, SECOND LINK TAXI TRACK, APRON EXPANSION, | AAI | N04000102 | 5-2023 | 11/2024 | Jul-2025 | 7/2025 | 185.75 | 274.38 | 274.38 | 200.46 | 95
May 2025 |  |  | 1429 | AGRA: DEVELOPMENT OF NEW CIVIL ENCLAVE AT AGRA AIRPORT. | AAI | N04000113 | 6-2024 | 7/2026 | N.A. | 7/2026 | 579 |  | 579 | 56.17 | 11.5
May 2025 |  |  | 1430 | VARANASI: DEVELOPMENT OF LAL BAHADUR SHASTRI INTERNATIONAL AIRPORT, VARANASI. | AAI | N04000114 | 7-2024 | 7/2027 | N.A. | 7/2027 | 2869.65 |  | 2869.65 | 255.45 | 14.5
May 2025 |  | COAL | 1431 | NEYVELI UTTAR PRADESH POWER PROJECT LIMITED 1980 MW | NLC | N06000152 | 7-2016 | 11/2021 | Oct-2025 | 10/2025 | 17237 | 21780.94 | 21780.94 | 19854.8 | 90.89
May 2025 |  | COAL | 1432 | KHADIA EXPANSION OCP | NCL | N06000208 | 6-2021 | 3/2025 | N.A. | 3/2027 | 491.67 |  | 491.67 | 185.6 | 39.73
May 2025 |  | PETROLEUM | 1433 | 60 KTA POLYPROPYLENE PROJECT | GAIL | N16000429 | 3-2019 | 4/2024 | Apr-2024 | 6/2025 | 910.56 | 1299.02 | 1299.02 | 961 | 95.8
May 2025 |  | PETROLEUM | 1434 | AUGMENTATION OF FACILITIES AT MATHURA BITUMEN PLANT | IOCL | N16000505 | 4-2022 | 4/2025 | Dec-2026 | 12/2026 | 260.12 |  | 260.12 | 1.03 | 25
May 2025 |  | PETROLEUM | 1435 | GRASS-ROOT TERMINAL AT MIRZAPUR UTTAR PRADESH | IOCL | N16000506 | 9-2022 | 6/2026 | N.A. | 11/2026 | 980.45 |  | 980.45 | 200.55 | 49.8
May 2025 |  | PETROLEUM | 1436 | CITY GAS DISTRIBUTION PROJECTS AT LAKHIMPUR KHERI , SITAPUR, BAHRAICH, SHRAVASTI,BALRAMPUR, | BPCL | N16000525 | 12-2022 | 6/2030 | N.A. | 6/2030 | 16654 |  | 16654 | 544.01 | 9.5
May 2025 |  | PETROLEUM | 1437 | KHURJA SUPER THERMAL POWER PROJECT | THDCIL | N18000272 | 3-2019 | 9/2023 | N.A. | 7/2025 | 11089.42 | 13276.16 | 13276.16 | 12317.27 | 95.5
May 2025 |  | PETROLEUM | 1438 | SINGRAULI SUPER THERMAL POWER PROJECT, STAGE-III (2X800 MW) | NTPC | N18000382 | 3-2024 | 2/2030 | N.A. | 2/2030 | 17195.31 |  | 17195.31 | 1302.8 | 1
May 2025 |  |  | 1439 | TRANSMISSION SYSTEM FOR EVACUATION OF POWER FROM RAJASTHAN REZ PH-IV (PART-4: 3.5 GW): PART A | PGCIL | N18000407 | 12-2024 | 12/2026 | N.A. | 12/2026 | 5846 |  | 5846 | 78.74
May 2025 |  |  | 1440 | TRANSMISSION SYSTEM FOR STRENGTHENING TO FACILITATE EVACUATION OF POWER FROM BHADLA/BIKANER COMPLEX | PGCIL | N18000423 | 12-2024 | 6/2026 | N.A. | 6/2026 | 213 |  | 213 | 0
May 2025 |  |  | 1441 | BURHWAL - GONDA - 3RD RUNNING LINE. | NER | N22000468 | 4-2016 | 3/2025 | N.A. | 9/2025 | 1015.59 |  | 1250 | 1178.02 | 50
May 2025 |  |  | 1442 | SHAHGANJ-BHATNI-PHEPHNA-INDARA, MAU- SHAHGANJ (EXCL. MAU-INDARA) PATCH DOUBLING. | NER | N22000470 | 4-2016 | 12/2024 | N.A. | 8/2025 | 1177.96 |  | 2145 | 2050.16 | 81
May 2025 |  |  | 1443 | JHANSI MANIKPUR AND KHAIRAR BHIMSEN DOUBLING | NCR | N22000495 | 3-2018 | 3/2026 | N.A. | 3/2027 | 4329.53 |  | 4329.53 | 2008.74 | 50
May 2025 |  |  | 1444 | JHANSI BINA DOUBLING | NCR | N22000496 | 9-2016 | 3/2022 | N.A. | 4/2026 | 2002 |  | 2001 | 1725.18 | 90
May 2025 |  |  | 1445 | MATHURA-JHANSI-3RD LINE (273.80 KM) | RVNL | N22000501 | 6-2016 | 12/2024 | N.A. | 12/2024 | 5323.39 |  | 5190.26 | 5046.07
May 2025 |  |  | 1446 | SURFACE TRIANGLE LINE BETWEEN BHADURA STATION AND NEW CROSSING STN KARMA DOUBLING | ECR | N22000525 | 10-2022 | 10/2027 | N.A. | 10/2027 | 199.96 |  | 199.96 | 55.09
May 2025 |  |  | 1447 | MUGHALSARAI - ALLAHABAD - 3RD LINE | NCR | N22000544 | 8-2019 | 12/2026 | N.A. | 12/2026 | 2649.44 |  | 2390 | 83.1 | 55
May 2025 |  |  | 1448 | ALIGARH-HARDUAGANJ FLYOVER (22 KM) | NCR | N22000545 | 4-2020 | 6/2026 | N.A. | 6/2026 | 1456.89 | 1244.13 | 1456.89 | 10.14 | 8.1
May 2025 |  |  | 1449 | LALITPUR - BIRARI WITH FLYOVER AT LALITPUR | NCR | N22000546 | 3-2017 | 12/2024 | N.A. | 11/2025 | 356.09 |  | 356 | 196.83 | 65
May 2025 |  |  | 1450 | ALIGARH-DAUD KHAN - 3RD LINE 6.9 KM AND CONSTRUCTION OF FLYOVER AT DAUD KHAN | NCR | N22000562 | 4-2019 | 12/2025 | N.A. | 12/2025 | 451.99 | 779.49 | 779.49 | 122.08 | 43
May 2025 |  |  | 1451 | ALLAHABAD-BAMHRAULI - 4TH LINE (10 KM) WITH FLY-OVER AT SUBEDARGANJ | NCR | N22000563 | 4-2019 | 3/2026 | N.A. | 3/2026 | 494.11 |  | 494.11 | 42.61 | 42
May 2025 |  |  | 1452 | BHANDAI - FLYOVER FOR ETAWAH BOUND DOWN TRAINS | NCR | N22000564 | 4-2019 | 12/2025 | N.A. | 3/2026 | 187.21 |  | 250.17 | 1.29 | 8
May 2025 |  |  | 1453 | SAHJANWA - DOHRIGHAT | NER | N22000565 | 8-2019 | 3/2029 | N.A. | 6/2027 | 371.77 |  | 1319.75 | 569.15 | 3
May 2025 |  |  | 1454 | BAHRAICH - NANPARA -NEPALGANJ (56.15 KM) | NER | N22000566 | 7-2020 | 12/2024 | N.A. | 6/2025 | 950 |  | 500 | 402.22 | 22
May 2025 |  |  | 1455 | BAHRAICH SRAVASTI BALRAMPUR | TULSIPUR | NER | 10-2018 | 10/2030 | N.A. | 3/2028 | 4939.78 |  | 4939.78 | 1114.69 | 7
May 2025 |  |  | 1456 | JANGHAI PRATAPGARH AMETHI DOUBLING | NR | N22000583 | 11-2017 | 3/2025 | N.A. | 12/2025 | 721.72 |  | 1100 | 58.98 | 70
May 2025 |  |  | 1457 | BARABANKI MALHAUR 3RD AND 4TH LINE | 32.84 KM | NR | 1-2019 | 3/2025 | Jan-2026 | 12/2025 | 323.85 |  | 407 | 5.17 | 58
May 2025 |  |  | 1458 | DOUBLING BETWEEN JAUNPUR JN- ZAFFARABAD (6.28 KM) | NR | N22000591 | 3-2023 | 12/2026 | N.A. | 12/2026 | 177.33 |  | 177.33 | 0.89 | 10
May 2025 |  |  | 1459 | JANGHAI-PHAPHAMAU - DOUBLING WITH ELECTRIFICATION (46.79 KM) | RVNL | N22000596 | 11-2018 | 3/2025 | N.A. | 3/2025 | 357.48 |  | 409.38 | 362.09
May 2025 |  |  | 1460 | BHATNI - AUNRIHAR WITH ELECTRIFICATION (125 KM) (EXCL INDARA - MAU (116.95 KM)) | RVNL | N22000598 | 5-2018 | 12/2024 | N.A. | 2/2025 | 2529.46 |  | 2529.46 | 1636.33
May 2025 |  |  | 1461 | MATHURA - VRINDAVAN (11 KM) | NCR | N22000612 | 8-2022 | 6/2025 | N.A. | 6/2025 | 402.88 |  | 402.88 | 0
May 2025 |  |  | 1462 | DOMINGARH - GORAKHPUR - GORAKHPUR CANTT - KUSUMHI - 3RD RUNNING LINE | 21.15 KM | NER | 11-2016 | 2/2025 | N.A. | 7/2025 | 351.03 |  | 500.37 | 476.09 | 86
May 2025 |  |  | 1463 | CONSTRUCTION OF RING ROAD FOR RAEBARELI CITY (PHASE -I) ON EASTERN SIDE OF NH 24B | MoRTH | N24000331 | 12-2019 | 4/2022 | N.A. | 7/2025 | 282.41 |  | 319.96 | 276.35 | 88
May 2025 |  |  | 1464 | 4-LANNING OF HARIDWAR-NAGINA SECTION OF NH 74 FROM (KM 204.300 OF NH 58) TO KM 73.00 | NHAI | N24000564 | 3-2016 | 7/2020 | Jul-2025 | 7/2025 | 1408 | 1659.12 | 1659.12 | 1329.27 | 88.97
May 2025 |  |  | 1465 | SIX LANING OF HAPUR BYPASS TO MORADABAD SECTION INCLUDING HAPUR BYPASS FROM KM 50.000 (DESIGN CHAINA | NHAI | N24000798 | 3-2018 | 11/2021 | N.A. | 6/2025 | 2140.93 |  | 2140.93 | 2067.7 | 99.65
May 2025 |  |  | 1466 | TWO / FOUR LANING OF RAEBARELI - JAGDISHPUR SECTION OF NH-330A FROM KM. 0.000 TO KM. 47.800 (DESIGN | NHAI | N24001306 | 10-2020 | 3/2023 | N.A. | 8/2025 | 724.6 |  | 724.6 | 569.96 | 96
May 2025 |  |  | 1467 | CONSTRUCTION OF 6 LANE BRIDGE ON GANGA ON NH-96 AND ITS APPROACHES IN PHAPHAMAU ALLAHABAD ON EPC MOD | MoRTH | N24001421 | 7-2018 | 2/2024 | N.A. | 8/2025 | 1948.25 |  | 1948.25 | 1133.21 | 77
May 2025 |  |  | 1468 | CONSTRUCTION OF FOUR-LANE ELEVATED VIADUCT FROM KM.4+634 TO KM.6+345 ON NH-24A INCLUDING RETAINING W | MoRTH | N24001424 | 3-2021 | 9/2023 | N.A. | 1/2025 | 185.09 | 269.81 | 269.81 | 266.35 | 100
May 2025 |  |  | 1469 | REHABILITATION AND UPGRADATION TO 2 LANE WITH PS OF RADHAITA TO PILIBHIT SECTION OF 46.130 KM | MoRTH | N24001456 | 4-2020 | 2/2024 | N.A. | 1/2025 | 199.39 | 212.96 | 199.39 | 200.01 | 100
May 2025 |  |  | 1470 | REHABILITATION AND UPGRADATION TO 2 LANE WITH PS OF MIRANPUR KATRA TO RADHAITA SECTION OF NH-730C F | MoRTH | N24001457 | 4-2020 | 7/2024 | N.A. | 9/2025 | 172.5 | 169.56 | 172.5 | 106.06 | 73
May 2025 |  |  | 1471 | 2-LANE WITH PS OF BEWAR TO NEAR KARRI VILLAGE SECTION OF NH-92 FROM KM.0.00 TO 30.00 UNDER GNHCP | MoRTH | N24001461 | 4-2020 | 3/2024 | N.A. | 7/2025 | 236.47 |  | 236.47 | 145.88 | 87
May 2025 |  |  | 1472 | 2-LANE WITH PS OF NEAR KARRI VILLAGE TO ETAWAH SECTION OF NH-92 FROM KM.30.000 TO 57.346 UNDER GNHCP | MoRTH | N24001462 | 4-2020 | 7/2024 | N.A. | 7/2025 | 211.09 |  | 211.09 | 147.58 | 96
May 2025 |  |  | 1473 | PROJECTS- REHABILITATION AND UPGRADATION OF NH-731A FROM KM 0.00 TO KM.35.00 | MoRTH | N24001464 | 3-2021 | 8/2023 | N.A. | 7/2025 | 264.86 |  | 264.86 | 129.12 | 84
May 2025 |  |  | 1474 | IMPROVEMENT AND UPGRADATION TO TWO LANE WITH PAVED SHOULDER CONFIGURATION FROM EXISTING KM 55.00 TO | MoRTH | N24001469 | 11-2021 | 5/2024 | N.A. | 7/2025 | 307.11 |  | 307.11 | 199.38 | 91
May 2025 |  |  | 1475 | R/U TO 2-LANE WITH PS OF BEWAR TO ALLAHGANJ SECTION OF NH-730C FROM KM.0.00 TO 52.770 UNDER GNHCP | MoRTH | N24001471 | 4-2020 | 11/2024 | N.A. | 7/2025 | 325.24 | 340.16 | 325.24 | 284.35 | 96
May 2025 |  |  | 1476 | WIDENING AND UPGRADATION TO FOUR LANE CONFIGURATION FROM KM.34.900 | BHADOHI) TO KM.73.134 (JAUNPUR | MoRTH | 3-2021 | 5/2024 | N.A. | 7/2025 | 395.62 | 392.03 | 395.62 | 281.93 | 72
May 2025 |  |  | 1477 | WIDENING AND STRENGTHENING FROM KM 0.00 TO KM 15.089 OF NH-334A (PURKAJI- LAKSAR-HARIDWAR ROAD) TO TW | MoRTH | N24001480 | 10-2021 | 4/2024 | N.A. | 3/2025 | 227.06 |  | 227.06 | 141.89 | 100
May 2025 |  |  | 1478 | 6L ACCESS-CONTROLLED HIGHWAY FROM (GANESHPUR) TO(NEAR MOHAND) OF GANESHPUR ? DEHRADUN SECTION FROM K | NHAI | N24001523 | 3-2021 | 10/2023 | Jun-2025 | 6/2025 | 836.24 |  | 836.24 | 792.55 | 98.85
May 2025 |  |  | 1479 | 6L OF ACCESS-CONTROLLED HIGHWAY FROM MOHAND TO DAAT KALI TUNNEL OF GANESHPUR ? DEHRADUN SECTION FROM | NHAI | N24001524 | 3-2021 | 10/2023 | Jun-2025 | 6/2025 | 990.28 |  | 990.28 | 997.62 | 98.79
May 2025 |  |  | 1480 | WIDENING AND STRENGTHENING OF SECTION FROM BHARTHANA CHOWK TO KODARKOOT (KM. 0.00 TO KM. 40.00) OF | MoRTH | N24001587 | 3-2020 | 9/2024 | N.A. | 7/2025 | 262.37 | 343.77 | 343.77 | 278.92 | 85
May 2025 |  |  | 1481 | 4L SPUR OF SHAMLI-MUZZAFARNAGAR CONNECTING NH-709AD (PANIPAT-SHAMLI- MUZAFFARNAGAR) AND NH-58 (MEERUT | NHAI | N24001726 | 1-2023 | 8/2024 | N.A. | 8/2024 | 391.26 |  | 391.26 | 14.12 | 80.3
May 2025 |  |  | 1482 | IMPROVEMENT AND UP-GRADATION OF EXISTING ROAD TO 2/4L PS FROM KM 40.000 TO 88.750, START OF KHUTAR B | NHAI | N24001727 | 3-2022 | 2/2025 | N.A. | 9/2025 | 762.62 |  | 838.68 | 561.21 | 94.75
May 2025 |  |  | 1483 | 4L SPUR OF PANIPAT - SHAMLI CONNECTING NH-709AD (PANIPAT ? SHAMLI ? MUZAFFARNAGAR) AND NH-709A (KARN | NHAI | N24001729 | 8-2022 | 4/2024 | N.A. | 7/2025 | 326.79 |  | 329.79 | 113.42 | 96
May 2025 |  |  | 1484 | 4L FROM GAJU VILLAGE AT KM 32.982 TO DEVINAGAR BYPASS (END) AT KM 208.000 OF NH 530B (PKG 1C) | NHAI | N24001730 | 12-2021 | 1/2025 | N.A. | 3/2025 | 1384.79 |  | 1384.79 | 657.94 | 97.98
May 2025 |  |  | 1485 | 6L GREENFIELD KANPUR - LUCKNOW (EXPRESSWAY) PKG II FROM KM. 28.500 TO KM. 73.744 | NHAI | N24001731 | 12-2021 | 5/2025 | May-2025 | 7/2025 | 2470.64 |  | 2335 | 691.28 | 87.62
May 2025 |  |  | 1486 | IMPROVEMENT AND UP-GRADATION OF EXISTING ROAD TO 4L PS FROM KM 229.070 TO 260.800, END OF HARDOI DIS | NHAI | N24001732 | 12-2021 | 10/2024 | N.A. | 7/2025 | 540.97 |  | 540.97 | 270.14 | 93.61
May 2025 |  |  | 1487 | 6L ACCESS CONTROLLED GREENFIELD HIGHWAY OF JUNCTION OF EPE (VILL.- MAVIKALAN) TO VILL.-LOHADDA FROM K | NHAI | N24001733 | 3-2022 | 8/2024 | N.A. | 7/2025 | 1602.48 |  | 1602.48 | 444.51 | 92
May 2025 |  |  | 1488 | 6L ACCESS CONTROL GREENFIELD HIGHWAY OF VILL-LOHADDA TO VILL- KARAUNDA MAHAJAN FROM KM. 27.000 TO KM. | NHAI | N24001734 | 3-2022 | 8/2024 | N.A. | 7/2025 | 1335.45 |  | 1335.45 | 462.61 | 82.45
May 2025 |  |  | 1489 | 6L ACCESS CONTROL GREENFIELD HIGHWAY OF VILL-KHYAWARI TO VILL- LATIFPUR AT SAHARANPUR BYPASS FROM KM | NHAI | N24001735 | 3-2022 | 8/2024 | N.A. | 7/2025 | 1428.19 |  | 1428.19 | 529.71 | 88.46
May 2025 |  |  | 1490 | 6L ACCESS CONTROL GREENFIELD HIGHWAY OF VILL-KARAUNDA MAHAJAN TO VILL-KHYAWARI FROM KM. 56.500 TO K | NHAI | N24001736 | 1-2022 | 8/2024 | N.A. | 7/2025 | 1159.96 |  | 1159.96 | 515.16 | 98.69
May 2025 |  |  | 1491 | 4LPS OF MUZAFFARNAGAR TO MIRANPUR SECTION OF NH-709AD, PKG-III | NHAI | N24001737 | 11-2021 | 4/2024 | N.A. | 4/2024 | 923.15 |  | 923.15 | 455.61 | 100
May 2025 |  |  | 1492 | 2LPS OF BIJNOR TO KOTAWALI SECTION OF NH-709AD, PKG-IV | NHAI | N24001738 | 9-2021 | 10/2023 | Dec-2024 | 12/2024 | 300.79 |  | 300.79 | 122.56 | 76.7
May 2025 |  |  | 1493 | REHABILITATION and UPGRADATION FROM 2 LANE TO 4 LANE OF NH STRETCH UNDER BHARATMALA PARIYOJANA FOR U | NHAI | N24001739 | 10-2019 | 11/2023 | Dec-2024 | 12/2024 | 1779.83 |  | 2200 | 1066 | 100
May 2025 |  |  | 1494 | 4L OF SHAMLI BYAPSS- SAHARANPUR FROM KM 92.2 TO KM 155.025 SECTION OF NH-709B, PKG-II | NHAI | N24001744 | 5-2019 | 11/2022 | N.A. | 7/2025 | 779.17 |  | 779.17 | 64.1 | 98.27
May 2025 |  |  | 1495 | KANPUR LUCKNOW EXPRESSWAY PKG-1 CONSTRUCTION OF 6-LANE TO EIGHT LANE OF KANPUR LUCKNOW EXPRESSWAY (N | NHAI | N24001745 | 12-2021 | 7/2025 | Jul-2025 | 7/2025 | 1972.1 |  | 1936 | 493.67 | 64.31
May 2025 |  |  | 1496 | 2-LANE EXISTING RAMPUR BYPASS OF RAMPUR TO BE DEVELOPED TO 4-LANE ON EPC MODE IN THE STATE OF UTTAR | NHAI | N24001746 | 3-2021 | 4/2024 | Jun-2025 | 6/2025 | 364.47 |  | 364.47 | 208.55 | 91.66
May 2025 |  |  | 1497 | 4 LANING OF NAJIBABAD BYPASS OF NH- 119 FROM KM. 105.423 TO KM. 118.373 (EXCLUDING 2.45 KM. OF NH-74 | NHAI | N24001753 | 2-2022 | 6/2024 | May-2025 | 5/2025 | 570.98 | 578.02 | 578.02 | 400.1 | 96.06
May 2025 |  |  | 1498 | SPUR OF MEERUT-GARH-MUKTESHWAR SECTION(NH-709A) CONNECTING NH-119 AND NH-58 BYPASSING MEERUT TOWN | NHAI | N24001754 | 1-2022 | 10/2024 | N.A. | 10/2024 | 953.79 |  | 953.79 | 384.66 | 68.59
May 2025 |  |  | 1499 | 4-LANING OF MEERUT NAJIBABAD SECTION FROM KM. 11.500 TO KM 39.250 AND KM 86.590 TO KM. 112.545.IN TH | NHAI | N24001755 | 10-2019 | 3/2023 | Dec-2024 | 12/2024 | 1936.68 |  | 2458.03 | 1380.9 | 100
May 2025 |  |  | 1500 | 4 LANE CONNECTOR FROM DELHI MEERUT EXPRESSWAY KM 50.000 TO KM 8.520 OF NH 235 IN THE STATE OF UTTAR | NHAI | N24001772 | 8-2021 | 3/2024 | Dec-2024 | 12/2024 | 1147.26 |  | 1147.26 | 81.34 | 60
May 2025 |  |  | 1501 | VARANASI RING ROAD (PKG-II) CONNECTING SANDAHA VILLAGE (KM 11.70 / NH-29) WITH REVASA VILLAGE (KM 81 | NHAI | N24001826 | 2-2019 | 2/2022 | Jun-2025 | 12/2025 | 927.77 |  | 1603 | 1202.77 | 91.25
May 2025 |  |  | 1502 | SIX LANE ACCESS CONTROLLED OF DELHI SAHARANPUR HIGHWAY FROM DELHI UP BORDER TO EPE JUNCTION CH.14.75 | NHAI | N24001830 | 6-2020 | 11/2023 | Dec-2024 | 12/2024 | 2002.79 |  | 2002.79 | 1989.85 | 99
May 2025 |  |  | 1503 | 4L FROM MATHURA BYPASS (START) AT EXISTING KM. 154.20 OF NH-44 TO GAJU VILLAGE AT KM 32.982 OF NH-53 | NHAI | N24001851 | 1-2022 | 3/2025 | N.A. | 3/2025 | 1738.2 |  | 1738.2 | 742.13 | 65
May 2025 |  |  | 1504 | 6L OF AGRA BYPASS (NORTHERN) CONNECTING KM. 174.500 OF NH-2 (NEW NH-19) TO KM. 141.000 OF YAMUNA EXP | NHAI | N24001852 | 10-2021 | 2/2025 | N.A. | 2/2025 | 957.62 |  | 957.62 | 832.8 | 86
May 2025 |  |  | 1505 | CONSTRUCTION OF LEFT OUT PORTION OF AGRA INNER RING ROAD CONNECTING VILLAGE DEORI TO NH-44 VILLAGE B | NHAI | N24001853 | 10-2021 | 9/2024 | Mar-2025 | 3/2025 | 772.05 |  | 772.05 | 593.39 | 67.5
May 2025 |  |  | 1506 | CONSTRUCTION OF 4-LANE GREEN FIELD HIGHWAY FROM KM. 35.000 TO KM. 49.155 OF NH-731A WITH PAVED SHOUL | MoRTH | N24001929 | 1-2022 | 10/2025 | N.A. | 10/2025 | 697.66 |  | 697.66 | 318.82 | 94
May 2025 |  |  | 1507 | BALANCE WORKS OF 4-LANNING OF RAMPUR-KATHGODAM SECTION OF NH-87 (NEW NH NO. 09) FROM KM. 0.000 (KM 1 | NHAI | N24001992 | 8-2022 | 2/2024 | Jun-2025 | 6/2025 | 199.31 | 244.26 | 244.26 | 190.1 | 91.87
May 2025 |  |  | 1508 | CONSTRUCTION OF TWO LANE WITH PAVED SHOULDER HIGHWAY FROM DESIGN CH.0.000 TO CH.49.2OO OF NH- 731B ON | MoRTH | N24001996 | 3-2022 | 11/2025 | N.A. | 11/2025 | 640.18 | 602.76 | 602.76 | 479.14 | 80
May 2025 |  |  | 1509 | CONSTRUCTION OF SHOHRATGARH BYPASS ON NH-730 UNDER EPC MODE IN THE STATE OF UTTAR PRADESH | MoRTH | N24001997 | 10-2022 | 5/2025 | N.A. | 2/2026 | 189.31 |  | 189.31 | 59.91 | 20
May 2025 |  |  | 1510 | IMPROVEMENT AND UPGRADATION TO TWO LANE WITH PAVED SHOULDER CONFIGURATION FROM EXISTING KM 90.00 TO | MoRTH | N24002015 | 11-2021 | 6/2025 | N.A. | 7/2025 | 403.36 | 328.49 | 403.36 | 137.71 | 70
May 2025 |  |  | 1511 | CONSTRUCTION OF PRATAPGARH BYPASS (EXTENSION) CONNECTING NH-31 TO NH- 330 | MoRTH | N24002016 | 10-2022 | 6/2025 | N.A. | 8/2025 | 225.17 |  | 225.17 | 96.21 | 55
May 2025 |  |  | 1512 | WIDENING TO FOUR LANE WITH PAVED SHOULDER FROM DESIGN KM.49.200 TO KM.89.285 OF NH-731B ON EPC MODE | MoRTH | N24002029 | 3-2022 | 1/2026 | N.A. | 1/2026 | 917.91 | 956.3 | 917.91 | 606.74 | 44
May 2025 |  |  | 1513 | CONSTRUCTION OF TWO LANE WITH PAVED SHOULDER FROM EXISTING KM.0.000 TO KM.55.610 (DESIGN KM. 0.000 T | MoRTH | N24002031 | 12-2021 | 2/2026 | N.A. | 2/2026 | 840.93 | 773.58 | 840.93 | 499.2 | 40
May 2025 |  |  | 1514 | CONSTRUCTION OF 4-LANE HIGHWAY WITH PAVED SHOULDERS FROM KM 49.155 TO KM 74.700 OF NH-731A ON HYBRID | MoRTH | N24002032 | 1-2022 | 1/2026 | N.A. | 1/2026 | 1156.72 |  | 1156.72 | 407.2 | 62
May 2025 |  |  | 1515 | DEVELOPMENT OF SIX-LANE ACCESS CONTROLLED HIGHWAY FROM GOGWAN JALALPUR (SHAMLI DISTRICT) TO RANIPUR | NHAI | N24002036 | 4-2022 | 5/2025 | N.A. | 5/2025 | 1843.59 |  | 1843.59 | 843.83 | 49
May 2025 |  |  | 1516 | GARHMUKTESHWAR (KM. 83.200 OF NH-24) TO MEERUT (KM. 9.860 OF NH-235) INCLUDING CONNECTOR TO NH-119 | NHAI | N24002073 | 10-2019 | 10/2023 | N.A. | 6/2025 | 2068.99 | 2171 | 2171 | 209.6 | 53.08
May 2025 |  |  | 1517 | CONSTRUCTION OF FOUR LANE HIGHWAY FORM GHAZIPUR BALLIA UP BIHAR STATE BORDER (GREENFIELD) SECTION OF | NHAI | N24002086 | 10-2022 | 7/2025 | N.A. | 7/2025 | 1706.47 |  | 1706.47 | 719.13 | 75
May 2025 |  |  | 1518 | CONSTRUCTION OF FOUR LANE HIGHWAY FROM GHAZIPUR BALLIA UP BIHAR STATE BORDER (GREENFIELD) SECTION OF | NHAI | N24002087 | 10-2022 | 10/2025 | N.A. | 10/2025 | 1493.14 |  | 1493.14 | 93.3 | 65
May 2025 |  |  | 1519 | CONSTRUCTION OF FOUR LANE HIGHWAY FROM GHAZIPUR BALLIA UP BIHAR STATE BORDER (GREENFIELD) SECTION OF | NHAI | N24002088 | 10-2022 | 8/2025 | N.A. | 8/2025 | 1493.5 |  | 1493.5 | 492.86 | 55
May 2025 |  |  | 1520 | CONSTRUCTION OF FOUR LANE HIGHWAY FROM GHAZIPUR BALLIA UP BIHAR STATE BORDER GREENFIELD SECTION OF N | NHAI | N24002089 | 10-2022 | 6/2025 | N.A. | 6/2025 | 617.87 |  | 617.88 | 106.2 | 71
May 2025 |  |  | 1521 | CONSTRUCTION OF FOUR-LANE ?WESTERN SIDE SPUR OF RAMPUR- RUDRAPUR SECTION CONNECTING NH-24 TO NH-87 BY | NHAI | N24002090 | 3-2021 | 11/2024 | Aug-2025 | 8/2025 | 646.27 |  | 646.27 | 91.95 | 45.61
May 2025 |  |  | 1522 | IMPROVEMENT , UP-GRADATION OF NH-734 SECTION OF MORADABAD - THAKURDWARA - KASHIPUR: ?PACKAGE-I: MORA | NHAI | N24002093 | 10-2022 | 9/2025 | N.A. | 9/2025 | 1841.92 |  | 1841.92 | 418.99 | 51.5
May 2025 |  |  | 1523 | IMPROVEMENT AND UP-GRADATION OF EXISTING ROAD TO 4L PS FROM KM 123.650 TO 175.080, FROM START OF SHA | NHAI | N24002094 | 9-2022 | 11/2025 | N.A. | 11/2025 | 1212.26 |  | 1212.26 | 329.68 | 30.27
May 2025 |  |  | 1524 | FOUR LANING OF SONAULI GORAKHPUR SECTION OF NH 29E (NEW NH 24) FROM DESIGN CH. 0.000 TO DESIGN CH. 7 | NHAI | N24002095 | 12-2021 | 3/2025 | N.A. | 3/2025 | 2555.5 |  | 2555.5 | 966.89 | 60.5
May 2025 |  |  | 1525 | CONSTRUCTION OF 4 LANE GREEN FIELD NORTHERN EAST SIDE GORAKHPUR BYPASS (26.616 KMS) STARTING FROM NH | NHAI | N24002096 | 2-2023 | 1/2026 | N.A. | 1/2026 | 1973.98 |  | 1973.98 | 736.14 | 47
May 2025 |  |  | 1526 | STRENGTHENING OF EXISTING 4L AYODHYA BYPASS SECTION FROM DESIGN KM.121.600 TO KM. 144.020 OF NH 28 ( | NHAI | N24002097 | 2-2023 | 9/2025 | N.A. | 8/2025 | 526.45 |  | 526.45 | 228.37 | 83
May 2025 |  |  | 1527 | CONSTRUCTION OF RING ROAD AROUND KANPUR FROM KM.000 TO KM. 23.325 (CHACHENDI SACHENDI I TO MAHARAJPU | NHAI | N24002104 | 1-2023 | 6/2026 | N.A. | 6/2026 | 1754 |  | 1754 | 343.02 | 34
May 2025 |  |  | 1528 | CONSTRUCTION OF NEW 4 LANE PRAYAGRAJ SOUTHERN BYPASS (PHASE-I) FROM DESIGN KM 43+200 (AT MAHUWARI VI | NHAI | N24002105 | 8-2023 | 6/2026 | N.A. | 6/2026 | 1378.36 |  | 739 | 198.15 | 25.1
May 2025 |  |  | 1529 | CONSTRUCTION OF NEW 4 LANE PRAYAGRAJ SOUTHERN BYPASS FROM DESIGN KM 50.860 (NABABA URF NIBI KALA UPA | NHAI | N24002106 | 8-2023 | 3/2025 | N.A. | 6/2025 | 993.77 |  | 349.48 | 372.8 | 92.86
May 2025 |  |  | 1530 | CONSTRUCTION OF MARIAHU BYPASS WITH FOUR LANE PAVED SHOULDER CONFIGURATION (KM.53.540 TO KM.59.200) | MoRTH | N24002115 | 3-2023 | 8/2025 | N.A. | 2/2026 | 438.24 | 362.39 | 438.24 | 211.72 | 36
May 2025 |  |  | 1531 | REHABILITATION AND UPGRADATION FROM KM 51.600 TO KM 75.700 OF NH-321G (NUHKHAS TO ETAH SECTION) TO T | MoRTH | N24002116 | 1-2022 | 8/2025 | N.A. | 8/2025 | 343.54 |  | 343.54 | 75.83 | 34
May 2025 |  |  | 1532 | CONSTRUCTION OF JASRA BYPASS WITH FOUR LANE PAVED SHOULDER CONFIGURATION FROM KM. 379.670 ON NH- 76 ( | MoRTH | N24002120 | 2-2023 | 9/2025 | N.A. | 9/2025 | 274.06 |  | 274.06 | 129.09 | 84
May 2025 |  |  | 1533 | IMPROVEMENT AND UP-GRADATION TO TWO LANE WITH PAVED SHOULDER CONFIGURATION FROM EXISTING KM. 420.00 | MoRTH | N24002121 | 1-2022 | 9/2025 | N.A. | 2/2026 | 509.65 |  | 509.65 | 188.67 | 21
May 2025 |  |  | 1534 | REHABILITATION AND UP-GRADATION FROM KM. 0.000 TO KM. 40.390 OF NH-730S (MAHARAJGANJ ? NICHLOUL ? TH | MoRTH | N24002134 | 3-2023 | 12/2025 | N.A. | 12/2025 | 809.25 |  | 809.25 | 262.06 | 33
May 2025 |  |  | 1535 | CONSTRUCTION OF FOUR LANE HIGHWAY WITH PAVED SHOULDER FROM KM.74.700 TO KM.112.950 OF NH-731A (I/C Y | MoRTH | N24002138 | 3-2022 | 6/2026 | N.A. | 6/2026 | 1141.67 |  | 1141.67 | 423.37 | 47
May 2025 |  |  | 1536 | CONSTRUCTION OF BALRAMPUR BYPASS WITH 2L FLEXIBLE PAVEMENT CONFIGURATION FROM KM.223.000 OF NH- 330 T | MoRTH | N24002150 | 12-2022 | 2/2026 | N.A. | 2/2026 | 515.69 |  | 515.69 | 172.49 | 28
May 2025 |  |  | 1537 | WIDENING TO 4L RIGID PAVEMENT CONFIGURATION FROM KM 90.00 TO KM 100.800 OF NH-96 (KM 42.O TO KM 53.3 | MoRTH | N24002199 | 12-2022 | 11/2026 | N.A. | 11/2026 | 309.63 |  | 309.63 | 11.05 | 15
May 2025 |  |  | 1538 | IMPROVEMENT AND UP-GRADATION TO TWO LANE WITH PAVED SHOULDER/FOUR LANE CONFIGURATION FROM EXISTING K | MoRTH | N24002201 | 1-2022 | 5/2027 | N.A. | 5/2027 | 974.19 |  | 974.19 | 586.68 | 10
May 2025 |  |  | 1539 | REHABILITATION AND UPGRADATION TO FOUR LANE ROAD FROM KM 70.500 TO KM 78.600 OF NH-92 UNDER EPC MODE | MoRTH | N24002211 | 1-2022 | 1/2027 | N.A. | 1/2027 | 296.02 |  | 296.02 | 27.94
May 2025 |  |  | 1540 | WIDENING AND STRENGTHENING FROM DESIGN KM. 67.280 TO KM. 88.622 OF NH- 727A (SALEMPUR-MAIRWA ROAD) TO | MoRTH | N24002212 | 3-2023 | 7/2026 | N.A. | 7/2026 | 371.89 |  | 371.89 | 134.82 | 32
May 2025 |  |  | 1541 | REHABILITATION and UP-GRADATION TO 2L+PS FROM KM. 0.0 TO KM. 7.80 AND KM. 35.400 TO KM. 52.345 (DESI | MoRTH | N24002213 | 3-2023 | 7/2026 | N.A. | 7/2026 | 701.02 |  | 701.02 | 243.54 | 10
May 2025 |  |  | 1542 | CONSTRUCTION OF AMETHI BYPASS (PART- II) AT KM.30.050 OF NH-931 UNDER EPC MODE IN THE STATE OF UTTAR | MoRTH | N24002214 | 12-2022 | 2/2027 | N.A. | 2/2027 | 283.86 |  | 283.86 | 58.92
May 2025 |  |  | 1543 | WIDENING TO 4L FROM KM.108.50 TO 139.00 OF NH-135A PKG-II (JAUNPUR TO AKBARPUR SECTION) ON HAM IN TH | MoRTH | N24002234 | 3-2023 | 3/2027 | N.A. | 3/2027 | 1511.57 |  | 1511.57 | 144.5 | 4
May 2025 |  |  | 1544 | CONSTRUCTION OF RAEBARELI RING ROAD (PHASE-2) WITH FOUR LANE CONFIGURATION FOR RAEBARELI CITY IN THE | MoRTH | N24002235 | 3-2022 | 5/2027 | N.A. | 5/2027 | 1273.72 |  | 1273.72 | 330.12
May 2025 |  |  | 1545 | IMPROVEMENT AND UP-GRADATION OF NH- 227B (84 KOSI PARIKRAMA MARG) PACKAGE ?I, FROM KM 228.920 (JAGARN | MoRTH | N24002240 | 3-2022 | 11/2026 | N.A. | 11/2026 | 912.5 |  | 912.5 | 388.5
May 2025 |  |  | 1546 | IMPROVEMENT AND UP-GRADATION OF NH- 227B (84 KOSI PARIKRAMA MARG) PACKAGE ?III, FROM KM.47.800 (GOSAI | MoRTH | N24002241 | 3-2022 | 11/2026 | N.A. | 11/2026 | 587.97 |  | 587.97 | 84.06
May 2025 |  | URBAN DEVELOPMENT | 1547 | KANPUR METRO RAIL PROJECT | LMRCL | N28000144 | 5-2019 | 3/2024 | N.A. | 3/2027 | 11076.48 |  | 11076.48 | 8736.58 | 72.5
May 2025 |  | URBAN DEVELOPMENT | 1548 | AGRA METRO RAIL PROJECT | LMRCL | N28000145 | 5-2019 | 3/2024 | N.A. | 6/2027 | 8379.62 |  | 8379.62 | 4987.53 | 54
May 2025 |  | WATER RESOURCES | 1549 | INTERCEPTION AND DIVERSION WORKS AND STP AT MUZAFFARNAGAR UTTAR PRADESH | UPJalNigam | N30000021 | 1-2019 | 12/2021 | Jan-2020 | 3/2025 | 231.79 | 234.03 | 234.03 | 141.79 | 100
May 2025 |  | WATER RESOURCES | 1550 | SEWERAGE SCHEME INTERCEPTION AND DIVERSION WITH STP WORKS AT MEERUT UTTAR PRADESH | UPJalNigam | N30000024 | 2-2019 | 6/2022 | N.A. | 12/2025 | 681.78 |  | 690.71 | 13.34 | 25
May 2025 |  | CIVIL AVIATION | 1551 | CONSTRUCTION OF DOMESTIC PASSENGER TERMINAL BUILDING AT DEHRADUN AIRPORT, DEHRADUN | AAI | N04000085 | 7-2018 | 9/2020 | Sep-2024 | 9/2024 | 456.86 | 500 | 500 | 483.96 | 100
May 2025 |  | CIVIL AVIATION | 1552 | TEHRI PUMPED STORAGE PLANT(1000MW) | THDCIL | N18000010 | 7-2006 | 7/2010 | Jun-2022 | 9/2025 | 1657 | 4825.6 | 7877.81 | 8007.27 | 98.2
May 2025 |  | CIVIL AVIATION | 1553 | TAPOVAN-VISHNUGAD HEP (4X130MW) | NTPC | N18000014 | 11-2006 | 3/2013 | Dec-2021 | 4/2029 | 2978.48 |  | 10907 | 6736.09 | 72.4
May 2025 |  | CIVIL AVIATION | 1554 | VISHNUGAD PIPALKOTI HYDRO ELECTRIC PROJECT | THDCIL | N18000042 | 8-2008 | 6/2013 | N.A. | 3/2027 | 2491.58 | 3860.35 | 6823.72 | 4819.19 | 70.5
May 2025 |  |  | 1555 | LATA-TAPOVAN HYDRO ELECTRIC POWER PROJECT 3X57 MW | NTPC | N18000142 | 7-2012 | 8/2017 | N.A. | 8/2017 | 1527 |  | 1527 | 149.93
May 2025 |  | RAILWAYS | 1556 | RISHIKESH - KARNAPRAYAG NEW LINE | RVNL | N22000406 | 4-2011 | 12/2025 | N.A. | 3/2025 | 38953.15 |  | 24659 | 18820.04
May 2025 |  | RAILWAYS | 1557 | 4-LANING OF KASHIPUR-SITARGANJ SECTION | AMR | N24000465 | 11-2012 | 8/2016 | N.A. | 8/2016 | 605.84 |  | 605.84 | 0
May 2025 |  | RAILWAYS | 1558 | CONSTRUCTION AND UPGRADATION OF EXISTING ROAD TO 2 LANE WITH PAVED SHOULDER FROM KM 368.00 TO KM 399 | NHIDCL | N24000741 | 3-2018 | 11/2020 | Mar-2024 | 3/2024 | 274.31 |  | 274.31 | 253.61 | 97.31
May 2025 |  | RAILWAYS | 1559 | 2 LANE WITH PAVED SHOULDER FROM KM 399.00 TO KM 430.00 OF KARANPARYAG TO CHAMOLI UNDER CHARDHAM PARI | NHIDCL | N24000742 | 3-2018 | 11/2020 | N.A. | 3/2024 | 403.36 |  | 403.36 | 340.32 | 98.93
May 2025 |  | RAILWAYS | 1560 | 2 LANE WITH PAVED SHOULDER FROM KM 430.00 TO KM 468.00 OF CHAMOLI TO PAINI UNDER CHARDHAM PARIYOJNA | NHIDCL | N24000743 | 3-2018 | 11/2020 | N.A. | 3/2024 | 417.24 |  | 417.24 | 344.2 | 99.88
May 2025 |  | RAILWAYS | 1561 | RECONSTRUCTION WITH GEOMETRIC IMPROVEMENT OF EXISTING 2 LANE/INTERMEDIATE LANE TO 2LANE WITH PAVED S | MoRTH | N24000772 | 12-2017 | 12/2019 | N.A. | 12/2019 | 257.34 |  | 257.34 | 232.69 | 100
May 2025 |  | RAILWAYS | 1562 | RECONSTRUCTION WITH GEOMETRIC IMPROVEMENT OF EXISTING 2 LANE/INTERMEDIATE LANE TO 2LANE WITH PAVED S | MoRTH | N24000773 | 12-2017 | 12/2019 | N.A. | 12/2019 | 200.34 | 253.43 | 200.34 | 227.98 | 100
May 2025 |  | RAILWAYS | 1563 | WIDENING OF EXISTING SINGLE LANE ROAD TO TWO LANE WITH PAVED SHOULDERS CONFIGURATION FROM KM. 235.00 | MoRTH | N24000774 | 12-2017 | 12/2019 | N.A. | 12/2019 | 248.22 |  | 248.22 | 236.8 | 100
May 2025 |  |  | 1564 | RECONSTRUCTION WITH GEOMETRIC IMPROVEMENT OF EXISTING 2 LANE/INTERMEDIATE LANE TO 2LANE WITH PAVED S | MoRTH | N24000775 | 6-2017 | 6/2019 | Mar-2023 | 3/2023 | 282.08 |  | 282.08 | 234.97 | 100
May 2025 |  |  | 1565 | RECONSTRUCTION WITH GEOMETIC IMPROVEMENT OF EXISTING TWO LANE TO 2- LANE WITH PAVED SHOULDERS CONFIG | MoRTH | N24000776 | 11-2017 | 11/2019 | N.A. | 11/2019 | 232.81 |  | 232.81 | 201.58 | 100
May 2025 |  |  | 1566 | RECONSTRUCTION WITH GEOMETIC IMPROVEMENT OF SINGLE LANE TO 2- LANE WITH PAVED SHOULDER CONFIGURATION | MoRTH | N24000777 | 11-2017 | 11/2019 | N.A. | 11/2019 | 283.51 |  | 283.51 | 278.51 | 100
May 2025 |  |  | 1567 | RECONSTRUCTION WITH GEOMETRIC IMPROVEMENT OF EXISTING SINGLE/INTERMEDIATE LANE TO 2LANE WITH PAVED S | MoRTH | N24000778 | 11-2017 | 11/2019 | N.A. | 11/2019 | 266.52 |  | 266.52 | 250.34 | 100
May 2025 |  |  | 1568 | RECONSTRUCTION WITH GEOMETRIC IMPROVEMENT OF EXISTING SINGLE/INTERMEDIATE LANE TO 2 LANE WITH EAR | MoRTH | N24000779 | 2-2018 | 2/2020 | Mar-2023 | 3/2023 | 418.88 |  | 418.88 | 339.71 | 94
May 2025 |  |  | 1569 | REHABILITATION AND UP GRADATION OF 2 LANE/ 2 LANE WITH PAVED SHOULDER FROM EXISTING KM. 172.900 TO K | MoRTH | N24000780 | 2-2018 | (Apr-2023) | {4/2023} |  | 293.68 |  | 293.68 | 244.25 | 100
May 2025 |  |  | 1570 | CONSTRUCTION OF KUND BYPASS FROM EXISTING KM 33+130 TO KM 41+260 (EXISTING LENGTH: 8.130 KM); DESIGN | MoRTH | N24000781 | 5-2018 | 5/2020 | Dec-2023 | 12/2023 | 248 |  | 248 | 120.5 | 66
May 2025 |  |  | 1571 | REHABILITATION AND UPGRADATION OF 2 LANE WITH PAVED SHOULDER FROM EXISTING KM. 195.175 TO KM. 220.00 | MoRTH | N24000782 | 3-2018 | (N.A.) | {} |  | 460.73 |  | 461 | 0
May 2025 |  |  | 1572 | CONSTRUCTION OF 4.5 KM LONG SILKYARA TUNNEL BETWEEN KM 25.40 TO 50.25 KM | TUNNEL WORK | NHIDCL | 3-2018 | 7/2022 | N.A. | 9/2026 | 1383.78 |  | 1383.78 | 709.72 | 63.84
May 2025 |  |  | 1573 | RECONSTRUCTION WITH GEOMETRIC IMPROVMENT OF EXISTING INTERMEDIATE LANE TO 2 LANE WITH PAVED SHOULDER | MoRTH | N24001130 | 8-2016 | 12/2017 | N.A. | 12/2017 | 234.88 | 273.49 | 234.88 | 237.19 | 100
May 2025 |  |  | 1574 | 6L ACCESS-CONTROLLED HIGHWAY OF DAAT KALI TUNNEL - DEHRADUN OF GANESHPUR ? DEHRADUN SECTION FROM KM. | NHAI | N24001525 | 3-2021 | 3/2024 | May-2025 | 5/2025 | 169.08 |  | 169.08 | 105.77 | 99.99
May 2025 |  |  | 1575 | UPGRADATION AND 4L OF HARIDWAR BYPASS FROM KM 0.000 (KM 188.100 OF NH- 58) TO KM. 15.100 (KM 5.100 OF | NHAI | N24001526 | 8-2021 | 10/2024 | Aug-2025 | 8/2025 | 1377.79 | 1384.11 | 1377.79 | 678.86 | 56.11
May 2025 |  |  | 1576 | 4L MEDINIPUR TO BALLUPUR FROM KM. 458.65 TO KM. 487.65 OF NH-07(PKG-2) | NHAI | N24001553 | 3-2022 | 2/2025 | Nov-2025 | 11/2025 | 1092.9 | 1092.9 | 1092.9 | 463.92 | 81.2
May 2025 |  |  | 1577 | 4L POANTA SAHEB?MEDNIPUR FROM KM. 435.65 TO KM. 458.65 OF NH-07(PKG-1) | NHAI | N24001990 | 6-2022 | 5/2025 | Oct-2025 | 10/2025 | 524.54 | 683.26 | 683.26 | 91.94 | 74.78
May 2025 |  |  | 1578 | ACCESS ROAD/BRIDGE CONNECTIVITY FROM NH-09 AT KM.40 NEAR JAGBUDA BRIDGE (INDIA) TO BOUNDARY PILLAR | NHAI | N24001991 | 5-2022 | 9/2024 | Nov-2026 | 11/2026 | 314.31 |  | 314.31 | 178.37 | 68.23
May 2025 |  |  | 1579 | CONSTRUCTION FOR MITIGATION MEASURES KM 368.00-UTTARAKHAND-TO KM 433.00 ON NH-07-PKG-1 | NHIDCL | N24002163 | 12-2023 | 12/2025 | N.A. | 12/2025 | 216.88 |  | 216.88 | 80.79 | 75.8
May 2025 |  |  | 1580 | CONSTRUCTION FOR MITIGATION MEASURES KM 450.00-UTTARAKHAND-TO KM 468.00 ON NH-07-PKG-3 | NHIDCL | N24002164 | 12-2023 | 12/2025 | N.A. | 12/2025 | 250.33 |  | 250.33 | 57.1 | 48.5
May 2025 |  |  | 1581 | CONSTRUCTION FOR MITIGATION MEASURES PKG-2 | NHIDCL | N24002206 | 12-2023 | 6/2026 | N.A. | 6/2026 | 259.64 |  | 259.64 | 4.16 | 20.23
May 2025 |  | CIVIL AVIATION | 1582 | CONSTRUCTION OF ATC TOWER AND TECHNICAL BLOCK AT NSCBI AIRPORT KOLKATA | AAI | N04000080 | 1-2016 | 3/2020 | Dec-2023 | 12/2023 | 458 |  | 458 | 251.64 | 100
May 2025 |  | CIVIL AVIATION | 1583 | AIRSIDE CAPACITY ENHANCEMENT OF NSBI AIRPORT, KOLKATA | AAI | N04000081 | 1-2019 | 11/2021 | May-2023 | 5/2023 | 389.71 | 397 | 397 | 396.61 | 100
May 2025 |  | CIVIL AVIATION | 1584 | NSCBI AIRPORT KOLKATA: RE- CONSTRUCTION OF RIGID POSITIONS OF SECONDARY RUNWAY, 'K' AND 'A' TAXIWAY | AAI | N04000109 | 4-2023 | 10/2025 | N.A. | 10/2025 | 328.3 |  | 328.3 | 79.39 | 36
May 2025 |  | CIVIL AVIATION | 1585 | BAGDOGRA AIRPORT: DEVELOPMENT OF NEW CIVIL ENCLAVE AT BAGDOGRA AIRPORT. SUB-HEAD : CONSTRUCTION OF N | AAI | N04000115 | 8-2024 | 3/2027 | N.A. | 3/2027 | 1549 |  | 1549 | 215.07 | 8.38
May 2025 |  | CIVIL AVIATION | 1586 | RANIGANJ MASTER PLAN | ECL | N06000163 | 8-2009 | 8/2019 | N.A. | 8/2024 | 2661.73 |  | 5146.48 | 784.1 | 42
May 2025 |  | CIVIL AVIATION | 1587 | SIDULI MINE (OC AND UG) | ECL | N06000165 | 5-2018 | 3/2027 | N.A. | 3/2027 | 535.18 |  | 535.17 | 4.75 | 14
May 2025 |  | CIVIL AVIATION | 1588 | NAKRAKONDA KUMARDIH B OCP | ECL | N06000170 | 8-2018 | 3/2029 | N.A. | 3/2029 | 502.68 |  | 502.67 | 71.07 | 25.5
May 2025 |  | CIVIL AVIATION | 1589 | SHYAMSUNDARPUR UG INCLUDING SAPI UNIT | ECL | N06000191 | 4-2020 | 3/2026 | Mar-2026 | 3/2026 | 483.65 |  | 483.65 | 55.23 | 12
May 2025 |  | CIVIL AVIATION | 1590 | 2.0 MTPA BHOJUDIH NLW WASHERY | BCCL | N06000195 | 12-2015 | 9/2020 | N.A. | 7/2025 | 384.57 |  | 384.57 | 348.66 | 97
May 2025 |  | CIVIL AVIATION | 1591 | SONEPUR BAZARI EXPANSION OC | ECL | N06000220 | 7-2021 | 3/2029 | N.A. | 3/2029 | 5365.88 | 5366 | 5365.88 | 553.51 | 17.3
May 2025 |  | CIVIL AVIATION | 1592 | EXPANSION PR OF JHANJRA UG (5.00 MTY) | ECL | N06000223 | 4-2020 | 3/2029 | N.A. | 3/2029 | 1210.12 |  | 1210.12 | 489.45 | 40
May 2025 |  | CIVIL AVIATION | 1593 | MOHANPUR EXPANSION OC PHASE II | ECL | N06000236 | 11-2020 | 3/2026 | N.A. | 3/2026 | 888.99 |  | 888.99 | 77.94 | 30.25
May 2025 |  |  | 1594 | BONJEMEHARI EXPANSION OCP | ECL | N06000244 | 8-2021 | 3/2026 | Mar-2026 | 3/2026 | 570.12 |  | 570.11 | 81.58 | 16
May 2025 |  |  | 1595 | ITAPARA OC | ECL | N06000272 | 12-2023 | 3/2030 | N.A. | 3/2030 | 929.1 |  | 929.1 | 64.61 | 6.8
May 2025 |  |  | 1596 | UCE OF TILABONI UG | ECL | N06000276 | 1-2023 | 3/2029 | N.A. | 3/2029 | 749.07 |  | 749.07 | 52.09 | 10.3
May 2025 |  |  | 1597 | UCE OF PARASEA BELBAID REORGANISATION UG | ECL | N06000277 | 1-2023 | 3/2029 | Mar-2028 | 3/2028 | 389.1 |  | 389.1 | 130.56 | 16.4
May 2025 |  |  | 1598 | PARASCOLE JAMBAD OCP | ECL | N06000281 | 11-2024 | 3/2037 | N.A. | 3/2037 | 1193.55 |  | 1193.55 | 5.91
May 2025 |  | DEPARTMENT OF HIGHER EDUCATION | 1599 | CONSTRUCTION OF TWO NOS GIRLS HOSTELS AND ONE NO BOYS HOSTEL OF 500 CAPACITY EACH G PLUS 8 STOREYED | CPWD EDUCATION | N28000146 | 3-2020 | 6/2020 | N.A. | 3/2024 | 193.83 |  | 193.83 | 187.65 | 99
May 2025 |  | MINES | 1600 | CONSTRUCTION OF BASEMENTG FLOOR10 STORIES BUILDING FOR THE STATE OF THE ART, DG, GSI AT SECTOR-V, SA | CPWD | N10000015 | 4-2019 | 4/2022 | N.A. | 8/2026 | 255.37 |  | 255.37 | 68.66 | 38
May 2025 |  | MINES | 1601 | DURGAPUR-HALDIA PIPELINE PROJECT | GAIL | N16000275 | 3-2017 | 12/2020 | Dec-2025 | 12/2025 | 1740 | 2433.15 | 2433.15 | 2185.1 | 89.8
May 2025 |  | MINES | 1602 | CITY GAS DISTRIBUTION IN WEST BENGAL | HPCL | N16000392 | 3-2019 | 3/2031 | Mar-2031 | 3/2031 | 5830.2 |  | 5830.2 | 875.27 | 33
May 2025 |  | MINES | 1603 | HALDIA PANAGARH PIPELINE PROJECT | HPCL | N16000478 | 11-2022 | 11/2025 | N.A. | 11/2025 | 1010 |  | 1010 | 546.6 | 79.09
May 2025 |  | MINES | 1604 | CGD PROJECT AT EAST MEDNIPORE, WEST MEDNIPORE AND JHARGRAM DISTRICTS | IOCL | N16000491 | 3-2022 | 3/2030 | N.A. | 6/2031 | 609 |  | 609 | 55.29 | 2.1
May 2025 |  | MINES | 1605 | CGD PROJECT IN WEST BENGAL 11TH ROUND | HPCL | N16000498 | 6-2022 | 6/2030 | N.A. | 6/2030 | 2628 |  | 2628 | 311.01 | 22
May 2025 |  |  | 1606 | CITY GAS DISTRIBUTION PROJECTS AT ALIPURDUAR AND COOCH BEHAR | BPCL | N16000522 | 12-2022 | 3/2030 | N.A. | 3/2030 | 1017 |  | 1017 | 160.8 | 30.6
May 2025 |  | POWER | 1607 | RAMMAM-III HEPP (3X40 MW) | NTPC | N18000178 | 9-2014 | 9/2019 | Dec-2024 | 3/2029 | 1381.84 |  | 1803 | 1302.76 | 43.68
May 2025 |  | POWER | 1608 | TARAKESWAR - BISHNUPUR NEW BG LINE (NL), ER | ER | 220100272 | 4-2000 | 3/2019 | Feb-2026 | 2/2026 | 1188.91 |  | 2582.49 | 1264.53 | 75
May 2025 |  | POWER | 1609 | NEW WORK FOR CONSTRUCTION OF METRO RAILWAY FROM NOAPARA-BARASAI VIA BIMANBANDER (MTP) | KOMRCL | N22000108 | 4-2010 | 8/2026 | N.A. | 3/2016 | 4829.6 |  | 2397.72 | 197.2 | 17
May 2025 |  | POWER | 1610 | NEW WORK FOR CONSTRUCTION OF METRO RAILWAY FROM BARANAGAR TO BARRACKPORE AND DAKSHINESHWAR | MTP | RVNL | 4-2010 | 12/2026 | N.A. | 12/2025 | 2298.42 |  | 2733.86 | 392.98
May 2025 |  | POWER | 1611 | NEW WORK FOR CONSTRUCTION OF METRO RAILWAY FROM NSCB AIRPORT TO NEW GARIA VIA RAJARHAT (MTP) | RVNL | N22000110 | 4-2010 | 12/2025 | N.A. | 3/2026 | 8964.35 |  | 8964.35 | 7387.4
May 2025 |  | POWER | 1612 | NEW WORK FOR CONSTRUCTION OF METRO RAILWAY FROM JOKA TO BINOY BADAL DINESH BAGH. | RVNL | N22000111 | 4-2010 | 12/2026 | N.A. | 12/2026 | 4834.54 |  | 4834.54 | 3918.86
May 2025 |  | POWER | 1613 | PURULIA TO KOTSHILA DOUBLING (39.1 KM) | SER | N22000510 | 4-2018 | 12/2024 | N.A. | 3/2025 | 393.83 |  | 393.83 | 318.36 | 100
May 2025 |  | POWER | 1614 | NAHATI - RANAGHAT 3RD LINE (MM OF KALINARAYANPUR - KRISHNANAGAR) | ER | N22000624 | 7-2015 | 3/2025 | N.A. | 3/2025 | 1000 |  | 283.54 | 167.13 | 44
May 2025 |  | POWER | 1615 | EAST WEST METRO CORRIDOR KOLKATA | KOMRCL | N22000628 | 2-2009 | 9/2016 | N.A. | 9/2016 | 4874.58 | 8575 | 10442.41 | 0
May 2025 |  | POWER | 1616 | KALIPAHARI - BAKHTARNAGAR 5TH LINE | 17.61 KM | ER | 4-2024 | 6/2027 | N.A. | 6/2027 | 350.46 |  | 350.46 | 0
May 2025 |  |  | 1617 | SITARAMPUR BYE - PASS LINE (6.59 KM) | ER | N22000631 | 2-2023 | 3/2027 | N.A. | 3/2027 | 461.64 |  | 461.64 | 25.84
May 2025 |  |  | 1618 | 4 LANING OF NH-31D FROM GHOSHPUKUR - SALSALABARI ( KM 0.00 TO KM . 83.785) | NHAI | N24000463 | 12-2015 | 6/2018 | May-2024 | 8/2023 | 1083 | 1414.01 | 1414.01 | 1080.05 | 100
May 2025 |  |  | 1619 | SIX-LANING OF BARWA ADDA-PANAGARH | NHAI | N24000515 | 4-2014 | 9/2016 | N.A. | 3/2025 | 1665 |  | 4977.49 | 4977.49 | 100
May 2025 |  |  | 1620 | REHABILITATION AND UP GRADATION OF EXISTING ROAD TO 2-LANE WITH PAVED SHOULDER CONFIGURATION IN PURU | NHAI | N24000788 | 3-2018 | 9/2022 | Dec-2022 | 12/2025 | 841.57 | 708.3 | 708.3 | 11802.22 | 96.13
May 2025 |  |  | 1621 | CONSTRUCTION OF NEW ROAD AT THE MISSING LINK PORTION OF NH-81 ALONG THE APPROVED ALIGNMENT BETWEEN H | MoRTH | N24000874 | 3-2016 | 11/2018 | Dec-2023 | 7/2025 | 271.17 | 291.2 | 291.2 | 199.72 | 82.47
May 2025 |  |  | 1622 | UPGRADATION OF NH-81 WITH A MINIMUM OF 2-LANE WITH PAVED SHOULDER CONFIGURATION STARTING FROM KM 19. | MoRTH | N24000880 | 2-2018 | 9/2020 | Jan-2024 | 2/2025 | 426.18 | 426.18 | 426.18 | 364.92 | 100
May 2025 |  |  | 1623 | SIX LANE OF PALSIT TO DANKUNI SECTION FROM 588.870 TO KM. 652.700 | NHAI | N24001747 | 3-2020 | 9/2024 | N.A. | 9/2024 | 2193.23 | 2314 | 2314 | 2085 | 96.4
May 2025 |  |  | 1624 | SIX LANING OF NATIONAL CORRIDOR NH19 FROM PANAGARH TO PALSIT IN THE STATE OF WEST BENGAL UNDER BHARA | NHAI | N24001748 | 3-2021 | 9/2024 | N.A. | 9/2025 | 2200.93 |  | 2621.43 | 2621.43 | 97.31
May 2025 |  |  | 1625 | FOUR LANING OF PURULIYA BYPASS SECTION OF NH 32 IN THE STATE OF WEST BENGAL ON EPC MODE | NHAI | N24001749 | 8-2021 | 8/2023 | N.A. | 6/2025 | 557.55 |  | 567.31 | 473.25 | 91.41
May 2025 |  |  | 1626 | CONSTRUCTION OF NEW 4 LANE BRIDGE OVER RIVER GANGA AT DOWNSTREAM OF FARAKKA BARRAGE INCLUDING APPROA | NHAI | N24001750 | 8-2018 | 12/2021 | N.A. | 7/2025 | 622.04 |  | 622.04 | 573.67 | 91.44
May 2025 |  |  | 1627 | DEVELOPMENT TO 4/6-LANNING OF NH-31 (NEW NH-10) WITH BOTH SIDE SERVICE ROADS FROM KM 569.258 TO KM 5 | MoRTH | N24001850 | 3-2022 | 9/2025 | Sep-2025 | 9/2025 | 995.04 | 995.04 | 995.04 | 383.85 | 49.91
May 2025 |  |  | 1628 | CONSTRUCTION OR 4 LANE RANIGANJ BYPASS OF LENGTH 5 261 KM ON NH 60 NEW NH 14 FROM KM 273 00 OF NH | MoRTH | N24002184 | 3-2023 | 3/2026 | Mar-2026 | 3/2026 | 410.83 |  | 410.83 | 152.32 | 34.89
May 2025 |  |  | 1629 | CONSTRUCTION OF ROB AND ITS APPROACHES IN LIEU OF LEVEL CROSSING NO 10 B T AT KM 307 050 OF NH 60 B | MoRTH | N24002191 | 3-2016 | 8/2025 | N.A. | 8/2025 | 155.87 |  | 155.87 | 21.68 | 10.1
May 2025 |  | STEEL | 1630 | REBUILDING OF COKE OVEN BATTERY NO.4 OF DURGAPUR STEEL PLANT | SAIL | N12000132 | 11-2023 | 12/2026 | N.A. | 12/2026 | 916.78 |  | 916.78 | 98.69 | 9.91
May 2025 |  | STEEL | 1631 | INSTALLATION OF NEW BAR MILL AT DURGAPUR STEEL PLANT | SAIL | N12000138 | 9-2024 | 6/2027 | N.A. | 6/2027 | 2115.44 |  | 2115.44 | 77.68 | 10.16
May 2025 |  | STEEL | 1632 | UP-GRADATION OF BLAST FURNACE NO. 3 AT DURGAPUR STEEL PLANT | SAIL | N12000139 | 9-2024 | 6/2026 | N.A. | 6/2026 | 758.09 |  | 758.09 | 35.34 | 202
May 2025 |  | STEEL | 1633 | REVAMPING OF AIR POLLUTION CONTROL SYSTEMS OF SP-1 AT DURGAPUR STEEL PLANT | SAIL | N12000140 | 11-2024 | 5/2026 | N.A. | 5/2026 | 196.4 |  | 196.4 | 0.19 | 0.9
May 2025 |  | STEEL | 1634 | THIRD LADLE FURNACE IN SECONDARY REFINERY UNIT AT IISCO STEEL PLANT | SAIL | N12000141 | 11-2024 | 7/2026 | N.A. | 7/2026 | 227.96 |  | 227.96 | 2.58 | 28.26
May 2025 |  | STEEL | 1635 | INTERCEPTION AND DIVERSION WITH STP AT MAHESHTALA | KMDA | N30000032 | 5-2018 | 2/2022 | N.A. | 8/2025 | 198.43 | 224.69 | 286.97 | 77.78 | 96
May 2025 |  |  | 1636 | INTERCEPTION DIVERSION TREATMENT WORKS AT TOLLYS NULLAH ADI GANGA | KMDA | N30000034 | 8-2017 | 9/2022 | Jan-2023 | 12/2026 | 307.12 |  | 653.67 | 0
May 2025 |  |  | 1637 | INTERCEPTION AND DIVERSION WITH STP AT HUGHLY-CHINSURAH | KMDA | N30000042 | 5-2018 | 2/2022 | Sep-2020 | 3/2025 | 160 | 154.73 | 154.73 | 91.87 | 92