## Summary
PAIMANA Flash Report — Aug 2025 vs Oct 2025
Source: PAIMANA Portal (ipm.mospi.gov.in) flash reports for Aug 2025 and Oct 2025 ¦ SIH 2026 PS 103
Metric | August 2025 | October 2025 | Change
Total Ongoing Projects | 800 | 820 | 20
Total Original Cost (Rs Cr) | 2375332.37 | 2552631.73 | 177299.36
Total Latest Revised Cost (Rs Cr) | 2907547.15 | 3083531.02 | 175983.87
Total Cumulative Expenditure (Rs Cr) | 1537609.45 | 1611187.71 | 73578.26
Average Physical Progress (%) | 49.1728 | 50.728 | 1.5552
Newly Added Projects (during Oct) |  | 35
Completed Projects (during Oct) |  | 6
Notes / Verification
• Figures are extracted directly from the PAIMANA Flash Report PDFs (Aug 2025: 67 pages, Oct 2025: 73 pages).
• 'All Ongoing Projects' row counts (800 for Aug, 820 for Oct) were cross-checked against the report's own Table 1 (Ministry-wise) grand totals and match exactly.
• 'State-wise' sheet counts exceed the project total because a project spanning multiple states (e.g. a transmission line or pipeline) is listed once under each state it touches — this matches the report's own structure, it is not a duplication error.
• Cost figures are in Rs. Crore, as reported in the source PDFs.
• Original Data columns preserved verbatim; 'Original Cost' / 'Revised Cost' were split out of the single stacked cell used in the PDF for readability.

## Aug - Ministry-wise
Month | Ministry/Department | Sector | Project Count | Original Cost (Rs Cr) | Latest Revised Cost (Rs Cr) | Cumulative Expenditure (Rs Cr)
August 2025 | Department for Promotion of Industry & Internal Trade | Real Estate | 2 | 3841.25 | 3841.25 | 494.3
August 2025 | Department of Higher Education | Education | 30 | 12754.41 | 12685.5 | 8159.38
August 2025 | Department of Telecommunications | Telecommunication | 14 | 150849.85 | 272942 | 72122.5
August 2025 | Department of Water Resources, River Development & GR | Waste & Water | 8 | 4039.12 | 4039.12 | 1643.05
August 2025 | Department of Water Resources, River Development & GR | Water Resources | 40 | 93248.95 | 195108 | 138397
August 2025 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | 26 | 23049.84 | 23511 | 24879.8
August 2025 | Ministry of Coal | Coal | 117 | 166806.82 | 164263 | 53439.3
August 2025 | Ministry of Coal | Electricity Generation | 5 | 46865.63 | 51408.8 | 23562.4
August 2025 | Ministry of Coal | Railways | 2 | 3485.86 | 3485.86 | 1641.67
August 2025 | Ministry of Health & Family Welfare | Healthcare | 3 | 4155 | 4492.95 | 2694.22
August 2025 | Ministry of Housing & Urban Affairs | Construction | 1 | 646.53 | 646.52 | 533.12
August 2025 | Ministry of Housing & Urban Affairs | Inland Waterways | 1 | 63246 | 63246 | 26410.2
August 2025 | Ministry of Housing & Urban Affairs | Real Estate | 4 | 33749.85 | 33749.8 | 58.58
August 2025 | Ministry of Housing & Urban Affairs | Urban Public Transport | 21 | 223016.77 | 243598 | 159570
August 2025 | Ministry of Housing & Urban Affairs | Waste & Water | 25 | 6085.6 | 6085.6 | 19062.9
August 2025 | Ministry of Mines | Construction | 1 | 255.37 | 255.37 | 79.34
August 2025 | Ministry of Mines | Metals & Mining | 9 | 12736.35 | 15116.5 | 6124.59
August 2025 | Ministry of Petroleum & Natural Gas | Energy Storage | 16 | 81301.48 | 120185 | 90497.5
August 2025 | Ministry of Petroleum & Natural Gas | Oil & Gas | 90 | 351248.78 | 383480 | 184032
August 2025 | Ministry of Ports, Shipping and Waterways | Healthcare | 1 | 693 | 693 | 58
August 2025 | Ministry of Ports, Shipping and Waterways | Inland Waterways | 2 | 9612.82 | 9304.79 | 3876.92
August 2025 | Ministry of Ports, Shipping and Waterways | Shipping | 5 | 4823.34 | 4823.34 | 2020.93
August 2025 | Ministry of Ports, Shipping and Waterways | Tourism, Hospitality & Wellness | 1 | 573 | 1238.05 | 496.63
August 2025 | Ministry of Power | Coal | 2 | 2083 | 2365 | 910.82
August 2025 | Ministry of Power | Electricity Generation | 30 | 223418.07 | 278228 | 132370
August 2025 | Ministry of Power | Transmission & Distribution | 61 | 142976.51 | 149491 | 52183.1
August 2025 | Ministry of Railways | Railways | 263 | 691320.92 | 837521 | 524256
August 2025 | Ministry of Steel | Metals & Mining | 1 | 1700 | 1756.2 | 65.44
August 2025 | Ministry of Steel | Steel | 19 | 16748.25 | 19986.5 | 7969.76

## Aug - State-wise
Month | State | Ministry/Department | Sector | Project Count | Original Cost (Rs Cr) | Latest Revised Cost (Rs Cr) | Cumulative Expenditure (Rs Cr)
August 2025 | Offshore | Ministry of Petroleum & Natural Gas | Oil & Gas | 6 | 19714.58 | 22972.8 | 10210.97
August 2025 | Offshore | Ministry of Railways | Railways | 2 | 1311.83 | 1311.83 | 583.6
August 2025 | PAN India | Department of Telecommunications | Telecommunication | 6 | 141891.67 | 264213 | 69165.67
August 2025 | Andaman & Nicobar | Ministry of Housing & Urban Affairs | Real Estate | 1 | 209.88 | 209.88 | 0
August 2025 | Andhra Pradesh | Department for Promotion of Industry & Internal Trade | Real Estate | 1 | 2139.44 | 2139.44 | 406.05
August 2025 | Andhra Pradesh | Department of Higher Education | Education | 1 | 305 | 305 | 83.33
August 2025 | Andhra Pradesh | Department of Telecommunications | Telecommunication | 2 | 5262.57 | 5262.57 | 1699.75
August 2025 | Andhra Pradesh | Department of Water Resources, River Development & GR | Water Resources | 3 | 10901.5 | 57269.5 | 25827.76
August 2025 | Andhra Pradesh | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | 3 | 1224.86 | 1224.86 | 613.89
August 2025 | Andhra Pradesh | Ministry of Housing & Urban Affairs | Waste & Water | 1 | 172.22 | 172.22 | 622.02
August 2025 | Andhra Pradesh | Ministry of Petroleum & Natural Gas | Energy Storage | 2 | 2898.34 | 3050 | 2242.8
August 2025 | Andhra Pradesh | Ministry of Petroleum & Natural Gas | Oil & Gas | 5 | 37997 | 38057 | 33498.29
August 2025 | Andhra Pradesh | Ministry of Power | Transmission & Distribution | 5 | 13395.24 | 13395.2 | 4512.61
August 2025 | Andhra Pradesh | Ministry of Railways | Railways | 28 | 56255.53 | 63480.7 | 32347.6
August 2025 | Arunachal Pradesh | Department of Higher Education | Education | 1 | 592.61 | 592.61 | 549.96
August 2025 | Arunachal Pradesh | Department of Telecommunications | Telecommunication | 1 | 1255.49 | 1255.49 | 284.04
August 2025 | Arunachal Pradesh | Ministry of Petroleum & Natural Gas | Energy Storage | 1 | 43129 | 79459 | 60295.14
August 2025 | Arunachal Pradesh | Ministry of Petroleum & Natural Gas | Oil & Gas | 1 | 9265 | 9265 | 6393.85
August 2025 | Arunachal Pradesh | Ministry of Power | Electricity Generation | 4 | 41850.64 | 61640.8 | 28586.95
August 2025 | Arunachal Pradesh | Ministry of Power | Transmission & Distribution | 1 | 4754.42 | 9129.32 | 7462.2
August 2025 | Arunachal Pradesh | Ministry of Railways | Railways | 1 | 435 | 1250 | 901
August 2025 | Assam | Department of Higher Education | Education | 1 | 153.71 | 153.71 | 54.05
August 2025 | Assam | Department of Telecommunications | Telecommunication | 1 | 1255.49 | 1255.49 | 284.04
August 2025 | Assam | Department of Water Resources, River Development & GR | Water Resources | 1 | 256.16 | 256.16 | 0
August 2025 | Assam | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | 1 | 1712 | 1712 | 2335.44
August 2025 | Assam | Ministry of Coal | Coal | 2 | 449.23 | 449.23 | 186.31
August 2025 | Assam | Ministry of Housing & Urban Affairs | Waste & Water | 1 | 186.8 | 186.8 | 1291.55
August 2025 | Assam | Ministry of Petroleum & Natural Gas | Energy Storage | 3 | 10768.4 | 11947.4 | 9941.27
August 2025 | Assam | Ministry of Petroleum & Natural Gas | Oil & Gas | 13 | 28019.15 | 41554 | 30591.24
August 2025 | Assam | Ministry of Power | Electricity Generation | 1 | 6285.33 | 26075.5 | 24880.95
August 2025 | Assam | Ministry of Power | Transmission & Distribution | 1 | 5111.33 | 6700 | 5277.24
August 2025 | Assam | Ministry of Railways | Railways | 7 | 14593.57 | 16308.6 | 10302.48
August 2025 | Bihar | Department of Higher Education | Education | 1 | 499.21 | 499.21 | 425.47
August 2025 | Bihar | Department of Telecommunications | Telecommunication | 3 | 2336.11 | 2107.64 | 960.21
August 2025 | Bihar | Department of Water Resources, River Development & GR | Waste & Water | 5 | 2351.43 | 2351.43 | 1303.45
August 2025 | Bihar | Department of Water Resources, River Development & GR | Water Resources | 3 | 2884.49 | 4060.84 | 1590.27
August 2025 | Bihar | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | 3 | 3541.56 | 3541.56 | 1256.71
August 2025 | Bihar | Ministry of Housing & Urban Affairs | Urban Public Transport | 1 | 13365.77 | 13365.8 | 4039.77
August 2025 | Bihar | Ministry of Housing & Urban Affairs | Waste & Water | 1 | 158.78 | 158.78 | 48.61
August 2025 | Bihar | Ministry of Petroleum & Natural Gas | Energy Storage | 1 | 10228 | 11407 | 9766.72
August 2025 | Bihar | Ministry of Petroleum & Natural Gas | Oil & Gas | 7 | 24636.5 | 26501.2 | 13258.37
August 2025 | Bihar | Ministry of Ports, Shipping and Waterways | Inland Waterways | 1 | 5369.18 | 5061.15 | 3510.72
August 2025 | Bihar | Ministry of Power | Electricity Generation | 1 | 10439.09 | 13756.6 | 12148.46
August 2025 | Bihar | Ministry of Power | Transmission & Distribution | 2 | 751.63 | 751.63 | 0.9
August 2025 | Bihar | Ministry of Railways | Railways | 20 | 48815.69 | 52817.3 | 22483.47
August 2025 | Chhattisgarh | Department of Telecommunications | Telecommunication | 2 | 5262.57 | 5262.57 | 1699.75
August 2025 | Chhattisgarh | Department of Water Resources, River Development & GR | Water Resources | 2 | 842.26 | 1109.33 | 616.93
August 2025 | Chhattisgarh | Ministry of Coal | Coal | 15 | 38654.89 | 38654.9 | 15480.4
August 2025 | Chhattisgarh | Ministry of Coal | Railways | 1 | 1686.22 | 1686.22 | 347.96
August 2025 | Chhattisgarh | Ministry of Petroleum & Natural Gas | Oil & Gas | 2 | 10056.25 | 10467 | 6509.05
August 2025 | Chhattisgarh | Ministry of Power | Electricity Generation | 2 | 25321 | 25321 | 2480
August 2025 | Chhattisgarh | Ministry of Power | Transmission & Distribution | 1 | 385.84 | 385.84 | 378.17
August 2025 | Chhattisgarh | Ministry of Railways | Railways | 19 | 32162 | 34222.7 | 18291.67
August 2025 | Chhattisgarh | Ministry of Steel | Metals & Mining | 1 | 1700 | 1756.2 | 65.44
August 2025 | Chhattisgarh | Ministry of Steel | Steel | 6 | 7530.14 | 10050.1 | 5270.32
August 2025 | Dadra & Nagar Haveli and Daman & Diu | Ministry of Housing & Urban Affairs | Waste & Water | 1 | 210 | 210 | 0
August 2025 | Dadra & Nagar Haveli and Daman & Diu | Ministry of Power | Transmission & Distribution | 1 | 4546.26 | 4546.26 | 4172.96
August 2025 | Dadra & Nagar Haveli and Daman & Diu | Ministry of Railways | Railways | 1 | 108000 | 108000 | 79918.89
August 2025 | Delhi | Department of Higher Education | Education | 2 | 706.49 | 706.49 | 300.98
August 2025 | Delhi | Department of Telecommunications | Telecommunication | 1 | 248.2 | 248.2 | 236.91
August 2025 | Delhi | Ministry of Housing & Urban Affairs | Construction | 1 | 646.53 | 646.52 | 533.12
August 2025 | Delhi | Ministry of Housing & Urban Affairs | Real Estate | 1 | 32850 | 32850 | 0
August 2025 | Delhi | Ministry of Housing & Urban Affairs | Urban Public Transport | 4 | 69853.45 | 69853.4 | 42116.99
August 2025 | Delhi | Ministry of Power | Transmission & Distribution | 4 | 4356.47 | 4908.47 | 3923.11
August 2025 | Delhi | Ministry of Railways | Railways | 14 | 28176.96 | 28177 | 5356.29
August 2025 | Goa | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | 1 | 255.69 | 255.69 | 130
August 2025 | Goa | Ministry of Railways | Railways | 2 | 5804.49 | 6182.62 | 5976.87
August 2025 | Gujarat | Department of Higher Education | Education | 1 | 490.63 | 490.63 | 301.44
August 2025 | Gujarat | Department of Telecommunications | Telecommunication | 1 | 336.89 | 301.13 | 227.82
August 2025 | Gujarat | Department of Water Resources, River Development & GR | Water Resources | 2 | 25739.93 | 40082.8 | 36722.58
August 2025 | Gujarat | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | 1 | 1305 | 1551 | 1348.78
August 2025 | Gujarat | Ministry of Coal | Coal | 1 | 7580 | 7580 | 3091
August 2025 | Gujarat | Ministry of Coal | Electricity Generation | 1 | 383.84 | 383.84 | 303.5
August 2025 | Gujarat | Ministry of Housing & Urban Affairs | Real Estate | 1 | 539 | 539 | 39.63
August 2025 | Gujarat | Ministry of Housing & Urban Affairs | Urban Public Transport | 3 | 28177.49 | 30329 | 23950.31
August 2025 | Gujarat | Ministry of Housing & Urban Affairs | Waste & Water | 1 | 200 | 200 | 100
August 2025 | Gujarat | Ministry of Petroleum & Natural Gas | Energy Storage | 3 | 62245 | 98575 | 75103.78
August 2025 | Gujarat | Ministry of Petroleum & Natural Gas | Oil & Gas | 11 | 32704.12 | 32178.7 | 22879.89
August 2025 | Gujarat | Ministry of Ports, Shipping and Waterways | Inland Waterways | 1 | 4243.64 | 4243.64 | 366.2
August 2025 | Gujarat | Ministry of Ports, Shipping and Waterways | Tourism, Hospitality & Wellness | 1 | 573 | 1238.05 | 496.63
August 2025 | Gujarat | Ministry of Power | Electricity Generation | 1 | 339.35 | 339.35 | 317.59
August 2025 | Gujarat | Ministry of Power | Transmission & Distribution | 13 | 45319.41 | 45318.9 | 12842.82
August 2025 | Gujarat | Ministry of Railways | Railways | 31 | 187430.66 | 262112 | 216423.66
August 2025 | Haryana | Ministry of Health & Family Welfare | Healthcare | 1 | 1299 | 1299 | 349.41
August 2025 | Haryana | Ministry of Housing & Urban Affairs | Urban Public Transport | 1 | 6230.99 | 6230.99 | 0.29
August 2025 | Haryana | Ministry of Housing & Urban Affairs | Waste & Water | 2 | 491.2 | 491.2 | 2617.89
August 2025 | Haryana | Ministry of Petroleum & Natural Gas | Energy Storage | 1 | 9028 | 9028 | 7136.41
August 2025 | Haryana | Ministry of Petroleum & Natural Gas | Oil & Gas | 5 | 45925.07 | 49596.1 | 33666.9
August 2025 | Haryana | Ministry of Power | Transmission & Distribution | 4 | 13362 | 13914 | 2619.3
August 2025 | Haryana | Ministry of Railways | Railways | 4 | 53464 | 126368 | 125567.23
August 2025 | Himachal Pradesh | Department of Higher Education | Education | 3 | 811.15 | 921.89 | 579.09
August 2025 | Himachal Pradesh | Department of Telecommunications | Telecommunication | 1 | 336.89 | 301.13 | 227.82
August 2025 | Himachal Pradesh | Ministry of Power | Electricity Generation | 4 | 7728.04 | 12252.1 | 4137.13
August 2025 | Himachal Pradesh | Ministry of Railways | Railways | 3 | 17005 | 17005.1 | 9366.44
August 2025 | Jammu and Kashmir | Department of Higher Education | Education | 1 | 424.93 | 500.91 | 484.52
August 2025 | Jammu and Kashmir | Department of Telecommunications | Telecommunication | 1 | 336.89 | 301.13 | 227.82
August 2025 | Jammu and Kashmir | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | 1 | 861.37 | 861.37 | 177.69
August 2025 | Jammu and Kashmir | Ministry of Health & Family Welfare | Healthcare | 1 | 1828 | 1828 | 1531.86
August 2025 | Jammu and Kashmir | Ministry of Petroleum & Natural Gas | Energy Storage | 1 | 676.89 | 676.89 | 526.1
August 2025 | Jammu and Kashmir | Ministry of Petroleum & Natural Gas | Oil & Gas | 2 | 1059.9 | 1059.9 | 193.82
August 2025 | Jammu and Kashmir | Ministry of Power | Electricity Generation | 4 | 22207.77 | 27945.1 | 12525.6
August 2025 | Jammu and Kashmir | Ministry of Power | Transmission & Distribution | 3 | 825.43 | 825.43 | 496.12
August 2025 | Jharkhand | Department of Telecommunications | Telecommunication | 2 | 5262.57 | 5262.57 | 1699.75
August 2025 | Jharkhand | Department of Water Resources, River Development & GR | Water Resources | 2 | 5430.04 | 12010.3 | 5704.07
August 2025 | Jharkhand | Ministry of Coal | Coal | 27 | 45414.48 | 45178.8 | 10417.02
August 2025 | Jharkhand | Ministry of Coal | Railways | 1 | 1799.64 | 1799.64 | 1293.71
August 2025 | Jharkhand | Ministry of Housing & Urban Affairs | Waste & Water | 3 | 654.14 | 654.14 | 2532.48
August 2025 | Jharkhand | Ministry of Mines | Metals & Mining | 2 | 3370.02 | 3370.02 | 16.57
August 2025 | Jharkhand | Ministry of Petroleum & Natural Gas | Energy Storage | 1 | 10228 | 11407 | 9766.72
August 2025 | Jharkhand | Ministry of Petroleum & Natural Gas | Oil & Gas | 3 | 2010.07 | 2010.07 | 595.56
August 2025 | Jharkhand | Ministry of Ports, Shipping and Waterways | Inland Waterways | 1 | 5369.18 | 5061.15 | 3510.72
August 2025 | Jharkhand | Ministry of Power | Coal | 2 | 2083 | 2365 | 910.82
August 2025 | Jharkhand | Ministry of Power | Electricity Generation | 2 | 31470 | 34660 | 18606.57
August 2025 | Jharkhand | Ministry of Railways | Railways | 12 | 43352.74 | 43746.7 | 14874.38
August 2025 | Jharkhand | Ministry of Steel | Steel | 6 | 2854.58 | 3572.87 | 1284.99
August 2025 | Karnataka | Department for Promotion of Industry & Internal Trade | Real Estate | 1 | 1701.81 | 1701.81 | 88.25
August 2025 | Karnataka | Department of Higher Education | Education | 1 | 420.41 | 420.41 | 360.72
August 2025 | Karnataka | Department of Water Resources, River Development & GR | Water Resources | 1 | 770.16 | 1606.07 | 1511.22
August 2025 | Karnataka | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | 3 | 1143.4 | 1143.4 | 515.77
August 2025 | Karnataka | Ministry of Housing & Urban Affairs | Urban Public Transport | 2 | 41193.24 | 45483.2 | 37902.51
August 2025 | Karnataka | Ministry of Housing & Urban Affairs | Waste & Water | 2 | 337.69 | 337.69 | 1278.27
August 2025 | Karnataka | Ministry of Petroleum & Natural Gas | Energy Storage | 1 | 678 | 1732 | 713.86
August 2025 | Karnataka | Ministry of Petroleum & Natural Gas | Oil & Gas | 5 | 9662 | 12693.6 | 8749.96
August 2025 | Karnataka | Ministry of Power | Transmission & Distribution | 6 | 15682.01 | 15682 | 2815.76
August 2025 | Karnataka | Ministry of Railways | Railways | 17 | 25363.59 | 31532.2 | 17702.61
August 2025 | Karnataka | Ministry of Steel | Steel | 1 | 1043.63 | 1043.63 | 229.77
August 2025 | Kerala | Department of Higher Education | Education | 1 | 1006.45 | 1217.4 | 623.6
August 2025 | Kerala | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | 1 | 484.57 | 484.57 | 83.95
August 2025 | Kerala | Ministry of Housing & Urban Affairs | Urban Public Transport | 1 | 1957.05 | 1957.05 | 329.94
August 2025 | Kerala | Ministry of Petroleum & Natural Gas | Oil & Gas | 3 | 7996.87 | 10990.9 | 4912.37
August 2025 | Kerala | Ministry of Railways | Railways | 3 | 2846 | 5199 | 3026.15
August 2025 | Ladakh | Department of Telecommunications | Telecommunication | 1 | 336.89 | 301.13 | 227.82
August 2025 | Ladakh | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | 1 | 480 | 640 | 434.79
August 2025 | Ladakh | Ministry of Power | Transmission & Distribution | 1 | 288.71 | 288.71 | 207.8
August 2025 | Madhya Pradesh | Department of Higher Education | Education | 1 | 496.28 | 496.28 | 143.95
August 2025 | Madhya Pradesh | Department of Telecommunications | Telecommunication | 2 | 1999.22 | 1806.51 | 732.39
August 2025 | Madhya Pradesh | Department of Water Resources, River Development & GR | Water Resources | 3 | 2628.27 | 2941.14 | 2725.95
August 2025 | Madhya Pradesh | Ministry of Coal | Coal | 14 | 8634.02 | 8634.02 | 3368.12
August 2025 | Madhya Pradesh | Ministry of Housing & Urban Affairs | Urban Public Transport | 2 | 14442.2 | 14442.2 | 7095.55
August 2025 | Madhya Pradesh | Ministry of Housing & Urban Affairs | Waste & Water | 4 | 1243.05 | 1243.05 | 6956.6
August 2025 | Madhya Pradesh | Ministry of Mines | Metals & Mining | 1 | 1856.36 | 1856.36 | 935.32
August 2025 | Madhya Pradesh | Ministry of Petroleum & Natural Gas | Energy Storage | 1 | 10088 | 10088 | 7672.23
August 2025 | Madhya Pradesh | Ministry of Petroleum & Natural Gas | Oil & Gas | 2 | 51211.25 | 51622 | 8351.1
August 2025 | Madhya Pradesh | Ministry of Power | Transmission & Distribution | 6 | 17446 | 17446 | 2930.65
August 2025 | Madhya Pradesh | Ministry of Railways | Railways | 18 | 56050.78 | 67640.2 | 42750.83
August 2025 | Maharashtra | Department of Higher Education | Education | 2 | 250.33 | 446.26 | 154.7
August 2025 | Maharashtra | Department of Telecommunications | Telecommunication | 3 | 5723.99 | 5723.99 | 1865.77
August 2025 | Maharashtra | Department of Water Resources, River Development & GR | Water Resources | 10 | 20736.55 | 30421.9 | 31303.79
August 2025 | Maharashtra | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | 1 | 500.48 | 500.48 | 332.26
August 2025 | Maharashtra | Ministry of Coal | Coal | 25 | 12455.88 | 12455.9 | 3084.72
August 2025 | Maharashtra | Ministry of Housing & Urban Affairs | Urban Public Transport | 6 | 34571.47 | 48711.5 | 28993.92
August 2025 | Maharashtra | Ministry of Housing & Urban Affairs | Waste & Water | 5 | 1088.72 | 1088.72 | 2313.41
August 2025 | Maharashtra | Ministry of Petroleum & Natural Gas | Energy Storage | 1 | 281.35 | 389.67 | 230.76
August 2025 | Maharashtra | Ministry of Petroleum & Natural Gas | Oil & Gas | 13 | 34264.24 | 37660.4 | 20702.79
August 2025 | Maharashtra | Ministry of Ports, Shipping and Waterways | Healthcare | 1 | 693 | 693 | 58
August 2025 | Maharashtra | Ministry of Ports, Shipping and Waterways | Shipping | 2 | 1266.8 | 1266.8 | 441.86
August 2025 | Maharashtra | Ministry of Power | Transmission & Distribution | 3 | 29589.67 | 29589.7 | 5993.74
August 2025 | Maharashtra | Ministry of Railways | Railways | 36 | 267281.11 | 358733 | 262133.68
August 2025 | Manipur | Department of Water Resources, River Development & GR | Water Resources | 1 | 1449.44 | 1822.24 | 1837.91
August 2025 | Manipur | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | 1 | 499 | 499 | 154.43
August 2025 | Manipur | Ministry of Petroleum & Natural Gas | Oil & Gas | 1 | 9265 | 9265 | 6393.85
August 2025 | Manipur | Ministry of Power | Transmission & Distribution | 1 | 5111.33 | 6700 | 5277.24
August 2025 | Manipur | Ministry of Railways | Railways | 1 | 14323 | 21885.9 | 15598.11
August 2025 | Meghalaya | Department of Higher Education | Education | 1 | 494.52 | 494.52 | 413.57
August 2025 | Meghalaya | Department of Telecommunications | Telecommunication | 1 | 971.96 | 971.96 | 208.25
August 2025 | Meghalaya | Ministry of Petroleum & Natural Gas | Oil & Gas | 1 | 9265 | 9265 | 6393.85
August 2025 | Meghalaya | Ministry of Power | Transmission & Distribution | 1 | 5111.33 | 6700 | 5277.24
August 2025 | Mizoram | Department of Higher Education | Education | 1 | 474.23 | 474.23 | 167.55
August 2025 | Mizoram | Ministry of Petroleum & Natural Gas | Oil & Gas | 1 | 9265 | 9265 | 6393.85
August 2025 | Mizoram | Ministry of Power | Transmission & Distribution | 1 | 5111.33 | 6700 | 5277.24
August 2025 | Nagaland | Department of Higher Education | Education | 1 | 275.63 | 275.63 | 260.1
August 2025 | Nagaland | Ministry of Petroleum & Natural Gas | Oil & Gas | 2 | 9492.62 | 9492.62 | 6402.97
August 2025 | Nagaland | Ministry of Power | Transmission & Distribution | 1 | 5111.33 | 6700 | 5277.24
August 2025 | Nagaland | Ministry of Railways | Railways | 2 | 8786.7 | 8786.7 | 5326
August 2025 | Odisha | Department of Higher Education | Education | 1 | 1229.32 | 773.76 | 837.04
August 2025 | Odisha | Department of Telecommunications | Telecommunication | 2 | 5262.57 | 5262.57 | 1699.75
August 2025 | Odisha | Department of Water Resources, River Development & GR | Water Resources | 2 | 1556.46 | 5291.33 | 5193.3
August 2025 | Odisha | Ministry of Coal | Coal | 12 | 36526.28 | 34218 | 13335.92
August 2025 | Odisha | Ministry of Coal | Electricity Generation | 1 | 27212.96 | 27213 | 1953.52
August 2025 | Odisha | Ministry of Mines | Metals & Mining | 5 | 7343.97 | 9724.14 | 5037.7
August 2025 | Odisha | Ministry of Petroleum & Natural Gas | Energy Storage | 2 | 12886.34 | 14217 | 11970.7
August 2025 | Odisha | Ministry of Petroleum & Natural Gas | Oil & Gas | 5 | 25285.44 | 23768.5 | 15778.36
August 2025 | Odisha | Ministry of Ports, Shipping and Waterways | Shipping | 1 | 3004.63 | 3004.63 | 1149.79
August 2025 | Odisha | Ministry of Power | Electricity Generation | 1 | 11843.75 | 12543 | 4161.68
August 2025 | Odisha | Ministry of Power | Transmission & Distribution | 1 | 342.69 | 342.69 | 0.6
August 2025 | Odisha | Ministry of Railways | Railways | 28 | 47401.37 | 52133.4 | 31907.65
August 2025 | Odisha | Ministry of Railways | Railways | 1 | 267.61 | 267.61 | 0
August 2025 | Odisha | Ministry of Steel | Steel | 1 | 1105.23 | 1105.23 | 769.08
August 2025 | Puducherry | Department of Higher Education | Education | 1 | 618.34 | 544.34 | 509.55
August 2025 | Puducherry | Ministry of Railways | Railways | 1 | 713 | 981 | 598.38
August 2025 | Punjab | Department of Higher Education | Education | 2 | 559.3 | 559.3 | 290.39
August 2025 | Punjab | Department of Water Resources, River Development & GR | Water Resources | 2 | 3727.07 | 5177.86 | 5072.69
August 2025 | Punjab | Ministry of Housing & Urban Affairs | Waste & Water | 2 | 545.53 | 545.53 | 612.96
August 2025 | Punjab | Ministry of Petroleum & Natural Gas | Oil & Gas | 6 | 13060.36 | 13090.4 | 8374.98
August 2025 | Punjab | Ministry of Power | Transmission & Distribution | 1 | 5969 | 5969 | 218.47
August 2025 | Punjab | Ministry of Railways | Railways | 3 | 15702.64 | 15702.6 | 8977.71
August 2025 | Rajasthan | Department of Telecommunications | Telecommunication | 2 | 758.54 | 530.07 | 361.9
August 2025 | Rajasthan | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | 2 | 1367 | 1367 | 634.54
August 2025 | Rajasthan | Ministry of Coal | Electricity Generation | 1 | 1813 | 1813 | 874.14
August 2025 | Rajasthan | Ministry of Petroleum & Natural Gas | Energy Storage | 3 | 52618.05 | 88948.1 | 67548.03
August 2025 | Rajasthan | Ministry of Petroleum & Natural Gas | Oil & Gas | 2 | 10599 | 10599 | 6647.57
August 2025 | Rajasthan | Ministry of Power | Electricity Generation | 1 | 5491.89 | 5491.89 | 4805.16
August 2025 | Rajasthan | Ministry of Power | Transmission & Distribution | 22 | 53646.51 | 54198.2 | 16979.78
August 2025 | Rajasthan | Ministry of Railways | Railways | 21 | 86599.15 | 162169 | 139520.05
August 2025 | Sikkim | Department of Higher Education | Education | 2 | 999.82 | 924.82 | 359.78
August 2025 | Sikkim | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | 1 | 323.26 | 323.26 | 29.7
August 2025 | Sikkim | Ministry of Petroleum & Natural Gas | Oil & Gas | 1 | 9265 | 9265 | 6393.85
August 2025 | Sikkim | Ministry of Power | Electricity Generation | 2 | 6686.33 | 7576.15 | 6161.06
August 2025 | Sikkim | Ministry of Power | Transmission & Distribution | 1 | 4754.42 | 9129.32 | 7462.2
August 2025 | Sikkim | Ministry of Railways | Railways | 1 | 7877 | 12133 | 9039.91
August 2025 | Tamil Nadu | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | 1 | 1207 | 1207 | 149.21
August 2025 | Tamil Nadu | Ministry of Coal | Electricity Generation | 1 | 218.03 | 218.03 | 161.73
August 2025 | Tamil Nadu | Ministry of Housing & Urban Affairs | Inland Waterways | 1 | 63246 | 63246 | 26410.15
August 2025 | Tamil Nadu | Ministry of Mines | Metals & Mining | 1 | 166 | 166 | 135
August 2025 | Tamil Nadu | Ministry of Petroleum & Natural Gas | Energy Storage | 3 | 2334 | 3448.71 | 1641.58
August 2025 | Tamil Nadu | Ministry of Petroleum & Natural Gas | Oil & Gas | 4 | 38385 | 46153 | 6060.57
August 2025 | Tamil Nadu | Ministry of Power | Transmission & Distribution | 1 | 548 | 548 | 14.68
August 2025 | Tamil Nadu | Ministry of Railways | Railways | 8 | 8730 | 11599 | 5805.89
August 2025 | Telangana | Department of Higher Education | Education | 1 | 262 | 262 | 177.09
August 2025 | Telangana | Department of Telecommunications | Telecommunication | 2 | 2038.99 | 2038.99 | 764.33
August 2025 | Telangana | Department of Water Resources, River Development & GR | Water Resources | 4 | 11670.14 | 24129.6 | 11830.43
August 2025 | Telangana | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | 1 | 500.48 | 500.48 | 332.26
August 2025 | Telangana | Ministry of Coal | Coal | 9 | 3890.03 | 3890.03 | 2462.36
August 2025 | Telangana | Ministry of Health & Family Welfare | Healthcare | 1 | 1028 | 1365.95 | 812.95
August 2025 | Telangana | Ministry of Power | Transmission & Distribution | 2 | 5694.56 | 5694.56 | 4337.14
August 2025 | Telangana | Ministry of Railways | Railways | 11 | 22284.15 | 26048.2 | 9009.21
August 2025 | Tripura | Ministry of Petroleum & Natural Gas | Energy Storage | 1 | 656 | 656 | 478.11
August 2025 | Tripura | Ministry of Petroleum & Natural Gas | Oil & Gas | 2 | 9474.33 | 9396.51 | 6462.73
August 2025 | Tripura | Ministry of Power | Transmission & Distribution | 1 | 5111.33 | 6700 | 5277.24
August 2025 | Uttar Pradesh | Department of Higher Education | Education | 1 | 246 | 246 | 193.38
August 2025 | Uttar Pradesh | Department of Telecommunications | Telecommunication | 3 | 2336.11 | 2107.64 | 960.21
August 2025 | Uttar Pradesh | Department of Water Resources, River Development & GR | Waste & Water | 2 | 1532.96 | 1532.96 | 243.43
August 2025 | Uttar Pradesh | Department of Water Resources, River Development & GR | Water Resources | 4 | 3694.65 | 8775.49 | 7633.54
August 2025 | Uttar Pradesh | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | 5 | 7268.31 | 7323.51 | 16971.73
August 2025 | Uttar Pradesh | Ministry of Coal | Coal | 2 | 1328.09 | 1328.09 | 1017.31
August 2025 | Uttar Pradesh | Ministry of Coal | Electricity Generation | 1 | 17237.8 | 21780.9 | 20269.54
August 2025 | Uttar Pradesh | Ministry of Housing & Urban Affairs | Urban Public Transport | 3 | 49730.1 | 49730.1 | 41466.62
August 2025 | Uttar Pradesh | Ministry of Housing & Urban Affairs | Waste & Water | 2 | 797.47 | 797.47 | 689.15
August 2025 | Uttar Pradesh | Ministry of Petroleum & Natural Gas | Energy Storage | 2 | 11068.45 | 11068.5 | 7888.89
August 2025 | Uttar Pradesh | Ministry of Petroleum & Natural Gas | Oil & Gas | 3 | 17824.68 | 18213.1 | 1578.44
August 2025 | Uttar Pradesh | Ministry of Ports, Shipping and Waterways | Inland Waterways | 1 | 5369.18 | 5061.15 | 3510.72
August 2025 | Uttar Pradesh | Ministry of Power | Electricity Generation | 2 | 28284.42 | 30471.2 | 14511.21
August 2025 | Uttar Pradesh | Ministry of Power | Transmission & Distribution | 3 | 8114.81 | 8114.81 | 1650.63
August 2025 | Uttar Pradesh | Ministry of Railways | Railways | 28 | 95245.3 | 169871 | 148169.27
August 2025 | Uttarakhand | Department of Higher Education | Education | 1 | 650.85 | 650.85 | 195.52
August 2025 | Uttarakhand | Department of Water Resources, River Development & GR | Water Resources | 1 | 2584.1 | 2584.1 | 968.52
August 2025 | Uttarakhand | Ministry of Housing & Urban Affairs | Real Estate | 1 | 150.97 | 150.97 | 18.95
August 2025 | Uttarakhand | Ministry of Power | Electricity Generation | 3 | 11663.95 | 26070 | 20361.54
August 2025 | Uttarakhand | Ministry of Railways | Railways | 1 | 38953 | 38953 | 24645.15
August 2025 | West Bengal | Department of Higher Education | Education | 2 | 787.2 | 729.2 | 693.6
August 2025 | West Bengal | Department of Telecommunications | Telecommunication | 1 | 1577.57 | 1577.57 | 598.31
August 2025 | West Bengal | Department of Water Resources, River Development & GR | Waste & Water | 1 | 154.73 | 154.73 | 96.17
August 2025 | West Bengal | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | 2 | 1877.3 | 1877.3 | 375.4
August 2025 | West Bengal | Ministry of Coal | Coal | 13 | 15863.74 | 15863.7 | 2802.3
August 2025 | West Bengal | Ministry of Mines | Construction | 1 | 255.37 | 255.37 | 79.34
August 2025 | West Bengal | Ministry of Petroleum & Natural Gas | Energy Storage | 1 | 10228 | 11407 | 9766.72
August 2025 | West Bengal | Ministry of Petroleum & Natural Gas | Oil & Gas | 8 | 18159.65 | 19007.2 | 11294.42
August 2025 | West Bengal | Ministry of Ports, Shipping and Waterways | Inland Waterways | 1 | 5369.18 | 5061.15 | 3510.72
August 2025 | West Bengal | Ministry of Ports, Shipping and Waterways | Shipping | 2 | 551.91 | 551.91 | 429.28
August 2025 | West Bengal | Ministry of Power | Electricity Generation | 3 | 20091.84 | 20160.8 | 3566.83
August 2025 | West Bengal | Ministry of Power | Transmission & Distribution | 2 | 751.63 | 751.63 | 0.9
August 2025 | West Bengal | Ministry of Railways | Railways | 16 | 49682.05 | 60254 | 33496.35
August 2025 | West Bengal | Ministry of Steel | Steel | 5 | 4214.67 | 4214.67 | 415.6

## Aug - NE Region
Month | Sl.No | Ministry/Department | Sector | Project Name | Implementing Agency | Project Code | State | Date of Approval | Start Date | Target DoC (Original) | Target DoC (Revised) | Original Cost (Rs Cr) | Revised Cost (Rs Cr) | Cumulative Expenditure (Rs Cr) | Physical Progress (%)
August 2025 | 1 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Guwahati Airport New Integrated Terminal Building Construction Project | Adani Airport Holdings Limited | 706724 | Assam | 12/2016 | 03/2018 | 03/2025 | 11/2025 | 1712 | 1712 | 2335.44 | 91
August 2025 | 2 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | C/o NITB Imphal Airport | Airport Authority of India [AAI] | 706718 | Manipur | 11/2021 | 07/2022 | 07/2024 | 12/2026 | 499 | 499 | 154.43 | 41
August 2025 | 3 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Widening of basic strip at Western Side of Runway Chainage 80m to 920m i/c slope stabilization Measures [Balance work] of uphill and Improvement of Storm Water Drainage System at Pakyong Airport, Sikkim on design & build basis [EPC] with integrated 10 years maintenance. | Airport Authority of India [AAI] | 612793 | Sikkim | 11/2023 | 12/2023 | 02/2026 | - | 323.26 | 323.26 | 29.7 | 12
August 2025 | 4 | Ministry of Coal | Coal | TIKAK EXTENSION OCP | MIS MoCoal Integration Logins | 615820 | Assam | 07/2022 | 07/2022 | 07/2031 | - | 159.77 | 159.77 | 80.84 | 0
August 2025 | 5 | Ministry of Coal | Coal | TIRAP OCP | MIS MoCoal Integration Logins | 615821 | Assam | 11/2022 | 11/2022 | 11/2030 | - | 289.46 | 289.46 | 105.47 | 0
August 2025 | 6 | Department of Higher Education | Education | Construction of Permanent Campus of National Institute of Technology Arunachal Pradesh | National Institute of Technology, Arunachal Pradesh | 612898 | Arunachal Pradesh | NA | 03/2013 | 08/2026 | - | 592.61 | 592.61 | 549.96 | 75
August 2025 | 7 | Department of Higher Education | Education | Tezpur University Projects | Tezpur University | 606112 | Assam | 05/2019 | 06/2021 | 11/2023 | 08/2025 | 153.71 | 153.71 | 54.05 | 95
August 2025 | 8 | Department of Higher Education | Education | Construction and Developement of National Institute of Technology Meghalaya Permanent Campus at Sohra | National Institute of Technology, Meghalaya | 612885 | Meghalaya | 03/2020 | 09/2014 | 03/2022 | 07/2025 | 494.52 | 494.52 | 413.57 | 86
August 2025 | 9 | Department of Higher Education | Education | Construction of Permanent Campus for NIT Mizoram at Lengpui, Aizawl | Ministry of Education | 612876 | Mizoram | 03/2020 | 05/2014 | 12/2029 | 12/2029 | 474.23 | 474.23 | 167.55 | 4
August 2025 | 10 | Department of Higher Education | Education | Establishment of NIT Nagaland | NIT Nagaland | 613013 | Nagaland | NA | 09/2012 | 12/2025 | - | 275.63 | 275.63 | 260.1 | 95
August 2025 | 11 | Department of Higher Education | Education | Establishment of Permanent Campus of NIT SIkkim at Khamdong-Gangtok District | Ministry of Education | 612883 | Sikkim | 02/2024 | 03/2024 | 02/2028 | 12/2026 | 685.76 | 610.76 | 121.56 | 9
August 2025 | 12 | Department of Higher Education | Education | Construction of Sikkim University Campus Phase-I Package-II at Yangang, South Sikkim | Sikkim University | 609736 | Sikkim | 08/2020 | 01/2022 | 01/2025 | 09/2025 | 314.06 | 314.06 | 238.22 | 82
August 2025 | 13 | Ministry of Power | Electricity Generation | 240MW Heo HE Project | North Eastern Electric Power Corporation Limited | 611698 | Arunachal Pradesh | 12/2024 | 05/2025 | 07/2029 | - | 1938.85 | 1938.85 | 49.31 | 3
August 2025 | 14 | Ministry of Power | Electricity Generation | 186 MW Tato-I H E Project | North Eastern Electric Power Corporation Limited | 611699 | Arunachal Pradesh | 12/2024 | 05/2025 | 07/2029 | - | 1750.07 | 1750.07 | 102.79 | 2
August 2025 | 15 | Ministry of Power | Electricity Generation | Dibang Multipurpose Project (National Highways & Infrastructure Development Corporation Ltd. | [NHIDCL] | 602182 | Arunachal Pradesh | 02/2023 | 02/2023 | 02/2032 | 02/2032 | 31876.39 | 31876.4 | 3553.9 | 16
August 2025 | 16 | Ministry of Power | Electricity Generation | Subansiri Lower HE Project [2000 MW] (National Highways & Infrastructure Development Corporation Ltd. | [NHIDCL] | 602096 | Multi-States (Arunachal Pradesh, Assam) | 09/2003 | 09/2003 | 09/2010 | 05/2026 | 6285.33 | 26075.5 | 24880.95 | 96
August 2025 | 17 | Ministry of Power | Electricity Generation | TEESTA-VI HE PROJECT, SIKKIM [500 MW], executed by LANCO TEESTA HYDRO POWER LIMITED [A wholly owned Subsidiary of NHPC LTD. acquired through NCLT] (National Highways & Infrastructure Development Corporation Ltd. | [NHIDCL] | 602181 | Sikkim | 03/2019 | 03/2019 | 03/2024 | 12/2027 | 5748.04 | 5748.04 | 4576.93 | 69
August 2025 | 18 | Ministry of Power | Electricity Generation | Rangit-IV HE Project [120 MW] executed by Jal Power Corporation Ltd. [JPCL] - A wholly owned subsidiary of NHPC Ltd. acquired through NCLT (National Highways & Infrastructure Development Corporation Ltd. | [NHIDCL] | 605156 | Sikkim | 03/2021 | 03/2021 | 05/2024 | 12/2025 | 938.29 | 1828.11 | 1584.13 | 91
August 2025 | 19 | Ministry of Power | Transmission & Distribution | Comprehensive Scheme for Strengthening of Transmission and Distribution [T&D] Systems [CSST&DS] in Arunachal Pradesh and Sikkim | Power Grid Corporation of India Limited [POWERGRID] | 602223 | Multi-States (Arunachal Pradesh, Sikkim) | 03/2021 | 01/2016 | 12/2018 | 03/2027 | 4754.42 | 9129.32 | 7462.2 | 81
August 2025 | 20 | Ministry of Power | Transmission & Distribution | NORTH EASTERN REGION POWER SYSTEM IMPROVEMENT PROJECT [NERPSIP] | Power Grid Corporation of India Limited [POWERGRID] | 607709 | Multi-States (Assam, Manipur, Meghalaya, Mizoram, Nagaland, Tripura) | 12/2014 | 03/2016 | 12/2018 | 12/2025 | 5111.33 | 6700 | 5277.24 | 96
August 2025 | 21 | Ministry of Petroleum & Natural Gas | Energy Storage | Rajasthan Refinery Project | MinistryofPetroleumNaturalGas | 701263 | Arunachal Pradesh | NA | 10/2017 | 10/2022 | 03/2026 | 43129 | 79459 | 60295.14 | 88
August 2025 | 22 | Ministry of Petroleum & Natural Gas | Energy Storage | Paradip-Numaligarh Crude Oil Pipeline [PNCPL] & Crude Oil Import Terminal [COIT] at Paradip | Ministry of Petroleum & Natural Gas | 701349 | Assam | NA | 01/2019 | 07/2024 | 09/2025 | 10228 | 11407 | 9766.72 | 87
August 2025 | 23 | Ministry of Petroleum & Natural Gas | Energy Storage | Construction of LPG Facilities at Kamardanga, Assam | Hindustan Petroleum Corporation Limited | 709754 | Assam | NA | 03/2023 | 07/2027 | 07/2027 | 156.36 | 156.36 | 54.15 | 46
August 2025 | 24 | Ministry of Petroleum & Natural Gas | Energy Storage | Setting up of new rail fed POL facility at Kamardanga, Assam | Hindustan Petroleum Corporation Limited [HPCL] | 709755 | Assam | NA | 03/2023 | 07/2027 | 07/2027 | 384.04 | 384.04 | 120.4 | 52
August 2025 | 25 | Ministry of Petroleum & Natural Gas | Energy Storage | Grass Root Rail-fed Depot at Sekerkote, Agartala as resitement of existing Dharmanagar Depot | Indian Oil Corporation Limited [IOCL] | 400035 | Tripura | NA | 06/2022 | 09/2025 | 06/2026 | 656 | 656 | 478.11 | 86
August 2025 | 26 | Ministry of Petroleum & Natural Gas | Oil & Gas | Numaligarh Refinery Expansion Project | Ministry of Petroleum & Natural Gas | 604791 | Assam | NA | 07/2020 | 07/2024 | 12/2025 | 12366 | 22494 | 16764.09 | 76
August 2025 | 27 | Ministry of Petroleum & Natural Gas | Oil & Gas | Assam Bio Refinery, ABRPL | Ministry of Petroleum & Natural Gas | 604792 | Assam | NA | 02/2018 | 09/2021 | 09/2025 | 1750 | 4930 | 4710 | 99
August 2025 | 28 | Ministry of Petroleum & Natural Gas | Oil & Gas | Development of Surface Facilities for production and evacuation of Crude Oil and Natural Gas from Nadua and East Khagorija | Ministry of Petroleum & Natural Gas | 604863 | Assam | NA | 01/2018 | 02/2020 | 12/2025 | 682.9 | 726.93 | 489.3 | 94
August 2025 | 29 | Ministry of Petroleum & Natural Gas | Oil & Gas | Guwahati Refinery Expansion [1.0 to 1.2 MMTPA] along with installation of CRU, Guwahati Refinery | Ministry of Petroleum & Natural Gas | 607701 | Assam | NA | 05/2021 | 10/2023 | 05/2026 | 412.3 | 577 | 430.83 | 85
August 2025 | 30 | Ministry of Petroleum & Natural Gas | Oil & Gas | Upgradation of Facilities of Numaligarh-Siliguri Product Pipeline [NSPL] for transportation of additional products from existing 1.72 MMTPA to 5.5 MMTPA | Ministry of Petroleum & Natural Gas | 701350 | Assam | NA | 06/2021 | 12/2024 | 10/2025 | 860 | 860 | 584.76 | 98
August 2025 | 31 | Ministry of Petroleum & Natural Gas | Oil & Gas | Construction of Field Gas Gathering Station at Baghjan area for collection, processing & transportation of natural Gas to be produced from Baghjan Field | Ministry of Petroleum & Natural Gas | 616858 | Assam | NA | 12/2020 | 03/2024 | 12/2025 | 430.76 | 430.76 | 327.27 | 85
August 2025 | 32 | Ministry of Petroleum & Natural Gas | Oil & Gas | Augmentation/Revamping of Facilities at existing Guwahati Terminal at Betkuchi | MinistryofPetroleumNaturalGas | 709776 | Assam | NA | 04/2022 | 09/2026 | 09/2026 | 277 | 323.09 | 185.18 | 68
August 2025 | 33 | Ministry of Petroleum & Natural Gas | Oil & Gas | Capacity Expansion of Digboi Refinery from 0.65 to 1.0 MMTPA | MinistryofPetroleumNaturalGas | 709779 | Assam | NA | 06/2022 | 03/2026 | 03/2026 | 768 | 740 | 107.72 | 39
August 2025 | 34 | Ministry of Petroleum & Natural Gas | Oil & Gas | Pipeline Network Project Rudrasagar | Ministry of Petroleum & Natural Gas | 709847 | Assam | NA | 01/2023 | 04/2026 | 04/2026 | 344.99 | 344.99 | 211.05 | 47
August 2025 | 35 | Ministry of Petroleum & Natural Gas | Oil & Gas | Borholla GGS Life Extension Project [BLEP] | Ministry of Petroleum & Natural Gas | 709850 | Assam | NA | 09/2023 | 05/2026 | 05/2026 | 198.7 | 198.7 | 36.8 | 30
August 2025 | 36 | Ministry of Petroleum & Natural Gas | Oil & Gas | DCU Revamp Project | NRL | 709864 | Assam | NA | 08/2021 | 07/2024 | 10/2025 | 370 | 370 | 253.17 | 60
August 2025 | 37 | Ministry of Petroleum & Natural Gas | Oil & Gas | Power Recovery Turbine [PRT] in PFCCU unit as an Energy Conservation Scheme | NRL | 709865 | Assam | NA | 04/2023 | 12/2024 | 10/2025 | 293.5 | 293.5 | 97.22 | 94
August 2025 | 38 | Ministry of Petroleum & Natural Gas | Oil & Gas | North East Gas Grid | Ministry of Petroleum & Natural Gas | 701346 | Multi-States (Arunachal Pradesh, Assam, Manipur, Meghalaya, Mizoram, Nagaland, Sikkim, Tripura) | NA | 04/2020 | 03/2024 | 03/2026 | 9265 | 9265 | 6393.85 | 85
August 2025 | 39 | Ministry of Petroleum & Natural Gas | Oil & Gas | Augmentation/ Revamping of Dimapur Depot, Dimapur | MinistryofPetroleumNaturalGas | 709786 | Nagaland | NA | 08/2023 | 11/2027 | 11/2027 | 227.62 | 227.62 | 9.12 | 22
August 2025 | 40 | Ministry of Petroleum & Natural Gas | Oil & Gas | Creation of Gas Dehydration Facilities, Tripura Asset | Oil and Natural Gas Corporation Limited [ONGC] | 709837 | Tripura | NA | 03/2022 | 05/2024 | 12/2025 | 209.33 | 131.51 | 68.88 | 62
August 2025 | 41 | Ministry of Railways | Railways | Doubling of New Bonggigaon to Kamakhya via Goalpara - 176 km | Northeast Frontier Railway [NFR] | 705572 | Assam | 09/2016 | 09/2016 | 03/2026 | 03/2026 | 4060 | 4961 | 3683.75 | 93
August 2025 | 42 | Ministry of Railways | Railways | Guwahati-Dibrugarh via Tinsukia & Simaluguri-Dibrugarh | Central Organisation for Railway Electrification [CORE] | 706922 | Assam | 09/2020 | 09/2018 | 09/2020 | 06/2024 | 890.36 | 889.36 | 391.73 | 89
August 2025 | 43 | Ministry of Railways | Railways | Mariani-Jorhat, Tinsukia-Dangri and Makum -TirapTrack Electrification Project | GM/C/ NFR | 706940 | Assam | NA | 01/2022 | 05/2024 | - | 183.99 | 183.99 | 0 | 0
August 2025 | 44 | Ministry of Railways | Railways | Harmuty-Murkongselek Branch Line Electrification Project | GM/C/ NFR | 706942 | Assam | NA | 01/2022 | 05/2024 | - | 237.52 | 237.52 | 0 | 0
August 2025 | 45 | Ministry of Railways | Railways | Jiribam-Imphal new line project | Northeast Frontier Railway [NFR] | 705391 | Manipur | 03/2013 | 12/2007 | 12/2026 | 06/2029 | 14323 | 21885.9 | 15598.11 | 69
August 2025 | 46 | Ministry of Railways | Railways | Murkongselek-Pasighat | Northeast Frontier Railway (NFR) - II | 705401 | Multi-States (Arunachal Pradesh, Assam) | NA | 03/2012 | 03/2025 | 12/2025 | 435 | 1250 | 901 | 56
August 2025 | 47 | Ministry of Railways | Railways | Dimapur [Dhansiri]-Sukhobi Kohima [Zubza] NL [82.5 Km] | Northeast Frontier Railway [NFR] | 705392 | Multi-States (Assam, Nagaland) | 08/2015 | 02/2016 | 03/2025 | 12/2025 | 6663 | 6663 | 5312.26 | 80
August 2025 | 48 | Ministry of Railways | Railways | Lumding Furkating Doubling Project 140 km | Northeast Frontier Railway [NFR] | 616701 | Multi-States (Assam, Nagaland) | NA | 01/2025 | 02/2028 | - | 2123.7 | 2123.7 | 13.74 | 0
August 2025 | 49 | Ministry of Railways | Railways | Sivok-Rangpo New Rail Line | Indian Railway Construction International Limited [IRCON] | 705432 | Sikkim | 10/2009 | 05/2010 | 05/2015 | 12/2027 | 7877 | 12133 | 9039.91 | 84
August 2025 | 50 | Department of Telecommunications | Telecommunication | Provision of 4G based Mobile Services in Uncovered Villages and National Highways of Meghalaya | Department of Telecommunications [DoT] | 701598 | Meghalaya | 09/2019 | 09/2020 | 03/2022 | 09/2025 | 971.96 | 971.96 | 208.25 | 99
August 2025 | 51 | Department of Telecommunications | Telecommunication | Provision of 4G Mobile Services in Uncovered Villages of Arunachal Pradesh and 2 Districts of Assam | Department of Telecommunications [DoT] | 701597 | Multi-States (Arunachal Pradesh, Assam) | 12/2020 | 10/2021 | 04/2023 | 09/2025 | 1255.49 | 1255.49 | 284.04 | 89
August 2025 | 52 | Ministry of Housing & Urban Affairs | Waste & Water | Dibrugarh Water Supply Infrastructure Project | Ministry of Housing & Urban Affairs | 702682 | Assam | NA | 01/2020 | 03/2023 | 12/2025 | 186.8 | 186.8 | 1291.55 | 98
August 2025 | 53 | Department of Water Resources, River Development & GR | Water Resources | Borolia Irrigation Project | Department of Water Resources, River Development & GR | 701370 | Assam | NA | 12/1996 | 12/2022 | 03/2026 | 256.16 | 256.16 | 0 | 55
August 2025 | 54 | Department of Water Resources, River Development & GR | Water Resources | Thoubal Multipurpose Project | Water Resources Department-MN | 701400 | Manipur | 01/2022 | 04/1997 | 12/2019 | 03/2026 | 1449.44 | 1822.24 | 1837.91 | 98

## Aug - All Ongoing
Month | Sl.No | Ministry/Department | Sector | Project Name | Implementing Agency | Project Code | State | Date of Approval | Start Date | Target DoC (Original) | Target DoC (Revised) | Original Cost (Rs Cr) | Revised Cost (Rs Cr) | Cumulative Expenditure (Rs Cr) | Physical Progress (%)
August 2025 | 1 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Construction of New Domestic Terminal Building Building and miscellaneous works including maintenance, operations and AICMC at Kadapa Airport | Airport Authority of India [AAI] | 612786 | Andhra Pradesh | 03/2023 | 01/2024 | 01/2026 | 03/2026 | 265.91 | 265.91 | 50.06 | 34
August 2025 | 2 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Construction of New Integrated Terminal Building and associated works including apron to park 3 code E type of aircraft or 6 code C type of aircraft at Vijayawada Airport. | Airport Authority of India [AAI] | 701107 | Andhra Pradesh | 06/2020 | 09/2020 | 09/2022 | 12/2025 | 611.8 | 611.8 | 473.27 | 79
August 2025 | 3 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Construction of New Domestic Terminal Building at Rajahmundry Airport. | Airport Authority of India [AAI] | 701121 | Andhra Pradesh | 12/2022 | 08/2023 | 08/2025 | 12/2025 | 347.15 | 347.15 | 90.56 | 51
August 2025 | 4 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Guwahati Airport New Integrated Terminal Building Construction Project | Adani Airport Holdings Limited | 706724 | Assam | 12/2016 | 03/2018 | 03/2025 | 11/2025 | 1712 | 1712 | 2335.44 | 91
August 2025 | 5 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Development of New Civil Enclave at Bihta | Airport Authority of India [AAI] | 612183 | Bihar | 08/2024 | 03/2025 | 09/2027 | - | 1413 | 1413 | 0 | 1
August 2025 | 6 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Development of New Civil Enclave and associated works at Darbhanga Airport | Airport Authority of India [AAI] | 612194 | Bihar | 07/2024 | 07/2024 | 01/2026 | - | 911.66 | 911.66 | 160.2 | 26
August 2025 | 7 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Construction of New Domestic Terminal Building [Phase-I and II] and other allied structures at JPNI Airport, Patna | Airport Authority of India [AAI] | 701101 | Bihar | 12/2018 | 10/2018 | 07/2023 | 11/2025 | 1216.9 | 1216.9 | 1096.51 | 94
August 2025 | 8 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Goa Airport Terminal Building Extension Project | Airport Authority of India [AAI] | 701105 | Goa | 11/2017 | 12/2019 | 12/2021 | 09/2025 | 255.69 | 255.69 | 130 | 90
August 2025 | 9 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Development of Dholera International Greenfield Airport , Gujarat | Airport Authority of India [AAI] | 701126 | Gujarat | 06/2022 | 07/2022 | 06/2026 | 06/2026 | 1305 | 1551 | 1348.78 | 64
August 2025 | 10 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Construction of NTB complex including apron, taxi track and other associated civil works and electrical & mechanical installations towards Tawi River side at CA Jammu. | Airport Authority of India [AAI] | 611047 | Jammu and Kashmir | 07/2022 | 07/2023 | 06/2026 | 06/2026 | 861.37 | 861.37 | 177.69 | 35
August 2025 | 11 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Construction of New Domestic Terminal Building and Miscellaneous works at Hubli Airport | Airport Authority of India [AAI] | 612787 | Karnataka | 06/2023 | 01/2024 | 01/2026 | 03/2026 | 320.47 | 320.47 | 61.79 | 38
August 2025 | 12 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Construction of New Domestic Terminal Building and Miscellaneous Works at Belagavi Airport. | Airport Authority of India [AAI] | 612788 | Karnataka | 06/2023 | 02/2024 | 01/2026 | 01/2026 | 322.45 | 322.45 | 121.72 | 52
August 2025 | 13 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Development of additional RESA on either end on Runway 10-28 at Calicut Airport. Construction of embankment with slope protection, drainage system and associated works for additional RESA on either end on Runway 10-28 | Airport Authority of India [AAI] | 612789 | Kerala | 06/2023 | 02/2024 | 09/2025 | 03/2026 | 484.57 | 484.57 | 83.95 | 21
August 2025 | 14 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Construction of Terminal Building & Associated works at Leh Airport, Ladakh | Airport Authority of India [AAI] | 400010 | Ladakh | 07/2018 | 09/2018 | 09/2021 | 10/2025 | 480 | 640 | 434.79 | 71
August 2025 | 15 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | C/o NITB Imphal Airport | Airport Authority of India [AAI] | 706718 | Manipur | 11/2021 | 07/2022 | 07/2024 | 12/2026 | 499 | 499 | 154.43 | 41
August 2025 | 16 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | SITC of ATM Automation System and ASMGCS [Including SMR & MLAT] for Mumbai, Navi Mumbai, Jewar [earlier MOPA, without ASMGCS], HIAL & BIAL | Airport Authority of India [AAI] | 611570 | Multi-States (Karnataka, Maharashtra, Telangana, Uttar Pradesh) | NA | 10/2022 | 09/2025 | 08/2026 | 500.48 | 500.48 | 332.26 | 75
August 2025 | 17 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Construction of New Passenger Terminal Building for Domestic Operations at Jodhpur Airport. | Airport Authority of India [AAI] | 701127 | Rajasthan | 05/2022 | 04/2023 | 11/2024 | 10/2025 | 480 | 480 | 281.72 | 84
August 2025 | 18 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Construction of New Integrated Passenger Terminal Building at Udaipur Airport | Airport Authority of India [AAI] | 701128 | Rajasthan | 06/2023 | 11/2022 | 03/2026 | 10/2026 | 887 | 887 | 352.82 | 49
August 2025 | 19 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Widening of basic strip at Western Side of Runway Chainage 80m to 920m i/c slope stabilization Measures [Balance work] of uphill and Improvement of Storm Water Drainage System at Pakyong Airport, Sikkim on design & build basis [EPC] with integrated 10 years maintenance. | Airport Authority of India [AAI] | 612793 | Sikkim | 11/2023 | 12/2023 | 02/2026 | - | 323.26 | 323.26 | 29.7 | 12
August 2025 | 20 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Modernization of Chennai Airport, Phase II, Part 2 | Airport Authority of India [AAI] | 611602 | Tamil Nadu | 05/2018 | 06/2023 | 07/2025 | 03/2026 | 1207 | 1207 | 149.21 | 22
August 2025 | 21 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Construction of New Terminal Building, Second Link Taxi Track, Apron Expansion, and associated works at Prayagraj Airport- On Design & Build Basis. | Airport Authority of India [AAI] | 612063 | Uttar Pradesh | NA | 08/2023 | 11/2024 | 08/2025 | 219.18 | 274.38 | 215.19 | 100
August 2025 | 22 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Lucknow Airport-Terminal 3- Phase 1 & Other Associated Works | Adani Airport Holdings Limited | 701091 | Uttar Pradesh | 06/2018 | 09/2018 | 03/2026 | - | 3100 | 3100 | 16024.42 | 100
August 2025 | 23 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Development of Lal Bahadur Shastri International airport, Varanasi including C/o New Terminal Building, Apron Extension, Runway Extension, PTT and allied works. | Airport Authority of India [AAI] | 701113 | Uttar Pradesh | 07/2024 | 07/2024 | 07/2027 | 07/2027 | 2869.65 | 2869.65 | 322.98 | 16
August 2025 | 24 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Development of New Integrated Civil Enclave at Agra Airport | Airport Authority of India [AAI] | 701122 | Uttar Pradesh | 06/2024 | 07/2024 | 07/2026 | - | 579 | 579 | 76.88 | 16
August 2025 | 25 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Development of New Civil Enclave at Bagdogra Airport | Airport Authority of India [AAI] | 611495 | West Bengal | 08/2024 | 10/2023 | 01/2027 | 01/2027 | 1549 | 1549 | 274.14 | 11
August 2025 | 26 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Re-Construction of Rigid portions of Secondary Runway, K and A Taxiway and Strengthening of C Taxiway at NSCBI Airport Kolkata. | Airport Authority of India [AAI] | 612791 | West Bengal | 04/2023 | 12/2023 | 02/2025 | 08/2026 | 328.3 | 328.3 | 101.26 | 45
August 2025 | 27 | Ministry of Coal | Coal | TIKAK EXTENSION OCP | MIS MoCoal Integration Logins | 615820 | Assam | 07/2022 | 07/2022 | 07/2031 | - | 159.77 | 159.77 | 80.84 | 0
August 2025 | 28 | Ministry of Coal | Coal | TIRAP OCP | MIS MoCoal Integration Logins | 615821 | Assam | 11/2022 | 11/2022 | 11/2030 | - | 289.46 | 289.46 | 105.47 | 0
August 2025 | 29 | Ministry of Coal | Coal | PORDA CHIMTAPANI OCP [10 MTY] | South Eastern Coalfields Limited [SECL] | 400144 | Chhattisgarh | 12/2020 | 12/2020 | 03/2029 | - | 2310.12 | 2310.12 | 83.66 | 10
August 2025 | 30 | Ministry of Coal | Coal | CHHAL OC SEAM III [6 MTY] | South Eastern Coalfields Limited [SECL] | 400145 | Chhattisgarh | 12/2013 | 12/2013 | 03/2022 | 09/2025 | 610.63 | 610.63 | 577.46 | 85
August 2025 | 31 | Ministry of Coal | Coal | KUSMUNDA OC EXPANSION [15 TO 50 MTY] | South Eastern Coalfields Limited [SECL] | 400147 | Chhattisgarh | 08/2013 | 08/2013 | 03/2023 | 03/2030 | 7612.33 | 7612.33 | 4697.95 | 81
August 2025 | 32 | Ministry of Coal | Coal | BAROUD OC EXPANSION [3.0-10.0M | South Eastern Coalfields Limited [SECL] | 400149 | Chhattisgarh | 08/2020 | 08/2020 | 03/2029 | - | 2309.8 | 2309.8 | 926.11 | 48
August 2025 | 33 | Ministry of Coal | Coal | DIPKA EXPANSION OCP [40 MTY] | South Eastern Coalfields Limited [SECL] | 400354 | Chhattisgarh | 12/2020 | 12/2020 | 03/2029 | - | 5241.4 | 5241.4 | 2830.01 | 37
August 2025 | 34 | Ministry of Coal | Coal | GEVRA OC [70 MTY] | South Eastern Coalfields Limited [SECL] | 400424 | Chhattisgarh | 03/2016 | 03/2016 | 03/2023 | 03/2026 | 11816.4 | 11816.4 | 5328.96 | 77
August 2025 | 35 | Ministry of Coal | Coal | JAMPALI OC RCE [2.0 MTY] | South Eastern Coalfields Limited [SECL] | 613795 | Chhattisgarh | 05/2020 | 05/2020 | 03/2025 | 06/2025 | 278.64 | 278.64 | 210.07 | 82
August 2025 | 36 | Ministry of Coal | Coal | AMERA OC RCE [1.0 MTY] | South Eastern Coalfields Limited [SECL] | 613798 | Chhattisgarh | 02/2015 | 02/2015 | 03/2026 | - | 335.97 | 335.97 | 88.21 | 42
August 2025 | 37 | Ministry of Coal | Coal | AMGAON OC RCE [1.0 MTY] | South Eastern Coalfields Limited [SECL] | 613799 | Chhattisgarh | 07/2015 | 07/2015 | 03/2026 | - | 316.11 | 316.11 | 188.6 | 72
August 2025 | 38 | Ministry of Coal | Coal | JAGANNATHPUR OC RCE PROJECT[3 | South Eastern Coalfields Limited [SECL] | 613800 | Chhattisgarh | 07/2016 | 07/2016 | 03/2025 | 03/2026 | 459.49 | 459.49 | 274.35 | 92
August 2025 | 39 | Ministry of Coal | Coal | MAHAMAYA OCP [1.50 MTY] | South Eastern Coalfields Limited [SECL] | 613801 | Chhattisgarh | 05/2018 | 05/2018 | 03/2026 | - | 410.26 | 410.26 | 181.23 | 38
August 2025 | 40 | Ministry of Coal | Coal | KATKONA RO UG MINE | South Eastern Coalfields Limited [SECL] | 615191 | Chhattisgarh | 01/2023 | 01/2023 | 03/2029 | - | 329.21 | 329.21 | 60.3 | 2
August 2025 | 41 | Ministry of Coal | Coal | PELMA OC MDO | South Eastern Coalfields Limited [SECL] | 616234 | Chhattisgarh | 10/2022 | 10/2022 | 03/2033 | - | 1725.04 | 1725.04 | 15.66 | 17
August 2025 | 42 | Ministry of Coal | Coal | KUSMUNDA OC EXPANSION PROJECT 50-75 MTY | SECL - CIL | 617287 | Chhattisgarh | 11/2024 | 11/2024 | 03/2030 | - | 4516.88 | 4516.88 | 16.97 | 3
August 2025 | 43 | Ministry of Coal | Coal | MANIKPUR OC EXPANSION PROJECT 7 MTY | South Eastern Coalfields Limited [SECL] | 617288 | Chhattisgarh | 01/2025 | 01/2025 | 03/2029 | - | 382.61 | 382.61 | 0.86 | 1
August 2025 | 44 | Ministry of Coal | Coal | DIPKA OC | SECL - CIL | 612838 | Gujarat | NA | 01/2017 | 03/2025 | - | 7580 | 7580 | 3091 | 65
August 2025 | 45 | Ministry of Coal | Coal | HURA C OCP | ECL - CIL | 400018 | Jharkhand | 08/2022 | 08/2022 | 03/2029 | - | 859.41 | 859.41 | 450.76 | 62
August 2025 | 46 | Ministry of Coal | Coal | KONAR EXPANSION OCP | Ministry of Coal | 400073 | Jharkhand | 01/2022 | 01/2022 | 03/2032 | - | 799.34 | 799.34 | 424.01 | 45
August 2025 | 47 | Ministry of Coal | Coal | KARO EXPANSION OCP | Ministry of Coal | 400074 | Jharkhand | 01/2022 | 01/2022 | 03/2029 | - | 908.47 | 908.47 | 269.18 | 22
August 2025 | 48 | Ministry of Coal | Coal | SANGHMITRA OC | Ministry of Coal | 400136 | Jharkhand | 03/2024 | 03/2027 | 03/2032 | - | 2660 | 2660 | 0 | 0
August 2025 | 49 | Ministry of Coal | Coal | CHANDRAGUPT OCP | Ministry of Coal | 400138 | Jharkhand | 08/2020 | 08/2020 | 03/2032 | - | 973.5 | 973.5 | 440.56 | 25
August 2025 | 50 | Ministry of Coal | Coal | KOTRE BASANTPUR PACHMO OCP | Ministry of Coal | 400139 | Jharkhand | 08/2020 | 08/2020 | 03/2032 | - | 861.06 | 625.4 | 455.95 | 42
August 2025 | 51 | Ministry of Coal | Coal | Pachwara South Coal Block | NLC India Limited [NLCIL] | 400142 | Jharkhand | NA | 12/2019 | 09/2028 | - | 2242.9 | 2242.9 | 1170.75 | 74
August 2025 | 52 | Ministry of Coal | Coal | RPR MAGADH EXP OCP | Ministry of Coal | 400150 | Jharkhand | 08/2020 | 08/2020 | 03/2028 | - | 7254.37 | 7254.37 | 1535.31 | 38
August 2025 | 53 | Ministry of Coal | Coal | NORTH URIMARI EXPANSION OCP | Ministry of Coal | 400151 | Jharkhand | 07/2021 | 07/2021 | 03/2029 | - | 778.8 | 778.8 | 695.99 | 67
August 2025 | 54 | Ministry of Coal | Coal | EPR ROHINI - KARKETTA OCP | Central Coalfields Limited [CCL] | 400153 | Jharkhand | 01/2021 | 01/2021 | 03/2028 | - | 1020.42 | 1020.42 | 83.95 | 20
August 2025 | 55 | Ministry of Coal | Coal | EPR PUNDI OCP | Ministry of Coal | 400154 | Jharkhand | 11/2020 | 11/2020 | 03/2027 | - | 713.35 | 713.35 | 236.58 | 10
August 2025 | 56 | Ministry of Coal | Coal | EPR ASHOK OC | Ministry of Coal | 400155 | Jharkhand | 05/2021 | 05/2021 | 03/2028 | - | 2898.28 | 2898.28 | 178.51 | 22
August 2025 | 57 | Ministry of Coal | Coal | EPR AMRAPALI OCP | Ministry of Coal | 400156 | Jharkhand | 02/2020 | 02/2020 | 03/2028 | - | 5136.15 | 5136.15 | 1154.6 | 43
August 2025 | 58 | Ministry of Coal | Coal | RAJRAPPA RCE OCP | Ministry of Coal | 400160 | Jharkhand | 12/2009 | 12/2009 | 03/2016 | 03/2027 | 510.85 | 510.85 | 488.67 | 76
August 2025 | 59 | Ministry of Coal | Coal | CHITRA EAST OC | Eastern Coal Fields Limited [ECL] | 400172 | Jharkhand | 08/2018 | 08/2018 | 03/2026 | - | 513.99 | 513.99 | 229.01 | 51
August 2025 | 60 | Ministry of Coal | Coal | JHARKHAND-LAIYO OCP | Ministry of Coal | 400352 | Jharkhand | 08/2020 | 08/2020 | 03/2031 | - | 764.57 | 764.57 | 145.81 | 29
August 2025 | 61 | Ministry of Coal | Coal | MOONIDIH XV SEAM UG | Ministry of Coal | 400425 | Jharkhand | 08/2011 | 08/2011 | 03/2019 | 05/2026 | 1230.27 | 1230.27 | 626.63 | 81
August 2025 | 62 | Ministry of Coal | Coal | 2.5 MTPA PATHERDIH NLW WASHERY | Ministry of Coal | 611017 | Jharkhand | 10/2015 | 04/2016 | 04/2018 | 03/2026 | 334.27 | 334.27 | 140.51 | 48
August 2025 | 63 | Ministry of Coal | Coal | AMALAGAMATED NTST KUJAMA OCP 8.5MTY | Ministry of Coal | 611864 | Jharkhand | 01/2023 | 01/2023 | 03/2030 | - | 4011.85 | 4011.85 | 398.5 | 28
August 2025 | 64 | Ministry of Coal | Coal | MURAIDIH UG PROJECT | Ministry of Coal | 613808 | Jharkhand | 02/2011 | 02/2011 | 04/2014 | 12/2026 | 339.87 | 339.87 | 191 | 70
August 2025 | 65 | Ministry of Coal | Coal | TAPIN SOUTH EXPN | Ministry of Coal | 615349 | Jharkhand | 11/2020 | 11/2020 | 03/2028 | - | 230.41 | 230.41 | 22.02 | 20
August 2025 | 66 | Ministry of Coal | Coal | SIRKA OC | Ministry of Coal | 615822 | Jharkhand | 05/2020 | 05/2020 | 03/2028 | - | 222.82 | 222.82 | 139.31 | 53
August 2025 | 67 | Ministry of Coal | Coal | TETARIAKHAR OC | Ministry of Coal | 615843 | Jharkhand | 11/2019 | 11/2019 | 03/2025 | 03/2027 | 243.52 | 243.52 | 44.64 | 30
August 2025 | 68 | Ministry of Coal | Coal | CHUPERBHITA SIMLONG OCP MDO 6 MTY | Eastern Coal Fields Limited [ECL] | 616225 | Jharkhand | 12/2023 | 12/2023 | 03/2037 | - | 979.08 | 979.08 | 0 | 0
August 2025 | 69 | Ministry of Coal | Coal | JARANGDIH EXPN. OCP 1.5 MTY | CCL - CIL | 616236 | Jharkhand | 02/2020 | 02/2020 | 03/2029 | - | 414.37 | 414.37 | 85.6 | 33
August 2025 | 70 | Ministry of Coal | Coal | BLOCK E OCP | Ministry of Coal | 616253 | Jharkhand | 03/2024 | 03/2024 | 03/2029 | - | 5850.83 | 5850.83 | 20.32 | 3
August 2025 | 71 | Ministry of Coal | Coal | AMADAND OCP[4.0MTY] | South Eastern Coalfields Limited [SECL] | 400148 | Madhya Pradesh | 03/2016 | 03/2016 | 03/2021 | 03/2027 | 869.44 | 869.44 | 273.45 | 75
August 2025 | 72 | Ministry of Coal | Coal | RAMPUR BATURA OCP [4.0MTY] | South Eastern Coalfields Limited [SECL] | 400152 | Madhya Pradesh | 07/2019 | 07/2019 | 03/2026 | - | 1248.93 | 1248.93 | 495.4 | 44
August 2025 | 73 | Ministry of Coal | Coal | BLOCK B EXPANSION [3.5 TO 8.0 | Northern Coalfields Limited [NCL] | 400162 | Madhya Pradesh | 07/2019 | 07/2019 | 03/2023 | 03/2027 | 998.71 | 998.71 | 457.2 | 47
August 2025 | 74 | Ministry of Coal | Coal | NIGAHI EXPANSION [15 TO 25 MTP | Northern Coalfields Limited [NCL] | 400321 | Madhya Pradesh | 11/2020 | 11/2020 | 03/2025 | 03/2028 | 1729.68 | 1729.68 | 804.11 | 48
August 2025 | 75 | Ministry of Coal | Coal | KANCHAN OC EXP | South Eastern Coalfields Limited [SECL] | 613802 | Madhya Pradesh | 12/2014 | 12/2014 | 03/2026 | - | 371.04 | 371.04 | 144.61 | 47
August 2025 | 76 | Ministry of Coal | Coal | JHIRIA WEST OCP [1.5 MTY] | South Eastern Coalfields Limited [SECL] | 613803 | Madhya Pradesh | 01/2024 | 01/2024 | 03/2026 | - | 366.94 | 366.94 | 34.05 | 41
August 2025 | 77 | Ministry of Coal | Coal | RPR TAWA-III UG 0.84 MTY | Western Coalfields Limited [WCL] | 613804 | Madhya Pradesh | 12/2021 | 12/2021 | 03/2027 | - | 314.09 | 314.09 | 5.79 | 17
August 2025 | 78 | Ministry of Coal | Coal | AMALGAMATED DHANKASA & JAMUNIA | Western Coalfields Limited [WCL] | 615185 | Madhya Pradesh | 09/2022 | 09/2022 | 03/2027 | - | 399.2 | 399.2 | 91.67 | 66
August 2025 | 79 | Ministry of Coal | Coal | RPR OF VISHNUPURI UG TO OC | Western Coalfields Limited [WCL] | 615187 | Madhya Pradesh | 11/2022 | 11/2022 | 03/2029 | - | 220.62 | 220.62 | 0 | 11
August 2025 | 80 | Ministry of Coal | Coal | URDHAN EXPANSION OC COST PLUS | Western Coalfields Limited [WCL] | 615194 | Madhya Pradesh | 07/2022 | 01/2023 | 03/2031 | - | 206.88 | 206.88 | 27.19 | 1
August 2025 | 81 | Ministry of Coal | Coal | SHARDA UG MINE | Western Coalfields Limited [WCL] | 615195 | Madhya Pradesh | 07/2023 | 09/2023 | 03/2028 | - | 166.25 | 166.25 | 3.96 | 9
August 2025 | 82 | Ministry of Coal | Coal | GANDHIGRAM UG MINE | Western Coalfields Limited [WCL] | 615206 | Madhya Pradesh | 08/2019 | 08/2019 | 03/2026 | - | 414.15 | 414.15 | 13.38 | 57
August 2025 | 83 | Ministry of Coal | Coal | BHATADI EXPANSION OC | Western Coalfields Limited [WCL] | 400033 | Maharashtra | 02/2020 | 05/2022 | 03/2028 | - | 580.61 | 580.61 | 69.73 | 26
August 2025 | 84 | Ministry of Coal | Coal | AMALGAMATED YEKONA I & YEKONA | Western Coalfields Limited [WCL] | 400177 | Maharashtra | 08/2015 | 08/2015 | 03/2025 | 03/2026 | 727.28 | 727.28 | 535.96 | 80
August 2025 | 85 | Ministry of Coal | Coal | DINESH[MAKARDHOKRA-III] OC | Western Coalfields Limited [WCL] | 400178 | Maharashtra | 02/2020 | 02/2020 | 03/2027 | - | 822.88 | 822.88 | 621.73 | 35
August 2025 | 86 | Ministry of Coal | Coal | DHUPTALA OC [SASTI UG TO OC ] | Western Coalfields Limited [WCL] | 400353 | Maharashtra | 10/2021 | 10/2021 | 03/2028 | - | 711.01 | 711.01 | 80.61 | 17
August 2025 | 87 | Ministry of Coal | Coal | SAONER UG MINE -1 EXPANSION 1. | Western Coalfields Limited [WCL] | 615184 | Maharashtra | 01/2022 | 01/2022 | 03/2028 | - | 228.64 | 228.64 | 141.21 | 68
August 2025 | 88 | Ministry of Coal | Coal | SASTI EXPANSION OPENCAST | Western Coalfields Limited [WCL] | 615186 | Maharashtra | 08/2020 | 08/2020 | 03/2026 | - | 319.04 | 319.04 | 90.31 | 20
August 2025 | 89 | Ministry of Coal | Coal | NEW MAJRI UG TO OC 3 MTY COST | Western Coalfields Limited [WCL] | 615188 | Maharashtra | 05/2019 | 09/2022 | 03/2027 | - | 402.27 | 402.27 | 55.44 | 24
August 2025 | 90 | Ministry of Coal | Coal | MAKARDHOKRA EXPN OC 4.9 MTY | Western Coalfields Limited [WCL] | 615189 | Maharashtra | 06/2022 | 06/2022 | 03/2026 | - | 361.87 | 361.87 | 70.22 | 12
August 2025 | 91 | Ministry of Coal | Coal | SINGHORI DEEP OC MIN 2.0 MTY | Western Coalfields Limited [WCL] | 615190 | Maharashtra | 05/2022 | 05/2022 | 03/2029 | - | 335.75 | 335.75 | 26.79 | 6
August 2025 | 92 | Ministry of Coal | Coal | GOKUL EXTENSION OC MINE | Western Coalfields Limited [WCL] | 615192 | Maharashtra | 04/2021 | 04/2021 | 03/2026 | - | 309.58 | 309.58 | 40.06 | 8
August 2025 | 93 | Ministry of Coal | Coal | KOLGAON EXPANSION DEEP OC MINE 0.80 MTY | Western Coalfields Limited [WCL] | 615199 | Maharashtra | 09/2023 | 09/2023 | 03/2027 | - | 198.71 | 198.71 | 0.71 | 3
August 2025 | 94 | Ministry of Coal | Coal | BALLARPUR NORTH WEST OC MINE | Western Coalfields Limited [WCL] | 615330 | Maharashtra | 12/2022 | 12/2022 | 03/2029 | - | 360.81 | 360.81 | 0.02 | 4
August 2025 | 95 | Ministry of Coal | Coal | GADEGAON OC 3 MTY | Western Coalfields Limited [WCL] | 615331 | Maharashtra | 10/2023 | 10/2023 | 03/2030 | - | 497.41 | 497.41 | 0.08 | 0
August 2025 | 96 | Ministry of Coal | Coal | GHONSA EXPANSION DEEP OC MINE | Western Coalfields Limited [WCL] | 615914 | Maharashtra | 03/2021 | 03/2021 | 03/2029 | - | 184.71 | 184.71 | 11.48 | 6
August 2025 | 97 | Ministry of Coal | Coal | AMLG GAURI PAUNI EXPANSION OC | Western Coalfields Limited [WCL] | 615916 | Maharashtra | 04/2024 | 04/2024 | 03/2030 | - | 1225.21 | 1225.21 | 78.87 | 1
August 2025 | 98 | Ministry of Coal | Coal | GAURIDEEP/GAURI CENTRAL OCP 7. | Western Coalfields Limited [WCL] | 615917 | Maharashtra | 06/2024 | 06/2024 | 03/2030 | - | 973.07 | 973.07 | 0.24 | 0
August 2025 | 99 | Ministry of Coal | Coal | RPR OF BHANEGAON OC | Western Coalfields Limited [WCL] | 615918 | Maharashtra | 02/2017 | 09/2022 | 03/2028 | - | 405.2 | 405.2 | 12.36 | 8
August 2025 | 100 | Ministry of Coal | Coal | N. EXTN. MUNGOLI NIRGUDA D OCP | Western Coalfields Limited [WCL] | 615919 | Maharashtra | 06/2024 | 06/2024 | 03/2030 | - | 1024.91 | 1024.91 | 168.59 | 0
August 2025 | 101 | Ministry of Coal | Coal | NILJAI EXPANSION DEEP OCP | Western Coalfields Limited [WCL] | 615982 | Maharashtra | 08/2016 | 08/2016 | 03/2022 | 03/2026 | 319.75 | 319.75 | 367.6 | 79
August 2025 | 102 | Ministry of Coal | Coal | UKNI DEEP OC MINE -COST PLUS | Western Coalfields Limited [WCL] | 616044 | Maharashtra | 01/2019 | 01/2019 | 03/2021 | 03/2026 | 237.06 | 237.06 | 165.57 | 87
August 2025 | 103 | Ministry of Coal | Coal | AMALGAMATED INDER-KAMPTEE DEEP OC | Western Coalfields Limited [WCL] | 616050 | Maharashtra | 09/2018 | 09/2018 | 03/2024 | 03/2026 | 235.9 | 235.9 | 237.12 | 98
August 2025 | 104 | Ministry of Coal | Coal | ADASA UG TO OC MINE | Western Coalfields Limited [WCL] | 616223 | Maharashtra | 11/2018 | 11/2018 | 03/2024 | 03/2026 | 316 | 316 | 308.84 | 86
August 2025 | 105 | Ministry of Coal | Coal | AMAL GONDEGAON GHATROHANA EXPN | Western Coalfields Limited [WCL] | 616229 | Maharashtra | 09/2024 | 09/2024 | 03/2030 | - | 668.54 | 668.54 | 1.18 | 0
August 2025 | 106 | Ministry of Coal | Coal | WAGHODA UG MINE [1.02 MTY] | Western Coalfields Limited [WCL] | 617233 | Maharashtra | 01/2024 | 01/2025 | 03/2030 | - | 379.3 | 379.3 | 0 | 0
August 2025 | 107 | Ministry of Coal | Coal | KOLARPIMPRI EXPANSION OC [2.5 MTY] | Western Coalfields Limited [WCL] | 617278 | Maharashtra | 06/2024 | 02/2025 | 03/2030 | - | 630.37 | 630.37 | 0 | 0
August 2025 | 108 | Ministry of Coal | Coal | Master Plan for Jharia and Raniganj Coalfields | Bharat Coking Coal Limited [BCCL] | 400313 | Multi-States (Jharkhand, West Bengal) | 08/2009 | 08/2009 | 08/2019 | 12/2028 | 2661.73 | 2661.73 | 788.85 | 43
August 2025 | 109 | Ministry of Coal | Coal | BINA KAKRI AMALGAMATION EXPANS | Northern Coalfields Limited [NCL] | 400369 | Multi-States (Madhya Pradesh, Uttar Pradesh) | 08/2020 | 08/2020 | 03/2024 | 03/2027 | 836.42 | 836.42 | 786.99 | 89
August 2025 | 110 | Ministry of Coal | Coal | KHADIA EXPANSION [10 TO 16 MTP | Northern Coalfields Limited [NCL] | 615183 | Multi-States (Madhya Pradesh, Uttar Pradesh) | 06/2021 | 06/2021 | 03/2025 | 03/2027 | 491.67 | 491.67 | 230.32 | 45
August 2025 | 111 | Ministry of Coal | Coal | SUBHADRA OCP | Mahanadi Coalfields Limited [MCL] | 400165 | Odisha | 05/2021 | 05/2021 | 04/2032 | - | 1693.81 | 1693.81 | 1321.15 | 42
August 2025 | 112 | Ministry of Coal | Coal | SIARMAL OCP | Mahanadi Coalfields Limited [MCL] | 400166 | Odisha | 02/2021 | 02/2021 | 03/2029 | - | 5194.95 | 5194.95 | 3456.05 | 55
August 2025 | 113 | Ministry of Coal | Coal | BALARAM EXPANSION OCP | Mahanadi Coalfields Limited (MCL | 400183 | Odisha | 06/2020 | 08/2020 | 03/2029 | - | 3504.21 | 3504.21 | 1028.92 | 52
August 2025 | 114 | Ministry of Coal | Coal | GOPALJI KANIHA OCP [10 TO 30 M | MCL - CIL | 400185 | Odisha | 04/2022 | 04/2022 | 03/2030 | - | 8416.19 | 6107.87 | 1708.88 | 17
August 2025 | 115 | Ministry of Coal | Coal | INTEGRATED LAKHANPUR-BELPAHAR- | Mahanadi Coalfields Limited [MCL] | 400187 | Odisha | 05/2018 | 05/2018 | 03/2027 | - | 2434.75 | 2434.75 | 1813.26 | 69
August 2025 | 116 | Ministry of Coal | Coal | BHARATPUR RE-ORGANIZATION OCP | Mahanadi Coalfields Limited (MCL | 400392 | Odisha | 11/2018 | 11/2018 | 03/2029 | - | 2838.86 | 2838.86 | 1748.41 | 47
August 2025 | 117 | Ministry of Coal | Coal | BASUNDHARA WEST EXTENSION OPEN | MCL - CIL | 615193 | Odisha | 05/2014 | 05/2014 | 03/2019 | 03/2029 | 479.15 | 479.15 | 281.01 | 64
August 2025 | 118 | Ministry of Coal | Coal | Naini Coal Mine | Singareni Collieries Company Limited [SCCL] | 615857 | Odisha | 03/2020 | 03/2020 | 03/2026 | - | 494.3 | 494.3 | 491.33 | 80
August 2025 | 119 | Ministry of Coal | Coal | INTEGRATED KULDA GARJANBAHAL O | Mahanadi Coalfields Limited (MCL | 616226 | Odisha | 04/2023 | 04/2023 | 03/2033 | - | 3563.5 | 3563.5 | 540.62 | 4
August 2025 | 120 | Ministry of Coal | Coal | BHUBANESWARI EXPN OCP 50 MTY | MCL - CIL | 616231 | Odisha | 03/2024 | 03/2024 | 03/2033 | - | 5366.27 | 5366.27 | 465.31 | 14
August 2025 | 121 | Ministry of Coal | Coal | HINGULA II OC EXPN PH III 15 M | MCL - CIL | 616232 | Odisha | 11/2022 | 11/2022 | 03/2029 | - | 1561.85 | 1561.85 | 269.61 | 23
August 2025 | 122 | Ministry of Coal | Coal | BALABHADRA OCP | MCL - CIL | 616233 | Odisha | 04/2023 | 04/2023 | 03/2030 | - | 978.44 | 978.44 | 211.37 | 11
August 2025 | 123 | Ministry of Coal | Coal | Jawahar Khani Open Cast Mine | Singareni Collieries Company Limited [SCCL] | 615818 | Telangana | 12/2021 | 12/2021 | 03/2025 | 03/2027 | 297.88 | 297.88 | 46.39 | 20
August 2025 | 124 | Ministry of Coal | Coal | Kalyanikhani Opencast Project | Singareni Collieries Company Limited [SCCL] | 615858 | Telangana | 03/2016 | 05/2017 | 03/2026 | - | 384.32 | 384.32 | 281.83 | 75
August 2025 | 125 | Ministry of Coal | Coal | Kakathiya Khani Opencast - III Project Phase - I | Singareni Collieries Company Limited [SCCL] | 615859 | Telangana | 03/2017 | 05/2017 | 03/2026 | - | 413.84 | 413.84 | 397.55 | 79
August 2025 | 126 | Ministry of Coal | Coal | Godavarikhani Coal Mine - 5 | Singareni Collieries Company Limited [SCCL] | 615860 | Telangana | 07/2019 | 05/2019 | 03/2025 | 03/2026 | 607.04 | 607.04 | 188.15 | 71
August 2025 | 127 | Ministry of Coal | Coal | Indaram Opencast Project | Singareni Collieries Company Limited [SCCL] | 615861 | Telangana | 08/2017 | 12/2022 | 03/2025 | 03/2026 | 424.81 | 424.81 | 402.64 | 80
August 2025 | 128 | Ministry of Coal | Coal | Goleti Opencast Mine | Singareni Collieries Company Limited [SCCL] | 615862 | Telangana | 07/2021 | 08/2021 | 03/2026 | - | 345.6 | 345.6 | 74.59 | 20
August 2025 | 129 | Ministry of Coal | Coal | Venkatesh Khani Coal Mine | Singareni Collieries Company Limited [SCCL] | 615863 | Telangana | 10/2020 | 06/2020 | 03/2026 | - | 484.5 | 484.5 | 460.67 | 95
August 2025 | 130 | Ministry of Coal | Coal | Ramagundam OC-II Extension Project | Singareni Collieries Company Limited [SCCL] | 615864 | Telangana | 11/2015 | 06/2015 | 03/2026 | - | 489.62 | 489.62 | 405.54 | 77
August 2025 | 131 | Ministry of Coal | Coal | Kakatiyakhani OC - 2 Project | Singareni Collieries Company Limited [SCCL] | 615865 | Telangana | 08/2017 | 09/2017 | 03/2025 | 03/2026 | 442.42 | 442.42 | 205 | 63
August 2025 | 132 | Ministry of Coal | Coal | MOHANPUR EXPANSION OC -PHASE II | Eastern Coal Fields Limited [ECL] | 400173 | West Bengal | 11/2020 | 11/2020 | 03/2026 | - | 888.99 | 888.99 | 93 | 30
August 2025 | 133 | Ministry of Coal | Coal | BONJEMEHARI EXPANSION OCP | Eastern Coal Fields Limited [ECL] | 400180 | West Bengal | 08/2021 | 08/2021 | 03/2026 | 03/2026 | 570.11 | 570.11 | 81.95 | 16
August 2025 | 134 | Ministry of Coal | Coal | NAKRAKONDA KUMARDIH- B OCP | Eastern Coal Fields Limited [ECL] | 400181 | West Bengal | 08/2018 | 08/2018 | 03/2029 | - | 502.68 | 502.67 | 67.61 | 26
August 2025 | 135 | Ministry of Coal | Coal | SIDULI [OC & UG] | ECL - CIL | 400182 | West Bengal | 05/2018 | 05/2018 | 03/2027 | - | 535.18 | 535.17 | 5.05 | 14
August 2025 | 136 | Ministry of Coal | Coal | TILABONI UG | Eastern Coal Fields Limited [ECL] | 400186 | West Bengal | 01/2023 | 03/2023 | 03/2029 | 03/2029 | 749.08 | 749.08 | 52.18 | 10
August 2025 | 137 | Ministry of Coal | Coal | JHANJRA EXPANSION UG | Eastern Coal Fields Limited [ECL] | 400312 | West Bengal | 04/2020 | 04/2020 | 03/2029 | - | 1210.12 | 1210.12 | 527.67 | 41
August 2025 | 138 | Ministry of Coal | Coal | SONEPUR BAZARI EXPANSION OCP [12 MTY] | Eastern Coal Fields Limited [ECL] | 400315 | West Bengal | 07/2021 | 07/2021 | 03/2029 | - | 5365.88 | 5365.88 | 565.26 | 17
August 2025 | 139 | Ministry of Coal | Coal | 2.0 MTPA BHOJUDIH NLW WASHERY | Ministry of Coal | 611016 | West Bengal | 12/2015 | 03/2019 | 09/2020 | 10/2025 | 384.57 | 384.57 | 353.21 | 97
August 2025 | 140 | Ministry of Coal | Coal | ITAPARA OCP | Eastern Coal Fields Limited [ECL] | 612816 | West Bengal | 12/2023 | 12/2023 | 03/2030 | - | 929.1 | 929.1 | 67.6 | 7
August 2025 | 141 | Ministry of Coal | Coal | SHYAMSUNDARPUR UG INCLUDING SA | Eastern Coal Fields Limited [ECL] | 613793 | West Bengal | 04/2020 | 04/2020 | 03/2026 | - | 483.65 | 483.65 | 59.04 | 12
August 2025 | 142 | Ministry of Coal | Coal | PARASEA-BELBAID UG PROJECT | Eastern Coal Fields Limited [ECL] | 613794 | West Bengal | 01/2023 | 01/2023 | 03/2028 | - | 389.1 | 389.1 | 131.42 | 17
August 2025 | 143 | Ministry of Coal | Coal | PARASCOLE JAMBAD OCP | Eastern Coal Fields Limited [ECL] | 616230 | West Bengal | 11/2024 | 11/2024 | 03/2037 | - | 1193.55 | 1193.55 | 9.46 | 0
August 2025 | 144 | Ministry of Coal | Electricity Generation | 50 MW Wind Power Project | NLC India Limited [NLCIL] | 617299 | Gujarat | 07/2022 | 02/2024 | 06/2025 | 01/2026 | 383.84 | 383.84 | 303.5 | 41
August 2025 | 145 | Ministry of Coal | Electricity Generation | NLC Talabira Thermal Power Project | NLC India Limited [NLCIL] | 400231 | Odisha | NA | 01/2024 | 03/2030 | - | 27212.96 | 27213 | 1953.52 | 1
August 2025 | 146 | Ministry of Coal | Electricity Generation | 300 MW SPP part of 510 MW CPSU scheme | NLC India Limited [NLCIL] | 612819 | Rajasthan | NA | 03/2023 | 09/2024 | 09/2025 | 1813 | 1813 | 874.14 | 70
August 2025 | 147 | Ministry of Coal | Electricity Generation | 50 MW Solar PP Minedout Area | NLC India Limited [NLCIL] | 615327 | Tamil Nadu | NA | 02/2024 | 03/2025 | 09/2025 | 218.03 | 218.03 | 161.73 | 50
August 2025 | 148 | Ministry of Coal | Electricity Generation | Ghatampur Thermal Power Plant 3 X 660 MW | NLC India Limited [NLCIL] | 400259 | Uttar Pradesh | NA | 08/2016 | 11/2020 | 10/2025 | 17237.8 | 21780.9 | 20269.54 | 92
August 2025 | 149 | Ministry of Coal | Railways | Dharamjaigarh-Korba | Railway | 400203 | Chhattisgarh | 05/2018 | 03/2017 | 12/2026 | 08/2026 | 1686.22 | 1686.22 | 347.96 | 41
August 2025 | 150 | Ministry of Coal | Railways | Shivpur-Kathautia New Rail [BG] Line [49 km] [Package II of Tori-Shivpur-Kathautia line] | Ministry of Coal | 400416 | Jharkhand | 02/2018 | 05/2022 | 06/2025 | - | 1799.64 | 1799.64 | 1293.71 | 60
August 2025 | 151 | Ministry of Power | Coal | Tubed Coal Mine | Damodar Valley Corporation | 400192 | Jharkhand | NA | 10/2016 | 05/2026 | 05/2026 | 1581 | 1581 | 596.94 | 34
August 2025 | 152 | Ministry of Power | Coal | Badam Coal Mining project of NTPC | National Thermal Power Corporation [NTPC] | 603293 | Jharkhand | 02/2019 | 09/2019 | 12/2056 | 04/2027 | 502 | 784 | 313.88 | 59
August 2025 | 153 | Ministry of Power | Electricity Generation | Dibang Multipurpose Project | National Highways & Infrastructure Development Corporation Ltd. [NHIDCL] | 602182 | Arunachal Pradesh | 02/2023 | 02/2023 | 02/2032 | 02/2032 | 31876.39 | 31876.4 | 3553.9 | 16
August 2025 | 154 | Ministry of Power | Electricity Generation | 240MW Heo HE Project | North Eastern Electric Power Corporation Limited | 611698 | Arunachal Pradesh | 12/2024 | 05/2025 | 07/2029 | - | 1938.85 | 1938.85 | 49.31 | 3
August 2025 | 155 | Ministry of Power | Electricity Generation | 186 MW Tato-I H E Project | North Eastern Electric Power Corporation Limited | 611699 | Arunachal Pradesh | 12/2024 | 05/2025 | 07/2029 | - | 1750.07 | 1750.07 | 102.79 | 2
August 2025 | 156 | Ministry of Power | Electricity Generation | Buxar Thermal Power Project [1320 MW] | Satluj Jal Vidyut Nigam [SJVN] Thermal Limited | 602579 | Bihar | 03/2019 | 06/2019 | 01/2024 | 12/2025 | 10439.09 | 13756.6 | 12148.46 | 92
August 2025 | 157 | Ministry of Power | Electricity Generation | Lara Super Thermal Power Project Stage-II [2 x 800 MW] | National Thermal Power Corporation [NTPC] | 611930 | Chhattisgarh | 08/2023 | 08/2023 | 06/2028 | - | 15530 | 15530 | 2480 | 16
August 2025 | 158 | Ministry of Power | Electricity Generation | Sipat Super Thermal Power Project, Stage-III [1x800 MW] | National Thermal Power Corporation [NTPC] | 617188 | Chhattisgarh | 09/2024 | 09/2024 | 09/2029 | - | 9791 | 9791 | 0 | 0
August 2025 | 159 | Ministry of Power | Electricity Generation | Bagodara Solar Power Project | Satluj Jal Vidyut Nigam [SJVN] Thermal Limited | 709747 | Gujarat | 03/2021 | 05/2021 | 12/2025 | 12/2025 | 339.35 | 339.35 | 317.59 | 51
August 2025 | 160 | Ministry of Power | Electricity Generation | Dhaulasidh Hydro Electric Project [66 MW] | Satluj Jal Vidyut Nigam [SJVN] Thermal Limited | 602582 | Himachal Pradesh | 10/2020 | 05/2021 | 11/2025 | 03/2027 | 687.97 | 1511.87 | 927.3 | 68
August 2025 | 161 | Ministry of Power | Electricity Generation | Luhri Stage-I Hydro Electric Project [210 MW] | Satluj Jal Vidyut Nigam [SJVN] Thermal Limited | 602593 | Himachal Pradesh | 11/2020 | 11/2020 | 01/2026 | 10/2029 | 1810.56 | 3584.53 | 1751.6 | 51
August 2025 | 162 | Ministry of Power | Electricity Generation | 382 MW Sunni Dam HEP | Satluj Jal Vidyut Nigam [SJVN] Thermal Limited | 602633 | Himachal Pradesh | NA | 04/2018 | 03/2027 | - | 2615 | 2615 | 495.57 | 0.5
August 2025 | 163 | Ministry of Power | Electricity Generation | Sunni Dam Hydro Electric Project [382 MW] | Satluj Jal Vidyut Nigam [SJVN] Thermal Limited | 611586 | Himachal Pradesh | 01/2023 | 01/2023 | 04/2028 | 12/2029 | 2614.51 | 4540.71 | 962.66 | 29
August 2025 | 164 | Ministry of Power | Electricity Generation | Pakal Dul [Drangdhuran] Hydroelectric Project, 1000 MW | National Highways & Infrastructure Development Corporation Ltd. [NHIDCL] | 602525 | Jammu and Kashmir | 10/2014 | 02/2018 | 04/2020 | 12/2026 | 8112.12 | 12728 | 7238.73 | 72
August 2025 | 165 | Ministry of Power | Electricity Generation | Kiru HE Project | National Highways & Infrastructure Development Corporation Ltd. [NHIDCL] | 602532 | Jammu and Kashmir | 03/2019 | 03/2019 | 09/2023 | 12/2026 | 4287.59 | 5409 | 3157.49 | 68
August 2025 | 166 | Ministry of Power | Electricity Generation | Ratle HE Project - 850 MW, Ratle Hydroelectric Power Corporation Limited. | National Highways & Infrastructure Development Corporation Ltd. [NHIDCL] | 602535 | Jammu and Kashmir | 02/2021 | 02/2021 | 02/2026 | 08/2029 | 5281.94 | 5281.94 | 1009.79 | 24
August 2025 | 167 | Ministry of Power | Electricity Generation | Kwar HE Project | National Highways & Infrastructure Development Corporation Ltd. [NHIDCL] | 605155 | Jammu and Kashmir | 05/2022 | 05/2022 | 11/2026 | 03/2028 | 4526.12 | 4526.12 | 1119.59 | 23
August 2025 | 168 | Ministry of Power | Electricity Generation | Patratu Thermal Power Station Expansion Project Phase-I [3x800 MW] | National Thermal Power Corporation [NTPC] | 400261 | Jharkhand | 11/2017 | 11/2017 | 03/2023 | 11/2026 | 17112 | 20302 | 17475 | 85
August 2025 | 169 | Ministry of Power | Electricity Generation | Koderma Thermal Power Station Phase II [2X800 MW] At Koderma, Jharkhand | Damodar Valley Corporation | 611509 | Jharkhand | NA | 11/2024 | 03/2029 | - | 14358 | 14358 | 1131.57 | 3
August 2025 | 170 | Ministry of Power | Electricity Generation | Subansiri Lower HE Project [2000 MW] | National Highways & Infrastructure Development Corporation Ltd. [NHIDCL] | 602096 | Multi-States (Arunachal Pradesh, Assam) | 09/2003 | 09/2003 | 09/2010 | 05/2026 | 6285.33 | 26075.5 | 24880.95 | 96
August 2025 | 171 | Ministry of Power | Electricity Generation | Talcher Thermal Power Station Stage III [2 x 660 MW] Expansion | National Thermal Power Corporation [NTPC] | 602961 | Odisha | 08/2022 | 09/2022 | 05/2027 | 03/2028 | 11843.75 | 12543 | 4161.68 | 32
August 2025 | 172 | Ministry of Power | Electricity Generation | BIKANER SOLAR POWER PROJECT | Satluj Jal Vidyut Nigam [SJVN] Thermal Limited | 709748 | Rajasthan | 10/2021 | 05/2022 | 04/2024 | 12/2025 | 5491.89 | 5491.89 | 4805.16 | 84
August 2025 | 173 | Ministry of Power | Electricity Generation | TEESTA-VI HE PROJECT, SIKKIM [500 MW], executed by LANCO TEESTA HYDRO POWER LIMITED [A wholly owned Subsidiary of NHPC LTD. acquired through NCLT] | National Highways & Infrastructure Development Corporation Ltd. [NHIDCL] | 602181 | Sikkim | 03/2019 | 03/2019 | 03/2024 | 12/2027 | 5748.04 | 5748.04 | 4576.93 | 69
August 2025 | 174 | Ministry of Power | Electricity Generation | Rangit-IV HE Project [120 MW] executed by Jal Power Corporation Ltd. [JPCL] -A wholly owned subsidiary of NHPC Ltd. acquired through NCLT | National Highways & Infrastructure Development Corporation Ltd. [NHIDCL] | 605156 | Sikkim | 03/2021 | 03/2021 | 05/2024 | 12/2025 | 938.29 | 1828.11 | 1584.13 | 91
August 2025 | 175 | Ministry of Power | Electricity Generation | Khurja super Thermal Power Plant [2X660 MW] | THDC India Limited | 602194 | Uttar Pradesh | 03/2019 | 08/2019 | 02/2024 | 09/2025 | 11089.42 | 13276.2 | 12772.21 | 97
August 2025 | 176 | Ministry of Power | Electricity Generation | Singrauli Super Thermal Power Project, Stage-III [2x800 MW] | National Thermal Power Corporation [NTPC] | 612142 | Uttar Pradesh | 03/2024 | 03/2024 | 02/2030 | - | 17195 | 17195 | 1739 | 9
August 2025 | 177 | Ministry of Power | Electricity Generation | Tapovan-Vishnugad HEP [4x130 MW] | National Thermal Power Corporation [NTPC] | 602185 | Uttarakhand | NA | 11/2006 | 03/2013 | 04/2029 | 2978 | 10907.3 | 7195.58 | 77
August 2025 | 178 | Ministry of Power | Electricity Generation | Tehri Pumped Storage Plant Project [4x250 MW] | THDC India Limited | 602193 | Uttarakhand | 07/2006 | 06/2011 | 06/2022 | 11/2025 | 4825.6 | 8339 | 8064.9 | 98
August 2025 | 179 | Ministry of Power | Electricity Generation | Vishnugad Pipalkoti Hydro Electric Project [444 MW] | THDC India Limited | 602195 | Uttarakhand | 08/2008 | 01/2014 | 12/2022 | 03/2027 | 3860.35 | 6823.72 | 5101.06 | 72
August 2025 | 180 | Ministry of Power | Electricity Generation | Raghunathpur Thermal Power Station Phase II [2X660 MW] at Raghunathpur, Purulia, West Bengal | Damodar Valley Corporation | 400062 | West Bengal | NA | 02/2025 | 06/2029 | - | 17673 | 17673 | 1192.71 | 1
August 2025 | 181 | Ministry of Power | Electricity Generation | Rammam-III HEPP [3x40 MW] | National Thermal Power Corporation [NTPC] | 602184 | West Bengal | 09/2024 | 09/2014 | 09/2019 | 03/2029 | 1381.84 | 1381.84 | 1281.85 | 47
August 2025 | 182 | Ministry of Power | Electricity Generation | Installation of FGD for 4x210 & 2x250 MW MTPS U 1-6 | Damodar Valley Corporation | 602538 | West Bengal | NA | 02/2021 | 01/2024 | 12/2025 | 1037 | 1106 | 1092.27 | 92
August 2025 | 183 | Ministry of Power | Transmission & Distribution | Transmission Scheme for Solar Energy Zone in Ananthpuram 2500MW and Kurnool 1000MW | Power Grid Corporation of India Limited [POWERGRID] | 611967 | Andhra Pradesh | 09/2023 | 09/2023 | 09/2025 | 04/2026 | 1248.69 | 1248.69 | 860.97 | 82
August 2025 | 184 | Ministry of Power | Transmission & Distribution | Augmentation of 1x1500 MVA 3rd 765/400 kV transformation capacity at Kurnool New Substation | Power Grid Corporation of India Limited [POWERGRID] | 612856 | Andhra Pradesh | 05/2023 | 12/2023 | 09/2025 | 11/2025 | 163.61 | 163.61 | 60.53 | 42
August 2025 | 185 | Ministry of Power | Transmission & Distribution | Transmission system strengthening at Kurnool- III PS for integration of additional RE generation projects [POWERGRID Kurnool III PS RE Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 617183 | Andhra Pradesh | 03/2025 | 03/2025 | 12/2027 | - | 2886 | 2886 | 117.86 | 0
August 2025 | 186 | Ministry of Power | Transmission & Distribution | Western Region Expansion Scheme-XXV | Power Grid Corporation of India Limited [POWERGRID] | 611737 | Chhattisgarh | 02/2023 | 02/2023 | 11/2023 | 12/2025 | 385.84 | 385.84 | 378.17 | 97
August 2025 | 187 | Ministry of Power | Transmission & Distribution | Transmission system strengthening scheme for evacuation of power from solar energy zones in Rajasthan 8.1 GW under Phase II- Part- G1 | Power Grid Corporation of India Limited [POWERGRID] | 608301 | Delhi | 02/2022 | 02/2022 | 09/2023 | 11/2025 | 359.47 | 359.47 | 330.91 | 93
August 2025 | 188 | Ministry of Power | Transmission & Distribution | Transmission scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase II- Part B | Power Grid Corporation of India Limited [POWERGRID] | 611656 | Gujarat | 03/2023 | 03/2023 | 03/2025 | 10/2025 | 1167.55 | 1167 | 1050.41 | 93
August 2025 | 189 | Ministry of Power | Transmission & Distribution | Transmission scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase II- Part C | Power Grid Corporation of India Limited [POWERGRID] | 611657 | Gujarat | 03/2023 | 03/2023 | 03/2025 | 11/2025 | 2820.99 | 2820.99 | 2570.25 | 84
August 2025 | 190 | Ministry of Power | Transmission & Distribution | Establishment of Khavda Pooling Station-2 KPS2 in Khavda RE Park KPS2 TRANSMISSION SYSTEM LIMITED | Power Grid Corporation of India Limited [POWERGRID] | 611660 | Gujarat | 03/2023 | 03/2023 | 12/2024 | 10/2025 | 966.79 | 966.79 | 904.52 | 95
August 2025 | 191 | Ministry of Power | Transmission & Distribution | Transmission system for Evacuation of Additional 7 GW RE power from Khavda RE park under Phase-III Part B [Vataman Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 612139 | Gujarat | 12/2023 | 12/2023 | 12/2025 | 06/2026 | 3751.82 | 3751.82 | 1575.72 | 22
August 2025 | 192 | Ministry of Power | Transmission & Distribution | Transmission System for Evacuation of Power from potential Renewable Energy zone in Khavda Area of Gujarat under Phase IV [7 GW] Part E3 | Power Grid Corporation of India Limited [POWERGRID] | 612151 | Gujarat | 07/2023 | 07/2023 | 07/2025 | 12/2025 | 334 | 334 | 73.48 | 30
August 2025 | 193 | Ministry of Power | Transmission & Distribution | Transmission System for Evacuation of Power from Potential Energy Renewable Zone in Khavda Area of Gujarat under Ph-IV [7GW] Part E2 | Power Grid Corporation of India Limited [POWERGRID] | 612855 | Gujarat | 05/2024 | 05/2024 | 05/2026 | 02/2026 | 679 | 679 | 97.23 | 19
August 2025 | 194 | Ministry of Power | Transmission & Distribution | Augmentation of Transformation Capacity at jam Khambhaliya PS [GIS] [SPV Name POWERGRID Jam Khambhaliya Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 615342 | Gujarat | 10/2024 | 10/2024 | 07/2026 | - | 329 | 329 | 10.07 | 1
August 2025 | 195 | Ministry of Power | Transmission & Distribution | Provision of Dynamic Reactive Compensation at Khavda pooling Station 1 [KPS1] and Khavda Pooling station 3 [KPS3] | Power Grid Corporation of India Limited [POWERGRID] | 615343 | Gujarat | 11/2024 | 11/2024 | 11/2026 | - | 501 | 501 | 6.01 | 1
August 2025 | 196 | Ministry of Power | Transmission & Distribution | Transmission System for Evacuation of Power from Potential Renewable Energy Zone in Khavda area of Gujarat under Phase-IV [7GW] Part B [SPV Name POWERGRID South Olpad Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 615345 | Gujarat | 10/2024 | 10/2024 | 10/2026 | - | 4766 | 4766 | 564.77 | 7
August 2025 | 197 | Ministry of Power | Transmission & Distribution | Augmentation of Transformation Capacity at KPS1 [GIS] and KPS2 [GIS] [Phase-V Part B1 and Part B2 Scheme] [SPV Name- POWERGRID KPS1 and 2 Augmentation Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 617069 | Gujarat | 02/2025 | 02/2025 | 02/2027 | - | 466 | 466 | 13.99 | 1
August 2025 | 198 | Ministry of Power | Transmission & Distribution | Augmentation of Banaskantha [Raghanesda] PS [GIS] [POWERGRID Banaskantha Transco Limited] | Power Grid Corporation of India Limited [POWERGRID] | 617182 | Gujarat | 03/2025 | 03/2025 | 03/2027 | - | 172 | 172 | 7.27 | 3
August 2025 | 199 | Ministry of Power | Transmission & Distribution | Implementation of LILO of both circuits of 400KV vindhyachal PS-Sasan D/C Line at Hindalco Switchyard | Power Grid Corporation of India Limited [POWERGRID] | 617272 | Haryana | 06/2024 | 06/2024 | 12/2026 | - | 370 | 370 | 3.7 | 1
August 2025 | 200 | Ministry of Power | Transmission & Distribution | Transmission system for evacuation of Power from Pakaldul HEP in Chenab Valley HEPs - LTA System | Power Grid Corporation of India Limited [POWERGRID] | 608302 | Jammu and Kashmir | 02/2022 | 02/2022 | 04/2025 | 09/2025 | 318.12 | 318.12 | 287.31 | 99
August 2025 | 201 | Ministry of Power | Transmission & Distribution | Transmission Scheme for evacuation of Power from Ratle HEP [850 MW] & kiru [624 MW] Part B | Power Grid Corporation of India Limited [POWERGRID] | 617179 | Jammu and Kashmir | 07/2024 | 07/2024 | 07/2026 | - | 218.6 | 218.6 | 1.01 | 0
August 2025 | 202 | Ministry of Power | Transmission & Distribution | Transmission Scheme for Integration of Renewable Energy Zone [Phase II] in Koppal II [Phase A&B] and gadag II[Phase A] in Karnataka [POWERGRID KOPPAL GADAG TRANSMISSION LIMITED] | Power Grid Corporation of India Limited [POWERGRID] | 612140 | Karnataka | 12/2023 | 12/2023 | 12/2025 | 03/2026 | 2889.39 | 2889.39 | 1332.21 | 46
August 2025 | 203 | Ministry of Power | Transmission & Distribution | System Strengthening at Koppal-II and GadagII for integration of RE generation projects [SPV Name POWERGRID Koppal Gadag Augmentation Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 616672 | Karnataka | 01/2025 | 01/2025 | 06/2027 | - | 1354 | 1354 | 17.73 | 0
August 2025 | 204 | Ministry of Power | Transmission & Distribution | Augmentation of Transformation Capacity by 3x500 MVA, 400/220 KV ICTS [6th-8th] and 1x1500 MVA, 765/400 KV ICT [4th] at Bidar PS [SPV Name- POWERGRID Bidar Augmentation Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 617068 | Karnataka | 02/2025 | 02/2025 | 06/2027 | - | 288 | 288 | 6.79 | 0
August 2025 | 205 | Ministry of Power | Transmission & Distribution | Transmission Scheme for integration of Davanagere/ Chitradurga and Bellary REZ in Karnataka [POWERGRID Chitradurga Bellary REZ Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 617184 | Karnataka | 03/2025 | 03/2025 | 09/2027 | - | 3453 | 3453 | 33.14 | 0
August 2025 | 206 | Ministry of Power | Transmission & Distribution | Transmission System for Evacuation of Power from Rajasthan REZ Ph-IV [Part-2 5.5GW] [Jaisalmer/Barmer Complex] Part H1 [POWERGRID KURAWAR TRANSMISSION LIMITED] | Power Grid Corporation of India Limited [POWERGRID] | 615344 | Madhya Pradesh | 10/2024 | 10/2024 | 10/2026 | - | 3674 | 3674 | 495.18 | 14
August 2025 | 207 | Ministry of Power | Transmission & Distribution | Transmission System for Evacuation of Power from Rajasthan REZ Ph-IV [Part-2 5.5 GW] [Jaisalmer/Barmer Complex] Part C [SPV Name POWERGRID Mandsaur Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 615346 | Madhya Pradesh | 08/2024 | 08/2024 | 08/2026 | - | 2708 | 2708 | 812.4 | 35
August 2025 | 208 | Ministry of Power | Transmission & Distribution | Transmission System for evacuation of power from Mahan Energen Limited Generating Station in Madhya Pradesh [SPV Name - POWERGRID MEL Power Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 617279 | Madhya Pradesh | 06/2025 | 06/2025 | 12/2027 | - | 558 | 558 | 16.74 | 0
August 2025 | 209 | Ministry of Power | Transmission & Distribution | Transmission System for Evacuation of power from Potential RE Zone in Khavda Area of Gujarat under phase IV 7GW-Part E4 | Power Grid Corporation of India Limited [POWERGRID] | 611966 | Maharashtra | 11/2023 | 11/2023 | 07/2025 | 12/2025 | 224.41 | 224.41 | 24.64 | 10
August 2025 | 210 | Ministry of Power | Transmission & Distribution | Transmission System for Integration of Kurnool-IV REZ Phase-I [for 4.5 GW] [POWERGRID Kurnool-IV Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 617185 | Multi-States (Andhra Pradesh, Karnataka) | 03/2025 | 03/2025 | 03/2027 | - | 5550 | 5550 | 281 | 0
August 2025 | 211 | Ministry of Power | Transmission & Distribution | Transmission System for Kurnool Wind Energy Zone/ Solar Energy Zone Part-A and Part-B | Power Grid Corporation of India Limited [POWERGRID] | 900808 | Multi-States (Andhra Pradesh, Telangana) | 11/2022 | 03/2023 | 11/2024 | 12/2025 | 3546.94 | 3546.94 | 3192.25 | 95
August 2025 | 212 | Ministry of Power | Transmission & Distribution | Comprehensive Scheme for Strengthening of Transmission and Distribution [T&D] Systems [CSST&DS] in Arunachal Pradesh and Sikkim | Power Grid Corporation of India Limited [POWERGRID] | 602223 | Multi-States (Arunachal Pradesh, Sikkim) | 03/2021 | 01/2016 | 12/2018 | 03/2027 | 4754.42 | 9129.32 | 7462.2 | 81
August 2025 | 213 | Ministry of Power | Transmission & Distribution | NORTH EASTERN REGION POWER SYSTEM IMPROVEMENT PROJECT [NERPSIP] | Power Grid Corporation of India Limited [POWERGRID] | 607709 | Multi-States (Assam, Manipur, Meghalaya, Mizoram, Nagaland, Tripura) | 12/2014 | 03/2016 | 12/2018 | 12/2025 | 5111.33 | 6700 | 5277.24 | 96
August 2025 | 214 | Ministry of Power | Transmission & Distribution | Eastern Region Expansion Scheme-43 [ERES-43] | Power Grid Corporation of India Limited [POWERGRID] | 617271 | Multi-States (Bihar, Odisha, West Bengal) | 09/2024 | 09/2024 | 03/2026 | - | 342.69 | 342.69 | 0.6 | 0
August 2025 | 215 | Ministry of Power | Transmission & Distribution | Eastern Region Expansion Scheme-44 [ERES-44] | Power Grid Corporation of India Limited [POWERGRID] | 617270 | Multi-States (Bihar, West Bengal) | 11/2024 | 11/2024 | 05/2026 | - | 408.94 | 408.94 | 0.3 | 0
August 2025 | 216 | Ministry of Power | Transmission & Distribution | Transmission Network Expansion in Gujarat to increase its ATC from ISTS Part B | Power Grid Corporation of India Limited [POWERGRID] | 400005 | Multi-States (Dadra & Nagar Haveli and Daman & Diu, Gujarat, Maharashtra) | 01/2022 | 07/2022 | 06/2023 | 12/2025 | 4546.26 | 4546.26 | 4172.96 | 93
August 2025 | 217 | Ministry of Power | Transmission & Distribution | Transmission System Strengthening Scheme for evacuation of power from SEZ in Rajasthan 8.1 GW under Phase II Part G | Power Grid Corporation of India Limited [POWERGRID] | 608922 | Multi-States (Delhi, Haryana, Rajasthan) | 05/2022 | 05/2022 | 11/2023 | 11/2025 | 1666 | 2218 | 2129.28 | 95
August 2025 | 218 | Ministry of Power | Transmission & Distribution | Transmission system for evacuation of power from REZ in Rajasthan 20GW under Phase-III Part J | Power Grid Corporation of India Limited [POWERGRID] | 611735 | Multi-States (Delhi, Rajasthan) | 12/2022 | 12/2022 | 03/2025 | 04/2026 | 331 | 331 | 82.72 | 29
August 2025 | 219 | Ministry of Power | Transmission & Distribution | Transmission Scheme for Evacuation of power from REZ in Rajasthan [20 GW] under Phase-III Part D [Sikar Khetri Transmission Ltd] | Power Grid Corporation of India Limited [POWERGRID] | 612132 | Multi-States (Delhi, Rajasthan) | 02/2024 | 02/2024 | 08/2025 | 05/2026 | 2000 | 2000 | 1380.2 | 62
August 2025 | 220 | Ministry of Power | Transmission & Distribution | TRANSMISSION SYSTEM FOR EVACUATION OF POWER FROM POTENTIAL RENEWABLE ENERGY ZONE IN KHAVDA AREA OF GUJARAT UNDER PHASE-V [8 GW] PART A [SPV Name POWERGRID West Central Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 615347 | Multi-States (Gujarat, Maharashtra) | 11/2024 | 11/2024 | 05/2029 | - | 24819 | 24819 | 1796.14 | 1
August 2025 | 221 | Ministry of Power | Transmission & Distribution | Transmission system for evacuation of power from Rajasthan REZ Ph-IV [Part- 3/6GW] [Bikaner complex] Part A [SPV Name POWERGRID Bikaner IV Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 615339 | Multi-States (Haryana, Punjab, Rajasthan) | 11/2024 | 11/2024 | 11/2026 | - | 5969 | 5969 | 218.47 | 5
August 2025 | 222 | Ministry of Power | Transmission & Distribution | TRANSMISSION SYSTEM FOR EVACUATION OF POWER FROM RAJASTHAN REZ PH-IV [PART-3/ 6 GW] [BIKANER COMPLEX] PART B [SPV Name POWERGRID Siwani Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 615340 | Multi-States (Haryana, Rajasthan) | 11/2024 | 11/2024 | 11/2026 | - | 5357 | 5357 | 267.85 | 9
August 2025 | 223 | Ministry of Power | Transmission & Distribution | Transmission System for Strengthening of Srinagar-Leh Tr. System | Power Grid Corporation of India Limited [POWERGRID] | 606781 | Multi-States (Jammu and Kashmir, Ladakh) | 03/2022 | 03/2022 | 12/2024 | 10/2025 | 288.71 | 288.71 | 207.8 | 75
August 2025 | 224 | Ministry of Power | Transmission & Distribution | Transmission Scheme for Solar Energy Zone in Bidar [2500 MW], Karnataka [Bidar Transmission Ltd] | Power Grid Corporation of India Limited [POWERGRID] | 612138 | Multi-States (Karnataka, Telangana) | 02/2024 | 02/2024 | 02/2026 | - | 2147.62 | 2147.62 | 1144.89 | 61
August 2025 | 225 | Ministry of Power | Transmission & Distribution | Transmission System for Evacuation of Power from Rajasthan REZ Ph-IV [Part-2 5.5 GW] [Jaisalmer/Barmer Complex] Part D [SPV Name POWERGRID Beawar Mandsaur Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 615333 | Multi-States (Madhya Pradesh, Rajasthan) | 08/2024 | 08/2024 | 08/2026 | - | 2227 | 2227 | 622.89 | 20
August 2025 | 226 | Ministry of Power | Transmission & Distribution | Transmission System for Evacuation of Power from Rajasthan REZ Ph-IV [Part-2 5.5 GW] [Jaisalmer/Barmer Complex] Part E [SPV Name POWERGRID Mewar Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 615334 | Multi-States (Madhya Pradesh, Rajasthan) | 08/2024 | 08/2024 | 08/2026 | - | 3251 | 3251 | 780.24 | 18
August 2025 | 227 | Ministry of Power | Transmission & Distribution | Rajasthan REZ Ph-V [Part-1- 4 GW] [Sirohi/Nagaur] Complex [Rajasthan V Power Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 617186 | Multi-States (Madhya Pradesh, Rajasthan) | 03/2025 | 03/2025 | 03/2027 | - | 5028 | 5028 | 203.2 | 1
August 2025 | 228 | Ministry of Power | Transmission & Distribution | Transmission System for Evacuation of power from Rajasthan REZ Ph-IV [Part-1] [Bikaner Complex] Part D [Neemrana Bareilly Transmission Ltd] | Power Grid Corporation of India Limited [POWERGRID] | 612133 | Multi-States (Rajasthan, Uttar Pradesh) | 12/2023 | 12/2023 | 12/2025 | 06/2026 | 2056 | 2056 | 1356.96 | 58
August 2025 | 229 | Ministry of Power | Transmission & Distribution | Transmission System for evacuation of Power from Rajasthan REZ Ph-IV [Part-4 3.5 GW] Part A [SPV name POWERGRID Ghiror Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 616670 | Multi-States (Rajasthan, Uttar Pradesh) | 12/2024 | 12/2024 | 12/2026 | - | 5846 | 5846 | 293.47 | 4
August 2025 | 230 | Ministry of Power | Transmission & Distribution | Transmission system strengthening scheme for evacuation of power from solar energy zones in Rajasthan[8.1 GW] under phase-II- Part E | Power Grid Corporation of India Limited [POWERGRID] | 611659 | Rajasthan | 03/2023 | 03/2023 | 09/2024 | 10/2025 | 1433.28 | 1433 | 1359.63 | 95
August 2025 | 231 | Ministry of Power | Transmission & Distribution | Transmission System for Evacuation of Power from REZ in Rajasthan 20GW under Phase III- Part E2 | Power Grid Corporation of India Limited [POWERGRID] | 611947 | Rajasthan | 11/2023 | 11/2023 | 06/2025 | 12/2025 | 428.3 | 428.3 | 179.89 | 51
August 2025 | 232 | Ministry of Power | Transmission & Distribution | Transmission system for evacuation of power from REZ in Rajasthan 20 GW under Phase-III part H | Power Grid Corporation of India Limited [POWERGRID] | 611948 | Rajasthan | 10/2023 | 10/2023 | 04/2025 | 12/2025 | 2211.29 | 2211.29 | 1817.46 | 80
August 2025 | 233 | Ministry of Power | Transmission & Distribution | Transmission system for evacuation of power from REZ in Rajasthan 20 GW under Phase-III part C1 | Power Grid Corporation of India Limited [POWERGRID] | 611949 | Rajasthan | 10/2023 | 10/2023 | 04/2025 | 10/2025 | 1796.02 | 1796.02 | 1247.87 | 83
August 2025 | 234 | Ministry of Power | Transmission & Distribution | Transmission system for evacuation of power from REZ in Rajasthan 20 GW under Phase-III part B1 | Power Grid Corporation of India Limited [POWERGRID] | 611950 | Rajasthan | 09/2023 | 09/2023 | 04/2025 | 12/2025 | 2190.54 | 2190.54 | 1870.72 | 83
August 2025 | 235 | Ministry of Power | Transmission & Distribution | Transmission system for evacuation of power from REZ in Rajasthan 20GW under Phase-III Part E1 | Power Grid Corporation of India Limited [POWERGRID] | 611951 | Rajasthan | 12/2021 | 08/2023 | 02/2025 | 09/2025 | 688.74 | 688.74 | 587.42 | 96
August 2025 | 236 | Ministry of Power | Transmission & Distribution | Transmission System for Evacuation of power from Rajasthan REZ Ph-IV [Part-1] [Bikaner Complex] Part A [Bikaner Neemrana Transmission Ltd] | Power Grid Corporation of India Limited [POWERGRID] | 612134 | Rajasthan | 12/2023 | 12/2023 | 12/2025 | 03/2026 | 2998.34 | 2998.34 | 1703.11 | 51
August 2025 | 237 | Ministry of Power | Transmission & Distribution | Transmission System for Evacuation of Power from Rajasthan REZ Ph-IV [Part-2 5.5 GW][Jaisalmer/Barmer Complex] Part B [SPV Name POWERGRID Sirohi Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 615332 | Rajasthan | 08/2024 | 08/2024 | 08/2026 | - | 3279 | 3279 | 688.59 | 21
August 2025 | 238 | Ministry of Power | Transmission & Distribution | Transmission System Strengthening for Interconnections of Bhadla-III & Bikaner III Complex [SPV Name POWERGRID BHADLA BIKANER TRANSMISSION LIMITED] | Power Grid Corporation of India Limited [POWERGRID] | 615335 | Rajasthan | 08/2024 | 08/2024 | 08/2026 | - | 1382 | 1382 | 41.46 | 4
August 2025 | 239 | Ministry of Power | Transmission & Distribution | Additional Transmission System for evacuation of Power from Bhadla-III PS as part of Rajasthan REZ Phase III Scheme [20 GW] [SPV Name POWERGRID Bhadla-III Power Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 615337 | Rajasthan | 08/2024 | 08/2024 | 02/2026 | - | 369 | 369 | 58.26 | 16
August 2025 | 240 | Ministry of Power | Transmission & Distribution | TRANSMISSION SYSTEM FOR EVACUATION OF POWER FROM RAJASTHAN REZ PH -IV [PART-2 5.5 GW] [JAISALMER/BARMER COMPLEX] PART F [SPV Name POWERGRID BARMER I TRANSMISSION LIMITED] | Power Grid Corporation of India Limited [POWERGRID] | 615338 | Rajasthan | 11/2024 | 11/2024 | 11/2026 | - | 2735 | 2735 | 82.05 | 8
August 2025 | 241 | Ministry of Power | Transmission & Distribution | Augmentation at Fatehgarh-II PS, Fatehgarh-IV PS [Section-II] and Barmer-I PS [POWERGRID Fatehgarh Barmer Augmentation Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 617181 | Rajasthan | 03/2025 | 03/2025 | 12/2026 | - | 404 | 404 | 8.04 | 0
August 2025 | 242 | Ministry of Power | Transmission & Distribution | Transmission System under ISTS for evacuation of Power from Kudankulam Unit-3&4 [2x1000 MW] [SPV Name POWERGRID Kudankulam Tarnsmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 616671 | Tamil Nadu | 01/2025 | 01/2025 | 12/2026 | 12/2026 | 548 | 548 | 14.68 | 6
August 2025 | 243 | Ministry of Power | Transmission & Distribution | Transmission System for Strengthening to facilitate evacuation of power from Bhadla/Bikaner Complex | Power Grid Corporation of India Limited [POWERGRID] | 617269 | Uttar Pradesh | 12/2024 | 12/2024 | 06/2026 | - | 212.81 | 212.81 | 0.2 | 0
August 2025 | 244 | Ministry of Housing & Urban Affairs | Construction | C/o 184 MS Flats for Hon'ble MPs at BKS Marg, New Delhi | Central Public Works Department [CPWD] | 617282 | Delhi | 01/2022 | 05/2022 | 05/2025 | 08/2025 | 646.53 | 646.52 | 533.12 | 99
August 2025 | 245 | Ministry of Housing & Urban Affairs | Inland Waterways | Chennai Metro Rail Phase-II Development Project | Chennai Metro Rail Limited [CMRL] | 702668 | Tamil Nadu | 10/2024 | 11/2020 | 08/2029 | - | 63246 | 63246 | 26410.15 | 45
August 2025 | 246 | Ministry of Housing & Urban Affairs | Real Estate | Integrated Command control Center [ICCC] - Construction and Development of Integrated Command Control Center with Security, Surveillance, ITMS, Connecting Port, Ship Service, Smart Solid Waste Management, Smart Public Transport System | ministry of housing and urban affairs | 707229 | Andaman & Nicobar | 07/2021 | 11/2021 | 05/2023 | - | 209.88 | 209.88 | 0 | 70
August 2025 | 247 | Ministry of Housing & Urban Affairs | Real Estate | Redevelopment of Seven General Pool Residential Accommodation [GPRA] Colonies in Delhi | National Buildings Construction Corporation [NBCC] | 400188 | Delhi | 07/2016 | 05/2018 | 12/2025 | 12/2025 | 32850 | 32850 | 0 | 0
August 2025 | 248 | Ministry of Housing & Urban Affairs | Real Estate | Rehablitation in Junavadaj Area Smart City Project | ministry of housing and urban affairs | 701719 | Gujarat | NA | 06/2016 | 07/2022 | - | 539 | 539 | 39.63 | 50
August 2025 | 249 | Ministry of Housing & Urban Affairs | Real Estate | Green Building Development Project | ministry of housing and urban affairs | 701766 | Uttarakhand | NA | 08/2019 | 11/2023 | - | 150.97 | 150.97 | 18.95 | 31
August 2025 | 250 | Ministry of Housing & Urban Affairs | Urban Public Transport | Patna Metro Rail Project | Patna Metro Rail Corporation Ltd. [PMRCL] | 702627 | Bihar | 02/2019 | 02/2019 | 02/2024 | 06/2027 | 13365.77 | 13365.8 | 4039.77 | 40.07
August 2025 | 251 | Ministry of Housing & Urban Affairs | Urban Public Transport | Delhi Metro Rail Phase-IV [2 Corridors] | Delhi Metro Rail Corporation Limited [DMRC] | 617207 | Delhi | 03/2024 | 03/2024 | 03/2029 | - | 8399.81 | 8399.81 | 5.58 | 0
August 2025 | 252 | Ministry of Housing & Urban Affairs | Urban Public Transport | DMRTS Phase - IV [3 Priority Corridors] | Delhi Metro Rail Corporation Limited [DMRC] | 702632 | Delhi | NA | 07/2019 | 03/2025 | 03/2026 | 24948.65 | 24948.7 | 15785.39 | 69
August 2025 | 253 | Ministry of Housing & Urban Affairs | Urban Public Transport | Surat Metro Rail Project | Gujarat Metro Rail Corporation Limited [GMRCL] | 702630 | Gujarat | 03/2019 | 04/2019 | 03/2024 | 06/2026 | 12020.32 | 12020.3 | 7595.47 | 70
August 2025 | 254 | Ministry of Housing & Urban Affairs | Urban Public Transport | Ahmedabad Metro Rail Project, Phase-II | Gujarat Metro Rail Corporation Limited [GMRCL] | 702631 | Gujarat | 03/2019 | 03/2019 | 03/2024 | 12/2025 | 5384.17 | 5384.17 | 4180.43 | 88
August 2025 | 255 | Ministry of Housing & Urban Affairs | Urban Public Transport | Ahmedabad Metro Rail Project [Phase-I] | Gujarat Metro Rail Corporation Limited [GMRCL] | 702639 | Gujarat | 11/2014 | 02/2015 | 03/2018 | 10/2025 | 10773 | 12924.5 | 12174.41 | 99
August 2025 | 256 | Ministry of Housing & Urban Affairs | Urban Public Transport | Construction of Bangalore Metro Rail Project Phase 2. | Bengaluru Metro Rail | 702635 | Karnataka | 02/2014 | 02/2016 | 03/2021 | 09/2026 | 26405.14 | 30695.1 | 29477.97 | 94
August 2025 | 257 | Ministry of Housing & Urban Affairs | Urban Public Transport | Construction Bangalore Metro Rail Project Phase-2A & 2B | Bengaluru Metro Rail | 702665 | Karnataka | 06/2021 | 01/2019 | 06/2026 | 06/2026 | 14788.1 | 14788.1 | 8424.54 | 53
August 2025 | 258 | Ministry of Housing & Urban Affairs | Urban Public Transport | Kochi Metro Rail Phase 2 Development Project | CSPCC Projects | 702664 | Kerala | 11/2022 | 11/2022 | 11/2026 | 11/2026 | 1957.05 | 1957.05 | 329.94 | 12
August 2025 | 259 | Ministry of Housing & Urban Affairs | Urban Public Transport | Bhopal Metro Rail Project | Madhya Pradesh Metro Rail Co Limited [MPMRCL] | 702625 | Madhya Pradesh | 11/2018 | 11/2018 | 11/2022 | 06/2028 | 6941.4 | 6941.4 | 3164.15 | 43
August 2025 | 260 | Ministry of Housing & Urban Affairs | Urban Public Transport | Indore Metro Rail Project | Madhya Pradesh Metro Rail Co Limited [MPMRCL] | 702626 | Madhya Pradesh | 11/2018 | 11/2018 | 11/2022 | 12/2028 | 7500.8 | 7500.8 | 3931.4 | 55
August 2025 | 261 | Ministry of Housing & Urban Affairs | Urban Public Transport | PCMC To Nigdi- Extension Of North South Corridor Of Phase-1 | Maharashtra Metro Rail Corporation Limited [MMRCL] | 617225 | Maharashtra | 10/2023 | 10/2023 | 01/2027 | - | 910.18 | 910.18 | 119.88 | 22
August 2025 | 262 | Ministry of Housing & Urban Affairs | Urban Public Transport | Pune Metro Phase-1 Extension line towards south from Swargate to Katraj | Maharashtra Metro Rail Corporation Limited [MMRCL] | 617226 | Maharashtra | 09/2024 | 09/2024 | 03/2029 | - | 2954.53 | 2954.53 | 19.61 | 3
August 2025 | 263 | Ministry of Housing & Urban Affairs | Urban Public Transport | New Suburba Station Development Project | ministry of housing and urban affairs | 701745 | Maharashtra | NA | 03/2019 | 07/2022 | - | 262.76 | 262.76 | 17.62 | 6
August 2025 | 264 | Ministry of Housing & Urban Affairs | Urban Public Transport | Kalyan Station Precinct Imporvement Project | ministry of housing and urban affairs | 701991 | Maharashtra | NA | 07/2020 | 07/2023 | - | 600 | 600 | 272.42 | 70
August 2025 | 265 | Ministry of Housing & Urban Affairs | Urban Public Transport | Mumbai Metro Line 3 | Mumbai Metro Rail Corporation Limited [MMRC] | 702637 | Maharashtra | 07/2013 | 06/2016 | 03/2023 | 08/2025 | 23136 | 37276 | 27519.07 | 91.9
August 2025 | 266 | Ministry of Housing & Urban Affairs | Urban Public Transport | Nagpur Metro Rail Phase II Development Project | Maharashtra Metro Rail Corporation Limited [MMRCL] | 702658 | Maharashtra | 12/2022 | 12/2022 | 12/2027 | - | 6708 | 6708 | 1045.32 | 25
August 2025 | 267 | Ministry of Housing & Urban Affairs | Urban Public Transport | Delhi Metro Rail Phase-IV [Rithala - Kundli Corridor] | Delhi Metro Rail Corporation Limited [DMRC] | 617206 | Multi-States (Delhi, Haryana) | 01/2025 | 01/2025 | 01/2029 | - | 6230.99 | 6230.99 | 0.29 | 0
August 2025 | 268 | Ministry of Housing & Urban Affairs | Urban Public Transport | Delhi-Ghaziabad-Meerut Regional Rapid Transit System [RRTS] corridor | National Capital Region Transport Corporation [NCRTC] | 702633 | Multi-States (Delhi, Uttar Pradesh) | 03/2019 | 03/2019 | 06/2025 | 08/2025 | 30274 | 30274 | 26325.73 | 95
August 2025 | 269 | Ministry of Housing & Urban Affairs | Urban Public Transport | Kanpur Metro Rail Project | Uttar Pradesh metro rail corporation [UPMRC] | 702628 | Uttar Pradesh | 05/2019 | 11/2019 | 05/2024 | 03/2027 | 11076.48 | 11076.5 | 9083.27 | 73
August 2025 | 270 | Ministry of Housing & Urban Affairs | Urban Public Transport | Agra Metro Rail Project | Uttar Pradesh metro rail corporation [UPMRC] | 702629 | Uttar Pradesh | 05/2019 | 12/2020 | 05/2024 | 06/2027 | 8379.62 | 8379.62 | 6057.62 | 62
August 2025 | 271 | Ministry of Housing & Urban Affairs | Waste & Water | ESR - 8 nos., distribution system - 216 Km, new house service connections - 38760 nos. upgrading of feeder mains, pumping station etc. - Phase II | Ministry of Housing & Urban Affairs | 702674 | Andhra Pradesh | NA | 07/2018 | 03/2023 | 12/2025 | 172.22 | 172.22 | 622.02 | 82
August 2025 | 272 | Ministry of Housing & Urban Affairs | Waste & Water | Dibrugarh Water Supply Infrastructure Project | Ministry of Housing & Urban Affairs | 702682 | Assam | NA | 01/2020 | 03/2023 | 12/2025 | 186.8 | 186.8 | 1291.55 | 98
August 2025 | 273 | Ministry of Housing & Urban Affairs | Waste & Water | Muzaffarpur Storm Water Drainage Phase-I Project | Ministry of Housing & Urban Affairs | 702699 | Bihar | NA | 02/2019 | 10/2023 | 03/2024 | 158.78 | 158.78 | 48.61 | 51
August 2025 | 274 | Ministry of Housing & Urban Affairs | Waste & Water | Storm water drainag Development Project | ministry of housing and urban affairs | 702355 | Dadra & Nagar Haveli and Daman & Diu | NA | 12/2021 | 03/2024 | - | 210 | 210 | 0 | 20
August 2025 | 275 | Ministry of Housing & Urban Affairs | Waste & Water | Upgradation of Sewerage system in Gandhinagar City | ministry of housing and urban affairs | 707267 | Gujarat | NA | 03/2021 | 06/2023 | - | 200 | 200 | 100 | 10
August 2025 | 276 | Ministry of Housing & Urban Affairs | Waste & Water | Sewerage Management Scheme Part-3 Implementation | Ministry of Housing & Urban Affairs | 702734 | Haryana | NA | 11/2017 | 09/2023 | 03/2026 | 278.01 | 278.01 | 1548.15 | 88
August 2025 | 277 | Ministry of Housing & Urban Affairs | Waste & Water | Sewerage Management Scheme Part-3 Implementation | Ministry of Housing & Urban Affairs | 702735 | Haryana | NA | 10/2018 | 03/2023 | 12/2025 | 213.19 | 213.19 | 1069.74 | 91
August 2025 | 278 | Ministry of Housing & Urban Affairs | Waste & Water | Dhanbad Water Supply Infrastructure Project | Ministry of Housing & Urban Affairs | 702741 | Jharkhand | NA | 12/2018 | 03/2023 | 03/2026 | 216.55 | 216.55 | 696.48 | 72
August 2025 | 279 | Ministry of Housing & Urban Affairs | Waste & Water | SAAP-3 Water Supply Infrastructure SAAP-3 Project | Ministry of Housing & Urban Affairs | 702742 | Jharkhand | NA | 12/2018 | 10/2023 | 03/2026 | 159.31 | 159.31 | 612.5 | 65
August 2025 | 280 | Ministry of Housing & Urban Affairs | Waste & Water | Augmentation and Strenghthning of Urban Water Supply Phase 1 - SAAP 3 | Ministry of Housing & Urban Affairs | 702746 | Jharkhand | NA | 12/2018 | 03/2023 | 03/2026 | 278.28 | 278.28 | 1223.5 | 78
August 2025 | 281 | Ministry of Housing & Urban Affairs | Waste & Water | Belgavi Improvement in Sewerage System Project | Ministry of Housing & Urban Affairs | 702760 | Karnataka | NA | 10/2016 | 07/2023 | 12/2025 | 162.73 | 162.73 | 562.71 | 80
August 2025 | 282 | Ministry of Housing & Urban Affairs | Waste & Water | 24/7 water supply under AMRUT for Davanagere | Ministry of Housing & Urban Affairs | 702764 | Karnataka | NA | 01/2018 | 03/2023 | 12/2025 | 174.96 | 174.96 | 715.56 | 65
August 2025 | 283 | Ministry of Housing & Urban Affairs | Waste & Water | Indore Water Supply Infrastructure Project | Ministry of Housing & Urban Affairs | 702793 | Madhya Pradesh | NA | 11/2017 | 03/2023 | 12/2025 | 287.17 | 287.17 | 1766 | 99
August 2025 | 284 | Ministry of Housing & Urban Affairs | Waste & Water | Jabalpur Sewerage Management and Treatment Infrastructure Project | Ministry of Housing & Urban Affairs | 702798 | Madhya Pradesh | NA | 12/2017 | 03/2023 | 12/2025 | 362.31 | 362.31 | 2264.18 | 93
August 2025 | 285 | Ministry of Housing & Urban Affairs | Waste & Water | Satna Sewerage Management and Treatment Infrastructure Project | Ministry of Housing & Urban Affairs | 702808 | Madhya Pradesh | NA | 12/2016 | 03/2024 | 12/2025 | 191.56 | 191.56 | 501.71 | 86
August 2025 | 286 | Ministry of Housing & Urban Affairs | Waste & Water | Singrauli Sewerage Management and Treatment Infrastructure Project | Ministry of Housing & Urban Affairs | 702810 | Madhya Pradesh | NA | 11/2017 | 03/2023 | 12/2025 | 402.01 | 402.01 | 2424.71 | 90
August 2025 | 287 | Ministry of Housing & Urban Affairs | Waste & Water | Kalyan-Dombivali Water Supply Infrastructure Project | Ministry of Housing & Urban Affairs | 702833 | Maharashtra | NA | 09/2019 | 10/2023 | 12/2025 | 194.2 | 194.2 | 375.32 | 70
August 2025 | 288 | Ministry of Housing & Urban Affairs | Waste & Water | Mira-Bhayandar Water Supply Infrastructure Project | Ministry of Housing & Urban Affairs | 702840 | Maharashtra | NA | 08/2018 | 03/2023 | 12/2025 | 204.55 | 204.55 | 581.09 | 99
August 2025 | 289 | Ministry of Housing & Urban Affairs | Waste & Water | Nagpur Water Supply Infrastructure Project | Ministry of Housing & Urban Affairs | 702842 | Maharashtra | NA | 08/2018 | 03/2023 | 09/2025 | 273.78 | 273.78 | 266.11 | 99
August 2025 | 290 | Ministry of Housing & Urban Affairs | Waste & Water | Pune Water Supply Infrastructure Project | Ministry of Housing & Urban Affairs | 702851 | Maharashtra | NA | 07/2017 | 03/2023 | 10/2025 | 235.95 | 235.95 | 614.06 | 92
August 2025 | 291 | Ministry of Housing & Urban Affairs | Waste & Water | Solapur Sewerage Management Infrastructure Project | Ministry of Housing & Urban Affairs | 702854 | Maharashtra | NA | 04/2018 | 03/2023 | 12/2025 | 180.24 | 180.24 | 476.83 | 91
August 2025 | 292 | Ministry of Housing & Urban Affairs | Waste & Water | Jalandhar Water Supply Infrastructure Project | Ministry of Housing & Urban Affairs | 703021 | Punjab | NA | 08/2020 | 08/2023 | 03/2026 | 258.53 | 258.53 | 161.02 | 58
August 2025 | 293 | Ministry of Housing & Urban Affairs | Waste & Water | Patiala Water Supply Infrastructure Part-2 Project | Ministry of Housing & Urban Affairs | 703057 | Punjab | NA | 08/2020 | 10/2023 | 12/2025 | 287 | 287 | 451.94 | 74
August 2025 | 294 | Ministry of Housing & Urban Affairs | Waste & Water | Jaunpur Sewerage Management Infrastructure Project | Ministry of Housing & Urban Affairs | 702948 | Uttar Pradesh | NA | 08/2019 | 06/2023 | 12/2025 | 235.73 | 235.73 | 166 | 87
August 2025 | 295 | Ministry of Housing & Urban Affairs | Waste & Water | Jhansi Water Supply Infrastructure Phase-II Project | Ministry of Housing & Urban Affairs | 702949 | Uttar Pradesh | NA | 06/2019 | 07/2023 | 09/2025 | 561.74 | 561.74 | 523.15 | 100
August 2025 | 296 | Ministry of Mines | Construction | Construction of Basement + Ground Floor+ 10 Storeyed building for State of the Art Director General, GSI Building at plot No.GN-40, Sector-V, Salt Lake, Kolkata | Central Public Works Department (CPWD | 617280 | West Bengal | 04/2019 | 02/2020 | 08/2026 | - | 255.37 | 255.37 | 79.34 | 79
August 2025 | 297 | Ministry of Mines | Metals & Mining | Rakha Underground Mining Project | Hindustan Copper Limited [HCL] | 611798 | Jharkhand | 12/2022 | 03/2024 | 03/2033 | - | 2705 | 2705 | 0 | 0
August 2025 | 298 | Ministry of Mines | Metals & Mining | Surda Underground Copper Mining Project | Hindustan Copper Limited [HCL] | 611800 | Jharkhand | 02/2022 | 03/2024 | 03/2028 | - | 665.02 | 665.02 | 16.57 | 1
August 2025 | 299 | Ministry of Mines | Metals & Mining | Expansion of Malanjkhand Copper Project | Hindustan Copper Limited [HCL] | 400426 | Madhya Pradesh | 09/2011 | 04/2015 | 04/2020 | 04/2026 | 1856.36 | 1856.36 | 935.32 | 80
August 2025 | 300 | Ministry of Mines | Metals & Mining | Expansion of Alumina Refinery Plant with addition of 5th Stream having capacity enhancement of 1.0 Million Tonee Per Annum | National Aluminium Company Limited [NALCO] | 400141 | Odisha | 04/2017 | 04/2017 | 12/2022 | 09/2025 | 4103 | 5677.4 | 3984.99 | 76
August 2025 | 301 | Ministry of Mines | Metals & Mining | Pottangi Bauxite Mines Project | National Aluminium Company Limited [NALCO] | 400299 | Odisha | 05/2018 | 05/2018 | 03/2025 | 05/2026 | 1381 | 1960.77 | 650.04 | 51
August 2025 | 302 | Ministry of Mines | Metals & Mining | UTKAL D AND E COAL BLOCK | National Aluminium Company Limited [NALCO] | 709829 | Odisha | NA | 02/2016 | 03/2025 | - | 1021.97 | 1021.97 | 0 | 0
August 2025 | 303 | Ministry of Mines | Metals & Mining | CONVERSION OF FLAT BOTTOM SETTLERS AND WASHERS WITH A SINGLE TRAIN OF HRDS AND DCWS IN STREAMS 1 AND | Ministry of Mines | 709830 | Odisha | NA | 04/2017 | 11/2026 | - | 355 | 581 | 0 | 0
August 2025 | 304 | Ministry of Mines | Metals & Mining | SOURCING OF BAUXITE ARRANGEMENT FOR 5TH STREAM ALUMINA REFINERY FROM SOUTH BLOCK MINING LEASE OF PANCHPATMAILI MINES | National Aluminium Company Limited [NALCO] | 709831 | Odisha | 11/2017 | 11/2019 | 05/2025 | 06/2026 | 483 | 483 | 402.67 | 90
August 2025 | 305 | Ministry of Mines | Metals & Mining | 25.5 MW WIND POWER PROJECT AT KAYATHAR IN TAMILNADU | National Aluminium Company Limited [NALCO] | 709832 | Tamil Nadu | 09/2017 | 12/2017 | 03/2025 | 03/2026 | 166 | 166 | 135 | 65
August 2025 | 306 | Department of Higher Education | Education | Construction of Permanent Campus of Central Tribal University of Andhra Pradesh Phase-1 | Central Tribal University of Andhra Pradesh | 613008 | Andhra Pradesh | NA | 12/2023 | 06/2027 | - | 305 | 305 | 83.33 | 24
August 2025 | 307 | Department of Higher Education | Education | Construction of Permanent Campus of National Institute of Technology Arunachal Pradesh | National Institute of Technology, Arunachal Pradesh | 612898 | Arunachal Pradesh | NA | 03/2013 | 08/2026 | - | 592.61 | 592.61 | 549.96 | 75
August 2025 | 308 | Department of Higher Education | Education | Tezpur University Projects | Tezpur University | 606112 | Assam | 05/2019 | 06/2021 | 11/2023 | 08/2025 | 153.71 | 153.71 | 54.05 | 95
August 2025 | 309 | Department of Higher Education | Education | Additional Campus of NITPatna | NIT Patna | 606013 | Bihar | 07/2022 | 08/2022 | 07/2024 | 01/2026 | 499.21 | 499.21 | 425.47 | 91
August 2025 | 310 | Department of Higher Education | Education | Phase 1B - Construction of Academic Block, Hostel, Residential Tower, Directors Residence and External Development works at National Institute of Technology, Delhi Campus on Engineering, Procurement and Construction basis | Ministry of Education | 612851 | Delhi | NA | 11/2022 | 09/2025 | - | 333.49 | 333.49 | 277.75 | 91
August 2025 | 311 | Department of Higher Education | Education | Delhi University Eastern Campus at Surajmal Vihar | Delhi University | 616886 | Delhi | NA | 01/2025 | 10/2026 | - | 373 | 373 | 23.23 | 15
August 2025 | 312 | Department of Higher Education | Education | Construction of permanent campus of Central University of Gujarat at Village kundhela, Dist. Vadodara, Gujarat. | Gujarat | 612916 | Gujarat | NA | 02/2021 | 03/2025 | 03/2026 | 490.63 | 490.63 | 301.44 | 76
August 2025 | 313 | Department of Higher Education | Education | Establishment of Permanent campus Phase 1 of IIM Sirmaur | Indian Institute of Management, Sirmaur | 602099 | Himachal Pradesh | 09/2018 | 08/2020 | 10/2023 | 02/2026 | 392.51 | 454.78 | 323.64 | 92
August 2025 | 314 | Department of Higher Education | Education | Hostel blocks & dining hall block | Indian Institute of Technology, Mandi | 612128 | Himachal Pradesh | NA | 03/2024 | 03/2026 | 03/2026 | 166.66 | 166.66 | 72.09 | 65
August 2025 | 315 | Department of Higher Education | Education | Construction of Permanent Campus of Central University of Himachal Pradesh at Dehra, District - Kangra, [H.P.] on Engineering. Procurement and Construction [EPC Mode 1] Basis. | Central University, Himachal Pradesh | 612894 | Himachal Pradesh | 03/2021 | 08/2022 | 11/2024 | 11/2025 | 251.98 | 300.45 | 183.36 | 78
August 2025 | 316 | Department of Higher Education | Education | Construction of Permanent Campus for IIM Jammu Phase-1 at Jagti, Nagrota, Jammu, J&K | Indian Institute of Management, Jammu | 602098 | Jammu and Kashmir | 03/2019 | 10/2020 | 06/2023 | 09/2025 | 424.93 | 500.91 | 484.52 | 96
August 2025 | 317 | Department of Higher Education | Education | Additional Infrastructure at IISc Bangalore-RCC Monolithic for Men Hostel S14, Women Hostel S11 , Postdoctoral Hostel S12 2 Block , International Hostel S 12 , D&E Block S 12 2 Block FR. | IISC Bangalore | 610940 | Karnataka | 08/2021 | 08/2021 | 03/2024 | 09/2025 | 420.41 | 420.41 | 360.72 | 99
August 2025 | 318 | Department of Higher Education | Education | CONSTRUCTION OF PERMANENT CAMPUS FOR IIT PALAKKAD UNDER PHASE 1A | INDIAN INSTITUTE OF TECHNOLOGY PALAKKAD | 606431 | Kerala | 07/2017 | 03/2020 | 06/2022 | 11/2026 | 1006.45 | 1217.4 | 623.6 | 71
August 2025 | 319 | Department of Higher Education | Education | Phase III A works at IIT Indore [03 Hostels, 01 Studio Apartment, 01 Housing, Heavy & Sophisticated lab complex, Academic POD and Infrastructure for center of excellence] | Indian Institute of Technology, Indore | 611957 | Madhya Pradesh | NA | 11/2023 | 12/2026 | - | 496.28 | 496.28 | 143.95 | 35
August 2025 | 320 | Department of Higher Education | Education | Hostel 4 -Earlier Known as Hostel 20 | Indian Institute of Technology, Bombay | 612135 | Maharashtra | NA | 05/2022 | 09/2025 | - | 182.33 | 182.33 | 132.44 | 95
August 2025 | 321 | Department of Higher Education | Education | Academic Block 1 & 2 | Indian Institute of Technology, Bombay | 612203 | Maharashtra | NA | 01/2023 | 07/2026 | 03/2027 | 68 | 263.93 | 22.26 | 18
August 2025 | 322 | Department of Higher Education | Education | Construction and Developement of National Institute of Technology Meghalaya Permanent Campus at Sohra | National Institute of Technology, Meghalaya | 612885 | Meghalaya | 03/2020 | 09/2014 | 03/2022 | 07/2025 | 494.52 | 494.52 | 413.57 | 86
August 2025 | 323 | Department of Higher Education | Education | Construction of Permanent Campus for NIT Mizoram at Lengpui, Aizawl | Ministry of Education | 612876 | Mizoram | 03/2020 | 05/2014 | 12/2029 | 12/2029 | 474.23 | 474.23 | 167.55 | 4
August 2025 | 324 | Department of Higher Education | Education | Establishment of NIT Nagaland | NIT Nagaland | 613013 | Nagaland | NA | 09/2012 | 12/2025 | - | 275.63 | 275.63 | 260.1 | 95
August 2025 | 325 | Department of Higher Education | Education | IISER BERHAMPUR | Indian Institutes of Science Education and Research, Behrampur | 610315 | Odisha | 10/2018 | 09/2019 | 03/2021 | 12/2025 | 1229.32 | 773.76 | 837.04 | 97
August 2025 | 326 | Department of Higher Education | Education | Establishment of NIT Puducherry Permanent Campus [Phase-I and Phase-II] | National Institute of Technology, Puducherry | 612877 | Puducherry | 03/2020 | 07/2013 | 12/2024 | 08/2025 | 618.34 | 544.34 | 509.55 | 94
August 2025 | 327 | Department of Higher Education | Education | Construction of Permanent Campus of Indian Institute of Management [IIM] Amritsar, Punjab, Phase-I | Indian intitue of Management, Amritsar | 605292 | Punjab | 10/2019 | 07/2020 | 06/2023 | 12/2025 | 348.31 | 348.31 | 290.39 | 91
August 2025 | 328 | Department of Higher Education | Education | Construction of Girls Hostel 400 seater, Boys Hostel 600 seater, Academic Block, International Hostel 100 seater, VC Residence and Purchase of Equipment | Central University of Punjab | 617221 | Punjab | 08/2024 | 04/2025 | 10/2027 | - | 210.99 | 210.99 | 0 | 0
August 2025 | 329 | Department of Higher Education | Education | Construction of Sikkim University Campus Phase-I Package-II at Yangang, South Sikkim | Sikkim University | 609736 | Sikkim | 08/2020 | 01/2022 | 01/2025 | 09/2025 | 314.06 | 314.06 | 238.22 | 82
August 2025 | 330 | Department of Higher Education | Education | Establishment of Permanent Campus of NIT SIkkim at Khamdong-Gangtok District | Ministry of Education | 612883 | Sikkim | 02/2024 | 03/2024 | 02/2028 | 12/2026 | 685.76 | 610.76 | 121.56 | 9
August 2025 | 331 | Department of Higher Education | Education | Construction of Precast housing and hostels at IIT Hyderabad | Indian Institute of Technology, Hyderabad | 609996 | Telangana | NA | 11/2022 | 10/2024 | 01/2026 | 262 | 262 | 177.09 | 73
August 2025 | 332 | Department of Higher Education | Education | Banaras Hindu University [ Kayakalp of Institute of Medical Sciences] | Banaras Hindu University | 606479 | Uttar Pradesh | NA | 06/2020 | 09/2022 | 03/2026 | 246 | 246 | 193.38 | 95
August 2025 | 333 | Department of Higher Education | Education | Construction & Development of Infrastructural Facilities in the main campus of NIT Uttarakhand at Sumari, Pauri Garhwal | National Institute of Technology Uttarakhand | 611963 | Uttarakhand | 06/2020 | 04/2024 | 09/2027 | - | 650.85 | 650.85 | 195.52 | 24
August 2025 | 334 | Department of Higher Education | Education | HEFA projects on development of student hostels, playgrounds, departmental buildings, class room complex and other campus facilities in IIT Kharagpur | Indian Institute of Technology, Kharagpur | 609019 | West Bengal | 06/2018 | 04/2019 | 03/2023 | 03/2026 | 500 | 442 | 383.6 | 87
August 2025 | 335 | Department of Higher Education | Education | IoE Projects [Civil Works], IIT Kharagpur | Indian Institute of Technology, Kharagpur | 609041 | West Bengal | NA | 04/2019 | 03/2023 | 12/2026 | 287.2 | 287.2 | 310 | 86
August 2025 | 336 | Ministry of Petroleum & Natural Gas | Energy Storage | Construction of Aviation Fuel farm Facilities at Bhogapuram Airport | Ministry of Petroleum & Natural Gas | 616235 | Andhra Pradesh | NA | 08/2024 | 03/2026 | 03/2026 | 240 | 240 | 38.82 | 59
August 2025 | 337 | Ministry of Petroleum & Natural Gas | Energy Storage | Construction of LPG Facilities at Kamardanga, Assam | Hindustan Petroleum Corporation Limited | 709754 | Assam | NA | 03/2023 | 07/2027 | 07/2027 | 156.36 | 156.36 | 54.15 | 46
August 2025 | 338 | Ministry of Petroleum & Natural Gas | Energy Storage | Setting up of new rail fed POL facility at Kamardanga, Assam | Hindustan Petroleum Corporation Limited [HPCL] | 709755 | Assam | NA | 03/2023 | 07/2027 | 07/2027 | 384.04 | 384.04 | 120.4 | 52
August 2025 | 339 | Ministry of Petroleum & Natural Gas | Energy Storage | Setting up a common user Petroleum Terminal at Jammu, J&K for resitement of existing PSU OMC's Depots from Jammu City | Bharat Petroleum Corporation Limited [BPCL] | 400235 | Jammu and Kashmir | NA | 04/2023 | 03/2025 | 01/2026 | 676.89 | 676.89 | 526.1 | 79
August 2025 | 340 | Ministry of Petroleum & Natural Gas | Energy Storage | Andheri Residential Towers, Mumbai | Ministry of Petroleum & Natural Gas | 604833 | Maharashtra | NA | 06/2017 | 05/2025 | 06/2026 | 281.35 | 389.67 | 230.76 | 50
August 2025 | 341 | Ministry of Petroleum & Natural Gas | Energy Storage | Srikakulam Angul Gas Pipeline Project | Ministry of Petroleum & Natural Gas | 701343 | Multi-States (Andhra Pradesh, Odisha) | NA | 09/2019 | 07/2022 | 12/2025 | 2658.34 | 2810 | 2203.98 | 95
August 2025 | 342 | Ministry of Petroleum & Natural Gas | Energy Storage | Rajasthan Refinery Project | MinistryofPetroleumNaturalGas | 701263 | Multi-States (Arunachal Pradesh, Gujarat, Rajasthan) | NA | 10/2017 | 10/2022 | 03/2026 | 43129 | 79459 | 60295.14 | 88
August 2025 | 343 | Ministry of Petroleum & Natural Gas | Energy Storage | Paradip-Numaligarh Crude Oil Pipeline [PNCPL] & Crude Oil Import Terminal [COIT] at Paradip | Ministry of Petroleum & Natural Gas | 701349 | Multi-States (Assam, Bihar, Jharkhand, Odisha, West Bengal) | NA | 01/2019 | 07/2024 | 09/2025 | 10228 | 11407 | 9766.72 | 87
August 2025 | 344 | Ministry of Petroleum & Natural Gas | Energy Storage | New Mundra Panipat Crude Oil Pipeline | Ministry of Petroleum & Natural Gas | 400078 | Multi-States (Gujarat, Haryana, Rajasthan) | NA | 12/2021 | 12/2024 | 12/2025 | 9028 | 9028 | 7136.41 | 85
August 2025 | 345 | Ministry of Petroleum & Natural Gas | Energy Storage | Kandla Gorakhpur LPG Pipeline | Ministry of Petroleum & Natural Gas | 400012 | Multi-States (Gujarat, Madhya Pradesh, Uttar Pradesh) | NA | 12/2018 | 12/2021 | 12/2025 | 10088 | 10088 | 7672.23 | 92
August 2025 | 346 | Ministry of Petroleum & Natural Gas | Energy Storage | Multi Product Pipeline from Irugur to Devangonthi | Department of Water Resources, River Development & GR | 400301 | Multi-States (Karnataka, Tamil Nadu) | NA | 11/2012 | 02/2017 | 10/2025 | 678 | 1732 | 713.86 | 69
August 2025 | 347 | Ministry of Petroleum & Natural Gas | Energy Storage | Petrochemical evacuation marketing terminal at Barmer, Rajasthan | Hindustan Petroleum Corporation Limited [HPCL] | 709759 | Rajasthan | NA | 12/2023 | 12/2026 | 12/2026 | 461.05 | 461.05 | 116.48 | 54
August 2025 | 348 | Ministry of Petroleum & Natural Gas | Energy Storage | Laying of POL Pipelines in Common Corridor for proposed grass root terminal at Vallur [Chennai] | Ministry of Petroleum & Natural Gas | 400043 | Tamil Nadu | NA | 01/2022 | 05/2026 | 05/2026 | 829 | 829 | 301.71 | 63
August 2025 | 349 | Ministry of Petroleum & Natural Gas | Energy Storage | Grass root POL Terminal at Vallur, Chennai | Indian Oil Corporation Limited [IOCL] | 400077 | Tamil Nadu | NA | 01/2022 | 12/2024 | 03/2026 | 827 | 887.71 | 626.01 | 88
August 2025 | 350 | Ministry of Petroleum & Natural Gas | Energy Storage | Grass Root Rail-fed Depot at Sekerkote, Agartala as resitement of existing Dharmanagar Depot | Indian Oil Corporation Limited [IOCL] | 400035 | Tripura | NA | 06/2022 | 09/2025 | 06/2026 | 656 | 656 | 478.11 | 86
August 2025 | 351 | Ministry of Petroleum & Natural Gas | Energy Storage | Grass-root Terminal at Mirzapur, Uttar Pradesh | Ministry of Petroleum & Natural Gas | 604852 | Uttar Pradesh | NA | 09/2022 | 11/2026 | 11/2026 | 980.45 | 980.45 | 216.66 | 52
August 2025 | 352 | Ministry of Petroleum & Natural Gas | Oil & Gas | KG-DWN-98/2 Cluster - II Development Project - NELP Block | Oil and Natural Gas Corporation Limited [ONGC] | 400120 | Andhra Pradesh | NA | 03/2016 | 06/2020 | 06/2026 | 34012 | 34012 | 33238.47 | 96
August 2025 | 353 | Ministry of Petroleum & Natural Gas | Oil & Gas | HP-COAT [Crude to Olefins and Aromatics Technology] demo unit at Visakh Refinery | Hindustan Petroleum Corporation Limited | 709752 | Andhra Pradesh | NA | 09/2021 | 06/2024 | 03/2026 | 160 | 220 | 80.29 | 69
August 2025 | 354 | Ministry of Petroleum & Natural Gas | Oil & Gas | HP Trijet Unit in Visakh Refinery | Hindustan Petroleum Corporation Limited | 709761 | Andhra Pradesh | NA | 07/2024 | 07/2027 | 07/2027 | 193 | 193 | 0.43 | 23
August 2025 | 355 | Ministry of Petroleum & Natural Gas | Oil & Gas | City Gas Distribution Project at Kurnool, Guntur & Prakasam Districts | MinistryofPetroleumNaturalGas | 709766 | Andhra Pradesh | NA | 03/2022 | 03/2030 | 03/2030 | 1420 | 1420 | 165.65 | 6
August 2025 | 356 | Ministry of Petroleum & Natural Gas | Oil & Gas | Numaligarh Refinery Expansion Project | Ministry of Petroleum & Natural Gas | 604791 | Assam | NA | 07/2020 | 07/2024 | 12/2025 | 12366 | 22494 | 16764.09 | 76
August 2025 | 357 | Ministry of Petroleum & Natural Gas | Oil & Gas | Assam Bio Refinery, ABRPL | Ministry of Petroleum & Natural Gas | 604792 | Assam | NA | 02/2018 | 09/2021 | 09/2025 | 1750 | 4930 | 4710 | 99
August 2025 | 358 | Ministry of Petroleum & Natural Gas | Oil & Gas | Development of Surface Facilities for production and evacuation of Crude Oil and Natural Gas from Nadua and East Khagorija | Ministry of Petroleum & Natural Gas | 604863 | Assam | NA | 01/2018 | 02/2020 | 12/2025 | 682.9 | 726.93 | 489.3 | 94
August 2025 | 359 | Ministry of Petroleum & Natural Gas | Oil & Gas | Guwahati Refinery Expansion [1.0 to 1.2 MMTPA] along with installation of CRU, Guwahati Refinery | Ministry of Petroleum & Natural Gas | 607701 | Assam | NA | 05/2021 | 10/2023 | 05/2026 | 412.3 | 577 | 430.83 | 85
August 2025 | 360 | Ministry of Petroleum & Natural Gas | Oil & Gas | Construction of Field Gas Gathering Station at Baghjan area for collection, processing & transportation of natural Gas to be produced from Baghjan Field | Ministry of Petroleum & Natural Gas | 616858 | Assam | NA | 12/2020 | 03/2024 | 12/2025 | 430.76 | 430.76 | 327.27 | 85
August 2025 | 361 | Ministry of Petroleum & Natural Gas | Oil & Gas | Augmentation/Revamping of Facilities at existing Guwahati Terminal at Betkuchi | MinistryofPetroleumNaturalGas | 709776 | Assam | NA | 04/2022 | 09/2026 | 09/2026 | 277 | 323.09 | 185.18 | 68
August 2025 | 362 | Ministry of Petroleum & Natural Gas | Oil & Gas | Capacity Expansion of Digboi Refinery from 0.65 to 1.0 MMTPA | MinistryofPetroleumNaturalGas | 709779 | Assam | NA | 06/2022 | 03/2026 | 03/2026 | 768 | 740 | 107.72 | 39
August 2025 | 363 | Ministry of Petroleum & Natural Gas | Oil & Gas | Pipeline Network Project Rudrasagar | Ministry of Petroleum & Natural Gas | 709847 | Assam | NA | 01/2023 | 04/2026 | 04/2026 | 344.99 | 344.99 | 211.05 | 47
August 2025 | 364 | Ministry of Petroleum & Natural Gas | Oil & Gas | Borholla GGS Life Extension Project [BLEP] | Ministry of Petroleum & Natural Gas | 709850 | Assam | NA | 09/2023 | 05/2026 | 05/2026 | 198.7 | 198.7 | 36.8 | 30
August 2025 | 365 | Ministry of Petroleum & Natural Gas | Oil & Gas | DCU Revamp Project | NRL | 709864 | Assam | NA | 08/2021 | 07/2024 | 10/2025 | 370 | 370 | 253.17 | 60
August 2025 | 366 | Ministry of Petroleum & Natural Gas | Oil & Gas | Power Recovery Turbine [PRT] in PFCCU unit as an Energy Conservation Scheme | NRL | 709865 | Assam | NA | 04/2023 | 12/2024 | 10/2025 | 293.5 | 293.5 | 97.22 | 94
August 2025 | 367 | Ministry of Petroleum & Natural Gas | Oil & Gas | City Gas Distribution Project at Khagaria, Saharsa and Madhepura | Ministry of Petroleum & Natural Gas | 617303 | Bihar | NA | 03/2019 | 03/2030 | 03/2030 | 163 | 163 | 96.07 | 40
August 2025 | 368 | Ministry of Petroleum & Natural Gas | Oil & Gas | Setting up of LPG Plant with Rail Unloading Facility at Hathua, Dist. Gopalganj, Bihar | MinistryofPetroleumNaturalGas | 617304 | Bihar | NA | 10/2023 | 03/2027 | 03/2027 | 340.15 | 340.15 | 91.32 | 26
August 2025 | 369 | Ministry of Petroleum & Natural Gas | Oil & Gas | Barauni Refinery Capacity Expansion from 6.0 to 9.0 MMTPA | Ministry of Petroleum & Natural Gas | 701324 | Bihar | NA | 01/2020 | 04/2023 | 08/2026 | 14810 | 16724 | 11880.66 | 87
August 2025 | 370 | Ministry of Petroleum & Natural Gas | Oil & Gas | Installation of Bitumen Manufacturing Unit along with allied facilities at Barauni Refinery | MinistryofPetroleumNaturalGas | 709777 | Bihar | NA | 01/2022 | 04/2025 | 10/2026 | 389.35 | 340 | 50.48 | 40
August 2025 | 371 | Ministry of Petroleum & Natural Gas | Oil & Gas | City Gas Distribution Projects at Darbhanga, Madhubani, Supaul, Sitamarhi and Sheohar districts | Bharat Petroleum Corporation Limited [BPCL] | 709792 | Bihar | NA | 12/2022 | 03/2030 | 03/2030 | 3638 | 3638 | 407.18 | 29
August 2025 | 372 | Ministry of Petroleum & Natural Gas | Oil & Gas | City Gas Distribution Projects at Gopalganj, Siwan, West Champaran, East Champaran and Deoria districts | Bharat Petroleum Corporation Limited [BPCL] | 709793 | Bihar | NA | 12/2022 | 06/2030 | 06/2030 | 3919 | 3919 | 400.92 | 18
August 2025 | 373 | Ministry of Petroleum & Natural Gas | Oil & Gas | Redevelopment of Sobhasan Complex | Oil and Natural Gas Corporation Limited [ONGC] | 400087 | Gujarat | NA | 08/2021 | 02/2026 | 02/2026 | 885.63 | 1286.67 | 789.49 | 78
August 2025 | 374 | Ministry of Petroleum & Natural Gas | Oil & Gas | Redevelopment of Santhal Field [Onshore-Mehsana Asset] | Oil and Natural Gas Corporation Limited [ONGC] | 400167 | Gujarat | NA | 02/2017 | 03/2026 | 03/2026 | 1162.56 | 1162.56 | 1157 | 94
August 2025 | 375 | Ministry of Petroleum & Natural Gas | Oil & Gas | Redevelopment of Linch Field | Oil and Natural Gas Corporation Limited [ONGC] | 400169 | Gujarat | NA | 04/2021 | 03/2025 | 10/2025 | 631.03 | 860.04 | 505.15 | 79
August 2025 | 376 | Ministry of Petroleum & Natural Gas | Oil & Gas | Petrochemical and Lube Integration Project at Gujarat Refinery | Ministry of Petroleum & Natural Gas | 701329 | Gujarat | NA | 09/2020 | 08/2024 | 12/2025 | 18936 | 17825 | 12327.91 | 83
August 2025 | 377 | Ministry of Petroleum & Natural Gas | Oil & Gas | Installation of new Biturox Unit along with allied facilities at Gujarat Refinery | MinistryofPetroleumNaturalGas | 709778 | Gujarat | NA | 01/2022 | 08/2025 | 09/2026 | 328.29 | 287 | 151.53 | 58
August 2025 | 378 | Ministry of Petroleum & Natural Gas | Oil & Gas | Commercial Polymer Flooding Project in Bechraji field | Oil and Natural Gas Corporation Limited [ONGC] | 709838 | Gujarat | NA | 01/2022 | 11/2024 | 11/2025 | 621.4 | 621.4 | 137.71 | 21
August 2025 | 379 | Ministry of Petroleum & Natural Gas | Oil & Gas | Restoration of Gas Terminal, Phase-I [Part-A], Hazira | Oil and Natural Gas Corporation Limited [ONGC] | 709840 | Gujarat | NA | 05/2022 | 02/2025 | 12/2025 | 249.43 | 249.43 | 209.45 | 94
August 2025 | 380 | Ministry of Petroleum & Natural Gas | Oil & Gas | Old Pipe Line Replacement [OPRP] Group-A | Oil and Natural Gas Corporation Limited [ONGC] | 709841 | Gujarat | NA | 07/2021 | 07/2025 | 03/2026 | 173.03 | 169.84 | 147.02 | 87
August 2025 | 381 | Ministry of Petroleum & Natural Gas | Oil & Gas | Kalol Redevelopment Project, Ahmedabad Asset | Oil and Natural Gas Corporation Limited [ONGC] | 709842 | Gujarat | NA | 08/2022 | 03/2027 | 03/2027 | 1487.41 | 1487.41 | 927.5 | 62
August 2025 | 382 | Ministry of Petroleum & Natural Gas | Oil & Gas | Revamping of SV Stations, Gas Terminal & Kribhco Terminal | Oil and Natural Gas Corporation Limited [ONGC] | 709845 | Gujarat | NA | 11/2022 | 08/2026 | 08/2026 | 837.34 | 837.34 | 219.13 | 52
August 2025 | 383 | Ministry of Petroleum & Natural Gas | Oil & Gas | Indian Oil Technology Development and Deployment Centre at R&D Campus-II, Faridabad | Ministry of Petroleum & Natural Gas | 604853 | Haryana | NA | 06/2019 | 12/2022 | 03/2026 | 2281.94 | 3200 | 1800.61 | 63
August 2025 | 384 | Ministry of Petroleum & Natural Gas | Oil & Gas | Poly Butadiene Rubber plant at Panipat | Indian Oil Corporation Limited [IOCL] | 611917 | Haryana | NA | 03/2022 | 03/2025 | 06/2026 | 1459 | 2531.44 | 1072.59 | 70
August 2025 | 385 | Ministry of Petroleum & Natural Gas | Oil & Gas | Capacity Expansion of Panipat Refinery from 15 to 25 MMTPA | Ministry of Petroleum & Natural Gas | 701289 | Haryana | NA | 02/2021 | 09/2024 | 12/2025 | 34627 | 36225 | 24355.1 | 89
August 2025 | 386 | Ministry of Petroleum & Natural Gas | Oil & Gas | Installation of Multiple Effect Evaporator [MEE] for ETP-1, 2 & 4 of Panipat Refinery and Petrochemical Complex. | MinistryofPetroleumNaturalGas | 709783 | Haryana | NA | 12/2020 | 06/2023 | 06/2026 | 165.13 | 247.69 | 130.6 | 72
August 2025 | 387 | Ministry of Petroleum & Natural Gas | Oil & Gas | City Gas Distribution Project at Jammu, Udhampur, Reasi, Samba and Kathua Districts | MinistryofPetroleumNaturalGas | 709773 | Jammu and Kashmir | NA | 03/2022 | 03/2032 | 03/2032 | 538 | 538 | 3.72 | 0
August 2025 | 388 | Ministry of Petroleum & Natural Gas | Oil & Gas | Development of Jharia CBM Block [Phase-1] | Oil and Natural Gas Corporation Limited [ONGC] | 610984 | Jharkhand | NA | 11/2019 | 01/2024 | 11/2025 | 431 | 431 | 211.4 | 59
August 2025 | 389 | Ministry of Petroleum & Natural Gas | Oil & Gas | Laying of Natural Gas Pipeline from Hazaribagh to Ranchi [HRPL] | MinistryofPetroleumNaturalGas | 709785 | Jharkhand | NA | 02/2023 | 02/2026 | 02/2026 | 202.07 | 202.07 | 52.42 | 45
August 2025 | 390 | Ministry of Petroleum & Natural Gas | Oil & Gas | Power System Upgradation Project | Mangalore Refinary and Petrochemicals Limited | 612790 | Karnataka | NA | 10/2023 | 11/2025 | 05/2026 | 385 | 385 | 137 | 64
August 2025 | 391 | Ministry of Petroleum & Natural Gas | Oil & Gas | Demo Bio-ATF Project | Ministry of Petroleum & Natural Gas | 616879 | Karnataka | NA | 03/2024 | 01/2027 | 01/2027 | 364 | 364 | 27.02 | 12
August 2025 | 392 | Ministry of Petroleum & Natural Gas | Oil & Gas | Revamping/ Augmentation of facilities at existing port terminal at Mangalore | Ministry of Petroleum & Natural Gas | 709774 | Karnataka | NA | 01/2022 | 12/2025 | 12/2025 | 463 | 500.62 | 271.16 | 82
August 2025 | 393 | Ministry of Petroleum & Natural Gas | Oil & Gas | Replacement and Extension of Jetty Pipelines [REJP] at KR | Bharat Petroleum Corporation Limited [BPCL] | 709790 | Kerala | NA | 03/2023 | 03/2026 | 03/2026 | 621.87 | 621.87 | 193.19 | 85
August 2025 | 394 | Ministry of Petroleum & Natural Gas | Oil & Gas | Setting up Polypropylene Unit at Kochi Refinery | MinistryofPetroleumNaturalGas | 709799 | Kerala | NA | 12/2023 | 10/2027 | 10/2027 | 4460 | 4460 | 265.89 | 13
August 2025 | 395 | Ministry of Petroleum & Natural Gas | Oil & Gas | Ethylene Cracker Project at Bina Refinery including downstream Petrochemical Plants and expansion of Refinery | MinistryofPetroleumNaturalGas | 709798 | Madhya Pradesh | NA | 05/2023 | 05/2028 | 05/2028 | 43367 | 43367 | 1855.5 | 14
August 2025 | 396 | Ministry of Petroleum & Natural Gas | Oil & Gas | Debottlenecking and Augmentation of Cryogenic facilities at Uran LPG Import Terminal | Department of Water Resources, River Development & GR | 400158 | Maharashtra | NA | 04/2021 | 02/2024 | 12/2025 | 1164.69 | 1629.86 | 932.25 | 86
August 2025 | 397 | Ministry of Petroleum & Natural Gas | Oil & Gas | 500 KTA PDHPP Project, Usar | Ministry of Petroleum & Natural Gas | 400168 | Maharashtra | NA | 04/2021 | 04/2025 | 10/2025 | 8797 | 11256 | 6877.59 | 85
August 2025 | 398 | Ministry of Petroleum & Natural Gas | Oil & Gas | Construction of lube oil blending plant at Rasayani | Ministry of Petroleum & Natural Gas | 610985 | Maharashtra | NA | 05/2022 | 12/2023 | 12/2025 | 423.39 | 526.26 | 301.01 | 80
August 2025 | 399 | Ministry of Petroleum & Natural Gas | Oil & Gas | Lube Modernization & Bottom Upgradation Project at Mumbai Refinery | Ministry of Petroleum and Natural Gas | 616933 | Maharashtra | NA | 12/2024 | 03/2028 | 03/2028 | 4679 | 4679 | 194.44 | 5
August 2025 | 400 | Ministry of Petroleum & Natural Gas | Oil & Gas | HP TDAE Unit in Mumbai Refinery | Hindustan Petroleum Corporation Limited | 709760 | Maharashtra | NA | 06/2024 | 04/2026 | 04/2026 | 240 | 240 | 34.42 | 40
August 2025 | 401 | Ministry of Petroleum & Natural Gas | Oil & Gas | City Gas Distribution Project at Beed, Jalgaon and Jalna Districts | MinistryofPetroleumNaturalGas | 709771 | Maharashtra | NA | 03/2022 | 09/2031 | 09/2031 | 865 | 865 | 69.15 | 2
August 2025 | 402 | Ministry of Petroleum & Natural Gas | Oil & Gas | Construction of Additional Tankages and Allied Facilities at JNPT Terminal | MinistryofPetroleumNaturalGas | 709780 | Maharashtra | NA | 04/2022 | 08/2026 | 08/2026 | 341.43 | 436.14 | 282.95 | 51
August 2025 | 403 | Ministry of Petroleum & Natural Gas | Oil & Gas | ATF Pipeline from Jawaharlal Nehru Port Trust to Navi Mumbai International Airport | Indian Oil Corporation Limited [IOCL] | 709782 | Maharashtra | NA | 08/2022 | 08/2025 | 03/2026 | 165 | 165 | 90.75 | 74
August 2025 | 404 | Ministry of Petroleum & Natural Gas | Oil & Gas | Installation of Independent De- Aromatized Solvents [DAS] production facilities at MR | Bharat Petroleum Corporation Limited [BPCL] | 709789 | Maharashtra | NA | 03/2023 | 07/2025 | 12/2025 | 405 | 343 | 205.63 | 86
August 2025 | 405 | Ministry of Petroleum & Natural Gas | Oil & Gas | POL & LOBS Installations with Receipt Pipelines at Rasayani | Bharat Petroleum Corporation Limited [BPCL] | 709797 | Maharashtra | NA | 05/2023 | 05/2026 | 05/2026 | 2585 | 2585 | 612.7 | 61
August 2025 | 406 | Ministry of Petroleum & Natural Gas | Oil & Gas | Part Replacement Pipeline Project [PRPP] | Oil and Natural Gas Corporation Limited [ONGC] | 709846 | Maharashtra | NA | 11/2022 | 05/2024 | 11/2025 | 1219.48 | 1145.1 | 744.81 | 90
August 2025 | 407 | Ministry of Petroleum & Natural Gas | Oil & Gas | Visakh Raipur Pipeline Project | Ministry of Petroleum and Natural Gas | 616254 | Multi-States (Andhra Pradesh, Chhattisgarh, Odisha) | NA | 09/2024 | 09/2027 | 09/2027 | 2212 | 2212 | 13.45 | 8
August 2025 | 408 | Ministry of Petroleum & Natural Gas | Oil & Gas | North East Gas Grid | Ministry of Petroleum & Natural Gas | 701346 | Multi-States (Arunachal Pradesh, Assam, Manipur, Meghalaya, Mizoram, Nagaland, Sikkim, Tripura, West Bengal) | NA | 04/2020 | 03/2024 | 03/2026 | 9265 | 9265 | 6393.85 | 85
August 2025 | 409 | Ministry of Petroleum & Natural Gas | Oil & Gas | Upgradation of Facilities of Numaligarh-Siliguri Product Pipeline [NSPL] for transportation of additional products from existing 1.72 MMTPA to 5.5 MMTPA | Ministry of Petroleum & Natural Gas | 701350 | Multi-States (Assam, West Bengal) | NA | 06/2021 | 12/2024 | 10/2025 | 860 | 860 | 584.76 | 98
August 2025 | 410 | Ministry of Petroleum & Natural Gas | Oil & Gas | CGD Project in Banka, Dumka, Godda, Jamtara, Pakur, Sahibganj GA ID 11A.02 | Hindustan Petroleum Corporation Limited | 709757 | Multi-States (Bihar, Jharkhand) | NA | 06/2022 | 06/2030 | 06/2030 | 1377 | 1377 | 331.74 | 27
August 2025 | 411 | Ministry of Petroleum & Natural Gas | Oil & Gas | Mumbai Nagpur Jharsuguda Pipeline Project | Ministry of Petroleum & Natural Gas | 701354 | Multi-States (Chhattisgarh, Madhya Pradesh, Maharashtra, Odisha) | NA | 06/2020 | 05/2023 | 09/2025 | 7844.25 | 8255 | 6495.6 | 96
August 2025 | 412 | Ministry of Petroleum & Natural Gas | Oil & Gas | Mehsana-Bhatinda & Bhatinda-Jammu Natural Gas Pipeline | Ministry of Petroleum & Natural Gas | 701330 | Multi-States (Gujarat, Haryana, Punjab, Rajasthan) | NA | 07/2011 | 06/2024 | 12/2025 | 7392 | 7392 | 6308 | 90
August 2025 | 413 | Ministry of Petroleum & Natural Gas | Oil & Gas | Gurdaspur Jammu Pipeline | Gas Authority of India Limited [GAIL] | 612853 | Multi-States (Jammu and Kashmir, Punjab) | NA | 07/2023 | 07/2026 | 07/2026 | 521.9 | 521.9 | 190.1 | 36
August 2025 | 414 | Ministry of Petroleum & Natural Gas | Oil & Gas | Kochi - Koottanad - Bangalore - Mangalore Pipeline Phase-II | Ministry of Petroleum & Natural Gas | 701228 | Multi-States (Karnataka, Kerala, Tamil Nadu) | NA | 06/2009 | 12/2012 | 12/2025 | 2915 | 5909 | 4453.29 | 94
August 2025 | 415 | Ministry of Petroleum & Natural Gas | Oil & Gas | City Gas Distribution Maharashtra Natural Gas Limited | Ministry of Petroleum & Natural Gas | 701338 | Multi-States (Karnataka, Maharashtra) | NA | 01/2006 | 06/2031 | 06/2031 | 5535 | 5535 | 3861.49 | 0
August 2025 | 416 | Ministry of Petroleum & Natural Gas | Oil & Gas | Dhamra Haldia Pipeline Project | Ministry of Petroleum & Natural Gas | 701344 | Multi-States (Odisha, West Bengal) | NA | 03/2020 | 11/2022 | 12/2025 | 1030.65 | 1125 | 854.6 | 87
August 2025 | 417 | Ministry of Petroleum & Natural Gas | Oil & Gas | City Gas Distribution Projects at Fazilka [except area already authorized], Ganganagar and Hanumangarh districts | Bharat Petroleum Corporation Limited [BPCL] | 709794 | Multi-States (Punjab, Rajasthan) | NA | 12/2022 | 06/2030 | 06/2030 | 3207 | 3207 | 339.57 | 24
August 2025 | 418 | Ministry of Petroleum & Natural Gas | Oil & Gas | Augmentation/ Revamping of Dimapur Depot, Dimapur | MinistryofPetroleumNaturalGas | 709786 | Nagaland | NA | 08/2023 | 11/2027 | 11/2027 | 227.62 | 227.62 | 9.12 | 22
August 2025 | 419 | Ministry of Petroleum & Natural Gas | Oil & Gas | Integrated Para Xylene [PX] and Purified Terephthalic Acid [PTA] Project at Paradip Refinery | Ministry of Petroleum & Natural Gas | 604859 | Odisha | NA | 07/2020 | 01/2024 | 08/2026 | 13805 | 11783 | 8310.16 | 90
August 2025 | 420 | Ministry of Petroleum & Natural Gas | Oil & Gas | CUF POL Depot at Sadashibpur [Meramundali], Odisha | MinistryofPetroleumNaturalGas | 709800 | Odisha | NA | 04/2021 | 03/2026 | 03/2026 | 393.54 | 393.54 | 104.55 | 44
August 2025 | 421 | Ministry of Petroleum & Natural Gas | Oil & Gas | Life Extension of 48 well platforms of Mumbai High & Heera Fields | Oil and Natural Gas Corporation Limited [ONGC] | 400119 | Offshore | NA | 12/2015 | 04/2018 | 12/2025 | 3190.69 | 3375.9 | 3074.25 | 89
August 2025 | 422 | Ministry of Petroleum & Natural Gas | Oil & Gas | PRP-VIII [Group-A] | Ministry of Petroleum & Natural Gas | 616950 | Offshore | NA | 09/2024 | 02/2026 | 02/2026 | 1486.4 | 1486.4 | 272.3 | 19
August 2025 | 423 | Ministry of Petroleum & Natural Gas | Oil & Gas | Daman Upside Development Project | Oil and Natural Gas Corporation Limited [ONGC] | 709839 | Offshore | NA | 06/2022 | 10/2025 | 02/2026 | 4144.41 | 6406.9 | 3894.53 | 85
August 2025 | 424 | Ministry of Petroleum & Natural Gas | Oil & Gas | MHN TCPP PGC BGC Project [MTPBP] | Ministry of Petroleum & Natural Gas | 709848 | Offshore | NA | 06/2022 | 05/2026 | 05/2026 | 2329.45 | 2354.23 | 820.24 | 53
August 2025 | 425 | Ministry of Petroleum & Natural Gas | Oil & Gas | PRP-VIII Group B [NH & BS Asset] | Ministry of Petroleum & Natural Gas | 709849 | Offshore | NA | 06/2024 | 02/2026 | 02/2026 | 2379.84 | 3165.53 | 1675.65 | 62
August 2025 | 426 | Ministry of Petroleum & Natural Gas | Oil & Gas | Integrated Development of 4 Contract Areas under DSF-II | Ministry of Petroleum & Natural Gas | 709851 | Offshore | NA | 05/2023 | 04/2027 | 04/2027 | 6183.79 | 6183.79 | 474 | 20
August 2025 | 427 | Ministry of Petroleum & Natural Gas | Oil & Gas | 2G Ethanol Biorefinery at Bathinda | Hindustan Petroleum Corporation Limited [HPCL] | 400171 | Punjab | NA | 05/2020 | 02/2023 | 03/2026 | 1421.46 | 1421.46 | 1182.4 | 95
August 2025 | 428 | Ministry of Petroleum & Natural Gas | Oil & Gas | Bathinda Sangrur Pipeline | Ministry of Petroleum and Natural Gas | 612998 | Punjab | NA | 11/2021 | 05/2024 | 09/2025 | 367 | 397 | 346.18 | 93
August 2025 | 429 | Ministry of Petroleum & Natural Gas | Oil & Gas | City Gas Distribution Project at Pathankot District | MinistryofPetroleumNaturalGas | 709770 | Punjab | NA | 03/2022 | 09/2033 | 09/2033 | 151 | 151 | 8.73 | 2
August 2025 | 430 | Ministry of Petroleum & Natural Gas | Oil & Gas | CBR 9 MMTPA Project | Chennai Petroleum Corporation Limited [CPCL] | 604795 | Tamil Nadu | NA | 09/2021 | 06/2025 | 10/2028 | 31580 | 36354 | 1342.27 | 10
August 2025 | 431 | Ministry of Petroleum & Natural Gas | Oil & Gas | Laying of new 28 inch Desal Water Pipeline and 10 inch Reject Water Pipeline between CPCL Manali Refinery and CPCL Desalination plant at Ennore | Chennai Petroleum Corporation Limited [CPCL] | 709750 | Tamil Nadu | NA | 01/2024 | 09/2025 | 12/2025 | 205 | 205 | 38.14 | 42
August 2025 | 432 | Ministry of Petroleum & Natural Gas | Oil & Gas | City Gas Distribution Projects at the Nilgiris and Erode districts | Bharat Petroleum Corporation Limited [BPCL] | 709796 | Tamil Nadu | NA | 12/2022 | 03/2030 | 03/2030 | 3685 | 3685 | 226.87 | 17
August 2025 | 433 | Ministry of Petroleum & Natural Gas | Oil & Gas | Creation of Gas Dehydration Facilities, Tripura Asset | Oil and Natural Gas Corporation Limited [ONGC] | 709837 | Tripura | NA | 03/2022 | 05/2024 | 12/2025 | 209.33 | 131.51 | 68.88 | 62
August 2025 | 434 | Ministry of Petroleum & Natural Gas | Oil & Gas | PP Project, Pata | Gas Authority of India Limited [GAIL] | 400161 | Uttar Pradesh | NA | 03/2019 | 01/2024 | 09/2025 | 910.56 | 1299.02 | 1019 | 97
August 2025 | 435 | Ministry of Petroleum & Natural Gas | Oil & Gas | Revamping / Augmentation of Facilities at Mathura Bitumen Plant | MinistryofPetroleumNaturalGas | 709781 | Uttar Pradesh | NA | 04/2022 | 06/2027 | 12/2026 | 260.12 | 260.12 | 1.11 | 26
August 2025 | 436 | Ministry of Petroleum & Natural Gas | Oil & Gas | City Gas Distribution Projects at Lakhimpur Kheri , Sitapur, Bahraich, Shravasti,Balrampur, Siddharth Nagar & Maharajganj districts | Bharat Petroleum Corporation Limited [BPCL] | 709795 | Uttar Pradesh | NA | 12/2022 | 06/2030 | 06/2030 | 16654 | 16654 | 558.33 | 11
August 2025 | 437 | Ministry of Petroleum & Natural Gas | Oil & Gas | Durgapur - Haldia Pipeline [Section-3B of JHBDPL Project] | Ministry of Petroleum & Natural Gas | 617302 | West Bengal | NA | 03/2017 | 12/2020 | 12/2025 | 1740 | 2493.15 | 2239.7 | 90
August 2025 | 438 | Ministry of Petroleum & Natural Gas | Oil & Gas | Haldia Panagarh Pipeline Project | Hindustan Petroleum Corporation Limited | 709753 | West Bengal | NA | 11/2022 | 11/2025 | 11/2025 | 1010 | 1010 | 645.07 | 82
August 2025 | 439 | Ministry of Petroleum & Natural Gas | Oil & Gas | CGD Project in Malda, Birbhum, Murshidabad, Dakshin Dinajpur GA ID 11A.03 | Hindustan Petroleum Corporation Limited | 709758 | West Bengal | NA | 06/2022 | 06/2030 | 06/2030 | 2628 | 2628 | 335.96 | 27
August 2025 | 440 | Ministry of Petroleum & Natural Gas | Oil & Gas | City Gas Distribution Project at East Mednipore, West Mednipore & Jhargram Districts | MinistryofPetroleumNaturalGas | 709772 | West Bengal | NA | 03/2022 | 06/2031 | 06/2031 | 609 | 609 | 56.35 | 2
August 2025 | 441 | Ministry of Petroleum & Natural Gas | Oil & Gas | City Gas Distribution Projects at Alipurduar and Cooch Behar | Bharat Petroleum Corporation Limited [BPCL] | 709791 | West Bengal | NA | 12/2022 | 03/2030 | 03/2030 | 1017 | 1017 | 184.13 | 39
August 2025 | 442 | Ministry of Health & Family Welfare | Healthcare | AIIMS Majra Rewari Haryana | Ministry of Health & Family Welfare | 701173 | Haryana | NA | 02/2019 | 02/2023 | 12/2026 | 1299 | 1299 | 349.41 | 28
August 2025 | 443 | Ministry of Health & Family Welfare | Healthcare | AIIMS Kashmir at Awantipora Jammu & Kashmir | Central Public Works Department [CPWD] | 701167 | Jammu and Kashmir | 01/2019 | 01/2019 | 01/2025 | 12/2025 | 1828 | 1828 | 1531.86 | 66
August 2025 | 444 | Ministry of Health & Family Welfare | Healthcare | AIIMS Bibinagar | Ministry of Health & Family Welfare | 701171 | Telangana | 12/2018 | 12/2018 | 09/2022 | 12/2025 | 1028 | 1365.95 | 812.95 | 84
August 2025 | 445 | Ministry of Ports, Shipping and Waterways | Healthcare | Establishment of 600 bed super specialty hospital with optional development of Medical college and further expansion on PPP basis. | Mumbai Port Trust [MPT] | 708662 | Maharashtra | 08/2019 | 01/2022 | 06/2026 | 12/2027 | 693 | 693 | 58 | 0
August 2025 | 446 | Ministry of Ports, Shipping and Waterways | Inland Waterways | Development of Container Terminal at Tuna-Tekra, Deendayal Port on BOT Basis Under PPP Mode | Deendayal Port Trust [DPT] | 609424 | Gujarat | NA | 12/2023 | 12/2026 | - | 4243.64 | 4243.64 | 366.2 | 10
August 2025 | 447 | Ministry of Ports, Shipping and Waterways | Inland Waterways | Jal Marg Vikas Project | Inland Waterways Authority of India [IWAI] | 701565 | Multi-States (Bihar, Jharkhand, Uttar Pradesh, West Bengal) | 01/2018 | 02/2018 | 12/2023 | 12/2025 | 5369.18 | 5061.15 | 3510.72 | 71
August 2025 | 448 | Ministry of Ports, Shipping and Waterways | Shipping | Setting up of a Floating Storage and Regasification Unit [FSRU] - Mumbai | Mumbai Port Trust [MPT] | 701586 | Maharashtra | NA | 04/2021 | 11/2026 | 11/2026 | 900 | 900 | 65 | 0
August 2025 | 449 | Ministry of Ports, Shipping and Waterways | Shipping | Operationalization of Coastal Berth & Shallow Water Berth through PPP | Jawaharlal Nehru Port Authority [JNPA] | 708655 | Maharashtra | NA | 07/2021 | 01/2026 | - | 366.8 | 366.8 | 376.86 | 25
August 2025 | 450 | Ministry of Ports, Shipping and Waterways | Shipping | Deepening and Optimization of Inner Harbour facilities including development of Western Dock on BOT basis to handle Cape size vessels | Paradip Port Trust [PPT] | 701574 | Odisha | 05/2022 | 01/2023 | 12/2027 | 10/2028 | 3004.63 | 3004.63 | 1149.79 | 40
August 2025 | 451 | Ministry of Ports, Shipping and Waterways | Shipping | Berth No. 2 [previously Berth 3] of HDC Mechanization Project | Haldia Dock Complex, Syama Prasad Mookerjee Port Authority | 701576 | West Bengal | NA | 03/2023 | 09/2025 | 01/2026 | 298.26 | 298.26 | 420 | 91
August 2025 | 452 | Ministry of Ports, Shipping and Waterways | Shipping | Shalukkhali Liquid Cargo Handling Facility Development Project | Haldia Dock Complex, Syama Prasad Mookerjee Port Authority | 701577 | West Bengal | NA | 08/2022 | 08/2025 | - | 253.65 | 253.65 | 9.28 | 0
August 2025 | 453 | Ministry of Ports, Shipping and Waterways | Tourism, Hospitality & Wellness | National Maritime Heritage Complex [NMHC] Phase-I | Indian Port Rail & Ropeway Corporation Ltd. [IPRCL] | 707215 | Gujarat | 02/2019 | 01/2022 | 03/2024 | 09/2025 | 573 | 1238.05 | 496.63 | 66
August 2025 | 454 | Ministry of Steel | Metals & Mining | Capacity expansion of Deposit-14 and 14 NMZ at Kirandul | National Mineral Development Corporation Limited [NMDC] | 615202 | Chhattisgarh | 08/2021 | 07/2022 | 12/2028 | 03/2028 | 1700 | 1756.2 | 65.44 | 3
August 2025 | 455 | Ministry of Steel | Steel | Replacement of Hot Leveller No.1 of Plate Mill at Bhilai Steel Plant | Steel Authority of India Limited [SAIL] | 617243 | Chhattisgarh | 07/2024 | 08/2024 | 07/2026 | - | 198.62 | 198.62 | 10.9 | 10
August 2025 | 456 | Ministry of Steel | Steel | Replacement of Converter Vessels, Trunnion Rings, Support System & Installation of Secondary Emission at Bhilai Steel Plant | Steel Authority of India Limited [SAIL] | 617255 | Chhattisgarh | NA | 12/2023 | 06/2026 | - | 471.83 | 471.83 | 130.66 | 40
August 2025 | 457 | Ministry of Steel | Steel | Rebuilding of Coke Oven Battery No.7 & 8 at Bhilai Steel Plant | Steel Authority of India Limited [SAIL] | 617256 | Chhattisgarh | NA | 01/2024 | 10/2025 | - | 884.1 | 884.1 | 466.31 | 77
August 2025 | 458 | Ministry of Steel | Steel | NMDC Slurry Pipeline Project Phase-1 | National Mineral Development Corporation Limited [NMDC] | 706811 | Chhattisgarh | 11/2015 | 09/2020 | 06/2023 | 12/2025 | 2907 | 5427 | 3038.85 | 85
August 2025 | 459 | Ministry of Steel | Steel | SCREENING PLANT-III AT KIRANDUL | National Mineral Development Corporation Limited [NMDC] | 709826 | Chhattisgarh | NA | 10/2021 | 01/2026 | - | 2718.84 | 2718.84 | 1341.08 | 72
August 2025 | 460 | Ministry of Steel | Steel | CONSTRUCTION OF RESIDENTIAL TOWERS AT BIOM KIRANDUL COMPLEX | National Mineral Development Corporation Limited [NMDC] | 709827 | Chhattisgarh | NA | 10/2022 | 12/2025 | - | 349.75 | 349.75 | 282.52 | 88
August 2025 | 461 | Ministry of Steel | Steel | New Sinter Plant at BSL, SAIL | Steel Authority of India Limited [SAIL] | 400174 | Jharkhand | 03/2015 | 05/2015 | 10/2017 | 06/2027 | 1034.01 | 1752.3 | 883.44 | 51
August 2025 | 462 | Ministry of Steel | Steel | Replacement of existing Grinders in CRM-I & II at Bokaro Steel Plant | Steel Authority of India Limited [SAIL] | 617249 | Jharkhand | 01/2025 | 02/2025 | 01/2027 | - | 211.94 | 211.94 | 15.04 | 10
August 2025 | 463 | Ministry of Steel | Steel | Secondary Emission Control in Converters of SMS-II at Bokaro Steel Plant | Steel Authority of India Limited [SAIL] | 617250 | Jharkhand | NA | 02/2025 | 10/2026 | - | 207.13 | 207.13 | 15.76 | 8
August 2025 | 464 | Ministry of Steel | Steel | Revamping of old sub-systems of Blast Furnace 3 at Bokaro Steel Plant | Steel Authority of India Limited [SAIL] | 617253 | Jharkhand | 09/2023 | 10/2023 | 07/2025 | 11/2025 | 513.82 | 513.82 | 234.54 | 71
August 2025 | 465 | Ministry of Steel | Steel | Replacement of remaining 04 sets of Battery Cyclones with 04 Nos. of ESPs in Sinter Plant-1 at Bokaro Steel Plant | Steel Authority of India Limited [SAIL] | 617254 | Jharkhand | NA | 04/2024 | 06/2026 | - | 260.37 | 260.37 | 44.25 | 22
August 2025 | 466 | Ministry of Steel | Steel | Rebuilding of Coke Oven Battery No.6 at Bokaro Steel Plant | Steel Authority of India Limited [SAIL] | 617257 | Jharkhand | NA | 12/2023 | 11/2026 | - | 627.31 | 627.31 | 91.96 | 38
August 2025 | 467 | Ministry of Steel | Steel | Construction of Screening Plant-II for Donimalai and Kumaraswamy Iron Ore Mining Complex of NMDC Limited at Ballari Dt, Karnataka. | National Mineral Development Corporation Limited [NMDC] | 400121 | Karnataka | 11/2014 | 06/2024 | 08/2026 | - | 1043.63 | 1043.63 | 229.77 | 29
August 2025 | 468 | Ministry of Steel | Steel | Installation of 4th Slab Caster along with its Auxiliaries and a New Ladle Furnace in SMS-II at Rourkela Steel Plant | Steel Authority of India Limited [SAIL] | 400065 | Odisha | 01/2022 | 02/2022 | 05/2025 | 09/2025 | 1105.23 | 1105.23 | 769.08 | 97
August 2025 | 469 | Ministry of Steel | Steel | Rebuilding of COB 4 at Durgapur Steel Plant | Steel Authority of India Limited [SAIL] | 612781 | West Bengal | 11/2023 | 12/2023 | 12/2026 | - | 916.78 | 916.78 | 126.25 | 14
August 2025 | 470 | Ministry of Steel | Steel | Installation of New Bar Mill at Durgapur Steel Plant | Steel Authority of India Limited [SAIL] | 617242 | West Bengal | 09/2024 | 10/2024 | 06/2027 | - | 2115.44 | 2115.44 | 209.11 | 27
August 2025 | 471 | Ministry of Steel | Steel | Up-gradation of Blast Furnace No. 3 at Durgapur Steel Plant | Steel Authority of India Limited [SAIL] | 617246 | West Bengal | 09/2024 | 10/2024 | 06/2026 | - | 758.09 | 758.09 | 63.81 | 4
August 2025 | 472 | Ministry of Steel | Steel | Third Ladle Furnace in Secondary Refinery Unit at IISCO Steel Plant | Steel Authority of India Limited [SAIL] | 617248 | West Bengal | NA | 12/2024 | 07/2026 | - | 227.96 | 227.96 | 16.24 | 29
August 2025 | 473 | Ministry of Steel | Steel | Revamping of Air Pollution Control Systems of SP-1 at Durgapur Steel Plant | Steel Authority of India Limited [SAIL] | 617251 | West Bengal | 11/2024 | 12/2024 | 05/2026 | - | 196.4 | 196.4 | 0.19 | 3
August 2025 | 474 | Ministry of Railways | Railways | Nadikudi - Srikalahasti New Line | South Central Railway [SCR] - II | 400298 | Andhra Pradesh | 03/2012 | 12/2016 | 05/2027 | 03/2028 | 2312 | 5200 | 2179 | 54
August 2025 | 475 | Ministry of Railways | Railways | Malugur- Palasamudram New Line Project [17.975 Km] | South Western Railway [SWR] - II | 611615 | Andhra Pradesh | 09/2022 | 11/2025 | 11/2027 | 12/2027 | 342 | 342.14 | 0 | 0
August 2025 | 476 | Ministry of Railways | Railways | GOOTY-PENDEKALLU DOUBLING 29.225 Km | South Central Railway [SCR] - II | 611752 | Andhra Pradesh | 03/2023 | 06/2023 | 03/2027 | 03/2027 | 351.83 | 351.83 | 18 | 25
August 2025 | 477 | Ministry of Railways | Railways | GUNTAKAL WEST-MALLAPPA GATE RAIL OVER RAIL - ROR TRACK | South Central Railway [SCR] - II | 611754 | Andhra Pradesh | NA | 07/2023 | 07/2026 | - | 293.3 | 293.3 | 0 | 0
August 2025 | 478 | Ministry of Railways | Railways | Kurnool - Setting up facilities for coach midlife rehabilitation workshop | WPO/Patna | 611927 | Andhra Pradesh | 01/2014 | 10/2017 | 12/2023 | - | 560.72 | 560.72 | 276.66 | 65
August 2025 | 479 | Ministry of Railways | Railways | Flyover between Pendurthi and Simhachalam North to avoid surface crossing at Simhachalam 7.135 km PB 73 of 2023 24 NR | East Coast Railway [ECoR] - II | 612827 | Andhra Pradesh | NA | 05/2024 | 04/2027 | - | 183.65 | 183.65 | 4.2 | 11
August 2025 | 480 | Ministry of Railways | Railways | 3rd & 4th line between Vadlapudi -Gate Jn. cabin and Tie line between Gate Junction to Gangavaram port | East Coast Railway [ECoR] - II | 616697 | Andhra Pradesh | NA | 03/2024 | 06/2026 | - | 154.28 | 154.28 | 10.98 | 16
August 2025 | 481 | Ministry of Railways | Railways | Tiupati Katpadi 104.39 kms | South Central Railway [SCR] - II | 617210 | Andhra Pradesh | 04/2025 | 04/2025 | 03/2029 | - | 1215.56 | 1215.56 | 0 | 0
August 2025 | 482 | Ministry of Railways | Railways | 3rd Line between Gudur Renigunta 83.17 Km | South Central Railway [SCR] - II | 617216 | Andhra Pradesh | 10/2024 | 10/2024 | 03/2027 | - | 877.34 | 877.34 | 2.97 | 0
August 2025 | 483 | Ministry of Railways | Railways | Kurnool Coach Midlife Rehabilitation Project | WPO/Patna | 705253 | Andhra Pradesh | NA | 07/2014 | 12/2020 | - | 563 | 563 | 120 | 0
August 2025 | 484 | Ministry of Railways | Railways | Kotapalli - Narasapur New Line | South Central Railway [SCR] - II | 705436 | Andhra Pradesh | 03/2009 | 09/2013 | 03/2028 | 03/2028 | 2501 | 2501 | 1303.41 | 29
August 2025 | 485 | Ministry of Railways | Railways | Guntur-Guntakal Doubling Project | South Central Railway [SCR] - II | 705633 | Andhra Pradesh | 03/2017 | 11/2017 | 12/2025 | 12/2026 | 3733 | 4295 | 4213.01 | 92
August 2025 | 486 | Ministry of Railways | Railways | Vijaywada-Gudur 3rd Line | RVNL - II | 705648 | Andhra Pradesh | 08/2016 | 04/2018 | 11/2024 | 12/2025 | 6654 | 6654 | 5922 | 90
August 2025 | 487 | Ministry of Railways | Railways | Penukonda - Dharmavaram Doubling Project [41.5 Km] | South Western Railway [SWR] - II | 705789 | Andhra Pradesh | 04/2019 | 12/2018 | 03/2026 | 03/2026 | 307.66 | 307.66 | 270.52 | 61
August 2025 | 488 | Ministry of Railways | Railways | Doubling of New Bonggigaon to Kamakhya via Goalpara - 176 km | Northeast Frontier Railway [NFR] | 705572 | Assam | 09/2016 | 09/2016 | 03/2026 | 03/2026 | 4060 | 4961 | 3683.75 | 93
August 2025 | 489 | Ministry of Railways | Railways | Guwahati-Dibrugarh via Tinsukia & Simaluguri-Dibrugarh | Central Organisation for Railway Electrification [CORE] | 706922 | Assam | 09/2020 | 09/2018 | 09/2020 | 06/2024 | 890.36 | 889.36 | 391.73 | 89
August 2025 | 490 | Ministry of Railways | Railways | Mariani-Jorhat, Tinsukia-Dangri and Makum -TirapTrack Electrification Project | GM/C/ NFR | 706940 | Assam | NA | 01/2022 | 05/2024 | - | 183.99 | 183.99 | 0 | 0
August 2025 | 491 | Ministry of Railways | Railways | Harmuty-Murkongselek Branch Line Electrification Project | GM/C/ NFR | 706942 | Assam | NA | 01/2022 | 05/2024 | - | 237.52 | 237.52 | 0 | 0
August 2025 | 492 | Ministry of Railways | Railways | Sakri -Hasanpur [via Harnagar - Kusheshwar Asthan] New Railway line | East Central Railway [ECR] - I | 400254 | Bihar | 12/2023 | 08/1997 | 12/2024 | 03/2027 | 735.2 | 735.2 | 585.84 | 82
August 2025 | 493 | Ministry of Railways | Railways | Khagaria-Kusheshwar Asthan [42Km] new line project | East Central Railway [ECR] - I | 705364 | Bihar | 04/2019 | 12/1998 | 12/2024 | 03/2027 | 614 | 1384 | 484.29 | 55
August 2025 | 494 | Ministry of Railways | Railways | Hajipur-Sagauli New line | East Central Railway [ECR] - I | 705366 | Bihar | 10/2007 | 10/2004 | 03/2020 | 12/2026 | 2067 | 2087 | 1968.45 | 74
August 2025 | 495 | Ministry of Railways | Railways | Araria Supaul New BG Line | East Central Railway [ECR] - I | 705368 | Bihar | 06/2018 | 03/2009 | 03/2024 | 01/2027 | 1605 | 2514 | 1490.2 | 35
August 2025 | 496 | Ministry of Railways | Railways | Fatuha-Islampur incl. MM for extn.of NL from Neora to Daniawan , Daniawan to Biharsharif, Biharsharif to Barbigha , Barbigha to Shekhpura | East Central Railway [ECR] - I | 705373 | Bihar | 08/2002 | 03/2002 | 03/2023 | 08/2025 | 1473 | 2882 | 2522.41 | 94
August 2025 | 497 | Ministry of Railways | Railways | Jogbani-Biratnagar New Rail Line project | Indian Railway Construction International Limited [IRCON] | 705450 | Bihar | 06/2010 | 01/2011 | 03/2022 | 12/2026 | 402 | 486 | 367.54 | 86
August 2025 | 498 | Ministry of Railways | Railways | Samastipur-Darbhanga Doubling Railway Project | East Central Railway [ECR] - I | 705526 | Bihar | NA | 12/2015 | 03/2025 | 10/2025 | 519 | 519 | 344.23 | 84
August 2025 | 499 | Ministry of Railways | Railways | Sagauli-Valmiknagar | East Central Railway [ECR] - I | 705527 | Bihar | 03/2018 | 03/2017 | 12/2025 | 12/2025 | 1216 | 2222 | 2044.54 | 91
August 2025 | 500 | Ministry of Railways | Railways | Muzaffarpur-Sugauli | East Central Railway [ECR] - I | 705528 | Bihar | 03/2018 | 03/2017 | 06/2024 | 08/2025 | 1586 | 1586 | 1463.45 | 99
August 2025 | 501 | Ministry of Railways | Railways | Rampur Dumra-Tal-Rajendrapul Additional Bridge and Railway Line Doubling | Indian Railway Construction International Limited [IRCON] | 706759 | Bihar | 03/2016 | 05/2017 | 12/2024 | 12/2025 | 2373.64 | 1700.24 | 1402.95 | 95
August 2025 | 502 | Ministry of Railways | Railways | Barauni-Bachwara [16 km] - 3rd & 4th line incl. Barauni yard remodelling [32 km] | East Central Railway [ECR] - I | 706860 | Bihar | 10/2022 | 08/2025 | 08/2025 | 10/2026 | 645 | 645 | 0.77 | 55
August 2025 | 503 | Ministry of Railways | Railways | Kharsia-Dharamjaygarh with Spur line [East Corridor-Phase 1] | Indian Railway Construction International Limited [IRCON] | 400220 | Chhattisgarh | 03/2016 | 01/2014 | 09/2018 | 03/2026 | 3055 | 3438 | 2574.54 | 94
August 2025 | 504 | Ministry of Railways | Railways | Doubling of Kirandul-Jagdalpur Line [150 km] | East Coast Railway [ECoR] - II | 400291 | Chhattisgarh | 02/2013 | 03/2013 | 03/2020 | 12/2025 | 1589 | 1798 | 1542.79 | 92
August 2025 | 505 | Ministry of Railways | Railways | Gauge Conversion of Kendri-Dhamtari including Abhanpur - Rajim Branch line 67.20 Kms - 2nd Material Modification to Raipur Titlagarh doubling. | SECR | 602792 | Chhattisgarh | 07/2011 | 05/2021 | 02/2025 | 11/2025 | 1171 | 1171 | 848 | 82
August 2025 | 506 | Ministry of Railways | Railways | 4th line between Nipania Bhatapara 14.4 Km | South East Central Railway [SECR] - II | 612815 | Chhattisgarh | NA | 05/2024 | 03/2027 | - | 170.49 | 170.49 | 0 | 0
August 2025 | 507 | Ministry of Railways | Railways | Dharamjaigarh-Korba 63 km | CERL | 613003 | Chhattisgarh | NA | 07/2022 | 08/2026 | - | 1686.26 | 1686.26 | 288.83 | 18.5
August 2025 | 508 | Ministry of Railways | Railways | KHARSIA- NAYA RAIPUR-PARMALKASA 5th and 6th Line [278KM] | CAO/C/SECR | 617200 | Chhattisgarh | 04/2025 | 04/2025 | 03/2031 | - | 7853.84 | 7853.84 | 0 | 0
August 2025 | 509 | Ministry of Railways | Railways | Dallirajhra- Rowghat New Railway Line - Phase I [95 km] | RVNL - II | 705433 | Chhattisgarh | 07/2009 | 12/2009 | 09/2025 | 12/2025 | 1628 | 1628 | 1440.85 | 82
August 2025 | 510 | Ministry of Railways | Railways | Gevra Road-Pendra Road New Railway Line [135 km] | Indian Railway Construction International Limited [IRCON] | 705444 | Chhattisgarh | NA | 04/2014 | 03/2022 | 12/2025 | 4970 | 4970 | 4346.55 | 73
August 2025 | 511 | Ministry of Railways | Railways | Chirimiri-Nagpur Halt New Railway Line Project | South East Central Railway [SECR] - II | 705756 | Chhattisgarh | 10/2018 | 06/2020 | 06/2030 | 06/2030 | 241 | 656.52 | 71 | 0
August 2025 | 512 | Ministry of Railways | Railways | Boridand - Ambikapur Doubling Line Project | South East Central Railway [SECR] - II | 706854 | Chhattisgarh | 06/2022 | 04/2022 | 06/2030 | 06/2030 | 1376 | 1576.23 | 218 | 18
August 2025 | 513 | Ministry of Railways | Railways | NIPANIA-BHATAPRA [14.4 KM] 4TH LINE [PB-72/NR/2022-23] | SECR | 709814 | Chhattisgarh | NA | 05/2024 | 12/2026 | 12/2026 | 170 | 184 | 0 | 0
August 2025 | 514 | Ministry of Railways | Railways | 4TH LINE - BHATAPARA-HATHBAND [8.8 KM] [PB-72/NR/2022-23] | SECR | 709815 | Chhattisgarh | NA | 05/2024 | 01/2027 | 12/2027 | 177.03 | 177.03 | 0 | 2
August 2025 | 515 | Ministry of Railways | Railways | 4TH LINE - BHILAI-BHILAI NAGAR [8.8 KM] [PB-72/NR/2022-23] | SECR | 709816 | Chhattisgarh | NA | 05/2024 | 02/2027 | 02/2027 | 177.34 | 177.34 | 1.16 | 2
August 2025 | 516 | Ministry of Railways | Railways | 4TH LINE - DADHAPARA-BELHA [9.2 KM] [PB-72/NR/2022-23] | SECR | 709817 | Chhattisgarh | NA | 05/2024 | 11/2026 | 11/2026 | 169.06 | 169.06 | 14.42 | 60
August 2025 | 517 | Ministry of Railways | Railways | 4TH LINE RAJNANDGAON-DONGARHGARH [31.2 KM] [PB-72/NR/2022-23] | SECR | 709818 | Chhattisgarh | NA | 05/2024 | 01/2027 | 01/2027 | 328.34 | 328.34 | 50.58 | 25
August 2025 | 518 | Ministry of Railways | Railways | 3RD AND 4TH LINE - SARAGBUNDIA AND MADWARANI | SECR | 709819 | Chhattisgarh | 09/2022 | 05/2025 | 12/2026 | 12/2026 | 167.64 | 167.64 | 0 | 2
August 2025 | 519 | Ministry of Railways | Railways | Redevelopment of New Delhi Railway Station and construction of associated infrastructure | Ministry of Railways | 613785 | Delhi | 01/2023 | 06/2024 | 12/2028 | - | 4744 | 4744 | 35.09 | 0
August 2025 | 520 | Ministry of Railways | Railways | North Region Video Surveillance Project | RCIL | 705298 | Delhi | NA | 04/2023 | 03/2024 | - | 274.39 | 274.39 | 0 | 0
August 2025 | 521 | Ministry of Railways | Railways | Anand Vihar-Tilak Bridge 3rd & 4th line | CAO/C/NR | 705583 | Delhi | 03/2013 | 03/2013 | 03/2023 | 12/2027 | 667 | 667 | 285.44 | 62
August 2025 | 522 | Ministry of Railways | Railways | Provision of Work-site Tampers [WST] Railway Project | EDTK[MC]/RB | 705694 | Delhi | NA | 01/2016 | 12/2023 | 01/2026 | 187.72 | 187.72 | 141.91 | 100
August 2025 | 523 | Ministry of Railways | Railways | WST Machine Procurement Project | EDTK[MC]/RB | 705708 | Delhi | NA | 06/2018 | 03/2024 | 12/2027 | 176 | 176 | 0 | 0
August 2025 | 524 | Ministry of Railways | Railways | PCT Machine Procurement Project | EDTK[MC]/RB | 705710 | Delhi | NA | 04/2019 | 04/2024 | 06/2027 | 336 | 336 | 74.32 | 85
August 2025 | 525 | Ministry of Railways | Railways | RBMV Machine Procurement Project | EDTK[MC]/RB | 705712 | Delhi | NA | 10/2019 | 06/2024 | 12/2027 | 480 | 480 | 0.33 | 7
August 2025 | 526 | Ministry of Railways | Railways | SRGM Machine Procurement Project | EDTK[MC]/RB | 705717 | Delhi | NA | 10/2019 | 12/2023 | 03/2026 | 440 | 440 | 390.03 | 90
August 2025 | 527 | Ministry of Railways | Railways | WST Machine Procurement Project | EDTK[MC]/RB | 705720 | Delhi | NA | 12/2019 | 04/2024 | 12/2026 | 384 | 384 | 0 | 0
August 2025 | 528 | Ministry of Railways | Railways | DTS Machine Procurement Project | EDTK[MC]/RB | 705721 | Delhi | NA | 12/2019 | 12/2024 | 12/2026 | 447.6 | 447.6 | 0 | 0
August 2025 | 529 | Ministry of Railways | Railways | BRM Machine Procurement Project | EDTK[MC]/RB | 705722 | Delhi | NA | 09/2019 | 06/2024 | 12/2027 | 210 | 210 | 0.02 | 0
August 2025 | 530 | Ministry of Railways | Railways | Track Machine Procurement Project | EDTK[MC]/RB | 705726 | Delhi | NA | 04/2020 | 03/2025 | 01/2028 | 6339 | 6339 | 4166.47 | 41
August 2025 | 531 | Ministry of Railways | Railways | Kosamba Umarpada 70 Km | PCE/WR | 611918 | Gujarat | NA | 07/2022 | 03/2027 | - | 468 | 468 | 20 | 8
August 2025 | 532 | Ministry of Railways | Railways | Adraj Moti Vijapur 40 Kms | Western Railway [WR] - II | 611937 | Gujarat | 05/2022 | 05/2022 | 05/2026 | 05/2026 | 417.53 | 417.53 | 223 | 86
August 2025 | 533 | Ministry of Railways | Railways | Vijapur Ambliyasan 42 km | PCE/WR | 611938 | Gujarat | 05/2022 | 05/2022 | 05/2026 | 05/2026 | 415.38 | 415.38 | 364 | 96
August 2025 | 534 | Ministry of Railways | Railways | Himatnagar Khedbrahma 55 km | Railway | 611939 | Gujarat | 06/2022 | 04/2017 | 06/2001 | 06/2026 | 482.42 | 482.42 | 461 | 96
August 2025 | 535 | Ministry of Railways | Railways | New broad gauge line between Naliya Jakhau Port 25 Kms | PCE/WR | 611943 | Gujarat | 02/2023 | 02/2023 | 01/2028 | 01/2028 | 410.26 | 410.26 | 6 | 4
August 2025 | 536 | Ministry of Railways | Railways | Quadrupling between Gandhidham Adipur with Y connection at Adipur for providing direct entry towards Mundra Port and Bhuj and high level platform at Gopalpur 11Kms | PCE/WR | 611944 | Gujarat | 02/2023 | 02/2023 | 03/2026 | 03/2026 | 152.44 | 152.44 | 20 | 68
August 2025 | 537 | Ministry of Railways | Railways | Petlad Bhadran 23 Kms | PCE/WR | 611945 | Gujarat | 05/2022 | 05/2022 | 05/2030 | 05/2030 | 307.11 | 307.11 | 82 | 17
August 2025 | 538 | Ministry of Railways | Railways | Choranda Motikoral 18 Kms | PCE/WR | 611969 | Gujarat | NA | 08/2023 | 10/2026 | - | 246 | 246 | 0 | 0
August 2025 | 539 | Ministry of Railways | Railways | Samlaya Timba Road 54 km | PCE/WR | 611970 | Gujarat | 02/2023 | 02/2023 | 03/2030 | 03/2030 | 670.17 | 670.17 | 102 | 12
August 2025 | 540 | Ministry of Railways | Railways | Samni Jambusar 24 km | PCE/WR | 611971 | Gujarat | 05/2022 | 05/2022 | 03/2030 | 03/2030 | 350 | 349.93 | 87 | 31
August 2025 | 541 | Ministry of Railways | Railways | Jambusar Kavi 26 Kms | PCE/WR | 611972 | Gujarat | NA | 04/2023 | 12/2026 | - | 318 | 318 | 0 | 0
August 2025 | 542 | Ministry of Railways | Railways | miyagam karjan Choranda maalsar 37 kms | PCE/WR | 611973 | Gujarat | NA | 06/2023 | 12/2026 | - | 450 | 450 | 0 | 0
August 2025 | 543 | Ministry of Railways | Railways | Western Railway Samakhiali Gandhidham Quadrupiling 53 Kms | PCE/WR | 611974 | Gujarat | 08/2023 | 08/2023 | 12/2026 | - | 1430 | 1430 | 0 | 0
August 2025 | 544 | Ministry of Railways | Railways | Dahod Creation of Infrastructure facilities for 9000 HP Electric locomotives Manufacturing at | PCE/WR | 611977 | Gujarat | NA | 02/2023 | 02/2025 | - | 487 | 487 | 108.69 | 0
August 2025 | 545 | Ministry of Railways | Railways | Dahod Rolling Stock Workshop Provision of Infrastructure for CBS at | PCE/WR | 611978 | Gujarat | NA | 03/2023 | 03/2025 | - | 158 | 158 | 47.31 | 0
August 2025 | 546 | Ministry of Railways | Railways | Sabarmati Setting up of Maintenance Facilities for Train Sets Phase ii | PCE/WR | 611979 | Gujarat | NA | 04/2023 | 06/2025 | - | 250 | 250 | 0 | 0
August 2025 | 547 | Ministry of Railways | Railways | 4th LINE BETWEEN BAREJADI NANDEJ-SANAND-AHMEDABAD BYPASS | Western Railway | 612072 | Gujarat | 02/2023 | 02/2023 | 03/2027 | 03/2027 | 961.67 | 961.67 | 327.53 | 17
August 2025 | 548 | Ministry of Railways | Railways | Redevelopment of Ahmedabad railway station and associated infrastructure on engineering, procurement and construction mode | Ministry of Railways | 613786 | Gujarat | 01/2023 | 11/2023 | 03/2028 | - | 2379 | 2379 | 656.84 | 16
August 2025 | 549 | Ministry of Railways | Railways | Miyagam-Karjan-Dabhoi-Samlaya [GC] | Western Railway [WR] - II | 705458 | Gujarat | 01/2017 | 01/2017 | 03/2021 | 12/2026 | 483.88 | 844.1 | 620.98 | 41
August 2025 | 550 | Ministry of Railways | Railways | Modasa-Shamlaji Road Railway Line Project | SECR | 706757 | Gujarat | 09/2012 | 04/2008 | 03/2025 | 03/2027 | 262 | 262 | 203 | 58
August 2025 | 551 | Ministry of Railways | Railways | Rajkot - Kanalus Doubling Project [111.2 Kms] | Western Railway [WR] - II | 706763 | Gujarat | 10/2021 | 12/2021 | 10/2026 | 10/2026 | 1080.58 | 1080.58 | 787.69 | 76
August 2025 | 552 | Ministry of Railways | Railways | NADIAD-PETLAD [37.26 KM] | Railway | 709812 | Gujarat | NA |  | 06/2030 | 06/2030 | 461.91 | 461.91 | 75 | 7
August 2025 | 553 | Ministry of Railways | Railways | NEW BG LINE INTERSECTION [5 NOS] BETWEEN GERATPUR-SANAND & BOTAD-AHMEDABAD [16.51 KM] [PB#29/NR/202 | SECR | 709813 | Gujarat | NA |  | 10/2027 | 10/2027 | 437.21 | 437.21 | 43 | 15
August 2025 | 554 | Ministry of Railways | Railways | Bhiwani - Dobh Bahali Doubling Project [42.30 Km] | North Western Railway [NWR] | 611884 | Haryana | 02/2023 | 02/2023 | 02/2028 | 02/2028 | 471 | 471 | 191.39 | 59
August 2025 | 555 | Ministry of Railways | Railways | Gomoh - Flyover for DN trains | East Central Railway [ECR] - I | 705765 | Jharkhand | 01/2018 | 01/2018 | 03/2026 | 03/2026 | 686 | 686 | 538.66 | 59
August 2025 | 556 | Ministry of Railways | Railways | Lodhma - Piska - Link Line bypassing Hatia/Ranchi with Y connection | South Eastern Railway [SER] - I | 705785 | Jharkhand | 08/2021 | 03/2019 | 06/2026 | 05/2027 | 473 | 473 | 284.34 | 4
August 2025 | 557 | Ministry of Railways | Railways | Pradhan Kuntha Jn Line Doubling Project | East Central Railway [ECR] - I | 706837 | Jharkhand | 11/2022 | 11/2022 | 11/2027 | 11/2027 | 349.22 | 349.22 | 90.64 | 60
August 2025 | 558 | Ministry of Railways | Railways | Construction of New BG line between Hassan to Belur [27 Km] | South Western Railway [SWR] - II | 400023 | Karnataka | 03/2019 | 12/2025 | 04/2028 | 04/2027 | 749 | 749 | 0 | 0
August 2025 | 559 | Ministry of Railways | Railways | Yeshvanthpur - Channasandra Doubling Project [21.70 Km] | Karnataka Rail Infrastructure Development Company Limited [K-RIDE] | 703585 | Karnataka | NA | 10/2019 | 03/2024 | 08/2025 | 314.1 | 683.57 | 151.11 | 52
August 2025 | 560 | Ministry of Railways | Railways | New Railway Line between Ginigera and Raichur [165.57 km] | South Western Railway [SWR] - II | 705434 | Karnataka | 03/2008 | 05/2009 | 03/2019 | 03/2027 | 2565 | 3034.98 | 2073.98 | 66
August 2025 | 561 | Ministry of Railways | Railways | Gadag-Wadi New Railway Line [257 km] | South Western Railway [SWR] - II | 705490 | Karnataka | 04/2013 | 08/2017 | 03/2027 | 12/2027 | 2842 | 6700 | 1735.22 | 30
August 2025 | 562 | Ministry of Railways | Railways | Kadur - Chickamagalur - Sakleshpur [93km] | South Western Railway [SWR] - II | 705492 | Karnataka | 01/2014 | 11/2016 | 06/2025 | 12/2025 | 825 | 825 | 788.13 | 83
August 2025 | 563 | Ministry of Railways | Railways | Bagalkot-Kudachi New Railway Line [142 km] | South Western Railway [SWR] - II | 705495 | Karnataka | 11/2021 | 11/2012 | 03/2027 | 01/2027 | 1378 | 1649 | 683.48 | 35
August 2025 | 564 | Ministry of Railways | Railways | Tumkur-Chitradurga-Davangere New Rail Line Project [191 km] | South Western Railway [SWR] - II | 705496 | Karnataka | 10/2013 | 01/2017 | 03/2019 | 12/2027 | 1876 | 1876 | 523.07 | 13
August 2025 | 565 | Ministry of Railways | Railways | Bangalore-Whitefield-Bangalore City-Krishnarajapuram [23.08 km] - Quadrupling | South Western Railway [SWR] - II | 705663 | Karnataka | 02/2018 | 06/2022 | 02/2026 | 02/2026 | 493 | 493 | 252.45 | 82
August 2025 | 566 | Ministry of Railways | Railways | SHIMOGA - SHIKARIPURA - RANEBENNUR [96 Km] | South Western Railway [SWR] - II | 705761 | Karnataka | NA | 02/2023 | 12/2027 | 06/2028 | 1454 | 1454 | 69.82 | 11
August 2025 | 567 | Ministry of Railways | Railways | Belgaum-Dharwad via Kittur [73.10Km] | South Western Railway [SWR] - II | 706835 | Karnataka | 09/2020 | 03/2025 | 12/2027 | 03/2029 | 1591 | 1591 | 0.75 | 0
August 2025 | 568 | Ministry of Railways | Railways | Kumbalam-Turavur doubling project [15.59 Km] | Southern Railway [SR] - II | 705638 | Kerala | 04/2023 | 04/2023 | 03/2027 | 03/2027 | 813 | 813 | 292.15 | 15
August 2025 | 569 | Ministry of Railways | Railways | Ernakulam-Kumbalam doubling project [7.71 Km] | SR-ERS | 705639 | Kerala | 04/2023 | 04/2023 | 03/2028 | 03/2028 | 601 | 601 | 283 | 17
August 2025 | 570 | Ministry of Railways | Railways | Lalitpur-Satna, Rewa-Singrauli & Mahoba-Khajuraho | North Central Railway | 705480 | Madhya Pradesh | 01/2007 | 03/1998 | 03/2027 | 12/2027 | 8914 | 8914 | 5013.49 | 72
August 2025 | 571 | Ministry of Railways | Railways | Katni - Bina Third Railway Line [279 km] | West Central Railway WCR I | 705651 | Madhya Pradesh | 06/2016 | 01/2017 | 03/2022 | 12/2025 | 2478.23 | 4127.23 | 3301.89 | 90
August 2025 | 572 | Ministry of Railways | Railways | Satna-Rewa Railway Line Doubling Project | West Central Railway [WCR] - II | 705659 | Madhya Pradesh | 11/2015 | 08/2017 | 03/2026 | 03/2026 | 500 | 584 | 561.38 | 80
August 2025 | 573 | Ministry of Railways | Railways | Doubling of Katni - Singrauli Railway Line [261 km] | Indian Railway Construction International Limited [IRCON] | 705660 | Madhya Pradesh | 03/2016 | 03/2017 | 12/2025 | 12/2025 | 2445 | 4377 | 3201.67 | 100
August 2025 | 574 | Ministry of Railways | Railways | Katni Grade Separator/Bye Pass | Indian Railway Construction International Limited [IRCON] | 705661 | Madhya Pradesh | 03/2016 | 09/2017 | 09/2024 | 03/2026 | 1248 | 1248 | 1587.21 | 94
August 2025 | 575 | Ministry of Railways | Railways | Indore - Budni New Railway Line [198 kms] | RVNL - II | 705763 | Madhya Pradesh | 08/2019 | 10/2020 | 09/2030 | 09/2030 | 7474 | 7474 | 1685.25 | 23
August 2025 | 576 | Ministry of Railways | Railways | Nimach-Ratlam Doubling [133 Km] | Western Railway [WR] - II | 705933 | Madhya Pradesh | 10/2021 | 10/2021 | 10/2027 | 10/2027 | 1095.88 | 1095.88 | 1067.49 | 89
August 2025 | 577 | Ministry of Railways | Railways | DHULE [BORVIHIR] - NARDANA NEW LINE [50.60 KMS] | CR | 400019 | Maharashtra | 01/2019 | 04/2023 | 12/2026 | 09/2027 | 492.76 | 1170.83 | 245.11 | 16
August 2025 | 578 | Ministry of Railways | Railways | Wardha-Nanded Via Yavatmal New BG Line | Central Railway [CR] - II | 400271 | Maharashtra | 12/2017 | 04/2008 | 03/2028 | 03/2028 | 3445 | 3445 | 3002.93 | 50
August 2025 | 579 | Ministry of Railways | Railways | AURANGABAD-ANKAI - DOUBLING PROJECT 98.25 Km | South Central Railway [SCR] - II | 611751 | Maharashtra | 05/2023 | 05/2023 | 03/2027 | - | 960.64 | 960.64 | 0 | 0.01
August 2025 | 580 | Ministry of Railways | Railways | Western Railway Vasai bypass double line between Naigaon Juchandra 6 km | PCE/WR | 611975 | Maharashtra | NA | 07/2023 | 03/2026 | - | 176 | 176 | 0 | 0
August 2025 | 581 | Ministry of Railways | Railways | Jogeshwari AT Development of JOS-AT as Trainset Maintenance Depot for energy efficient Vande Bharat Sleeper Trains | PCE/WR | 611976 | Maharashtra | NA | 06/2023 | 10/2025 | - | 221 | 221 | 0 | 0
August 2025 | 582 | Ministry of Railways | Railways | Redevelopment of Chhatrapati Shivaji Maharaj Terminus [CSMT] and construction of associated infrastructure | Ministry of Railways | 613015 | Maharashtra | 04/2023 | 07/2023 | 03/2027 | - | 1813 | 1813 | 569.08 | 13
August 2025 | 583 | Ministry of Railways | Railways | Gondia-Balharshah [Chanda Fort] Doubling [240 Km] | South East Central Railway | 617201 | Maharashtra | 04/2025 | 04/2025 | 04/2030 | - | 4373.04 | 4373.04 | 0 | 0
August 2025 | 584 | Ministry of Railways | Railways | Doubling between Parbhani Parli Vaijanath stations 64.71 Km | South Central Railway [SCR] - II | 617215 | Maharashtra | 12/2023 | 12/2023 | 03/2028 | - | 769.93 | 769.93 | 0 | 0
August 2025 | 585 | Ministry of Railways | Railways | Western Region Video Surveillance Project | RCIL | 705300 | Maharashtra | NA | 04/2023 | 12/2023 | - | 227.59 | 227.59 | 0 | 0
August 2025 | 586 | Ministry of Railways | Railways | Ahmednagar - Beed - Parli - Vaijnath New Broad Gauge Line Railway Project [261.3 km] | Central Railways | 705356 | Maharashtra | 01/1999 | 10/2002 | 03/2026 | 03/2026 | 2538.67 | 4957.27 | 4975.74 | 98
August 2025 | 587 | Ministry of Railways | Railways | Baramati Lonand New Line Project | Central Railway [CR] - II | 705357 | Maharashtra | 03/2016 | 03/1999 | 03/2027 | 03/2027 | 138.48 | 1843.9 | 735.33 | 51
August 2025 | 588 | Ministry of Railways | Railways | Wadsa-Gadchiroli | South East Central Railway | 705479 | Maharashtra | 05/2017 | 03/2012 | 03/2027 | 03/2027 | 1886 | 1886 | 925.28 | 50
August 2025 | 589 | Ministry of Railways | Railways | 3rd Line Kalyan - Kasara [67.35 Kilometres] | Central Railway [CR] - II | 705498 | Maharashtra | 09/2015 | 09/2015 | 12/2026 | 12/2026 | 792.89 | 1395.79 | 899.47 | 51
August 2025 | 590 | Ministry of Railways | Railways | 3rd Line Wardha - Sewagram - Nagpur | Central Railway [CR] - II | 705500 | Maharashtra | 09/2015 | 05/2016 | 12/2025 | 12/2025 | 540.02 | 944.24 | 754.27 | 81
August 2025 | 591 | Ministry of Railways | Railways | 3rd Line Wardha - Ballarshah [132 Kilometres] | Central Railway [CR] - II | 705502 | Maharashtra | 03/2016 | 12/2016 | 12/2025 | 02/2026 | 1384.72 | 2033.59 | 1655.88 | 68
August 2025 | 592 | Ministry of Railways | Railways | Pune - Miraj-Londa [467 Kilometres] | Central Railway [CR] - II | 705503 | Maharashtra | 06/2016 | 06/2016 | 02/2025 | 08/2025 | 4027.53 | 4872.52 | 4833.04 | 85
August 2025 | 593 | Ministry of Railways | Railways | Doubling of Daund Manmad Line [247.6 km] | Central Railway [CR] - II | 705504 | Maharashtra | 10/2017 | 03/2017 | 12/2025 | 03/2026 | 2081.27 | 3267.06 | 2816.46 | 88
August 2025 | 594 | Ministry of Railways | Railways | 4th Line Wardha - Nagpur [78.7 Kilometres] | Central Railway [CR] - II | 705505 | Maharashtra | 04/2017 | 05/2018 | 12/2025 | 02/2026 | 637.95 | 1341.28 | 983.16 | 81
August 2025 | 595 | Ministry of Railways | Railways | 3rd Line Manmad - Jalgaon [160 Kilometres] | Central Railway [CR] - II | 705506 | Maharashtra | NA | 04/2018 | 12/2024 | 08/2025 | 1035.16 | 1558.75 | 1726.94 | 95
August 2025 | 596 | Ministry of Railways | Railways | Solapur-tuljapur-Osmanabad | Railway | 705735 | Maharashtra | NA | 12/2023 | 03/2027 | 03/2028 | 904.92 | 3295.74 | 1127.14 | 12
August 2025 | 597 | Ministry of Railways | Railways | Nagpur- Nagbhir Railway Line Gauge Conversion Project | MRIDC | 705799 | Maharashtra | 10/2019 | 04/2020 | 12/2025 | 12/2025 | 1400 | 1400 | 1472 | 80
August 2025 | 598 | Ministry of Railways | Railways | Mumbai Urban Transport Project [MUTP] - PHASE II | Mumbai Rail Vikas Corporation Ltd.[MRVC] | 706779 | Maharashtra | 05/2008 | 04/2008 | 03/2014 | 12/2027 | 8087 | 8087 | 7364 | 87
August 2025 | 599 | Ministry of Railways | Railways | Mumbai Urban Transport Project [MUTP] Phase-IIIA | Mumbai Rail Vikas Corporation Ltd.[MRVC] | 706780 | Maharashtra | 04/2019 | 04/2019 | 12/2027 | 12/2027 | 33690 | 33690 | 2303.4 | 16
August 2025 | 600 | Ministry of Railways | Railways | Mumbai Urban Transport Project Phase-III | Mumbai Rail Vikas Corporation Ltd.[MRVC] | 706781 | Maharashtra | 11/2016 | 12/2016 | 03/2022 | 12/2026 | 10947 | 10947 | 5152.7 | 60
August 2025 | 601 | Ministry of Railways | Railways | PACHORA-JAMNER WITH EXTENSION UPTO MALKAPUR NG TO BG | CR | 709808 | Maharashtra | NA | 01/2022 | 08/2027 | 03/2028 | 955.39 | 2093.82 | 130.42 | 11
August 2025 | 602 | Ministry of Railways | Railways | KALYAN-MURBAD VIA ULHASNAGAR [UMBRELLA WORK] | Central Railway [CR] - II | 709809 | Maharashtra | NA | 04/2023 | 03/2027 | 03/2027 | 726.46 | 836.12 | 9.29 | 0
August 2025 | 603 | Ministry of Railways | Railways | Jiribam-Imphal new line project | Northeast Frontier Railway [NFR] | 705391 | Manipur | 03/2013 | 12/2007 | 12/2026 | 06/2029 | 14323 | 21885.9 | 15598.11 | 69
August 2025 | 604 | Ministry of Railways | Railways | Marikuppam - Kuppam New Line Project [23.70 Km] | South Western Railway [SWR] - II | 705491 | Multi-States (Andhra Pradesh, Karnataka) | 04/2012 | 10/2018 | 06/2026 | 06/2026 | 297 | 297 | 123.38 | 15
August 2025 | 605 | Ministry of Railways | Railways | Rayadurg-Tumkur via Kalyandurg New Line [207 km] | South Western Railway [SWR] - II | 705494 | Multi-States (Andhra Pradesh, Karnataka) | 03/2008 | 07/2010 | 09/2015 | 02/2028 | 2496 | 2496 | 1706.31 | 68
August 2025 | 606 | Ministry of Railways | Railways | Renigunta, Wadi & Gooty Bypass Railway Project | South Central Railway [SCR] - I | 705610 | Multi-States (Andhra Pradesh, Karnataka) | 04/2016 | 04/2016 | 12/2025 | 12/2025 | 302 | 543 | 381 | 50
August 2025 | 607 | Ministry of Railways | Railways | Doubling between Mudkhed Medchal & Mahbubnagar Dhone section 417.88 Km | South Central Railway [SCR] - II | 617212 | Multi-States (Andhra Pradesh, Maharashtra, Telangana) | 08/2023 | 08/2023 | 03/2029 | - | 4686.09 | 4686.09 | 0 | 0
August 2025 | 608 | Ministry of Railways | Railways | Vizianagaram - Titlagarh 3rd line [272 Km including By - pass line of 7.68 KM] | RVNL - II | 400253 | Multi-States (Andhra Pradesh, Odisha) | 06/2016 | 11/2016 | 12/2026 | 12/2026 | 4803 | 6670 | 5722.01 | 89
August 2025 | 609 | Ministry of Railways | Railways | Doubling of Kottavalasa-Koraput Rail Line [189 KM] | East Coast Railway [ECoR] - II | 705512 | Multi-States (Andhra Pradesh, Odisha) | 12/2015 | 01/2016 | 03/2022 | 03/2028 | 2500 | 2500 | 1987.17 | 70
August 2025 | 610 | Ministry of Railways | Railways | Vizianagaram-Sambhalpur 3rd Line Project | RVNL | 705520 | Multi-States (Andhra Pradesh, Odisha) | NA | 12/2016 | 03/2025 | - | 4803.16 | 4803.16 | 2979.23 | 0
August 2025 | 611 | Ministry of Railways | Railways | Malkangiri Pandurangapuram new railway line project | Indian Railways | 616702 | Multi-States (Andhra Pradesh, Odisha, Telangana) | 08/2024 | 01/2027 | 11/2031 | - | 3591.76 | 3591.76 | 0 | 0
August 2025 | 612 | Ministry of Railways | Railways | Tindivanam-Nagari New Line Project [184.5 km] | Southern Railway [SR] - II | 400275 | Multi-States (Andhra Pradesh, Tamil Nadu) | 07/2008 | 10/2008 | 09/2016 | 03/2028 | 3631 | 3631 | 1113.53 | 18
August 2025 | 613 | Ministry of Railways | Railways | Doubling between Motumari Vishnupuram - 88.81 Km and Rail over Rail - RoR at Motumari - 10.877 Km | South Central Railway [SCR] - II | 616857 | Multi-States (Andhra Pradesh, Telangana) | NA | 03/2025 | 03/2029 | - | 1595.55 | 1595.55 | 7.69 | 1
August 2025 | 614 | Ministry of Railways | Railways | Doubling of Guntur Bibinagar 239 Km | South Central Railway [SCR] - II | 617211 | Multi-States (Andhra Pradesh, Telangana) | 08/2023 | 08/2023 | 03/2029 | - | 2853.23 | 2853.23 | 43.88 | 1
August 2025 | 615 | Ministry of Railways | Railways | Rail Connectivity to Errupalem Amravati Namburu 57 Km | South Central Railway [SCR] - II | 617214 | Multi-States (Andhra Pradesh, Telangana) | 11/2024 | 11/2024 | 03/2027 | - | 2047.4 | 2047.4 | 0 | 0
August 2025 | 616 | Ministry of Railways | Railways | Kazipet-Vijayawada 3rd line with electrification [220 km] | South Central Railway [SCR] - II | 705612 | Multi-States (Andhra Pradesh, Telangana) | 03/2013 | 08/2014 | 02/2025 | 12/2025 | 1953 | 3363 | 3073.74 | 91
August 2025 | 617 | Ministry of Railways | Railways | Vijayawada - Kazipet Byepass line | South Central Railway [SCR] - II | 705632 | Multi-States (Andhra Pradesh, Telangana) | 04/2016 | 04/2016 | 01/2025 | 12/2025 | 647 | 904 | 888.91 | 91
August 2025 | 618 | Ministry of Railways | Railways | Murkongselek-Pasighat | Northeast Frontier Railway (NFR) - II | 705401 | Multi-States (Arunachal Pradesh, Assam) | NA | 03/2012 | 03/2025 | 12/2025 | 435 | 1250 | 901 | 56
August 2025 | 619 | Ministry of Railways | Railways | Lumding Furkating Doubling Project 140 km | Northeast Frontier Railway [NFR] | 616701 | Multi-States (Assam, Nagaland) | NA | 01/2025 | 02/2028 | - | 2123.7 | 2123.7 | 13.74 | 0
August 2025 | 620 | Ministry of Railways | Railways | Dimapur [Dhansiri]-Sukhobi Kohima [Zubza] NL [82.5 Km] | Northeast Frontier Railway [NFR] | 705392 | Multi-States (Assam, Nagaland) | 08/2015 | 02/2016 | 03/2025 | 12/2025 | 6663 | 6663 | 5312.26 | 80
August 2025 | 621 | Ministry of Railways | Railways | New Delhi- Howrah Speed Booster[160Kmph] Project | PCE/NCR | 705794 | Multi-States (Bihar, Delhi, Jharkhand, Uttar Pradesh, West Bengal) | NA | 09/2019 | 03/2024 | - | 6684.81 | 6684.81 | 127.03 | 0
August 2025 | 622 | Ministry of Railways | Railways | Third Railway Line between Patratu-Sonnagar [281 kms] | RVNL - II | 400234 | Multi-States (Bihar, Jharkhand) | 11/2016 | 08/2018 | 03/2026 | 07/2026 | 8975 | 8975 | 4950 | 88
August 2025 | 623 | Ministry of Railways | Railways | Multi tracking of Son Nagar-Andal 374.53 rkm & 814.38 tkm | East Central Railway [ECR] - I | 616699 | Multi-States (Bihar, Jharkhand) | 08/2023 | 08/2023 | 03/2028 | - | 12333.57 | 12333.6 | 467.55 | 11
August 2025 | 624 | Ministry of Railways | Railways | Koderma-Tilaiya New Line | East Central Railway [ECR] - I | 705375 | Multi-States (Bihar, Jharkhand) | 11/2004 | 03/2002 | 02/2025 | 02/2026 | 1626 | 2020 | 2000.4 | 95
August 2025 | 625 | Ministry of Railways | Railways | Pirpainti - Jasidih [100.52 Km] New BG line | Eastern Railway [ER] - I | 705385 | Multi-States (Bihar, Jharkhand) | 03/2014 | 03/2022 | 03/2028 | 03/2028 | 2555 | 2555 | 767.04 | 48
August 2025 | 626 | Ministry of Railways | Railways | NER Provision of Automatic Block Signalling on Gorakhpur Cantt[Excl] Chhapra Gramin & Burhwal Jn [Excl] Sitapur Jn section of high density routes | North Eastern Railway [NER] | 611669 | Multi-States (Bihar, Uttar Pradesh) | NA | 06/2023 | 03/2027 | - | 380.47 | 380.47 | 24.53 | 0
August 2025 | 627 | Ministry of Railways | Railways | Gorakhpur-Valmikinagar Doubling project | NER | 617224 | Multi-States (Bihar, Uttar Pradesh) | NA | 03/2024 | 12/2027 | - | 1120 | 1120 | 204.59 | 20
August 2025 | 628 | Ministry of Railways | Railways | Chhapra-Ballia Patch Doubling | North Eastern Railway [NER] | 705562 | Multi-States (Bihar, Uttar Pradesh) | 03/2013 | 11/2015 | 02/2025 | 03/2025 | 963 | 1046 | 911.66 | 95
August 2025 | 629 | Ministry of Railways | Railways | Katihar - Kumedpur Doubling Line Project | GM/C/ NFR | 706844 | Multi-States (Bihar, West Bengal) | 08/2022 |  | 08/2027 | 08/2027 | 942 | 942 | 356 | 45
August 2025 | 630 | Ministry of Railways | Railways | Rajnandgaon - Nagpur [Kalumna] Third Railway Line [228.30 km] | South East Central Railway [SECR] - II | 705617 | Multi-States (Chhattisgarh, Maharashtra) | 09/2016 | 12/2016 | 12/2024 | 06/2026 | 3545 | 3545 | 3428.26 | 95
August 2025 | 631 | Ministry of Railways | Railways | Jagdalpur-Koraput | East Coast Railway [ECoR] - II | 705511 | Multi-States (Chhattisgarh, Odisha) | 12/2015 | 03/2016 | 03/2024 | 12/2026 | 1547 | 1547 | 1323.05 | 90
August 2025 | 632 | Ministry of Railways | Railways | Jharsuguda-Bilaspur Fourth Railway Line [206 km] | SECR | 705616 | Multi-States (Chhattisgarh, Odisha) | 09/2016 | 09/2016 | 10/2024 | 12/2025 | 2140 | 2979 | 2143.64 | 89
August 2025 | 633 | Ministry of Railways | Railways | Mumbai-Ahmedabad High Speed Rail Project- 508 km | National High Speed Rail Corporation [NHSRC] | 705728 | Multi-States (Dadra & Nagar Haveli and Daman & Diu, Gujarat, Maharashtra) | 03/2015 | 09/2017 | 08/2027 | 12/2029 | 108000 | 108000 | 79918.89 | 53
August 2025 | 634 | Ministry of Railways | Railways | New Delhi- Mumbai Speed Booster[160Kmph] Project | PCE/WR | 705793 | Multi-States (Delhi, Gujarat, Madhya Pradesh, Maharashtra, Rajasthan) | NA | 09/2019 | 03/2024 | - | 6806.44 | 6806.44 | 135.65 | 0
August 2025 | 635 | Ministry of Railways | Railways | Hospet - Tinaighat - Vasco Rail Doubling Project | RVNL - II | 705650 | Multi-States (Goa, Karnataka) | 03/2010 | 07/2012 | 03/2027 | 12/2027 | 5060 | 5060 | 5007.82 | 86
August 2025 | 636 | Ministry of Railways | Railways | Hospet-Hubli-Vasco da Gama Line Electrification Project | RVNL | 706950 | Multi-States (Goa, Karnataka) | NA | 05/2018 | 03/2023 | 03/2024 | 744.49 | 1122.62 | 969.05 | 95
August 2025 | 637 | Ministry of Railways | Railways | Western Dedicated Freight Corridor | DFCCIL | 705237 | Multi-States (Gujarat, Haryana, Maharashtra, Rajasthan, Uttar Pradesh) | 02/2008 | 01/2012 | 03/2022 | 12/2025 | 51101 | 124005 | 124623 | 96
August 2025 | 638 | Ministry of Railways | Railways | New line Dahod-Indore via Sardarpur, Jabuwa and Dhar | Western Railway [WR] - II | 705453 | Multi-States (Gujarat, Madhya Pradesh) | 06/2012 | 06/2012 | 02/2027 | 02/2027 | 456.07 | 1873.1 | 3412.33 | 46
August 2025 | 639 | Ministry of Railways | Railways | Chhota Udaipur - Dhar New Line Project [157 km] | Western Railway [WR] - II | 705454 | Multi-States (Gujarat, Madhya Pradesh) | 11/2008 | 01/2014 | 12/2025 | 12/2025 | 1794 | 1794 | 1804.05 | 80
August 2025 | 640 | Ministry of Railways | Railways | MUMBAI CENTRAL VIRAR VADODARA AHMEDABAAD TRAIN PROTECTION SYSTEM 500 RKM | Western Railway | 611452 | Multi-States (Gujarat, Maharashtra) | 09/2019 | 03/2023 | 12/2025 | 06/2025 | 311 | 311 | 208 | 92
August 2025 | 641 | Ministry of Railways | Railways | Taranga Hill-Abu Road via Ambaji | North Western Railway [NWR] | 400022 | Multi-States (Gujarat, Rajasthan) | 07/2022 | 07/2022 | 07/2030 | 07/2030 | 2798 | 2798 | 1915.38 | 15
August 2025 | 642 | Ministry of Railways | Railways | LUNI- SAMDARI- BHILDI DOUBLING | North Western Railway [NWR] | 616842 | Multi-States (Gujarat, Rajasthan) | 02/2024 | 02/2024 | 07/2027 | - | 3085.59 | 3085.59 | 171.32 | 7
August 2025 | 643 | Ministry of Railways | Railways | Chandigarh-Baddi New Rail Line- 36 km | Northen Railway [NR] | 705424 | Multi-States (Haryana, Himachal Pradesh) | 02/2018 | 02/2018 | 12/2026 | 12/2026 | 1540 | 1540.13 | 506.73 | 31
August 2025 | 644 | Ministry of Railways | Railways | Rewari - Kathuwas Doubling Project [27.72 Km] | North Western Railway [NWR] | 611861 | Multi-States (Haryana, Rajasthan) | 02/2023 | 12/2022 | 06/2027 | 06/2027 | 352 | 352 | 246.11 | 63
August 2025 | 645 | Ministry of Railways | Railways | Nangal Dam-Talwara New Broad Gauge Line [84 KM] and Taking Over Siding Mukerian-Talwara [29 KM] | Northen Railway [NR] | 705410 | Multi-States (Himachal Pradesh, Punjab) | 03/1983 | 05/1985 | 12/2025 | 01/2027 | 2018 | 2018 | 2053.9 | 45
August 2025 | 646 | Ministry of Railways | Railways | Bhanupalli-Bilaspur-Beri New Railway Line Project | RVNL - II | 705428 | Multi-States (Himachal Pradesh, Punjab) | 03/2009 | 04/2015 | 12/2026 | 12/2027 | 13447 | 13447 | 6805.81 | 60
August 2025 | 647 | Ministry of Railways | Railways | Doubling of Hatia [Ranchi]-Bondamunda Rail Line - 159 km | South Eastern Railway - JH | 705628 | Multi-States (Jharkhand, Odisha) | 03/2016 | 02/2017 | 06/2025 | 06/2026 | 3029 | 3029 | 2470.12 | 85
August 2025 | 648 | Ministry of Railways | Railways | Buramara-Chakulia new line [59.96 km] | South Eastern Railway [SER] - I | 616588 | Multi-States (Jharkhand, Odisha, West Bengal) | 08/2024 | 12/2024 | 12/2029 | - | 1459.13 | 1459.13 | 2.11 | 0
August 2025 | 649 | Ministry of Railways | Railways | Chandil - Anara - Damodar - 3rd line [121.26 km] | CAO/C/SER | 616227 | Multi-States (Jharkhand, West Bengal) | NA | 07/2025 | 09/2029 | - | 1932.01 | 1932.01 | 0.03 | 0
August 2025 | 650 | Ministry of Railways | Railways | KHARAGPUR-ADITYAPUR THIRD RAIL LINE- 132 KM | RVNL - II | 705668 | Multi-States (Jharkhand, West Bengal) | 09/2016 | 01/2018 | 03/2025 | 12/2025 | 3250 | 3250 | 3176.46 | 97
August 2025 | 651 | Ministry of Railways | Railways | Hotgi-Kudgi-Gadag Doubling Project | South Western Railway [SWR] - II | 705662 | Multi-States (Karnataka, Maharashtra) | 04/2014 | 01/2016 | 12/2024 | 03/2026 | 1878 | 2459 | 2642.04 | 92
August 2025 | 652 | Ministry of Railways | Railways | Baiyyappanahalli - Hosur Doubling Project [48 km] | Karnataka Rail Infrastructure Development Company Limited [K-RIDE] | 703586 | Multi-States (Karnataka, Tamil Nadu) | 04/2019 | 02/2019 | 12/2024 | 01/2026 | 499 | 499 | 595 | 97
August 2025 | 653 | Ministry of Railways | Railways | Trivandrum- Kanyakumari | Southern Railway (SR) - I | 705635 | Multi-States (Kerala, Tamil Nadu) | 08/2017 | 03/2016 | 03/2024 | 12/2027 | 1432 | 3785 | 2451 | 46
August 2025 | 654 | Ministry of Railways | Railways | Ratlam-Mhow-Khandwa-Akola Gauge Conversion | Western Railway [WR] - II | 705457 | Multi-States (Madhya Pradesh, Maharashtra) | 04/2008 | 03/2010 | 03/2027 | 09/2028 | 1656.25 | 5735.88 | 4428.77 | 80
August 2025 | 655 | Ministry of Railways | Railways | Itarsi - Nagpur Third Railway Line [280 km] | Central Railway [CR] - II | 705507 | Multi-States (Madhya Pradesh, Maharashtra) | 09/2016 | 09/2016 | 03/2027 | 03/2027 | 2449.91 | 2506.68 | 1843.76 | 51
August 2025 | 656 | Ministry of Railways | Railways | Gwalior - Seopurkala with extension to Kota [Gauge Conversion] | North Central Railway | 705419 | Multi-States (Madhya Pradesh, Rajasthan) | 03/2011 | 07/2018 | 03/2025 | 02/2026 | 2913 | 2913 | 2097.51 | 78
August 2025 | 657 | Ministry of Railways | Railways | Ramganjmandi-Bhopal New Line Project [262 km] | West Central Railway [WCR] - II | 705481 | Multi-States (Madhya Pradesh, Rajasthan) | 03/2001 | 10/2004 | 12/2025 | 12/2027 | 3032 | 5073 | 3621.79 | 70
August 2025 | 658 | Ministry of Railways | Railways | Nimach-Badi Sadri New Rail Line Project | Western Railway [WR] - II | 705764 | Multi-States (Madhya Pradesh, Rajasthan) | 04/2017 | 09/2021 | 03/2026 | 06/2026 | 495 | 825 | 79.55 | 53
August 2025 | 659 | Ministry of Railways | Railways | Mathura-Jhansi Third Railway Line [274 Km] | RVNL - II | 705667 | Multi-States (Madhya Pradesh, Rajasthan, Uttar Pradesh) | 12/2015 | 03/2018 | 12/2024 | 12/2026 | 5961 | 5961 | 4928.62 | 94
August 2025 | 660 | Ministry of Railways | Railways | Jhansi - Bina Third Railway Line [153 Km] | CAO/C/NCR | 705598 | Multi-States (Madhya Pradesh, Uttar Pradesh) | 09/2016 | 03/2018 | 03/2022 | 03/2026 | 2002 | 2002 | 1795.86 | 93
August 2025 | 661 | Ministry of Railways | Railways | Jhansi-Khairar-Manikpur & Khirar-Bhimsen | North Central Railway | 705608 | Multi-States (Madhya Pradesh, Uttar Pradesh) | 03/2018 | 03/2017 | 03/2026 | 03/2026 | 4330 | 4330 | 2184.56 | 55
August 2025 | 662 | Ministry of Railways | Railways | Third Line [new] between Kazipet - Balharshah with electrification [201.04 Km] | South Central Railway [SCR] - II | 705613 | Multi-States (Maharashtra, Telangana) | 09/2016 | 10/2016 | 01/2025 | 11/2025 | 2595 | 3071 | 3223.67 | 93
August 2025 | 663 | Ministry of Railways | Railways | Narayangarh-Bhadrak 3rd line | South Eastern Railway [SER] - I | 705629 | Multi-States (Odisha, West Bengal) | 03/2019 | 03/2017 | 12/2025 | 06/2026 | 2400 | 2400 | 2236.9 | 65
August 2025 | 664 | Ministry of Railways | Railways | Nagapattinam-Tiruturaipundi and Karaikal-Peralam New Line | Southern Railway [SR] - II | 400223 | Multi-States (Puducherry, Tamil Nadu) | 07/2008 | 01/2019 | 03/2026 | 03/2027 | 713 | 981 | 598.38 | 80
August 2025 | 665 | Ministry of Railways | Railways | Sivok-Rangpo New Rail Line | Indian Railway Construction International Limited [IRCON] | 705432 | Multi-States (Sikkim, West Bengal) | 10/2009 | 05/2010 | 05/2015 | 12/2027 | 7877 | 12133 | 9039.91 | 84
August 2025 | 666 | Ministry of Railways | Railways | Sainthia, Sitarampur, Mughalsarai, Allahabad & Etawah - Bypass Line Project | Eastern Railway [ER] - I | 602797 | Multi-States (Uttar Pradesh, West Bengal) | 08/2017 | 12/2017 | 03/2027 | 03/2027 | 461.64 | 461.64 | 186.03 | 7
August 2025 | 667 | Ministry of Railways | Railways | Proposed 6 nos Road Over Bridge [ROB] at different locations under MCL Talcher Under Deposit Scheme. | East Coast Railway [ECoR] - II | 400045 | Odisha | 08/2022 | 07/2022 | 03/2025 | 01/2025 | 168.32 | 168.32 | 69.85 | 82
August 2025 | 668 | Ministry of Railways | Railways | Brundamal-Jharsuguda- flyover connection for joining downline | East Coast Railway [ECoR] - II | 400232 | Odisha | 01/2014 | 01/2014 | 12/2026 | 12/2026 | 297 | 297 | 193.22 | 30
August 2025 | 669 | Ministry of Railways | Railways | 3rd & 4th line between Sarla - Sason [8 km] [PB 73/2023-24/NR] | East Coast Railway [ECoR] - II | 612834 | Odisha | 04/2023 | 04/2023 | 12/2025 | - | 252 | 252 | 79.55 | 45
August 2025 | 670 | Ministry of Railways | Railways | Bangriposi-Gorumahisani new line [ 85.60 km ] | CAO/C/SER | 616586 | Odisha | 08/2024 | 09/2025 | 12/2029 | - | 2269.49 | 2269.49 | 2.31 | 0
August 2025 | 671 | Ministry of Railways | Railways | Badampahar-Kendujhargarh new line [82.06 km] | CAO/C/SER | 616587 | Odisha | 08/2024 | 09/2025 | 12/2029 | - | 1875.72 | 1875.72 | 0.53 | 0
August 2025 | 672 | Ministry of Railways | Railways | Flyover between Siju and Paradeep coaching Yard to avoid Surface crossing of trains | East Coast Railway [ECoR] - II | 616694 | Odisha | 04/2023 | 10/2025 | 07/2028 | - | 200.77 | 200.77 | 0 | 0
August 2025 | 673 | Ministry of Railways | Railways | Paradeep - Badabandha 3rd & 4th Line / 18.51kms | East Coast Railway [ECoR] - II | 616695 | Odisha | 08/2023 | 04/2025 | 11/2028 | - | 300.15 | 300.15 | 0.01 | 0
August 2025 | 674 | Ministry of Railways | Railways | Khurda-Bolangir New Broad Gauge Rail Link [301km] | East Coast Railway [ECoR] - II | 705358 | Odisha | 03/1994 | 03/2001 | 12/2026 | 12/2026 | 3792 | 5089 | 5027.62 | 89
August 2025 | 675 | Ministry of Railways | Railways | Talcher-Bimlagarh New Railway Line | East Coast Railway [ECoR] - II | 705359 | Odisha | 03/2004 | 12/2004 | 03/2025 | 03/2027 | 1928 | 1928 | 1934.28 | 48
August 2025 | 676 | Ministry of Railways | Railways | Bhadrak-Nergundi Third Line | East Coast Railway [ECoR] - II | 705510 | Odisha | 10/2015 | 04/2015 | 11/2024 | 01/2026 | 1284 | 1284 | 1298 | 80
August 2025 | 677 | Ministry of Railways | Railways | Koraput - Singapur Railway Doubling | East Coast Railway [ECoR] - II | 705513 | Odisha | 12/2015 | 12/2015 | 12/2027 | 03/2028 | 2362 | 2362 | 1798.71 | 68
August 2025 | 678 | Ministry of Railways | Railways | Jarapada- Budhapank with flyover at Talcher road 3rd and 4th Line | East Coast Railway [ECoR] - II | 705514 | Odisha | NA | 12/2015 | 11/2018 | 03/2026 | 1000 | 810.02 | 401.61 | 36
August 2025 | 679 | Ministry of Railways | Railways | 3rd & 4th Railway Line Project from Salegaon to Budhapank via Rajathgarh. | East Coast Railway [ECoR] - II | 705515 | Odisha | 07/2013 | 12/2015 | 03/2026 | 03/2026 | 1173 | 2092 | 1971 | 80
August 2025 | 680 | Ministry of Railways | Railways | Jeypore-Navarangpur New Rail Line Project | East Coast Railway [ECoR] - II | 705741 | Odisha | 07/2017 | 04/2023 | 07/2028 | 12/2029 | 748 | 748 | 10.56 | 1
August 2025 | 681 | Ministry of Railways | Railways | Jeypore-Malkanagiri New Railway Line Project | East Coast Railway [ECoR] - II | 705742 | Odisha | 02/2018 | 12/2023 | 07/2033 | 07/2033 | 2344 | 2344 | 225.84 | 8
August 2025 | 682 | Ministry of Railways | Railways | Talcher-Angul New Line with Y-Connection at Talcher | CAO/C/ECoR | 705743 | Odisha | 07/2018 |  | 05/2027 | 05/2028 | 495 | 495 | 29.5 | 1
August 2025 | 683 | Ministry of Railways | Railways | Baghuapal Flyover Construction Project | CAO/C/ECoR | 705767 | Odisha | 08/2019 | 10/2022 | 03/2028 | 03/2028 | 257.97 | 258 | 0.83 | 0
August 2025 | 684 | Ministry of Railways | Railways | Khurda Road - Balangir Electrification of Railway Track Project | Ministry of Railways | 706898 | Odisha | NA | 09/2019 | 03/2021 | - | 267.61 | 267.61 | 0 | 0
August 2025 | 685 | Ministry of Railways | Railways | KODINGAMALI BAUXITE MINES TO SINGARAM RAILWAY STATION | Indian Railway | 709810 | Odisha | 08/2022 | 01/2026 | 08/2027 | 08/2027 | 190.9 | 190.9 | 0 | 0
August 2025 | 686 | Ministry of Railways | Railways | GANDHAMARDAN IRON ORE MINES TO GOALDIH STATION/12.76kms | East Coast Railway [ECoR] - II | 709811 | Odisha | 09/2022 | 05/2025 | 09/2027 | 09/2027 | 190 | 190 | 0 | 0
August 2025 | 687 | Ministry of Railways | Railways | Junagarh Visavadar 42 Kms | Railway | 611980 | Offshore | 06/2022 | 02/2023 | 09/2028 | 09/2028 | 492.83 | 492.83 | 3 | 1
August 2025 | 688 | Ministry of Railways | Railways | Jaynagar-Bijalpura, incl. extn. Bet, Bijalpura-Bardibas [Nepal] | East Central Railway [ECR] - I | 705362 | Offshore | 08/2015 | 03/2011 | 03/2022 | 03/2026 | 819 | 819 | 580.6 | 75
August 2025 | 689 | Ministry of Railways | Railways | Ludhiana- Killa Raipur Railway Doubling Project | Railway | 705783 | Punjab | 03/2019 | 12/2022 | 03/2025 | 03/2026 | 237.64 | 237.64 | 118 | 55
August 2025 | 690 | Ministry of Railways | Railways | Dedicated Test Track for RDSO Phase II | North Western Railway [NWR] | 611614 | Rajasthan | 11/2021 | 11/2021 | 11/2026 | 11/2026 | 819.48 | 967.06 | 471 | 86
August 2025 | 691 | Ministry of Railways | Railways | Devgarh Madariya - Nathdwara Gauge Conversion [82.54 Km] part of Marwar - Mavli Gauge Conversion [152 Km] | North Western Railway [NWR] | 611849 | Rajasthan | 01/2023 | 01/2023 | 06/2028 | 06/2028 | 968.92 | 968.92 | 98.62 | 51
August 2025 | 692 | Ministry of Railways | Railways | Maintenance cum workshop depot for Vande Bharat Sleeper Trains as per conditions under WTA 527 | WPO/Patna | 611929 | Rajasthan | NA | 06/2023 | 12/2024 | - | 166.86 | 166.86 | 0 | 0
August 2025 | 693 | Ministry of Railways | Railways | RINGUS KHATUSHYAMJI NEW LINE | North Western Railway [NWR] | 616696 | Rajasthan | 03/2024 | 03/2024 | 03/2028 | - | 254.06 | 254.06 | 2.94 | 0
August 2025 | 694 | Ministry of Railways | Railways | RAS- MERTA CITY NEW LINE INCL BYPASS AT MERTA ROAD | North Western Railway [NWR] | 616840 | Rajasthan | NA | 02/2024 | 03/2028 | - | 947 | 947 | 1.36 | 0
August 2025 | 695 | Ministry of Railways | Railways | PUSHKAR- MERTA CITY NEW LINE | North Western Railway [NWR] | 616841 | Rajasthan | 02/2024 | 02/2024 | 12/2026 | - | 799.64 | 799.64 | 14.5 | 4
August 2025 | 696 | Ministry of Railways | Railways | AJMER- CHANDERIYA DOUBLING | North Western Railway [NWR] | 616843 | Rajasthan | 02/2024 | 02/2024 | 06/2027 | - | 1634.79 | 1634.79 | 74.43 | 6
August 2025 | 697 | Ministry of Railways | Railways | Dholpur - Sirmuttra Gauge Conversion | North Central Railway | 705482 | Rajasthan | 03/2022 | 04/2020 | 02/2019 | 02/2027 | 747 | 747 | 355.13 | 43
August 2025 | 698 | Ministry of Railways | Railways | Gudha-Thatha Mithri Construction of Railway Track Project | North Western Railway [NWR] | 705752 | Rajasthan | 04/2019 | 04/2019 | 11/2026 | 11/2026 | 819.48 | 967.06 | 471 | 98
August 2025 | 699 | Ministry of Railways | Railways | Sawai Madhopur-Jaipur Railway Line Project | North Western Railway [NWR] | 705912 | Rajasthan | NA | 04/2023 | 03/2027 | - | 1203.89 | 1203.89 | 46.07 | 7
August 2025 | 700 | Ministry of Railways | Railways | Agra Fort-Bandikui Doubling Line Project | CAO/C/NCR | 705919 | Rajasthan | 06/2022 | 02/2021 | 06/2027 | 06/2027 | 1390 | 1390 | 123 | 25
August 2025 | 701 | Ministry of Railways | Railways | Sawaimadhopur Bye Pass Line Project | North Western Railway [NWR] | 706866 | Rajasthan | 12/2022 | 01/2023 | 03/2026 | 05/2027 | 304 | 304 | 43.07 | 44
August 2025 | 702 | Ministry of Railways | Railways | Ph II extension of MRTS from Velachery to St Thomas Mount | Southern Railways [SR] - construction | 400280 | Tamil Nadu | 11/2007 | 11/2008 | 07/2024 | 08/2025 | 734 | 982 | 475.73 | 99
August 2025 | 703 | Ministry of Railways | Railways | Redevelopment of Chennai Egmore Station | Railway | 613002 | Tamil Nadu | NA | 10/2022 | 03/2026 | - | 842 | 842 | 340 | 0
August 2025 | 704 | Ministry of Railways | Railways | Coach Production Factory Upgradation Project | CPM/ICF | 705244 | Tamil Nadu | NA | 07/2018 | 12/2021 | - | 520 | 520 | 192.25 | 0
August 2025 | 705 | Ministry of Railways | Railways | Morappur - Dharmpuri New Railway Line Project | Southern Railway [SR] - I | 705755 | Tamil Nadu | 05/2019 | 12/2016 | 03/2028 | 03/2028 | 359 | 359 | 40 | 1
August 2025 | 706 | Ministry of Railways | Railways | Doubling between Bhadrachalam Road and Dornakal | South Central Railway [SCR] - II | 616856 | Telangana | NA | 04/2025 | 04/2029 | - | 770.12 | 770.12 | 0 | 0
August 2025 | 707 | Ministry of Railways | Railways | Kazipet Wagon Overhauling Project | RVNL | 705252 | Telangana | NA | 07/2017 | 12/2023 | - | 385 | 385 | 0 | 0
August 2025 | 708 | Ministry of Railways | Railways | Manoharabad-Kothapalli New Rail Line [151 km] | South Central Railway [SCR] - II | 705437 | Telangana | 07/2016 | 01/2017 | 03/2027 | 12/2027 | 1160 | 2781 | 1771.32 | 71
August 2025 | 709 | Ministry of Railways | Railways | Bahraich-Shravasti-Balrampur-Siddharthnagar -Santkabir nagar | North Eastern Railway [NER] | 400204 | Uttar Pradesh | 10/2018 | 03/2017 | 10/2030 | 10/2030 | 4939.78 | 4939.78 | 1232.64 | 8
August 2025 | 710 | Ministry of Railways | Railways | Sahjanwa-Dohrighat | North Eastern Railway [NER] | 400205 | Uttar Pradesh | 08/2019 | 03/2017 | 03/2029 | 03/2029 | 1319.75 | 1319.75 | 460.2 | 3
August 2025 | 711 | Ministry of Railways | Railways | Anandnagar - Ghugli via Maharajganj New line 52.7 km | Construction NER | 617252 | Uttar Pradesh | 10/2023 | 11/2023 | 03/2028 | - | 958.27 | 958.27 | 436.95 | 23
August 2025 | 712 | Ministry of Railways | Railways | Chunar-Chopan doubling project | North Central Railway | 617284 | Uttar Pradesh | 08/2023 | 01/2025 | 03/2028 | - | 1423.96 | 1423.96 | 49.57 | 2
August 2025 | 713 | Ministry of Railways | Railways | Domingarh-Gorakhpur-Gorakhpur Cantt.-Kusumhi - 3rd Railway Line Project | North Eastern Railway [NER] | 705566 | Uttar Pradesh | 11/2016 | 06/2018 | 02/2025 | 09/2025 | 351 | 521.47 | 495.86 | 98
August 2025 | 714 | Ministry of Railways | Railways | Burhwal Gonda 3rd line | North Eastern Railway [NER] | 705567 | Uttar Pradesh | 11/2017 | 07/2019 | 03/2025 | 09/2025 | 1016 | 1118 | 1373.8 | 73
August 2025 | 715 | Ministry of Railways | Railways | Janghai-Pratapgarh- Amethi | CAO/C/II/NR | 705588 | Uttar Pradesh | 11/2017 | 03/2017 | 03/2025 | 03/2026 | 722 | 1194 | 1550 | 70
August 2025 | 716 | Ministry of Railways | Railways | Lalitpur-Birari with flyover at Lalitpur- 16 Km | North Central Railway | 705766 | Uttar Pradesh | 03/2017 | 03/2017 | 12/2024 | 11/2025 | 304.44 | 356 | 220.8 | 72
August 2025 | 717 | Ministry of Railways | Railways | Allahabad-Bamhrauli Flyover Construction & 4th Railway Line Project | North Central Railway | 705771 | Uttar Pradesh | 04/2019 | 10/2020 | 03/2026 | 03/2026 | 494 | 494 | 333 | 70
August 2025 | 718 | Ministry of Railways | Railways | Mughalsarai-Allahabad, 3rd line | North Central Railway | 705772 | Uttar Pradesh | 12/2015 | 03/2016 | 12/2026 | 03/2027 | 2649 | 2649.44 | 1561.89 | 62
August 2025 | 719 | Ministry of Railways | Railways | Aligarh -Daud Khan Flyover Construction & 3rd Railway Line Project | CAO/C/NCR | 705774 | Uttar Pradesh | 04/2019 | 09/2020 | 01/2025 | 03/2027 | 758 | 779.49 | 315.37 | 55
August 2025 | 720 | Ministry of Railways | Railways | Bhandai - Flyover for Etawah bound down train- 10 Km | North Central Railway (NCR) - II | 705777 | Uttar Pradesh | 07/2020 | 04/2021 | 02/2026 | 02/2027 | 250.18 | 250.18 | 113.94 | 3
August 2025 | 721 | Ministry of Railways | Railways | Phephna-Indara, Mau-Shahganj doubling excluding Indara-Mau | South Eastern Railway [SER] - I | 705779 | Uttar Pradesh | 05/2017 | 03/2017 | 12/2024 | 03/2026 | 1178 | 1777 | 1489.5 | 85
August 2025 | 722 | Ministry of Railways | Railways | Bhatni-Aurnihar with electrification excluding Indara-Mau | RVNL - II | 705780 | Uttar Pradesh | 03/2018 | 03/2017 | 12/2024 | 10/2025 | 2529 | 2529.46 | 2051.69 | 94
August 2025 | 723 | Ministry of Railways | Railways | Barabanki-Malhaur 3rd & 4th Railway Line Project | CAO/C/NR | 705782 | Uttar Pradesh | 01/2019 | 04/2017 | 03/2025 | 03/2026 | 407 | 407 | 317 | 75
August 2025 | 724 | Ministry of Railways | Railways | Janghai-Phaphamau Doubling Rail Line Project | RVNL | 705784 | Uttar Pradesh | 11/2018 | 03/2020 | 03/2025 | 03/2025 | 357 | 978.77 | 579 | 95
August 2025 | 725 | Ministry of Railways | Railways | Bahraich - Nanpara - Nepalganj Road Gauge Conversion | North Eastern Railway [NER] | 705863 | Uttar Pradesh | 07/2020 | 04/2021 | 07/2025 | 09/2025 | 950 | 550 | 511.18 | 90
August 2025 | 726 | Ministry of Railways | Railways | Allahabad division - Aligarh - Harduaganj Flyover | North Central Railway | 705918 | Uttar Pradesh | 04/2020 | 02/2021 | 06/2026 | 03/2027 | 1457 | 1457 | 50 | 14
August 2025 | 727 | Ministry of Railways | Railways | DOUBLING BETWEEN JAUNPUR JN-ZAFFARABAD [6.28 KM] | Northen Railway [NR] | 900872 | Uttar Pradesh | 01/2023 |  | 01/2027 | 12/2028 | 177 | 177 | 41 | 10
August 2025 | 728 | Ministry of Railways | Railways | Rishikesh-Karnaprayag New Rail Line- 125 km | RVNL - II | 705429 | Uttarakhand | 11/2016 | 08/2018 | 12/2025 | 03/2027 | 38953 | 38953 | 24645.15 | 65
August 2025 | 729 | Ministry of Railways | Railways | Kalinarayanpur-Krishnanagar Doubling Alongwith Krishnanagar - Chapra New Line And Naihati-Ranaghat 3rd Line. | Eastern Railway [ER] - I | 400247 | West Bengal | 07/2015 | 11/2005 | 02/2027 | 02/2027 | 1000 | 1000 | 1031.21 | 67
August 2025 | 730 | Ministry of Railways | Railways | Tarakeshwar-Bishnupur New Line [82.47 km] | Eastern Railway [ER] - I | 400273 | West Bengal | 03/2001 | 02/2008 | 03/2019 | 02/2026 | 1189 | 1542 | 1307.52 | 90
August 2025 | 731 | Ministry of Railways | Railways | Dum Dum Airport-New Garia via Rajarhat-Construction of Metro Railway | RVNL - II | 400277 | West Bengal | 03/2010 | 10/2011 | 12/2025 | 03/2026 | 8964 | 8964 | 8097.47 | 80
August 2025 | 732 | Ministry of Railways | Railways | Construction of Balurghat-Hilli new BG Line | Northeast Frontier Railway [NFR] | 612096 | West Bengal | 12/2010 | 12/2010 | 03/2027 | 03/2025 | 1209 | 1209 | 405.31 | 9
August 2025 | 733 | Ministry of Railways | Railways | Kalipahari Bakhtarnagar 5th line | Eastern Railway [ER] - I | 617322 | West Bengal | 08/2024 | 07/2025 | 06/2027 | 06/2027 | 350.46 | 350.46 | 0 | 0
August 2025 | 734 | Ministry of Railways | Railways | Joka-BBD Bag new metro project | RVNL - II | 705730 | West Bengal | 03/2010 | 04/2010 | 12/2026 | 12/2028 | 4835 | 10362 | 4373.24 | 60
August 2025 | 735 | Ministry of Railways | Railways | Noapara-Barasat via Bimanbandar - Construction of Metro railway [18 km] | Metro Railway, Kolkata | 706776 | West Bengal | 11/2010 | 03/2010 | 08/2026 | 03/2029 | 4830 | 4830 | 2764.13 | 32
August 2025 | 736 | Ministry of Railways | Railways | Baranagar-Barrackpore and Dakshineshwar- Construction of Metro Railway | RVNL - II | 706777 | West Bengal | 03/2010 | 03/2010 | 12/2026 | 12/2025 | 2298 | 2734 | 393 | 17
August 2025 | 737 | Department for Promotion of Industry & Internal Trade | Real Estate | Krishnapatnam Node - Phase 1 - Roads and Services Development | National Industrial Corridor Development Corporation | 701658 | Andhra Pradesh | 12/2020 | 02/2024 | 02/2028 | - | 2139.44 | 2139.44 | 406.05 | 17
August 2025 | 738 | Department for Promotion of Industry & Internal Trade | Real Estate | Tumakuru Node - Phase 1 - Roads and Services Development | National Highways & Infrastructure Development Corporation Ltd. [NHIDCL] | 701657 | Karnataka | 12/2020 | 02/2023 | 09/2026 | - | 1701.81 | 1701.81 | 88.25 | 8
August 2025 | 739 | Department of Telecommunications | Telecommunication | SETTING UP OF PHYSICAL INFRASTRUCTURE FOR THE NATIONAL INSTITUTE OF COMMUNICATION FINANCE [NICF] AT GHITORNI | National Communication Academy - Finance (Erstwhile NICF | 709859 | Delhi | 10/2014 | 04/2018 | 02/2020 | 10/2025 | 248.2 | 248.2 | 236.91 | 98
August 2025 | 740 | Department of Telecommunications | Telecommunication | Provision of 4G based Mobile Services in Uncovered Villages and National Highways of Meghalaya | Department of Telecommunications [DoT] | 701598 | Meghalaya | 09/2019 | 09/2020 | 03/2022 | 09/2025 | 971.96 | 971.96 | 208.25 | 99
August 2025 | 741 | Department of Telecommunications | Telecommunication | Mobile connectivity in Left Wing Extremism [LWE] affected areas-Phase2 | Department of Telecommunications [DoT] | 701599 | Multi-States (Andhra Pradesh, Bihar, Chhattisgarh, Jharkhand, Madhya Pradesh, Maharashtra, Odisha, Telangana, Uttar Pradesh, West Bengal) | NA | 09/2021 | 03/2023 | 11/2025 | 1577.57 | 1577.57 | 598.31 | 87
August 2025 | 742 | Department of Telecommunications | Telecommunication | Provision of 4G based mobile services in 7,287 uncovered villages of 44 Aspirational District across 5 states of Andhra Pradesh, Chhattisgarh, Jharkhand, Maharashtra & Odisha | Department of Telecommunications [DoT] | 701602 | Multi-States (Andhra Pradesh, Chhattisgarh, Jharkhand, Maharashtra, Odisha) | 11/2021 | 05/2022 | 11/2023 | 11/2025 | 3685 | 3685 | 1101.44 | 79
August 2025 | 743 | Department of Telecommunications | Telecommunication | Provision of 4G Mobile Services in Uncovered Villages of Arunachal Pradesh and 2 Districts of Assam | Department of Telecommunications [DoT] | 701597 | Multi-States (Arunachal Pradesh, Assam) | 12/2020 | 10/2021 | 04/2023 | 09/2025 | 1255.49 | 1255.49 | 284.04 | 89
August 2025 | 744 | Department of Telecommunications | Telecommunication | 354 Uncovered Villages Scheme | Department of Telecommunications [DoT] | 701600 | Multi-States (Bihar, Gujarat, Himachal Pradesh, Jammu and Kashmir, Ladakh, Rajasthan, Uttar Pradesh) | 12/2019 | 04/2020 | 10/2021 | 08/2025 | 336.89 | 301.13 | 227.82 | 97
August 2025 | 745 | Department of Telecommunications | Telecommunication | 502 Aspirational District Scheme in Four states - Bihar, Madhya Pradesh, Rajastha and Uttar Pradesh | Department of Telecommunications [DoT] | 704495 | Multi-States (Bihar, Madhya Pradesh, Rajasthan, Uttar Pradesh) | NA | 03/2021 | 03/2022 | 12/2025 | 421.65 | 228.94 | 134.08 | 96
August 2025 | 746 | Department of Telecommunications | Telecommunication | PHASE-I OF CONSOLIDATION OF EXISTING CDR DATA CENTERS AND NIB-P3 DATA CENTERS WITH STATE OF THE ART | BSNL | 709749 | Multi-States (Maharashtra, Telangana) | NA | 03/2020 | 06/2021 | 12/2025 | 461.42 | 461.42 | 166.02 | 81
August 2025 | 747 | Department of Telecommunications | Telecommunication | Saturation 4G mobile coverage of Uncovered Villages through USOF | Department of Telecommunications [DoT] | 400013 | PAN India | 07/2022 | 07/2022 | 06/2024 | 03/2026 | 26316 | 30620 | 9791.8 | 73
August 2025 | 748 | Department of Telecommunications | Telecommunication | 4G Services by BSNL | Department of Telecommunications [DoT] | 701593 | PAN India | 11/2020 | 11/2020 | 03/2024 | 03/2026 | 28466 | 19592 | 8390.32 | 96
August 2025 | 749 | Department of Telecommunications | Telecommunication | BharatNet | Department of Telecommunications [DoT] | 706775 | PAN India | 07/2017 | 10/2011 | 08/2023 | 03/2027 | 61109 | 188000 | 41486.14 | 81
August 2025 | 750 | Department of Telecommunications | Telecommunication | MPLS-IP BASED ACCESS AND AGGREGATION NETWORK [MAAN] IN BSNL ALONG WITH TEST AND MEASURING EQUIPMENT | BSNL | 709856 | PAN India | NA | 05/2023 | 08/2024 | 10/2025 | 645.13 | 645.13 | 364.34 | 91
August 2025 | 751 | Department of Telecommunications | Telecommunication | Planning, Engineering, Supply, Installation, Testing, Commissioning, Integration & Annual Maintenance of 4G mobile network at 1 Lakh sites on PAN India basis including Mumbai & Delhi LSA on turnkey basis under Phase IX.2 Project. | BSNL | 709857 | PAN India | NA | 06/2023 | 06/2025 | 03/2026 | 24544.55 | 24544.5 | 8391.17 | 96
August 2025 | 752 | Department of Telecommunications | Telecommunication | OPTICAL TRANSPORT NETWORK [OTN] PH-4 IN BSNL | BSNL | 709858 | PAN India | NA | 02/2024 | 08/2025 | 10/2025 | 810.99 | 810.99 | 741.9 | 100
August 2025 | 753 | Department of Water Resources, River Development & GR | Waste & Water | Interception and Diversion and STP works in Bhagalpur under Hybrid annuity based PPP mode-Namami Gange Programme | National Mission for Clean Ganga | 616600 | Bihar | 10/2017 | 03/2022 | 02/2025 | 12/2025 | 413.29 | 413.29 | 126.67 | 97
August 2025 | 754 | Department of Water Resources, River Development & GR | Waste & Water | Sewage Treatment Plant 100MLD and Sewerage Network 288 km in Digha-Patna under Hybrid annuity based PPP mode-Namami Gange Programme | National Mission for Clean Ganga | 616611 | Bihar | 08/2017 | 07/2019 | 12/2025 | - | 824 | 824 | 396.71 | 56
August 2025 | 755 | Department of Water Resources, River Development & GR | Waste & Water | Sewage Treatment Plant 50MLD and Sewerage Network 150 km in Kankarbagh- Patna under Hybrid annuity based PPP mode-Namami Gange Programme | National Mission for Clean Ganga | 616612 | Bihar | 08/2017 | 07/2019 | 12/2025 | - | 578.89 | 578.89 | 171.79 | 54
August 2025 | 756 | Department of Water Resources, River Development & GR | Waste & Water | Sewer Network, SPS and STP at Begusarai | National Mission for Clean Ganga | 616615 | Bihar | 03/2010 | 03/2018 | 04/2025 | 12/2025 | 230.06 | 230.06 | 261.82 | 97
August 2025 | 757 | Department of Water Resources, River Development & GR | Waste & Water | Sewer Networks, SPS and STP at Hajipur | National Mission for Clean Ganga | 616616 | Bihar | 03/2010 | 03/2018 | 06/2025 | 12/2025 | 305.19 | 305.19 | 346.46 | 95
August 2025 | 758 | Department of Water Resources, River Development & GR | Waste & Water | Interception & Diversion with Rehabilitation of sewerage scheme at Agra under Hybrid annuity based PPP model-Namami Gange Programme | National Mission for Clean Ganga | 616594 | Uttar Pradesh | 05/2020 | 04/2023 | 04/2025 | 12/2025 | 842.25 | 842.25 | 208.64 | 73
August 2025 | 759 | Department of Water Resources, River Development & GR | Waste & Water | Pollution Abatement Works for River Kali Meerut under Meerut Municipality Interception & Diversion with STP | National Mission for Clean Ganga | 616605 | Uttar Pradesh | 05/2020 | 11/2024 | 12/2024 | 05/2027 | 690.71 | 690.71 | 34.79 | 27
August 2025 | 760 | Department of Water Resources, River Development & GR | Waste & Water | Pollution Abatement works for River Ganga at Hooghly Chinsurah- Municipal Town Interception & Diversion with STP | National Mission for Clean Ganga | 616604 | West Bengal | 05/2018 | 12/2021 | 03/2025 | 12/2025 | 154.73 | 154.73 | 96.17 | 92
August 2025 | 761 | Department of Water Resources, River Development & GR | Water Resources | Sardar Gouthu Latchanna Thotapalli Barrage Project | Water Resources-AP | 400100 | Andhra Pradesh | NA | 01/2006 | 12/2019 | 06/2026 | 353.05 | 1023.24 | 869.11 | 95
August 2025 | 762 | Department of Water Resources, River Development & GR | Water Resources | Gundlakamma project | Water Resources-AP | 400101 | Andhra Pradesh | NA | 04/2005 | 12/2019 | 03/2027 | 397.41 | 697.39 | 610.89 | 98
August 2025 | 763 | Department of Water Resources, River Development & GR | Water Resources | Polavaram Irrigation Project | Water Resources-AP | 701415 | Andhra Pradesh | 02/2009 | 11/2004 | 04/2022 | 03/2026 | 10151.04 | 55548.9 | 24347.76 | 83
August 2025 | 764 | Department of Water Resources, River Development & GR | Water Resources | Borolia Irrigation Project | Department of Water Resources, River Development & GR | 701370 | Assam | NA | 12/1996 | 12/2022 | 03/2026 | 256.16 | 256.16 | 0 | 55
August 2025 | 765 | Department of Water Resources, River Development & GR | Water Resources | Punpun Barrage Project | Water Resources-BR | 400104 | Bihar | NA | 04/2007 | 12/2019 | 03/2026 | 571.07 | 658.12 | 469.66 | 44
August 2025 | 766 | Department of Water Resources, River Development & GR | Water Resources | Durgawati Reservoir Project | Irrigation and CAD-TG | 701371 | Bihar | NA | 04/1997 | 12/2019 | 12/2024 | 691.15 | 971.96 | 978.51 | 87
August 2025 | 767 | Department of Water Resources, River Development & GR | Water Resources | Kelo Irrigation Project | Water Resources-CT | 400111 | Chhattisgarh | NA | 04/2008 | 12/2019 | 06/2026 | 459.97 | 727.04 | 616.93 | 71
August 2025 | 768 | Department of Water Resources, River Development & GR | Water Resources | Kudali Irrigation Project | Department of Water Resources, River Development & GR | 701399 | Chhattisgarh | NA | 12/2009 | 12/2025 | - | 382.29 | 382.29 | 0 | 86
August 2025 | 769 | Department of Water Resources, River Development & GR | Water Resources | Sardar Sarovar CADWM Project | Narmada and Water Resources, Water Supply and Kalpsar Department-GJ | 400097 | Gujarat | NA | 04/2004 | 12/2019 | 03/2025 | 5021.76 | 6670.31 | 4954.99 | 90.3
August 2025 | 770 | Department of Water Resources, River Development & GR | Water Resources | Sardar Sarovar Project | Narmada and Water Resources, Water Supply and Kalpsar Department-GJ | 701372 | Gujarat | NA | 04/1996 | 12/2019 | 12/2025 | 20718.17 | 33412.5 | 31767.59 | 93
August 2025 | 771 | Department of Water Resources, River Development & GR | Water Resources | Subernarekha Multipurpose Project, Jharkhand | Department of Water Resources-JH | 701376 | Jharkhand | NA | 01/2012 | 12/2019 | 03/2026 | 3807.77 | 9579.58 | 5561.97 | 69
August 2025 | 772 | Department of Water Resources, River Development & GR | Water Resources | Upper Tunga Irrigation Project | Water Resources-KA | 701377 | Karnataka | NA | 04/2014 | 12/2019 | 12/2025 | 770.16 | 1606.07 | 1511.22 | 99
August 2025 | 773 | Department of Water Resources, River Development & GR | Water Resources | Omkareshwar CADWM Project | Water resource-mp | 400096 | Madhya Pradesh | NA | 04/2015 | 12/2019 | 03/2026 | 648.09 | 648.09 | 172.56 | 3
August 2025 | 774 | Department of Water Resources, River Development & GR | Water Resources | Bargi Diversion Project Phase - IV [km. 154 to km 197] | Water Resources-MP | 400115 | Madhya Pradesh | NA | 01/2009 | 12/2019 | 03/2025 | 751.03 | 893.35 | 746.19 | 75
August 2025 | 775 | Department of Water Resources, River Development & GR | Water Resources | Bargi Diversion Project Phase - III [km. 104 to km 154] | Water Resources-MP | 400116 | Madhya Pradesh | NA | 04/2007 | 12/2019 | 12/2025 | 1229.15 | 1399.7 | 1807.2 | 79
August 2025 | 776 | Department of Water Resources, River Development & GR | Water Resources | Gosikhurd CADWM Project | Department of water resources-MH - II | 400095 | Maharashtra | 04/2017 | 04/2017 | 12/2019 | 06/2026 | 743.73 | 743.73 | 252 | 50
August 2025 | 777 | Department of Water Resources, River Development & GR | Water Resources | Urmodi Irrigation Project | Department of water resources-MH - II | 400105 | Maharashtra | NA | 04/2018 | 06/2022 | 12/2026 | 580.79 | 895.81 | 713.46 | 76
August 2025 | 778 | Department of Water Resources, River Development & GR | Water Resources | Sulwade-Jamphal-Kanoli Lift Irrigation Scheme | Department of water resources-MH - II | 400107 | Maharashtra | NA | 02/2019 | 06/2023 | 06/2027 | 2407.67 | 2407.67 | 2436.43 | 80
August 2025 | 779 | Department of Water Resources, River Development & GR | Water Resources | Purna Barrage-2 [Ner Dhamana] Medium Irrigation Project | Department of water resources-MH - II | 400109 | Maharashtra | NA | 04/2018 | 06/2020 | 06/2026 | 848.07 | 888.43 | 690.49 | 69
August 2025 | 780 | Department of Water Resources, River Development & GR | Water Resources | Jigaon Irrigation Project | Department of water resources-MH - II | 400112 | Maharashtra | NA | 04/2018 | 06/2028 | - | 7222.95 | 7222.95 | 8501.45 | 90
August 2025 | 781 | Department of Water Resources, River Development & GR | Water Resources | Waghur Project | Department of water resources-MH - II | 701383 | Maharashtra | NA | 04/1996 | 12/2019 | 03/2026 | 1058.99 | 1758.51 | 1530.45 | 89
August 2025 | 782 | Department of Water Resources, River Development & GR | Water Resources | Gosikhurd Project | Department of water resources-MH - II | 701386 | Maharashtra | 12/2017 | 04/2008 | 12/2019 | 06/2026 | 7196.47 | 12770.1 | 13533.29 | 72
August 2025 | 783 | Department of Water Resources, River Development & GR | Water Resources | Aruna Medium Irrigation Project | Department of water resources-MH - II | 701391 | Maharashtra | NA | 01/2010 | 12/2019 | 12/2025 | 210.45 | 1472.14 | 1697.94 | 97
August 2025 | 784 | Department of Water Resources, River Development & GR | Water Resources | Lower Pedhi Project | Department of water resources-MH - II | 701396 | Maharashtra | NA | 04/2008 | 12/2019 | 06/2026 | 255.97 | 1480.7 | 1324.78 | 64
August 2025 | 785 | Department of Water Resources, River Development & GR | Water Resources | Nardave Medium Irrigation Project | Department of water resources-MH - II | 701398 | Maharashtra | NA | 04/2009 | 12/2019 | 06/2026 | 211.46 | 781.85 | 623.5 | 72
August 2025 | 786 | Department of Water Resources, River Development & GR | Water Resources | Thoubal Multipurpose Project | Water Resources Department-MN | 701400 | Manipur | 01/2022 | 04/1997 | 12/2019 | 03/2026 | 1449.44 | 1822.24 | 1837.91 | 98
August 2025 | 787 | Department of Water Resources, River Development & GR | Water Resources | North Koel Reservoir Project | Department of Water Resources, River Development & GR | 701412 | Multi-States (Bihar, Jharkhand) | NA | 01/2021 | 03/2021 | 03/2026 | 1622.27 | 2430.76 | 142.1 | 32
August 2025 | 788 | Department of Water Resources, River Development & GR | Water Resources | Integrated Anandpur Barrage Project | Water Resources-OR | 603945 | Odisha | NA | 01/1998 | 12/2019 | 06/2026 | 567.03 | 2990.05 | 2629.74 | 62
August 2025 | 789 | Department of Water Resources, River Development & GR | Water Resources | Kanupur Irrigation Project | Irrigation and CAD-TG | 701404 | Odisha | NA | 01/2004 | 12/2019 | 12/2024 | 989.43 | 2301.28 | 2563.56 | 79
August 2025 | 790 | Department of Water Resources, River Development & GR | Water Resources | Relining of Rajasthan feeder and Sirhind Feeder canal | Department of Water Resources-PB | 701410 | Punjab | 02/2016 | 04/2018 | 06/2021 | 06/2026 | 1441.26 | 2462.16 | 3000.36 | 80
August 2025 | 791 | Department of Water Resources, River Development & GR | Water Resources | Shahpur Kandi Dam Project | Department of Water Resources-PB | 701411 | Punjab | 02/2010 | 04/2018 | 06/2022 | 10/2025 | 2285.81 | 2715.7 | 2072.33 | 80
August 2025 | 792 | Department of Water Resources, River Development & GR | Water Resources | Sri Ram Sagar Project Stage - II | Irrigation and CAD-TG | 400102 | Telangana | NA | 04/2005 | 12/2019 | 03/2026 | 736.13 | 949.87 | 940.7 | 96
August 2025 | 793 | Department of Water Resources, River Development & GR | Water Resources | Indiramma Flood Flow Canal Project | Irrigation and CAD-TG | 400103 | Telangana | NA | 01/2006 | 12/2019 | 12/2026 | 1331.3 | 5940.09 | 4491.08 | 92
August 2025 | 794 | Department of Water Resources, River Development & GR | Water Resources | J. Chokka Rao Devadula Lift Irrigation Scheme | Irrigation and CAD-TG | 701405 | Telangana | NA | 04/2006 | 12/2019 | 12/2025 | 8200.71 | 14730 | 4558.89 | 87
August 2025 | 795 | Department of Water Resources, River Development & GR | Water Resources | Rajiv Bhima Lift Irrigation Scheme | Irrigation and CAD-TG | 701406 | Telangana | NA | 01/2008 | 12/2019 | 03/2026 | 1402 | 2509.66 | 1839.76 | 100
August 2025 | 796 | Department of Water Resources, River Development & GR | Water Resources | Saryu Nahar CADWM Project | Irrigation & Water Resources-UP | 400093 | Uttar Pradesh | NA | 04/2017 | 12/2019 | 03/2026 | 1672.7 | 1672.7 | 0 | 0
August 2025 | 797 | Department of Water Resources, River Development & GR | Water Resources | Arjun Sahayak Project | Irrigation & Water Resources-UP | 400117 | Uttar Pradesh | NA | 04/2009 | 12/2019 | 12/2019 | 741.38 | 2465.68 | 3218.3 | 100
August 2025 | 798 | Department of Water Resources, River Development & GR | Water Resources | Morna [Gureghar] Irrigation Project | Department of Water Resources, River Development & GR | 701395 | Uttar Pradesh | NA | 12/2007 | 12/2025 | - | 219.9 | 219.9 | 0 | 0
August 2025 | 799 | Department of Water Resources, River Development & GR | Water Resources | Madhya Ganga canal Phase-II | Irrigation & Water Resources-UP | 701408 | Uttar Pradesh | NA | 07/2007 | 12/2019 | 12/2025 | 1060.67 | 4417.21 | 4415.24 | 82
August 2025 | 800 | Department of Water Resources, River Development & GR | Water Resources | Jamrani Dam Multipurpose Project | Irrigation-UK | 613787 | Uttarakhand | 10/2023 | 04/2023 | 06/2029 | - | 2584.1 | 2584.1 | 968.52 | 16

## Oct - Ministry-wise
Month | Ministry/Department | Sector | Project Count | Original Cost (Rs Cr) | Latest Revised Cost (Rs Cr) | Cumulative Expenditure (Rs Cr)
October 2025 | Department for Promotion of Industry & Internal Trade | Real Estate | 2 | 3841.25 | 3841.25 | 590.15
October 2025 | Department of Higher Education | Education | 29 | 12467.21 | 12401.2 | 7908.95
October 2025 | Department of Sports | Education | 1 | 906.47 | 611.74 | 553.38
October 2025 | Department of Telecommunications | Telecommunication | 15 | 152734.45 | 274827 | 77354.9
October 2025 | Department of Water Resources, River Development & GR | Waste & Water | 8 | 4039.12 | 4039.12 | 1643.05
October 2025 | Department of Water Resources, River Development & GR | Water Resources | 39 | 93740.23 | 193594 | 138530
October 2025 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | 26 | 23049.84 | 23511 | 24797.1
October 2025 | Ministry of Coal | Coal | 116 | 157554.96 | 155011 | 48288.1
October 2025 | Ministry of Coal | Electricity Generation | 6 | 50201.48 | 54744.6 | 25385.2
October 2025 | Ministry of Coal | Railways | 2 | 3485.86 | 4250.56 | 1815.47
October 2025 | Ministry of Health & Family Welfare | Healthcare | 3 | 4155 | 4492.95 | 2477.91
October 2025 | Ministry of Housing & Urban Affairs | Construction | 2 | 1290.53 | 1290.52 | 633.46
October 2025 | Ministry of Housing & Urban Affairs | Inland Waterways | 1 | 63246 | 63246 | 28779
October 2025 | Ministry of Housing & Urban Affairs | Real Estate | 4 | 33749.85 | 33749.8 | 58.58
October 2025 | Ministry of Housing & Urban Affairs | Urban Public Transport | 22 | 235216.87 | 255798 | 168648
October 2025 | Ministry of Housing & Urban Affairs | Waste & Water | 25 | 6085.6 | 6085.6 | 38687.6
October 2025 | Ministry of Labour and Employment | Healthcare | 15 | 3576.21 | 3818.61 | 3422.37
October 2025 | Ministry of Mines | Construction | 1 | 255.37 | 255.37 | 85.9
October 2025 | Ministry of Mines | Metals & Mining | 9 | 12736.35 | 15116.5 | 6356.85
October 2025 | Ministry of Petroleum & Natural Gas | Energy Storage | 16 | 81301.48 | 120224 | 93188.6
October 2025 | Ministry of Petroleum & Natural Gas | Oil & Gas | 86 | 348775.78 | 377915 | 185369
October 2025 | Ministry of Ports, Shipping and Waterways | Healthcare | 1 | 693 | 693 | 58
October 2025 | Ministry of Ports, Shipping and Waterways | Inland Waterways | 2 | 5546.18 | 5258.15 | 3710.31
October 2025 | Ministry of Ports, Shipping and Waterways | Shipping | 10 | 16923.41 | 17089.9 | 10375
October 2025 | Ministry of Ports, Shipping and Waterways | Tourism, Hospitality & Wellness | 1 | 573 | 1238.05 | 496.63
October 2025 | Ministry of Power | Coal | 2 | 2083 | 2365 | 911.94
October 2025 | Ministry of Power | Electricity Generation | 30 | 223418.07 | 278208 | 136137
October 2025 | Ministry of Power | Transmission & Distribution | 68 | 150796.17 | 157311 | 59403.7
October 2025 | Ministry of Railways | Railways | 257 | 839222.35 | 988283 | 536735
October 2025 | Ministry of Steel | Metals & Mining | 1 | 1700 | 1756.2 | 133.22
October 2025 | Ministry of Steel | Steel | 20 | 19266.64 | 22504.9 | 8653.34

## Oct - State-wise
Month | State | Ministry/Department | Sector | Project Count | Original Cost (Rs Cr) | Latest Revised Cost (Rs Cr) | Cumulative Expenditure (Rs Cr)
October 2025 |  | Ministry of Steel | Steel | 1 | 2518.39 | 2518.39 | 152.23
October 2025 | Offshore | Ministry of Petroleum & Natural Gas | Oil & Gas | 6 | 19714.58 | 22972.8 | 11505.5
October 2025 | Offshore | Ministry of Ports, Shipping and Waterways | Inland Waterways | 1 | 177 | 197 | 183.32
October 2025 | Offshore | Ministry of Railways | Railways | 2 | 150819 | 150819 | 2520.51
October 2025 | PAN India | Department of Telecommunications | Telecommunication | 6 | 141891.67 | 264213 | 74254.01
October 2025 | Andaman & Nicobar | Ministry of Housing & Urban Affairs | Real Estate | 1 | 209.88 | 209.88 | 0
October 2025 | Andhra Pradesh | Department for Promotion of Industry & Internal Trade | Real Estate | 1 | 2139.44 | 2139.44 | 472.8
October 2025 | Andhra Pradesh | Department of Higher Education | Education | 1 | 305 | 305 | 19.96
October 2025 | Andhra Pradesh | Department of Telecommunications | Telecommunication | 3 | 7147.17 | 7147.17 | 1835.88
October 2025 | Andhra Pradesh | Department of Water Resources, River Development & GR | Water Resources | 3 | 10901.5 | 57269.5 | 26326.17
October 2025 | Andhra Pradesh | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | 3 | 1224.86 | 1224.86 | 676.79
October 2025 | Andhra Pradesh | Ministry of Housing & Urban Affairs | Waste & Water | 1 | 172.22 | 172.22 | 799.74
October 2025 | Andhra Pradesh | Ministry of Labour and Employment | Healthcare | 1 | 384.27 | 384.27 | 105
October 2025 | Andhra Pradesh | Ministry of Petroleum & Natural Gas | Energy Storage | 2 | 2898.34 | 3050 | 2344.92
October 2025 | Andhra Pradesh | Ministry of Petroleum & Natural Gas | Oil & Gas | 4 | 37804 | 37864 | 32464.75
October 2025 | Andhra Pradesh | Ministry of Power | Transmission & Distribution | 5 | 13395.24 | 13395.2 | 4917.6
October 2025 | Andhra Pradesh | Ministry of Railways | Railways | 27 | 52663.77 | 59888.8 | 33853.71
October 2025 | Arunachal Pradesh | Department of Higher Education | Education | 1 | 592.61 | 592.61 | 550.27
October 2025 | Arunachal Pradesh | Department of Telecommunications | Telecommunication | 1 | 1255.49 | 1255.49 | 284.04
October 2025 | Arunachal Pradesh | Ministry of Petroleum & Natural Gas | Energy Storage | 1 | 43129 | 79459 | 61926.61
October 2025 | Arunachal Pradesh | Ministry of Petroleum & Natural Gas | Oil & Gas | 1 | 9265 | 9265 | 6603.95
October 2025 | Arunachal Pradesh | Ministry of Power | Electricity Generation | 4 | 41850.64 | 61640.8 | 29133.62
October 2025 | Arunachal Pradesh | Ministry of Power | Transmission & Distribution | 2 | 4963.8 | 9338.7 | 7705.17
October 2025 | Arunachal Pradesh | Ministry of Railways | Railways | 1 | 435 | 1250 | 542.07
October 2025 | Assam | Department of Higher Education | Education | 1 | 153.71 | 153.71 | 124.33
October 2025 | Assam | Department of Telecommunications | Telecommunication | 1 | 1255.49 | 1255.49 | 284.04
October 2025 | Assam | Department of Water Resources, River Development & GR | Water Resources | 1 | 256.16 | 256.16 | 44.7
October 2025 | Assam | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | 1 | 1712 | 1712 | 2397.37
October 2025 | Assam | Ministry of Coal | Coal | 2 | 449.23 | 449.23 | 187.07
October 2025 | Assam | Ministry of Housing & Urban Affairs | Waste & Water | 1 | 186.8 | 186.8 | 1664.41
October 2025 | Assam | Ministry of Labour and Employment | Healthcare | 1 | 143.23 | 154.75 | 101.83
October 2025 | Assam | Ministry of Petroleum & Natural Gas | Energy Storage | 3 | 10768.4 | 11947.4 | 10126.88
October 2025 | Assam | Ministry of Petroleum & Natural Gas | Oil & Gas | 12 | 26269.15 | 36624 | 27088.69
October 2025 | Assam | Ministry of Power | Electricity Generation | 1 | 6285.33 | 26075.5 | 25244.57
October 2025 | Assam | Ministry of Power | Transmission & Distribution | 1 | 5111.33 | 6700 | 5317.79
October 2025 | Assam | Ministry of Railways | Railways | 7 | 14593.57 | 16308.6 | 10247.14
October 2025 | Bihar | Department of Higher Education | Education | 1 | 499.21 | 499.21 | 441.47
October 2025 | Bihar | Department of Telecommunications | Telecommunication | 4 | 4220.71 | 3992.24 | 1070.43
October 2025 | Bihar | Department of Water Resources, River Development & GR | Waste & Water | 5 | 2351.43 | 2351.43 | 1303.45
October 2025 | Bihar | Department of Water Resources, River Development & GR | Water Resources | 2 | 2193.34 | 3088.88 | 598.72
October 2025 | Bihar | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | 3 | 3541.56 | 3541.56 | 1338.95
October 2025 | Bihar | Ministry of Housing & Urban Affairs | Urban Public Transport | 1 | 13365.77 | 13365.8 | 4039.77
October 2025 | Bihar | Ministry of Housing & Urban Affairs | Waste & Water | 1 | 158.78 | 158.78 | 602.5
October 2025 | Bihar | Ministry of Petroleum & Natural Gas | Energy Storage | 1 | 10228 | 11407 | 9921.29
October 2025 | Bihar | Ministry of Petroleum & Natural Gas | Oil & Gas | 6 | 24473.5 | 26338.2 | 13509.65
October 2025 | Bihar | Ministry of Ports, Shipping and Waterways | Inland Waterways | 1 | 5369.18 | 5061.15 | 3526.99
October 2025 | Bihar | Ministry of Power | Electricity Generation | 1 | 10439.09 | 13756.6 | 12571.15
October 2025 | Bihar | Ministry of Power | Transmission & Distribution | 2 | 751.63 | 751.63 | 1.03
October 2025 | Bihar | Ministry of Railways | Railways | 23 | 50603.79 | 55072 | 22922.7
October 2025 | Chhattisgarh | Department of Telecommunications | Telecommunication | 3 | 7147.17 | 7147.17 | 1835.88
October 2025 | Chhattisgarh | Department of Water Resources, River Development & GR | Water Resources | 2 | 842.26 | 1109.33 | 855.96
October 2025 | Chhattisgarh | Ministry of Coal | Coal | 14 | 31042.56 | 31042.6 | 13042.96
October 2025 | Chhattisgarh | Ministry of Coal | Railways | 1 | 1686.22 | 1686.22 | 353.12
October 2025 | Chhattisgarh | Ministry of Petroleum & Natural Gas | Oil & Gas | 2 | 10056.25 | 10467 | 6682.3
October 2025 | Chhattisgarh | Ministry of Power | Electricity Generation | 2 | 25321 | 25321 | 3730.56
October 2025 | Chhattisgarh | Ministry of Power | Transmission & Distribution | 1 | 385.84 | 385.84 | 382.4
October 2025 | Chhattisgarh | Ministry of Railways | Railways | 19 | 34549.26 | 36180.5 | 18969.33
October 2025 | Chhattisgarh | Ministry of Steel | Metals & Mining | 1 | 1700 | 1756.2 | 133.22
October 2025 | Chhattisgarh | Ministry of Steel | Steel | 6 | 7530.14 | 10050.1 | 5536.55
October 2025 | Dadra & Nagar Haveli and Daman & Diu | Ministry of Housing & Urban Affairs | Waste & Water | 1 | 210 | 210 | 0
October 2025 | Dadra & Nagar Haveli and Daman & Diu | Ministry of Power | Transmission & Distribution | 1 | 4546.26 | 4546.26 | 4210.3
October 2025 | Dadra & Nagar Haveli and Daman & Diu | Ministry of Railways | Railways | 1 | 108000 | 108000 | 82967.89
October 2025 | Delhi | Department of Higher Education | Education | 2 | 706.49 | 709.42 | 312.96
October 2025 | Delhi | Department of Telecommunications | Telecommunication | 1 | 248.2 | 248.2 | 236.91
October 2025 | Delhi | Ministry of Housing & Urban Affairs | Construction | 1 | 646.53 | 646.52 | 545.86
October 2025 | Delhi | Ministry of Housing & Urban Affairs | Real Estate | 1 | 32850 | 32850 | 0
October 2025 | Delhi | Ministry of Housing & Urban Affairs | Urban Public Transport | 4 | 69853.45 | 69853.4 | 44578.92
October 2025 | Delhi | Ministry of Power | Transmission & Distribution | 4 | 4356.47 | 4908.47 | 4066.48
October 2025 | Delhi | Ministry of Railways | Railways | 15 | 28623.17 | 28623.2 | 5954.91
October 2025 | Goa | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | 1 | 255.69 | 255.69 | 154.3
October 2025 | Goa | Ministry of Railways | Railways | 2 | 5804.49 | 6182.62 | 6215.96
October 2025 | Gujarat | Department of Higher Education | Education | 1 | 490.63 | 490.63 | 313.84
October 2025 | Gujarat | Department of Telecommunications | Telecommunication | 1 | 336.89 | 301.13 | 227.82
October 2025 | Gujarat | Department of Water Resources, River Development & GR | Water Resources | 2 | 25739.93 | 40082.8 | 36815.85
October 2025 | Gujarat | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | 1 | 1305 | 1551 | 718.2
October 2025 | Gujarat | Ministry of Coal | Electricity Generation | 2 | 3719.69 | 3719.69 | 981.48
October 2025 | Gujarat | Ministry of Housing & Urban Affairs | Real Estate | 1 | 539 | 539 | 39.63
October 2025 | Gujarat | Ministry of Housing & Urban Affairs | Urban Public Transport | 3 | 28177.49 | 30329 | 24498.08
October 2025 | Gujarat | Ministry of Housing & Urban Affairs | Waste & Water | 1 | 200 | 200 | 100
October 2025 | Gujarat | Ministry of Labour and Employment | Healthcare | 3 | 973.35 | 973.35 | 270.39
October 2025 | Gujarat | Ministry of Petroleum & Natural Gas | Energy Storage | 3 | 62245 | 98575 | 77278.48
October 2025 | Gujarat | Ministry of Petroleum & Natural Gas | Oil & Gas | 11 | 32704.12 | 32296.3 | 23575.09
October 2025 | Gujarat | Ministry of Ports, Shipping and Waterways | Shipping | 3 | 4514.64 | 4681.1 | 1104.03
October 2025 | Gujarat | Ministry of Ports, Shipping and Waterways | Tourism, Hospitality & Wellness | 1 | 573 | 1238.05 | 496.63
October 2025 | Gujarat | Ministry of Power | Electricity Generation | 1 | 339.35 | 339.35 | 317.59
October 2025 | Gujarat | Ministry of Power | Transmission & Distribution | 16 | 50389.44 | 50388.9 | 13736.39
October 2025 | Gujarat | Ministry of Railways | Railways | 26 | 185518.86 | 262039 | 219809.16
October 2025 | Haryana | Ministry of Health & Family Welfare | Healthcare | 1 | 1299 | 1299 | 349.41
October 2025 | Haryana | Ministry of Housing & Urban Affairs | Urban Public Transport | 1 | 6230.99 | 6230.99 | 72.38
October 2025 | Haryana | Ministry of Housing & Urban Affairs | Waste & Water | 2 | 491.2 | 491.2 | 3435.51
October 2025 | Haryana | Ministry of Petroleum & Natural Gas | Energy Storage | 1 | 9028 | 9028 | 7292.34
October 2025 | Haryana | Ministry of Petroleum & Natural Gas | Oil & Gas | 5 | 45925.07 | 49596.1 | 36223.79
October 2025 | Haryana | Ministry of Power | Transmission & Distribution | 4 | 13362 | 13914 | 3062.26
October 2025 | Haryana | Ministry of Railways | Railways | 4 | 53464 | 126368 | 125637.7
October 2025 | Himachal Pradesh | Department of Higher Education | Education | 3 | 811.15 | 921.89 | 595.63
October 2025 | Himachal Pradesh | Department of Telecommunications | Telecommunication | 1 | 336.89 | 301.13 | 227.82
October 2025 | Himachal Pradesh | Ministry of Power | Electricity Generation | 4 | 7728.04 | 12301.5 | 4286.22
October 2025 | Himachal Pradesh | Ministry of Railways | Railways | 3 | 17005 | 17005.1 | 9510.37
October 2025 | Jammu and Kashmir | Department of Higher Education | Education | 1 | 424.93 | 500.91 | 484.52
October 2025 | Jammu and Kashmir | Department of Telecommunications | Telecommunication | 1 | 336.89 | 301.13 | 227.82
October 2025 | Jammu and Kashmir | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | 1 | 861.37 | 861.37 | 212.12
October 2025 | Jammu and Kashmir | Ministry of Health & Family Welfare | Healthcare | 1 | 1828 | 1828 | 1321.7
October 2025 | Jammu and Kashmir | Ministry of Labour and Employment | Healthcare | 1 | 131.05 | 164.93 | 1747.76
October 2025 | Jammu and Kashmir | Ministry of Petroleum & Natural Gas | Energy Storage | 1 | 676.89 | 715.89 | 550.45
October 2025 | Jammu and Kashmir | Ministry of Petroleum & Natural Gas | Oil & Gas | 2 | 1059.9 | 1059.9 | 234.3
October 2025 | Jammu and Kashmir | Ministry of Power | Electricity Generation | 4 | 22207.77 | 27945.1 | 12904.53
October 2025 | Jammu and Kashmir | Ministry of Power | Transmission & Distribution | 3 | 825.43 | 825.43 | 599.25
October 2025 | Jharkhand | Department of Telecommunications | Telecommunication | 3 | 7147.17 | 7147.17 | 1835.88
October 2025 | Jharkhand | Department of Water Resources, River Development & GR | Water Resources | 2 | 5430.04 | 12010.3 | 5941.33
October 2025 | Jharkhand | Ministry of Coal | Coal | 28 | 51354.95 | 51119.3 | 10572.55
October 2025 | Jharkhand | Ministry of Coal | Railways | 1 | 1799.64 | 2564.34 | 1462.35
October 2025 | Jharkhand | Ministry of Housing & Urban Affairs | Waste & Water | 3 | 654.14 | 654.14 | 3255.3
October 2025 | Jharkhand | Ministry of Mines | Metals & Mining | 2 | 3370.02 | 3370.02 | 23.43
October 2025 | Jharkhand | Ministry of Petroleum & Natural Gas | Energy Storage | 1 | 10228 | 11407 | 9921.29
October 2025 | Jharkhand | Ministry of Petroleum & Natural Gas | Oil & Gas | 3 | 2010.07 | 2010.07 | 628.64
October 2025 | Jharkhand | Ministry of Ports, Shipping and Waterways | Inland Waterways | 1 | 5369.18 | 5061.15 | 3526.99
October 2025 | Jharkhand | Ministry of Power | Coal | 2 | 2083 | 2365 | 911.94
October 2025 | Jharkhand | Ministry of Power | Electricity Generation | 2 | 31470 | 34660 | 19242.94
October 2025 | Jharkhand | Ministry of Power | Transmission & Distribution | 1 | 1842.25 | 1842.25 | 1648.05
October 2025 | Jharkhand | Ministry of Railways | Railways | 12 | 41769.95 | 42630.6 | 15247.24
October 2025 | Jharkhand | Ministry of Steel | Steel | 6 | 2854.58 | 3572.87 | 1383.16
October 2025 | Karnataka | Department for Promotion of Industry & Internal Trade | Real Estate | 1 | 1701.81 | 1701.81 | 117.35
October 2025 | Karnataka | Department of Higher Education | Education | 1 | 420.41 | 420.41 | 364.44
October 2025 | Karnataka | Department of Water Resources, River Development & GR | Water Resources | 1 | 770.16 | 1606.07 | 1515.32
October 2025 | Karnataka | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | 3 | 1143.4 | 1143.4 | 553.88
October 2025 | Karnataka | Ministry of Housing & Urban Affairs | Urban Public Transport | 2 | 41193.24 | 45483.2 | 38533.6
October 2025 | Karnataka | Ministry of Housing & Urban Affairs | Waste & Water | 2 | 337.69 | 337.69 | 1644.73
October 2025 | Karnataka | Ministry of Labour and Employment | Healthcare | 2 | 428.92 | 428.92 | 27.8
October 2025 | Karnataka | Ministry of Petroleum & Natural Gas | Energy Storage | 1 | 678 | 1732 | 800.88
October 2025 | Karnataka | Ministry of Petroleum & Natural Gas | Oil & Gas | 5 | 9662 | 12693.6 | 8966.37
October 2025 | Karnataka | Ministry of Ports, Shipping and Waterways | Shipping | 1 | 153.23 | 153.23 | 50.1
October 2025 | Karnataka | Ministry of Power | Transmission & Distribution | 7 | 16061.01 | 16061 | 3412.08
October 2025 | Karnataka | Ministry of Railways | Railways | 17 | 25363.29 | 31781.9 | 17620.93
October 2025 | Karnataka | Ministry of Steel | Steel | 1 | 1043.63 | 1043.63 | 288.87
October 2025 | Kerala | Department of Higher Education | Education | 1 | 1006.45 | 1217.4 | 641.73
October 2025 | Kerala | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | 1 | 484.57 | 484.57 | 91.67
October 2025 | Kerala | Ministry of Housing & Urban Affairs | Urban Public Transport | 1 | 1957.05 | 1957.05 | 425.58
October 2025 | Kerala | Ministry of Petroleum & Natural Gas | Oil & Gas | 3 | 7996.87 | 10990.9 | 5019.06
October 2025 | Kerala | Ministry of Ports, Shipping and Waterways | Shipping | 1 | 1799 | 1799 | 1558.39
October 2025 | Kerala | Ministry of Railways | Railways | 3 | 2846 | 5183.64 | 2862.02
October 2025 | Ladakh | Department of Telecommunications | Telecommunication | 1 | 336.89 | 301.13 | 227.82
October 2025 | Ladakh | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | 1 | 480 | 640 | 471.59
October 2025 | Ladakh | Ministry of Power | Transmission & Distribution | 1 | 288.71 | 288.71 | 280.02
October 2025 | Madhya Pradesh | Department of Higher Education | Education | 1 | 496.28 | 496.28 | 38.62
October 2025 | Madhya Pradesh | Department of Telecommunications | Telecommunication | 3 | 3883.82 | 3691.11 | 842.61
October 2025 | Madhya Pradesh | Department of Water Resources, River Development & GR | Water Resources | 3 | 2628.27 | 2941.14 | 2892.91
October 2025 | Madhya Pradesh | Ministry of Coal | Coal | 14 | 8634.02 | 8634.02 | 3457.47
October 2025 | Madhya Pradesh | Ministry of Housing & Urban Affairs | Urban Public Transport | 2 | 14442.2 | 14442.2 | 7899.62
October 2025 | Madhya Pradesh | Ministry of Housing & Urban Affairs | Waste & Water | 4 | 1243.05 | 1243.05 | 9847.62
October 2025 | Madhya Pradesh | Ministry of Mines | Metals & Mining | 1 | 1856.36 | 1856.36 | 940.27
October 2025 | Madhya Pradesh | Ministry of Petroleum & Natural Gas | Energy Storage | 1 | 10088 | 10088 | 8059.53
October 2025 | Madhya Pradesh | Ministry of Petroleum & Natural Gas | Oil & Gas | 2 | 51211.25 | 51622 | 8616.2
October 2025 | Madhya Pradesh | Ministry of Power | Transmission & Distribution | 7 | 17765 | 17765 | 3666.37
October 2025 | Madhya Pradesh | Ministry of Railways | Railways | 19 | 58468.02 | 72465.1 | 43676.54
October 2025 | Maharashtra | Department of Higher Education | Education | 2 | 250.33 | 446.26 | 183.91
October 2025 | Maharashtra | Department of Telecommunications | Telecommunication | 4 | 7608.59 | 7608.59 | 2001.9
October 2025 | Maharashtra | Department of Water Resources, River Development & GR | Water Resources | 11 | 22660.36 | 32345.7 | 33732.04
October 2025 | Maharashtra | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | 1 | 500.48 | 500.48 | 332.26
October 2025 | Maharashtra | Ministry of Coal | Coal | 25 | 12455.88 | 12455.9 | 3205.76
October 2025 | Maharashtra | Ministry of Housing & Urban Affairs | Urban Public Transport | 7 | 46771.57 | 60911.6 | 33511.04
October 2025 | Maharashtra | Ministry of Housing & Urban Affairs | Waste & Water | 5 | 1088.72 | 1088.72 | 8573.67
October 2025 | Maharashtra | Ministry of Labour and Employment | Healthcare | 3 | 884.31 | 886.08 | 548.78
October 2025 | Maharashtra | Ministry of Petroleum & Natural Gas | Energy Storage | 1 | 281.35 | 389.67 | 238.39
October 2025 | Maharashtra | Ministry of Petroleum & Natural Gas | Oil & Gas | 13 | 34264.24 | 37660.4 | 21424.44
October 2025 | Maharashtra | Ministry of Ports, Shipping and Waterways | Healthcare | 1 | 693 | 693 | 58
October 2025 | Maharashtra | Ministry of Ports, Shipping and Waterways | Shipping | 2 | 6900 | 6900 | 6064.89
October 2025 | Maharashtra | Ministry of Power | Transmission & Distribution | 3 | 29589.67 | 29589.7 | 6229.42
October 2025 | Maharashtra | Ministry of Railways | Railways | 35 | 266858.79 | 358832 | 267526.11
October 2025 | Manipur | Department of Sports | Education | 1 | 906.47 | 611.74 | 553.38
October 2025 | Manipur | Department of Water Resources, River Development & GR | Water Resources | 1 | 1449.44 | 1822.24 | 1837.91
October 2025 | Manipur | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | 1 | 499 | 499 | 155.72
October 2025 | Manipur | Ministry of Petroleum & Natural Gas | Oil & Gas | 1 | 9265 | 9265 | 6603.95
October 2025 | Manipur | Ministry of Power | Transmission & Distribution | 1 | 5111.33 | 6700 | 5317.79
October 2025 | Manipur | Ministry of Railways | Railways | 1 | 14323 | 21885.9 | 15598.11
October 2025 | Meghalaya | Department of Higher Education | Education | 1 | 494.52 | 494.52 | 419.57
October 2025 | Meghalaya | Department of Telecommunications | Telecommunication | 1 | 971.96 | 971.96 | 208.25
October 2025 | Meghalaya | Ministry of Petroleum & Natural Gas | Oil & Gas | 1 | 9265 | 9265 | 6603.95
October 2025 | Meghalaya | Ministry of Power | Transmission & Distribution | 1 | 5111.33 | 6700 | 5317.79
October 2025 | Mizoram | Department of Higher Education | Education | 1 | 474.23 | 474.23 | 167.55
October 2025 | Mizoram | Ministry of Petroleum & Natural Gas | Oil & Gas | 1 | 9265 | 9265 | 6603.95
October 2025 | Mizoram | Ministry of Power | Transmission & Distribution | 1 | 5111.33 | 6700 | 5317.79
October 2025 | Nagaland | Department of Higher Education | Education | 1 | 275.63 | 275.63 | 261.24
October 2025 | Nagaland | Ministry of Petroleum & Natural Gas | Oil & Gas | 2 | 9492.62 | 9492.62 | 6614.75
October 2025 | Nagaland | Ministry of Power | Transmission & Distribution | 1 | 5111.33 | 6700 | 5317.79
October 2025 | Nagaland | Ministry of Railways | Railways | 2 | 8786.7 | 8786.7 | 5585.56
October 2025 | Odisha | Department of Higher Education | Education | 1 | 1229.32 | 773.76 | 838.21
October 2025 | Odisha | Department of Telecommunications | Telecommunication | 3 | 7147.17 | 7147.17 | 1835.88
October 2025 | Odisha | Department of Water Resources, River Development & GR | Water Resources | 2 | 1556.46 | 5291.33 | 5342.49
October 2025 | Odisha | Ministry of Coal | Coal | 12 | 36526.28 | 34218 | 13233.8
October 2025 | Odisha | Ministry of Coal | Electricity Generation | 1 | 27212.96 | 27213 | 2549.31
October 2025 | Odisha | Ministry of Labour and Employment | Healthcare | 1 | 164.6 | 164.6 | 16.4
October 2025 | Odisha | Ministry of Mines | Metals & Mining | 5 | 7343.97 | 9724.14 | 5258.15
October 2025 | Odisha | Ministry of Petroleum & Natural Gas | Energy Storage | 2 | 12886.34 | 14217 | 12204.27
October 2025 | Odisha | Ministry of Petroleum & Natural Gas | Oil & Gas | 5 | 25285.44 | 23768.5 | 16095.66
October 2025 | Odisha | Ministry of Ports, Shipping and Waterways | Shipping | 1 | 3004.63 | 3004.63 | 1149.79
October 2025 | Odisha | Ministry of Power | Electricity Generation | 1 | 11843.75 | 12543 | 4839.68
October 2025 | Odisha | Ministry of Power | Transmission & Distribution | 1 | 342.69 | 342.69 | 0.71
October 2025 | Odisha | Ministry of Railways | Railways | 25 | 46848.33 | 51580.4 | 33305.37
October 2025 | Odisha | Ministry of Railways | Railways | 1 | 267.61 | 267.61 | 0
October 2025 | Odisha | Ministry of Steel | Steel | 1 | 1105.23 | 1105.23 | 790.11
October 2025 | Puducherry | Department of Higher Education | Education | 1 | 618.34 | 544.34 | 529.9
October 2025 | Puducherry | Ministry of Railways | Railways | 1 | 713 | 981 | 598.38
October 2025 | Punjab | Department of Higher Education | Education | 2 | 559.3 | 559.3 | 290.39
October 2025 | Punjab | Department of Water Resources, River Development & GR | Water Resources | 2 | 3727.07 | 5177.86 | 5182.41
October 2025 | Punjab | Ministry of Housing & Urban Affairs | Waste & Water | 2 | 545.53 | 545.53 | 2807.11
October 2025 | Punjab | Ministry of Petroleum & Natural Gas | Oil & Gas | 5 | 12693.36 | 12693.4 | 8097.02
October 2025 | Punjab | Ministry of Power | Transmission & Distribution | 1 | 5969 | 5969 | 485.87
October 2025 | Punjab | Ministry of Railways | Railways | 3 | 15702.64 | 15703 | 9117.19
October 2025 | Rajasthan | Department of Telecommunications | Telecommunication | 2 | 758.54 | 530.07 | 369.83
October 2025 | Rajasthan | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | 2 | 1367 | 1367 | 696.69
October 2025 | Rajasthan | Ministry of Coal | Electricity Generation | 1 | 1813 | 1813 | 1167.4
October 2025 | Rajasthan | Ministry of Petroleum & Natural Gas | Energy Storage | 3 | 52618.05 | 88948.1 | 69364.07
October 2025 | Rajasthan | Ministry of Petroleum & Natural Gas | Oil & Gas | 2 | 10599 | 10599 | 6656.41
October 2025 | Rajasthan | Ministry of Power | Electricity Generation | 1 | 5491.89 | 5491.89 | 5084.68
October 2025 | Rajasthan | Ministry of Power | Transmission & Distribution | 22 | 53646.51 | 54198.2 | 19895.8
October 2025 | Rajasthan | Ministry of Railways | Railways | 23 | 88639.51 | 164210 | 140285.65
October 2025 | Sikkim | Department of Higher Education | Education | 2 | 999.82 | 924.82 | 359.78
October 2025 | Sikkim | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | 1 | 323.26 | 323.26 | 38.69
October 2025 | Sikkim | Ministry of Petroleum & Natural Gas | Oil & Gas | 1 | 9265 | 9265 | 6603.95
October 2025 | Sikkim | Ministry of Power | Electricity Generation | 2 | 6686.33 | 7576.15 | 5273.06
October 2025 | Sikkim | Ministry of Power | Transmission & Distribution | 1 | 4754.42 | 9129.32 | 7705.14
October 2025 | Sikkim | Ministry of Railways | Railways | 1 | 7877 | 12133 | 9039.91
October 2025 | Tamil Nadu | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | 1 | 1207 | 1207 | 183.02
October 2025 | Tamil Nadu | Ministry of Coal | Electricity Generation | 1 | 218.03 | 218.03 | 164.7
October 2025 | Tamil Nadu | Ministry of Housing & Urban Affairs | Inland Waterways | 1 | 63246 | 63246 | 28778.98
October 2025 | Tamil Nadu | Ministry of Labour and Employment | Healthcare | 1 | 152.95 | 152.95 | 107.83
October 2025 | Tamil Nadu | Ministry of Mines | Metals & Mining | 1 | 166 | 166 | 135
October 2025 | Tamil Nadu | Ministry of Petroleum & Natural Gas | Energy Storage | 3 | 2334 | 3448.71 | 1767.45
October 2025 | Tamil Nadu | Ministry of Petroleum & Natural Gas | Oil & Gas | 4 | 38385 | 46153 | 6149.73
October 2025 | Tamil Nadu | Ministry of Power | Transmission & Distribution | 1 | 548 | 548 | 37.86
October 2025 | Tamil Nadu | Ministry of Railways | Railways | 7 | 8370.7 | 11490.2 | 5856.1
October 2025 | Telangana | Department of Higher Education | Education | 1 | 262 | 262 | 186.49
October 2025 | Telangana | Department of Telecommunications | Telecommunication | 3 | 3923.59 | 3923.59 | 866.62
October 2025 | Telangana | Department of Water Resources, River Development & GR | Water Resources | 4 | 11670.14 | 24129.6 | 11936.34
October 2025 | Telangana | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | 1 | 500.48 | 500.48 | 332.26
October 2025 | Telangana | Ministry of Coal | Coal | 9 | 3890.03 | 3890.03 | 2513.8
October 2025 | Telangana | Ministry of Health & Family Welfare | Healthcare | 1 | 1028 | 1365.95 | 806.8
October 2025 | Telangana | Ministry of Housing & Urban Affairs | Construction | 1 | 644 | 644 | 87.6
October 2025 | Telangana | Ministry of Labour and Employment | Healthcare | 1 | 211.13 | 211.13 | 198.95
October 2025 | Telangana | Ministry of Power | Transmission & Distribution | 2 | 5694.56 | 5694.56 | 4808.49
October 2025 | Telangana | Ministry of Railways | Railways | 11 | 19213.75 | 22977.8 | 10959.9
October 2025 | Tripura | Ministry of Petroleum & Natural Gas | Energy Storage | 1 | 656 | 656 | 509.92
October 2025 | Tripura | Ministry of Petroleum & Natural Gas | Oil & Gas | 2 | 9474.33 | 9396.51 | 6674.05
October 2025 | Tripura | Ministry of Power | Transmission & Distribution | 1 | 5111.33 | 6700 | 5317.79
October 2025 | Uttar Pradesh | Department of Higher Education | Education | 1 | 246 | 246 | 198.02
October 2025 | Uttar Pradesh | Department of Telecommunications | Telecommunication | 4 | 4220.71 | 3992.24 | 1070.43
October 2025 | Uttar Pradesh | Department of Water Resources, River Development & GR | Waste & Water | 2 | 1532.96 | 1532.96 | 243.43
October 2025 | Uttar Pradesh | Department of Water Resources, River Development & GR | Water Resources | 3 | 2953.27 | 6309.81 | 4689.88
October 2025 | Uttar Pradesh | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | 5 | 7268.31 | 7323.51 | 17022.23
October 2025 | Uttar Pradesh | Ministry of Coal | Coal | 2 | 1328.09 | 1328.09 | 1052.76
October 2025 | Uttar Pradesh | Ministry of Coal | Electricity Generation | 1 | 17237.8 | 21780.9 | 20522.3
October 2025 | Uttar Pradesh | Ministry of Housing & Urban Affairs | Urban Public Transport | 3 | 49730.1 | 49730.1 | 41774.16
October 2025 | Uttar Pradesh | Ministry of Housing & Urban Affairs | Waste & Water | 2 | 797.47 | 797.47 | 5957.01
October 2025 | Uttar Pradesh | Ministry of Petroleum & Natural Gas | Energy Storage | 2 | 11068.45 | 11068.5 | 8286.57
October 2025 | Uttar Pradesh | Ministry of Petroleum & Natural Gas | Oil & Gas | 3 | 17824.68 | 18213.1 | 1645.07
October 2025 | Uttar Pradesh | Ministry of Ports, Shipping and Waterways | Inland Waterways | 1 | 5369.18 | 5061.15 | 3526.99
October 2025 | Uttar Pradesh | Ministry of Power | Electricity Generation | 2 | 28284.42 | 30471.2 | 14867.23
October 2025 | Uttar Pradesh | Ministry of Power | Transmission & Distribution | 3 | 8114.81 | 8114.81 | 2073.46
October 2025 | Uttar Pradesh | Ministry of Railways | Railways | 26 | 92690.92 | 167547 | 147592.53
October 2025 | Uttarakhand | Department of Higher Education | Education | 1 | 650.85 | 650.85 | 195.52
October 2025 | Uttarakhand | Department of Water Resources, River Development & GR | Water Resources | 1 | 2584.1 | 2584.1 | 968.52
October 2025 | Uttarakhand | Ministry of Housing & Urban Affairs | Real Estate | 1 | 150.97 | 150.97 | 18.95
October 2025 | Uttarakhand | Ministry of Labour and Employment | Healthcare | 1 | 102.4 | 297.63 | 297.63
October 2025 | Uttarakhand | Ministry of Power | Electricity Generation | 3 | 11663.95 | 26070 | 20164.22
October 2025 | Uttarakhand | Ministry of Railways | Railways | 1 | 38953 | 38953 | 24645.15
October 2025 | West Bengal | Department of Higher Education | Education | 1 | 500 | 442 | 390.6
October 2025 | West Bengal | Department of Telecommunications | Telecommunication | 2 | 3462.17 | 3462.17 | 700.6
October 2025 | West Bengal | Department of Water Resources, River Development & GR | Waste & Water | 1 | 154.73 | 154.73 | 96.17
October 2025 | West Bengal | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | 2 | 1877.3 | 1877.3 | 418.18
October 2025 | West Bengal | Ministry of Coal | Coal | 13 | 15863.74 | 15863.7 | 2866.12
October 2025 | West Bengal | Ministry of Mines | Construction | 1 | 255.37 | 255.37 | 85.9
October 2025 | West Bengal | Ministry of Petroleum & Natural Gas | Energy Storage | 1 | 10228 | 11407 | 9921.29
October 2025 | West Bengal | Ministry of Petroleum & Natural Gas | Oil & Gas | 8 | 18159.65 | 19007.2 | 11678.42
October 2025 | West Bengal | Ministry of Ports, Shipping and Waterways | Inland Waterways | 1 | 5369.18 | 5061.15 | 3526.99
October 2025 | West Bengal | Ministry of Ports, Shipping and Waterways | Shipping | 2 | 551.91 | 551.91 | 447.78
October 2025 | West Bengal | Ministry of Power | Electricity Generation | 3 | 20091.84 | 20091.8 | 3721.21
October 2025 | West Bengal | Ministry of Power | Transmission & Distribution | 2 | 751.63 | 751.63 | 1.03
October 2025 | West Bengal | Ministry of Railways | Railways | 15 | 47626.45 | 58198.4 | 34098.13
October 2025 | West Bengal | Ministry of Steel | Steel | 5 | 4214.67 | 4214.67 | 502.42

## Oct - Completed
Month | Sl.No | Ministry/Department | Sector | Project Name | Implementing Agency | Project Code | State | Date of Approval | Start Date | Actual Completion Date | Target DoC (Original) | Target DoC (Revised) | Original Cost (Rs Cr) | Revised Cost (Rs Cr) | Cumulative Expenditure (Rs Cr)
October 2025 | 1 | Ministry of Petroleum & Natural Gas | Oil & Gas | HP Trijet Unit in Visakh Refinery | Hindustan Petroleum Corporation Limited | 709761 | Andhra Pradesh | 07/2024 | 07/2024 | 11/2025 | 07/2027 | 11/2025 | 193 | 193 | 0.43
October 2025 | 2 | Ministry of Petroleum & Natural Gas | Oil & Gas | Bathinda Sangrur Pipeline | Ministry of Petroleum and Natural Gas | 612998 | Punjab | 11/2021 | 11/2021 | 10/2015 | 05/2024 | 10/2025 | 367 | 397 | 355.93
October 2025 | 3 | Ministry of Railways | Railways | Vijapur Ambliyasan Gauge Conversion | Western Railway (WR) - II | 611938 | Gujarat | 05/2022 | 05/2022 | 10/2025 | 05/2026 | 10/2025 | 415.38 | 415.38 | 701.04
October 2025 | 4 | Ministry of Railways | Railways | Himmatnagar Khedbrahma Gauge Conversion | Western Railway (WR) - II | 611939 | Gujarat | 06/2022 | 04/2017 | 08/2025 | 06/2001 | 08/2025 | 482.42 | 482.42 | 894.4
October 2025 | 5 | Ministry of Railways | Railways | Domingarh-Gorakhpur-Gorakhpur Cantt.-Kusumhi - 3rd Railway Line Project | North Eastern Railway [NER] | 705566 | Uttar Pradesh | 11/2016 | 06/2018 | 09/2025 | 02/2025 | 09/2025 | 351 | 521.47 | 499.64
October 2025 | 6 | Ministry of Railways | Railways | Bahraich - Nanpara - Nepalganj Road Gauge Conversion | North Eastern Railway [NER] | 705863 | Uttar Pradesh | 07/2020 | 04/2021 | 09/2025 | 07/2025 | 09/2025 | 950 | 550 | 507.02

## Oct - Newly Added
Month | Sl.No | Ministry/Department | Sector | Project Name | Implementing Agency | Project Code | State | Date of Approval | Start Date | Target DoC (Original) | Target DoC (Revised) | Original Cost (Rs Cr) | Revised Cost (Rs Cr)
October 2025 | 1 | Department of Sports | Education | National Sports University [NSU], Imphal [Manipur] | Department of Sports & Youth Affairs | 400081 | Manipur |  | 01/2022 | 08/2024 | 11/2025 | 906.47 | 611.74
October 2025 | 2 | Ministry of Coal | Electricity Generation | 600 MW Khavda Solar Power Project | NLC India Limited [NLCIL] | 617730 | Gujarat | 08/2023 | 06/2024 | 06/2026 | - | 3335.85
October 2025 | 3 | Ministry of Labour and Employment | Healthcare | Construction of 350 beds + 50 Super Specialty beds ESIC Hospital Sheelanagar, Visakhapatnam, Andhra Pradesh | Employee's State Insurance Company [ESIC] | 612167 | Andhra Pradesh | 02/2021 | 04/2023 | 10/2025 | 01/2026 | 384.27
October 2025 | 4 | Ministry of Labour and Employment | Healthcare | Construction of 200 bedded ESIC Hospital with 62 Nos Staff quarters , Beltola | Employee's State Insurance Company [ESIC] | 612201 | Assam | 12/2017 | 10/2021 | 04/2025 | 10/2025 | 143.23 | 154.75
October 2025 | 5 | Ministry of Labour and Employment | Healthcare | Demolition, Construction and upgradation of ESI Hospital, Kalol, Gujarat from 50 beds to 150 beds. | Employee's State Insurance Company [ESIC] | 612211 | Gujarat | 08/2022 | 10/2023 | 10/2025 | 06/2026 | 205.87
October 2025 | 6 | Ministry of Labour and Employment | Healthcare | C/o Construction of 200 bedded [Up-gradable to 300 bedded] ESI Hospital at Surat Gujarat. | Employee's State Insurance Company [ESIC] | 612185 | Gujarat | 06/2019 | 03/2021 | 06/2025 | 05/2025 | 209.36
October 2025 | 7 | Ministry of Labour and Employment | Healthcare | 350 Bedded [Upgradable to 500 beds] ESI Hospital at Sanand | Employee's State Insurance Company [ESIC] | 612186 | Gujarat | 06/2022 | 04/2023 | 03/2026 | 02/2026 | 558.12
October 2025 | 8 | Ministry of Labour and Employment | Healthcare | Construction of 100 bedded ESIC Hospital & 32 nos. of Staff qtrs at OMPURA J&K. | Employee's State Insurance Company [ESIC] | 612239 | Jammu and Kashmir | 09/2019 | 12/2021 | 09/2024 | 05/2025 | 131.05 | 164.93
October 2025 | 9 | Ministry of Labour and Employment | Healthcare | Construction of 200 bed ESI Hospital at Bommasandra, Karnataka | Employee's State Insurance Company [ESIC] | 612745 | Karnataka | 02/2015 | 10/2024 | 01/2027 | - | 278
October 2025 | 10 | Ministry of Labour and Employment | Healthcare | Construction of 100 bed ESI Hospital and Staff Quarters [32 Nos.] at Harohalli, Karnataka | Employee's State Insurance Company [ESIC] | 612748 | Karnataka | 07/2019 | 03/2025 | 02/2027 | - | 150.92
October 2025 | 11 | Ministry of Labour and Employment | Healthcare | Construction of 200 Bedded [Upgradable to 500 Bedded including 50 beds of SST] ESIC Hospital at Bibewadi, Pune | Employee's State Insurance Company [ESIC] | 612188 | Maharashtra | 05/2018 | 03/2023 | 09/2025 | 02/2026 | 429.25
October 2025 | 12 | Ministry of Labour and Employment | Healthcare | Construction of 200 Bedded ESIC Hospital at Butibori, Nagpur, Maharashtra. | Employee's State Insurance Company [ESIC] | 612213 | Maharashtra | 10/2013 | 08/2022 | 08/2025 | 08/2025 | 194.93 | 196.7
October 2025 | 13 | Ministry of Labour and Employment | Healthcare | Upgradation & Extension of ESIC Hospital and Construction of PG Hostel / Staff Housing for ESIC Hospital at Andheri, Mumbai | Employee's State Insurance Company [ESIC] | 616691 | Maharashtra |  | 06/2009 | 08/2025 | 12/2025 | 260.13
October 2025 | 14 | Ministry of Labour and Employment | Healthcare | Construction of 100 Bedded ESI Hospital at Duburi, Odisha. | Employee's State Insurance Company [ESIC] | 612513 | Odisha | 12/2010 | 02/2025 | 06/2027 | - | 164.6
October 2025 | 15 | Ministry of Labour and Employment | Healthcare | Construction of 100 Bedded ESIC Hospital building and 32 Nos Residential Quarters at Vallam Vadangal, SIPCOT, Sriperumbudur | Employee's State Insurance Company [ESIC] | 612178 | Tamil Nadu | 02/2015 | 03/2023 | 06/2025 | - | 152.95
October 2025 | 16 | Ministry of Labour and Employment | Healthcare | Construction of New OPD Block 200 Bed ward Basement + GF + 6 Floors at the location of old OPD block, at existing ESIC Hospital/ Medical college campus, Sanathnagar, Hyderabad | Employee's State Insurance Company [ESIC] | 612688 | Telangana | 11/2017 | 10/2021 | 06/2024 | 06/2025 | 211.13
October 2025 | 17 | Ministry of Labour and Employment | Healthcare | CONSTRUCTION OF 300 BEDDED HOSPITAL AT HARIDWAR | Employee's State Insurance Company [ESIC] | 612259 | Uttarakhand | 02/2021 | 12/2021 | 10/2024 | 06/2025 | 102.4 | 297.63
October 2025 | 18 | Ministry of Ports, Shipping and Waterways | Shipping | Mechanization of Berth No.14 for handling Containers and other cargo on DBFOT basis - Phase II | New Mangalore Port Authority | 617804 | Karnataka |  | 06/2024 | 03/2027 | - | 153.23
October 2025 | 19 | Ministry of Power | Transmission & Distribution | Provision of ICT Augmentation & Bus Reactor at Bhuj-II PS | Power Grid Corporation of India Limited [POWERGRID] | 617801 | Gujarat | 03/2025 | 03/2025 | 12/2026 | 03/2027 | 581.74
October 2025 | 20 | Ministry of Power | Transmission & Distribution | Transmission System Strengthening at Davanagere for Integration of RE Generation [SPV Name - POWERGRID Davanagere Power Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 617803 | Karnataka | 09/2025 | 09/2025 | 09/2027 | - | 379
October 2025 | 21 | Ministry of Power | Transmission & Distribution | Augmentation of Transformation Capacity and Implementation of Line Bays at Mandsaur S/S for RE Interconnection [SPV Name- POWERGRID Mandsaur I RE Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 617802 | Madhya Pradesh | 10/2025 | 10/2025 | 03/2028 | - | 319
October 2025 | 22 | Ministry of Railways | Railways | 3rd Line between Gudur Renigunta 83.17 Km | South Central Railway [SCR] - II | 617216 | Andhra Pradesh | 10/2024 | 10/2024 | 03/2027 | - | 877.34
October 2025 | 23 | Ministry of Railways | Railways | Tiupati Katpadi 104.39 kms | South Central Railway [SCR] - II | 617210 | Andhra Pradesh | 04/2025 | 04/2025 | 03/2029 | - | 1215.56
October 2025 | 24 | Ministry of Railways | Railways | Malugur- Palasamudram New Line Project [17.975 Km] | South Western Railway [SWR] - II | 611615 | Andhra Pradesh | 09/2022 | 07/2026 | 11/2027 | 12/2027 | 342
October 2025 | 25 | Ministry of Railways | Railways | Construction of Bulb line at Nabinagar Ankorah of East Central Railway | East Central Railway [ECR] - I | 617231 | Bihar | 06/2024 | 06/2024 | 06/2028 | - | 611.74
October 2025 | 26 | Ministry of Railways | Railways | KHARSIA- NAYA RAIPUR-PARMALKASA 5th and 6th Line [278KM] | CAO/C/SECR | 617200 | Chhattisgarh | 04/2025 | 04/2025 | 03/2031 | - | 7853.84
October 2025 | 27 | Ministry of Railways | Railways | Construction of New BG line between Hassan to Belur [27 Km] | South Western Railway [SWR] - II | 400023 | Karnataka | 03/2019 | 12/2025 | 04/2028 | 04/2027 | 749
October 2025 | 28 | Ministry of Railways | Railways | Belgaum-Dharwad via Kittur [73.10Km] | South Western Railway [SWR] - II | 706835 | Karnataka | 09/2020 | 03/2025 | 12/2027 | 03/2029 | 1591
October 2025 | 29 | Ministry of Railways | Railways | Gondia-Balharshah [Chanda Fort] Doubling [240 Km] | South East Central Railway | 617201 | Maharashtra | 04/2025 | 04/2025 | 03/2031 | - | 4373.04
October 2025 | 30 | Ministry of Railways | Railways | Rail Connectivity to Errupalem Amravati Namburu 57 Km | South Central Railway [SCR] - II | 617214 | Multi-States (Andhra Pradesh, Telangana) | 11/2024 | 11/2024 | 03/2027 | - | 2047.4
October 2025 | 31 | Ministry of Railways | Railways | Buramara-Chakulia new line [59.96 km] | South Eastern Railway [SER] - I | 616588 | Multi-States (Jharkhand, Odisha, West Bengal) | 08/2024 | 12/2024 | 12/2029 | - | 1459.13
October 2025 | 32 | Ministry of Railways | Railways | Jeypore-Malkanagiri New Railway Line Project | East Coast Railway [ECoR] - II | 705742 | Odisha | 02/2018 | 12/2023 | 07/2033 | 07/2033 | 2344
October 2025 | 33 | Ministry of Railways | Railways | Bangriposi-Gorumahisani new line [ 85.60 km ] | CAO/C/SER | 616586 | Odisha | 08/2024 | 09/2025 | 12/2029 | - | 2269.49
October 2025 | 34 | Ministry of Railways | Railways | Badampahar-Kendujhargarh new line [82.06 km] | CAO/C/SER | 616587 | Odisha | 08/2024 | 09/2025 | 12/2029 | - | 1875.72
October 2025 | 35 | Ministry of Railways | Railways | Doubling between Bhadrachalam Road and Dornakal | South Central Railway [SCR] - II | 616856 | Telangana | 08/2023 | 04/2025 | 04/2029 | - | 770.12

## Oct - NE Region
Month | Sl.No | Ministry/Department | Sector | Project Name | Implementing Agency | Project Code | State | Date of Approval | Start Date | Target DoC (Original) | Target DoC (Revised) | Original Cost (Rs Cr) | Revised Cost (Rs Cr) | Cumulative Expenditure (Rs Cr) | Physical Progress (%)
October 2025 | 1 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Guwahati Airport New Integrated Terminal Building Construction Project | Adani Airport Holdings Limited | 706724 | Assam | 12/2016 | 03/2018 | 03/2025 | 11/2025 | 1712 | 1712 | 2397.37 | 91
October 2025 | 2 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | C/o NITB Imphal Airport | Airport Authority of India [AAI] | 706718 | Manipur | 11/2021 | 07/2022 | 07/2024 | 12/2026 | 499 | 499 | 155.72 | 41
October 2025 | 3 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Widening of basic strip at Western Side of Runway Chainage 80m to 920m i/c slope stabilization Measures [Balance work] of uphill and Improvement of Storm Water Drainage System at Pakyong Airport, Sikkim on design & build basis [EPC] with integrated 10 years maintenance. | Airport Authority of India [AAI] | 612793 | Sikkim | 11/2023 | 12/2023 | 02/2026 | - | 323.26 | 323.26 | 38.69 | 14
October 2025 | 4 | Ministry of Coal | Coal | TIKAK EXTENSION OCP | MIS MoCoal Integration Logins | 615820 | Assam | 07/2022 | 07/2022 | 07/2031 | - | 159.77 | 159.77 | 81.47 | 0
October 2025 | 5 | Ministry of Coal | Coal | TIRAP OCP | MIS MoCoal Integration Logins | 615821 | Assam | 11/2022 | 11/2022 | 11/2030 | - | 289.46 | 289.46 | 105.6 | 3
October 2025 | 6 | Department of Higher Education | Education | Construction of Permanent Campus of National Institute of Technology Arunachal Pradesh | National Institute of Technology, Arunachal Pradesh | 612898 | Arunachal Pradesh | 09/2009 | 03/2013 | 08/2026 | - | 592.61 | 592.61 | 550.27 | 80
October 2025 | 7 | Department of Higher Education | Education | Tezpur University Projects | Tezpur University | 606112 | Assam | 05/2019 | 06/2021 | 11/2023 | 10/2025 | 153.71 | 153.71 | 124.33 | 97
October 2025 | 8 | Department of Higher Education | Education | Construction and Developement of National Institute of Technology Meghalaya Permanent Campus at Sohra | National Institute of Technology, Meghalaya | 612885 | Meghalaya | 09/2009 | 09/2014 | 03/2022 | 07/2025 | 494.52 | 494.52 | 419.57 | 89
October 2025 | 9 | Department of Higher Education | Education | Construction of Permanent Campus for NIT Mizoram at Lengpui, Aizawl | NIT Mizoram | 612876 | Mizoram | 09/2009 | 06/2014 | 12/2029 | 12/2029 | 474.23 | 474.23 | 167.55 | 4
October 2025 | 10 | Department of Higher Education | Education | Establishment of NIT Nagaland | NIT Nagaland | 613013 | Nagaland | 09/2009 | 12/2014 | 12/2025 | - | 275.63 | 275.63 | 261.24 | 97
October 2025 | 11 | Department of Higher Education | Education | Establishment of Permanent Campus of NIT SIkkim at Khamdong-Gangtok District | NIT Sikkim | 612883 | Sikkim | 02/2024 | 03/2024 | 02/2028 | 12/2026 | 685.76 | 610.76 | 121.56 | 14
October 2025 | 12 | Department of Higher Education | Education | Construction of Sikkim University Campus Phase-I Package-II at Yangang, South Sikkim | Sikkim University | 609736 | Sikkim | 08/2020 | 01/2022 | 01/2025 | 03/2026 | 314.06 | 314.06 | 238.22 | 85
October 2025 | 13 | Department of Sports | Education | National Sports University [NSU], Imphal [Manipur] | Department of Sports & Youth Affairs | 400081 | Manipur | NA | 01/2022 | 08/2024 | 11/2025 | 906.47 | 611.74 | 553.38 | 94
October 2025 | 14 | Ministry of Power | Electricity Generation | Dibang Multipurpose Project | National Hydroelectric Power Corporation Limited [NHPC] | 602182 | Arunachal Pradesh | 02/2023 | 02/2023 | 02/2032 | 02/2032 | 31876.39 | 31876.4 | 3708.61 | 16
October 2025 | 15 | Ministry of Power | Electricity Generation | 240MW Heo HE Project | North Eastern Electric Power Corporation Limited | 611698 | Arunachal Pradesh | 12/2024 | 05/2025 | 07/2029 | - | 1938.85 | 1938.85 | 64.36 | 3
October 2025 | 16 | Ministry of Power | Electricity Generation | 186 MW Tato-I H E Project | North Eastern Electric Power Corporation Limited | 611699 | Arunachal Pradesh | 12/2024 | 05/2025 | 07/2029 | - | 1750.07 | 1750.07 | 116.08 | 2
October 2025 | 17 | Ministry of Power | Electricity Generation | Subansiri Lower HE Project [2000 MW] | National Hydroelectric Power Corporation Limited [NHPC] | 602096 | Multi-States (Arunachal Pradesh, Assam) | 09/2003 | 01/2005 | 09/2010 | 05/2026 | 6285.33 | 26075.5 | 25244.57 | 97
October 2025 | 18 | Ministry of Power | Electricity Generation | TEESTA-VI HE PROJECT, SIKKIM [500 MW], executed by LANCO TEESTA HYDRO POWER LIMITED [A wholly owned Subsidiary of NHPC LTD. acquired through NCLT] | National Hydroelectric Power Corporation Limited [NHPC] | 602181 | Sikkim | 03/2019 | 03/2020 | 03/2024 | 12/2027 | 5748.04 | 5748.04 | 3817.49 | 70
October 2025 | 19 | Ministry of Power | Electricity Generation | Rangit-IV HE Project [120 MW] executed by Jal Power Corporation Ltd. [JPCL] - A wholly owned subsidiary of NHPC Ltd. acquired through NCLT | National Hydroelectric Power Corporation Limited [NHPC] | 605156 | Sikkim | 03/2021 | 08/2021 | 05/2024 | 12/2025 | 938.29 | 1828.11 | 1455.57 | 93
October 2025 | 20 | Ministry of Power | Transmission & Distribution | North Eastern Region Expansion Scheme-XXIII [NERES-XXIII] | Power Grid Corporation of India Limited [POWERGRID] | 617375 | Arunachal Pradesh | 08/2025 | 08/2025 | 02/2028 | - | 209.38 | 209.38 | 0.03 | 0
October 2025 | 21 | Ministry of Power | Transmission & Distribution | Comprehensive Scheme for Strengthening of Transmission and Distribution [T&D] Systems [CSST&DS] in Arunachal Pradesh and Sikkim | Power Grid Corporation of India Limited [POWERGRID] | 602223 | Multi-States (Arunachal Pradesh, Sikkim) | 10/2014 | 10/2014 | 12/2018 | 03/2027 | 4754.42 | 9129.32 | 7705.14 | 82
October 2025 | 22 | Ministry of Power | Transmission & Distribution | NORTH EASTERN REGION POWER SYSTEM IMPROVEMENT PROJECT [NERPSIP] | Power Grid Corporation of India Limited [POWERGRID] | 607709 | Multi-States (Assam, Manipur, Meghalaya, Mizoram, Nagaland, Tripura) | 12/2014 | 03/2016 | 12/2018 | 03/2026 | 5111.33 | 6700 | 5317.79 | 96
October 2025 | 23 | Ministry of Petroleum & Natural Gas | Energy Storage | Rajasthan Refinery Project | MinistryofPetroleumNaturalGas | 701263 | Arunachal Pradesh | 10/2017 | 10/2017 | 10/2022 | 03/2026 | 43129 | 79459 | 61926.61 | 89
October 2025 | 24 | Ministry of Petroleum & Natural Gas | Energy Storage | Paradip-Numaligarh Crude Oil Pipeline [PNCPL] & Crude Oil Import Terminal [COIT] at Paradip | Ministry of Petroleum & Natural Gas | 701349 | Assam | 01/2019 | 01/2019 | 07/2024 | 03/2026 | 10228 | 11407 | 9921.29 | 88
October 2025 | 25 | Ministry of Petroleum & Natural Gas | Energy Storage | Construction of LPG Facilities at Kamardanga, Assam | Hindustan Petroleum Corporation Limited | 709754 | Assam | 03/2023 | 03/2023 | 07/2027 | 07/2027 | 156.36 | 156.36 | 63.31 | 50
October 2025 | 26 | Ministry of Petroleum & Natural Gas | Energy Storage | Setting up of new rail fed POL facility at Kamardanga, Assam | Hindustan Petroleum Corporation Limited [HPCL] | 709755 | Assam | 03/2023 | 03/2023 | 07/2027 | 07/2027 | 384.04 | 384.04 | 142.28 | 57
October 2025 | 27 | Ministry of Petroleum & Natural Gas | Energy Storage | Grass Root Rail-fed Depot at Sekerkote, Agartala as resitement of existing Dharmanagar Depot | Indian Oil Corporation Limited [IOCL] | 400035 | Tripura | 06/2022 | 06/2022 | 09/2025 | 06/2026 | 656 | 656 | 509.92 | 89
October 2025 | 28 | Ministry of Petroleum & Natural Gas | Oil & Gas | Guwahati Refinery Expansion [1.0 to 1.2 MMTPA] along with installation of CRU, Guwahati Refinery | Ministry of Petroleum & Natural Gas | 607701 | Assam | 05/2021 | 05/2021 | 10/2023 | 05/2026 | 412.3 | 577 | 445.73 | 87
October 2025 | 29 | Ministry of Petroleum & Natural Gas | Oil & Gas | Numaligarh Refinery Expansion Project | Ministry of Petroleum & Natural Gas | 604791 | Assam | 07/2020 | 07/2020 | 07/2024 | 12/2025 | 12366 | 22494 | 17659.09 | 78
October 2025 | 30 | Ministry of Petroleum & Natural Gas | Oil & Gas | Development of Surface Facilities for production and evacuation of Crude Oil and Natural Gas from Nadua and East Khagorija | Ministry of Petroleum & Natural Gas | 604863 | Assam | 01/2018 | 01/2018 | 02/2020 | 12/2025 | 682.9 | 726.93 | 491.64 | 94
October 2025 | 31 | Ministry of Petroleum & Natural Gas | Oil & Gas | Upgradation of Facilities of Numaligarh-Siliguri Product Pipeline [NSPL] for transportation of additional products from existing 1.72 MMTPA to 5.5 MMTPA | Ministry of Petroleum & Natural Gas | 701350 | Assam | 06/2021 | 06/2021 | 12/2024 | 12/2025 | 860 | 860 | 615.47 | 99
October 2025 | 32 | Ministry of Petroleum & Natural Gas | Oil & Gas | Construction of Field Gas Gathering Station at Baghjan area for collection, processing & transportation of natural Gas to be produced from Baghjan Field | Ministry of Petroleum & Natural Gas | 616858 | Assam | 12/2020 | 12/2020 | 03/2024 | 12/2025 | 430.76 | 430.76 | 330.99 | 87
October 2025 | 33 | Ministry of Petroleum & Natural Gas | Oil & Gas | Augmentation/Revamping of Facilities at existing Guwahati Terminal at Betkuchi | MinistryofPetroleumNaturalGas | 709776 | Assam | 04/2022 | 04/2022 | 09/2026 | 09/2026 | 277 | 323.09 | 188.04 | 68
October 2025 | 34 | Ministry of Petroleum & Natural Gas | Oil & Gas | Capacity Expansion of Digboi Refinery from 0.65 to 1.0 MMTPA | MinistryofPetroleumNaturalGas | 709779 | Assam | 06/2022 | 06/2022 | 03/2026 | 07/2027 | 768 | 740 | 123.97 | 44
October 2025 | 35 | Ministry of Petroleum & Natural Gas | Oil & Gas | Pipeline Network Project Rudrasagar | Ministry of Petroleum & Natural Gas | 709847 | Assam | 01/2023 | 01/2023 | 04/2026 | 04/2026 | 344.99 | 344.99 | 215.98 | 48
October 2025 | 36 | Ministry of Petroleum & Natural Gas | Oil & Gas | Borholla GGS Life Extension Project [BLEP] | Ministry of Petroleum & Natural Gas | 709850 | Assam | 09/2023 | 09/2023 | 05/2026 | 05/2026 | 198.7 | 198.7 | 50.26 | 40
October 2025 | 37 | Ministry of Petroleum & Natural Gas | Oil & Gas | DCU Revamp Project | NRL | 709864 | Assam | 08/2021 | 08/2021 | 07/2024 | 06/2026 | 370 | 370 | 266.35 | 64
October 2025 | 38 | Ministry of Petroleum & Natural Gas | Oil & Gas | Power Recovery Turbine [PRT] in PFCCU unit as an Energy Conservation Scheme | NRL | 709865 | Assam | 04/2023 | 04/2023 | 12/2024 | 12/2025 | 293.5 | 293.5 | 97.22 | 96
October 2025 | 39 | Ministry of Petroleum & Natural Gas | Oil & Gas | North East Gas Grid | Ministry of Petroleum & Natural Gas | 701346 | Multi-States (Arunachal Pradesh, Assam, Manipur, Meghalaya, Mizoram, Nagaland, Sikkim, Tripura) | 04/2020 | 04/2020 | 03/2024 | 03/2026 | 9265 | 9265 | 6603.95 | 86
October 2025 | 40 | Ministry of Petroleum & Natural Gas | Oil & Gas | Augmentation/ Revamping of Dimapur Depot, Dimapur | MinistryofPetroleumNaturalGas | 709786 | Nagaland | 08/2023 | 08/2023 | 11/2027 | 11/2027 | 227.62 | 227.62 | 10.8 | 25
October 2025 | 41 | Ministry of Petroleum & Natural Gas | Oil & Gas | Creation of Gas Dehydration Facilities, Tripura Asset | Oil and Natural Gas Corporation Limited [ONGC] | 709837 | Tripura | 03/2022 | 03/2022 | 05/2024 | 12/2025 | 209.33 | 131.51 | 70.1 | 66
October 2025 | 42 | Ministry of Labour and Employment | Healthcare | Construction of 200 bedded ESIC Hospital with 62 Nos Staff quarters , Beltola | Employee's State Insurance Company [ESIC] | 612201 | Assam | 12/2017 | 10/2021 | 04/2025 | 10/2025 | 143.23 | 154.75 | 101.83 | 93
October 2025 | 43 | Ministry of Railways | Railways | Guwahati-Dibrugarh via Tinsukia & Simaluguri-Dibrugarh | Central Organisation for Railway Electrification [CORE] | 706922 | Assam | 09/2020 | 09/2018 | 09/2020 | 06/2024 | 890.36 | 889.36 | 391.73 | 89
October 2025 | 44 | Ministry of Railways | Railways | Mariani-Jorhat, Tinsukia-Dangri and Makum -TirapTrack Electrification Project | GM/C/ NFR | 706940 | Assam | 09/2018 | 01/2022 | 05/2024 | - | 183.99 | 183.99 | 0 | 0
October 2025 | 45 | Ministry of Railways | Railways | Harmuty-Murkongselek Branch Line Electrification Project | GM/C/ NFR | 706942 | Assam | 09/2018 | 01/2022 | 05/2024 | - | 237.52 | 237.52 | 0 | 0
October 2025 | 46 | Ministry of Railways | Railways | Doubling of New Bonggigaon to Kamakhya via Goalpara - 176 km | Northeast Frontier Railway [NFR] | 705572 | Assam | 09/2016 | 09/2016 | 03/2026 | 03/2026 | 4060 | 4961 | 3727.78 | 93
October 2025 | 47 | Ministry of Railways | Railways | Jiribam-Imphal new line project | Northeast Frontier Railway [NFR] | 705391 | Manipur | 03/2013 | 12/2007 | 12/2026 | 06/2029 | 14323 | 21885.9 | 15598.11 | 69
October 2025 | 48 | Ministry of Railways | Railways | Murkongselek-Pasighat | Northeast Frontier Railway (NFR) - II | 705401 | Multi-States (Arunachal Pradesh, Assam) | 02/2011 | 03/2023 | 03/2025 | 05/2026 | 435 | 1250 | 542.07 | 61
October 2025 | 49 | Ministry of Railways | Railways | Dimapur [Dhansiri]-Sukhobi Kohima [Zubza] NL [82.5 Km] | Northeast Frontier Railway [NFR] | 705392 | Multi-States (Assam, Nagaland) | 08/2015 | 02/2016 | 03/2025 | 12/2025 | 6663 | 6663 | 5571.82 | 81
October 2025 | 50 | Ministry of Railways | Railways | Lumding Furkating Doubling Project 140 km | Northeast Frontier Railway [NFR] | 616701 | Multi-States (Assam, Nagaland) | 02/2024 | 01/2025 | 02/2028 | - | 2123.7 | 2123.7 | 13.74 | 0
October 2025 | 51 | Ministry of Railways | Railways | Sivok-Rangpo New Rail Line | Indian Railway Construction International Limited [IRCON] | 705432 | Sikkim | 10/2009 | 05/2010 | 05/2015 | 12/2027 | 7877 | 12133 | 9039.91 | 84
October 2025 | 52 | Department of Telecommunications | Telecommunication | Provision of 4G based Mobile Services in Uncovered Villages and National Highways of Meghalaya | Department of Telecommunications | 701598 | Meghalaya | 09/2019 | 09/2020 | 03/2022 | 03/2026 | 971.96 | 971.96 | 208.25 | 99
October 2025 | 53 | Department of Telecommunications | Telecommunication | Provision of 4G Mobile Services in Uncovered Villages of Arunachal Pradesh and 2 Districts of Assam | Department of Telecommunications | 701597 | Multi-States (Arunachal Pradesh, Assam) | 12/2020 | 10/2021 | 04/2023 | 03/2026 | 1255.49 | 1255.49 | 284.04 | 91
October 2025 | 54 | Ministry of Housing & Urban Affairs | Waste & Water | Dibrugarh Water Supply Infrastructure Project | Ministry of Housing & Urban Affairs | 702682 | Assam | 02/2016 | 01/2020 | 03/2023 | 12/2025 | 186.8 | 186.8 | 1664.41 | 100
October 2025 | 55 | Department of Water Resources, River Development & GR | Water Resources | Borolia Irrigation Project | Department of Water Resources, River Development & GR | 701370 | Assam | 04/1996 | 12/1996 | 12/2022 | 03/2026 | 256.16 | 256.16 | 44.7 | 55
October 2025 | 56 | Department of Water Resources, River Development & GR | Water Resources | Thoubal Multipurpose Project | Water Resources Department-MN | 701400 | Manipur | 04/1997 | 04/1997 | 12/2019 | 03/2026 | 1449.44 | 1822.24 | 1837.91 | 98

## Oct - All Ongoing
Month | Sl.No | Ministry/Department | Sector | Project Name | Implementing Agency | Project Code | State | Date of Approval | Start Date | Target DoC (Original) | Target DoC (Revised) | Original Cost (Rs Cr) | Revised Cost (Rs Cr) | Cumulative Expenditure (Rs Cr) | Physical Progress (%)
October 2025 | 1 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Construction of New Domestic Terminal Building Building and miscellaneous works including maintenance, operations and AICMC at Kadapa Airport | Airport Authority of India [AAI] | 612786 | Andhra Pradesh | 03/2023 | 01/2024 | 01/2026 | 03/2026 | 265.91 | 265.91 | 67.22 | 39
October 2025 | 2 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Construction of New Integrated Terminal Building and associated works including apron to park 3 code E type of aircraft or 6 code C type of aircraft at Vijayawada Airport. | Airport Authority of India [AAI] | 701107 | Andhra Pradesh | 06/2020 | 09/2020 | 09/2022 | 12/2025 | 611.8 | 611.8 | 507.14 | 84
October 2025 | 3 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Construction of New Domestic Terminal Building at Rajahmundry Airport. | Airport Authority of India [AAI] | 701121 | Andhra Pradesh | 12/2022 | 08/2023 | 08/2025 | 12/2025 | 347.15 | 347.15 | 102.43 | 57
October 2025 | 4 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Guwahati Airport New Integrated Terminal Building Construction Project | Adani Airport Holdings Limited | 706724 | Assam | 12/2016 | 03/2018 | 03/2025 | 11/2025 | 1712 | 1712 | 2397.37 | 91
October 2025 | 5 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Development of New Civil Enclave at Bihta | Airport Authority of India [AAI] | 612183 | Bihar | 08/2024 | 03/2025 | 09/2027 | - | 1413 | 1413 | 0 | 1
October 2025 | 6 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Development of New Civil Enclave and associated works at Darbhanga Airport | Airport Authority of India [AAI] | 612194 | Bihar | 07/2024 | 07/2024 | 01/2026 | - | 911.66 | 911.66 | 213.22 | 38
October 2025 | 7 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Construction of New Domestic Terminal Building [Phase-I and II] and other allied structures at JPNI Airport, Patna | Airport Authority of India [AAI] | 701101 | Bihar | 12/2018 | 10/2018 | 07/2023 | 11/2025 | 1216.9 | 1216.9 | 1125.73 | 95
October 2025 | 8 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Goa Airport Terminal Building Extension Project | Airport Authority of India [AAI] | 701105 | Goa | 11/2017 | 12/2019 | 12/2021 | 09/2025 | 255.69 | 255.69 | 154.3 | 94
October 2025 | 9 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Development of Dholera International Greenfield Airport , Gujarat | Airport Authority of India [AAI] | 701126 | Gujarat | 06/2022 | 07/2022 | 06/2026 | 06/2026 | 1305 | 1551 | 718.2 | 67
October 2025 | 10 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Construction of NTB complex including apron, taxi track and other associated civil works and electrical & mechanical installations towards Tawi River side at CA Jammu. | Airport Authority of India [AAI] | 611047 | Jammu and Kashmir | 07/2022 | 07/2023 | 06/2026 | 06/2026 | 861.37 | 861.37 | 212.12 | 39
October 2025 | 11 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Construction of New Domestic Terminal Building and Miscellaneous works at Hubli Airport | Airport Authority of India [AAI] | 612787 | Karnataka | 06/2023 | 01/2024 | 01/2026 | 03/2026 | 320.47 | 320.47 | 81.22 | 45
October 2025 | 12 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Construction of New Domestic Terminal Building and Miscellaneous Works at Belagavi Airport. | Airport Authority of India [AAI] | 612788 | Karnataka | 06/2023 | 02/2024 | 01/2026 | 01/2026 | 322.45 | 322.45 | 140.4 | 59
October 2025 | 13 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Development of additional RESA on either end on Runway 10-28 at Calicut Airport. Construction of embankment with slope protection, drainage system and associated works for additional RESA on either end on Runway 10-28 | Airport Authority of India [AAI] | 612789 | Kerala | 06/2023 | 02/2024 | 09/2025 | 03/2026 | 484.57 | 484.57 | 91.67 | 23
October 2025 | 14 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Construction of Terminal Building & Associated works at Leh Airport, Ladakh | Airport Authority of India [AAI] | 400010 | Ladakh | 07/2018 | 09/2018 | 09/2021 | 10/2025 | 480 | 640 | 471.59 | 77
October 2025 | 15 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | C/o NITB Imphal Airport | Airport Authority of India [AAI] | 706718 | Manipur | 11/2021 | 07/2022 | 07/2024 | 12/2026 | 499 | 499 | 155.72 | 41
October 2025 | 16 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | SITC of ATM Automation System and ASMGCS [Including SMR & MLAT] for Mumbai, Navi Mumbai, Jewar [earlier MOPA, without ASMGCS], HIAL & BIAL | Airport Authority of India [AAI] | 611570 | Multi-States (Karnataka, Maharashtra, Telangana, Uttar Pradesh) | NA | 10/2022 | 09/2025 | 08/2026 | 500.48 | 500.48 | 332.26 | 75
October 2025 | 17 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Construction of New Passenger Terminal Building for Domestic Operations at Jodhpur Airport. | Airport Authority of India [AAI] | 701127 | Rajasthan | 05/2022 | 04/2023 | 11/2024 | 11/2025 | 480 | 480 | 317.88 | 96
October 2025 | 18 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Construction of New Integrated Passenger Terminal Building at Udaipur Airport | Airport Authority of India [AAI] | 701128 | Rajasthan | 06/2023 | 11/2022 | 03/2026 | 10/2026 | 887 | 887 | 378.81 | 50
October 2025 | 19 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Widening of basic strip at Western Side of Runway Chainage 80m to 920m i/c slope stabilization Measures [Balance work] of uphill and Improvement of Storm Water Drainage System at Pakyong Airport, Sikkim on design & build basis [EPC] with integrated 10 years maintenance. | Airport Authority of India [AAI] | 612793 | Sikkim | 11/2023 | 12/2023 | 02/2026 | - | 323.26 | 323.26 | 38.69 | 14
October 2025 | 20 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Modernization of Chennai Airport, Phase II, Part 2 | Airport Authority of India [AAI] | 611602 | Tamil Nadu | 05/2018 | 06/2023 | 07/2025 | 06/2026 | 1207 | 1207 | 183.02 | 25
October 2025 | 21 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Construction of New Terminal Building, Second Link Taxi Track, Apron Expansion, and associated works at Prayagraj Airport- On Design & Build Basis. | Airport Authority of India [AAI] | 612063 | Uttar Pradesh | NA | 08/2023 | 11/2024 | 08/2025 | 219.18 | 274.38 | 215.2 | 100
October 2025 | 22 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Lucknow Airport-Terminal 3- Phase 1 & Other Associated Works | Adani Airport Holdings Limited | 701091 | Uttar Pradesh | 06/2018 | 09/2018 | 03/2026 | - | 3100 | 3100 | 16024.42 | 100
October 2025 | 23 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Development of Lal Bahadur Shastri International airport, Varanasi including C/o New Terminal Building, Apron Extension, Runway Extension, PTT and allied works. | Airport Authority of India [AAI] | 701113 | Uttar Pradesh | 07/2024 | 07/2024 | 07/2027 | 07/2027 | 2869.65 | 2869.65 | 361.71 | 18
October 2025 | 24 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Development of New Integrated Civil Enclave at Agra Airport | Airport Authority of India [AAI] | 701122 | Uttar Pradesh | 06/2024 | 07/2024 | 07/2026 | - | 579 | 579 | 88.64 | 20
October 2025 | 25 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Development of New Civil Enclave at Bagdogra Airport | Airport Authority of India [AAI] | 611495 | West Bengal | 08/2024 | 10/2023 | 01/2027 | 01/2027 | 1549 | 1549 | 310.58 | 13
October 2025 | 26 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Re-Construction of Rigid portions of Secondary Runway, K and A Taxiway and Strengthening of C Taxiway at NSCBI Airport Kolkata. | Airport Authority of India [AAI] | 612791 | West Bengal | 04/2023 | 12/2023 | 02/2025 | 08/2026 | 328.3 | 328.3 | 107.6 | 49
October 2025 | 27 | Ministry of Coal | Coal | TIKAK EXTENSION OCP | MIS MoCoal Integration Logins | 615820 | Assam | 07/2022 | 07/2022 | 07/2031 | - | 159.77 | 159.77 | 81.47 | 0
October 2025 | 28 | Ministry of Coal | Coal | TIRAP OCP | MIS MoCoal Integration Logins | 615821 | Assam | 11/2022 | 11/2022 | 11/2030 | - | 289.46 | 289.46 | 105.6 | 3
October 2025 | 29 | Ministry of Coal | Coal | PORDA CHIMTAPANI OCP [10 MTY] | South Eastern Coalfields Limited [SECL] | 400144 | Chhattisgarh | 12/2020 | 12/2020 | 03/2029 | - | 2310.12 | 2310.12 | 87.97 | 10
October 2025 | 30 | Ministry of Coal | Coal | CHHAL OC SEAM III [6 MTY] | South Eastern Coalfields Limited [SECL] | 400145 | Chhattisgarh | 12/2013 | 12/2013 | 03/2022 | 11/2025 | 610.63 | 610.63 | 579.82 | 85
October 2025 | 31 | Ministry of Coal | Coal | BAROUD OC EXPANSION [3.0-10.0M | South Eastern Coalfields Limited [SECL] | 400149 | Chhattisgarh | 08/2020 | 08/2020 | 03/2029 | - | 2309.8 | 2309.8 | 937.38 | 50
October 2025 | 32 | Ministry of Coal | Coal | DIPKA EXPANSION OCP [40 MTY] | South Eastern Coalfields Limited [SECL] | 400354 | Chhattisgarh | 12/2020 | 12/2020 | 03/2029 | - | 5241.4 | 5241.4 | 2841.08 | 37
October 2025 | 33 | Ministry of Coal | Coal | GEVRA OC [70 MTY] | South Eastern Coalfields Limited [SECL] | 400424 | Chhattisgarh | 03/2016 | 03/2016 | 03/2023 | 03/2026 | 11816.4 | 11816.4 | 6687.44 | 78
October 2025 | 34 | Ministry of Coal | Coal | JAMPALI OC RCE [2.0 MTY] | South Eastern Coalfields Limited [SECL] | 613795 | Chhattisgarh | 05/2020 | 05/2020 | 03/2025 | 06/2025 | 278.64 | 278.64 | 210.07 | 82
October 2025 | 35 | Ministry of Coal | Coal | AMERA OC RCE [1.0 MTY] | South Eastern Coalfields Limited [SECL] | 613798 | Chhattisgarh | 02/2015 | 02/2015 | 03/2026 | - | 335.97 | 335.97 | 88.24 | 42
October 2025 | 36 | Ministry of Coal | Coal | AMGAON OC RCE [1.0 MTY] | South Eastern Coalfields Limited [SECL] | 613799 | Chhattisgarh | 07/2015 | 07/2015 | 03/2026 | - | 316.11 | 316.11 | 188.62 | 78
October 2025 | 37 | Ministry of Coal | Coal | JAGANNATHPUR OC RCE PROJECT | South Eastern Coalfields Limited [SECL] | 613800 | Chhattisgarh | 07/2016 | 07/2016 | 03/2025 | 03/2026 | 459.49 | 459.49 | 274.35 | 96
October 2025 | 38 | Ministry of Coal | Coal | MAHAMAYA OCP [1.50 MTY] | South Eastern Coalfields Limited [SECL] | 613801 | Chhattisgarh | 05/2018 | 05/2018 | 03/2026 | - | 410.26 | 410.26 | 182.83 | 54
October 2025 | 39 | Ministry of Coal | Coal | KATKONA RO UG MINE | South Eastern Coalfields Limited [SECL] | 615191 | Chhattisgarh | 01/2023 | 01/2023 | 03/2029 | - | 329.21 | 329.21 | 61.34 | 2
October 2025 | 40 | Ministry of Coal | Coal | PELMA OC MDO | South Eastern Coalfields Limited [SECL] | 616234 | Chhattisgarh | 10/2022 | 10/2022 | 03/2033 | - | 1725.04 | 1725.04 | 15.66 | 40
October 2025 | 41 | Ministry of Coal | Coal | KUSMUNDA OC EXPANSION PROJECT | SECL - CIL | 617287 | Chhattisgarh | 11/2024 | 11/2024 | 03/2030 | - | 4516.88 | 4516.88 | 775.13 | 21
October 2025 | 42 | Ministry of Coal | Coal | MANIKPUR OC EXPANSION PROJECT | South Eastern Coalfields Limited [SECL] | 617288 | Chhattisgarh | 01/2025 | 01/2025 | 03/2029 | - | 382.61 | 382.61 | 113.03 | 21
October 2025 | 43 | Ministry of Coal | Coal | HURA C OCP | ECL - CIL | 400018 | Jharkhand | 08/2022 | 08/2022 | 03/2029 | - | 859.41 | 859.41 | 451.62 | 62
October 2025 | 44 | Ministry of Coal | Coal | KONAR EXPANSION OCP | Ministry of Coal | 400073 | Jharkhand | 01/2022 | 01/2022 | 03/2032 | - | 799.34 | 799.34 | 429.65 | 45
October 2025 | 45 | Ministry of Coal | Coal | KARO EXPANSION OCP | Ministry of Coal | 400074 | Jharkhand | 01/2022 | 01/2022 | 03/2029 | - | 908.47 | 908.47 | 269.26 | 22
October 2025 | 46 | Ministry of Coal | Coal | SANGHMITRA OC | Ministry of Coal | 400136 | Jharkhand | 03/2024 | 03/2024 | 03/2032 | - | 2660 | 2660 | 0 | 0
October 2025 | 47 | Ministry of Coal | Coal | CHANDRAGUPT OCP | Ministry of Coal | 400138 | Jharkhand | 08/2020 | 08/2020 | 03/2032 | - | 973.5 | 973.5 | 440.56 | 24
October 2025 | 48 | Ministry of Coal | Coal | KOTRE BASANTPUR PACHMO OCP | Ministry of Coal | 400139 | Jharkhand | 08/2020 | 08/2020 | 03/2032 | - | 861.06 | 625.4 | 455.95 | 42
October 2025 | 49 | Ministry of Coal | Coal | Pachwara South Coal Block | NLC India Limited [NLCIL] | 400142 | Jharkhand | 03/2016 | 11/2019 | 09/2028 | - | 2242.9 | 2242.9 | 1220.76 | 74
October 2025 | 50 | Ministry of Coal | Coal | RPR MAGADH EXP OCP | Ministry of Coal | 400150 | Jharkhand | 08/2020 | 08/2020 | 03/2028 | - | 7254.37 | 7254.37 | 1600.77 | 38
October 2025 | 51 | Ministry of Coal | Coal | NORTH URIMARI EXPANSION OCP | Ministry of Coal | 400151 | Jharkhand | 07/2021 | 07/2021 | 03/2029 | - | 778.8 | 778.8 | 696.05 | 67
October 2025 | 52 | Ministry of Coal | Coal | EPR ROHINI - KARKETTA OCP | Ministry of Coal | 400153 | Jharkhand | 01/2021 | 01/2021 | 03/2028 | - | 1020.42 | 1020.42 | 84.74 | 21
October 2025 | 53 | Ministry of Coal | Coal | EPR PUNDI OCP | Ministry of Coal | 400154 | Jharkhand | 11/2020 | 11/2020 | 03/2027 | - | 713.35 | 713.35 | 236.58 | 10
October 2025 | 54 | Ministry of Coal | Coal | EPR ASHOK OC | Ministry of Coal | 400155 | Jharkhand | 05/2021 | 05/2021 | 03/2031 | - | 2898.28 | 2898.28 | 179.7 | 24
October 2025 | 55 | Ministry of Coal | Coal | EPR AMRAPALI OCP | Ministry of Coal | 400156 | Jharkhand | 02/2020 | 02/2020 | 03/2028 | - | 5136.15 | 5136.15 | 1168.11 | 42
October 2025 | 56 | Ministry of Coal | Coal | RAJRAPPA RCE OCP | Ministry of Coal | 400160 | Jharkhand | 12/2009 | 12/2009 | 03/2016 | 03/2027 | 510.85 | 510.85 | 488.69 | 76
October 2025 | 57 | Ministry of Coal | Coal | CHITRA EAST OC | Eastern Coal Fields Limited [ECL] | 400172 | Jharkhand | 08/2018 | 08/2018 | 03/2026 | 03/2028 | 513.99 | 513.99 | 229.86 | 51
October 2025 | 58 | Ministry of Coal | Coal | JHARKHAND-LAIYO OCP | Ministry of Coal | 400352 | Jharkhand | 08/2020 | 08/2020 | 03/2031 | - | 764.57 | 764.57 | 145.81 | 29
October 2025 | 59 | Ministry of Coal | Coal | MOONIDIH XV SEAM UG | Ministry of Coal | 400425 | Jharkhand | 08/2011 | 08/2011 | 03/2019 | 05/2026 | 1230.27 | 1230.27 | 631.73 | 81
October 2025 | 60 | Ministry of Coal | Coal | 2.5 MTPA PATHERDIH NLW WASHERY | Ministry of Coal | 611017 | Jharkhand | 10/2015 | 04/2016 | 04/2018 | 03/2026 | 334.27 | 334.27 | 142.64 | 48
October 2025 | 61 | Ministry of Coal | Coal | AMALAGAMATED NTST KUJAMA OCP 8.5MTY | Ministry of Coal | 611864 | Jharkhand | 01/2023 | 01/2023 | 03/2030 | - | 4011.85 | 4011.85 | 404.49 | 28
October 2025 | 62 | Ministry of Coal | Coal | MURAIDIH UG PROJECT | Ministry of Coal | 613808 | Jharkhand | 02/2011 | 02/2011 | 04/2014 | 12/2026 | 339.87 | 339.87 | 191 | 70
October 2025 | 63 | Ministry of Coal | Coal | TAPIN SOUTH EXPN | Ministry of Coal | 615349 | Jharkhand | 11/2020 | 11/2020 | 03/2028 | - | 230.41 | 230.41 | 22.02 | 20
October 2025 | 64 | Ministry of Coal | Coal | SIRKA OC | Ministry of Coal | 615822 | Jharkhand | 05/2020 | 05/2020 | 03/2028 | - | 222.82 | 222.82 | 140.58 | 53
October 2025 | 65 | Ministry of Coal | Coal | TETARIAKHAR OC | Ministry of Coal | 615843 | Jharkhand | 11/2019 | 11/2019 | 03/2025 | 03/2027 | 243.52 | 243.52 | 44.64 | 29
October 2025 | 66 | Ministry of Coal | Coal | CHUPERBHITA SIMLONG OCP MDO 6 | Eastern Coal Fields Limited [ECL] | 616225 | Jharkhand | 12/2023 | 12/2023 | 03/2037 | - | 979.08 | 979.08 | 0 | 0
October 2025 | 67 | Ministry of Coal | Coal | JARANGDIH EXPN. OCP 1.5 MTY | CCL - CIL | 616236 | Jharkhand | 02/2020 | 02/2020 | 03/2029 | - | 414.37 | 414.37 | 85.6 | 32
October 2025 | 68 | Ministry of Coal | Coal | BLOCK E OCP | Ministry of Coal | 616253 | Jharkhand | 03/2024 | 03/2024 | 03/2029 | - | 5850.83 | 5850.83 | 20.32 | 3
October 2025 | 69 | Ministry of Coal | Coal | Revised Jharia Master Plan for Dealing with Fire, Subsidence & Rehabilitation of affected families in Jharia Coalfield- Reg. | Bharat Coking Coal Limited (BCCL | 617416 | Jharkhand | 06/2025 | 07/2025 | 12/2028 | - | 5940.47 | 5940.47 | 0 | 8
October 2025 | 70 | Ministry of Coal | Coal | AMADAND OCP[4.0MTY] | Ministry of Coal | 400148 | Madhya Pradesh | 03/2016 | 03/2016 | 03/2021 | 03/2027 | 869.44 | 869.44 | 275.35 | 75
October 2025 | 71 | Ministry of Coal | Coal | RAMPUR BATURA OCP [4.0MTY] | South Eastern Coalfields Limited [SECL] | 400152 | Madhya Pradesh | 07/2019 | 07/2019 | 03/2026 | - | 1248.93 | 1248.93 | 498.04 | 44
October 2025 | 72 | Ministry of Coal | Coal | BLOCK B EXPANSION [3.5 TO 8.0 | Northern Coalfields Limited [NCL] | 400162 | Madhya Pradesh | 07/2019 | 07/2019 | 03/2023 | 03/2027 | 998.71 | 998.71 | 470.87 | 47
October 2025 | 73 | Ministry of Coal | Coal | NIGAHI EXPANSION [15 TO 25 MTP | Northern Coalfields Limited [NCL] | 400321 | Madhya Pradesh | 11/2020 | 11/2020 | 03/2025 | 03/2028 | 1729.68 | 1729.68 | 833.62 | 48
October 2025 | 74 | Ministry of Coal | Coal | KANCHAN OC EXP | South Eastern Coalfields Limited [SECL] | 613802 | Madhya Pradesh | 12/2014 | 12/2014 | 03/2026 | - | 371.04 | 371.04 | 144.61 | 58
October 2025 | 75 | Ministry of Coal | Coal | JHIRIA WEST OCP [1.5 MTY] | South Eastern Coalfields Limited [SECL] | 613803 | Madhya Pradesh | 01/2024 | 01/2024 | 03/2029 | - | 366.94 | 366.94 | 34.07 | 41
October 2025 | 76 | Ministry of Coal | Coal | RPR TAWA-III UG 0.84 MTY | Western Coalfields Limited [WCL] | 613804 | Madhya Pradesh | 12/2021 | 12/2021 | 03/2027 | - | 314.09 | 314.09 | 6.84 | 17
October 2025 | 77 | Ministry of Coal | Coal | AMALGAMATED DHANKASA & JAMUNIA | Western Coalfields Limited [WCL] | 615185 | Madhya Pradesh | 09/2022 | 09/2022 | 03/2027 | - | 399.2 | 399.2 | 93.52 | 66
October 2025 | 78 | Ministry of Coal | Coal | RPR OF VISHNUPURI UG TO OC | Western Coalfields Limited [WCL] | 615187 | Madhya Pradesh | 11/2022 | 11/2022 | 03/2029 | - | 220.62 | 220.62 | 0 | 11
October 2025 | 79 | Ministry of Coal | Coal | URDHAN EXPANSION OC COST PLUS | Western Coalfields Limited [WCL] | 615194 | Madhya Pradesh | 07/2022 | 01/2023 | 03/2031 | - | 206.88 | 206.88 | 27.19 | 0
October 2025 | 80 | Ministry of Coal | Coal | SHARDA UG MINE | Western Coalfields Limited [WCL] | 615195 | Madhya Pradesh | 07/2022 | 09/2023 | 03/2028 | - | 166.25 | 166.25 | 5.08 | 9
October 2025 | 81 | Ministry of Coal | Coal | GANDHIGRAM UG MINE | Western Coalfields Limited [WCL] | 615206 | Madhya Pradesh | 08/2019 | 08/2019 | 03/2026 | - | 414.15 | 414.15 | 15.52 | 56
October 2025 | 82 | Ministry of Coal | Coal | BHATADI EXPANSION OC | Western Coalfields Limited [WCL] | 400033 | Maharashtra | 02/2020 | 05/2022 | 03/2028 | - | 580.61 | 580.61 | 73.77 | 28
October 2025 | 83 | Ministry of Coal | Coal | AMALGAMATED YEKONA I & YEKONA | Western Coalfields Limited [WCL] | 400177 | Maharashtra | 08/2015 | 08/2015 | 03/2025 | 03/2026 | 727.28 | 727.28 | 539.93 | 80
October 2025 | 84 | Ministry of Coal | Coal | DINESH[MAKARDHOKRA-III] OC | Western Coalfields Limited [WCL] | 400178 | Maharashtra | 02/2020 | 02/2020 | 03/2027 | - | 822.88 | 822.88 | 621.94 | 34
October 2025 | 85 | Ministry of Coal | Coal | DHUPTALA OC [SASTI UG TO OC ] | Western Coalfields Limited [WCL] | 400353 | Maharashtra | 02/2019 | 10/2021 | 03/2028 | - | 711.01 | 711.01 | 169.11 | 19
October 2025 | 86 | Ministry of Coal | Coal | SAONER UG MINE -1 EXPANSION 1. | Western Coalfields Limited [WCL] | 615184 | Maharashtra | 01/2022 | 01/2022 | 03/2028 | - | 228.64 | 228.64 | 143.37 | 68
October 2025 | 87 | Ministry of Coal | Coal | SASTI EXPANSION OPENCAST | Western Coalfields Limited [WCL] | 615186 | Maharashtra | 08/2020 | 08/2020 | 03/2026 | - | 319.04 | 319.04 | 91.48 | 20
October 2025 | 88 | Ministry of Coal | Coal | NEW MAJRI UG TO OC 3 MTY COST | Western Coalfields Limited [WCL] | 615188 | Maharashtra | 05/2019 | 09/2022 | 03/2027 | - | 402.27 | 402.27 | 60.03 | 24
October 2025 | 89 | Ministry of Coal | Coal | MAKARDHOKRA EXPN OC 4.9 MTY | Western Coalfields Limited [WCL] | 615189 | Maharashtra | 06/2022 | 06/2022 | 03/2026 | - | 361.87 | 361.87 | 76.32 | 11
October 2025 | 90 | Ministry of Coal | Coal | SINGHORI DEEP OC MIN 2.0 MTY | Western Coalfields Limited [WCL] | 615190 | Maharashtra | 05/2022 | 05/2022 | 03/2029 | - | 335.75 | 335.75 | 26.98 | 6
October 2025 | 91 | Ministry of Coal | Coal | GOKUL EXTENSION OC MINE | Western Coalfields Limited [WCL] | 615192 | Maharashtra | 04/2021 | 04/2021 | 03/2026 | - | 309.58 | 309.58 | 43.88 | 8
October 2025 | 92 | Ministry of Coal | Coal | KOLGAON EXPANSION DEEP OC MINE | Western Coalfields Limited [WCL] | 615199 | Maharashtra | 01/2023 | 09/2023 | 03/2027 | - | 198.71 | 198.71 | 0.76 | 2
October 2025 | 93 | Ministry of Coal | Coal | BALLARPUR NORTH WEST OC MINE | Western Coalfields Limited [WCL] | 615330 | Maharashtra | 12/2022 | 12/2022 | 03/2029 | - | 360.81 | 360.81 | 0.02 | 4
October 2025 | 94 | Ministry of Coal | Coal | GADEGAON OC 3 MTY | Western Coalfields Limited [WCL] | 615331 | Maharashtra | 10/2023 | 10/2023 | 03/2030 | - | 497.41 | 497.41 | 0.08 | 0
October 2025 | 95 | Ministry of Coal | Coal | GHONSA EXPANSION DEEP OC MINE | Western Coalfields Limited [WCL] | 615914 | Maharashtra | 03/2021 | 03/2021 | 03/2029 | - | 184.71 | 184.71 | 14.48 | 5
October 2025 | 96 | Ministry of Coal | Coal | AMLG GAURI PAUNI EXPANSION OC | Western Coalfields Limited [WCL] | 615916 | Maharashtra | 04/2024 | 04/2024 | 03/2030 | - | 1225.21 | 1225.21 | 79.73 | 2
October 2025 | 97 | Ministry of Coal | Coal | GAURIDEEP/GAURI CENTRAL OCP 7. | Western Coalfields Limited [WCL] | 615917 | Maharashtra | 08/2023 | 06/2024 | 03/2030 | - | 973.07 | 973.07 | 0.24 | 0
October 2025 | 98 | Ministry of Coal | Coal | RPR OF BHANEGAON OC | Western Coalfields Limited [WCL] | 615918 | Maharashtra | 02/2017 | 09/2022 | 03/2028 | - | 405.2 | 405.2 | 12.39 | 7
October 2025 | 99 | Ministry of Coal | Coal | N. EXTN. MUNGOLI NIRGUDA D OCP | Western Coalfields Limited [WCL] | 615919 | Maharashtra | 06/2024 | 06/2024 | 03/2029 | - | 1024.91 | 1024.91 | 170.94 | 0
October 2025 | 100 | Ministry of Coal | Coal | NILJAI EXPANSION DEEP OCP | Western Coalfields Limited [WCL] | 615982 | Maharashtra | 08/2016 | 11/2018 | 03/2024 | 03/2026 | 319.75 | 319.75 | 367.6 | 79
October 2025 | 101 | Ministry of Coal | Coal | UKNI DEEP OC MINE -COST PLUS | Western Coalfields Limited [WCL] | 616044 | Maharashtra | 11/2018 | 01/2019 | 03/2021 | 03/2026 | 237.06 | 237.06 | 165.57 | 87
October 2025 | 102 | Ministry of Coal | Coal | AMALGAMATED INDER-KAMPTEE DEEP OC | Western Coalfields Limited [WCL] | 616050 | Maharashtra | 09/2018 | 09/2018 | 03/2024 | 03/2026 | 235.9 | 235.9 | 237.12 | 98
October 2025 | 103 | Ministry of Coal | Coal | ADASA UG TO OC MINE | Western Coalfields Limited [WCL] | 616223 | Maharashtra | 11/2018 | 11/2018 | 03/2024 | 03/2026 | 316 | 316 | 308.84 | 86
October 2025 | 104 | Ministry of Coal | Coal | AMAL GONDEGAON GHATROHANA EXPN | Western Coalfields Limited [WCL] | 616229 | Maharashtra | 09/2024 | 09/2024 | 03/2029 | - | 668.54 | 668.54 | 1.18 | 0
October 2025 | 105 | Ministry of Coal | Coal | WAGHODA UG MINE [1.02 MTY] | Western Coalfields Limited [WCL] | 617233 | Maharashtra | 01/2024 | 01/2025 | 03/2030 | - | 379.3 | 379.3 | 0 | 0
October 2025 | 106 | Ministry of Coal | Coal | KOLARPIMPRI EXPANSION OC [2.5 | Western Coalfields Limited [WCL] | 617278 | Maharashtra | 06/2024 | 02/2025 | 03/2030 | - | 630.37 | 630.37 | 0 | 0
October 2025 | 107 | Ministry of Coal | Coal | Master Plan for Jharia and Raniganj Coalfields | Bharat Coking Coal Limited [BCCL] | 400313 | Multi-States (Jharkhand, West Bengal) | 08/2009 | 08/2009 | 08/2019 | 12/2028 | 2661.73 | 2661.73 | 791.42 | 43
October 2025 | 108 | Ministry of Coal | Coal | BINA KAKRI AMALGAMATION EXPANS | Northern Coalfields Limited [NCL] | 400369 | Multi-States (Madhya Pradesh, Uttar Pradesh) | 08/2020 | 08/2020 | 03/2024 | 03/2027 | 836.42 | 836.42 | 809.2 | 89
October 2025 | 109 | Ministry of Coal | Coal | KHADIA EXPANSION [10 TO 16 MTP | Northern Coalfields Limited [NCL] | 615183 | Multi-States (Madhya Pradesh, Uttar Pradesh) | 06/2021 | 06/2021 | 03/2025 | 03/2027 | 491.67 | 491.67 | 243.56 | 47
October 2025 | 110 | Ministry of Coal | Coal | SUBHADRA OCP | Mahanadi Coalfields Limited [MCL] | 400165 | Odisha | 05/2021 | 05/2021 | 04/2032 | - | 1693.81 | 1693.81 | 1323.62 | 42
October 2025 | 111 | Ministry of Coal | Coal | SIARMAL OCP | Mahanadi Coalfields Limited [MCL] | 400166 | Odisha | 02/2021 | 02/2021 | 03/2029 | - | 5194.95 | 5194.95 | 3456.93 | 55
October 2025 | 112 | Ministry of Coal | Coal | BALARAM EXPANSION OCP | Mahanadi Coalfields Limited (MCL | 400183 | Odisha | 06/2020 | 08/2020 | 03/2029 | - | 3504.21 | 3504.21 | 922.92 | 53
October 2025 | 113 | Ministry of Coal | Coal | GOPALJI KANIHA OCP [10 TO 30 M | MCL - CIL | 400185 | Odisha | 04/2022 | 04/2022 | 03/2030 | - | 8416.19 | 6107.87 | 1734.86 | 17
October 2025 | 114 | Ministry of Coal | Coal | INTEGRATED LAKHANPUR-BELPAHAR- | Mahanadi Coalfields Limited [MCL] | 400187 | Odisha | 05/2018 | 05/2018 | 03/2027 | - | 2434.75 | 2434.75 | 1834.91 | 69
October 2025 | 115 | Ministry of Coal | Coal | BHARATPUR RE-ORGANIZATION OCP | Mahanadi Coalfields Limited (MCL | 400392 | Odisha | 11/2018 | 11/2018 | 03/2029 | - | 2838.86 | 2838.86 | 1673.49 | 47
October 2025 | 116 | Ministry of Coal | Coal | BASUNDHARA WEST EXTENSION OPEN | MCL - CIL | 615193 | Odisha | 05/2014 | 05/2014 | 03/2019 | 03/2029 | 479.15 | 479.15 | 274.52 | 64
October 2025 | 117 | Ministry of Coal | Coal | Naini Coal Mine | Singareni Collieries Company Limited [SCCL] | 615857 | Odisha | 03/2020 | 03/2020 | 03/2026 | - | 494.3 | 494.3 | 491.33 | 80
October 2025 | 118 | Ministry of Coal | Coal | INTEGRATED KULDA GARJANBAHAL O | Mahanadi Coalfields Limited [MCL] | 616226 | Odisha | 04/2023 | 04/2023 | 03/2033 | - | 3563.5 | 3563.5 | 568.97 | 3
October 2025 | 119 | Ministry of Coal | Coal | BHUBANESWARI EXPN OCP 50 MTY | MCL - CIL | 616231 | Odisha | 03/2024 | 03/2024 | 03/2033 | - | 5366.27 | 5366.27 | 466.28 | 14
October 2025 | 120 | Ministry of Coal | Coal | HINGULA II OC EXPN PH III 15 M | MCL - CIL | 616232 | Odisha | 11/2022 | 11/2022 | 03/2029 | - | 1561.85 | 1561.85 | 273.03 | 24
October 2025 | 121 | Ministry of Coal | Coal | BALABHADRA OCP | MCL - CIL | 616233 | Odisha | 04/2023 | 04/2023 | 03/2030 | - | 978.44 | 978.44 | 212.94 | 11
October 2025 | 122 | Ministry of Coal | Coal | Jawahar Khani Open Cast Mine | Singareni Collieries Company Limited [SCCL] | 615818 | Telangana | 12/2021 | 12/2021 | 03/2025 | 03/2027 | 297.88 | 297.88 | 46.83 | 20
October 2025 | 123 | Ministry of Coal | Coal | Kalyanikhani Opencast Project | Singareni Collieries Company Limited [SCCL] | 615858 | Telangana | 03/2016 | 05/2017 | 03/2026 | - | 384.32 | 384.32 | 283.94 | 75
October 2025 | 124 | Ministry of Coal | Coal | Kakathiya Khani Opencast - III Project Phase - I | Singareni Collieries Company Limited [SCCL] | 615859 | Telangana | 03/2017 | 05/2017 | 03/2026 | - | 413.84 | 413.84 | 397.55 | 79
October 2025 | 125 | Ministry of Coal | Coal | Godavarikhani Coal Mine - 5 | Singareni Collieries Company Limited [SCCL] | 615860 | Telangana | 07/2019 | 05/2019 | 03/2025 | 03/2026 | 607.04 | 607.04 | 191.37 | 71
October 2025 | 126 | Ministry of Coal | Coal | Indaram Opencast Project | Singareni Collieries Company Limited [SCCL] | 615861 | Telangana | 08/2017 | 12/2022 | 03/2025 | 03/2026 | 424.81 | 424.81 | 404.96 | 80
October 2025 | 127 | Ministry of Coal | Coal | Goleti Opencast Mine | Singareni Collieries Company Limited [SCCL] | 615862 | Telangana | 07/2021 | 08/2021 | 03/2026 | - | 345.6 | 345.6 | 76.19 | 21
October 2025 | 128 | Ministry of Coal | Coal | Venkatesh Khani Coal Mine | Singareni Collieries Company Limited [SCCL] | 615863 | Telangana | 10/2020 | 06/2020 | 03/2026 | - | 484.5 | 484.5 | 477.14 | 97
October 2025 | 129 | Ministry of Coal | Coal | Ramagundam OC-II Extension Project | Singareni Collieries Company Limited [SCCL] | 615864 | Telangana | 11/2015 | 06/2015 | 03/2026 | - | 489.62 | 489.62 | 405.54 | 77
October 2025 | 130 | Ministry of Coal | Coal | Kakatiyakhani OC - 2 Project | Singareni Collieries Company Limited [SCCL] | 615865 | Telangana | 08/2017 | 09/2017 | 03/2025 | 03/2026 | 442.42 | 442.42 | 230.28 | 63
October 2025 | 131 | Ministry of Coal | Coal | MOHANPUR EXPANSION OC -PHASE I | Eastern Coal Fields Limited [ECL] | 400173 | West Bengal | 11/2020 | 11/2020 | 03/2026 | 03/2030 | 888.99 | 888.99 | 115.8 | 30
October 2025 | 132 | Ministry of Coal | Coal | BONJEMEHARI EXPANSION OCP | Eastern Coal Fields Limited [ECL] | 400180 | West Bengal | 08/2021 | 08/2021 | 03/2026 | 03/2030 | 570.11 | 570.11 | 82.25 | 16
October 2025 | 133 | Ministry of Coal | Coal | NAKRAKONDA KUMARDIH- B OCP | Eastern Coal Fields Limited [ECL] | 400181 | West Bengal | 08/2018 | 08/2018 | 03/2029 | - | 502.68 | 502.67 | 71.11 | 26
October 2025 | 134 | Ministry of Coal | Coal | SIDULI [OC & UG] | ECL - CIL | 400182 | West Bengal | 05/2018 | 05/2018 | 03/2027 | 03/2030 | 535.18 | 535.17 | 5.28 | 14
October 2025 | 135 | Ministry of Coal | Coal | TILABONI UG | Eastern Coal Fields Limited [ECL] | 400186 | West Bengal | 01/2023 | 01/2023 | 03/2029 | - | 749.08 | 749.07 | 52.55 | 10
October 2025 | 136 | Ministry of Coal | Coal | JHANJRA EXPANSION UG | Eastern Coal Fields Limited [ECL] | 400312 | West Bengal | 04/2020 | 04/2020 | 03/2029 | - | 1210.12 | 1210.12 | 537.77 | 44
October 2025 | 137 | Ministry of Coal | Coal | SONEPUR BAZARI EXPANSION OCP [ | Eastern Coal Fields Limited [ECL] | 400315 | West Bengal | 07/2021 | 07/2021 | 03/2029 | - | 5365.88 | 5365.88 | 583.82 | 17
October 2025 | 138 | Ministry of Coal | Coal | 2.0 MTPA BHOJUDIH NLW WASHERY | Ministry of Coal | 611016 | West Bengal | 12/2015 | 03/2019 | 09/2020 | 12/2025 | 384.57 | 384.57 | 354.75 | 97
October 2025 | 139 | Ministry of Coal | Coal | ITAPARA OCP | Eastern Coal Fields Limited [ECL] | 612816 | West Bengal | 12/2023 | 12/2023 | 03/2030 | - | 929.1 | 929.1 | 68.9 | 7
October 2025 | 140 | Ministry of Coal | Coal | SHYAMSUNDARPUR UG INCLUDING SA | Eastern Coal Fields Limited [ECL] | 613793 | West Bengal | 04/2020 | 04/2020 | 03/2026 | 03/2028 | 483.65 | 483.65 | 60.46 | 12
October 2025 | 141 | Ministry of Coal | Coal | PARASEA-BELBAID UG PROJECT | Eastern Coal Fields Limited [ECL] | 613794 | West Bengal | 01/2023 | 01/2023 | 03/2028 | - | 389.1 | 389.1 | 132.48 | 21
October 2025 | 142 | Ministry of Coal | Coal | PARASCOLE JAMBAD OCP | Eastern Coal Fields Limited [ECL] | 616230 | West Bengal | 11/2024 | 11/2024 | 03/2037 | - | 1193.55 | 1193.55 | 9.53 | 0
October 2025 | 143 | Ministry of Coal | Electricity Generation | 50 MW Wind Power Project | NLC India Limited [NLCIL] | 617299 | Gujarat | 07/2022 | 01/2024 | 06/2025 | 01/2026 | 383.84 | 383.84 | 314.83 | 45
October 2025 | 144 | Ministry of Coal | Electricity Generation | 600 MW Khavda Solar Power Project | NLC India Limited [NLCIL] | 617730 | Gujarat | 08/2023 | 06/2024 | 06/2026 | - | 3335.85 | 3335.85 | 666.65 | 17
October 2025 | 145 | Ministry of Coal | Electricity Generation | NLC Talabira Thermal Power Project | NLC India Limited [NLCIL] | 400231 | Odisha | 01/2017 | 01/2024 | 03/2030 | - | 27212.96 | 27213 | 2549.31 | 1
October 2025 | 146 | Ministry of Coal | Electricity Generation | 300 MW SPP part of 510 MW CPSU scheme | NLC India Limited [NLCIL] | 612819 | Rajasthan | 07/2022 | 03/2023 | 09/2024 | 12/2025 | 1813 | 1813 | 1167.4 | 85
October 2025 | 147 | Ministry of Coal | Electricity Generation | 50 MW Solar PP Minedout Area | NLC India Limited [NLCIL] | 615327 | Tamil Nadu | 08/2023 | 02/2024 | 03/2025 | 12/2025 | 218.03 | 218.03 | 164.7 | 69
October 2025 | 148 | Ministry of Coal | Electricity Generation | Ghatampur Thermal Power Plant 3 X 660 MW | NLC India Limited [NLCIL] | 400259 | Uttar Pradesh | 07/2016 | 02/2016 | 11/2020 | 12/2025 | 17237.8 | 21780.9 | 20522.3 | 93
October 2025 | 149 | Ministry of Coal | Railways | Dharamjaigarh-Korba | Railway | 400203 | Chhattisgarh | 05/2018 | 03/2017 | 12/2026 | 08/2026 | 1686.22 | 1686.22 | 353.12 | 42
October 2025 | 150 | Ministry of Coal | Railways | Shivpur-Kathautia New Rail [BG] Line [49 km] [Package II of Tori-Shivpur-Kathautia line] | Ministry of Coal | 400416 | Jharkhand | 02/2018 | 05/2022 | 06/2025 | 06/2026 | 1799.64 | 2564.34 | 1462.35 | 61
October 2025 | 151 | Ministry of Power | Coal | Tubed Coal Mine | Damodar Valley Corporation | 400192 | Jharkhand | 07/2016 | 10/2016 | 05/2026 | 05/2026 | 1581 | 1581 | 598.06 | 35
October 2025 | 152 | Ministry of Power | Coal | Badam Coal Mining project of NTPC | National Thermal Power Corporation [NTPC] | 603293 | Jharkhand | 02/2019 | 09/2019 | 12/2056 | 04/2027 | 502 | 784 | 313.88 | 59
October 2025 | 153 | Ministry of Power | Electricity Generation | Dibang Multipurpose Project | National Hydroelectric Power Corporation Limited [NHPC] | 602182 | Arunachal Pradesh | 02/2023 | 02/2023 | 02/2032 | 02/2032 | 31876.39 | 31876.4 | 3708.61 | 16
October 2025 | 154 | Ministry of Power | Electricity Generation | 240MW Heo HE Project | North Eastern Electric Power Corporation Limited | 611698 | Arunachal Pradesh | 12/2024 | 05/2025 | 07/2029 | - | 1938.85 | 1938.85 | 64.36 | 3
October 2025 | 155 | Ministry of Power | Electricity Generation | 186 MW Tato-I H E Project | North Eastern Electric Power Corporation Limited | 611699 | Arunachal Pradesh | 12/2024 | 05/2025 | 07/2029 | - | 1750.07 | 1750.07 | 116.08 | 2
October 2025 | 156 | Ministry of Power | Electricity Generation | Buxar Thermal Power Project [1320 MW] | Satluj Jal Vidyut Nigam [SJVN] Thermal Limited | 602579 | Bihar | 03/2019 | 06/2019 | 01/2024 | 12/2025 | 10439.09 | 13756.6 | 12571.15 | 92
October 2025 | 157 | Ministry of Power | Electricity Generation | Lara Super Thermal Power Project Stage-II [2 x 800 MW] | National Thermal Power Corporation [NTPC] | 611930 | Chhattisgarh | 08/2023 | 08/2023 | 06/2028 | - | 15530 | 15530 | 2874 | 18
October 2025 | 158 | Ministry of Power | Electricity Generation | Sipat Super Thermal Power Project, Stage-III [1x800 MW] | National Thermal Power Corporation [NTPC] | 617188 | Chhattisgarh | 09/2024 | 09/2024 | 09/2029 | - | 9791 | 9791 | 856.56 | 8
October 2025 | 159 | Ministry of Power | Electricity Generation | Bagodara Solar Power Project | Satluj Jal Vidyut Nigam [SJVN] Thermal Limited | 709747 | Gujarat | 03/2021 | 05/2021 | 12/2025 | 12/2025 | 339.35 | 339.35 | 317.59 | 51
October 2025 | 160 | Ministry of Power | Electricity Generation | Dhaulasidh Hydro Electric Project [66 MW] | Satluj Jal Vidyut Nigam [SJVN] Thermal Limited | 602582 | Himachal Pradesh | 10/2020 | 05/2021 | 11/2025 | 03/2027 | 687.97 | 1561.21 | 986.12 | 70
October 2025 | 161 | Ministry of Power | Electricity Generation | Luhri Stage-I Hydro Electric Project [210 MW] | Satluj Jal Vidyut Nigam [SJVN] Thermal Limited | 602593 | Himachal Pradesh | 11/2020 | 11/2020 | 01/2026 | 10/2029 | 1810.56 | 3584.53 | 1793.11 | 51
October 2025 | 162 | Ministry of Power | Electricity Generation | 382 MW Sunni Dam HEP | Satluj Jal Vidyut Nigam [SJVN] Thermal Limited | 602633 | Himachal Pradesh | NA | 04/2018 | 03/2027 | - | 2615 | 2615 | 495.57 | 0.5
October 2025 | 163 | Ministry of Power | Electricity Generation | Sunni Dam Hydro Electric Project [382 MW] | Satluj Jal Vidyut Nigam [SJVN] Thermal Limited | 611586 | Himachal Pradesh | 01/2023 | 01/2023 | 04/2028 | 12/2029 | 2614.51 | 4540.71 | 1011.42 | 30
October 2025 | 164 | Ministry of Power | Electricity Generation | Pakal Dul [Drangdhuran] Hydroelectric Project, 1000 MW | National Hydroelectric Power Corporation Limited [NHPC] | 602525 | Jammu and Kashmir | 10/2014 | 02/2018 | 04/2020 | 12/2026 | 8112.12 | 12728 | 7581.19 | 74
October 2025 | 165 | Ministry of Power | Electricity Generation | Kiru HE Project | National Hydroelectric Power Corporation Limited [NHPC] | 602532 | Jammu and Kashmir | 03/2019 | 02/2020 | 09/2023 | 12/2026 | 4287.59 | 5409 | 3116.72 | 72
October 2025 | 166 | Ministry of Power | Electricity Generation | Ratle HE Project - 850 MW, Ratle Hydroelectric Power Corporation Limited. | National Hydroelectric Power Corporation Limited [NHPC] | 602535 | Jammu and Kashmir | 02/2021 | 01/2022 | 02/2026 | 11/2028 | 5281.94 | 5281.94 | 1112.08 | 25
October 2025 | 167 | Ministry of Power | Electricity Generation | Kwar HE Project | National Hydroelectric Power Corporation Limited [NHPC] | 605155 | Jammu and Kashmir | 05/2022 | 11/2022 | 11/2026 | 03/2028 | 4526.12 | 4526.12 | 1094.54 | 24
October 2025 | 168 | Ministry of Power | Electricity Generation | Patratu Thermal Power Station Expansion Project Phase-I [3x800 MW] | National Thermal Power Corporation [NTPC] | 400261 | Jharkhand | 07/2017 | 11/2017 | 03/2023 | 11/2026 | 17112 | 20302 | 17861.4 | 85
October 2025 | 169 | Ministry of Power | Electricity Generation | Koderma Thermal Power Station Phase II [2X800 MW] At Koderma, Jharkhand | Damodar Valley Corporation | 611509 | Jharkhand | 04/2023 | 11/2024 | 03/2029 | - | 14358 | 14358 | 1381.54 | 3
October 2025 | 170 | Ministry of Power | Electricity Generation | Subansiri Lower HE Project [2000 MW] | National Hydroelectric Power Corporation Limited [NHPC] | 602096 | Multi-States (Arunachal Pradesh, Assam) | 09/2003 | 01/2005 | 09/2010 | 05/2026 | 6285.33 | 26075.5 | 25244.57 | 97
October 2025 | 171 | Ministry of Power | Electricity Generation | Talcher Thermal Power Station Stage III [2 x 660 MW] Expansion | National Thermal Power Corporation [NTPC] | 602961 | Odisha | 08/2022 | 09/2022 | 05/2027 | 03/2028 | 11843.75 | 12543 | 4839.68 | 40
October 2025 | 172 | Ministry of Power | Electricity Generation | BIKANER SOLAR POWER PROJECT | Satluj Jal Vidyut Nigam [SJVN] Thermal Limited | 709748 | Rajasthan | 10/2021 | 05/2022 | 04/2024 | 12/2025 | 5491.89 | 5491.89 | 5084.68 | 88
October 2025 | 173 | Ministry of Power | Electricity Generation | TEESTA-VI HE PROJECT, SIKKIM [500 MW], executed by LANCO TEESTA HYDRO POWER LIMITED [A wholly owned Subsidiary of NHPC LTD. acquired through NCLT] | National Hydroelectric Power Corporation Limited [NHPC] | 602181 | Sikkim | 03/2019 | 03/2020 | 03/2024 | 12/2027 | 5748.04 | 5748.04 | 3817.49 | 70
October 2025 | 174 | Ministry of Power | Electricity Generation | Rangit-IV HE Project [120 MW] executed by Jal Power Corporation Ltd. [JPCL] -A wholly owned subsidiary of NHPC Ltd. acquired through NCLT | National Hydroelectric Power Corporation Limited [NHPC] | 605156 | Sikkim | 03/2021 | 08/2021 | 05/2024 | 12/2025 | 938.29 | 1828.11 | 1455.57 | 93
October 2025 | 175 | Ministry of Power | Electricity Generation | Khurja super Thermal Power Plant [2X660 MW] | THDC India Limited | 602194 | Uttar Pradesh | 03/2019 | 08/2019 | 02/2024 | 09/2025 | 11089.42 | 13276.2 | 12888.23 | 100
October 2025 | 176 | Ministry of Power | Electricity Generation | Singrauli Super Thermal Power Project, Stage-III [2x800 MW] | National Thermal Power Corporation [NTPC] | 612142 | Uttar Pradesh | 03/2024 | 03/2024 | 02/2030 | - | 17195 | 17195 | 1979 | 11
October 2025 | 177 | Ministry of Power | Electricity Generation | Tapovan-Vishnugad HEP [4x130 MW] | National Thermal Power Corporation [NTPC] | 602185 | Uttarakhand | NA | 11/2006 | 03/2013 | 04/2029 | 2978 | 10907.3 | 6769.58 | 77
October 2025 | 178 | Ministry of Power | Electricity Generation | Tehri Pumped Storage Plant Project [4x250 MW] | THDC India Limited | 602193 | Uttarakhand | 07/2006 | 06/2011 | 06/2022 | 12/2025 | 4825.6 | 8339 | 8149.63 | 98
October 2025 | 179 | Ministry of Power | Electricity Generation | Vishnugad Pipalkoti Hydro Electric Project [444 MW] | THDC India Limited | 602195 | Uttarakhand | 08/2008 | 01/2014 | 12/2022 | 03/2027 | 3860.35 | 6823.72 | 5245.01 | 73
October 2025 | 180 | Ministry of Power | Electricity Generation | Raghunathpur Thermal Power Station Phase II [2X660 MW] at Raghunathpur, Purulia, West Bengal | Damodar Valley Corporation | 400062 | West Bengal | 01/2023 | 02/2025 | 06/2029 | - | 17673 | 17673 | 1408.8 | 2
October 2025 | 181 | Ministry of Power | Electricity Generation | Rammam-III HEPP [3x40 MW] | National Thermal Power Corporation [NTPC] | 602184 | West Bengal | 10/2014 | 09/2014 | 09/2019 | 03/2029 | 1381.84 | 1381.84 | 1382.42 | 47
October 2025 | 182 | Ministry of Power | Electricity Generation | Installation of FGD for 4x210 & 2x250 MW MTPS U 1-6 | Damodar Valley Corporation | 602538 | West Bengal | 06/2019 | 02/2021 | 01/2024 | 12/2025 | 1037 | 1037 | 929.99 | 67
October 2025 | 183 | Ministry of Power | Transmission & Distribution | Transmission Scheme for Solar Energy Zone in Ananthpuram 2500MW and Kurnool 1000MW | Power Grid Corporation of India Limited [POWERGRID] | 611967 | Andhra Pradesh | 09/2023 | 09/2023 | 09/2025 | 03/2026 | 1248.69 | 1248.69 | 998.95 | 87
October 2025 | 184 | Ministry of Power | Transmission & Distribution | Augmentation of 1x1500 MVA 3rd 765/400 kV transformation capacity at Kurnool New Substation | Power Grid Corporation of India Limited [POWERGRID] | 612856 | Andhra Pradesh | 05/2023 | 12/2023 | 09/2025 | 01/2026 | 163.61 | 163.61 | 85.07 | 62
October 2025 | 185 | Ministry of Power | Transmission & Distribution | Transmission system strengthening at Kurnool- III PS for integration of additional RE generation projects [POWERGRID Kurnool III PS RE Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 617183 | Andhra Pradesh | 03/2025 | 03/2025 | 12/2027 | - | 2886 | 2886 | 131.31 | 1
October 2025 | 186 | Ministry of Power | Transmission & Distribution | North Eastern Region Expansion Scheme-XXIII [NERES-XXIII] | Power Grid Corporation of India Limited [POWERGRID] | 617375 | Arunachal Pradesh | 08/2025 | 08/2025 | 02/2028 | - | 209.38 | 209.38 | 0.03 | 0
October 2025 | 187 | Ministry of Power | Transmission & Distribution | Western Region Expansion Scheme-XXV | Power Grid Corporation of India Limited [POWERGRID] | 611737 | Chhattisgarh | 02/2023 | 02/2023 | 11/2023 | 10/2025 | 385.84 | 385.84 | 382.4 | 100
October 2025 | 188 | Ministry of Power | Transmission & Distribution | Transmission system strengthening scheme for evacuation of power from solar energy zones in Rajasthan 8.1 GW under Phase II- Part- G1 | Power Grid Corporation of India Limited [POWERGRID] | 608301 | Delhi | 02/2022 | 02/2022 | 09/2023 | 12/2025 | 359.47 | 359.47 | 341.49 | 97
October 2025 | 189 | Ministry of Power | Transmission & Distribution | Transmission scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase II- Part B | Power Grid Corporation of India Limited [POWERGRID] | 611656 | Gujarat | 03/2023 | 03/2023 | 03/2025 | 11/2025 | 1167.55 | 1167 | 1147.74 | 97
October 2025 | 190 | Ministry of Power | Transmission & Distribution | Transmission scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase II- Part C | Power Grid Corporation of India Limited [POWERGRID] | 611657 | Gujarat | 03/2023 | 03/2023 | 03/2025 | 12/2025 | 2820.99 | 2820.99 | 2736.36 | 93
October 2025 | 191 | Ministry of Power | Transmission & Distribution | Establishment of Khavda Pooling Station-2 KPS2 in Khavda RE Park KPS2 TRANSMISSION SYSTEM LIMITED | Power Grid Corporation of India Limited [POWERGRID] | 611660 | Gujarat | 03/2023 | 03/2023 | 12/2024 | 11/2025 | 966.79 | 966.79 | 936.24 | 97
October 2025 | 192 | Ministry of Power | Transmission & Distribution | Transmission system for Evacuation of Additional 7 GW RE power from Khavda RE park under Phase-III Part B [Vataman Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 612139 | Gujarat | 12/2023 | 12/2023 | 12/2025 | 12/2026 | 3751.82 | 3751.82 | 1688.32 | 28
October 2025 | 193 | Ministry of Power | Transmission & Distribution | Transmission System for Evacuation of Power from potential Renewable Energy zone in Khavda Area of Gujarat under Phase IV [7 GW] Part E3 | Power Grid Corporation of India Limited [POWERGRID] | 612151 | Gujarat | 07/2023 | 07/2023 | 07/2025 | 03/2026 | 334 | 334 | 118.1 | 36
October 2025 | 194 | Ministry of Power | Transmission & Distribution | Transmission System for Evacuation of Power from Potential Energy Renewable Zone in Khavda Area of Gujarat under Ph-IV [7GW] Part E2 | Power Grid Corporation of India Limited [POWERGRID] | 612855 | Gujarat | 05/2024 | 05/2024 | 05/2026 | 06/2026 | 679 | 679 | 135.8 | 27
October 2025 | 195 | Ministry of Power | Transmission & Distribution | Augmentation of Transformation Capacity at jam Khambhaliya PS [GIS] [SPV Name POWERGRID Jam Khambhaliya Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 615342 | Gujarat | 10/2024 | 10/2024 | 07/2026 | - | 329 | 329 | 13.17 | 3
October 2025 | 196 | Ministry of Power | Transmission & Distribution | Provision of Dynamic Reactive Compensation at Khavda pooling Station 1 [KPS1] and Khavda Pooling station 3 [KPS3] | Power Grid Corporation of India Limited [POWERGRID] | 615343 | Gujarat | 11/2024 | 11/2024 | 11/2026 | - | 501 | 501 | 8.11 | 2
October 2025 | 197 | Ministry of Power | Transmission & Distribution | Transmission System for Evacuation of Power from Potential Renewable Energy Zone in Khavda area of Gujarat under Phase-IV [7GW] Part B [SPV Name POWERGRID South Olpad Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 615345 | Gujarat | 10/2024 | 10/2024 | 10/2026 | 03/2027 | 4766 | 4766 | 714.9 | 9
October 2025 | 198 | Ministry of Power | Transmission & Distribution | Augmentation of Transformation Capacity at KPS1 [GIS] and KPS2 [GIS] [Phase-V Part B1 and Part B2 Scheme] [SPV Name- POWERGRID KPS1 and 2 Augmentation Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 617069 | Gujarat | 02/2025 | 02/2025 | 02/2027 | - | 466 | 466 | 24.3 | 2
October 2025 | 199 | Ministry of Power | Transmission & Distribution | Augmentation of Banaskantha [Raghanesda] PS [GIS] [POWERGRID Banaskantha Transco Limited] | Power Grid Corporation of India Limited [POWERGRID] | 617182 | Gujarat | 03/2025 | 03/2025 | 03/2027 | - | 172 | 172 | 17.27 | 15
October 2025 | 200 | Ministry of Power | Transmission & Distribution | Augmentation of Transformation Capacity at Bhuj-II PS [GIS] | Power Grid Corporation of India Limited [POWERGRID] | 617391 | Gujarat | 02/2025 | 02/2025 | 11/2026 | 03/2027 | 488.29 | 488.29 | 0.12 | 0
October 2025 | 201 | Ministry of Power | Transmission & Distribution | Jamnagar Transmission Limited | Adani Transmission Limited | 617405 | Gujarat | NA | 10/2024 | 10/2026 | - | 4000 | 4000 | 0 | 0
October 2025 | 202 | Ministry of Power | Transmission & Distribution | Provision of ICT Augmentation & Bus Reactor at Bhuj-II PS | Power Grid Corporation of India Limited [POWERGRID] | 617801 | Gujarat | 03/2025 | 03/2025 | 12/2026 | 03/2027 | 581.74 | 581.74 | 0.2 | 0
October 2025 | 203 | Ministry of Power | Transmission & Distribution | Implementation of LILO of both circuits of 400KV vindhyachal PS-Sasan D/C Line at Hindalco Switchyard | Power Grid Corporation of India Limited [POWERGRID] | 617272 | Haryana | 06/2024 | 06/2024 | 12/2026 | - | 370 | 370 | 18.55 | 6
October 2025 | 204 | Ministry of Power | Transmission & Distribution | Transmission system for evacuation of Power from Pakaldul HEP in Chenab Valley HEPs - LTA System | Power Grid Corporation of India Limited [POWERGRID] | 608302 | Jammu and Kashmir | 02/2022 | 02/2022 | 04/2025 | 11/2025 | 318.12 | 318.12 | 317.12 | 100
October 2025 | 205 | Ministry of Power | Transmission & Distribution | Transmission Scheme for evacuation of Power from Ratle HEP [850 MW] & kiru [624 MW] Part B | Power Grid Corporation of India Limited [POWERGRID] | 617179 | Jammu and Kashmir | 07/2024 | 07/2024 | 07/2026 | 03/2027 | 218.6 | 218.6 | 2.11 | 0
October 2025 | 206 | Ministry of Power | Transmission & Distribution | Implementation of Transmission Systems in the State of Jharkhand consisting of 400/220/132/33 kV transmission lines and substations under Jharkhand Consultancy Project | Power Grid Corporation of India Limited [POWERGRID] | 617326 | Jharkhand | 02/2012 | 02/2012 | 03/2026 | - | 1842.25 | 1842.25 | 1648.05 | 95
October 2025 | 207 | Ministry of Power | Transmission & Distribution | Transmission Scheme for Integration of Renewable Energy Zone [Phase II] in Koppal II [Phase A&B] and gadag II[Phase A] in Karnataka [POWERGRID KOPPAL GADAG TRANSMISSION LIMITED] | Power Grid Corporation of India Limited [POWERGRID] | 612140 | Karnataka | 12/2023 | 12/2023 | 12/2025 | 06/2026 | 2889.39 | 2889.39 | 1533.89 | 54
October 2025 | 208 | Ministry of Power | Transmission & Distribution | System Strengthening at Koppal-II and GadagII for integration of RE generation projects [SPV Name POWERGRID Koppal Gadag Augmentation Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 616672 | Karnataka | 01/2025 | 01/2025 | 06/2027 | - | 1354 | 1354 | 40.62 | 1
October 2025 | 209 | Ministry of Power | Transmission & Distribution | Augmentation of Transformation Capacity by 3x500 MVA, 400/220 KV ICTS [6th-8th] and 1x1500 MVA, 765/400 KV ICT [4th] at Bidar PS [SPV Name- POWERGRID Bidar Augmentation Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 617068 | Karnataka | 02/2025 | 02/2025 | 06/2027 | - | 288 | 288 | 6.91 | 1
October 2025 | 210 | Ministry of Power | Transmission & Distribution | Transmission Scheme for integration of Davanagere/ Chitradurga and Bellary REZ in Karnataka [POWERGRID Chitradurga Bellary REZ Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 617184 | Karnataka | 03/2025 | 03/2025 | 09/2027 | - | 3453 | 3453 | 52.48 | 1
October 2025 | 211 | Ministry of Power | Transmission & Distribution | Transmission System Strengthening at Davanagere for Integration of RE Generation [SPV Name - POWERGRID Davanagere Power Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 617803 | Karnataka | 09/2025 | 09/2025 | 09/2027 | - | 379 | 379 | 6.6 | 0
October 2025 | 212 | Ministry of Power | Transmission & Distribution | Transmission System for Evacuation of Power from Rajasthan REZ Ph-IV [Part-2 5.5GW] [Jaisalmer/Barmer Complex] Part H1 [POWERGRID KURAWAR TRANSMISSION LIMITED] | Power Grid Corporation of India Limited [POWERGRID] | 615344 | Madhya Pradesh | 10/2024 | 10/2024 | 10/2026 | 03/2027 | 3674 | 3674 | 624.58 | 17
October 2025 | 213 | Ministry of Power | Transmission & Distribution | Transmission System for Evacuation of Power from Rajasthan REZ Ph-IV [Part-2 5.5 GW] [Jaisalmer/Barmer Complex] Part C [SPV Name POWERGRID Mandsaur Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 615346 | Madhya Pradesh | 08/2024 | 08/2024 | 08/2026 | 12/2026 | 2708 | 2708 | 1029.04 | 41
October 2025 | 214 | Ministry of Power | Transmission & Distribution | Transmission System for evacuation of power from Mahan Energen Limited Generating Station in Madhya Pradesh [SPV Name - POWERGRID MEL Power Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 617279 | Madhya Pradesh | 06/2025 | 06/2025 | 12/2027 | - | 558 | 558 | 33.48 | 1
October 2025 | 215 | Ministry of Power | Transmission & Distribution | Augmentation of Transformation Capacity and Implementation of Line Bays at Mandsaur S/S for RE Interconnection [SPV Name- POWERGRID Mandsaur I RE Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 617802 | Madhya Pradesh | 10/2025 | 10/2025 | 03/2028 | - | 319 | 319 | 0.1 | 0
October 2025 | 216 | Ministry of Power | Transmission & Distribution | Transmission System for Evacuation of power from Potential RE Zone in Khavda Area of Gujarat under phase IV 7GW-Part E4 | Power Grid Corporation of India Limited [POWERGRID] | 611966 | Maharashtra | 11/2023 | 11/2023 | 07/2025 | 03/2026 | 224.41 | 224.41 | 33.66 | 18
October 2025 | 217 | Ministry of Power | Transmission & Distribution | Transmission System for Integration of Kurnool-IV REZ Phase-I [for 4.5 GW] [POWERGRID Kurnool-IV Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 617185 | Multi-States (Andhra Pradesh, Karnataka) | 03/2025 | 03/2025 | 03/2027 | - | 5550 | 5550 | 332.68 | 1
October 2025 | 218 | Ministry of Power | Transmission & Distribution | Transmission System for Kurnool Wind Energy Zone/ Solar Energy Zone Part-A and Part-B | Power Grid Corporation of India Limited [POWERGRID] | 900808 | Multi-States (Andhra Pradesh, Telangana) | 11/2022 | 03/2023 | 11/2024 | 01/2026 | 3546.94 | 3546.94 | 3369.59 | 97
October 2025 | 219 | Ministry of Power | Transmission & Distribution | Comprehensive Scheme for Strengthening of Transmission and Distribution [T&D] Systems [CSST&DS] in Arunachal Pradesh and Sikkim | Power Grid Corporation of India Limited [POWERGRID] | 602223 | Multi-States (Arunachal Pradesh, Sikkim) | 10/2014 | 10/2014 | 12/2018 | 03/2027 | 4754.42 | 9129.32 | 7705.14 | 82
October 2025 | 220 | Ministry of Power | Transmission & Distribution | NORTH EASTERN REGION POWER SYSTEM IMPROVEMENT PROJECT [NERPSIP] | Power Grid Corporation of India Limited [POWERGRID] | 607709 | Multi-States (Assam, Manipur, Meghalaya, Mizoram, Nagaland, Tripura) | 12/2014 | 03/2016 | 12/2018 | 03/2026 | 5111.33 | 6700 | 5317.79 | 96
October 2025 | 221 | Ministry of Power | Transmission & Distribution | Eastern Region Expansion Scheme-43 [ERES-43] | Power Grid Corporation of India Limited [POWERGRID] | 617271 | Multi-States (Bihar, Odisha, West Bengal) | 09/2024 | 09/2024 | 03/2026 | 06/2026 | 342.69 | 342.69 | 0.71 | 0
October 2025 | 222 | Ministry of Power | Transmission & Distribution | Eastern Region Expansion Scheme-44 [ERES-44] | Power Grid Corporation of India Limited [POWERGRID] | 617270 | Multi-States (Bihar, West Bengal) | 11/2024 | 11/2024 | 05/2026 | 03/2027 | 408.94 | 408.94 | 0.32 | 0
October 2025 | 223 | Ministry of Power | Transmission & Distribution | Transmission Network Expansion in Gujarat to increase its ATC from ISTS Part B | Power Grid Corporation of India Limited [POWERGRID] | 400005 | Multi-States (Dadra & Nagar Haveli and Daman & Diu, Gujarat, Maharashtra) | 01/2022 | 07/2022 | 06/2023 | 12/2025 | 4546.26 | 4546.26 | 4210.3 | 93
October 2025 | 224 | Ministry of Power | Transmission & Distribution | Transmission System Strengthening Scheme for evacuation of power from SEZ in Rajasthan 8.1 GW under Phase II Part G | Power Grid Corporation of India Limited [POWERGRID] | 608922 | Multi-States (Delhi, Haryana, Rajasthan) | 05/2022 | 05/2022 | 11/2023 | 11/2025 | 1666 | 2218 | 2129.28 | 96
October 2025 | 225 | Ministry of Power | Transmission & Distribution | Transmission system for evacuation of power from REZ in Rajasthan 20GW under Phase-III Part J | Power Grid Corporation of India Limited [POWERGRID] | 611735 | Multi-States (Delhi, Rajasthan) | 12/2022 | 12/2022 | 03/2025 | 07/2026 | 331 | 331 | 135.71 | 31
October 2025 | 226 | Ministry of Power | Transmission & Distribution | Transmission Scheme for Evacuation of power from REZ in Rajasthan [20 GW] under Phase-III Part D [Sikar Khetri Transmission Ltd] | Power Grid Corporation of India Limited [POWERGRID] | 612132 | Multi-States (Delhi, Rajasthan) | 02/2024 | 02/2024 | 08/2025 | 06/2026 | 2000 | 2000 | 1460 | 68
October 2025 | 227 | Ministry of Power | Transmission & Distribution | TRANSMISSION SYSTEM FOR EVACUATION OF POWER FROM POTENTIAL RENEWABLE ENERGY ZONE IN KHAVDA AREA OF GUJARAT UNDER PHASE-V [8 GW] PART A [SPV Name POWERGRID West Central Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 615347 | Multi-States (Gujarat, Maharashtra) | 11/2024 | 11/2024 | 05/2029 | - | 24819 | 24819 | 1985.46 | 2
October 2025 | 228 | Ministry of Power | Transmission & Distribution | Transmission system for evacuation of power from Rajasthan REZ Ph-IV [Part- 3/6GW] [Bikaner complex] Part A [SPV Name POWERGRID Bikaner IV Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 615339 | Multi-States (Haryana, Punjab, Rajasthan) | 11/2024 | 11/2024 | 11/2026 | 03/2027 | 5969 | 5969 | 485.87 | 9
October 2025 | 229 | Ministry of Power | Transmission & Distribution | TRANSMISSION SYSTEM FOR EVACUATION OF POWER FROM RAJASTHAN REZ PH-IV [PART-3/ 6 GW] [BIKANER COMPLEX] PART B [SPV Name POWERGRID Siwani Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 615340 | Multi-States (Haryana, Rajasthan) | 11/2024 | 11/2024 | 11/2026 | 03/2027 | 5357 | 5357 | 428.56 | 13
October 2025 | 230 | Ministry of Power | Transmission & Distribution | Transmission System for Strengthening of Srinagar-Leh Tr. System | Power Grid Corporation of India Limited [POWERGRID] | 606781 | Multi-States (Jammu and Kashmir, Ladakh) | 03/2022 | 03/2022 | 12/2024 | 11/2025 | 288.71 | 288.71 | 280.02 | 99
October 2025 | 231 | Ministry of Power | Transmission & Distribution | Transmission Scheme for Solar Energy Zone in Bidar [2500 MW], Karnataka [Bidar Transmission Ltd] | Power Grid Corporation of India Limited [POWERGRID] | 612138 | Multi-States (Karnataka, Telangana) | 02/2024 | 02/2024 | 02/2026 | 06/2026 | 2147.62 | 2147.62 | 1438.9 | 67
October 2025 | 232 | Ministry of Power | Transmission & Distribution | Transmission System for Evacuation of Power from Rajasthan REZ Ph-IV [Part-2 5.5 GW] [Jaisalmer/Barmer Complex] Part D [SPV Name POWERGRID Beawar Mandsaur Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 615333 | Multi-States (Madhya Pradesh, Rajasthan) | 08/2024 | 08/2024 | 08/2026 | - | 2227 | 2227 | 779.45 | 23
October 2025 | 233 | Ministry of Power | Transmission & Distribution | Transmission System for Evacuation of Power from Rajasthan REZ Ph-IV [Part-2 5.5 GW] [Jaisalmer/Barmer Complex] Part E [SPV Name POWERGRID Mewar Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 615334 | Multi-States (Madhya Pradesh, Rajasthan) | 08/2024 | 08/2024 | 08/2026 | 03/2027 | 3251 | 3251 | 942.79 | 26
October 2025 | 234 | Ministry of Power | Transmission & Distribution | Rajasthan REZ Ph-V [Part-1- 4 GW] [Sirohi/Nagaur] Complex [Rajasthan V Power Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 617186 | Multi-States (Madhya Pradesh, Rajasthan) | 03/2025 | 03/2025 | 03/2027 | - | 5028 | 5028 | 256.93 | 2
October 2025 | 235 | Ministry of Power | Transmission & Distribution | Transmission System for Evacuation of power from Rajasthan REZ Ph-IV [Part-1] [Bikaner Complex] Part D [Neemrana Bareilly Transmission Ltd] | Power Grid Corporation of India Limited [POWERGRID] | 612133 | Multi-States (Rajasthan, Uttar Pradesh) | 12/2023 | 12/2023 | 12/2025 | 06/2026 | 2056 | 2056 | 1603.68 | 62
October 2025 | 236 | Ministry of Power | Transmission & Distribution | Transmission System for evacuation of Power from Rajasthan REZ Ph-IV [Part-4 3.5 GW] Part A [SPV name POWERGRID Ghiror Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 616670 | Multi-States (Rajasthan, Uttar Pradesh) | 12/2024 | 12/2024 | 12/2026 | 03/2027 | 5846 | 5846 | 467.68 | 9
October 2025 | 237 | Ministry of Power | Transmission & Distribution | Transmission system strengthening scheme for evacuation of power from solar energy zones in Rajasthan[8.1 GW] under phase-II- Part E | Power Grid Corporation of India Limited [POWERGRID] | 611659 | Rajasthan | 03/2023 | 03/2023 | 09/2024 | 11/2025 | 1433.28 | 1433 | 1418.67 | 98
October 2025 | 238 | Ministry of Power | Transmission & Distribution | Transmission System for Evacuation of Power from REZ in Rajasthan 20GW under Phase III- Part E2 | Power Grid Corporation of India Limited [POWERGRID] | 611947 | Rajasthan | 11/2023 | 11/2023 | 06/2025 | 03/2026 | 428.3 | 428.3 | 291.24 | 73
October 2025 | 239 | Ministry of Power | Transmission & Distribution | Transmission system for evacuation of power from REZ in Rajasthan 20 GW under Phase-III part H | Power Grid Corporation of India Limited [POWERGRID] | 611948 | Rajasthan | 10/2023 | 10/2023 | 04/2025 | 01/2026 | 2211.29 | 2211.29 | 1945.93 | 88
October 2025 | 240 | Ministry of Power | Transmission & Distribution | Transmission system for evacuation of power from REZ in Rajasthan 20 GW under Phase-III part C1 | Power Grid Corporation of India Limited [POWERGRID] | 611949 | Rajasthan | 10/2023 | 10/2023 | 04/2025 | 03/2026 | 1796.02 | 1796.02 | 1436.81 | 89
October 2025 | 241 | Ministry of Power | Transmission & Distribution | Transmission system for evacuation of power from REZ in Rajasthan 20 GW under Phase-III part B1 | Power Grid Corporation of India Limited [POWERGRID] | 611950 | Rajasthan | 09/2023 | 09/2023 | 04/2025 | 12/2025 | 2190.54 | 2190.54 | 1949.58 | 91
October 2025 | 242 | Ministry of Power | Transmission & Distribution | Transmission system for evacuation of power from REZ in Rajasthan 20GW under Phase-III Part E1 | Power Grid Corporation of India Limited [POWERGRID] | 611951 | Rajasthan | 12/2021 | 08/2023 | 02/2025 | 12/2025 | 688.74 | 688.74 | 654.3 | 97
October 2025 | 243 | Ministry of Power | Transmission & Distribution | Transmission System for Evacuation of power from Rajasthan REZ Ph-IV [Part-1] [Bikaner Complex] Part A [Bikaner Neemrana Transmission Ltd] | Power Grid Corporation of India Limited [POWERGRID] | 612134 | Rajasthan | 12/2023 | 12/2023 | 12/2025 | 06/2026 | 2998.34 | 2998.34 | 2008.88 | 57
October 2025 | 244 | Ministry of Power | Transmission & Distribution | Transmission System for Evacuation of Power from Rajasthan REZ Ph-IV [Part-2 5.5 GW][Jaisalmer/Barmer Complex] Part B [SPV Name POWERGRID Sirohi Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 615332 | Rajasthan | 08/2024 | 08/2024 | 08/2026 | 12/2026 | 3279 | 3279 | 918.12 | 26
October 2025 | 245 | Ministry of Power | Transmission & Distribution | Transmission System Strengthening for Interconnections of Bhadla-III & Bikaner III Complex [SPV Name POWERGRID BHADLA BIKANER TRANSMISSION LIMITED] | Power Grid Corporation of India Limited [POWERGRID] | 615335 | Rajasthan | 08/2024 | 08/2024 | 08/2026 | 12/2026 | 1382 | 1382 | 138.2 | 9
October 2025 | 246 | Ministry of Power | Transmission & Distribution | Additional Transmission System for evacuation of Power from Bhadla-III PS as part of Rajasthan REZ Phase III Scheme [20 GW] [SPV Name POWERGRID Bhadla-III Power Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 615337 | Rajasthan | 08/2024 | 08/2024 | 02/2026 | 03/2026 | 369 | 369 | 103.32 | 22
October 2025 | 247 | Ministry of Power | Transmission & Distribution | TRANSMISSION SYSTEM FOR EVACUATION OF POWER FROM RAJASTHAN REZ PH -IV [PART-2 5.5 GW] [JAISALMER/BARMER COMPLEX] PART F [SPV Name POWERGRID BARMER I TRANSMISSION LIMITED] | Power Grid Corporation of India Limited [POWERGRID] | 615338 | Rajasthan | 11/2024 | 11/2024 | 11/2026 | 06/2027 | 2735 | 2735 | 324.64 | 11
October 2025 | 248 | Ministry of Power | Transmission & Distribution | Augmentation at Fatehgarh-II PS, Fatehgarh-IV PS [Section-II] and Barmer-I PS [POWERGRID Fatehgarh Barmer Augmentation Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 617181 | Rajasthan | 03/2025 | 03/2025 | 12/2026 | 03/2027 | 404 | 404 | 16.16 | 1
October 2025 | 249 | Ministry of Power | Transmission & Distribution | Transmission System under ISTS for evacuation of Power from Kudankulam Unit-3&4 [2x1000 MW] [SPV Name POWERGRID Kudankulam Tarnsmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 616671 | Tamil Nadu | 01/2025 | 01/2025 | 12/2026 | 12/2026 | 548 | 548 | 37.86 | 9
October 2025 | 250 | Ministry of Power | Transmission & Distribution | Transmission System for Strengthening to facilitate evacuation of power from Bhadla/Bikaner Complex | Power Grid Corporation of India Limited [POWERGRID] | 617269 | Uttar Pradesh | 12/2024 | 12/2024 | 06/2026 | 08/2026 | 212.81 | 212.81 | 2.1 | 0
October 2025 | 251 | Ministry of Housing & Urban Affairs | Construction | C/o 184 MS Flats for Hon'ble MPs at BKS Marg, New Delhi | Central Public Works Department [CPWD] | 617282 | Delhi | 01/2022 | 05/2022 | 05/2025 | 09/2025 | 646.53 | 646.52 | 545.86 | 100
October 2025 | 252 | Ministry of Housing & Urban Affairs | Construction | Construction of One Tower of Office Complex and another Tower of Residential quarters consisting of 10Nos. Type-V, 10Nos. Type-VI & 1No.Type-VII Quarters i/c internal water supply, sanitary installation and all development and bulk services, Horticulture works on EPC Mode-I basis i/c comprehensive operation and maintenance of Civil, E&M services for 7 years after completion of original construction work for Ranga Reddy, Secunderabad, Medchal, AuditI, Audit-II Commissionerates of Central Tax at Khajaguda, Serilingampally, Hyderabad. | Central Public Works Department - CPWD | 617412 | Telangana | 03/2024 | 11/2024 | 09/2027 | - | 644 | 644 | 87.6 | 6
October 2025 | 253 | Ministry of Housing & Urban Affairs | Inland Waterways | Chennai Metro Rail Phase-II Development Project | Chennai Metro Rail Limited [CMRL] | 702668 | Tamil Nadu | 10/2024 | 11/2020 | 08/2029 | - | 63246 | 63246 | 28778.98 | 47
October 2025 | 254 | Ministry of Housing & Urban Affairs | Real Estate | Integrated Command control Center [ICCC] - Construction and Development of Integrated Command Control Center with Security, Surveillance, ITMS, Connecting Port, Ship Service, Smart Solid Waste Management, Smart Public Transport System | ministry of housing and urban affairs | 707229 | Andaman & Nicobar | 07/2021 | 11/2021 | 05/2023 | - | 209.88 | 209.88 | 0 | 70
October 2025 | 255 | Ministry of Housing & Urban Affairs | Real Estate | Redevelopment of Seven General Pool Residential Accommodation [GPRA] Colonies in Delhi | National Buildings Construction Corporation [NBCC] | 400188 | Delhi | 07/2016 | 05/2018 | 12/2025 | 12/2025 | 32850 | 32850 | 0 | 0
October 2025 | 256 | Ministry of Housing & Urban Affairs | Real Estate | Rehablitation in Junavadaj Area Smart City Project | ministry of housing and urban affairs | 701719 | Gujarat | 02/2016 | 06/2016 | 07/2022 | - | 539 | 539 | 39.63 | 50
October 2025 | 257 | Ministry of Housing & Urban Affairs | Real Estate | Green Building Development Project | ministry of housing and urban affairs | 701766 | Uttarakhand | 11/2019 | 08/2019 | 11/2023 | - | 150.97 | 150.97 | 18.95 | 31
October 2025 | 258 | Ministry of Housing & Urban Affairs | Urban Public Transport | Patna Metro Rail Project | Patna Metro Rail Corporation Ltd. [PMRCL] | 702627 | Bihar | 02/2019 | 02/2019 | 02/2024 | 06/2027 | 13365.77 | 13365.8 | 4039.77 | 46
October 2025 | 259 | Ministry of Housing & Urban Affairs | Urban Public Transport | Delhi Metro Rail Phase-IV [2 Corridors] | Delhi Metro Rail Corporation Limited [DMRC] | 617207 | Delhi | 03/2024 | 03/2024 | 03/2029 | - | 8399.81 | 8399.81 | 55.92 | 0
October 2025 | 260 | Ministry of Housing & Urban Affairs | Urban Public Transport | DMRTS Phase - IV [3 Priority Corridors] | Delhi Metro Rail Corporation Limited [DMRC] | 702632 | Delhi | 07/2019 | 07/2019 | 03/2025 | 03/2026 | 24948.65 | 24948.7 | 17838.17 | 71
October 2025 | 261 | Ministry of Housing & Urban Affairs | Urban Public Transport | Surat Metro Rail Project | Gujarat Metro Rail Corporation Limited [GMRCL] | 702630 | Gujarat | 03/2019 | 04/2019 | 03/2024 | 06/2026 | 12020.32 | 12020.3 | 7977.03 | 72
October 2025 | 262 | Ministry of Housing & Urban Affairs | Urban Public Transport | Ahmedabad Metro Rail Project, Phase-II | Gujarat Metro Rail Corporation Limited [GMRCL] | 702631 | Gujarat | 03/2019 | 03/2019 | 03/2024 | 12/2025 | 5384.17 | 5384.17 | 4308.13 | 91
October 2025 | 263 | Ministry of Housing & Urban Affairs | Urban Public Transport | Ahmedabad Metro Rail Project [Phase-I] | Gujarat Metro Rail Corporation Limited [GMRCL] | 702639 | Gujarat | 11/2014 | 02/2015 | 03/2018 | 10/2025 | 10773 | 12924.5 | 12212.92 | 99
October 2025 | 264 | Ministry of Housing & Urban Affairs | Urban Public Transport | Construction of Bangalore Metro Rail Project Phase 2. | Bengaluru Metro Rail | 702635 | Karnataka | 02/2014 | 02/2016 | 03/2021 | 09/2026 | 26405.14 | 30695.1 | 29617.97 | 94
October 2025 | 265 | Ministry of Housing & Urban Affairs | Urban Public Transport | Construction Bangalore Metro Rail Project Phase-2A & 2B | Bengaluru Metro Rail | 702665 | Karnataka | 06/2021 | 01/2019 | 06/2026 | 06/2026 | 14788.1 | 14788.1 | 8915.63 | 57
October 2025 | 266 | Ministry of Housing & Urban Affairs | Urban Public Transport | Kochi Metro Rail Phase 2 Development Project | CSPCC Projects | 702664 | Kerala | 11/2022 | 11/2022 | 11/2026 | 11/2026 | 1957.05 | 1957.05 | 425.58 | 19
October 2025 | 267 | Ministry of Housing & Urban Affairs | Urban Public Transport | Bhopal Metro Rail Project | Madhya Pradesh Metro Rail Co Limited [MPMRCL] | 702625 | Madhya Pradesh | 11/2018 | 11/2018 | 11/2022 | 06/2028 | 6941.4 | 6941.4 | 3676.19 | 47
October 2025 | 268 | Ministry of Housing & Urban Affairs | Urban Public Transport | Indore Metro Rail Project | Madhya Pradesh Metro Rail Co Limited [MPMRCL] | 702626 | Madhya Pradesh | 11/2018 | 11/2018 | 11/2022 | 12/2028 | 7500.8 | 7500.8 | 4223.43 | 57
October 2025 | 269 | Ministry of Housing & Urban Affairs | Urban Public Transport | PCMC To Nigdi- Extension Of North South Corridor Of Phase-1 | Maharashtra Metro Rail Corporation Limited [MMRCL] | 617225 | Maharashtra | 10/2023 | 10/2023 | 01/2027 | - | 910.18 | 910.18 | 147.84 | 26
October 2025 | 270 | Ministry of Housing & Urban Affairs | Urban Public Transport | Pune Metro Phase-1 Extension line towards south from Swargate to Katraj | Maharashtra Metro Rail Corporation Limited [MMRCL] | 617226 | Maharashtra | 09/2024 | 09/2024 | 03/2029 | - | 2954.53 | 2954.53 | 22.17 | 3
October 2025 | 271 | Ministry of Housing & Urban Affairs | Urban Public Transport | Thane Integral Ring Metro Rail Project | Maharashtra Metro Rail Corporation Limited [MMRCL] | 617327 | Maharashtra | 09/2024 | 09/2024 | 09/2029 | - | 12200.1 | 12200.1 | 7.77 | 3
October 2025 | 272 | Ministry of Housing & Urban Affairs | Urban Public Transport | New Suburba Station Development Project | ministry of housing and urban affairs | 701745 | Maharashtra | 04/2018 | 03/2019 | 07/2022 | - | 262.76 | 262.76 | 17.62 | 6
October 2025 | 273 | Ministry of Housing & Urban Affairs | Urban Public Transport | Kalyan Station Precinct Imporvement Project | ministry of housing and urban affairs | 701991 | Maharashtra | 04/2018 | 07/2020 | 07/2023 | - | 600 | 600 | 272.42 | 70
October 2025 | 274 | Ministry of Housing & Urban Affairs | Urban Public Transport | Mumbai Metro Line 3 | Mumbai Metro Rail Corporation Limited [MMRC] | 702637 | Maharashtra | 07/2013 | 06/2016 | 03/2023 | 08/2025 | 23136 | 37276 | 31783.93 | 96
October 2025 | 275 | Ministry of Housing & Urban Affairs | Urban Public Transport | Nagpur Metro Rail Phase II Development Project | Maharashtra Metro Rail Corporation Limited [MMRCL] | 702658 | Maharashtra | 12/2022 | 12/2022 | 12/2027 | - | 6708 | 6708 | 1259.29 | 28
October 2025 | 276 | Ministry of Housing & Urban Affairs | Urban Public Transport | Delhi Metro Rail Phase-IV [Rithala - Kundli Corridor] | Delhi Metro Rail Corporation Limited [DMRC] | 617206 | Multi-States (Delhi, Haryana) | 01/2025 | 01/2025 | 01/2029 | - | 6230.99 | 6230.99 | 72.38 | 0
October 2025 | 277 | Ministry of Housing & Urban Affairs | Urban Public Transport | Delhi-Ghaziabad-Meerut Regional Rapid Transit System [RRTS] corridor | National Capital Region Transport Corporation [NCRTC] | 702633 | Multi-States (Delhi, Uttar Pradesh) | 03/2019 | 03/2019 | 06/2025 | 10/2025 | 30274 | 30274 | 26612.45 | 95
October 2025 | 278 | Ministry of Housing & Urban Affairs | Urban Public Transport | Kanpur Metro Rail Project | Uttar Pradesh metro rail corporation [UPMRC] | 702628 | Uttar Pradesh | 05/2019 | 11/2019 | 05/2024 | 03/2027 | 11076.48 | 11076.5 | 9093.83 | 76
October 2025 | 279 | Ministry of Housing & Urban Affairs | Urban Public Transport | Agra Metro Rail Project | Uttar Pradesh metro rail corporation [UPMRC] | 702629 | Uttar Pradesh | 05/2019 | 12/2020 | 05/2024 | 06/2027 | 8379.62 | 8379.62 | 6067.88 | 63
October 2025 | 280 | Ministry of Housing & Urban Affairs | Waste & Water | ESR - 8 nos., distribution system - 216 Km, new house service connections - 38760 nos. upgrading of feeder mains, pumping station etc. - Phase II | Ministry of Housing & Urban Affairs | 702674 | Andhra Pradesh | 02/2017 | 07/2018 | 03/2023 | 12/2025 | 172.22 | 172.22 | 799.74 | 82
October 2025 | 281 | Ministry of Housing & Urban Affairs | Waste & Water | Dibrugarh Water Supply Infrastructure Project | Ministry of Housing & Urban Affairs | 702682 | Assam | 02/2016 | 01/2020 | 03/2023 | 12/2025 | 186.8 | 186.8 | 1664.41 | 100
October 2025 | 282 | Ministry of Housing & Urban Affairs | Waste & Water | Muzaffarpur Storm Water Drainage Phase-I Project | Ministry of Housing & Urban Affairs | 702699 | Bihar | 11/2016 | 02/2019 | 10/2023 | 12/2025 | 158.78 | 158.78 | 602.5 | 83
October 2025 | 283 | Ministry of Housing & Urban Affairs | Waste & Water | Storm water drainag Development Project | ministry of housing and urban affairs | 702355 | Dadra & Nagar Haveli and Daman & Diu | 08/2020 | 12/2021 | 03/2024 | - | 210 | 210 | 0 | 20
October 2025 | 284 | Ministry of Housing & Urban Affairs | Waste & Water | Upgradation of Sewerage system in Gandhinagar City | ministry of housing and urban affairs | 707267 | Gujarat | 07/2020 | 03/2021 | 06/2023 | - | 200 | 200 | 100 | 10
October 2025 | 285 | Ministry of Housing & Urban Affairs | Waste & Water | Sewerage Management Scheme Part-3 Implementation | Ministry of Housing & Urban Affairs | 702734 | Haryana | 03/2017 | 11/2017 | 09/2023 | 03/2026 | 278.01 | 278.01 | 2005.13 | 88
October 2025 | 286 | Ministry of Housing & Urban Affairs | Waste & Water | Sewerage Management Scheme Part-3 Implementation | Ministry of Housing & Urban Affairs | 702735 | Haryana | 03/2017 | 10/2018 | 03/2023 | 12/2025 | 213.19 | 213.19 | 1430.38 | 91
October 2025 | 287 | Ministry of Housing & Urban Affairs | Waste & Water | Dhanbad Water Supply Infrastructure Project | Ministry of Housing & Urban Affairs | 702741 | Jharkhand | 02/2017 | 12/2018 | 03/2023 | 03/2026 | 216.55 | 216.55 | 1057.8 | 72
October 2025 | 288 | Ministry of Housing & Urban Affairs | Waste & Water | SAAP-3 Water Supply Infrastructure SAAP-3 Project | Ministry of Housing & Urban Affairs | 702742 | Jharkhand | 02/2017 | 12/2018 | 10/2023 | 03/2026 | 159.31 | 159.31 | 787.5 | 65
October 2025 | 289 | Ministry of Housing & Urban Affairs | Waste & Water | Augmentation and Strenghthning of Urban Water Supply Phase 1 - SAAP 3 | Ministry of Housing & Urban Affairs | 702746 | Jharkhand | 02/2017 | 12/2018 | 03/2023 | 03/2026 | 278.28 | 278.28 | 1410 | 78
October 2025 | 290 | Ministry of Housing & Urban Affairs | Waste & Water | Belgavi Improvement in Sewerage System Project | Ministry of Housing & Urban Affairs | 702760 | Karnataka | 12/2015 | 10/2016 | 07/2023 | 12/2025 | 162.73 | 162.73 | 721.71 | 80
October 2025 | 291 | Ministry of Housing & Urban Affairs | Waste & Water | 24/7 water supply under AMRUT for Davanagere | Ministry of Housing & Urban Affairs | 702764 | Karnataka | 11/2016 | 01/2018 | 03/2023 | 12/2025 | 174.96 | 174.96 | 923.02 | 65
October 2025 | 292 | Ministry of Housing & Urban Affairs | Waste & Water | Indore Water Supply Infrastructure Project | Ministry of Housing & Urban Affairs | 702793 | Madhya Pradesh | 12/2016 | 11/2017 | 03/2023 | 12/2025 | 287.17 | 287.17 | 2271 | 99
October 2025 | 293 | Ministry of Housing & Urban Affairs | Waste & Water | Jabalpur Sewerage Management and Treatment Infrastructure Project | Ministry of Housing & Urban Affairs | 702798 | Madhya Pradesh | 10/2018 | 12/2017 | 03/2023 | 12/2025 | 362.31 | 362.31 | 2930.96 | 93
October 2025 | 294 | Ministry of Housing & Urban Affairs | Waste & Water | Satna Sewerage Management and Treatment Infrastructure Project | Ministry of Housing & Urban Affairs | 702808 | Madhya Pradesh | 11/2015 | 12/2016 | 03/2024 | 12/2025 | 191.56 | 191.56 | 1469.73 | 86
October 2025 | 295 | Ministry of Housing & Urban Affairs | Waste & Water | Singrauli Sewerage Management and Treatment Infrastructure Project | Ministry of Housing & Urban Affairs | 702810 | Madhya Pradesh | 05/2016 | 11/2017 | 03/2023 | 12/2025 | 402.01 | 402.01 | 3175.93 | 90
October 2025 | 296 | Ministry of Housing & Urban Affairs | Waste & Water | Kalyan-Dombivali Water Supply Infrastructure Project | Ministry of Housing & Urban Affairs | 702833 | Maharashtra | 07/2016 | 09/2019 | 10/2023 | 12/2025 | 194.2 | 194.2 | 1055.02 | 70
October 2025 | 297 | Ministry of Housing & Urban Affairs | Waste & Water | Mira-Bhayandar Water Supply Infrastructure Project | Ministry of Housing & Urban Affairs | 702840 | Maharashtra | 11/2016 | 08/2018 | 03/2023 | 12/2025 | 204.55 | 204.55 | 1765.97 | 99
October 2025 | 298 | Ministry of Housing & Urban Affairs | Waste & Water | Nagpur Water Supply Infrastructure Project | Ministry of Housing & Urban Affairs | 702842 | Maharashtra | 12/2015 | 08/2018 | 03/2023 | 12/2025 | 273.78 | 273.78 | 2409.09 | 99
October 2025 | 299 | Ministry of Housing & Urban Affairs | Waste & Water | Pune Water Supply Infrastructure Project | Ministry of Housing & Urban Affairs | 702851 | Maharashtra | 03/2017 | 07/2017 | 03/2023 | 10/2025 | 235.95 | 235.95 | 1901.3 | 92
October 2025 | 300 | Ministry of Housing & Urban Affairs | Waste & Water | Solapur Sewerage Management Infrastructure Project | Ministry of Housing & Urban Affairs | 702854 | Maharashtra | 03/2017 | 04/2018 | 03/2023 | 12/2025 | 180.24 | 180.24 | 1442.29 | 91
October 2025 | 301 | Ministry of Housing & Urban Affairs | Waste & Water | Jalandhar Water Supply Infrastructure Project | Ministry of Housing & Urban Affairs | 703021 | Punjab | 11/2016 | 08/2020 | 08/2023 | 03/2026 | 258.53 | 258.53 | 1390.73 | 58
October 2025 | 302 | Ministry of Housing & Urban Affairs | Waste & Water | Patiala Water Supply Infrastructure Part-2 Project | Ministry of Housing & Urban Affairs | 703057 | Punjab | 11/2016 | 08/2020 | 10/2023 | 12/2025 | 287 | 287 | 1416.38 | 74
October 2025 | 303 | Ministry of Housing & Urban Affairs | Waste & Water | Jaunpur Sewerage Management Infrastructure Project | Ministry of Housing & Urban Affairs | 702948 | Uttar Pradesh | 03/2017 | 08/2019 | 06/2023 | 12/2025 | 235.73 | 235.73 | 1911.66 | 87
October 2025 | 304 | Ministry of Housing & Urban Affairs | Waste & Water | Jhansi Water Supply Infrastructure Phase-II Project | Ministry of Housing & Urban Affairs | 702949 | Uttar Pradesh | 03/2017 | 06/2019 | 07/2023 | 12/2025 | 561.74 | 561.74 | 4045.35 | 91
October 2025 | 305 | Ministry of Mines | Construction | Construction of Basement + Ground Floor+ 10 Storeyed building for State of the Art Director General, GSI Building at plot No.GN-40, Sector-V, Salt Lake, Kolkata | Central Public Works Department (CPWD | 617280 | West Bengal | 04/2019 | 02/2020 | 08/2026 | - | 255.37 | 255.37 | 85.9 | 42
October 2025 | 306 | Ministry of Mines | Metals & Mining | Rakha Underground Mining Project | Hindustan Copper Limited [HCL] | 611798 | Jharkhand | 12/2022 | 03/2024 | 03/2033 | - | 2705 | 2705 | 0 | 0
October 2025 | 307 | Ministry of Mines | Metals & Mining | Surda Underground Copper Mining Project | Hindustan Copper Limited [HCL] | 611800 | Jharkhand | 02/2022 | 03/2024 | 03/2028 | - | 665.02 | 665.02 | 23.43 | 1
October 2025 | 308 | Ministry of Mines | Metals & Mining | Expansion of Malanjkhand Copper Project | Hindustan Copper Limited [HCL] | 400426 | Madhya Pradesh | 09/2011 | 04/2015 | 04/2020 | 04/2026 | 1856.36 | 1856.36 | 940.27 | 81
October 2025 | 309 | Ministry of Mines | Metals & Mining | Expansion of Alumina Refinery Plant with addition of 5th Stream having capacity enhancement of 1.0 Million Tonee Per Annum | National Aluminium Company Limited [NALCO] | 400141 | Odisha | 04/2017 | 04/2017 | 12/2022 | 09/2025 | 4103 | 5677.4 | 4196.32 | 78
October 2025 | 310 | Ministry of Mines | Metals & Mining | Pottangi Bauxite Mines Project | National Aluminium Company Limited [NALCO] | 400299 | Odisha | 05/2018 | 05/2018 | 03/2025 | 05/2026 | 1381 | 1960.77 | 650.04 | 51
October 2025 | 311 | Ministry of Mines | Metals & Mining | UTKAL D AND E COAL BLOCK | National Aluminium Company Limited [NALCO] | 709829 | Odisha | NA | 02/2016 | 03/2025 | - | 1021.97 | 1021.97 | 0 | 0
October 2025 | 312 | Ministry of Mines | Metals & Mining | CONVERSION OF FLAT BOTTOM SETTLERS AND WASHERS WITH A SINGLE TRAIN OF HRDS AND DCWS IN STREAMS 1 AND | Ministry of Mines | 709830 | Odisha | NA | 04/2017 | 11/2026 | - | 355 | 581 | 0 | 0
October 2025 | 313 | Ministry of Mines | Metals & Mining | SOURCING OF BAUXITE ARRANGEMENT FOR 5TH STREAM ALUMINA REFINERY FROM SOUTH BLOCK MINING LEASE OF PANCHPATMAILI MINES | National Aluminium Company Limited [NALCO] | 709831 | Odisha | 11/2017 | 11/2019 | 05/2025 | 06/2026 | 483 | 483 | 411.79 | 90
October 2025 | 314 | Ministry of Mines | Metals & Mining | 25.5 MW WIND POWER PROJECT AT KAYATHAR IN TAMILNADU | National Aluminium Company Limited [NALCO] | 709832 | Tamil Nadu | 09/2017 | 12/2017 | 03/2025 | 03/2026 | 166 | 166 | 135 | 65
October 2025 | 315 | Department of Higher Education | Education | Construction of Permanent Campus of Central Tribal University of Andhra Pradesh Phase-1 | Central Tribal University of Andhra Pradesh | 613008 | Andhra Pradesh | 09/2019 | 12/2023 | 06/2027 | - | 305 | 305 | 19.96 | 32
October 2025 | 316 | Department of Higher Education | Education | Construction of Permanent Campus of National Institute of Technology Arunachal Pradesh | National Institute of Technology, Arunachal Pradesh | 612898 | Arunachal Pradesh | 09/2009 | 03/2013 | 08/2026 | - | 592.61 | 592.61 | 550.27 | 80
October 2025 | 317 | Department of Higher Education | Education | Tezpur University Projects | Tezpur University | 606112 | Assam | 05/2019 | 06/2021 | 11/2023 | 10/2025 | 153.71 | 153.71 | 124.33 | 97
October 2025 | 318 | Department of Higher Education | Education | Additional Campus of NITPatna | NIT Patna | 606013 | Bihar | 07/2022 | 08/2022 | 07/2024 | 01/2026 | 499.21 | 499.21 | 441.47 | 99
October 2025 | 319 | Department of Higher Education | Education | Phase 1B - Construction of Academic Block, Hostel, Residential Tower, Directors Residence and External Development works at National Institute of Technology, Delhi Campus on Engineering, Procurement and Construction basis | National Institute of Technology Delhi | 612851 | Delhi | 09/2009 | 11/2022 | 09/2025 | - | 333.49 | 336.42 | 291.33 | 97
October 2025 | 320 | Department of Higher Education | Education | Delhi University Eastern Campus at Surajmal Vihar | Delhi University | 616886 | Delhi | 09/2024 | 03/2025 | 10/2026 | - | 373 | 373 | 21.63 | 16
October 2025 | 321 | Department of Higher Education | Education | Construction of permanent campus of Central University of Gujarat at Village kundhela, Dist. Vadodara, Gujarat. | Central University of Gujarat | 612916 | Gujarat | 12/2020 | 02/2021 | 03/2025 | 03/2026 | 490.63 | 490.63 | 313.84 | 80
October 2025 | 322 | Department of Higher Education | Education | Establishment of Permanent campus Phase 1 of IIM Sirmaur | Indian Institute of Management, Sirmaur | 602099 | Himachal Pradesh | 09/2018 | 08/2020 | 10/2023 | 02/2026 | 392.51 | 454.78 | 326.24 | 93
October 2025 | 323 | Department of Higher Education | Education | Hostel blocks & dining hall block | Indian Institute of Technology, Mandi | 612128 | Himachal Pradesh | 03/2023 | 03/2024 | 03/2026 | 03/2026 | 166.66 | 166.66 | 85.92 | 73
October 2025 | 324 | Department of Higher Education | Education | Construction of Permanent Campus of Central University of Himachal Pradesh at Dehra, District - Kangra, [H.P.] on Engineering. Procurement and Construction [EPC Mode 1] Basis. | Central University, Himachal Pradesh | 612894 | Himachal Pradesh | 03/2021 | 08/2022 | 11/2024 | 11/2025 | 251.98 | 300.45 | 183.47 | 80
October 2025 | 325 | Department of Higher Education | Education | Construction of Permanent Campus for IIM Jammu Phase-1 at Jagti, Nagrota, Jammu, J&K | Indian Institute of Management, Jammu | 602098 | Jammu and Kashmir | 03/2019 | 10/2020 | 06/2023 | 11/2025 | 424.93 | 500.91 | 484.52 | 96
October 2025 | 326 | Department of Higher Education | Education | Additional Infrastructure at IISc Bangalore-RCC Monolithic for Men Hostel S14, Women Hostel S11 , Postdoctoral Hostel S12 2 Block , International Hostel S 12 , D&E Block S 12 2 Block FR. | IISC Bangalore | 610940 | Karnataka | 08/2021 | 08/2021 | 03/2024 | 12/2025 | 420.41 | 420.41 | 364.44 | 99
October 2025 | 327 | Department of Higher Education | Education | CONSTRUCTION OF PERMANENT CAMPUS FOR IIT PALAKKAD UNDER PHASE 1A | INDIAN INSTITUTE OF TECHNOLOGY PALAKKAD | 606431 | Kerala | 07/2017 | 03/2020 | 06/2022 | 11/2026 | 1006.45 | 1217.4 | 641.73 | 74
October 2025 | 328 | Department of Higher Education | Education | Phase III A works at IIT Indore [03 Hostels, 01 Studio Apartment, 01 Housing, Heavy & Sophisticated lab complex, Academic POD and Infrastructure for center of excellence] | Indian Institute of Technology, Indore | 611957 | Madhya Pradesh | 12/2023 | 04/2024 | 02/2027 | - | 496.28 | 496.28 | 38.62 | 37
October 2025 | 329 | Department of Higher Education | Education | Hostel 4 -Earlier Known as Hostel 20 | Indian Institute of Technology, Bombay | 612135 | Maharashtra | 09/2022 | 12/2023 | 09/2025 | 12/2025 | 182.33 | 182.33 | 156.51 | 98
October 2025 | 330 | Department of Higher Education | Education | Academic Block 1 & 2 | Indian Institute of Technology, Bombay | 612203 | Maharashtra | 09/2022 | 05/2023 | 07/2026 | 03/2027 | 68 | 263.93 | 27.4 | 20
October 2025 | 331 | Department of Higher Education | Education | Construction and Developement of National Institute of Technology Meghalaya Permanent Campus at Sohra | National Institute of Technology, Meghalaya | 612885 | Meghalaya | 09/2009 | 09/2014 | 03/2022 | 07/2025 | 494.52 | 494.52 | 419.57 | 89
October 2025 | 332 | Department of Higher Education | Education | Construction of Permanent Campus for NIT Mizoram at Lengpui, Aizawl | NIT Mizoram | 612876 | Mizoram | 09/2009 | 06/2014 | 12/2029 | 12/2029 | 474.23 | 474.23 | 167.55 | 4
October 2025 | 333 | Department of Higher Education | Education | Establishment of NIT Nagaland | NIT Nagaland | 613013 | Nagaland | 09/2009 | 12/2014 | 12/2025 | - | 275.63 | 275.63 | 261.24 | 97
October 2025 | 334 | Department of Higher Education | Education | IISER BERHAMPUR | Indian Institutes of Science Education and Research, Behrampur | 610315 | Odisha | 10/2018 | 09/2019 | 03/2021 | 12/2025 | 1229.32 | 773.76 | 838.21 | 97
October 2025 | 335 | Department of Higher Education | Education | Establishment of NIT Puducherry Permanent Campus [Phase-I and Phase-II] | National Institute of Technology, Puducherry | 612877 | Puducherry | 09/2009 | 07/2013 | 12/2024 | 08/2025 | 618.34 | 544.34 | 529.9 | 96
October 2025 | 336 | Department of Higher Education | Education | Construction of Permanent Campus of Indian Institute of Management [IIM] Amritsar, Punjab, Phase-I | Indian intitue of Management, Amritsar | 605292 | Punjab | 10/2019 | 07/2020 | 06/2023 | 12/2025 | 348.31 | 348.31 | 290.39 | 91
October 2025 | 337 | Department of Higher Education | Education | Construction of Girls Hostel 400 seater, Boys Hostel 600 seater, Academic Block, International Hostel 100 seater, VC Residence and Purchase of Equipment | Central University of Punjab | 617221 | Punjab | 08/2024 | 04/2025 | 10/2027 | - | 210.99 | 210.99 | 0 | 0
October 2025 | 338 | Department of Higher Education | Education | Construction of Sikkim University Campus Phase-I Package-II at Yangang, South Sikkim | Sikkim University | 609736 | Sikkim | 08/2020 | 01/2022 | 01/2025 | 03/2026 | 314.06 | 314.06 | 238.22 | 85
October 2025 | 339 | Department of Higher Education | Education | Establishment of Permanent Campus of NIT SIkkim at Khamdong-Gangtok District | NIT Sikkim | 612883 | Sikkim | 02/2024 | 03/2024 | 02/2028 | 12/2026 | 685.76 | 610.76 | 121.56 | 14
October 2025 | 340 | Department of Higher Education | Education | Construction of Precast housing and hostels at IIT Hyderabad | Indian Institute of Technology, Hyderabad | 609996 | Telangana | 09/2022 | 11/2022 | 10/2024 | 01/2026 | 262 | 262 | 186.49 | 79
October 2025 | 341 | Department of Higher Education | Education | Banaras Hindu University [ Kayakalp of Institute of Medical Sciences] | Banaras Hindu University | 606479 | Uttar Pradesh | 06/2020 | 06/2020 | 09/2022 | 03/2026 | 246 | 246 | 198.02 | 96
October 2025 | 342 | Department of Higher Education | Education | Construction & Development of Infrastructural Facilities in the main campus of NIT Uttarakhand at Sumari, Pauri Garhwal | National Institute of Technology Uttarakhand | 611963 | Uttarakhand | 06/2020 | 04/2024 | 09/2027 | - | 650.85 | 650.85 | 195.52 | 33
October 2025 | 343 | Department of Higher Education | Education | HEFA projects on development of student hostels, playgrounds, departmental buildings, class room complex and other campus facilities in IIT Kharagpur | Indian Institute of Technology, Kharagpur | 609019 | West Bengal | 06/2018 | 04/2019 | 03/2023 | 03/2026 | 500 | 442 | 390.6 | 89
October 2025 | 344 | Department of Sports | Education | National Sports University [NSU], Imphal [Manipur] | Department of Sports & Youth Affairs | 400081 | Manipur | NA | 01/2022 | 08/2024 | 11/2025 | 906.47 | 611.74 | 553.38 | 94
October 2025 | 345 | Ministry of Petroleum & Natural Gas | Energy Storage | Construction of Aviation Fuel farm Facilities at Bhogapuram Airport | Ministry of Petroleum & Natural Gas | 616235 | Andhra Pradesh | 08/2024 | 08/2024 | 03/2026 | 03/2026 | 240 | 240 | 61.94 | 77
October 2025 | 346 | Ministry of Petroleum & Natural Gas | Energy Storage | Construction of LPG Facilities at Kamardanga, Assam | Hindustan Petroleum Corporation Limited | 709754 | Assam | 03/2023 | 03/2023 | 07/2027 | 07/2027 | 156.36 | 156.36 | 63.31 | 50
October 2025 | 347 | Ministry of Petroleum & Natural Gas | Energy Storage | Setting up of new rail fed POL facility at Kamardanga, Assam | Hindustan Petroleum Corporation Limited [HPCL] | 709755 | Assam | 03/2023 | 03/2023 | 07/2027 | 07/2027 | 384.04 | 384.04 | 142.28 | 57
October 2025 | 348 | Ministry of Petroleum & Natural Gas | Energy Storage | Setting up a common user Petroleum Terminal at Jammu, J&K for resitement of existing PSU OMC's Depots from Jammu City | Bharat Petroleum Corporation Limited [BPCL] | 400235 | Jammu and Kashmir | 04/2023 | 04/2023 | 03/2025 | 01/2026 | 676.89 | 715.89 | 550.45 | 84
October 2025 | 349 | Ministry of Petroleum & Natural Gas | Energy Storage | Andheri Residential Towers, Mumbai | Ministry of Petroleum & Natural Gas | 604833 | Maharashtra | 06/2017 | 06/2017 | 05/2025 | 06/2026 | 281.35 | 389.67 | 238.39 | 51
October 2025 | 350 | Ministry of Petroleum & Natural Gas | Energy Storage | Srikakulam Angul Gas Pipeline Project | Ministry of Petroleum & Natural Gas | 701343 | Multi-States (Andhra Pradesh, Odisha) | 09/2019 | 09/2019 | 07/2022 | 12/2025 | 2658.34 | 2810 | 2282.98 | 96
October 2025 | 351 | Ministry of Petroleum & Natural Gas | Energy Storage | Rajasthan Refinery Project | MinistryofPetroleumNaturalGas | 701263 | Multi-States (Arunachal Pradesh, Gujarat, Rajasthan) | 10/2017 | 10/2017 | 10/2022 | 03/2026 | 43129 | 79459 | 61926.61 | 89
October 2025 | 352 | Ministry of Petroleum & Natural Gas | Energy Storage | Paradip-Numaligarh Crude Oil Pipeline [PNCPL] & Crude Oil Import Terminal [COIT] at Paradip | Ministry of Petroleum & Natural Gas | 701349 | Multi-States (Assam, Bihar, Jharkhand, Odisha, West Bengal) | 01/2019 | 01/2019 | 07/2024 | 03/2026 | 10228 | 11407 | 9921.29 | 88
October 2025 | 353 | Ministry of Petroleum & Natural Gas | Energy Storage | New Mundra Panipat Crude Oil Pipeline | Ministry of Petroleum & Natural Gas | 400078 | Multi-States (Gujarat, Haryana, Rajasthan) | 12/2021 | 12/2021 | 12/2024 | 12/2025 | 9028 | 9028 | 7292.34 | 86
October 2025 | 354 | Ministry of Petroleum & Natural Gas | Energy Storage | Kandla Gorakhpur LPG Pipeline | Ministry of Petroleum & Natural Gas | 400012 | Multi-States (Gujarat, Madhya Pradesh, Uttar Pradesh) | 12/2018 | 12/2018 | 12/2021 | 12/2025 | 10088 | 10088 | 8059.53 | 93
October 2025 | 355 | Ministry of Petroleum & Natural Gas | Energy Storage | Multi Product Pipeline from Irugur to Devangonthi | Department of Water Resources, River Development & GR | 400301 | Multi-States (Karnataka, Tamil Nadu) | 11/2012 | 11/2012 | 02/2017 | 09/2026 | 678 | 1732 | 800.88 | 73
October 2025 | 356 | Ministry of Petroleum & Natural Gas | Energy Storage | Petrochemical evacuation marketing terminal at Barmer, Rajasthan | Hindustan Petroleum Corporation Limited [HPCL] | 709759 | Rajasthan | 12/2023 | 12/2023 | 12/2026 | 12/2026 | 461.05 | 461.05 | 145.12 | 64
October 2025 | 357 | Ministry of Petroleum & Natural Gas | Energy Storage | Laying of POL Pipelines in Common Corridor for proposed grass root terminal at Vallur [Chennai] | Ministry of Petroleum & Natural Gas | 400043 | Tamil Nadu | 01/2022 | 01/2022 | 05/2026 | 05/2026 | 829 | 829 | 327.86 | 67
October 2025 | 358 | Ministry of Petroleum & Natural Gas | Energy Storage | Grass root POL Terminal at Vallur, Chennai | Indian Oil Corporation Limited [IOCL] | 400077 | Tamil Nadu | 01/2022 | 01/2022 | 12/2024 | 03/2026 | 827 | 887.71 | 638.71 | 89
October 2025 | 359 | Ministry of Petroleum & Natural Gas | Energy Storage | Grass Root Rail-fed Depot at Sekerkote, Agartala as resitement of existing Dharmanagar Depot | Indian Oil Corporation Limited [IOCL] | 400035 | Tripura | 06/2022 | 06/2022 | 09/2025 | 06/2026 | 656 | 656 | 509.92 | 89
October 2025 | 360 | Ministry of Petroleum & Natural Gas | Energy Storage | Grass-root Terminal at Mirzapur, Uttar Pradesh | Ministry of Petroleum & Natural Gas | 604852 | Uttar Pradesh | 09/2022 | 09/2022 | 11/2026 | 11/2026 | 980.45 | 980.45 | 227.04 | 57
October 2025 | 361 | Ministry of Petroleum & Natural Gas | Oil & Gas | KG-DWN-98/2 Cluster - II Development Project - NELP Block | Oil and Natural Gas Corporation Limited [ONGC] | 400120 | Andhra Pradesh | 03/2016 | 03/2016 | 06/2020 | 06/2026 | 34012 | 34012 | 32184.03 | 96
October 2025 | 362 | Ministry of Petroleum & Natural Gas | Oil & Gas | HP-COAT [Crude to Olefins and Aromatics Technology] demo unit at Visakh Refinery | Hindustan Petroleum Corporation Limited | 709752 | Andhra Pradesh | 09/2021 | 09/2021 | 06/2024 | 03/2026 | 160 | 220 | 92.6 | 76
October 2025 | 363 | Ministry of Petroleum & Natural Gas | Oil & Gas | City Gas Distribution Project at Kurnool, Guntur & Prakasam Districts | MinistryofPetroleumNaturalGas | 709766 | Andhra Pradesh | 03/2022 | 03/2022 | 03/2030 | 03/2030 | 1420 | 1420 | 167.02 | 6
October 2025 | 364 | Ministry of Petroleum & Natural Gas | Oil & Gas | Numaligarh Refinery Expansion Project | Ministry of Petroleum & Natural Gas | 604791 | Assam | 07/2020 | 07/2020 | 07/2024 | 12/2025 | 12366 | 22494 | 17659.09 | 78
October 2025 | 365 | Ministry of Petroleum & Natural Gas | Oil & Gas | Development of Surface Facilities for production and evacuation of Crude Oil and Natural Gas from Nadua and East Khagorija | Ministry of Petroleum & Natural Gas | 604863 | Assam | 01/2018 | 01/2018 | 02/2020 | 12/2025 | 682.9 | 726.93 | 491.64 | 94
October 2025 | 366 | Ministry of Petroleum & Natural Gas | Oil & Gas | Guwahati Refinery Expansion [1.0 to 1.2 MMTPA] along with installation of CRU, Guwahati Refinery | Ministry of Petroleum & Natural Gas | 607701 | Assam | 05/2021 | 05/2021 | 10/2023 | 05/2026 | 412.3 | 577 | 445.73 | 87
October 2025 | 367 | Ministry of Petroleum & Natural Gas | Oil & Gas | Construction of Field Gas Gathering Station at Baghjan area for collection, processing & transportation of natural Gas to be produced from Baghjan Field | Ministry of Petroleum & Natural Gas | 616858 | Assam | 12/2020 | 12/2020 | 03/2024 | 12/2025 | 430.76 | 430.76 | 330.99 | 87
October 2025 | 368 | Ministry of Petroleum & Natural Gas | Oil & Gas | Augmentation/Revamping of Facilities at existing Guwahati Terminal at Betkuchi | MinistryofPetroleumNaturalGas | 709776 | Assam | 04/2022 | 04/2022 | 09/2026 | 09/2026 | 277 | 323.09 | 188.04 | 68
October 2025 | 369 | Ministry of Petroleum & Natural Gas | Oil & Gas | Capacity Expansion of Digboi Refinery from 0.65 to 1.0 MMTPA | MinistryofPetroleumNaturalGas | 709779 | Assam | 06/2022 | 06/2022 | 03/2026 | 07/2027 | 768 | 740 | 123.97 | 44
October 2025 | 370 | Ministry of Petroleum & Natural Gas | Oil & Gas | Pipeline Network Project Rudrasagar | Ministry of Petroleum & Natural Gas | 709847 | Assam | 01/2023 | 01/2023 | 04/2026 | 04/2026 | 344.99 | 344.99 | 215.98 | 48
October 2025 | 371 | Ministry of Petroleum & Natural Gas | Oil & Gas | Borholla GGS Life Extension Project [BLEP] | Ministry of Petroleum & Natural Gas | 709850 | Assam | 09/2023 | 09/2023 | 05/2026 | 05/2026 | 198.7 | 198.7 | 50.26 | 40
October 2025 | 372 | Ministry of Petroleum & Natural Gas | Oil & Gas | DCU Revamp Project | NRL | 709864 | Assam | 08/2021 | 08/2021 | 07/2024 | 06/2026 | 370 | 370 | 266.35 | 64
October 2025 | 373 | Ministry of Petroleum & Natural Gas | Oil & Gas | Power Recovery Turbine [PRT] in PFCCU unit as an Energy Conservation Scheme | NRL | 709865 | Assam | 04/2023 | 04/2023 | 12/2024 | 12/2025 | 293.5 | 293.5 | 97.22 | 96
October 2025 | 374 | Ministry of Petroleum & Natural Gas | Oil & Gas | Setting up of LPG Plant with Rail Unloading Facility at Hathua, Dist. Gopalganj, Bihar | MinistryofPetroleumNaturalGas | 617304 | Bihar | 10/2023 | 10/2023 | 03/2027 | 03/2027 | 340.15 | 340.15 | 107.35 | 29
October 2025 | 375 | Ministry of Petroleum & Natural Gas | Oil & Gas | Barauni Refinery Capacity Expansion from 6.0 to 9.0 MMTPA | Ministry of Petroleum & Natural Gas | 701324 | Bihar | 01/2020 | 01/2020 | 04/2023 | 08/2026 | 14810 | 16724 | 12138.96 | 88
October 2025 | 376 | Ministry of Petroleum & Natural Gas | Oil & Gas | Installation of Bitumen Manufacturing Unit along with allied facilities at Barauni Refinery | MinistryofPetroleumNaturalGas | 709777 | Bihar | 01/2022 | 01/2022 | 04/2025 | 10/2026 | 389.35 | 340 | 73.97 | 47
October 2025 | 377 | Ministry of Petroleum & Natural Gas | Oil & Gas | City Gas Distribution Projects at Darbhanga, Madhubani, Supaul, Sitamarhi and Sheohar districts | Bharat Petroleum Corporation Limited [BPCL] | 709792 | Bihar | 12/2022 | 12/2022 | 03/2030 | 03/2030 | 3638 | 3638 | 422.37 | 29
October 2025 | 378 | Ministry of Petroleum & Natural Gas | Oil & Gas | City Gas Distribution Projects at Gopalganj, Siwan, West Champaran, East Champaran and Deoria districts | Bharat Petroleum Corporation Limited [BPCL] | 709793 | Bihar | 12/2022 | 12/2022 | 06/2030 | 06/2030 | 3919 | 3919 | 421.98 | 20
October 2025 | 379 | Ministry of Petroleum & Natural Gas | Oil & Gas | Redevelopment of Sobhasan Complex | Oil and Natural Gas Corporation Limited [ONGC] | 400087 | Gujarat | 08/2021 | 08/2021 | 02/2026 | 02/2026 | 885.63 | 1286.67 | 876.53 | 79
October 2025 | 380 | Ministry of Petroleum & Natural Gas | Oil & Gas | Redevelopment of Santhal Field [Onshore-Mehsana Asset] | Oil and Natural Gas Corporation Limited [ONGC] | 400167 | Gujarat | 02/2017 | 02/2017 | 03/2026 | 03/2026 | 1162.56 | 1162.56 | 1139.5 | 94
October 2025 | 381 | Ministry of Petroleum & Natural Gas | Oil & Gas | Redevelopment of Linch Field | Oil and Natural Gas Corporation Limited [ONGC] | 400169 | Gujarat | 04/2021 | 04/2021 | 03/2025 | 03/2026 | 631.03 | 860.04 | 572.74 | 85
October 2025 | 382 | Ministry of Petroleum & Natural Gas | Oil & Gas | Petrochemical and Lube Integration Project at Gujarat Refinery | Ministry of Petroleum & Natural Gas | 701329 | Gujarat | 09/2020 | 09/2020 | 08/2024 | 06/2026 | 18936 | 17825 | 12779.56 | 84
October 2025 | 383 | Ministry of Petroleum & Natural Gas | Oil & Gas | Installation of new Biturox Unit along with allied facilities at Gujarat Refinery | MinistryofPetroleumNaturalGas | 709778 | Gujarat | 01/2022 | 01/2022 | 08/2025 | 09/2026 | 328.29 | 287 | 172.32 | 65
October 2025 | 384 | Ministry of Petroleum & Natural Gas | Oil & Gas | Commercial Polymer Flooding Project in Bechraji field | Oil and Natural Gas Corporation Limited [ONGC] | 709838 | Gujarat | 01/2022 | 01/2022 | 11/2024 | 05/2027 | 621.4 | 739.02 | 137.73 | 24
October 2025 | 385 | Ministry of Petroleum & Natural Gas | Oil & Gas | Restoration of Gas Terminal, Phase-I [Part-A], Hazira | Oil and Natural Gas Corporation Limited [ONGC] | 709840 | Gujarat | 05/2022 | 05/2022 | 02/2025 | 12/2025 | 249.43 | 249.43 | 210.42 | 95
October 2025 | 386 | Ministry of Petroleum & Natural Gas | Oil & Gas | Old Pipe Line Replacement [OPRP] Group-A | Oil and Natural Gas Corporation Limited [ONGC] | 709841 | Gujarat | 07/2021 | 07/2021 | 07/2025 | 03/2026 | 173.03 | 169.84 | 152.39 | 89
October 2025 | 387 | Ministry of Petroleum & Natural Gas | Oil & Gas | Kalol Redevelopment Project, Ahmedabad Asset | Oil and Natural Gas Corporation Limited [ONGC] | 709842 | Gujarat | 08/2022 | 08/2022 | 03/2027 | 03/2027 | 1487.41 | 1487.41 | 937.5 | 62
October 2025 | 388 | Ministry of Petroleum & Natural Gas | Oil & Gas | Revamping of SV Stations, Gas Terminal & Kribhco Terminal | Oil and Natural Gas Corporation Limited [ONGC] | 709845 | Gujarat | 11/2022 | 11/2022 | 08/2026 | 08/2026 | 837.34 | 837.34 | 288.4 | 56
October 2025 | 389 | Ministry of Petroleum & Natural Gas | Oil & Gas | Indian Oil Technology Development and Deployment Centre at R&D Campus-II, Faridabad | Ministry of Petroleum & Natural Gas | 604853 | Haryana | 06/2019 | 06/2019 | 12/2022 | 10/2026 | 2281.94 | 3200 | 1841.09 | 64
October 2025 | 390 | Ministry of Petroleum & Natural Gas | Oil & Gas | Poly Butadiene Rubber plant at Panipat | Indian Oil Corporation Limited [IOCL] | 611917 | Haryana | 03/2022 | 03/2022 | 03/2025 | 06/2026 | 1459 | 2531.44 | 1381.16 | 74
October 2025 | 391 | Ministry of Petroleum & Natural Gas | Oil & Gas | Capacity Expansion of Panipat Refinery from 15 to 25 MMTPA | Ministry of Petroleum & Natural Gas | 701289 | Haryana | 02/2021 | 02/2021 | 09/2024 | 06/2026 | 34627 | 36225 | 26555.13 | 90
October 2025 | 392 | Ministry of Petroleum & Natural Gas | Oil & Gas | Installation of Multiple Effect Evaporator [MEE] for ETP-1, 2 & 4 of Panipat Refinery and Petrochemical Complex. | MinistryofPetroleumNaturalGas | 709783 | Haryana | 12/2020 | 12/2020 | 06/2023 | 06/2026 | 165.13 | 247.69 | 138.41 | 76
October 2025 | 393 | Ministry of Petroleum & Natural Gas | Oil & Gas | City Gas Distribution Project at Jammu, Udhampur, Reasi, Samba and Kathua Districts | MinistryofPetroleumNaturalGas | 709773 | Jammu and Kashmir | 03/2022 | 03/2022 | 03/2032 | 03/2032 | 538 | 538 | 4.1 | 0
October 2025 | 394 | Ministry of Petroleum & Natural Gas | Oil & Gas | Development of Jharia CBM Block [Phase-1] | Oil and Natural Gas Corporation Limited [ONGC] | 610984 | Jharkhand | 11/2019 | 11/2019 | 01/2024 | 01/2026 | 431 | 431 | 223.39 | 60
October 2025 | 395 | Ministry of Petroleum & Natural Gas | Oil & Gas | Laying of Natural Gas Pipeline from Hazaribagh to Ranchi [HRPL] | MinistryofPetroleumNaturalGas | 709785 | Jharkhand | 02/2023 | 02/2023 | 02/2026 | 02/2026 | 202.07 | 202.07 | 60.23 | 48
October 2025 | 396 | Ministry of Petroleum & Natural Gas | Oil & Gas | Power System Upgradation Project | Mangalore Refinary and Petrochemicals Limited | 612790 | Karnataka | 10/2023 | 10/2023 | 11/2025 | 05/2026 | 385 | 385 | 155.14 | 69
October 2025 | 397 | Ministry of Petroleum & Natural Gas | Oil & Gas | Demo Bio-ATF Project | Ministry of Petroleum & Natural Gas | 616879 | Karnataka | 03/2024 | 03/2024 | 01/2027 | 01/2027 | 364 | 364 | 32.59 | 19
October 2025 | 398 | Ministry of Petroleum & Natural Gas | Oil & Gas | Revamping/ Augmentation of facilities at existing port terminal at Mangalore | Ministry of Petroleum & Natural Gas | 709774 | Karnataka | 01/2022 | 01/2022 | 12/2025 | 12/2025 | 463 | 500.62 | 285.36 | 74
October 2025 | 399 | Ministry of Petroleum & Natural Gas | Oil & Gas | Replacement and Extension of Jetty Pipelines [REJP] at KR | Bharat Petroleum Corporation Limited [BPCL] | 709790 | Kerala | 03/2023 | 03/2023 | 03/2026 | 03/2026 | 621.87 | 621.87 | 203.68 | 88
October 2025 | 400 | Ministry of Petroleum & Natural Gas | Oil & Gas | Setting up Polypropylene Unit at Kochi Refinery | MinistryofPetroleumNaturalGas | 709799 | Kerala | 12/2023 | 12/2023 | 10/2027 | 10/2027 | 4460 | 4460 | 308.59 | 17
October 2025 | 401 | Ministry of Petroleum & Natural Gas | Oil & Gas | Ethylene Cracker Project at Bina Refinery including downstream Petrochemical Plants and expansion of Refinery | MinistryofPetroleumNaturalGas | 709798 | Madhya Pradesh | 05/2023 | 05/2023 | 05/2028 | 05/2028 | 43367 | 43367 | 1955 | 16
October 2025 | 402 | Ministry of Petroleum & Natural Gas | Oil & Gas | Debottlenecking and Augmentation of Cryogenic facilities at Uran LPG Import Terminal | Department of Water Resources, River Development & GR | 400158 | Maharashtra | 04/2021 | 04/2021 | 02/2024 | 12/2025 | 1164.69 | 1629.86 | 958.12 | 89
October 2025 | 403 | Ministry of Petroleum & Natural Gas | Oil & Gas | 500 KTA PDHPP Project, Usar | Ministry of Petroleum & Natural Gas | 400168 | Maharashtra | 04/2021 | 04/2021 | 04/2025 | 12/2025 | 8797 | 11256 | 7122.88 | 86
October 2025 | 404 | Ministry of Petroleum & Natural Gas | Oil & Gas | Construction of lube oil blending plant at Rasayani | Ministry of Petroleum & Natural Gas | 610985 | Maharashtra | 05/2022 | 05/2022 | 12/2023 | 12/2025 | 423.39 | 526.26 | 313 | 82
October 2025 | 405 | Ministry of Petroleum & Natural Gas | Oil & Gas | Lube Modernization & Bottom Upgradation Project at Mumbai Refinery | Ministry of Petroleum and Natural Gas | 616933 | Maharashtra | 12/2024 | 12/2024 | 03/2028 | 03/2028 | 4679 | 4679 | 211.77 | 5
October 2025 | 406 | Ministry of Petroleum & Natural Gas | Oil & Gas | HP TDAE Unit in Mumbai Refinery | Hindustan Petroleum Corporation Limited | 709760 | Maharashtra | 06/2024 | 06/2024 | 04/2026 | 04/2026 | 240 | 240 | 44.87 | 54
October 2025 | 407 | Ministry of Petroleum & Natural Gas | Oil & Gas | City Gas Distribution Project at Beed, Jalgaon and Jalna Districts | MinistryofPetroleumNaturalGas | 709771 | Maharashtra | 03/2022 | 03/2022 | 09/2031 | 09/2031 | 865 | 865 | 71.43 | 3
October 2025 | 408 | Ministry of Petroleum & Natural Gas | Oil & Gas | Construction of Additional Tankages and Allied Facilities at JNPT Terminal | MinistryofPetroleumNaturalGas | 709780 | Maharashtra | 04/2022 | 04/2022 | 08/2026 | 08/2026 | 341.43 | 436.14 | 289.06 | 52
October 2025 | 409 | Ministry of Petroleum & Natural Gas | Oil & Gas | ATF Pipeline from Jawaharlal Nehru Port Trust to Navi Mumbai International Airport | Indian Oil Corporation Limited [IOCL] | 709782 | Maharashtra | 08/2022 | 08/2022 | 08/2025 | 03/2026 | 165 | 165 | 94.21 | 78
October 2025 | 410 | Ministry of Petroleum & Natural Gas | Oil & Gas | Installation of Independent De- Aromatized Solvents [DAS] production facilities at MR | Bharat Petroleum Corporation Limited [BPCL] | 709789 | Maharashtra | 03/2023 | 03/2023 | 07/2025 | 12/2025 | 405 | 343 | 214.5 | 92
October 2025 | 411 | Ministry of Petroleum & Natural Gas | Oil & Gas | POL & LOBS Installations with Receipt Pipelines at Rasayani | Bharat Petroleum Corporation Limited [BPCL] | 709797 | Maharashtra | 05/2023 | 05/2023 | 05/2026 | 05/2026 | 2585 | 2585 | 711.91 | 65
October 2025 | 412 | Ministry of Petroleum & Natural Gas | Oil & Gas | Part Replacement Pipeline Project [PRPP] | Oil and Natural Gas Corporation Limited [ONGC] | 709846 | Maharashtra | 11/2022 | 11/2022 | 05/2024 | 12/2025 | 1219.48 | 1145.1 | 745 | 90
October 2025 | 413 | Ministry of Petroleum & Natural Gas | Oil & Gas | Visakh Raipur Pipeline Project | Ministry of Petroleum and Natural Gas | 616254 | Multi-States (Andhra Pradesh, Chhattisgarh, Odisha) | 09/2024 | 09/2024 | 09/2027 | 09/2027 | 2212 | 2212 | 21.1 | 11
October 2025 | 414 | Ministry of Petroleum & Natural Gas | Oil & Gas | North East Gas Grid | Ministry of Petroleum & Natural Gas | 701346 | Multi-States (Arunachal Pradesh, Assam, Manipur, Meghalaya, Mizoram, Nagaland, Sikkim, Tripura, West Bengal) | 04/2020 | 04/2020 | 03/2024 | 03/2026 | 9265 | 9265 | 6603.95 | 86
October 2025 | 415 | Ministry of Petroleum & Natural Gas | Oil & Gas | Upgradation of Facilities of Numaligarh-Siliguri Product Pipeline [NSPL] for transportation of additional products from existing 1.72 MMTPA to 5.5 MMTPA | Ministry of Petroleum & Natural Gas | 701350 | Multi-States (Assam, West Bengal) | 06/2021 | 06/2021 | 12/2024 | 12/2025 | 860 | 860 | 615.47 | 99
October 2025 | 416 | Ministry of Petroleum & Natural Gas | Oil & Gas | CGD Project in Banka, Dumka, Godda, Jamtara, Pakur, Sahibganj GA ID 11A.02 | Hindustan Petroleum Corporation Limited | 709757 | Multi-States (Bihar, Jharkhand) | 06/2022 | 06/2022 | 06/2030 | 06/2030 | 1377 | 1377 | 345.02 | 29
October 2025 | 417 | Ministry of Petroleum & Natural Gas | Oil & Gas | Mumbai Nagpur Jharsuguda Pipeline Project | Ministry of Petroleum & Natural Gas | 701354 | Multi-States (Chhattisgarh, Madhya Pradesh, Maharashtra, Odisha) | 06/2020 | 06/2020 | 05/2023 | 12/2025 | 7844.25 | 8255 | 6661.2 | 96
October 2025 | 418 | Ministry of Petroleum & Natural Gas | Oil & Gas | Mehsana-Bhatinda & Bhatinda-Jammu Natural Gas Pipeline | Ministry of Petroleum & Natural Gas | 701330 | Multi-States (Gujarat, Haryana, Punjab, Rajasthan) | 07/2011 | 07/2011 | 06/2024 | 12/2025 | 7392 | 7392 | 6308 | 90
October 2025 | 419 | Ministry of Petroleum & Natural Gas | Oil & Gas | Gurdaspur Jammu Pipeline | Gas Authority of India Limited [GAIL] | 612853 | Multi-States (Jammu and Kashmir, Punjab) | 07/2023 | 07/2023 | 07/2026 | 07/2026 | 521.9 | 521.9 | 230.2 | 40
October 2025 | 420 | Ministry of Petroleum & Natural Gas | Oil & Gas | Kochi - Koottanad - Bangalore - Mangalore Pipeline Phase-II | Ministry of Petroleum & Natural Gas | 701228 | Multi-States (Karnataka, Kerala, Tamil Nadu) | 06/2009 | 06/2009 | 12/2012 | 12/2025 | 2915 | 5909 | 4506.79 | 95
October 2025 | 421 | Ministry of Petroleum & Natural Gas | Oil & Gas | City Gas Distribution Maharashtra Natural Gas Limited | Ministry of Petroleum & Natural Gas | 701338 | Multi-States (Karnataka, Maharashtra) | 01/2006 | 01/2006 | 06/2031 | 06/2031 | 5535 | 5535 | 3986.49 | 0
October 2025 | 422 | Ministry of Petroleum & Natural Gas | Oil & Gas | Dhamra Haldia Pipeline Project | Ministry of Petroleum & Natural Gas | 701344 | Multi-States (Odisha, West Bengal) | 03/2020 | 03/2020 | 11/2022 | 12/2025 | 1030.65 | 1125 | 879.8 | 88
October 2025 | 423 | Ministry of Petroleum & Natural Gas | Oil & Gas | City Gas Distribution Projects at Fazilka [except area already authorized], Ganganagar and Hanumangarh districts | Bharat Petroleum Corporation Limited [BPCL] | 709794 | Multi-States (Punjab, Rajasthan) | 12/2022 | 12/2022 | 06/2030 | 06/2030 | 3207 | 3207 | 348.41 | 25
October 2025 | 424 | Ministry of Petroleum & Natural Gas | Oil & Gas | Augmentation/ Revamping of Dimapur Depot, Dimapur | MinistryofPetroleumNaturalGas | 709786 | Nagaland | 08/2023 | 08/2023 | 11/2027 | 11/2027 | 227.62 | 227.62 | 10.8 | 25
October 2025 | 425 | Ministry of Petroleum & Natural Gas | Oil & Gas | Integrated Para Xylene [PX] and Purified Terephthalic Acid [PTA] Project at Paradip Refinery | Ministry of Petroleum & Natural Gas | 604859 | Odisha | 07/2020 | 07/2020 | 01/2024 | 08/2026 | 13805 | 11783 | 8422.69 | 91
October 2025 | 426 | Ministry of Petroleum & Natural Gas | Oil & Gas | CUF POL Depot at Sadashibpur [Meramundali], Odisha | MinistryofPetroleumNaturalGas | 709800 | Odisha | 04/2021 | 04/2021 | 03/2026 | 03/2026 | 393.54 | 393.54 | 110.87 | 48
October 2025 | 427 | Ministry of Petroleum & Natural Gas | Oil & Gas | Life Extension of 48 well platforms of Mumbai High & Heera Fields | Oil and Natural Gas Corporation Limited [ONGC] | 400119 | Offshore | 12/2015 | 12/2015 | 04/2018 | 12/2025 | 3190.69 | 3375.9 | 3119.29 | 89
October 2025 | 428 | Ministry of Petroleum & Natural Gas | Oil & Gas | PRP-VIII [Group-A] | Ministry of Petroleum & Natural Gas | 616950 | Offshore | 09/2024 | 09/2024 | 02/2026 | 02/2026 | 1486.4 | 1486.4 | 272.3 | 23
October 2025 | 429 | Ministry of Petroleum & Natural Gas | Oil & Gas | Daman Upside Development Project | Oil and Natural Gas Corporation Limited [ONGC] | 709839 | Offshore | 06/2022 | 06/2022 | 10/2025 | 02/2026 | 4144.41 | 6406.9 | 4563.85 | 88
October 2025 | 430 | Ministry of Petroleum & Natural Gas | Oil & Gas | MHN TCPP PGC BGC Project [MTPBP] | Ministry of Petroleum & Natural Gas | 709848 | Offshore | 06/2022 | 06/2022 | 05/2026 | 05/2026 | 2329.45 | 2354.23 | 1148.9 | 59
October 2025 | 431 | Ministry of Petroleum & Natural Gas | Oil & Gas | PRP-VIII Group B [NH & BS Asset] | Ministry of Petroleum & Natural Gas | 709849 | Offshore | 06/2024 | 06/2024 | 02/2026 | 02/2026 | 2379.84 | 3165.53 | 1806.88 | 64
October 2025 | 432 | Ministry of Petroleum & Natural Gas | Oil & Gas | Integrated Development of 4 Contract Areas under DSF-II | Ministry of Petroleum & Natural Gas | 709851 | Offshore | 05/2023 | 05/2023 | 04/2027 | 04/2027 | 6183.79 | 6183.79 | 594.28 | 23
October 2025 | 433 | Ministry of Petroleum & Natural Gas | Oil & Gas | 2G Ethanol Biorefinery at Bathinda | Hindustan Petroleum Corporation Limited [HPCL] | 400171 | Punjab | 05/2020 | 05/2020 | 02/2023 | 03/2026 | 1421.46 | 1421.46 | 1201.66 | 95
October 2025 | 434 | Ministry of Petroleum & Natural Gas | Oil & Gas | City Gas Distribution Project at Pathankot District | MinistryofPetroleumNaturalGas | 709770 | Punjab | 03/2022 | 03/2022 | 09/2033 | 09/2033 | 151 | 151 | 8.75 | 2
October 2025 | 435 | Ministry of Petroleum & Natural Gas | Oil & Gas | CBR 9 MMTPA Project | Chennai Petroleum Corporation Limited [CPCL] | 604795 | Tamil Nadu | 09/2021 | 09/2021 | 06/2025 | 10/2028 | 31580 | 36354 | 1342.27 | 10
October 2025 | 436 | Ministry of Petroleum & Natural Gas | Oil & Gas | Laying of new 28 inch Desal Water Pipeline and 10 inch Reject Water Pipeline between CPCL Manali Refinery and CPCL Desalination plant at Ennore | Chennai Petroleum Corporation Limited [CPCL] | 709750 | Tamil Nadu | 01/2024 | 01/2024 | 09/2025 | 12/2025 | 205 | 205 | 56.22 | 51
October 2025 | 437 | Ministry of Petroleum & Natural Gas | Oil & Gas | City Gas Distribution Projects at the Nilgiris and Erode districts | Bharat Petroleum Corporation Limited [BPCL] | 709796 | Tamil Nadu | 12/2022 | 12/2022 | 03/2030 | 03/2030 | 3685 | 3685 | 244.45 | 20
October 2025 | 438 | Ministry of Petroleum & Natural Gas | Oil & Gas | Creation of Gas Dehydration Facilities, Tripura Asset | Oil and Natural Gas Corporation Limited [ONGC] | 709837 | Tripura | 03/2022 | 03/2022 | 05/2024 | 12/2025 | 209.33 | 131.51 | 70.1 | 66
October 2025 | 439 | Ministry of Petroleum & Natural Gas | Oil & Gas | PP Project, Pata | Gas Authority of India Limited [GAIL] | 400161 | Uttar Pradesh | 03/2019 | 03/2019 | 01/2024 | 11/2025 | 910.56 | 1299.02 | 1041 | 98
October 2025 | 440 | Ministry of Petroleum & Natural Gas | Oil & Gas | Revamping / Augmentation of Facilities at Mathura Bitumen Plant | MinistryofPetroleumNaturalGas | 709781 | Uttar Pradesh | 04/2022 | 04/2022 | 06/2027 | 12/2026 | 260.12 | 260.12 | 8.14 | 30
October 2025 | 441 | Ministry of Petroleum & Natural Gas | Oil & Gas | City Gas Distribution Projects at Lakhimpur Kheri , Sitapur, Bahraich, Shravasti,Balrampur, Siddharth Nagar & Maharajganj districts | Bharat Petroleum Corporation Limited [BPCL] | 709795 | Uttar Pradesh | 12/2022 | 12/2022 | 06/2030 | 06/2030 | 16654 | 16654 | 595.93 | 12
October 2025 | 442 | Ministry of Petroleum & Natural Gas | Oil & Gas | Durgapur - Haldia Pipeline [Section-3B of JHBDPL Project] | Ministry of Petroleum & Natural Gas | 617302 | West Bengal | 03/2017 | 03/2017 | 12/2020 | 12/2025 | 1740 | 2493.15 | 2285 | 90
October 2025 | 443 | Ministry of Petroleum & Natural Gas | Oil & Gas | Haldia Panagarh Pipeline Project | Hindustan Petroleum Corporation Limited | 709753 | West Bengal | 11/2022 | 11/2022 | 11/2025 | 05/2026 | 1010 | 1010 | 692.62 | 84
October 2025 | 444 | Ministry of Petroleum & Natural Gas | Oil & Gas | CGD Project in Malda, Birbhum, Murshidabad, Dakshin Dinajpur GA ID 11A.03 | Hindustan Petroleum Corporation Limited | 709758 | West Bengal | 06/2022 | 06/2022 | 06/2030 | 06/2030 | 2628 | 2628 | 348.91 | 29
October 2025 | 445 | Ministry of Petroleum & Natural Gas | Oil & Gas | City Gas Distribution Project at East Mednipore, West Mednipore & Jhargram Districts | MinistryofPetroleumNaturalGas | 709772 | West Bengal | 03/2022 | 03/2022 | 06/2031 | 06/2031 | 609 | 609 | 58.09 | 2
October 2025 | 446 | Ministry of Petroleum & Natural Gas | Oil & Gas | City Gas Distribution Projects at Alipurduar and Cooch Behar | Bharat Petroleum Corporation Limited [BPCL] | 709791 | West Bengal | 12/2022 | 12/2022 | 03/2030 | 03/2030 | 1017 | 1017 | 194.58 | 40
October 2025 | 447 | Ministry of Health & Family Welfare | Healthcare | AIIMS Majra Rewari Haryana | PMSSY AND Institute of NATIONAL Importance | 701173 | Haryana | 12/2023 | 02/2019 | 02/2023 | 12/2026 | 1299 | 1299 | 349.41 | 28
October 2025 | 448 | Ministry of Health & Family Welfare | Healthcare | AIIMS Kashmir at Awantipora Jammu & Kashmir | PMSSY AND Institute of NATIONAL Importance | 701167 | Jammu and Kashmir | 01/2019 | 11/2020 | 01/2025 | 12/2025 | 1828 | 1828 | 1321.7 | 68
October 2025 | 449 | Ministry of Health & Family Welfare | Healthcare | AIIMS Bibinagar | PMSSY AND Institute of NATIONAL Importance | 701171 | Telangana | 12/2018 | 07/2022 | 09/2022 | 12/2025 | 1028 | 1365.95 | 806.8 | 85
October 2025 | 450 | Ministry of Labour and Employment | Healthcare | Construction of 350 beds + 50 Super Specialty beds ESIC Hospital Sheelanagar, Visakhapatnam, Andhra Pradesh | Employee's State Insurance Company [ESIC] | 612167 | Andhra Pradesh | 02/2021 | 04/2023 | 10/2025 | 01/2026 | 384.27 | 384.27 | 105 | 40
October 2025 | 451 | Ministry of Labour and Employment | Healthcare | Construction of 200 bedded ESIC Hospital with 62 Nos Staff quarters , Beltola | Employee's State Insurance Company [ESIC] | 612201 | Assam | 12/2017 | 10/2021 | 04/2025 | 10/2025 | 143.23 | 154.75 | 101.83 | 93
October 2025 | 452 | Ministry of Labour and Employment | Healthcare | C/o Construction of 200 bedded [Up-gradable to 300 bedded] ESI Hospital at Surat Gujarat. | Employee's State Insurance Company [ESIC] | 612185 | Gujarat | 06/2019 | 03/2021 | 06/2025 | 05/2025 | 209.36 | 209.36 | 180.54 | 98
October 2025 | 453 | Ministry of Labour and Employment | Healthcare | 350 Bedded [Upgradable to 500 beds] ESI Hospital at Sanand | Employee's State Insurance Company [ESIC] | 612186 | Gujarat | 06/2022 | 04/2023 | 03/2026 | 02/2026 | 558.12 | 558.12 | 58.36 | 7
October 2025 | 454 | Ministry of Labour and Employment | Healthcare | Demolition, Construction and upgradation of ESI Hospital, Kalol, Gujarat from 50 beds to 150 beds. | Employee's State Insurance Company [ESIC] | 612211 | Gujarat | 08/2022 | 10/2023 | 10/2025 | 06/2026 | 205.87 | 205.87 | 31.49 | 16
October 2025 | 455 | Ministry of Labour and Employment | Healthcare | Construction of 100 bedded ESIC Hospital & 32 nos. of Staff qtrs at OMPURA J&K. | Employee's State Insurance Company [ESIC] | 612239 | Jammu and Kashmir | 09/2019 | 12/2021 | 09/2024 | 05/2025 | 131.05 | 164.93 | 1747.76 | 99
October 2025 | 456 | Ministry of Labour and Employment | Healthcare | Construction of 200 bed ESI Hospital at Bommasandra, Karnataka | Employee's State Insurance Company [ESIC] | 612745 | Karnataka | 02/2015 | 10/2024 | 01/2027 | - | 278 | 278 | 27.8 | 0
October 2025 | 457 | Ministry of Labour and Employment | Healthcare | Construction of 100 bed ESI Hospital and Staff Quarters [32 Nos.] at Harohalli, Karnataka | Employee's State Insurance Company [ESIC] | 612748 | Karnataka | 07/2019 | 03/2025 | 02/2027 | - | 150.92 | 150.92 | 0 | 0
October 2025 | 458 | Ministry of Labour and Employment | Healthcare | Construction of 200 Bedded [Upgradable to 500 Bedded including 50 beds of SST] ESIC Hospital at Bibewadi, Pune | Employee's State Insurance Company [ESIC] | 612188 | Maharashtra | 05/2018 | 03/2023 | 09/2025 | 02/2026 | 429.25 | 429.25 | 252.06 | 68
October 2025 | 459 | Ministry of Labour and Employment | Healthcare | Construction of 200 Bedded ESIC Hospital at Butibori, Nagpur, Maharashtra. | Employee's State Insurance Company [ESIC] | 612213 | Maharashtra | 10/2013 | 08/2022 | 08/2025 | 08/2025 | 194.93 | 196.7 | 86.6 | 60
October 2025 | 460 | Ministry of Labour and Employment | Healthcare | Upgradation & Extension of ESIC Hospital and Construction of PG Hostel / Staff Housing for ESIC Hospital at Andheri, Mumbai | Employee's State Insurance Company [ESIC] | 616691 | Maharashtra | NA | 06/2009 | 08/2025 | 12/2025 | 260.13 | 260.13 | 210.12 | 88
October 2025 | 461 | Ministry of Labour and Employment | Healthcare | Construction of 100 Bedded ESI Hospital at Duburi, Odisha. | Employee's State Insurance Company [ESIC] | 612513 | Odisha | 12/2010 | 02/2025 | 06/2027 | - | 164.6 | 164.6 | 16.4 | 1
October 2025 | 462 | Ministry of Labour and Employment | Healthcare | Construction of 100 Bedded ESIC Hospital building and 32 Nos Residential Quarters at Vallam Vadangal, SIPCOT, Sriperumbudur | Employee's State Insurance Company [ESIC] | 612178 | Tamil Nadu | 02/2015 | 03/2023 | 06/2025 | - | 152.95 | 152.95 | 107.83 | 98
October 2025 | 463 | Ministry of Labour and Employment | Healthcare | Construction of New OPD Block 200 Bed ward Basement + GF + 6 Floors at the location of old OPD block, at existing ESIC Hospital/ Medical college campus, Sanathnagar, Hyderabad | Employee's State Insurance Company [ESIC] | 612688 | Telangana | 11/2017 | 10/2021 | 06/2024 | 06/2025 | 211.13 | 211.13 | 198.95 | 100
October 2025 | 464 | Ministry of Labour and Employment | Healthcare | CONSTRUCTION OF 300 BEDDED HOSPITAL AT HARIDWAR | Employee's State Insurance Company [ESIC] | 612259 | Uttarakhand | 02/2021 | 12/2021 | 10/2024 | 06/2025 | 102.4 | 297.63 | 297.63 | 68
October 2025 | 465 | Ministry of Ports, Shipping and Waterways | Healthcare | Establishment of 600 bed super specialty hospital with optional development of Medical college and further expansion on PPP basis. | Mumbai Port Trust [MPT] | 708662 | Maharashtra | 08/2019 | 01/2022 | 06/2026 | 12/2027 | 693 | 693 | 58 | 0
October 2025 | 466 | Ministry of Ports, Shipping and Waterways | Inland Waterways | Jal Marg Vikas Project | Inland Waterways Authority of India [IWAI] | 701565 | Multi-States (Bihar, Jharkhand, Uttar Pradesh, West Bengal) | 01/2018 | 02/2018 | 12/2023 | 12/2025 | 5369.18 | 5061.15 | 3526.99 | 72
October 2025 | 467 | Ministry of Ports, Shipping and Waterways | Inland Waterways | Fairway Development in West Bengal Farakka - Kahelgaon | Inland Waterways Authority of India [IWAI] | 611142 | Offshore | NA | 08/2018 | 07/2023 | 04/2024 | 177 | 197 | 183.32 | 100
October 2025 | 468 | Ministry of Ports, Shipping and Waterways | Shipping | Development of Container Terminal at Tuna-Tekra, Deendayal Port on BOT Basis Under PPP Mode | Deendayal Port Trust [DPT] | 609424 | Gujarat | 10/2022 | 03/2024 | 03/2027 | - | 4243.64 | 4243.64 | 800.04 | 32
October 2025 | 469 | Ministry of Ports, Shipping and Waterways | Shipping | Construction of oil jetty No.8 at old kandla through internal resources | Deendayal Port Trust [DPT] | 701568 | Gujarat | NA | 02/2021 | 02/2023 | 07/2024 | 100 | 225.85 | 166.48 | 90
October 2025 | 470 | Ministry of Ports, Shipping and Waterways | Shipping | Replacement and revamping of pipeline projects in oil jetty area, Kandla | Deendayal Port Trust [DPT] | 701570 | Gujarat | 09/2021 | 09/2021 | 09/2023 | 03/2025 | 171 | 211.61 | 137.51 | 71
October 2025 | 471 | Ministry of Ports, Shipping and Waterways | Shipping | Mechanization of Berth No.14 for handling Containers and other cargo on DBFOT basis - Phase II | New Mangalore Port Authority | 617804 | Karnataka | NA | 06/2024 | 03/2027 | - | 153.23 | 153.23 | 50.1 | 33
October 2025 | 472 | Ministry of Ports, Shipping and Waterways | Shipping | Construction of new dry dock at exisitng Cochin Shipyard Limited premises at Perumanoor, Kochi 682 015 | Cochin Shipyard | 701564 | Kerala | 04/2018 | 05/2018 | 12/2022 | 03/2025 | 1799 | 1799 | 1558.39 | 96
October 2025 | 473 | Ministry of Ports, Shipping and Waterways | Shipping | Rewas Port Project | Reliance Industries Ltd | 400382 | Maharashtra | NA | 01/2020 | 03/2023 | - | 6000 | 6000 | 5999.89 | 0
October 2025 | 474 | Ministry of Ports, Shipping and Waterways | Shipping | Setting up of a Floating Storage and Regasification Unit [FSRU] - Mumbai | Mumbai Port Trust [MPT] | 701586 | Maharashtra | NA | 04/2021 | 11/2026 | 11/2026 | 900 | 900 | 65 | 0
October 2025 | 475 | Ministry of Ports, Shipping and Waterways | Shipping | Deepening and Optimization of Inner Harbour facilities including development of Western Dock on BOT basis to handle Cape size vessels | Paradip Port Trust [PPT] | 701574 | Odisha | 05/2022 | 01/2023 | 12/2027 | 10/2028 | 3004.63 | 3004.63 | 1149.79 | 40
October 2025 | 476 | Ministry of Ports, Shipping and Waterways | Shipping | Berth No. 2 [previously Berth 3] of HDC Mechanization Project | Haldia Dock Complex, Syama Prasad Mookerjee Port Authority | 701576 | West Bengal | NA | 03/2023 | 09/2025 | 01/2026 | 298.26 | 298.26 | 438.5 | 97
October 2025 | 477 | Ministry of Ports, Shipping and Waterways | Shipping | Shalukkhali Liquid Cargo Handling Facility Development Project | Haldia Dock Complex, Syama Prasad Mookerjee Port Authority | 701577 | West Bengal | NA | 08/2022 | 08/2025 | - | 253.65 | 253.65 | 9.28 | 0
October 2025 | 478 | Ministry of Ports, Shipping and Waterways | Tourism, Hospitality & Wellness | National Maritime Heritage Complex [NMHC] Phase-I | Indian Port Rail & Ropeway Corporation Ltd. [IPRCL] | 707215 | Gujarat | 02/2019 | 01/2022 | 03/2024 | 09/2025 | 573 | 1238.05 | 496.63 | 66
October 2025 | 479 | Ministry of Steel | Metals & Mining | Capacity expansion of Deposit-14 and 14 NMZ at Kirandul | National Mineral Development Corporation Limited [NMDC] | 615202 | Chhattisgarh | 08/2021 | 07/2022 | 12/2028 | 03/2028 | 1700 | 1756.2 | 133.22 | 6
October 2025 | 480 | Ministry of Steel | Steel | Stamp Charge Battery No.12 Battery Proper at IISCO Steel Plant | Steel Authority of India Limited [SAIL] | 617338 |  | 01/2025 | 02/2025 | 07/2028 | - | 2518.39 | 2518.39 | 152.23 | 4
October 2025 | 481 | Ministry of Steel | Steel | Replacement of Hot Leveller No.1 of Plate Mill at Bhilai Steel Plant | Steel Authority of India Limited [SAIL] | 617243 | Chhattisgarh | 07/2024 | 08/2024 | 07/2026 | - | 198.62 | 198.62 | 12.21 | 15
October 2025 | 482 | Ministry of Steel | Steel | Replacement of Converter Vessels, Trunnion Rings, Support System & Installation of Secondary Emission at Bhilai Steel Plant | Steel Authority of India Limited [SAIL] | 617255 | Chhattisgarh | 10/2023 | 12/2023 | 06/2026 | - | 471.83 | 471.83 | 158.07 | 46
October 2025 | 483 | Ministry of Steel | Steel | Rebuilding of Coke Oven Battery No.7 & 8 at Bhilai Steel Plant | Steel Authority of India Limited [SAIL] | 617256 | Chhattisgarh | 11/2023 | 01/2024 | 10/2025 | - | 884.1 | 884.1 | 506.96 | 80
October 2025 | 484 | Ministry of Steel | Steel | NMDC Slurry Pipeline Project Phase-1 | National Mineral Development Corporation Limited [NMDC] | 706811 | Chhattisgarh | 11/2015 | 09/2020 | 06/2023 | 12/2025 | 2907 | 5427 | 3179.93 | 88
October 2025 | 485 | Ministry of Steel | Steel | SCREENING PLANT-III AT KIRANDUL | National Mineral Development Corporation Limited [NMDC] | 709826 | Chhattisgarh | NA | 10/2021 | 01/2026 | - | 2718.84 | 2718.84 | 1384.73 | 77
October 2025 | 486 | Ministry of Steel | Steel | CONSTRUCTION OF RESIDENTIAL TOWERS AT BIOM KIRANDUL COMPLEX | National Mineral Development Corporation Limited [NMDC] | 709827 | Chhattisgarh | NA | 10/2022 | 12/2025 | - | 349.75 | 349.75 | 294.65 | 94
October 2025 | 487 | Ministry of Steel | Steel | New Sinter Plant at BSL, SAIL | Steel Authority of India Limited [SAIL] | 400174 | Jharkhand | 03/2015 | 10/2015 | 10/2017 | 06/2027 | 1034.01 | 1752.3 | 885.26 | 53
October 2025 | 488 | Ministry of Steel | Steel | Replacement of existing Grinders in CRM-I & II at Bokaro Steel Plant | Steel Authority of India Limited [SAIL] | 617249 | Jharkhand | 01/2025 | 02/2025 | 01/2027 | - | 211.94 | 211.94 | 16.04 | 11
October 2025 | 489 | Ministry of Steel | Steel | Secondary Emission Control in Converters of SMS-II at Bokaro Steel Plant | Steel Authority of India Limited [SAIL] | 617250 | Jharkhand | 01/2025 | 02/2025 | 10/2026 | - | 207.13 | 207.13 | 15.76 | 8
October 2025 | 490 | Ministry of Steel | Steel | Revamping of old sub-systems of Blast Furnace 3 at Bokaro Steel Plant | Steel Authority of India Limited [SAIL] | 617253 | Jharkhand | 08/2023 | 03/2023 | 07/2025 | 11/2025 | 513.82 | 513.82 | 257.89 | 74
October 2025 | 491 | Ministry of Steel | Steel | Replacement of remaining 04 sets of Battery Cyclones with 04 Nos. of ESPs in Sinter Plant-1 at Bokaro Steel Plant | Steel Authority of India Limited [SAIL] | 617254 | Jharkhand | 03/2024 | 04/2024 | 06/2026 | - | 260.37 | 260.37 | 54.89 | 23
October 2025 | 492 | Ministry of Steel | Steel | Rebuilding of Coke Oven Battery No.6 at Bokaro Steel Plant | Steel Authority of India Limited [SAIL] | 617257 | Jharkhand | 11/2023 | 12/2023 | 11/2026 | - | 627.31 | 627.31 | 153.32 | 46
October 2025 | 493 | Ministry of Steel | Steel | Construction of Screening Plant-II for Donimalai and Kumaraswamy Iron Ore Mining Complex of NMDC Limited at Ballari Dt, Karnataka. | National Mineral Development Corporation Limited [NMDC] | 400121 | Karnataka | 11/2014 | 06/2024 | 08/2026 | - | 1043.63 | 1043.63 | 288.87 | 35
October 2025 | 494 | Ministry of Steel | Steel | Installation of 4th Slab Caster along with its Auxiliaries and a New Ladle Furnace in SMS-II at Rourkela Steel Plant | Steel Authority of India Limited [SAIL] | 400065 | Odisha | 01/2022 | 02/2022 | 05/2025 | 09/2025 | 1105.23 | 1105.23 | 790.11 | 99
October 2025 | 495 | Ministry of Steel | Steel | Rebuilding of COB 4 at Durgapur Steel Plant | Steel Authority of India Limited [SAIL] | 612781 | West Bengal | 09/2023 | 09/2023 | 12/2026 | - | 916.78 | 916.78 | 146.64 | 20
October 2025 | 496 | Ministry of Steel | Steel | Installation of New Bar Mill at Durgapur Steel Plant | Steel Authority of India Limited [SAIL] | 617242 | West Bengal | 07/2024 | 08/2024 | 06/2027 | - | 2115.44 | 2115.44 | 236.73 | 32
October 2025 | 497 | Ministry of Steel | Steel | Up-gradation of Blast Furnace No. 3 at Durgapur Steel Plant | Steel Authority of India Limited [SAIL] | 617246 | West Bengal | 09/2024 | 08/2024 | 06/2026 | - | 758.09 | 758.09 | 85.89 | 7
October 2025 | 498 | Ministry of Steel | Steel | Third Ladle Furnace in Secondary Refinery Unit at IISCO Steel Plant | Steel Authority of India Limited [SAIL] | 617248 | West Bengal | 11/2024 | 12/2024 | 07/2026 | - | 227.96 | 227.96 | 27.2 | 33
October 2025 | 499 | Ministry of Steel | Steel | Revamping of Air Pollution Control Systems of SP-1 at Durgapur Steel Plant | Steel Authority of India Limited [SAIL] | 617251 | West Bengal | 07/2024 | 12/2024 | 05/2026 | - | 196.4 | 196.4 | 5.96 | 5
October 2025 | 500 | Ministry of Railways | Railways | Nadikudi - Srikalahasti New Line | South Central Railway [SCR] - II | 400298 | Andhra Pradesh | 03/2012 | 12/2016 | 05/2027 | 03/2028 | 2312 | 5200 | 2179 | 54
October 2025 | 501 | Ministry of Railways | Railways | Malugur- Palasamudram New Line Project [17.975 Km] | South Western Railway [SWR] - II | 611615 | Andhra Pradesh | 09/2022 | 07/2026 | 11/2027 | 12/2027 | 342 | 342 | 0 | 0
October 2025 | 502 | Ministry of Railways | Railways | GOOTY-PENDEKALLU DOUBLING 29.225 Km | South Central Railway [SCR] - II | 611752 | Andhra Pradesh | 03/2023 | 06/2023 | 03/2027 | 03/2027 | 351.83 | 351.83 | 18 | 25
October 2025 | 503 | Ministry of Railways | Railways | GUNTAKAL WEST-MALLAPPA GATE RAIL OVER RAIL - ROR TRACK | South Central Railway [SCR] - II | 611754 | Andhra Pradesh | 07/2023 | 07/2023 | 07/2026 | - | 293.3 | 293.3 | 0 | 0
October 2025 | 504 | Ministry of Railways | Railways | Kurnool - Setting up facilities for coach midlife rehabilitation workshop | WPO/Patna | 611927 | Andhra Pradesh | 01/2014 | 10/2017 | 12/2023 | - | 560.72 | 560.72 | 276.66 | 65
October 2025 | 505 | Ministry of Railways | Railways | Flyover between Pendurthi and Simhachalam North to avoid surface crossing at Simhachalam 7.135 km PB 73 of 2023 24 NR | East Coast Railway [ECoR] - II | 612827 | Andhra Pradesh | 04/2023 | 05/2024 | 04/2027 | - | 183.65 | 183.65 | 5.11 | 11
October 2025 | 506 | Ministry of Railways | Railways | 3rd & 4th line between Vadlapudi -Gate Jn. cabin and Tie line between Gate Junction to Gangavaram port | East Coast Railway [ECoR] - II | 616697 | Andhra Pradesh | 04/2023 | 03/2024 | 06/2026 | - | 154.28 | 154.28 | 20.15 | 21
October 2025 | 507 | Ministry of Railways | Railways | Tiupati Katpadi 104.39 kms | South Central Railway [SCR] - II | 617210 | Andhra Pradesh | 04/2025 | 04/2025 | 03/2029 | - | 1215.56 | 1215.56 | 0.1 | 0
October 2025 | 508 | Ministry of Railways | Railways | 3rd Line between Gudur Renigunta 83.17 Km | South Central Railway [SCR] - II | 617216 | Andhra Pradesh | 10/2024 | 10/2024 | 03/2027 | - | 877.34 | 877.34 | 23.35 | 0
October 2025 | 509 | Ministry of Railways | Railways | Kurnool Coach Midlife Rehabilitation Project | WPO/Patna | 705253 | Andhra Pradesh | 05/2016 | 07/2014 | 12/2020 | - | 563 | 563 | 120 | 0
October 2025 | 510 | Ministry of Railways | Railways | Kotapalli - Narasapur New Line | South Central Railway [SCR] - II | 705436 | Andhra Pradesh | 03/2009 | 09/2013 | 03/2028 | 03/2028 | 2501 | 2501 | 1318.88 | 29
October 2025 | 511 | Ministry of Railways | Railways | Guntur-Guntakal Doubling Project | South Central Railway [SCR] - II | 705633 | Andhra Pradesh | 03/2017 | 11/2017 | 12/2025 | 12/2026 | 3733 | 4295 | 4475.84 | 93
October 2025 | 512 | Ministry of Railways | Railways | Vijaywada-Gudur 3rd Line | RVNL - II | 705648 | Andhra Pradesh | 08/2016 | 04/2018 | 11/2024 | 12/2025 | 6654 | 6654 | 5922 | 90
October 2025 | 513 | Ministry of Railways | Railways | Penukonda - Dharmavaram Doubling Project [41.5 Km] | South Western Railway [SWR] - II | 705789 | Andhra Pradesh | 06/2018 | 12/2018 | 03/2026 | 03/2026 | 307.66 | 307.66 | 259.52 | 65
October 2025 | 514 | Ministry of Railways | Railways | Doubling of New Bonggigaon to Kamakhya via Goalpara - 176 km | Northeast Frontier Railway [NFR] | 705572 | Assam | 09/2016 | 09/2016 | 03/2026 | 03/2026 | 4060 | 4961 | 3727.78 | 93
October 2025 | 515 | Ministry of Railways | Railways | Guwahati-Dibrugarh via Tinsukia & Simaluguri-Dibrugarh | Central Organisation for Railway Electrification [CORE] | 706922 | Assam | 09/2020 | 09/2018 | 09/2020 | 06/2024 | 890.36 | 889.36 | 391.73 | 89
October 2025 | 516 | Ministry of Railways | Railways | Mariani-Jorhat, Tinsukia-Dangri and Makum -TirapTrack Electrification Project | GM/C/ NFR | 706940 | Assam | 09/2018 | 01/2022 | 05/2024 | - | 183.99 | 183.99 | 0 | 0
October 2025 | 517 | Ministry of Railways | Railways | Harmuty-Murkongselek Branch Line Electrification Project | GM/C/ NFR | 706942 | Assam | 09/2018 | 01/2022 | 05/2024 | - | 237.52 | 237.52 | 0 | 0
October 2025 | 518 | Ministry of Railways | Railways | Sakri -Hasanpur [via Harnagar - Kusheshwar Asthan] New Railway line | East Central Railway [ECR] - I | 400254 | Bihar | 12/2023 | 08/1997 | 12/2024 | 03/2027 | 735.2 | 735.2 | 588.66 | 84
October 2025 | 519 | Ministry of Railways | Railways | Construction of Bulb line at Nabinagar Ankorah of East Central Railway | East Central Railway [ECR] - I | 617231 | Bihar | 06/2024 | 06/2024 | 06/2028 | - | 611.74 | 611.74 | 0 | 0
October 2025 | 520 | Ministry of Railways | Railways | Jhajha-Batai New Line Project | East Central Railway [ECR] - I | 617373 | Bihar | 03/2023 | 03/2023 | 03/2027 | - | 588.18 | 588.18 | 3.05 | 0
October 2025 | 521 | Ministry of Railways | Railways | Khagaria-Kusheshwar Asthan [42Km] new line project | East Central Railway [ECR] - I | 705364 | Bihar | 04/2019 | 12/1998 | 12/2024 | 03/2027 | 614 | 1384 | 487.99 | 55
October 2025 | 522 | Ministry of Railways | Railways | Hajipur-Sagauli New line | East Central Railway [ECR] - I | 705366 | Bihar | 10/2007 | 10/2004 | 03/2020 | 12/2026 | 2067 | 2087 | 2013.82 | 74
October 2025 | 523 | Ministry of Railways | Railways | Araria Supaul New BG Line | East Central Railway [ECR] - I | 705368 | Bihar | 06/2018 | 03/2009 | 03/2024 | 01/2027 | 1605 | 2514 | 1547.96 | 35
October 2025 | 524 | Ministry of Railways | Railways | Fatuha-Islampur incl. MM for extn.of NL from Neora to Daniawan , Daniawan to Biharsharif, Biharsharif to Barbigha , Barbigha to Shekhpura | East Central Railway [ECR] - I | 705373 | Bihar | 08/2002 | 03/2002 | 03/2023 | 08/2025 | 1473 | 2882 | 2535.73 | 94
October 2025 | 525 | Ministry of Railways | Railways | Jogbani-Biratnagar New Rail Line project | Indian Railway Construction International Limited [IRCON] | 705450 | Bihar | 06/2010 | 01/2011 | 03/2022 | 12/2026 | 402 | 486 | 367.54 | 86
October 2025 | 526 | Ministry of Railways | Railways | Samastipur-Darbhanga Doubling Railway Project | East Central Railway [ECR] - I | 705526 | Bihar | 11/2015 | 12/2015 | 03/2025 | 10/2025 | 519 | 519 | 367.57 | 84
October 2025 | 527 | Ministry of Railways | Railways | Sagauli-Valmiknagar | East Central Railway [ECR] - I | 705527 | Bihar | 03/2018 | 03/2017 | 12/2025 | 12/2025 | 1216 | 2222 | 2072.37 | 91
October 2025 | 528 | Ministry of Railways | Railways | Muzaffarpur-Sugauli | East Central Railway [ECR] - I | 705528 | Bihar | 03/2018 | 03/2017 | 06/2024 | 02/2026 | 1586 | 1586 | 1470.4 | 99
October 2025 | 529 | Ministry of Railways | Railways | Rampur Dumra-Tal-Rajendrapul Additional Bridge and Railway Line Doubling | Indian Railway Construction International Limited [IRCON] | 706759 | Bihar | 03/2016 | 05/2017 | 12/2024 | 12/2025 | 2373.64 | 1700.24 | 1427.78 | 97
October 2025 | 530 | Ministry of Railways | Railways | Barauni-Bachwara [16 km] - 3rd & 4th line incl. Barauni yard remodelling [32 km] | East Central Railway [ECR] - I | 706860 | Bihar | 10/2022 | 08/2025 | 08/2025 | 10/2026 | 645 | 645 | 7.96 | 55
October 2025 | 531 | Ministry of Railways | Railways | JHAJHA - BATIA | East Central Railway [ECR] - I | 900874 | Bihar | 03/2023 | 03/2023 | 03/2028 | 01/2030 | 588.18 | 588.18 | 0.8 | 0
October 2025 | 532 | Ministry of Railways | Railways | Kharsia-Dharamjaygarh with Spur line [East Corridor-Phase 1] | Indian Railway Construction International Limited [IRCON] | 400220 | Chhattisgarh | 03/2016 | 01/2014 | 09/2018 | 03/2026 | 3055 | 3438 | 2594.89 | 94
October 2025 | 533 | Ministry of Railways | Railways | Doubling of Kirandul-Jagdalpur Line [150 km] | East Coast Railway [ECoR] - II | 400291 | Chhattisgarh | 02/2013 | 03/2013 | 03/2020 | 12/2025 | 1589 | 1798 | 1566.97 | 93
October 2025 | 534 | Ministry of Railways | Railways | Gauge Conversion of Kendri-Dhamtari including Abhanpur - Rajim Branch line 67.20 Kms - 2nd Material Modification to Raipur Titlagarh doubling. | SECR | 602792 | Chhattisgarh | 07/2011 | 05/2021 | 02/2025 | 03/2026 | 1171 | 1171 | 376 | 100
October 2025 | 535 | Ministry of Railways | Railways | 4th line between Nipania Bhatapara 14.4 Km | South East Central Railway [SECR] - II | 612815 | Chhattisgarh | 12/2022 | 05/2024 | 03/2027 | - | 170.49 | 170.49 | 1.34 | 5
October 2025 | 536 | Ministry of Railways | Railways | Dharamjaigarh-Korba 63 km | CERL | 613003 | Chhattisgarh | 08/2023 | 07/2022 | 08/2026 | - | 1686.26 | 1686.26 | 288.83 | 18.5
October 2025 | 537 | Ministry of Railways | Railways | KHARSIA- NAYA RAIPUR-PARMALKASA 5th and 6th Line [278KM] | CAO/C/SECR | 617200 | Chhattisgarh | 04/2025 | 04/2025 | 03/2031 | - | 7853.84 | 7853.84 | 0 | 0
October 2025 | 538 | Ministry of Railways | Railways | Dallirajhara - Rowghat New Rail Line Project, Phase-I | Rail Vikas Nigam Limited | 617374 | Chhattisgarh | NA | 11/2009 | 03/2025 | - | 1516.45 | 1516.45 | 873.79 | 92
October 2025 | 539 | Ministry of Railways | Railways | Dallirajhra- Rowghat New Railway Line - Phase I [95 km] | Rail Vikas Nigam Limited | 705433 | Chhattisgarh | 07/2009 | 12/2009 | 09/2025 | 12/2025 | 1628 | 1628 | 1440.85 | 82
October 2025 | 540 | Ministry of Railways | Railways | Gevra Road-Pendra Road New Railway Line [135 km] | Indian Railway Construction International Limited [IRCON] | 705444 | Chhattisgarh | 04/2014 | 04/2014 | 03/2022 | 12/2025 | 4970 | 4970 | 4449.99 | 73
October 2025 | 541 | Ministry of Railways | Railways | Boridand - Ambikapur Doubling Line Project | South East Central Railway [SECR] - II | 706854 | Chhattisgarh | 06/2022 | 04/2022 | 06/2030 | 06/2030 | 1376 | 1576.23 | 139.49 | 21
October 2025 | 542 | Ministry of Railways | Railways | 4TH LINE - BHATAPARA-HATHBAND [8.8 KM] [PB-72/NR/2022-23] | SECR | 709815 | Chhattisgarh | 09/2022 | 05/2024 | 01/2027 | 12/2027 | 177.03 | 177.03 | 0 | 3
October 2025 | 543 | Ministry of Railways | Railways | 4TH LINE - BHILAI-BHILAI NAGAR [8.8 KM] [PB-72/NR/2022-23] | SECR | 709816 | Chhattisgarh | 09/2022 | 05/2024 | 02/2027 | 02/2027 | 177.34 | 177.34 | 1.64 | 5
October 2025 | 544 | Ministry of Railways | Railways | 4TH LINE - DADHAPARA-BELHA [9.2 KM] [PB-72/NR/2022-23] | SECR | 709817 | Chhattisgarh | 09/2022 | 05/2024 | 11/2026 | 11/2026 | 169.06 | 169.06 | 17.84 | 60
October 2025 | 545 | Ministry of Railways | Railways | 4TH LINE RAJNANDGAON-DONGARHGARH [31.2 KM] [PB-72/NR/2022-23] | SECR | 709818 | Chhattisgarh | 09/2022 | 05/2024 | 01/2027 | 01/2027 | 328.34 | 328.34 | 56.1 | 26
October 2025 | 546 | Ministry of Railways | Railways | 3RD AND 4TH LINE - SARAGBUNDIA AND MADWARANI | SECR | 709819 | Chhattisgarh | 09/2022 | 05/2025 | 12/2026 | 12/2026 | 167.64 | 167.64 | 0.09 | 4
October 2025 | 547 | Ministry of Railways | Railways | Redevelopment of New Delhi Railway Station and construction of associated infrastructure | Rail Land Development Authority | 613785 | Delhi | 01/2023 | 06/2024 | 12/2028 | - | 4744 | 4744 | 119.95 | 1
October 2025 | 548 | Ministry of Railways | Railways | Development of New Bijwasan Railway Terminal | Northern Railways | 617379 | Delhi | 02/2008 | 03/2013 | 03/2020 | - | 446.21 | 446.21 | 511.94 | 80
October 2025 | 549 | Ministry of Railways | Railways | North Region Video Surveillance Project | RCIL | 705298 | Delhi | 06/2020 | 04/2023 | 03/2024 | - | 274.39 | 274.39 | 0 | 0
October 2025 | 550 | Ministry of Railways | Railways | Anand Vihar-Tilak Bridge 3rd & 4th line | CAO/C/NR | 705583 | Delhi | 03/2013 | 03/2013 | 03/2023 | 12/2027 | 667 | 667 | 287.26 | 62
October 2025 | 551 | Ministry of Railways | Railways | Provision of Work-site Tampers [WST] Railway Project | EDTK[MC]/RB | 705694 | Delhi | 01/2016 | 01/2016 | 12/2023 | 01/2026 | 187.72 | 187.72 | 141.91 | 100
October 2025 | 552 | Ministry of Railways | Railways | WST Machine Procurement Project | EDTK[MC]/RB | 705708 | Delhi | 06/2018 | 06/2018 | 03/2024 | 12/2027 | 176 | 176 | 0 | 0
October 2025 | 553 | Ministry of Railways | Railways | PCT Machine Procurement Project | EDTK[MC]/RB | 705710 | Delhi | 04/2019 | 04/2019 | 04/2024 | 06/2027 | 336 | 336 | 74.32 | 85
October 2025 | 554 | Ministry of Railways | Railways | RBMV Machine Procurement Project | EDTK[MC]/RB | 705712 | Delhi | 10/2019 | 10/2019 | 06/2024 | 12/2027 | 480 | 480 | 0.33 | 7
October 2025 | 555 | Ministry of Railways | Railways | SRGM Machine Procurement Project | EDTK[MC]/RB | 705717 | Delhi | 10/2019 | 10/2019 | 12/2023 | 03/2026 | 440 | 440 | 390.03 | 90
October 2025 | 556 | Ministry of Railways | Railways | WST Machine Procurement Project | EDTK[MC]/RB | 705720 | Delhi | 12/2019 | 12/2019 | 04/2024 | 12/2026 | 384 | 384 | 0 | 0
October 2025 | 557 | Ministry of Railways | Railways | DTS Machine Procurement Project | EDTK[MC]/RB | 705721 | Delhi | 12/2019 | 12/2019 | 12/2024 | 12/2026 | 447.6 | 447.6 | 0 | 0
October 2025 | 558 | Ministry of Railways | Railways | BRM Machine Procurement Project | EDTK[MC]/RB | 705722 | Delhi | 09/2019 | 09/2019 | 06/2024 | 12/2027 | 210 | 210 | 0.02 | 0
October 2025 | 559 | Ministry of Railways | Railways | Track Machine Procurement Project | EDTK[MC]/RB | 705726 | Delhi | 04/2020 | 04/2020 | 03/2025 | 01/2028 | 6339 | 6339 | 4166.47 | 41
October 2025 | 560 | Ministry of Railways | Railways | Kosamba Umarpada 70 Km | PCE/WR | 611918 | Gujarat | 07/2023 | 07/2022 | 03/2027 | - | 468 | 468 | 20.28 | 8
October 2025 | 561 | Ministry of Railways | Railways | Adraj Moti Vijapur 40 Kms | Western Railway (WR) - II | 611937 | Gujarat | 05/2022 | 05/2022 | 05/2026 | 12/2025 | 417.53 | 417.53 | 494.13 | 90
October 2025 | 562 | Ministry of Railways | Railways | New Broad Gauge line between Naliya to Jakhau Port | Western Railway (WR) - II | 611943 | Gujarat | 02/2023 | 02/2023 | 01/2028 | 01/2028 | 410.26 | 410.26 | 6.6 | 4
October 2025 | 563 | Ministry of Railways | Railways | Quadrupling between Gandhidham Adipur with Y connection at Adipur for providing direct entry towards Mundra Port and Bhuj and high level platform at Gopalpur 11Kms | Western Railway (WR) - II | 611944 | Gujarat | 02/2023 | 02/2023 | 03/2026 | 03/2026 | 152.44 | 152.44 | 101.74 | 75
October 2025 | 564 | Ministry of Railways | Railways | Petlad Bhadran 23 Kms | Western Railway | 611945 | Gujarat | 05/2022 | 05/2022 | 05/2030 | 05/2030 | 307.11 | 307.11 | 13.58 | 17
October 2025 | 565 | Ministry of Railways | Railways | Samlaya Timba Road 54 km | PCE/WR | 611970 | Gujarat | 02/2023 | 02/2023 | 03/2030 | 03/2030 | 670.17 | 670.17 | 44.8 | 12
October 2025 | 566 | Ministry of Railways | Railways | Samni Jambusar 24 km | PCE/WR | 611971 | Gujarat | 05/2022 | 05/2022 | 03/2030 | 03/2030 | 350 | 349.93 | 67.73 | 31
October 2025 | 567 | Ministry of Railways | Railways | Western Railway Samakhiali Gandhidham Quadrupiling 53 Kms | Western Railway (WR) - II | 611974 | Gujarat | 08/2023 | 08/2023 | 12/2026 | 06/2027 | 1430 | 1430 | 220.11 | 20
October 2025 | 568 | Ministry of Railways | Railways | Dahod Creation of Infrastructure facilities for 9000 HP Electric locomotives Manufacturing at | PCE/WR | 611977 | Gujarat | 05/2022 | 02/2023 | 02/2025 | - | 487 | 487 | 108.69 | 0
October 2025 | 569 | Ministry of Railways | Railways | Dahod Rolling Stock Workshop Provision of Infrastructure for CBS at | PCE/WR | 611978 | Gujarat | 11/2022 | 03/2023 | 03/2025 | - | 158 | 158 | 47.31 | 0
October 2025 | 570 | Ministry of Railways | Railways | Sabarmati Setting up of Maintenance Facilities for Train Sets Phase ii | PCE/WR | 611979 | Gujarat | 01/2023 | 04/2023 | 06/2025 | - | 250 | 250 | 0 | 0
October 2025 | 571 | Ministry of Railways | Railways | 4th LINE BETWEEN BAREJADI NANDEJ-SANAND-AHMEDABAD BYPASS | Western Railway (WR) - II | 612072 | Gujarat | 02/2023 | 02/2023 | 03/2027 | 07/2028 | 961.67 | 961.67 | 335.93 | 17
October 2025 | 572 | Ministry of Railways | Railways | Redevelopment of Ahmedabad railway station and associated infrastructure on engineering, procurement and construction mode | Rail Land Development Authority | 613786 | Gujarat | 01/2023 | 11/2023 | 03/2028 | - | 2379 | 2379 | 726.91 | 19
October 2025 | 573 | Ministry of Railways | Railways | Miyagam-Karjan-Dabhoi-Samlaya [GC] | Western Railway [WR] - II | 705458 | Gujarat | 01/2017 | 01/2017 | 03/2021 | 12/2026 | 483.88 | 1039.13 | 621.53 | 41
October 2025 | 574 | Ministry of Railways | Railways | Modasa-Shamlaji Road Railway Line Project | Western Railway (WR) - II | 706757 | Gujarat | 09/2012 | 04/2008 | 03/2025 | 03/2027 | 262 | 262 | 337.45 | 62
October 2025 | 575 | Ministry of Railways | Railways | Rajkot - Kanalus Doubling Project [111.2 Kms] | Western Railway (WR) - II | 706763 | Gujarat | 10/2021 | 12/2021 | 10/2026 | 10/2026 | 1080.58 | 1080.58 | 822.77 | 77
October 2025 | 576 | Ministry of Railways | Railways | NADIAD-PETLAD [37.26 KM] | Railway | 709812 | Gujarat | 05/2022 | 10/2023 | 06/2030 | 06/2030 | 461.91 | 461.91 | 92.88 | 7
October 2025 | 577 | Ministry of Railways | Railways | NEW BG LINE INTERSECTION [5 NOS] BETWEEN GERATPUR-SANAND & BOTAD-AHMEDABAD [16.51 KM] | Western Railway (WR) - II | 709813 | Gujarat | 10/2022 | 07/2025 | 06/2028 | 10/2027 | 437.21 | 437.21 | 19.06 | 17
October 2025 | 578 | Ministry of Railways | Railways | Bhiwani - Dobh Bahali Doubling Project [42.30 Km] | North Western Railway [NWR] | 611884 | Haryana | 02/2023 | 02/2023 | 02/2028 | 02/2028 | 471 | 471 | 215.11 | 65
October 2025 | 579 | Ministry of Railways | Railways | Doubling between Pradhankunta-Patherih-Bhojudih of East Central Railway | East Central Railway [ECR] - I | 617372 | Jharkhand | 11/2022 | 11/2022 | 12/2025 | - | 349.22 | 349.22 | 106.11 | 70
October 2025 | 580 | Ministry of Railways | Railways | Gomoh - Flyover for DN trains | East Central Railway [ECR] - I | 705765 | Jharkhand | 01/2018 | 01/2018 | 03/2026 | 03/2026 | 686 | 686 | 574.14 | 59
October 2025 | 581 | Ministry of Railways | Railways | Lodhma - Piska - Link Line bypassing Hatia/Ranchi with Y connection | South Eastern Railway [SER] - I | 705785 | Jharkhand | 08/2021 | 03/2019 | 06/2026 | 05/2027 | 473 | 473 | 288.59 | 5
October 2025 | 582 | Ministry of Railways | Railways | Pradhan Kuntha Jn Line Doubling Project | East Central Railway [ECR] - I | 706837 | Jharkhand | 11/2022 | 11/2022 | 11/2027 | 11/2027 | 349.22 | 349.22 | 106.11 | 62
October 2025 | 583 | Ministry of Railways | Railways | Construction of New BG line between Hassan to Belur [27 Km] | South Western Railway [SWR] - II | 400023 | Karnataka | 03/2019 | 12/2025 | 04/2028 | 04/2027 | 749 | 749 | 0 | 0
October 2025 | 584 | Ministry of Railways | Railways | Yeshvanthpur - Channasandra Doubling Project [21.70 Km] | Karnataka Rail Infrastructure Development Company Limited [K-RIDE] | 703585 | Karnataka | 04/2019 | 10/2019 | 03/2024 | 03/2026 | 314.1 | 683.57 | 152.31 | 53
October 2025 | 585 | Ministry of Railways | Railways | New Railway Line between Ginigera and Raichur [165.57 km] | South Western Railway [SWR] - II | 705434 | Karnataka | 03/2008 | 05/2009 | 03/2019 | 03/2027 | 2565 | 3034.98 | 2105.62 | 66
October 2025 | 586 | Ministry of Railways | Railways | Gadag-Wadi New Railway Line [257 km] | South Western Railway [SWR] - II | 705490 | Karnataka | 04/2013 | 08/2017 | 03/2027 | 12/2027 | 2842 | 6700 | 1400.27 | 30
October 2025 | 587 | Ministry of Railways | Railways | Kadur - Chickamagalur - Sakleshpur [93km] | South Western Railway [SWR] - II | 705492 | Karnataka | 01/2014 | 11/2016 | 06/2025 | 12/2025 | 825 | 825 | 699.12 | 83
October 2025 | 588 | Ministry of Railways | Railways | Bagalkot-Kudachi New Railway Line [142 km] | South Western Railway [SWR] - II | 705495 | Karnataka | 10/2013 | 11/2012 | 03/2027 | 01/2027 | 1378 | 1649 | 716.65 | 35
October 2025 | 589 | Ministry of Railways | Railways | Tumkur-Chitradurga-Davangere New Rail Line Project [191 km] | South Western Railway [SWR] - II | 705496 | Karnataka | 10/2013 | 01/2017 | 03/2019 | 12/2027 | 1876 | 1876 | 436.37 | 13
October 2025 | 590 | Ministry of Railways | Railways | Bangalore-Whitefield-Bangalore City-Krishnarajapuram [23.08 km] - Quadrupling | South Western Railway [SWR] - II | 705663 | Karnataka | 02/2018 | 06/2022 | 02/2026 | 02/2026 | 493 | 493 | 252.45 | 82
October 2025 | 591 | Ministry of Railways | Railways | SHIMOGA - SHIKARIPURA - RANEBENNUR [96 Km] | South Western Railway [SWR] - II | 705761 | Karnataka | 09/2019 | 02/2023 | 12/2027 | 06/2028 | 1454 | 1454 | 71.89 | 11
October 2025 | 592 | Ministry of Railways | Railways | Belgaum-Dharwad via Kittur [73.10Km] | South Western Railway [SWR] - II | 706835 | Karnataka | 09/2020 | 03/2025 | 12/2027 | 03/2029 | 1591 | 1591 | 0.38 | 0
October 2025 | 593 | Ministry of Railways | Railways | Kumbalam-Turavur doubling project [15.59 Km] | Southern Railway [SR] - II | 705638 | Kerala | 04/2023 | 04/2023 | 03/2027 | 03/2027 | 813 | 802.8 | 66.7 | 18
October 2025 | 594 | Ministry of Railways | Railways | Ernakulam-Kumbalam doubling project [7.71 Km] | SR-ERS | 705639 | Kerala | 04/2023 | 04/2023 | 03/2028 | 02/2027 | 601 | 595.39 | 289.52 | 19
October 2025 | 595 | Ministry of Railways | Railways | Lalitpur-Satna, Rewa-Singrauli & Mahoba-Khajuraho | North Central Railway | 705480 | Madhya Pradesh | 01/2007 | 03/1998 | 03/2027 | 12/2027 | 8914 | 8914 | 5013.49 | 72
October 2025 | 596 | Ministry of Railways | Railways | Katni - Bina Third Railway Line [279 km] | West Central Railway WCR I | 705651 | Madhya Pradesh | 06/2016 | 01/2017 | 03/2022 | 12/2025 | 2478.23 | 4127.23 | 3330.66 | 92
October 2025 | 597 | Ministry of Railways | Railways | Satna-Rewa Railway Line Doubling Project | West Central Railway [WCR] - II | 705659 | Madhya Pradesh | 11/2015 | 08/2017 | 03/2026 | 03/2026 | 500 | 584 | 565.61 | 80
October 2025 | 598 | Ministry of Railways | Railways | Doubling of Katni - Singrauli Railway Line [261 km] | Indian Railway Construction International Limited [IRCON] | 705660 | Madhya Pradesh | 03/2016 | 03/2017 | 12/2025 | 12/2025 | 2445 | 4377 | 3234.88 | 100
October 2025 | 599 | Ministry of Railways | Railways | Katni Grade Separator/Bye Pass | Indian Railway Construction International Limited [IRCON] | 705661 | Madhya Pradesh | 03/2016 | 09/2017 | 09/2024 | 03/2026 | 1248 | 1248 | 1651.34 | 95
October 2025 | 600 | Ministry of Railways | Railways | Indore - Budni New Railway Line [198 kms] | RVNL - II | 705763 | Madhya Pradesh | 08/2019 | 10/2020 | 09/2030 | 09/2030 | 7474 | 7474 | 1780.6 | 25
October 2025 | 601 | Ministry of Railways | Railways | Nimach-Ratlam Doubling [133 Km] | Western Railway [WR] - II | 705933 | Madhya Pradesh | 10/2021 | 10/2021 | 10/2027 | 10/2027 | 1095.88 | 1095.88 | 1067.49 | 89
October 2025 | 602 | Ministry of Railways | Railways | DHULE [BORVIHIR] - NARDANA NEW LINE [50.60 KMS] | Central Railway | 400019 | Maharashtra | 01/2019 | 04/2023 | 12/2026 | 09/2027 | 492.76 | 1170.83 | 276.86 | 16
October 2025 | 603 | Ministry of Railways | Railways | Wardha-Nanded Via Yavatmal New BG Line | Central Railway [CR] - II | 400271 | Maharashtra | 12/2017 | 04/2008 | 03/2028 | 03/2028 | 3445 | 3445 | 3002.93 | 50
October 2025 | 604 | Ministry of Railways | Railways | AURANGABAD-ANKAI - DOUBLING PROJECT 98.25 Km | South Central Railway [SCR] - II | 611751 | Maharashtra | 05/2023 | 05/2023 | 03/2027 | - | 960.64 | 960.64 | 511.61 | 1
October 2025 | 605 | Ministry of Railways | Railways | Redevelopment of Chhatrapati Shivaji Maharaj Terminus [CSMT] and construction of associated infrastructure | Rail Land Development Authority | 613015 | Maharashtra | 04/2023 | 07/2023 | 03/2027 | - | 1813 | 1813 | 600.75 | 16
October 2025 | 606 | Ministry of Railways | Railways | Gondia-Balharshah [Chanda Fort] Doubling [240 Km] | South East Central Railway | 617201 | Maharashtra | 04/2025 | 04/2025 | 03/2031 | - | 4373.04 | 4373.04 | 0 | 0
October 2025 | 607 | Ministry of Railways | Railways | Doubling between Parbhani Parli Vaijanath stations 64.71 Km | South Central Railway [SCR] - II | 617215 | Maharashtra | 12/2023 | 12/2023 | 03/2028 | - | 769.93 | 769.93 | 20.91 | 0
October 2025 | 608 | Ministry of Railways | Railways | Babupeth - Sasti New Rail Line [13.114 KMs] | Central Railway (CR) - II | 617361 | Maharashtra | 10/2024 | 10/2024 | 03/2028 | - | 362.81 | 362.81 | 0 | 0
October 2025 | 609 | Ministry of Railways | Railways | Double Chord line Between Nilaje-Kopar | Central Railway (CR) - II | 617364 | Maharashtra | 01/2025 | 01/2025 | 07/2028 | - | 338.33 | 205 | 3.42 | 0
October 2025 | 610 | Ministry of Railways | Railways | Western Region Video Surveillance Project | RCIL | 705300 | Maharashtra | 06/2020 | 04/2023 | 12/2023 | - | 227.59 | 227.59 | 0 | 0
October 2025 | 611 | Ministry of Railways | Railways | Ahmednagar - Beed - Parli - Vaijnath New Broad Gauge Line Railway Project [261.3 km] | Central Railway [CR] - II | 705356 | Maharashtra | 01/1999 | 10/2002 | 03/2026 | 03/2026 | 2538.67 | 4957.27 | 5091.94 | 98
October 2025 | 612 | Ministry of Railways | Railways | Baramati Lonand New Line Project | Central Railway | 705357 | Maharashtra | 03/2016 | 03/1999 | 03/2027 | 03/2027 | 138.48 | 1843.9 | 845.56 | 51
October 2025 | 613 | Ministry of Railways | Railways | Wadsa-Gadchiroli | South East Central Railway | 705479 | Maharashtra | 05/2017 | 03/2012 | 03/2027 | 03/2027 | 1886 | 1886 | 727.89 | 53
October 2025 | 614 | Ministry of Railways | Railways | 3rd Line Kalyan - Kasara [67.35 Kilometres] | Central Railway | 705498 | Maharashtra | 09/2015 | 09/2015 | 12/2026 | 12/2026 | 792.89 | 1395.79 | 931.97 | 51
October 2025 | 615 | Ministry of Railways | Railways | 3rd Line Wardha - Sewagram - Nagpur | Central Railway [CR] - II | 705500 | Maharashtra | 09/2015 | 05/2016 | 12/2025 | 12/2025 | 540.02 | 944.24 | 779.07 | 83
October 2025 | 616 | Ministry of Railways | Railways | 3rd Line Wardha - Ballarshah [132 Kilometres] | Central Railway [CR] - II | 705502 | Maharashtra | 03/2016 | 12/2016 | 12/2025 | 02/2026 | 1384.72 | 2033.59 | 1705.4 | 80
October 2025 | 617 | Ministry of Railways | Railways | Pune - Miraj-Londa [467 Kilometres] | Central Railway | 705503 | Maharashtra | 06/2016 | 06/2016 | 02/2025 | 08/2025 | 4027.53 | 4872.52 | 4924.05 | 85
October 2025 | 618 | Ministry of Railways | Railways | Doubling of Daund Manmad Line [247.6 km] | Central Railway | 705504 | Maharashtra | 10/2017 | 03/2017 | 12/2025 | 03/2026 | 2081.27 | 3267.06 | 2861.77 | 92
October 2025 | 619 | Ministry of Railways | Railways | 4th Line Wardha - Nagpur [78.7 Kilometres] | Central Railway [CR] - II | 705505 | Maharashtra | 04/2017 | 05/2018 | 12/2025 | 02/2026 | 637.95 | 1341.28 | 1010.3 | 83
October 2025 | 620 | Ministry of Railways | Railways | 3rd Line Manmad - Jalgaon [160 Kilometres] | Central Railway [CR] - II | 705506 | Maharashtra | 05/2017 | 04/2018 | 12/2024 | 08/2025 | 1035.16 | 1558.75 | 1726.94 | 95
October 2025 | 621 | Ministry of Railways | Railways | Solapur-tuljapur-Osmanabad | Central Railway | 705735 | Maharashtra | 08/2018 | 12/2023 | 03/2027 | 03/2028 | 904.92 | 3295.74 | 1153.7 | 12
October 2025 | 622 | Ministry of Railways | Railways | Nagpur- Nagbhir Railway Line Gauge Conversion Project | MRIDC | 705799 | Maharashtra | 10/2019 | 04/2020 | 12/2025 | 12/2025 | 1400 | 1400 | 1472 | 80
October 2025 | 623 | Ministry of Railways | Railways | Mumbai Urban Transport Project [MUTP] - PHASE II | Mumbai Rail Vikas Corporation Ltd.[MRVC] | 706779 | Maharashtra | 05/2008 | 04/2008 | 03/2014 | 12/2027 | 8087 | 8087 | 7364 | 87
October 2025 | 624 | Ministry of Railways | Railways | Mumbai Urban Transport Project [MUTP] Phase-IIIA | Mumbai Rail Vikas Corporation Ltd.[MRVC] | 706780 | Maharashtra | 04/2019 | 04/2019 | 12/2027 | 12/2027 | 33690 | 33690 | 2436.22 | 16
October 2025 | 625 | Ministry of Railways | Railways | Mumbai Urban Transport Project Phase-III | Mumbai Rail Vikas Corporation Ltd.[MRVC] | 706781 | Maharashtra | 11/2016 | 12/2016 | 03/2022 | 12/2026 | 10947 | 10947 | 5460.49 | 65
October 2025 | 626 | Ministry of Railways | Railways | PACHORA-JAMNER WITH EXTENSION UPTO MALKAPUR NG TO BG | CR | 709808 | Maharashtra | 08/2022 | 01/2022 | 08/2027 | 03/2028 | 955.39 | 2093.82 | 130.42 | 11
October 2025 | 627 | Ministry of Railways | Railways | Jiribam-Imphal new line project | Northeast Frontier Railway [NFR] | 705391 | Manipur | 03/2013 | 12/2007 | 12/2026 | 06/2029 | 14323 | 21885.9 | 15598.11 | 69
October 2025 | 628 | Ministry of Railways | Railways | Marikuppam - Kuppam New Line Project [23.70 Km] | South Western Railway [SWR] - II | 705491 | Multi-States (Andhra Pradesh, Karnataka) | 04/2012 | 10/2018 | 06/2026 | 06/2026 | 297 | 297 | 134.31 | 15
October 2025 | 629 | Ministry of Railways | Railways | Rayadurg-Tumkur via Kalyandurg New Line [207 km] | South Western Railway [SWR] - II | 705494 | Multi-States (Andhra Pradesh, Karnataka) | 03/2008 | 07/2010 | 09/2015 | 02/2028 | 2496 | 2496 | 1739.53 | 69
October 2025 | 630 | Ministry of Railways | Railways | Renigunta, Wadi & Gooty Bypass Railway Project | South Central Railway [SCR] - I | 705610 | Multi-States (Andhra Pradesh, Karnataka) | 04/2016 | 04/2016 | 12/2025 | 12/2025 | 302 | 543 | 381 | 50
October 2025 | 631 | Ministry of Railways | Railways | Doubling between Mudkhed Medchal & Mahbubnagar Dhone section 417.88 Km | South Central Railway [SCR] - II | 617212 | Multi-States (Andhra Pradesh, Maharashtra, Telangana) | 08/2023 | 08/2023 | 03/2029 | - | 4686.09 | 4686.09 | 668.81 | 1
October 2025 | 632 | Ministry of Railways | Railways | Vizianagaram - Titlagarh 3rd line [272 Km including By - pass line of 7.68 KM] | RVNL - II | 400253 | Multi-States (Andhra Pradesh, Odisha) | 06/2016 | 11/2016 | 12/2026 | 12/2026 | 4803 | 6670 | 5722.01 | 89
October 2025 | 633 | Ministry of Railways | Railways | Doubling of Kottavalasa-Koraput Rail Line [189 KM] | East Coast Railway [ECoR] - II | 705512 | Multi-States (Andhra Pradesh, Odisha) | 12/2015 | 01/2016 | 03/2022 | 03/2028 | 2500 | 2500 | 2023.97 | 71
October 2025 | 634 | Ministry of Railways | Railways | Vizianagaram-Sambhalpur 3rd Line Project | RVNL | 705520 | Multi-States (Andhra Pradesh, Odisha) | 06/2016 | 12/2016 | 03/2025 | - | 4803.16 | 4803.16 | 2979.23 | 0
October 2025 | 635 | Ministry of Railways | Railways | Tindivanam-Nagari New Line Project [184.5 km] | Southern Railway [SR] - II | 400275 | Multi-States (Andhra Pradesh, Tamil Nadu) | 07/2008 | 10/2008 | 09/2016 | 03/2028 | 3631 | 3631 | 1113.53 | 18
October 2025 | 636 | Ministry of Railways | Railways | Doubling between Motumari Vishnupuram - 88.81 Km and Rail over Rail - RoR at Motumari - 10.877 Km | South Central Railway [SCR] - II | 616857 | Multi-States (Andhra Pradesh, Telangana) | 02/2024 | 03/2025 | 03/2029 | - | 1595.55 | 1595.55 | 14.27 | 1
October 2025 | 637 | Ministry of Railways | Railways | Doubling of Guntur Bibinagar 239 Km | South Central Railway [SCR] - II | 617211 | Multi-States (Andhra Pradesh, Telangana) | 08/2023 | 08/2023 | 03/2029 | - | 2853.23 | 2853.23 | 62.29 | 1
October 2025 | 638 | Ministry of Railways | Railways | Rail Connectivity to Errupalem Amravati Namburu 57 Km | South Central Railway [SCR] - II | 617214 | Multi-States (Andhra Pradesh, Telangana) | 11/2024 | 11/2024 | 03/2027 | - | 2047.4 | 2047.4 | 14.49 | 0
October 2025 | 639 | Ministry of Railways | Railways | Kazipet-Vijayawada 3rd line with electrification [220 km] | South Central Railway [SCR] - II | 705612 | Multi-States (Andhra Pradesh, Telangana) | 03/2013 | 08/2014 | 02/2025 | 12/2025 | 1953 | 3363 | 3436.15 | 94
October 2025 | 640 | Ministry of Railways | Railways | Vijayawada - Kazipet Byepass line | South Central Railway [SCR] - II | 705632 | Multi-States (Andhra Pradesh, Telangana) | 04/2016 | 04/2016 | 01/2025 | 12/2025 | 647 | 904 | 945.51 | 92
October 2025 | 641 | Ministry of Railways | Railways | Murkongselek-Pasighat | Northeast Frontier Railway (NFR) - II | 705401 | Multi-States (Arunachal Pradesh, Assam) | 02/2011 | 03/2023 | 03/2025 | 05/2026 | 435 | 1250 | 542.07 | 61
October 2025 | 642 | Ministry of Railways | Railways | Lumding Furkating Doubling Project 140 km | Northeast Frontier Railway [NFR] | 616701 | Multi-States (Assam, Nagaland) | 02/2024 | 01/2025 | 02/2028 | - | 2123.7 | 2123.7 | 13.74 | 0
October 2025 | 643 | Ministry of Railways | Railways | Dimapur [Dhansiri]-Sukhobi Kohima [Zubza] NL [82.5 Km] | Northeast Frontier Railway [NFR] | 705392 | Multi-States (Assam, Nagaland) | 08/2015 | 02/2016 | 03/2025 | 12/2025 | 6663 | 6663 | 5571.82 | 81
October 2025 | 644 | Ministry of Railways | Railways | New Delhi- Howrah Speed Booster[160Kmph] Project | PCE/NCR | 705794 | Multi-States (Bihar, Delhi, Jharkhand, Uttar Pradesh, West Bengal) | 09/2019 | 09/2019 | 03/2024 | - | 6684.81 | 6684.81 | 127.03 | 0
October 2025 | 645 | Ministry of Railways | Railways | Third Railway Line between Patratu-Sonnagar [281 kms] | RVNL - II | 400234 | Multi-States (Bihar, Jharkhand) | 11/2016 | 08/2018 | 03/2026 | 07/2026 | 8975 | 8975 | 4950 | 88
October 2025 | 646 | Ministry of Railways | Railways | Multi tracking of Son Nagar-Andal 374.53 rkm & 814.38 tkm | East Central Railway [ECR] - I | 616699 | Multi-States (Bihar, Jharkhand) | 08/2023 | 08/2023 | 03/2028 | - | 12333.57 | 12333.6 | 520.39 | 13
October 2025 | 647 | Ministry of Railways | Railways | Koderma-Tilaiya New Line | East Central Railway [ECR] - I | 705375 | Multi-States (Bihar, Jharkhand) | 11/2004 | 03/2002 | 02/2025 | 02/2026 | 1626 | 2486.62 | 2113.82 | 93
October 2025 | 648 | Ministry of Railways | Railways | Pirpainti - Jasidih [100.52 Km] New BG line | Eastern Railway [ER] - I | 705385 | Multi-States (Bihar, Jharkhand) | 03/2014 | 03/2022 | 03/2028 | 03/2028 | 2555 | 2555 | 780.18 | 49
October 2025 | 649 | Ministry of Railways | Railways | NER Provision of Automatic Block Signalling on Gorakhpur Cantt[Excl] Chhapra Gramin & Burhwal Jn [Excl] Sitapur Jn section of high density routes | North Eastern Railway [NER] | 611669 | Multi-States (Bihar, Uttar Pradesh) | NA | 06/2023 | 03/2027 | - | 380.47 | 380.47 | 24.53 | 0
October 2025 | 650 | Ministry of Railways | Railways | Gorakhpur-Valmikinagar Doubling project | NER | 617224 | Multi-States (Bihar, Uttar Pradesh) | 08/2023 | 03/2024 | 12/2027 | - | 1120 | 1120 | 247.46 | 26
October 2025 | 651 | Ministry of Railways | Railways | Chhapra-Ballia Patch Doubling | North Eastern Railway [NER] | 705562 | Multi-States (Bihar, Uttar Pradesh) | 03/2013 | 12/2015 | 02/2025 | 03/2026 | 963 | 1046 | 911.66 | 95
October 2025 | 652 | Ministry of Railways | Railways | Katihar - Kumedpur Doubling Line Project | GM/C/ NFR | 706844 | Multi-States (Bihar, West Bengal) | 08/2022 |  | 08/2027 | 08/2027 | 942 | 942 | 356 | 45
October 2025 | 653 | Ministry of Railways | Railways | Rajnandgaon - Nagpur [Kalumna] Third Railway Line [228.30 km] | South East Central Railway [SECR] - II | 705617 | Multi-States (Chhattisgarh, Maharashtra) | 09/2016 | 12/2016 | 12/2024 | 06/2026 | 3545 | 3545 | 3507.04 | 96
October 2025 | 654 | Ministry of Railways | Railways | Sardega -Bhalumuda New Double line [37.24 Km] | SECR | 617390 | Multi-States (Chhattisgarh, Odisha) | 09/2024 | 09/2024 | 03/2028 | - | 1281.81 | 1281.81 | 128 | 1
October 2025 | 655 | Ministry of Railways | Railways | Jagdalpur-Koraput | East Coast Railway [ECoR] - II | 705511 | Multi-States (Chhattisgarh, Odisha) | 12/2015 | 03/2016 | 03/2024 | 12/2026 | 1547 | 1547 | 1329.73 | 90
October 2025 | 656 | Ministry of Railways | Railways | Jharsuguda-Bilaspur Fourth Railway Line [206 km] | SECR | 705616 | Multi-States (Chhattisgarh, Odisha) | 09/2016 | 09/2016 | 10/2024 | 12/2025 | 2140 | 2979 | 2196.74 | 93
October 2025 | 657 | Ministry of Railways | Railways | Mumbai-Ahmedabad High Speed Rail Project- 508 km | National High Speed Rail Corporation [NHSRC] | 705728 | Multi-States (Dadra & Nagar Haveli and Daman & Diu, Gujarat, Maharashtra) | 03/2015 | 09/2017 | 08/2027 | 12/2029 | 108000 | 108000 | 82967.89 | 55
October 2025 | 658 | Ministry of Railways | Railways | New Delhi- Mumbai Speed Booster[160Kmph] Project | PCE/WR | 705793 | Multi-States (Delhi, Gujarat, Madhya Pradesh, Maharashtra, Rajasthan) | 09/2019 | 09/2019 | 03/2024 | - | 6806.44 | 6806.44 | 135.65 | 0
October 2025 | 659 | Ministry of Railways | Railways | Hospet - Tinaighat - Vasco Rail Doubling Project | RVNL - II | 705650 | Multi-States (Goa, Karnataka) | 03/2010 | 07/2012 | 03/2027 | 12/2027 | 5060 | 5060 | 5246.91 | 86
October 2025 | 660 | Ministry of Railways | Railways | Hospet-Hubli-Vasco da Gama Line Electrification Project | RVNL | 706950 | Multi-States (Goa, Karnataka) | 07/2015 | 05/2018 | 03/2023 | 03/2024 | 744.49 | 1122.62 | 969.05 | 95
October 2025 | 661 | Ministry of Railways | Railways | Western Dedicated Freight Corridor | DFCCIL | 705237 | Multi-States (Gujarat, Haryana, Maharashtra, Rajasthan, Uttar Pradesh) | 02/2008 | 01/2012 | 03/2022 | 12/2025 | 51101 | 124005 | 124623 | 96
October 2025 | 662 | Ministry of Railways | Railways | New line Dahod-Indore via Sardarpur, Jabuwa and Dhar | Western Railway [WR] - II | 705453 | Multi-States (Gujarat, Madhya Pradesh) | 06/2012 | 06/2012 | 02/2027 | 02/2027 | 456.07 | 3516.77 | 3633.27 | 49
October 2025 | 663 | Ministry of Railways | Railways | Chhota Udaipur - Dhar New Line Project [157 km] | Western Railway [WR] - II | 705454 | Multi-States (Gujarat, Madhya Pradesh) | 11/2008 | 01/2014 | 12/2025 | 12/2025 | 1794 | 1794 | 1815.94 | 80
October 2025 | 664 | Ministry of Railways | Railways | MUMBAI CENTRAL VIRAR VADODARA AHMEDABAAD TRAIN PROTECTION SYSTEM 500 RKM | Western Railway | 611452 | Multi-States (Gujarat, Maharashtra) | 09/2019 | 03/2023 | 12/2025 | 06/2025 | 311 | 311 | 208 | 92
October 2025 | 665 | Ministry of Railways | Railways | Taranga Hill-Abu Road via Ambaji | North Western Railway [NWR] | 400022 | Multi-States (Gujarat, Rajasthan) | 07/2022 | 07/2022 | 07/2030 | 07/2030 | 2798 | 2798 | 2014.6 | 17
October 2025 | 666 | Ministry of Railways | Railways | LUNI- SAMDARI- BHILDI DOUBLING | North Western Railway [NWR] | 616842 | Multi-States (Gujarat, Rajasthan) | 02/2024 | 02/2024 | 07/2027 | - | 3085.59 | 3085.59 | 329.31 | 13
October 2025 | 667 | Ministry of Railways | Railways | Chandigarh-Baddi New Rail Line- 36 km | Northen Railway [NR] | 705424 | Multi-States (Haryana, Himachal Pradesh) | 02/2018 | 02/2018 | 12/2026 | 12/2026 | 1540 | 1540.13 | 527.66 | 34
October 2025 | 668 | Ministry of Railways | Railways | Rewari - Kathuwas Doubling Project [27.72 Km] | North Western Railway [NWR] | 611861 | Multi-States (Haryana, Rajasthan) | 02/2023 | 12/2022 | 06/2027 | 06/2027 | 352 | 352 | 271.93 | 65
October 2025 | 669 | Ministry of Railways | Railways | Nangal Dam-Talwara New Broad Gauge Line [84 KM] and Taking Over Siding Mukerian-Talwara [29 KM] | Northen Railway [NR] | 705410 | Multi-States (Himachal Pradesh, Punjab) | 03/1983 | 05/1985 | 12/2025 | 01/2027 | 2018 | 2018 | 2053.9 | 45
October 2025 | 670 | Ministry of Railways | Railways | Bhanupalli-Bilaspur-Beri New Railway Line Project | RVNL - II | 705428 | Multi-States (Himachal Pradesh, Punjab) | 03/2009 | 04/2015 | 12/2026 | 12/2027 | 13447 | 13447 | 6928.81 | 61
October 2025 | 671 | Ministry of Railways | Railways | Doubling of Hatia [Ranchi]-Bondamunda Rail Line - 159 km | South Eastern Railway - JH | 705628 | Multi-States (Jharkhand, Odisha) | 03/2016 | 02/2017 | 06/2025 | 06/2026 | 3029 | 3029.04 | 2501.09 | 86
October 2025 | 672 | Ministry of Railways | Railways | Buramara-Chakulia new line [59.96 km] | South Eastern Railway [SER] - I | 616588 | Multi-States (Jharkhand, Odisha, West Bengal) | 08/2024 | 12/2024 | 12/2029 | - | 1459.13 | 1459.13 | 3.32 | 0
October 2025 | 673 | Ministry of Railways | Railways | KHARAGPUR-ADITYAPUR THIRD RAIL LINE- 132 KM | RVNL - I | 705668 | Multi-States (Jharkhand, West Bengal) | 09/2016 | 01/2018 | 03/2025 | 12/2025 | 3250 | 3250 | 3176.46 | 97
October 2025 | 674 | Ministry of Railways | Railways | Hotgi-Kudgi-Gadag Doubling Project | South Western Railway [SWR] - II | 705662 | Multi-States (Karnataka, Maharashtra) | 04/2014 | 01/2016 | 12/2024 | 03/2026 | 1878 | 2459 | 2684.66 | 92
October 2025 | 675 | Ministry of Railways | Railways | Baiyyappanahalli - Hosur Doubling Project [48 km] | Karnataka Rail Infrastructure Development Company Limited [K-RIDE] | 703586 | Multi-States (Karnataka, Tamil Nadu) | 04/2019 | 02/2019 | 03/2024 | 01/2026 | 498.7 | 748.7 | 630.41 | 86
October 2025 | 676 | Ministry of Railways | Railways | Trivandrum- Kanyakumari | Southern Railway (SR) - I | 705635 | Multi-States (Kerala, Tamil Nadu) | 08/2017 | 03/2016 | 03/2025 | 12/2026 | 1432 | 3785.45 | 2505.8 | 50
October 2025 | 677 | Ministry of Railways | Railways | Ratlam-Mhow-Khandwa-Akola Gauge Conversion | Western Railway [WR] - II | 705457 | Multi-States (Madhya Pradesh, Maharashtra) | 04/2008 | 03/2010 | 03/2027 | 09/2028 | 1656.25 | 6499.86 | 4445.82 | 81
October 2025 | 678 | Ministry of Railways | Railways | Itarsi - Nagpur Third Railway Line [280 km] | Central Railway (CR) - II | 705507 | Multi-States (Madhya Pradesh, Maharashtra) | 09/2016 | 09/2016 | 03/2027 | 03/2027 | 2449.91 | 2506.68 | 1850.73 | 51
October 2025 | 679 | Ministry of Railways | Railways | RATLAM- DUNGARPUR VIA BANSWARA NEW LINE PROJECT | North Western Railway [NWR] | 617406 | Multi-States (Madhya Pradesh, Rajasthan) | 10/2015 | 05/2023 | 03/2028 | - | 2417.24 | 2417.24 | 5.66 | 7
October 2025 | 680 | Ministry of Railways | Railways | Gwalior - Seopurkala with extension to Kota [Gauge Conversion] | North Central Railway | 705419 | Multi-States (Madhya Pradesh, Rajasthan) | 03/2011 | 07/2018 | 03/2025 | 02/2026 | 2913 | 2913 | 2109.86 | 84
October 2025 | 681 | Ministry of Railways | Railways | Ramganjmandi-Bhopal New Line Project [262 km] | West Central Railway [WCR] - II | 705481 | Multi-States (Madhya Pradesh, Rajasthan) | 03/2001 | 10/2004 | 12/2025 | 12/2027 | 3032 | 5073 | 3723.61 | 70
October 2025 | 682 | Ministry of Railways | Railways | Nimach-Badi Sadri New Rail Line Project | Western Railway [WR] - II | 705764 | Multi-States (Madhya Pradesh, Rajasthan) | 04/2017 | 09/2021 | 03/2026 | 06/2026 | 495 | 825 | 123.77 | 57
October 2025 | 683 | Ministry of Railways | Railways | Mathura-Jhansi Third Railway Line [274 Km] | RVNL - II | 705667 | Multi-States (Madhya Pradesh, Rajasthan, Uttar Pradesh) | 12/2015 | 03/2018 | 12/2024 | 12/2026 | 5961 | 5961 | 4964.19 | 94
October 2025 | 684 | Ministry of Railways | Railways | Jhansi - Bina Third Railway Line [153 Km] | CAO/C/NCR | 705598 | Multi-States (Madhya Pradesh, Uttar Pradesh) | 09/2016 | 03/2018 | 03/2022 | 03/2026 | 2002 | 2002 | 1806.86 | 93
October 2025 | 685 | Ministry of Railways | Railways | Jhansi-Khairar-Manikpur & Khirar-Bhimsen | North Central Railway | 705608 | Multi-States (Madhya Pradesh, Uttar Pradesh) | 03/2018 | 04/2019 | 03/2026 | 03/2026 | 4330 | 4330 | 2417.11 | 60
October 2025 | 686 | Ministry of Railways | Railways | Third Line [new] between Kazipet - Balharshah with electrification [201.04 Km] | South Central Railway [SCR] - II | 705613 | Multi-States (Maharashtra, Telangana) | 09/2016 | 10/2016 | 01/2025 | 11/2025 | 2595 | 3071 | 3396.31 | 94
October 2025 | 687 | Ministry of Railways | Railways | Narayangarh-Bhadrak 3rd line | South Eastern Railway [SER] - I | 705629 | Multi-States (Odisha, West Bengal) | 03/2019 | 03/2017 | 12/2025 | 06/2026 | 2400 | 2400 | 2311.95 | 66
October 2025 | 688 | Ministry of Railways | Railways | Nagapattinam-Tiruturaipundi and Karaikal-Peralam New Line | Southern Railway [SR] - II | 400223 | Multi-States (Puducherry, Tamil Nadu) | 07/2008 | 01/2019 | 03/2026 | 03/2027 | 713 | 981 | 598.38 | 80
October 2025 | 689 | Ministry of Railways | Railways | Sivok-Rangpo New Rail Line | Indian Railway Construction International Limited [IRCON] | 705432 | Multi-States (Sikkim, West Bengal) | 10/2009 | 05/2010 | 05/2015 | 12/2027 | 7877 | 12133 | 9039.91 | 84
October 2025 | 690 | Ministry of Railways | Railways | Sainthia, Sitarampur, Mughalsarai, Allahabad & Etawah - Bypass Line Project | Eastern Railway [ER] - I | 602797 | Multi-States (Uttar Pradesh, West Bengal) | 08/2017 | 12/2017 | 03/2027 | 03/2027 | 461.64 | 461.64 | 192.72 | 8
October 2025 | 691 | Ministry of Railways | Railways | Proposed 6 nos Road Over Bridge [ROB] at different locations under MCL Talcher Under Deposit Scheme. | East Coast Railway [ECoR] - II | 400045 | Odisha | 08/2022 | 07/2022 | 03/2025 | 01/2025 | 168.32 | 168.32 | 69.85 | 82
October 2025 | 692 | Ministry of Railways | Railways | Brundamal-Jharsuguda- flyover connection for joining downline | East Coast Railway [ECoR] - II | 400232 | Odisha | 01/2014 | 01/2014 | 12/2026 | 12/2026 | 297 | 297 | 193.22 | 30
October 2025 | 693 | Ministry of Railways | Railways | 3rd & 4th line between Sarla - Sason [8 km] [PB 73/2023-24/NR] | East Coast Railway [ECoR] - II | 612834 | Odisha | 04/2023 | 04/2023 | 12/2025 | - | 252 | 252 | 88.95 | 48
October 2025 | 694 | Ministry of Railways | Railways | Bangriposi-Gorumahisani new line [ 85.60 km ] | CAO/C/SER | 616586 | Odisha | 08/2024 | 09/2025 | 12/2029 | - | 2269.49 | 2269.49 | 3.06 | 0
October 2025 | 695 | Ministry of Railways | Railways | Badampahar-Kendujhargarh new line [82.06 km] | CAO/C/SER | 616587 | Odisha | 08/2024 | 09/2025 | 12/2029 | - | 1875.72 | 1875.72 | 0.91 | 0
October 2025 | 696 | Ministry of Railways | Railways | Paradeep - Badabandha 3rd & 4th Line / 18.51kms | East Coast Railway [ECoR] - II | 616695 | Odisha | 08/2023 | 04/2025 | 11/2028 | - | 300.15 | 300.15 | 0 | 0
October 2025 | 697 | Ministry of Railways | Railways | Jeypore - Malkangiri New BG Line Project | Indian Railways | 617290 | Odisha | NA | 02/2018 | 12/2030 | - | 2343.64 | 2343.64 | 630.83 | 13
October 2025 | 698 | Ministry of Railways | Railways | New B.G Railway Line between Jeypore & Navarangpur [38 Km] with Electrification | Indian Railway and Govt of Odisha | 617320 | Odisha | 07/2017 | 09/2022 | 09/2025 | - | 747.91 | 747.91 | 7.21 | 0
October 2025 | 699 | Ministry of Railways | Railways | Khurda-Bolangir New Broad Gauge Rail Link [301km] | East Coast Railway [ECoR] - II | 705358 | Odisha | 03/1994 | 03/2001 | 12/2026 | 12/2026 | 3792 | 5089 | 5147.89 | 89
October 2025 | 700 | Ministry of Railways | Railways | Talcher-Bimlagarh New Railway Line | East Coast Railway [ECoR] - II | 705359 | Odisha | 03/2004 | 12/2004 | 03/2025 | 03/2027 | 1928 | 1928 | 1955.9 | 48
October 2025 | 701 | Ministry of Railways | Railways | Bhadrak-Nergundi Third Line | East Coast Railway [ECoR] - II | 705510 | Odisha | 10/2015 | 04/2015 | 11/2024 | 01/2026 | 1284 | 1284 | 1298 | 80
October 2025 | 702 | Ministry of Railways | Railways | Koraput - Singapur Railway Doubling | East Coast Railway [ECoR] - II | 705513 | Odisha | 12/2015 | 12/2015 | 12/2027 | 03/2028 | 2362 | 2362 | 1825.42 | 70
October 2025 | 703 | Ministry of Railways | Railways | Jarapada- Budhapank with flyover at Talcher road 3rd and 4th Line | East Coast Railway [ECoR] - II | 705514 | Odisha | 11/2015 | 12/2015 | 11/2018 | 03/2026 | 1000 | 810.02 | 415.46 | 58
October 2025 | 704 | Ministry of Railways | Railways | 3rd & 4th Railway Line Project from Salegaon to Budhapank via Rajathgarh. | East Coast Railway [ECoR] - II | 705515 | Odisha | 07/2013 | 12/2015 | 03/2026 | 03/2026 | 1173 | 2092 | 1971 | 80
October 2025 | 705 | Ministry of Railways | Railways | Jeypore-Navarangpur New Rail Line Project | East Coast Railway [ECoR] - II | 705741 | Odisha | 07/2017 | 04/2023 | 07/2028 | 12/2029 | 748 | 748 | 12.06 | 1
October 2025 | 706 | Ministry of Railways | Railways | Jeypore-Malkanagiri New Railway Line Project | East Coast Railway [ECoR] - II | 705742 | Odisha | 02/2018 | 12/2023 | 07/2033 | 07/2033 | 2344 | 2344 | 489.57 | 20
October 2025 | 707 | Ministry of Railways | Railways | Khurda Road - Balangir Electrification of Railway Track Project | Ministry of Railways | 706898 | Odisha | 09/2018 | 09/2019 | 03/2021 | - | 267.61 | 267.61 | 0 | 0
October 2025 | 708 | Ministry of Railways | Railways | Godhani-Kalumna Chord 13.7 km | Ministry of Railways | 617321 | Offshore | 07/2018 | 07/2018 | 07/2028 | - | 150000 | 150000 | 1940 | 11
October 2025 | 709 | Ministry of Railways | Railways | Jaynagar-Bijalpura, incl. extn. Bet, Bijalpura-Bardibas [Nepal] | East Central Railway [ECR] - I | 705362 | Offshore | 08/2015 | 03/2011 | 03/2022 | 03/2026 | 819 | 819 | 580.51 | 75
October 2025 | 710 | Ministry of Railways | Railways | Ludhiana- Killa Raipur Railway Doubling Project | Railway | 705783 | Punjab | 03/2019 | 12/2022 | 03/2025 | 03/2026 | 237.64 | 238 | 134.48 | 50
October 2025 | 711 | Ministry of Railways | Railways | Dedicated Test Track for RDSO Phase II | North Western Railway [NWR] | 611614 | Rajasthan | 11/2021 | 11/2021 | 11/2026 | 11/2026 | 819.48 | 967.06 | 471 | 86
October 2025 | 712 | Ministry of Railways | Railways | Devgarh Madariya - Nathdwara Gauge Conversion [82.54 Km] part of Marwar - Mavli Gauge Conversion [152 Km] | North Western Railway [NWR] | 611849 | Rajasthan | 01/2023 | 01/2023 | 06/2028 | 06/2028 | 968.92 | 968.92 | 137.16 | 51
October 2025 | 713 | Ministry of Railways | Railways | Maintenance cum workshop depot for Vande Bharat Sleeper Trains as per conditions under WTA 527 | WPO/Patna | 611929 | Rajasthan | 09/2022 | 06/2023 | 12/2024 | - | 166.86 | 166.86 | 0 | 0
October 2025 | 714 | Ministry of Railways | Railways | PUSHKAR- MERTA CITY NEW LINE | North Western Railway [NWR] | 616841 | Rajasthan | 02/2024 | 02/2024 | 12/2026 | - | 799.64 | 799.64 | 14.64 | 4
October 2025 | 715 | Ministry of Railways | Railways | AJMER- CHANDERIYA DOUBLING | North Western Railway [NWR] | 616843 | Rajasthan | 02/2024 | 02/2024 | 06/2027 | - | 1634.79 | 1634.79 | 123.05 | 7
October 2025 | 716 | Ministry of Railways | Railways | SADULPUR - CHURU DOUBLING PROJECT | North Western Railway [NWR] | 617403 | Rajasthan | 01/2024 | 01/2024 | 06/2026 | - | 468.64 | 468.64 | 125.08 | 50
October 2025 | 717 | Ministry of Railways | Railways | POKHRAN - RAMDEVRA New Line | North Western Railway [NWR] | 617404 | Rajasthan | 04/2025 | 04/2025 | 03/2028 | - | 189.21 | 189.21 | 0 | 0
October 2025 | 718 | Ministry of Railways | Railways | NATHDWARA- NATHDWARA TOWN NL | North Western Railway [NWR] | 617408 | Rajasthan | 03/2019 | 04/2024 | 03/2027 | - | 166.33 | 166.33 | 81.41 | 1
October 2025 | 719 | Ministry of Railways | Railways | Dholpur - Sirmuttra Gauge Conversion | North Central Railway | 705482 | Rajasthan | 03/2022 | 04/2020 | 02/2019 | 02/2027 | 747 | 747 | 378.05 | 44
October 2025 | 720 | Ministry of Railways | Railways | Gudha-Thatha Mithri Construction of Railway Track Project | North Western Railway [NWR] | 705752 | Rajasthan | 04/2019 | 04/2019 | 11/2026 | 11/2026 | 819.48 | 967.06 | 384.28 | 99
October 2025 | 721 | Ministry of Railways | Railways | Sawai Madhopur-Jaipur Railway Line Project | North Western Railway [NWR] | 705912 | Rajasthan | 02/2024 | 04/2023 | 03/2027 | - | 1203.89 | 1203.89 | 94.76 | 12
October 2025 | 722 | Ministry of Railways | Railways | Agra Fort-Bandikui Doubling Line Project | CAO/C/NCR | 705919 | Rajasthan | 06/2022 | 02/2021 | 06/2027 | 06/2027 | 1390 | 1390 | 123 | 25
October 2025 | 723 | Ministry of Railways | Railways | Sawaimadhopur Bye Pass Line Project | North Western Railway [NWR] | 706866 | Rajasthan | 12/2022 | 01/2023 | 03/2026 | 05/2027 | 304 | 304 | 51.64 | 45
October 2025 | 724 | Ministry of Railways | Railways | Ph II extension of MRTS from Velachery to St Thomas Mount | Southern Railways [SR] - construction | 400280 | Tamil Nadu | 11/2007 | 11/2008 | 07/2024 | 08/2025 | 734 | 982 | 475.73 | 99
October 2025 | 725 | Ministry of Railways | Railways | Redevelopment of Chennai Egmore Station | Railway | 613002 | Tamil Nadu | 05/2022 | 10/2022 | 03/2026 | - | 842 | 842 | 340 | 0
October 2025 | 726 | Ministry of Railways | Railways | Coach Production Factory Upgradation Project | CPM/ICF | 705244 | Tamil Nadu | 12/2017 | 07/2018 | 12/2021 | - | 520 | 520 | 192.25 | 0
October 2025 | 727 | Ministry of Railways | Railways | Doubling between Bhadrachalam Road and Dornakal | South Central Railway [SCR] - II | 616856 | Telangana | 08/2023 | 04/2025 | 04/2029 | - | 770.12 | 770.12 | 16.34 | 0
October 2025 | 728 | Ministry of Railways | Railways | Railway Manufacturing Unit | South Central Railway [SCR] - II | 617409 | Telangana | 07/2016 | 02/2023 | 12/2026 | - | 521.36 | 521.36 | 420 | 58
October 2025 | 729 | Ministry of Railways | Railways | Kazipet Wagon Overhauling Project | RVNL | 705252 | Telangana | 09/2017 | 07/2017 | 12/2023 | - | 385 | 385 | 0 | 0
October 2025 | 730 | Ministry of Railways | Railways | Manoharabad-Kothapalli New Rail Line [151 km] | South Central Railway [SCR] - II | 705437 | Telangana | 07/2016 | 01/2017 | 03/2027 | 12/2027 | 1160 | 2781 | 1985.73 | 71
October 2025 | 731 | Ministry of Railways | Railways | Bahraich-Shravasti-Balrampur-Siddharthnagar -Santkabir nagar | North Eastern Railway [NER] | 400204 | Uttar Pradesh | 10/2018 | 03/2017 | 10/2030 | 10/2030 | 4939.78 | 4939.78 | 1251.81 | 8
October 2025 | 732 | Ministry of Railways | Railways | Sahjanwa-Dohrighat | North Eastern Railway [NER] | 400205 | Uttar Pradesh | 08/2019 | 03/2017 | 03/2029 | 03/2029 | 1319.75 | 1319.75 | 475.67 | 3
October 2025 | 733 | Ministry of Railways | Railways | Anandnagar - Ghugli via Maharajganj New line 52.7 km | Construction NER | 617252 | Uttar Pradesh | 10/2023 | 11/2023 | 03/2028 | - | 958.27 | 958.27 | 449.37 | 23
October 2025 | 734 | Ministry of Railways | Railways | Chunar-Chopan doubling project | North Central Railway | 617284 | Uttar Pradesh | 08/2023 | 01/2025 | 03/2028 | - | 1423.96 | 1423.96 | 53.81 | 4
October 2025 | 735 | Ministry of Railways | Railways | Surface triangle line bet. Bhadura stn and new crossing stn Karma | East Central Railway [ECR] - I | 617333 | Uttar Pradesh | 10/2022 | 05/2024 | 02/2027 | - | 199.96 | 199.96 | 0 | 0
October 2025 | 736 | Ministry of Railways | Railways | Doubling between Jaunpur Jn - Zaffarabad 6.28 km | M/S SRC company Infra Private Limited | 617370 | Uttar Pradesh | 03/2023 | 02/2025 | 01/2027 | - | 180.66 | 180.66 | 4 | 11
October 2025 | 737 | Ministry of Railways | Railways | Burhwal Gonda 3rd line | North Eastern Railway [NER] | 705567 | Uttar Pradesh | 11/2017 | 07/2019 | 03/2025 | 01/2026 | 1016 | 1118 | 1410.08 | 88
October 2025 | 738 | Ministry of Railways | Railways | Janghai-Pratapgarh- Amethi | CAO/C/II/NR | 705588 | Uttar Pradesh | 11/2017 | 03/2017 | 03/2025 | 03/2026 | 722 | 1194 | 1567 | 70
October 2025 | 739 | Ministry of Railways | Railways | Lalitpur-Birari with flyover at Lalitpur- 16 Km | North Central Railway | 705766 | Uttar Pradesh | 03/2017 | 11/2017 | 12/2024 | 01/2026 | 304.44 | 356 | 231.37 | 78
October 2025 | 740 | Ministry of Railways | Railways | Allahabad-Bamhrauli Flyover Construction & 4th Railway Line Project | North Central Railway | 705771 | Uttar Pradesh | 04/2019 | 10/2020 | 03/2026 | 03/2026 | 494 | 494 | 333 | 70
October 2025 | 741 | Ministry of Railways | Railways | Mughalsarai-Allahabad, 3rd line | North Central Railway | 705772 | Uttar Pradesh | 12/2015 | 03/2016 | 12/2026 | 03/2027 | 2649 | 2649.44 | 1561.89 | 62
October 2025 | 742 | Ministry of Railways | Railways | Aligarh -Daud Khan Flyover Construction & 3rd Railway Line Project | CAO/C/NCR | 705774 | Uttar Pradesh | 04/2019 | 09/2020 | 01/2025 | 03/2027 | 758 | 779.49 | 387.73 | 69
October 2025 | 743 | Ministry of Railways | Railways | Bhandai - Flyover for Etawah bound down train- 10 Km | North Central Railway (NCR) - II | 705777 | Uttar Pradesh | 07/2020 | 04/2021 | 02/2026 | 02/2027 | 250.18 | 250.18 | 115.05 | 8
October 2025 | 744 | Ministry of Railways | Railways | Phephna-Indara, Mau-Shahganj doubling excluding Indara-Mau | RVNL - I | 705779 | Uttar Pradesh | 05/2017 | 10/2019 | 12/2024 | 03/2026 | 1178 | 1777 | 1489.5 | 85
October 2025 | 745 | Ministry of Railways | Railways | Bhatni-Aurnihar with electrification excluding Indara-Mau | RVNL - I | 705780 | Uttar Pradesh | 03/2018 | 03/2017 | 12/2024 | 10/2025 | 2529 | 2529.46 | 2051.69 | 94
October 2025 | 746 | Ministry of Railways | Railways | Barabanki-Malhaur 3rd & 4th Railway Line Project | CAO/C/NR | 705782 | Uttar Pradesh | 01/2019 | 04/2017 | 03/2025 | 03/2026 | 407 | 407 | 317 | 75
October 2025 | 747 | Ministry of Railways | Railways | Janghai-Phaphamau Doubling Rail Line Project | RVNL | 705784 | Uttar Pradesh | 11/2018 | 03/2020 | 03/2025 | 03/2025 | 357 | 978.77 | 579 | 95
October 2025 | 748 | Ministry of Railways | Railways | Rishikesh-Karnaprayag New Rail Line- 125 km | RVNL - I | 705429 | Uttarakhand | 11/2016 | 08/2018 | 12/2025 | 03/2027 | 38953 | 38953 | 24645.15 | 65
October 2025 | 749 | Ministry of Railways | Railways | Kalinarayanpur-Krishnanagar Doubling Alongwith Krishnanagar - Chapra New Line And Naihati-Ranaghat 3rd Line. | Eastern Railway [ER] - I | 400247 | West Bengal | 07/2015 | 11/2005 | 02/2027 | 02/2027 | 1000 | 1000 | 1053.4 | 69
October 2025 | 750 | Ministry of Railways | Railways | Tarakeshwar-Bishnupur New Line [82.47 km] | Eastern Railway [ER] - I | 400273 | West Bengal | 03/2001 | 02/2008 | 03/2019 | 02/2026 | 1189 | 1542 | 1323.68 | 91
October 2025 | 751 | Ministry of Railways | Railways | Dum Dum Airport-New Garia via Rajarhat-Construction of Metro Railway | RVNL - II | 400277 | West Bengal | 03/2010 | 10/2011 | 12/2025 | 03/2026 | 8964 | 8964 | 8316.32 | 81
October 2025 | 752 | Ministry of Railways | Railways | Construction of Balurghat-Hilli new BG Line | Northeast Frontier Railway [NFR] | 612096 | West Bengal | 12/2010 | 12/2010 | 03/2027 | 03/2025 | 1209 | 1209 | 405.31 | 9
October 2025 | 753 | Ministry of Railways | Railways | SER Upgradation of maintenance infrastructure at Shalimar into Vande Bharat Chair Car maintenance cum workshop depot. | South Eastern Railway - JH | 617345 | West Bengal | NA | 12/2024 | 10/2026 | - | 226.87 | 226.87 | 0.21 | 5
October 2025 | 754 | Ministry of Railways | Railways | Joka-BBD Bag new metro project | RVNL - II | 705730 | West Bengal | 03/2010 | 04/2010 | 12/2026 | 12/2029 | 4835 | 10362 | 4634.68 | 59
October 2025 | 755 | Ministry of Railways | Railways | Noapara-Barasat via Bimanbandar - Construction of Metro railway [18 km] | Metro Railway, Kolkata | 706776 | West Bengal | 11/2010 | 03/2010 | 08/2026 | 03/2029 | 4830 | 4830 | 2764.13 | 32
October 2025 | 756 | Ministry of Railways | Railways | Baranagar-Barrackpore and Dakshineshwar- Construction of Metro Railway | RVNL - II | 706777 | West Bengal | 03/2010 | 03/2010 | 12/2026 | 12/2025 | 2298 | 2734 | 393.01 | 17
October 2025 | 757 | Department for Promotion of Industry & Internal Trade | Real Estate | Krishnapatnam Node - Phase 1 - Roads and Services Development | National Industrial Corridor Development Corporation | 701658 | Andhra Pradesh | 12/2020 | 02/2024 | 02/2028 | - | 2139.44 | 2139.44 | 472.8 | 21
October 2025 | 758 | Department for Promotion of Industry & Internal Trade | Real Estate | Tumakuru Node - Phase 1 - Roads and Services Development | National Highways & Infrastructure Development Corporation Ltd. [NHIDCL] | 701657 | Karnataka | 12/2020 | 02/2023 | 09/2026 | - | 1701.81 | 1701.81 | 117.35 | 10
October 2025 | 759 | Department of Telecommunications | Telecommunication | SETTING UP OF PHYSICAL INFRASTRUCTURE FOR THE NATIONAL INSTITUTE OF COMMUNICATION FINANCE [NICF] AT GHITORNI | National Communication Academy - Finance (Erstwhile NICF | 709859 | Delhi | 10/2014 | 04/2018 | 02/2020 | 10/2025 | 248.2 | 248.2 | 236.91 | 98
October 2025 | 760 | Department of Telecommunications | Telecommunication | Provision of 4G based Mobile Services in Uncovered Villages and National Highways of Meghalaya | Department of Telecommunications | 701598 | Meghalaya | 09/2019 | 09/2020 | 03/2022 | 03/2026 | 971.96 | 971.96 | 208.25 | 99
October 2025 | 761 | Department of Telecommunications | Telecommunication | Mobile connectivity in Left Wing Extremism [LWE] affected areas-Phase 1 Upgradation | Department of Telecommunications [DoT] | 617413 | Multi-States (Andhra Pradesh, Bihar, Chhattisgarh, Jharkhand, Madhya Pradesh, Maharashtra, Odisha, Telangana, Uttar Pradesh, West Bengal) | 04/2022 | 05/2024 | 05/2025 | 11/2025 | 1884.6 | 1884.6 | 100 | 67
October 2025 | 762 | Department of Telecommunications | Telecommunication | Mobile connectivity in Left Wing Extremism [LWE] affected areas-Phase2 | Department of Telecommunications [DoT] | 701599 | Multi-States (Andhra Pradesh, Bihar, Chhattisgarh, Jharkhand, Madhya Pradesh, Maharashtra, Odisha, Telangana, Uttar Pradesh, West Bengal) | NA | 09/2021 | 03/2023 | 11/2025 | 1577.57 | 1577.57 | 600.6 | 87
October 2025 | 763 | Department of Telecommunications | Telecommunication | Provision of 4G based mobile services in 7,287 uncovered villages of 44 Aspirational District across 5 states of Andhra Pradesh, Chhattisgarh, Jharkhand, Maharashtra & Odisha | Department of Telecommunications [DoT] | 701602 | Multi-States (Andhra Pradesh, Chhattisgarh, Jharkhand, Maharashtra, Odisha) | 11/2021 | 05/2022 | 11/2023 | 11/2025 | 3685 | 3685 | 1135.28 | 81
October 2025 | 764 | Department of Telecommunications | Telecommunication | Provision of 4G Mobile Services in Uncovered Villages of Arunachal Pradesh and 2 Districts of Assam | Department of Telecommunications | 701597 | Multi-States (Arunachal Pradesh, Assam) | 12/2020 | 10/2021 | 04/2023 | 03/2026 | 1255.49 | 1255.49 | 284.04 | 91
October 2025 | 765 | Department of Telecommunications | Telecommunication | 354 Uncovered Villages Scheme | Department of Telecommunications [DoT] | 701600 | Multi-States (Bihar, Gujarat, Himachal Pradesh, Jammu and Kashmir, Ladakh, Rajasthan, Uttar Pradesh) | 12/2019 | 04/2020 | 10/2021 | 08/2025 | 336.89 | 301.13 | 227.82 | 97
October 2025 | 766 | Department of Telecommunications | Telecommunication | 502 Aspirational District Scheme in Four states - Bihar, Madhya Pradesh, Rajastha and Uttar Pradesh | Department of Telecommunications [DoT] | 704495 | Multi-States (Bihar, Madhya Pradesh, Rajasthan, Uttar Pradesh) | NA | 03/2021 | 03/2022 | 12/2025 | 421.65 | 228.94 | 142.01 | 96
October 2025 | 767 | Department of Telecommunications | Telecommunication | PHASE-I OF CONSOLIDATION OF EXISTING CDR DATA CENTERS AND NIB-P3 DATA CENTERS WITH STATE OF THE ART | BSNL | 709749 | Multi-States (Maharashtra, Telangana) | 03/2020 | 03/2020 | 06/2021 | 12/2025 | 461.42 | 461.42 | 166.02 | 81
October 2025 | 768 | Department of Telecommunications | Telecommunication | Saturation 4G mobile coverage of Uncovered Villages through USOF | Department of Telecommunications [DoT] | 400013 | PAN India | 07/2022 | 07/2022 | 06/2024 | 03/2026 | 26316 | 30620 | 9791.8 | 76
October 2025 | 769 | Department of Telecommunications | Telecommunication | 4G Services by BSNL | Department of Telecommunications [DoT] | 701593 | PAN India | 11/2020 | 11/2020 | 03/2024 | 03/2026 | 28466 | 19592 | 8419.04 | 96
October 2025 | 770 | Department of Telecommunications | Telecommunication | BharatNet | Department of Telecommunications [DoT] | 706775 | PAN India | 07/2017 | 10/2011 | 08/2023 | 03/2027 | 61109 | 188000 | 46431.54 | 81
October 2025 | 771 | Department of Telecommunications | Telecommunication | MPLS-IP BASED ACCESS AND AGGREGATION NETWORK [MAAN] IN BSNL ALONG WITH TEST AND MEASURING EQUIPMENT | BSNL | 709856 | PAN India | 05/2023 | 05/2023 | 08/2024 | 10/2025 | 645.13 | 645.13 | 377.27 | 92
October 2025 | 772 | Department of Telecommunications | Telecommunication | Planning, Engineering, Supply, Installation, Testing, Commissioning, Integration & Annual Maintenance of 4G mobile network at 1 Lakh sites on PAN India basis including Mumbai & Delhi LSA on turnkey basis under Phase IX.2 Project. | BSNL | 709857 | PAN India | 05/2023 | 06/2023 | 06/2025 | 03/2026 | 24544.55 | 24544.5 | 8448.06 | 97
October 2025 | 773 | Department of Telecommunications | Telecommunication | OPTICAL TRANSPORT NETWORK [OTN] PH-4 IN BSNL | BSNL | 709858 | PAN India | 02/2024 | 02/2024 | 08/2025 | 11/2025 | 810.99 | 810.99 | 786.3 | 100
October 2025 | 774 | Department of Water Resources, River Development & GR | Waste & Water | Interception and Diversion and STP works in Bhagalpur under Hybrid annuity based PPP mode-Namami Gange Programme | National Mission for Clean Ganga | 616600 | Bihar | 10/2017 | 03/2022 | 02/2025 | 12/2025 | 413.29 | 413.29 | 126.67 | 97
October 2025 | 775 | Department of Water Resources, River Development & GR | Waste & Water | Sewage Treatment Plant 100MLD and Sewerage Network 288 km in Digha-Patna under Hybrid annuity based PPP mode-Namami Gange Programme | National Mission for Clean Ganga | 616611 | Bihar | 08/2017 | 07/2019 | 12/2025 | - | 824 | 824 | 396.71 | 56
October 2025 | 776 | Department of Water Resources, River Development & GR | Waste & Water | Sewage Treatment Plant 50MLD and Sewerage Network 150 km in Kankarbagh- Patna under Hybrid annuity based PPP mode-Namami Gange Programme | National Mission for Clean Ganga | 616612 | Bihar | 08/2017 | 07/2019 | 12/2025 | - | 578.89 | 578.89 | 171.79 | 54
October 2025 | 777 | Department of Water Resources, River Development & GR | Waste & Water | Sewer Network, SPS and STP at Begusarai | National Mission for Clean Ganga | 616615 | Bihar | 03/2010 | 03/2018 | 04/2025 | 12/2025 | 230.06 | 230.06 | 261.82 | 97
October 2025 | 778 | Department of Water Resources, River Development & GR | Waste & Water | Sewer Networks, SPS and STP at Hajipur | National Mission for Clean Ganga | 616616 | Bihar | 03/2010 | 03/2018 | 06/2025 | 12/2025 | 305.19 | 305.19 | 346.46 | 95
October 2025 | 779 | Department of Water Resources, River Development & GR | Waste & Water | Interception & Diversion with Rehabilitation of sewerage scheme at Agra under Hybrid annuity based PPP model-Namami Gange Programme | National Mission for Clean Ganga | 616594 | Uttar Pradesh | 05/2020 | 04/2023 | 04/2025 | 12/2025 | 842.25 | 842.25 | 208.64 | 75
October 2025 | 780 | Department of Water Resources, River Development & GR | Waste & Water | Pollution Abatement Works for River Kali Meerut under Meerut Municipality Interception & Diversion with STP | National Mission for Clean Ganga | 616605 | Uttar Pradesh | 05/2020 | 11/2024 | 12/2024 | 05/2027 | 690.71 | 690.71 | 34.79 | 34
October 2025 | 781 | Department of Water Resources, River Development & GR | Waste & Water | Pollution Abatement works for River Ganga at Hooghly Chinsurah- Municipal Town Interception & Diversion with STP | National Mission for Clean Ganga | 616604 | West Bengal | 05/2018 | 12/2021 | 03/2025 | 12/2025 | 154.73 | 154.73 | 96.17 | 92
October 2025 | 782 | Department of Water Resources, River Development & GR | Water Resources | Sardar Gouthu Latchanna Thotapalli Barrage Project | Water Resources-AP | 400100 | Andhra Pradesh | 04/2005 | 01/2006 | 12/2019 | 06/2026 | 353.05 | 1023.24 | 869.11 | 95
October 2025 | 783 | Department of Water Resources, River Development & GR | Water Resources | Gundlakamma project | Water Resources-AP | 400101 | Andhra Pradesh | 04/2005 | 04/2005 | 12/2019 | 03/2027 | 397.41 | 697.39 | 619.09 | 98
October 2025 | 784 | Department of Water Resources, River Development & GR | Water Resources | Polavaram Irrigation Project | Water Resources-AP | 701415 | Andhra Pradesh | 01/2009 | 11/2009 | 04/2022 | 03/2026 | 10151.04 | 55548.9 | 24837.97 | 84
October 2025 | 785 | Department of Water Resources, River Development & GR | Water Resources | Borolia Irrigation Project | Department of Water Resources, River Development & GR | 701370 | Assam | 04/1996 | 12/1996 | 12/2022 | 03/2026 | 256.16 | 256.16 | 44.7 | 55
October 2025 | 786 | Department of Water Resources, River Development & GR | Water Resources | Punpun Barrage Project | Water Resources-BR | 400104 | Bihar | 04/2007 | 04/2007 | 12/2019 | 03/2026 | 571.07 | 658.12 | 447.68 | 44
October 2025 | 787 | Department of Water Resources, River Development & GR | Water Resources | Kelo Irrigation Project | Water Resources-CT | 400111 | Chhattisgarh | 04/2008 | 04/2008 | 12/2019 | 06/2026 | 459.97 | 727.04 | 616.93 | 72
October 2025 | 788 | Department of Water Resources, River Development & GR | Water Resources | Kudali Irrigation Project | Department of Water Resources, River Development & GR | 701399 | Chhattisgarh | 04/2009 | 12/2009 | 12/2025 | - | 382.29 | 382.29 | 239.03 | 86
October 2025 | 789 | Department of Water Resources, River Development & GR | Water Resources | Sardar Sarovar CADWM Project | Narmada and Water Resources, Water Supply and Kalpsar Department-GJ | 400097 | Gujarat | 04/2017 | 04/2017 | 12/2019 | 03/2026 | 5021.76 | 6670.31 | 4954.99 | 90
October 2025 | 790 | Department of Water Resources, River Development & GR | Water Resources | Sardar Sarovar Project | Narmada and Water Resources, Water Supply and Kalpsar Department-GJ | 701372 | Gujarat | 04/1996 | 04/1996 | 12/2019 | 03/2026 | 20718.17 | 33412.5 | 31860.86 | 93
October 2025 | 791 | Department of Water Resources, River Development & GR | Water Resources | Subernarekha Multipurpose Project, Jharkhand | Department of Water Resources-JH | 701376 | Jharkhand | 04/2011 | 01/2012 | 12/2019 | 03/2026 | 3807.77 | 9579.58 | 5790.29 | 70
October 2025 | 792 | Department of Water Resources, River Development & GR | Water Resources | Upper Tunga Irrigation Project | Water Resources-KA | 701377 | Karnataka | 04/2014 | 04/2014 | 12/2019 | 03/2026 | 770.16 | 1606.07 | 1515.32 | 99
October 2025 | 793 | Department of Water Resources, River Development & GR | Water Resources | Omkareshwar CADWM Project | Water resource-mp | 400096 | Madhya Pradesh | 04/2017 | 04/2017 | 12/2019 | 03/2026 | 648.09 | 648.09 | 172.56 | 3
October 2025 | 794 | Department of Water Resources, River Development & GR | Water Resources | Bargi Diversion Project Phase - IV [km. 154 to km 197] | Water Resources-MP | 400115 | Madhya Pradesh | 04/2008 | 01/2009 | 12/2019 | 03/2026 | 751.03 | 893.35 | 783.1 | 75
October 2025 | 795 | Department of Water Resources, River Development & GR | Water Resources | Bargi Diversion Project Phase - III [km. 104 to km 154] | Water Resources-MP | 400116 | Madhya Pradesh | 04/2007 | 04/2007 | 12/2019 | 03/2026 | 1229.15 | 1399.7 | 1937.25 | 80
October 2025 | 796 | Department of Water Resources, River Development & GR | Water Resources | Gosikhurd CADWM Project | Department of water resources-MH - II | 400095 | Maharashtra | 04/2017 | 04/2017 | 12/2019 | 06/2026 | 743.73 | 743.73 | 295.12 | 52
October 2025 | 797 | Department of Water Resources, River Development & GR | Water Resources | Urmodi Irrigation Project | Department of water resources-MH - II | 400105 | Maharashtra | 04/2017 | 04/2018 | 06/2022 | 12/2026 | 580.79 | 895.81 | 713.46 | 76
October 2025 | 798 | Department of Water Resources, River Development & GR | Water Resources | Sulwade-Jamphal-Kanoli Lift Irrigation Scheme | Department of water resources-MH - II | 400107 | Maharashtra | 04/2017 | 02/2019 | 06/2023 | 06/2027 | 2407.67 | 2407.67 | 2570.94 | 80
October 2025 | 799 | Department of Water Resources, River Development & GR | Water Resources | Purna Barrage-2 [Ner Dhamana] Medium Irrigation Project | Department of water resources-MH - II | 400109 | Maharashtra | 04/2017 | 04/2018 | 06/2020 | 06/2026 | 848.07 | 888.43 | 690.49 | 69
October 2025 | 800 | Department of Water Resources, River Development & GR | Water Resources | Jigaon Irrigation Project | Department of water resources-MH - II | 400112 | Maharashtra | 04/2017 | 04/2018 | 06/2028 | - | 7222.95 | 7222.95 | 8722.81 | 90
October 2025 | 801 | Department of Water Resources, River Development & GR | Water Resources | Bodwad Parisar Sinchan Yojna | Department of Water Resources-MH | 617422 | Maharashtra | 05/2002 | 01/2017 | 07/2027 | - | 1923.81 | 1923.81 | 1770.13 | 49
October 2025 | 802 | Department of Water Resources, River Development & GR | Water Resources | Waghur Project | Department of water resources-MH - II | 701383 | Maharashtra | 04/1996 | 04/1996 | 12/2019 | 03/2026 | 1058.99 | 1758.51 | 1557.45 | 89
October 2025 | 803 | Department of Water Resources, River Development & GR | Water Resources | Gosikhurd Project | Department of water resources-MH - II | 701386 | Maharashtra | 04/2008 | 04/2008 | 12/2019 | 06/2028 | 7196.47 | 12770.1 | 13765.22 | 72
October 2025 | 804 | Department of Water Resources, River Development & GR | Water Resources | Aruna Medium Irrigation Project | Department of water resources-MH - II | 701391 | Maharashtra | 04/2009 | 01/2010 | 12/2019 | 12/2025 | 210.45 | 1472.14 | 1697.94 | 97
October 2025 | 805 | Department of Water Resources, River Development & GR | Water Resources | Lower Pedhi Project | Department of water resources-MH - II | 701396 | Maharashtra | 04/2008 | 04/2008 | 12/2019 | 06/2026 | 255.97 | 1480.7 | 1324.98 | 65
October 2025 | 806 | Department of Water Resources, River Development & GR | Water Resources | Nardave Medium Irrigation Project | Department of water resources-MH - II | 701398 | Maharashtra | 04/2009 | 04/2009 | 12/2019 | 06/2026 | 211.46 | 781.85 | 623.5 | 72
October 2025 | 807 | Department of Water Resources, River Development & GR | Water Resources | Thoubal Multipurpose Project | Water Resources Department-MN | 701400 | Manipur | 04/1997 | 04/1997 | 12/2019 | 03/2026 | 1449.44 | 1822.24 | 1837.91 | 98
October 2025 | 808 | Department of Water Resources, River Development & GR | Water Resources | North Koel Reservoir Project | Department of Water Resources, River Development & GR | 701412 | Multi-States (Bihar, Jharkhand) | 08/2017 | 01/2021 | 03/2021 | 03/2026 | 1622.27 | 2430.76 | 151.04 | 32
October 2025 | 809 | Department of Water Resources, River Development & GR | Water Resources | Integrated Anandpur Barrage Project | Water Resources-OR | 603945 | Odisha | 04/1997 | 01/1998 | 12/2019 | 06/2026 | 567.03 | 2990.05 | 2629.74 | 62
October 2025 | 810 | Department of Water Resources, River Development & GR | Water Resources | Kanupur Irrigation Project | Irrigation and CAD-TG | 701404 | Odisha | 04/2003 | 01/2004 | 12/2019 | 06/2026 | 989.43 | 2301.28 | 2712.75 | 79
October 2025 | 811 | Department of Water Resources, River Development & GR | Water Resources | Relining of Rajasthan feeder and Sirhind Feeder canal | Department of Water Resources-PB | 701410 | Punjab | 02/2016 | 04/2018 | 06/2021 | 06/2026 | 1441.26 | 2462.16 | 3012.69 | 80
October 2025 | 812 | Department of Water Resources, River Development & GR | Water Resources | Shahpur Kandi Dam Project | Department of Water Resources-PB | 701411 | Punjab | 02/2010 | 04/2018 | 06/2022 | 10/2025 | 2285.81 | 2715.7 | 2169.72 | 88
October 2025 | 813 | Department of Water Resources, River Development & GR | Water Resources | Sri Ram Sagar Project Stage - II | Irrigation and CAD-TG | 400102 | Telangana | 04/2005 | 04/2005 | 12/2019 | 03/2026 | 736.13 | 949.87 | 940.7 | 96
October 2025 | 814 | Department of Water Resources, River Development & GR | Water Resources | Indiramma Flood Flow Canal Project | Irrigation and CAD-TG | 400103 | Telangana | 04/2005 | 01/2006 | 12/2019 | 12/2026 | 1331.3 | 5940.09 | 4491.08 | 92
October 2025 | 815 | Department of Water Resources, River Development & GR | Water Resources | J. Chokka Rao Devadula Lift Irrigation Scheme | Irrigation and CAD-TG | 701405 | Telangana | 04/2006 | 04/2006 | 12/2019 | 12/2025 | 8200.71 | 14730 | 4664.8 | 87
October 2025 | 816 | Department of Water Resources, River Development & GR | Water Resources | Rajiv Bhima Lift Irrigation Scheme | Irrigation and CAD-TG | 701406 | Telangana | 04/2007 | 01/2008 | 12/2019 | 03/2026 | 1402 | 2509.66 | 1839.76 | 100
October 2025 | 817 | Department of Water Resources, River Development & GR | Water Resources | Saryu Nahar CADWM Project | Irrigation & Water Resources-UP | 400093 | Uttar Pradesh | 04/2017 | 04/2017 | 12/2019 | 03/2026 | 1672.7 | 1672.7 | 22.24 | 1
October 2025 | 818 | Department of Water Resources, River Development & GR | Water Resources | Morna [Gureghar] Irrigation Project | Department of Water Resources, River Development & GR | 701395 | Uttar Pradesh | 04/2007 | 12/2007 | 12/2025 | - | 219.9 | 219.9 | 115.2 | 31
October 2025 | 819 | Department of Water Resources, River Development & GR | Water Resources | Madhya Ganga canal Phase-II | Irrigation & Water Resources-UP | 701408 | Uttar Pradesh | 04/2008 | 04/2008 | 12/2019 | 12/2025 | 1060.67 | 4417.21 | 4552.44 | 82
October 2025 | 820 | Department of Water Resources, River Development & GR | Water Resources | Jamrani Dam Multipurpose Project | Irrigation-UK | 613787 | Uttarakhand | 10/2023 | 11/2023 | 06/2029 | - | 2584.1 | 2584.1 | 968.52 | 16

## Combined - All Ongoing
Month | Sl.No | Ministry/Department | Sector | Project Name | Implementing Agency | Project Code | State | Date of Approval | Start Date | Target DoC (Original) | Target DoC (Revised) | Original Cost (Rs Cr) | Revised Cost (Rs Cr) | Cumulative Expenditure (Rs Cr) | Physical Progress (%)
August 2025 | 1 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Construction of New Domestic Terminal Building Building and miscellaneous works including maintenance, operations and AICMC at Kadapa Airport | Airport Authority of India [AAI] | 612786 | Andhra Pradesh | 03/2023 | 01/2024 | 01/2026 | 03/2026 | 265.91 | 265.91 | 50.06 | 34
August 2025 | 2 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Construction of New Integrated Terminal Building and associated works including apron to park 3 code E type of aircraft or 6 code C type of aircraft at Vijayawada Airport. | Airport Authority of India [AAI] | 701107 | Andhra Pradesh | 06/2020 | 09/2020 | 09/2022 | 12/2025 | 611.8 | 611.8 | 473.27 | 79
August 2025 | 3 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Construction of New Domestic Terminal Building at Rajahmundry Airport. | Airport Authority of India [AAI] | 701121 | Andhra Pradesh | 12/2022 | 08/2023 | 08/2025 | 12/2025 | 347.15 | 347.15 | 90.56 | 51
August 2025 | 4 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Guwahati Airport New Integrated Terminal Building Construction Project | Adani Airport Holdings Limited | 706724 | Assam | 12/2016 | 03/2018 | 03/2025 | 11/2025 | 1712 | 1712 | 2335.44 | 91
August 2025 | 5 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Development of New Civil Enclave at Bihta | Airport Authority of India [AAI] | 612183 | Bihar | 08/2024 | 03/2025 | 09/2027 | - | 1413 | 1413 | 0 | 1
August 2025 | 6 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Development of New Civil Enclave and associated works at Darbhanga Airport | Airport Authority of India [AAI] | 612194 | Bihar | 07/2024 | 07/2024 | 01/2026 | - | 911.66 | 911.66 | 160.2 | 26
August 2025 | 7 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Construction of New Domestic Terminal Building [Phase-I and II] and other allied structures at JPNI Airport, Patna | Airport Authority of India [AAI] | 701101 | Bihar | 12/2018 | 10/2018 | 07/2023 | 11/2025 | 1216.9 | 1216.9 | 1096.51 | 94
August 2025 | 8 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Goa Airport Terminal Building Extension Project | Airport Authority of India [AAI] | 701105 | Goa | 11/2017 | 12/2019 | 12/2021 | 09/2025 | 255.69 | 255.69 | 130 | 90
August 2025 | 9 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Development of Dholera International Greenfield Airport , Gujarat | Airport Authority of India [AAI] | 701126 | Gujarat | 06/2022 | 07/2022 | 06/2026 | 06/2026 | 1305 | 1551 | 1348.78 | 64
August 2025 | 10 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Construction of NTB complex including apron, taxi track and other associated civil works and electrical & mechanical installations towards Tawi River side at CA Jammu. | Airport Authority of India [AAI] | 611047 | Jammu and Kashmir | 07/2022 | 07/2023 | 06/2026 | 06/2026 | 861.37 | 861.37 | 177.69 | 35
August 2025 | 11 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Construction of New Domestic Terminal Building and Miscellaneous works at Hubli Airport | Airport Authority of India [AAI] | 612787 | Karnataka | 06/2023 | 01/2024 | 01/2026 | 03/2026 | 320.47 | 320.47 | 61.79 | 38
August 2025 | 12 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Construction of New Domestic Terminal Building and Miscellaneous Works at Belagavi Airport. | Airport Authority of India [AAI] | 612788 | Karnataka | 06/2023 | 02/2024 | 01/2026 | 01/2026 | 322.45 | 322.45 | 121.72 | 52
August 2025 | 13 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Development of additional RESA on either end on Runway 10-28 at Calicut Airport. Construction of embankment with slope protection, drainage system and associated works for additional RESA on either end on Runway 10-28 | Airport Authority of India [AAI] | 612789 | Kerala | 06/2023 | 02/2024 | 09/2025 | 03/2026 | 484.57 | 484.57 | 83.95 | 21
August 2025 | 14 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Construction of Terminal Building & Associated works at Leh Airport, Ladakh | Airport Authority of India [AAI] | 400010 | Ladakh | 07/2018 | 09/2018 | 09/2021 | 10/2025 | 480 | 640 | 434.79 | 71
August 2025 | 15 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | C/o NITB Imphal Airport | Airport Authority of India [AAI] | 706718 | Manipur | 11/2021 | 07/2022 | 07/2024 | 12/2026 | 499 | 499 | 154.43 | 41
August 2025 | 16 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | SITC of ATM Automation System and ASMGCS [Including SMR & MLAT] for Mumbai, Navi Mumbai, Jewar [earlier MOPA, without ASMGCS], HIAL & BIAL | Airport Authority of India [AAI] | 611570 | Multi-States (Karnataka, Maharashtra, Telangana, Uttar Pradesh) | NA | 10/2022 | 09/2025 | 08/2026 | 500.48 | 500.48 | 332.26 | 75
August 2025 | 17 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Construction of New Passenger Terminal Building for Domestic Operations at Jodhpur Airport. | Airport Authority of India [AAI] | 701127 | Rajasthan | 05/2022 | 04/2023 | 11/2024 | 10/2025 | 480 | 480 | 281.72 | 84
August 2025 | 18 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Construction of New Integrated Passenger Terminal Building at Udaipur Airport | Airport Authority of India [AAI] | 701128 | Rajasthan | 06/2023 | 11/2022 | 03/2026 | 10/2026 | 887 | 887 | 352.82 | 49
August 2025 | 19 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Widening of basic strip at Western Side of Runway Chainage 80m to 920m i/c slope stabilization Measures [Balance work] of uphill and Improvement of Storm Water Drainage System at Pakyong Airport, Sikkim on design & build basis [EPC] with integrated 10 years maintenance. | Airport Authority of India [AAI] | 612793 | Sikkim | 11/2023 | 12/2023 | 02/2026 | - | 323.26 | 323.26 | 29.7 | 12
August 2025 | 20 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Modernization of Chennai Airport, Phase II, Part 2 | Airport Authority of India [AAI] | 611602 | Tamil Nadu | 05/2018 | 06/2023 | 07/2025 | 03/2026 | 1207 | 1207 | 149.21 | 22
August 2025 | 21 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Construction of New Terminal Building, Second Link Taxi Track, Apron Expansion, and associated works at Prayagraj Airport- On Design & Build Basis. | Airport Authority of India [AAI] | 612063 | Uttar Pradesh | NA | 08/2023 | 11/2024 | 08/2025 | 219.18 | 274.38 | 215.19 | 100
August 2025 | 22 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Lucknow Airport-Terminal 3- Phase 1 & Other Associated Works | Adani Airport Holdings Limited | 701091 | Uttar Pradesh | 06/2018 | 09/2018 | 03/2026 | - | 3100 | 3100 | 16024.42 | 100
August 2025 | 23 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Development of Lal Bahadur Shastri International airport, Varanasi including C/o New Terminal Building, Apron Extension, Runway Extension, PTT and allied works. | Airport Authority of India [AAI] | 701113 | Uttar Pradesh | 07/2024 | 07/2024 | 07/2027 | 07/2027 | 2869.65 | 2869.65 | 322.98 | 16
August 2025 | 24 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Development of New Integrated Civil Enclave at Agra Airport | Airport Authority of India [AAI] | 701122 | Uttar Pradesh | 06/2024 | 07/2024 | 07/2026 | - | 579 | 579 | 76.88 | 16
August 2025 | 25 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Development of New Civil Enclave at Bagdogra Airport | Airport Authority of India [AAI] | 611495 | West Bengal | 08/2024 | 10/2023 | 01/2027 | 01/2027 | 1549 | 1549 | 274.14 | 11
August 2025 | 26 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Re-Construction of Rigid portions of Secondary Runway, K and A Taxiway and Strengthening of C Taxiway at NSCBI Airport Kolkata. | Airport Authority of India [AAI] | 612791 | West Bengal | 04/2023 | 12/2023 | 02/2025 | 08/2026 | 328.3 | 328.3 | 101.26 | 45
August 2025 | 27 | Ministry of Coal | Coal | TIKAK EXTENSION OCP | MIS MoCoal Integration Logins | 615820 | Assam | 07/2022 | 07/2022 | 07/2031 | - | 159.77 | 159.77 | 80.84 | 0
August 2025 | 28 | Ministry of Coal | Coal | TIRAP OCP | MIS MoCoal Integration Logins | 615821 | Assam | 11/2022 | 11/2022 | 11/2030 | - | 289.46 | 289.46 | 105.47 | 0
August 2025 | 29 | Ministry of Coal | Coal | PORDA CHIMTAPANI OCP [10 MTY] | South Eastern Coalfields Limited [SECL] | 400144 | Chhattisgarh | 12/2020 | 12/2020 | 03/2029 | - | 2310.12 | 2310.12 | 83.66 | 10
August 2025 | 30 | Ministry of Coal | Coal | CHHAL OC SEAM III [6 MTY] | South Eastern Coalfields Limited [SECL] | 400145 | Chhattisgarh | 12/2013 | 12/2013 | 03/2022 | 09/2025 | 610.63 | 610.63 | 577.46 | 85
August 2025 | 31 | Ministry of Coal | Coal | KUSMUNDA OC EXPANSION [15 TO 50 MTY] | South Eastern Coalfields Limited [SECL] | 400147 | Chhattisgarh | 08/2013 | 08/2013 | 03/2023 | 03/2030 | 7612.33 | 7612.33 | 4697.95 | 81
August 2025 | 32 | Ministry of Coal | Coal | BAROUD OC EXPANSION [3.0-10.0M | South Eastern Coalfields Limited [SECL] | 400149 | Chhattisgarh | 08/2020 | 08/2020 | 03/2029 | - | 2309.8 | 2309.8 | 926.11 | 48
August 2025 | 33 | Ministry of Coal | Coal | DIPKA EXPANSION OCP [40 MTY] | South Eastern Coalfields Limited [SECL] | 400354 | Chhattisgarh | 12/2020 | 12/2020 | 03/2029 | - | 5241.4 | 5241.4 | 2830.01 | 37
August 2025 | 34 | Ministry of Coal | Coal | GEVRA OC [70 MTY] | South Eastern Coalfields Limited [SECL] | 400424 | Chhattisgarh | 03/2016 | 03/2016 | 03/2023 | 03/2026 | 11816.4 | 11816.4 | 5328.96 | 77
August 2025 | 35 | Ministry of Coal | Coal | JAMPALI OC RCE [2.0 MTY] | South Eastern Coalfields Limited [SECL] | 613795 | Chhattisgarh | 05/2020 | 05/2020 | 03/2025 | 06/2025 | 278.64 | 278.64 | 210.07 | 82
August 2025 | 36 | Ministry of Coal | Coal | AMERA OC RCE [1.0 MTY] | South Eastern Coalfields Limited [SECL] | 613798 | Chhattisgarh | 02/2015 | 02/2015 | 03/2026 | - | 335.97 | 335.97 | 88.21 | 42
August 2025 | 37 | Ministry of Coal | Coal | AMGAON OC RCE [1.0 MTY] | South Eastern Coalfields Limited [SECL] | 613799 | Chhattisgarh | 07/2015 | 07/2015 | 03/2026 | - | 316.11 | 316.11 | 188.6 | 72
August 2025 | 38 | Ministry of Coal | Coal | JAGANNATHPUR OC RCE PROJECT[3 | South Eastern Coalfields Limited [SECL] | 613800 | Chhattisgarh | 07/2016 | 07/2016 | 03/2025 | 03/2026 | 459.49 | 459.49 | 274.35 | 92
August 2025 | 39 | Ministry of Coal | Coal | MAHAMAYA OCP [1.50 MTY] | South Eastern Coalfields Limited [SECL] | 613801 | Chhattisgarh | 05/2018 | 05/2018 | 03/2026 | - | 410.26 | 410.26 | 181.23 | 38
August 2025 | 40 | Ministry of Coal | Coal | KATKONA RO UG MINE | South Eastern Coalfields Limited [SECL] | 615191 | Chhattisgarh | 01/2023 | 01/2023 | 03/2029 | - | 329.21 | 329.21 | 60.3 | 2
August 2025 | 41 | Ministry of Coal | Coal | PELMA OC MDO | South Eastern Coalfields Limited [SECL] | 616234 | Chhattisgarh | 10/2022 | 10/2022 | 03/2033 | - | 1725.04 | 1725.04 | 15.66 | 17
August 2025 | 42 | Ministry of Coal | Coal | KUSMUNDA OC EXPANSION PROJECT 50-75 MTY | SECL - CIL | 617287 | Chhattisgarh | 11/2024 | 11/2024 | 03/2030 | - | 4516.88 | 4516.88 | 16.97 | 3
August 2025 | 43 | Ministry of Coal | Coal | MANIKPUR OC EXPANSION PROJECT 7 MTY | South Eastern Coalfields Limited [SECL] | 617288 | Chhattisgarh | 01/2025 | 01/2025 | 03/2029 | - | 382.61 | 382.61 | 0.86 | 1
August 2025 | 44 | Ministry of Coal | Coal | DIPKA OC | SECL - CIL | 612838 | Gujarat | NA | 01/2017 | 03/2025 | - | 7580 | 7580 | 3091 | 65
August 2025 | 45 | Ministry of Coal | Coal | HURA C OCP | ECL - CIL | 400018 | Jharkhand | 08/2022 | 08/2022 | 03/2029 | - | 859.41 | 859.41 | 450.76 | 62
August 2025 | 46 | Ministry of Coal | Coal | KONAR EXPANSION OCP | Ministry of Coal | 400073 | Jharkhand | 01/2022 | 01/2022 | 03/2032 | - | 799.34 | 799.34 | 424.01 | 45
August 2025 | 47 | Ministry of Coal | Coal | KARO EXPANSION OCP | Ministry of Coal | 400074 | Jharkhand | 01/2022 | 01/2022 | 03/2029 | - | 908.47 | 908.47 | 269.18 | 22
August 2025 | 48 | Ministry of Coal | Coal | SANGHMITRA OC | Ministry of Coal | 400136 | Jharkhand | 03/2024 | 03/2027 | 03/2032 | - | 2660 | 2660 | 0 | 0
August 2025 | 49 | Ministry of Coal | Coal | CHANDRAGUPT OCP | Ministry of Coal | 400138 | Jharkhand | 08/2020 | 08/2020 | 03/2032 | - | 973.5 | 973.5 | 440.56 | 25
August 2025 | 50 | Ministry of Coal | Coal | KOTRE BASANTPUR PACHMO OCP | Ministry of Coal | 400139 | Jharkhand | 08/2020 | 08/2020 | 03/2032 | - | 861.06 | 625.4 | 455.95 | 42
August 2025 | 51 | Ministry of Coal | Coal | Pachwara South Coal Block | NLC India Limited [NLCIL] | 400142 | Jharkhand | NA | 12/2019 | 09/2028 | - | 2242.9 | 2242.9 | 1170.75 | 74
August 2025 | 52 | Ministry of Coal | Coal | RPR MAGADH EXP OCP | Ministry of Coal | 400150 | Jharkhand | 08/2020 | 08/2020 | 03/2028 | - | 7254.37 | 7254.37 | 1535.31 | 38
August 2025 | 53 | Ministry of Coal | Coal | NORTH URIMARI EXPANSION OCP | Ministry of Coal | 400151 | Jharkhand | 07/2021 | 07/2021 | 03/2029 | - | 778.8 | 778.8 | 695.99 | 67
August 2025 | 54 | Ministry of Coal | Coal | EPR ROHINI - KARKETTA OCP | Central Coalfields Limited [CCL] | 400153 | Jharkhand | 01/2021 | 01/2021 | 03/2028 | - | 1020.42 | 1020.42 | 83.95 | 20
August 2025 | 55 | Ministry of Coal | Coal | EPR PUNDI OCP | Ministry of Coal | 400154 | Jharkhand | 11/2020 | 11/2020 | 03/2027 | - | 713.35 | 713.35 | 236.58 | 10
August 2025 | 56 | Ministry of Coal | Coal | EPR ASHOK OC | Ministry of Coal | 400155 | Jharkhand | 05/2021 | 05/2021 | 03/2028 | - | 2898.28 | 2898.28 | 178.51 | 22
August 2025 | 57 | Ministry of Coal | Coal | EPR AMRAPALI OCP | Ministry of Coal | 400156 | Jharkhand | 02/2020 | 02/2020 | 03/2028 | - | 5136.15 | 5136.15 | 1154.6 | 43
August 2025 | 58 | Ministry of Coal | Coal | RAJRAPPA RCE OCP | Ministry of Coal | 400160 | Jharkhand | 12/2009 | 12/2009 | 03/2016 | 03/2027 | 510.85 | 510.85 | 488.67 | 76
August 2025 | 59 | Ministry of Coal | Coal | CHITRA EAST OC | Eastern Coal Fields Limited [ECL] | 400172 | Jharkhand | 08/2018 | 08/2018 | 03/2026 | - | 513.99 | 513.99 | 229.01 | 51
August 2025 | 60 | Ministry of Coal | Coal | JHARKHAND-LAIYO OCP | Ministry of Coal | 400352 | Jharkhand | 08/2020 | 08/2020 | 03/2031 | - | 764.57 | 764.57 | 145.81 | 29
August 2025 | 61 | Ministry of Coal | Coal | MOONIDIH XV SEAM UG | Ministry of Coal | 400425 | Jharkhand | 08/2011 | 08/2011 | 03/2019 | 05/2026 | 1230.27 | 1230.27 | 626.63 | 81
August 2025 | 62 | Ministry of Coal | Coal | 2.5 MTPA PATHERDIH NLW WASHERY | Ministry of Coal | 611017 | Jharkhand | 10/2015 | 04/2016 | 04/2018 | 03/2026 | 334.27 | 334.27 | 140.51 | 48
August 2025 | 63 | Ministry of Coal | Coal | AMALAGAMATED NTST KUJAMA OCP 8.5MTY | Ministry of Coal | 611864 | Jharkhand | 01/2023 | 01/2023 | 03/2030 | - | 4011.85 | 4011.85 | 398.5 | 28
August 2025 | 64 | Ministry of Coal | Coal | MURAIDIH UG PROJECT | Ministry of Coal | 613808 | Jharkhand | 02/2011 | 02/2011 | 04/2014 | 12/2026 | 339.87 | 339.87 | 191 | 70
August 2025 | 65 | Ministry of Coal | Coal | TAPIN SOUTH EXPN | Ministry of Coal | 615349 | Jharkhand | 11/2020 | 11/2020 | 03/2028 | - | 230.41 | 230.41 | 22.02 | 20
August 2025 | 66 | Ministry of Coal | Coal | SIRKA OC | Ministry of Coal | 615822 | Jharkhand | 05/2020 | 05/2020 | 03/2028 | - | 222.82 | 222.82 | 139.31 | 53
August 2025 | 67 | Ministry of Coal | Coal | TETARIAKHAR OC | Ministry of Coal | 615843 | Jharkhand | 11/2019 | 11/2019 | 03/2025 | 03/2027 | 243.52 | 243.52 | 44.64 | 30
August 2025 | 68 | Ministry of Coal | Coal | CHUPERBHITA SIMLONG OCP MDO 6 MTY | Eastern Coal Fields Limited [ECL] | 616225 | Jharkhand | 12/2023 | 12/2023 | 03/2037 | - | 979.08 | 979.08 | 0 | 0
August 2025 | 69 | Ministry of Coal | Coal | JARANGDIH EXPN. OCP 1.5 MTY | CCL - CIL | 616236 | Jharkhand | 02/2020 | 02/2020 | 03/2029 | - | 414.37 | 414.37 | 85.6 | 33
August 2025 | 70 | Ministry of Coal | Coal | BLOCK E OCP | Ministry of Coal | 616253 | Jharkhand | 03/2024 | 03/2024 | 03/2029 | - | 5850.83 | 5850.83 | 20.32 | 3
August 2025 | 71 | Ministry of Coal | Coal | AMADAND OCP[4.0MTY] | South Eastern Coalfields Limited [SECL] | 400148 | Madhya Pradesh | 03/2016 | 03/2016 | 03/2021 | 03/2027 | 869.44 | 869.44 | 273.45 | 75
August 2025 | 72 | Ministry of Coal | Coal | RAMPUR BATURA OCP [4.0MTY] | South Eastern Coalfields Limited [SECL] | 400152 | Madhya Pradesh | 07/2019 | 07/2019 | 03/2026 | - | 1248.93 | 1248.93 | 495.4 | 44
August 2025 | 73 | Ministry of Coal | Coal | BLOCK B EXPANSION [3.5 TO 8.0 | Northern Coalfields Limited [NCL] | 400162 | Madhya Pradesh | 07/2019 | 07/2019 | 03/2023 | 03/2027 | 998.71 | 998.71 | 457.2 | 47
August 2025 | 74 | Ministry of Coal | Coal | NIGAHI EXPANSION [15 TO 25 MTP | Northern Coalfields Limited [NCL] | 400321 | Madhya Pradesh | 11/2020 | 11/2020 | 03/2025 | 03/2028 | 1729.68 | 1729.68 | 804.11 | 48
August 2025 | 75 | Ministry of Coal | Coal | KANCHAN OC EXP | South Eastern Coalfields Limited [SECL] | 613802 | Madhya Pradesh | 12/2014 | 12/2014 | 03/2026 | - | 371.04 | 371.04 | 144.61 | 47
August 2025 | 76 | Ministry of Coal | Coal | JHIRIA WEST OCP [1.5 MTY] | South Eastern Coalfields Limited [SECL] | 613803 | Madhya Pradesh | 01/2024 | 01/2024 | 03/2026 | - | 366.94 | 366.94 | 34.05 | 41
August 2025 | 77 | Ministry of Coal | Coal | RPR TAWA-III UG 0.84 MTY | Western Coalfields Limited [WCL] | 613804 | Madhya Pradesh | 12/2021 | 12/2021 | 03/2027 | - | 314.09 | 314.09 | 5.79 | 17
August 2025 | 78 | Ministry of Coal | Coal | AMALGAMATED DHANKASA & JAMUNIA | Western Coalfields Limited [WCL] | 615185 | Madhya Pradesh | 09/2022 | 09/2022 | 03/2027 | - | 399.2 | 399.2 | 91.67 | 66
August 2025 | 79 | Ministry of Coal | Coal | RPR OF VISHNUPURI UG TO OC | Western Coalfields Limited [WCL] | 615187 | Madhya Pradesh | 11/2022 | 11/2022 | 03/2029 | - | 220.62 | 220.62 | 0 | 11
August 2025 | 80 | Ministry of Coal | Coal | URDHAN EXPANSION OC COST PLUS | Western Coalfields Limited [WCL] | 615194 | Madhya Pradesh | 07/2022 | 01/2023 | 03/2031 | - | 206.88 | 206.88 | 27.19 | 1
August 2025 | 81 | Ministry of Coal | Coal | SHARDA UG MINE | Western Coalfields Limited [WCL] | 615195 | Madhya Pradesh | 07/2023 | 09/2023 | 03/2028 | - | 166.25 | 166.25 | 3.96 | 9
August 2025 | 82 | Ministry of Coal | Coal | GANDHIGRAM UG MINE | Western Coalfields Limited [WCL] | 615206 | Madhya Pradesh | 08/2019 | 08/2019 | 03/2026 | - | 414.15 | 414.15 | 13.38 | 57
August 2025 | 83 | Ministry of Coal | Coal | BHATADI EXPANSION OC | Western Coalfields Limited [WCL] | 400033 | Maharashtra | 02/2020 | 05/2022 | 03/2028 | - | 580.61 | 580.61 | 69.73 | 26
August 2025 | 84 | Ministry of Coal | Coal | AMALGAMATED YEKONA I & YEKONA | Western Coalfields Limited [WCL] | 400177 | Maharashtra | 08/2015 | 08/2015 | 03/2025 | 03/2026 | 727.28 | 727.28 | 535.96 | 80
August 2025 | 85 | Ministry of Coal | Coal | DINESH[MAKARDHOKRA-III] OC | Western Coalfields Limited [WCL] | 400178 | Maharashtra | 02/2020 | 02/2020 | 03/2027 | - | 822.88 | 822.88 | 621.73 | 35
August 2025 | 86 | Ministry of Coal | Coal | DHUPTALA OC [SASTI UG TO OC ] | Western Coalfields Limited [WCL] | 400353 | Maharashtra | 10/2021 | 10/2021 | 03/2028 | - | 711.01 | 711.01 | 80.61 | 17
August 2025 | 87 | Ministry of Coal | Coal | SAONER UG MINE -1 EXPANSION 1. | Western Coalfields Limited [WCL] | 615184 | Maharashtra | 01/2022 | 01/2022 | 03/2028 | - | 228.64 | 228.64 | 141.21 | 68
August 2025 | 88 | Ministry of Coal | Coal | SASTI EXPANSION OPENCAST | Western Coalfields Limited [WCL] | 615186 | Maharashtra | 08/2020 | 08/2020 | 03/2026 | - | 319.04 | 319.04 | 90.31 | 20
August 2025 | 89 | Ministry of Coal | Coal | NEW MAJRI UG TO OC 3 MTY COST | Western Coalfields Limited [WCL] | 615188 | Maharashtra | 05/2019 | 09/2022 | 03/2027 | - | 402.27 | 402.27 | 55.44 | 24
August 2025 | 90 | Ministry of Coal | Coal | MAKARDHOKRA EXPN OC 4.9 MTY | Western Coalfields Limited [WCL] | 615189 | Maharashtra | 06/2022 | 06/2022 | 03/2026 | - | 361.87 | 361.87 | 70.22 | 12
August 2025 | 91 | Ministry of Coal | Coal | SINGHORI DEEP OC MIN 2.0 MTY | Western Coalfields Limited [WCL] | 615190 | Maharashtra | 05/2022 | 05/2022 | 03/2029 | - | 335.75 | 335.75 | 26.79 | 6
August 2025 | 92 | Ministry of Coal | Coal | GOKUL EXTENSION OC MINE | Western Coalfields Limited [WCL] | 615192 | Maharashtra | 04/2021 | 04/2021 | 03/2026 | - | 309.58 | 309.58 | 40.06 | 8
August 2025 | 93 | Ministry of Coal | Coal | KOLGAON EXPANSION DEEP OC MINE 0.80 MTY | Western Coalfields Limited [WCL] | 615199 | Maharashtra | 09/2023 | 09/2023 | 03/2027 | - | 198.71 | 198.71 | 0.71 | 3
August 2025 | 94 | Ministry of Coal | Coal | BALLARPUR NORTH WEST OC MINE | Western Coalfields Limited [WCL] | 615330 | Maharashtra | 12/2022 | 12/2022 | 03/2029 | - | 360.81 | 360.81 | 0.02 | 4
August 2025 | 95 | Ministry of Coal | Coal | GADEGAON OC 3 MTY | Western Coalfields Limited [WCL] | 615331 | Maharashtra | 10/2023 | 10/2023 | 03/2030 | - | 497.41 | 497.41 | 0.08 | 0
August 2025 | 96 | Ministry of Coal | Coal | GHONSA EXPANSION DEEP OC MINE | Western Coalfields Limited [WCL] | 615914 | Maharashtra | 03/2021 | 03/2021 | 03/2029 | - | 184.71 | 184.71 | 11.48 | 6
August 2025 | 97 | Ministry of Coal | Coal | AMLG GAURI PAUNI EXPANSION OC | Western Coalfields Limited [WCL] | 615916 | Maharashtra | 04/2024 | 04/2024 | 03/2030 | - | 1225.21 | 1225.21 | 78.87 | 1
August 2025 | 98 | Ministry of Coal | Coal | GAURIDEEP/GAURI CENTRAL OCP 7. | Western Coalfields Limited [WCL] | 615917 | Maharashtra | 06/2024 | 06/2024 | 03/2030 | - | 973.07 | 973.07 | 0.24 | 0
August 2025 | 99 | Ministry of Coal | Coal | RPR OF BHANEGAON OC | Western Coalfields Limited [WCL] | 615918 | Maharashtra | 02/2017 | 09/2022 | 03/2028 | - | 405.2 | 405.2 | 12.36 | 8
August 2025 | 100 | Ministry of Coal | Coal | N. EXTN. MUNGOLI NIRGUDA D OCP | Western Coalfields Limited [WCL] | 615919 | Maharashtra | 06/2024 | 06/2024 | 03/2030 | - | 1024.91 | 1024.91 | 168.59 | 0
August 2025 | 101 | Ministry of Coal | Coal | NILJAI EXPANSION DEEP OCP | Western Coalfields Limited [WCL] | 615982 | Maharashtra | 08/2016 | 08/2016 | 03/2022 | 03/2026 | 319.75 | 319.75 | 367.6 | 79
August 2025 | 102 | Ministry of Coal | Coal | UKNI DEEP OC MINE -COST PLUS | Western Coalfields Limited [WCL] | 616044 | Maharashtra | 01/2019 | 01/2019 | 03/2021 | 03/2026 | 237.06 | 237.06 | 165.57 | 87
August 2025 | 103 | Ministry of Coal | Coal | AMALGAMATED INDER-KAMPTEE DEEP OC | Western Coalfields Limited [WCL] | 616050 | Maharashtra | 09/2018 | 09/2018 | 03/2024 | 03/2026 | 235.9 | 235.9 | 237.12 | 98
August 2025 | 104 | Ministry of Coal | Coal | ADASA UG TO OC MINE | Western Coalfields Limited [WCL] | 616223 | Maharashtra | 11/2018 | 11/2018 | 03/2024 | 03/2026 | 316 | 316 | 308.84 | 86
August 2025 | 105 | Ministry of Coal | Coal | AMAL GONDEGAON GHATROHANA EXPN | Western Coalfields Limited [WCL] | 616229 | Maharashtra | 09/2024 | 09/2024 | 03/2030 | - | 668.54 | 668.54 | 1.18 | 0
August 2025 | 106 | Ministry of Coal | Coal | WAGHODA UG MINE [1.02 MTY] | Western Coalfields Limited [WCL] | 617233 | Maharashtra | 01/2024 | 01/2025 | 03/2030 | - | 379.3 | 379.3 | 0 | 0
August 2025 | 107 | Ministry of Coal | Coal | KOLARPIMPRI EXPANSION OC [2.5 MTY] | Western Coalfields Limited [WCL] | 617278 | Maharashtra | 06/2024 | 02/2025 | 03/2030 | - | 630.37 | 630.37 | 0 | 0
August 2025 | 108 | Ministry of Coal | Coal | Master Plan for Jharia and Raniganj Coalfields | Bharat Coking Coal Limited [BCCL] | 400313 | Multi-States (Jharkhand, West Bengal) | 08/2009 | 08/2009 | 08/2019 | 12/2028 | 2661.73 | 2661.73 | 788.85 | 43
August 2025 | 109 | Ministry of Coal | Coal | BINA KAKRI AMALGAMATION EXPANS | Northern Coalfields Limited [NCL] | 400369 | Multi-States (Madhya Pradesh, Uttar Pradesh) | 08/2020 | 08/2020 | 03/2024 | 03/2027 | 836.42 | 836.42 | 786.99 | 89
August 2025 | 110 | Ministry of Coal | Coal | KHADIA EXPANSION [10 TO 16 MTP | Northern Coalfields Limited [NCL] | 615183 | Multi-States (Madhya Pradesh, Uttar Pradesh) | 06/2021 | 06/2021 | 03/2025 | 03/2027 | 491.67 | 491.67 | 230.32 | 45
August 2025 | 111 | Ministry of Coal | Coal | SUBHADRA OCP | Mahanadi Coalfields Limited [MCL] | 400165 | Odisha | 05/2021 | 05/2021 | 04/2032 | - | 1693.81 | 1693.81 | 1321.15 | 42
August 2025 | 112 | Ministry of Coal | Coal | SIARMAL OCP | Mahanadi Coalfields Limited [MCL] | 400166 | Odisha | 02/2021 | 02/2021 | 03/2029 | - | 5194.95 | 5194.95 | 3456.05 | 55
August 2025 | 113 | Ministry of Coal | Coal | BALARAM EXPANSION OCP | Mahanadi Coalfields Limited (MCL | 400183 | Odisha | 06/2020 | 08/2020 | 03/2029 | - | 3504.21 | 3504.21 | 1028.92 | 52
August 2025 | 114 | Ministry of Coal | Coal | GOPALJI KANIHA OCP [10 TO 30 M | MCL - CIL | 400185 | Odisha | 04/2022 | 04/2022 | 03/2030 | - | 8416.19 | 6107.87 | 1708.88 | 17
August 2025 | 115 | Ministry of Coal | Coal | INTEGRATED LAKHANPUR-BELPAHAR- | Mahanadi Coalfields Limited [MCL] | 400187 | Odisha | 05/2018 | 05/2018 | 03/2027 | - | 2434.75 | 2434.75 | 1813.26 | 69
August 2025 | 116 | Ministry of Coal | Coal | BHARATPUR RE-ORGANIZATION OCP | Mahanadi Coalfields Limited (MCL | 400392 | Odisha | 11/2018 | 11/2018 | 03/2029 | - | 2838.86 | 2838.86 | 1748.41 | 47
August 2025 | 117 | Ministry of Coal | Coal | BASUNDHARA WEST EXTENSION OPEN | MCL - CIL | 615193 | Odisha | 05/2014 | 05/2014 | 03/2019 | 03/2029 | 479.15 | 479.15 | 281.01 | 64
August 2025 | 118 | Ministry of Coal | Coal | Naini Coal Mine | Singareni Collieries Company Limited [SCCL] | 615857 | Odisha | 03/2020 | 03/2020 | 03/2026 | - | 494.3 | 494.3 | 491.33 | 80
August 2025 | 119 | Ministry of Coal | Coal | INTEGRATED KULDA GARJANBAHAL O | Mahanadi Coalfields Limited (MCL | 616226 | Odisha | 04/2023 | 04/2023 | 03/2033 | - | 3563.5 | 3563.5 | 540.62 | 4
August 2025 | 120 | Ministry of Coal | Coal | BHUBANESWARI EXPN OCP 50 MTY | MCL - CIL | 616231 | Odisha | 03/2024 | 03/2024 | 03/2033 | - | 5366.27 | 5366.27 | 465.31 | 14
August 2025 | 121 | Ministry of Coal | Coal | HINGULA II OC EXPN PH III 15 M | MCL - CIL | 616232 | Odisha | 11/2022 | 11/2022 | 03/2029 | - | 1561.85 | 1561.85 | 269.61 | 23
August 2025 | 122 | Ministry of Coal | Coal | BALABHADRA OCP | MCL - CIL | 616233 | Odisha | 04/2023 | 04/2023 | 03/2030 | - | 978.44 | 978.44 | 211.37 | 11
August 2025 | 123 | Ministry of Coal | Coal | Jawahar Khani Open Cast Mine | Singareni Collieries Company Limited [SCCL] | 615818 | Telangana | 12/2021 | 12/2021 | 03/2025 | 03/2027 | 297.88 | 297.88 | 46.39 | 20
August 2025 | 124 | Ministry of Coal | Coal | Kalyanikhani Opencast Project | Singareni Collieries Company Limited [SCCL] | 615858 | Telangana | 03/2016 | 05/2017 | 03/2026 | - | 384.32 | 384.32 | 281.83 | 75
August 2025 | 125 | Ministry of Coal | Coal | Kakathiya Khani Opencast - III Project Phase - I | Singareni Collieries Company Limited [SCCL] | 615859 | Telangana | 03/2017 | 05/2017 | 03/2026 | - | 413.84 | 413.84 | 397.55 | 79
August 2025 | 126 | Ministry of Coal | Coal | Godavarikhani Coal Mine - 5 | Singareni Collieries Company Limited [SCCL] | 615860 | Telangana | 07/2019 | 05/2019 | 03/2025 | 03/2026 | 607.04 | 607.04 | 188.15 | 71
August 2025 | 127 | Ministry of Coal | Coal | Indaram Opencast Project | Singareni Collieries Company Limited [SCCL] | 615861 | Telangana | 08/2017 | 12/2022 | 03/2025 | 03/2026 | 424.81 | 424.81 | 402.64 | 80
August 2025 | 128 | Ministry of Coal | Coal | Goleti Opencast Mine | Singareni Collieries Company Limited [SCCL] | 615862 | Telangana | 07/2021 | 08/2021 | 03/2026 | - | 345.6 | 345.6 | 74.59 | 20
August 2025 | 129 | Ministry of Coal | Coal | Venkatesh Khani Coal Mine | Singareni Collieries Company Limited [SCCL] | 615863 | Telangana | 10/2020 | 06/2020 | 03/2026 | - | 484.5 | 484.5 | 460.67 | 95
August 2025 | 130 | Ministry of Coal | Coal | Ramagundam OC-II Extension Project | Singareni Collieries Company Limited [SCCL] | 615864 | Telangana | 11/2015 | 06/2015 | 03/2026 | - | 489.62 | 489.62 | 405.54 | 77
August 2025 | 131 | Ministry of Coal | Coal | Kakatiyakhani OC - 2 Project | Singareni Collieries Company Limited [SCCL] | 615865 | Telangana | 08/2017 | 09/2017 | 03/2025 | 03/2026 | 442.42 | 442.42 | 205 | 63
August 2025 | 132 | Ministry of Coal | Coal | MOHANPUR EXPANSION OC -PHASE II | Eastern Coal Fields Limited [ECL] | 400173 | West Bengal | 11/2020 | 11/2020 | 03/2026 | - | 888.99 | 888.99 | 93 | 30
August 2025 | 133 | Ministry of Coal | Coal | BONJEMEHARI EXPANSION OCP | Eastern Coal Fields Limited [ECL] | 400180 | West Bengal | 08/2021 | 08/2021 | 03/2026 | 03/2026 | 570.11 | 570.11 | 81.95 | 16
August 2025 | 134 | Ministry of Coal | Coal | NAKRAKONDA KUMARDIH- B OCP | Eastern Coal Fields Limited [ECL] | 400181 | West Bengal | 08/2018 | 08/2018 | 03/2029 | - | 502.68 | 502.67 | 67.61 | 26
August 2025 | 135 | Ministry of Coal | Coal | SIDULI [OC & UG] | ECL - CIL | 400182 | West Bengal | 05/2018 | 05/2018 | 03/2027 | - | 535.18 | 535.17 | 5.05 | 14
August 2025 | 136 | Ministry of Coal | Coal | TILABONI UG | Eastern Coal Fields Limited [ECL] | 400186 | West Bengal | 01/2023 | 03/2023 | 03/2029 | 03/2029 | 749.08 | 749.08 | 52.18 | 10
August 2025 | 137 | Ministry of Coal | Coal | JHANJRA EXPANSION UG | Eastern Coal Fields Limited [ECL] | 400312 | West Bengal | 04/2020 | 04/2020 | 03/2029 | - | 1210.12 | 1210.12 | 527.67 | 41
August 2025 | 138 | Ministry of Coal | Coal | SONEPUR BAZARI EXPANSION OCP [12 MTY] | Eastern Coal Fields Limited [ECL] | 400315 | West Bengal | 07/2021 | 07/2021 | 03/2029 | - | 5365.88 | 5365.88 | 565.26 | 17
August 2025 | 139 | Ministry of Coal | Coal | 2.0 MTPA BHOJUDIH NLW WASHERY | Ministry of Coal | 611016 | West Bengal | 12/2015 | 03/2019 | 09/2020 | 10/2025 | 384.57 | 384.57 | 353.21 | 97
August 2025 | 140 | Ministry of Coal | Coal | ITAPARA OCP | Eastern Coal Fields Limited [ECL] | 612816 | West Bengal | 12/2023 | 12/2023 | 03/2030 | - | 929.1 | 929.1 | 67.6 | 7
August 2025 | 141 | Ministry of Coal | Coal | SHYAMSUNDARPUR UG INCLUDING SA | Eastern Coal Fields Limited [ECL] | 613793 | West Bengal | 04/2020 | 04/2020 | 03/2026 | - | 483.65 | 483.65 | 59.04 | 12
August 2025 | 142 | Ministry of Coal | Coal | PARASEA-BELBAID UG PROJECT | Eastern Coal Fields Limited [ECL] | 613794 | West Bengal | 01/2023 | 01/2023 | 03/2028 | - | 389.1 | 389.1 | 131.42 | 17
August 2025 | 143 | Ministry of Coal | Coal | PARASCOLE JAMBAD OCP | Eastern Coal Fields Limited [ECL] | 616230 | West Bengal | 11/2024 | 11/2024 | 03/2037 | - | 1193.55 | 1193.55 | 9.46 | 0
August 2025 | 144 | Ministry of Coal | Electricity Generation | 50 MW Wind Power Project | NLC India Limited [NLCIL] | 617299 | Gujarat | 07/2022 | 02/2024 | 06/2025 | 01/2026 | 383.84 | 383.84 | 303.5 | 41
August 2025 | 145 | Ministry of Coal | Electricity Generation | NLC Talabira Thermal Power Project | NLC India Limited [NLCIL] | 400231 | Odisha | NA | 01/2024 | 03/2030 | - | 27212.96 | 27213 | 1953.52 | 1
August 2025 | 146 | Ministry of Coal | Electricity Generation | 300 MW SPP part of 510 MW CPSU scheme | NLC India Limited [NLCIL] | 612819 | Rajasthan | NA | 03/2023 | 09/2024 | 09/2025 | 1813 | 1813 | 874.14 | 70
August 2025 | 147 | Ministry of Coal | Electricity Generation | 50 MW Solar PP Minedout Area | NLC India Limited [NLCIL] | 615327 | Tamil Nadu | NA | 02/2024 | 03/2025 | 09/2025 | 218.03 | 218.03 | 161.73 | 50
August 2025 | 148 | Ministry of Coal | Electricity Generation | Ghatampur Thermal Power Plant 3 X 660 MW | NLC India Limited [NLCIL] | 400259 | Uttar Pradesh | NA | 08/2016 | 11/2020 | 10/2025 | 17237.8 | 21780.9 | 20269.54 | 92
August 2025 | 149 | Ministry of Coal | Railways | Dharamjaigarh-Korba | Railway | 400203 | Chhattisgarh | 05/2018 | 03/2017 | 12/2026 | 08/2026 | 1686.22 | 1686.22 | 347.96 | 41
August 2025 | 150 | Ministry of Coal | Railways | Shivpur-Kathautia New Rail [BG] Line [49 km] [Package II of Tori-Shivpur-Kathautia line] | Ministry of Coal | 400416 | Jharkhand | 02/2018 | 05/2022 | 06/2025 | - | 1799.64 | 1799.64 | 1293.71 | 60
August 2025 | 151 | Ministry of Power | Coal | Tubed Coal Mine | Damodar Valley Corporation | 400192 | Jharkhand | NA | 10/2016 | 05/2026 | 05/2026 | 1581 | 1581 | 596.94 | 34
August 2025 | 152 | Ministry of Power | Coal | Badam Coal Mining project of NTPC | National Thermal Power Corporation [NTPC] | 603293 | Jharkhand | 02/2019 | 09/2019 | 12/2056 | 04/2027 | 502 | 784 | 313.88 | 59
August 2025 | 153 | Ministry of Power | Electricity Generation | Dibang Multipurpose Project | National Highways & Infrastructure Development Corporation Ltd. [NHIDCL] | 602182 | Arunachal Pradesh | 02/2023 | 02/2023 | 02/2032 | 02/2032 | 31876.39 | 31876.4 | 3553.9 | 16
August 2025 | 154 | Ministry of Power | Electricity Generation | 240MW Heo HE Project | North Eastern Electric Power Corporation Limited | 611698 | Arunachal Pradesh | 12/2024 | 05/2025 | 07/2029 | - | 1938.85 | 1938.85 | 49.31 | 3
August 2025 | 155 | Ministry of Power | Electricity Generation | 186 MW Tato-I H E Project | North Eastern Electric Power Corporation Limited | 611699 | Arunachal Pradesh | 12/2024 | 05/2025 | 07/2029 | - | 1750.07 | 1750.07 | 102.79 | 2
August 2025 | 156 | Ministry of Power | Electricity Generation | Buxar Thermal Power Project [1320 MW] | Satluj Jal Vidyut Nigam [SJVN] Thermal Limited | 602579 | Bihar | 03/2019 | 06/2019 | 01/2024 | 12/2025 | 10439.09 | 13756.6 | 12148.46 | 92
August 2025 | 157 | Ministry of Power | Electricity Generation | Lara Super Thermal Power Project Stage-II [2 x 800 MW] | National Thermal Power Corporation [NTPC] | 611930 | Chhattisgarh | 08/2023 | 08/2023 | 06/2028 | - | 15530 | 15530 | 2480 | 16
August 2025 | 158 | Ministry of Power | Electricity Generation | Sipat Super Thermal Power Project, Stage-III [1x800 MW] | National Thermal Power Corporation [NTPC] | 617188 | Chhattisgarh | 09/2024 | 09/2024 | 09/2029 | - | 9791 | 9791 | 0 | 0
August 2025 | 159 | Ministry of Power | Electricity Generation | Bagodara Solar Power Project | Satluj Jal Vidyut Nigam [SJVN] Thermal Limited | 709747 | Gujarat | 03/2021 | 05/2021 | 12/2025 | 12/2025 | 339.35 | 339.35 | 317.59 | 51
August 2025 | 160 | Ministry of Power | Electricity Generation | Dhaulasidh Hydro Electric Project [66 MW] | Satluj Jal Vidyut Nigam [SJVN] Thermal Limited | 602582 | Himachal Pradesh | 10/2020 | 05/2021 | 11/2025 | 03/2027 | 687.97 | 1511.87 | 927.3 | 68
August 2025 | 161 | Ministry of Power | Electricity Generation | Luhri Stage-I Hydro Electric Project [210 MW] | Satluj Jal Vidyut Nigam [SJVN] Thermal Limited | 602593 | Himachal Pradesh | 11/2020 | 11/2020 | 01/2026 | 10/2029 | 1810.56 | 3584.53 | 1751.6 | 51
August 2025 | 162 | Ministry of Power | Electricity Generation | 382 MW Sunni Dam HEP | Satluj Jal Vidyut Nigam [SJVN] Thermal Limited | 602633 | Himachal Pradesh | NA | 04/2018 | 03/2027 | - | 2615 | 2615 | 495.57 | 0.5
August 2025 | 163 | Ministry of Power | Electricity Generation | Sunni Dam Hydro Electric Project [382 MW] | Satluj Jal Vidyut Nigam [SJVN] Thermal Limited | 611586 | Himachal Pradesh | 01/2023 | 01/2023 | 04/2028 | 12/2029 | 2614.51 | 4540.71 | 962.66 | 29
August 2025 | 164 | Ministry of Power | Electricity Generation | Pakal Dul [Drangdhuran] Hydroelectric Project, 1000 MW | National Highways & Infrastructure Development Corporation Ltd. [NHIDCL] | 602525 | Jammu and Kashmir | 10/2014 | 02/2018 | 04/2020 | 12/2026 | 8112.12 | 12728 | 7238.73 | 72
August 2025 | 165 | Ministry of Power | Electricity Generation | Kiru HE Project | National Highways & Infrastructure Development Corporation Ltd. [NHIDCL] | 602532 | Jammu and Kashmir | 03/2019 | 03/2019 | 09/2023 | 12/2026 | 4287.59 | 5409 | 3157.49 | 68
August 2025 | 166 | Ministry of Power | Electricity Generation | Ratle HE Project - 850 MW, Ratle Hydroelectric Power Corporation Limited. | National Highways & Infrastructure Development Corporation Ltd. [NHIDCL] | 602535 | Jammu and Kashmir | 02/2021 | 02/2021 | 02/2026 | 08/2029 | 5281.94 | 5281.94 | 1009.79 | 24
August 2025 | 167 | Ministry of Power | Electricity Generation | Kwar HE Project | National Highways & Infrastructure Development Corporation Ltd. [NHIDCL] | 605155 | Jammu and Kashmir | 05/2022 | 05/2022 | 11/2026 | 03/2028 | 4526.12 | 4526.12 | 1119.59 | 23
August 2025 | 168 | Ministry of Power | Electricity Generation | Patratu Thermal Power Station Expansion Project Phase-I [3x800 MW] | National Thermal Power Corporation [NTPC] | 400261 | Jharkhand | 11/2017 | 11/2017 | 03/2023 | 11/2026 | 17112 | 20302 | 17475 | 85
August 2025 | 169 | Ministry of Power | Electricity Generation | Koderma Thermal Power Station Phase II [2X800 MW] At Koderma, Jharkhand | Damodar Valley Corporation | 611509 | Jharkhand | NA | 11/2024 | 03/2029 | - | 14358 | 14358 | 1131.57 | 3
August 2025 | 170 | Ministry of Power | Electricity Generation | Subansiri Lower HE Project [2000 MW] | National Highways & Infrastructure Development Corporation Ltd. [NHIDCL] | 602096 | Multi-States (Arunachal Pradesh, Assam) | 09/2003 | 09/2003 | 09/2010 | 05/2026 | 6285.33 | 26075.5 | 24880.95 | 96
August 2025 | 171 | Ministry of Power | Electricity Generation | Talcher Thermal Power Station Stage III [2 x 660 MW] Expansion | National Thermal Power Corporation [NTPC] | 602961 | Odisha | 08/2022 | 09/2022 | 05/2027 | 03/2028 | 11843.75 | 12543 | 4161.68 | 32
August 2025 | 172 | Ministry of Power | Electricity Generation | BIKANER SOLAR POWER PROJECT | Satluj Jal Vidyut Nigam [SJVN] Thermal Limited | 709748 | Rajasthan | 10/2021 | 05/2022 | 04/2024 | 12/2025 | 5491.89 | 5491.89 | 4805.16 | 84
August 2025 | 173 | Ministry of Power | Electricity Generation | TEESTA-VI HE PROJECT, SIKKIM [500 MW], executed by LANCO TEESTA HYDRO POWER LIMITED [A wholly owned Subsidiary of NHPC LTD. acquired through NCLT] | National Highways & Infrastructure Development Corporation Ltd. [NHIDCL] | 602181 | Sikkim | 03/2019 | 03/2019 | 03/2024 | 12/2027 | 5748.04 | 5748.04 | 4576.93 | 69
August 2025 | 174 | Ministry of Power | Electricity Generation | Rangit-IV HE Project [120 MW] executed by Jal Power Corporation Ltd. [JPCL] -A wholly owned subsidiary of NHPC Ltd. acquired through NCLT | National Highways & Infrastructure Development Corporation Ltd. [NHIDCL] | 605156 | Sikkim | 03/2021 | 03/2021 | 05/2024 | 12/2025 | 938.29 | 1828.11 | 1584.13 | 91
August 2025 | 175 | Ministry of Power | Electricity Generation | Khurja super Thermal Power Plant [2X660 MW] | THDC India Limited | 602194 | Uttar Pradesh | 03/2019 | 08/2019 | 02/2024 | 09/2025 | 11089.42 | 13276.2 | 12772.21 | 97
August 2025 | 176 | Ministry of Power | Electricity Generation | Singrauli Super Thermal Power Project, Stage-III [2x800 MW] | National Thermal Power Corporation [NTPC] | 612142 | Uttar Pradesh | 03/2024 | 03/2024 | 02/2030 | - | 17195 | 17195 | 1739 | 9
August 2025 | 177 | Ministry of Power | Electricity Generation | Tapovan-Vishnugad HEP [4x130 MW] | National Thermal Power Corporation [NTPC] | 602185 | Uttarakhand | NA | 11/2006 | 03/2013 | 04/2029 | 2978 | 10907.3 | 7195.58 | 77
August 2025 | 178 | Ministry of Power | Electricity Generation | Tehri Pumped Storage Plant Project [4x250 MW] | THDC India Limited | 602193 | Uttarakhand | 07/2006 | 06/2011 | 06/2022 | 11/2025 | 4825.6 | 8339 | 8064.9 | 98
August 2025 | 179 | Ministry of Power | Electricity Generation | Vishnugad Pipalkoti Hydro Electric Project [444 MW] | THDC India Limited | 602195 | Uttarakhand | 08/2008 | 01/2014 | 12/2022 | 03/2027 | 3860.35 | 6823.72 | 5101.06 | 72
August 2025 | 180 | Ministry of Power | Electricity Generation | Raghunathpur Thermal Power Station Phase II [2X660 MW] at Raghunathpur, Purulia, West Bengal | Damodar Valley Corporation | 400062 | West Bengal | NA | 02/2025 | 06/2029 | - | 17673 | 17673 | 1192.71 | 1
August 2025 | 181 | Ministry of Power | Electricity Generation | Rammam-III HEPP [3x40 MW] | National Thermal Power Corporation [NTPC] | 602184 | West Bengal | 09/2024 | 09/2014 | 09/2019 | 03/2029 | 1381.84 | 1381.84 | 1281.85 | 47
August 2025 | 182 | Ministry of Power | Electricity Generation | Installation of FGD for 4x210 & 2x250 MW MTPS U 1-6 | Damodar Valley Corporation | 602538 | West Bengal | NA | 02/2021 | 01/2024 | 12/2025 | 1037 | 1106 | 1092.27 | 92
August 2025 | 183 | Ministry of Power | Transmission & Distribution | Transmission Scheme for Solar Energy Zone in Ananthpuram 2500MW and Kurnool 1000MW | Power Grid Corporation of India Limited [POWERGRID] | 611967 | Andhra Pradesh | 09/2023 | 09/2023 | 09/2025 | 04/2026 | 1248.69 | 1248.69 | 860.97 | 82
August 2025 | 184 | Ministry of Power | Transmission & Distribution | Augmentation of 1x1500 MVA 3rd 765/400 kV transformation capacity at Kurnool New Substation | Power Grid Corporation of India Limited [POWERGRID] | 612856 | Andhra Pradesh | 05/2023 | 12/2023 | 09/2025 | 11/2025 | 163.61 | 163.61 | 60.53 | 42
August 2025 | 185 | Ministry of Power | Transmission & Distribution | Transmission system strengthening at Kurnool- III PS for integration of additional RE generation projects [POWERGRID Kurnool III PS RE Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 617183 | Andhra Pradesh | 03/2025 | 03/2025 | 12/2027 | - | 2886 | 2886 | 117.86 | 0
August 2025 | 186 | Ministry of Power | Transmission & Distribution | Western Region Expansion Scheme-XXV | Power Grid Corporation of India Limited [POWERGRID] | 611737 | Chhattisgarh | 02/2023 | 02/2023 | 11/2023 | 12/2025 | 385.84 | 385.84 | 378.17 | 97
August 2025 | 187 | Ministry of Power | Transmission & Distribution | Transmission system strengthening scheme for evacuation of power from solar energy zones in Rajasthan 8.1 GW under Phase II- Part- G1 | Power Grid Corporation of India Limited [POWERGRID] | 608301 | Delhi | 02/2022 | 02/2022 | 09/2023 | 11/2025 | 359.47 | 359.47 | 330.91 | 93
August 2025 | 188 | Ministry of Power | Transmission & Distribution | Transmission scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase II- Part B | Power Grid Corporation of India Limited [POWERGRID] | 611656 | Gujarat | 03/2023 | 03/2023 | 03/2025 | 10/2025 | 1167.55 | 1167 | 1050.41 | 93
August 2025 | 189 | Ministry of Power | Transmission & Distribution | Transmission scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase II- Part C | Power Grid Corporation of India Limited [POWERGRID] | 611657 | Gujarat | 03/2023 | 03/2023 | 03/2025 | 11/2025 | 2820.99 | 2820.99 | 2570.25 | 84
August 2025 | 190 | Ministry of Power | Transmission & Distribution | Establishment of Khavda Pooling Station-2 KPS2 in Khavda RE Park KPS2 TRANSMISSION SYSTEM LIMITED | Power Grid Corporation of India Limited [POWERGRID] | 611660 | Gujarat | 03/2023 | 03/2023 | 12/2024 | 10/2025 | 966.79 | 966.79 | 904.52 | 95
August 2025 | 191 | Ministry of Power | Transmission & Distribution | Transmission system for Evacuation of Additional 7 GW RE power from Khavda RE park under Phase-III Part B [Vataman Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 612139 | Gujarat | 12/2023 | 12/2023 | 12/2025 | 06/2026 | 3751.82 | 3751.82 | 1575.72 | 22
August 2025 | 192 | Ministry of Power | Transmission & Distribution | Transmission System for Evacuation of Power from potential Renewable Energy zone in Khavda Area of Gujarat under Phase IV [7 GW] Part E3 | Power Grid Corporation of India Limited [POWERGRID] | 612151 | Gujarat | 07/2023 | 07/2023 | 07/2025 | 12/2025 | 334 | 334 | 73.48 | 30
August 2025 | 193 | Ministry of Power | Transmission & Distribution | Transmission System for Evacuation of Power from Potential Energy Renewable Zone in Khavda Area of Gujarat under Ph-IV [7GW] Part E2 | Power Grid Corporation of India Limited [POWERGRID] | 612855 | Gujarat | 05/2024 | 05/2024 | 05/2026 | 02/2026 | 679 | 679 | 97.23 | 19
August 2025 | 194 | Ministry of Power | Transmission & Distribution | Augmentation of Transformation Capacity at jam Khambhaliya PS [GIS] [SPV Name POWERGRID Jam Khambhaliya Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 615342 | Gujarat | 10/2024 | 10/2024 | 07/2026 | - | 329 | 329 | 10.07 | 1
August 2025 | 195 | Ministry of Power | Transmission & Distribution | Provision of Dynamic Reactive Compensation at Khavda pooling Station 1 [KPS1] and Khavda Pooling station 3 [KPS3] | Power Grid Corporation of India Limited [POWERGRID] | 615343 | Gujarat | 11/2024 | 11/2024 | 11/2026 | - | 501 | 501 | 6.01 | 1
August 2025 | 196 | Ministry of Power | Transmission & Distribution | Transmission System for Evacuation of Power from Potential Renewable Energy Zone in Khavda area of Gujarat under Phase-IV [7GW] Part B [SPV Name POWERGRID South Olpad Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 615345 | Gujarat | 10/2024 | 10/2024 | 10/2026 | - | 4766 | 4766 | 564.77 | 7
August 2025 | 197 | Ministry of Power | Transmission & Distribution | Augmentation of Transformation Capacity at KPS1 [GIS] and KPS2 [GIS] [Phase-V Part B1 and Part B2 Scheme] [SPV Name- POWERGRID KPS1 and 2 Augmentation Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 617069 | Gujarat | 02/2025 | 02/2025 | 02/2027 | - | 466 | 466 | 13.99 | 1
August 2025 | 198 | Ministry of Power | Transmission & Distribution | Augmentation of Banaskantha [Raghanesda] PS [GIS] [POWERGRID Banaskantha Transco Limited] | Power Grid Corporation of India Limited [POWERGRID] | 617182 | Gujarat | 03/2025 | 03/2025 | 03/2027 | - | 172 | 172 | 7.27 | 3
August 2025 | 199 | Ministry of Power | Transmission & Distribution | Implementation of LILO of both circuits of 400KV vindhyachal PS-Sasan D/C Line at Hindalco Switchyard | Power Grid Corporation of India Limited [POWERGRID] | 617272 | Haryana | 06/2024 | 06/2024 | 12/2026 | - | 370 | 370 | 3.7 | 1
August 2025 | 200 | Ministry of Power | Transmission & Distribution | Transmission system for evacuation of Power from Pakaldul HEP in Chenab Valley HEPs - LTA System | Power Grid Corporation of India Limited [POWERGRID] | 608302 | Jammu and Kashmir | 02/2022 | 02/2022 | 04/2025 | 09/2025 | 318.12 | 318.12 | 287.31 | 99
August 2025 | 201 | Ministry of Power | Transmission & Distribution | Transmission Scheme for evacuation of Power from Ratle HEP [850 MW] & kiru [624 MW] Part B | Power Grid Corporation of India Limited [POWERGRID] | 617179 | Jammu and Kashmir | 07/2024 | 07/2024 | 07/2026 | - | 218.6 | 218.6 | 1.01 | 0
August 2025 | 202 | Ministry of Power | Transmission & Distribution | Transmission Scheme for Integration of Renewable Energy Zone [Phase II] in Koppal II [Phase A&B] and gadag II[Phase A] in Karnataka [POWERGRID KOPPAL GADAG TRANSMISSION LIMITED] | Power Grid Corporation of India Limited [POWERGRID] | 612140 | Karnataka | 12/2023 | 12/2023 | 12/2025 | 03/2026 | 2889.39 | 2889.39 | 1332.21 | 46
August 2025 | 203 | Ministry of Power | Transmission & Distribution | System Strengthening at Koppal-II and GadagII for integration of RE generation projects [SPV Name POWERGRID Koppal Gadag Augmentation Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 616672 | Karnataka | 01/2025 | 01/2025 | 06/2027 | - | 1354 | 1354 | 17.73 | 0
August 2025 | 204 | Ministry of Power | Transmission & Distribution | Augmentation of Transformation Capacity by 3x500 MVA, 400/220 KV ICTS [6th-8th] and 1x1500 MVA, 765/400 KV ICT [4th] at Bidar PS [SPV Name- POWERGRID Bidar Augmentation Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 617068 | Karnataka | 02/2025 | 02/2025 | 06/2027 | - | 288 | 288 | 6.79 | 0
August 2025 | 205 | Ministry of Power | Transmission & Distribution | Transmission Scheme for integration of Davanagere/ Chitradurga and Bellary REZ in Karnataka [POWERGRID Chitradurga Bellary REZ Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 617184 | Karnataka | 03/2025 | 03/2025 | 09/2027 | - | 3453 | 3453 | 33.14 | 0
August 2025 | 206 | Ministry of Power | Transmission & Distribution | Transmission System for Evacuation of Power from Rajasthan REZ Ph-IV [Part-2 5.5GW] [Jaisalmer/Barmer Complex] Part H1 [POWERGRID KURAWAR TRANSMISSION LIMITED] | Power Grid Corporation of India Limited [POWERGRID] | 615344 | Madhya Pradesh | 10/2024 | 10/2024 | 10/2026 | - | 3674 | 3674 | 495.18 | 14
August 2025 | 207 | Ministry of Power | Transmission & Distribution | Transmission System for Evacuation of Power from Rajasthan REZ Ph-IV [Part-2 5.5 GW] [Jaisalmer/Barmer Complex] Part C [SPV Name POWERGRID Mandsaur Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 615346 | Madhya Pradesh | 08/2024 | 08/2024 | 08/2026 | - | 2708 | 2708 | 812.4 | 35
August 2025 | 208 | Ministry of Power | Transmission & Distribution | Transmission System for evacuation of power from Mahan Energen Limited Generating Station in Madhya Pradesh [SPV Name - POWERGRID MEL Power Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 617279 | Madhya Pradesh | 06/2025 | 06/2025 | 12/2027 | - | 558 | 558 | 16.74 | 0
August 2025 | 209 | Ministry of Power | Transmission & Distribution | Transmission System for Evacuation of power from Potential RE Zone in Khavda Area of Gujarat under phase IV 7GW-Part E4 | Power Grid Corporation of India Limited [POWERGRID] | 611966 | Maharashtra | 11/2023 | 11/2023 | 07/2025 | 12/2025 | 224.41 | 224.41 | 24.64 | 10
August 2025 | 210 | Ministry of Power | Transmission & Distribution | Transmission System for Integration of Kurnool-IV REZ Phase-I [for 4.5 GW] [POWERGRID Kurnool-IV Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 617185 | Multi-States (Andhra Pradesh, Karnataka) | 03/2025 | 03/2025 | 03/2027 | - | 5550 | 5550 | 281 | 0
August 2025 | 211 | Ministry of Power | Transmission & Distribution | Transmission System for Kurnool Wind Energy Zone/ Solar Energy Zone Part-A and Part-B | Power Grid Corporation of India Limited [POWERGRID] | 900808 | Multi-States (Andhra Pradesh, Telangana) | 11/2022 | 03/2023 | 11/2024 | 12/2025 | 3546.94 | 3546.94 | 3192.25 | 95
August 2025 | 212 | Ministry of Power | Transmission & Distribution | Comprehensive Scheme for Strengthening of Transmission and Distribution [T&D] Systems [CSST&DS] in Arunachal Pradesh and Sikkim | Power Grid Corporation of India Limited [POWERGRID] | 602223 | Multi-States (Arunachal Pradesh, Sikkim) | 03/2021 | 01/2016 | 12/2018 | 03/2027 | 4754.42 | 9129.32 | 7462.2 | 81
August 2025 | 213 | Ministry of Power | Transmission & Distribution | NORTH EASTERN REGION POWER SYSTEM IMPROVEMENT PROJECT [NERPSIP] | Power Grid Corporation of India Limited [POWERGRID] | 607709 | Multi-States (Assam, Manipur, Meghalaya, Mizoram, Nagaland, Tripura) | 12/2014 | 03/2016 | 12/2018 | 12/2025 | 5111.33 | 6700 | 5277.24 | 96
August 2025 | 214 | Ministry of Power | Transmission & Distribution | Eastern Region Expansion Scheme-43 [ERES-43] | Power Grid Corporation of India Limited [POWERGRID] | 617271 | Multi-States (Bihar, Odisha, West Bengal) | 09/2024 | 09/2024 | 03/2026 | - | 342.69 | 342.69 | 0.6 | 0
August 2025 | 215 | Ministry of Power | Transmission & Distribution | Eastern Region Expansion Scheme-44 [ERES-44] | Power Grid Corporation of India Limited [POWERGRID] | 617270 | Multi-States (Bihar, West Bengal) | 11/2024 | 11/2024 | 05/2026 | - | 408.94 | 408.94 | 0.3 | 0
August 2025 | 216 | Ministry of Power | Transmission & Distribution | Transmission Network Expansion in Gujarat to increase its ATC from ISTS Part B | Power Grid Corporation of India Limited [POWERGRID] | 400005 | Multi-States (Dadra & Nagar Haveli and Daman & Diu, Gujarat, Maharashtra) | 01/2022 | 07/2022 | 06/2023 | 12/2025 | 4546.26 | 4546.26 | 4172.96 | 93
August 2025 | 217 | Ministry of Power | Transmission & Distribution | Transmission System Strengthening Scheme for evacuation of power from SEZ in Rajasthan 8.1 GW under Phase II Part G | Power Grid Corporation of India Limited [POWERGRID] | 608922 | Multi-States (Delhi, Haryana, Rajasthan) | 05/2022 | 05/2022 | 11/2023 | 11/2025 | 1666 | 2218 | 2129.28 | 95
August 2025 | 218 | Ministry of Power | Transmission & Distribution | Transmission system for evacuation of power from REZ in Rajasthan 20GW under Phase-III Part J | Power Grid Corporation of India Limited [POWERGRID] | 611735 | Multi-States (Delhi, Rajasthan) | 12/2022 | 12/2022 | 03/2025 | 04/2026 | 331 | 331 | 82.72 | 29
August 2025 | 219 | Ministry of Power | Transmission & Distribution | Transmission Scheme for Evacuation of power from REZ in Rajasthan [20 GW] under Phase-III Part D [Sikar Khetri Transmission Ltd] | Power Grid Corporation of India Limited [POWERGRID] | 612132 | Multi-States (Delhi, Rajasthan) | 02/2024 | 02/2024 | 08/2025 | 05/2026 | 2000 | 2000 | 1380.2 | 62
August 2025 | 220 | Ministry of Power | Transmission & Distribution | TRANSMISSION SYSTEM FOR EVACUATION OF POWER FROM POTENTIAL RENEWABLE ENERGY ZONE IN KHAVDA AREA OF GUJARAT UNDER PHASE-V [8 GW] PART A [SPV Name POWERGRID West Central Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 615347 | Multi-States (Gujarat, Maharashtra) | 11/2024 | 11/2024 | 05/2029 | - | 24819 | 24819 | 1796.14 | 1
August 2025 | 221 | Ministry of Power | Transmission & Distribution | Transmission system for evacuation of power from Rajasthan REZ Ph-IV [Part- 3/6GW] [Bikaner complex] Part A [SPV Name POWERGRID Bikaner IV Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 615339 | Multi-States (Haryana, Punjab, Rajasthan) | 11/2024 | 11/2024 | 11/2026 | - | 5969 | 5969 | 218.47 | 5
August 2025 | 222 | Ministry of Power | Transmission & Distribution | TRANSMISSION SYSTEM FOR EVACUATION OF POWER FROM RAJASTHAN REZ PH-IV [PART-3/ 6 GW] [BIKANER COMPLEX] PART B [SPV Name POWERGRID Siwani Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 615340 | Multi-States (Haryana, Rajasthan) | 11/2024 | 11/2024 | 11/2026 | - | 5357 | 5357 | 267.85 | 9
August 2025 | 223 | Ministry of Power | Transmission & Distribution | Transmission System for Strengthening of Srinagar-Leh Tr. System | Power Grid Corporation of India Limited [POWERGRID] | 606781 | Multi-States (Jammu and Kashmir, Ladakh) | 03/2022 | 03/2022 | 12/2024 | 10/2025 | 288.71 | 288.71 | 207.8 | 75
August 2025 | 224 | Ministry of Power | Transmission & Distribution | Transmission Scheme for Solar Energy Zone in Bidar [2500 MW], Karnataka [Bidar Transmission Ltd] | Power Grid Corporation of India Limited [POWERGRID] | 612138 | Multi-States (Karnataka, Telangana) | 02/2024 | 02/2024 | 02/2026 | - | 2147.62 | 2147.62 | 1144.89 | 61
August 2025 | 225 | Ministry of Power | Transmission & Distribution | Transmission System for Evacuation of Power from Rajasthan REZ Ph-IV [Part-2 5.5 GW] [Jaisalmer/Barmer Complex] Part D [SPV Name POWERGRID Beawar Mandsaur Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 615333 | Multi-States (Madhya Pradesh, Rajasthan) | 08/2024 | 08/2024 | 08/2026 | - | 2227 | 2227 | 622.89 | 20
August 2025 | 226 | Ministry of Power | Transmission & Distribution | Transmission System for Evacuation of Power from Rajasthan REZ Ph-IV [Part-2 5.5 GW] [Jaisalmer/Barmer Complex] Part E [SPV Name POWERGRID Mewar Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 615334 | Multi-States (Madhya Pradesh, Rajasthan) | 08/2024 | 08/2024 | 08/2026 | - | 3251 | 3251 | 780.24 | 18
August 2025 | 227 | Ministry of Power | Transmission & Distribution | Rajasthan REZ Ph-V [Part-1- 4 GW] [Sirohi/Nagaur] Complex [Rajasthan V Power Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 617186 | Multi-States (Madhya Pradesh, Rajasthan) | 03/2025 | 03/2025 | 03/2027 | - | 5028 | 5028 | 203.2 | 1
August 2025 | 228 | Ministry of Power | Transmission & Distribution | Transmission System for Evacuation of power from Rajasthan REZ Ph-IV [Part-1] [Bikaner Complex] Part D [Neemrana Bareilly Transmission Ltd] | Power Grid Corporation of India Limited [POWERGRID] | 612133 | Multi-States (Rajasthan, Uttar Pradesh) | 12/2023 | 12/2023 | 12/2025 | 06/2026 | 2056 | 2056 | 1356.96 | 58
August 2025 | 229 | Ministry of Power | Transmission & Distribution | Transmission System for evacuation of Power from Rajasthan REZ Ph-IV [Part-4 3.5 GW] Part A [SPV name POWERGRID Ghiror Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 616670 | Multi-States (Rajasthan, Uttar Pradesh) | 12/2024 | 12/2024 | 12/2026 | - | 5846 | 5846 | 293.47 | 4
August 2025 | 230 | Ministry of Power | Transmission & Distribution | Transmission system strengthening scheme for evacuation of power from solar energy zones in Rajasthan[8.1 GW] under phase-II- Part E | Power Grid Corporation of India Limited [POWERGRID] | 611659 | Rajasthan | 03/2023 | 03/2023 | 09/2024 | 10/2025 | 1433.28 | 1433 | 1359.63 | 95
August 2025 | 231 | Ministry of Power | Transmission & Distribution | Transmission System for Evacuation of Power from REZ in Rajasthan 20GW under Phase III- Part E2 | Power Grid Corporation of India Limited [POWERGRID] | 611947 | Rajasthan | 11/2023 | 11/2023 | 06/2025 | 12/2025 | 428.3 | 428.3 | 179.89 | 51
August 2025 | 232 | Ministry of Power | Transmission & Distribution | Transmission system for evacuation of power from REZ in Rajasthan 20 GW under Phase-III part H | Power Grid Corporation of India Limited [POWERGRID] | 611948 | Rajasthan | 10/2023 | 10/2023 | 04/2025 | 12/2025 | 2211.29 | 2211.29 | 1817.46 | 80
August 2025 | 233 | Ministry of Power | Transmission & Distribution | Transmission system for evacuation of power from REZ in Rajasthan 20 GW under Phase-III part C1 | Power Grid Corporation of India Limited [POWERGRID] | 611949 | Rajasthan | 10/2023 | 10/2023 | 04/2025 | 10/2025 | 1796.02 | 1796.02 | 1247.87 | 83
August 2025 | 234 | Ministry of Power | Transmission & Distribution | Transmission system for evacuation of power from REZ in Rajasthan 20 GW under Phase-III part B1 | Power Grid Corporation of India Limited [POWERGRID] | 611950 | Rajasthan | 09/2023 | 09/2023 | 04/2025 | 12/2025 | 2190.54 | 2190.54 | 1870.72 | 83
August 2025 | 235 | Ministry of Power | Transmission & Distribution | Transmission system for evacuation of power from REZ in Rajasthan 20GW under Phase-III Part E1 | Power Grid Corporation of India Limited [POWERGRID] | 611951 | Rajasthan | 12/2021 | 08/2023 | 02/2025 | 09/2025 | 688.74 | 688.74 | 587.42 | 96
August 2025 | 236 | Ministry of Power | Transmission & Distribution | Transmission System for Evacuation of power from Rajasthan REZ Ph-IV [Part-1] [Bikaner Complex] Part A [Bikaner Neemrana Transmission Ltd] | Power Grid Corporation of India Limited [POWERGRID] | 612134 | Rajasthan | 12/2023 | 12/2023 | 12/2025 | 03/2026 | 2998.34 | 2998.34 | 1703.11 | 51
August 2025 | 237 | Ministry of Power | Transmission & Distribution | Transmission System for Evacuation of Power from Rajasthan REZ Ph-IV [Part-2 5.5 GW][Jaisalmer/Barmer Complex] Part B [SPV Name POWERGRID Sirohi Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 615332 | Rajasthan | 08/2024 | 08/2024 | 08/2026 | - | 3279 | 3279 | 688.59 | 21
August 2025 | 238 | Ministry of Power | Transmission & Distribution | Transmission System Strengthening for Interconnections of Bhadla-III & Bikaner III Complex [SPV Name POWERGRID BHADLA BIKANER TRANSMISSION LIMITED] | Power Grid Corporation of India Limited [POWERGRID] | 615335 | Rajasthan | 08/2024 | 08/2024 | 08/2026 | - | 1382 | 1382 | 41.46 | 4
August 2025 | 239 | Ministry of Power | Transmission & Distribution | Additional Transmission System for evacuation of Power from Bhadla-III PS as part of Rajasthan REZ Phase III Scheme [20 GW] [SPV Name POWERGRID Bhadla-III Power Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 615337 | Rajasthan | 08/2024 | 08/2024 | 02/2026 | - | 369 | 369 | 58.26 | 16
August 2025 | 240 | Ministry of Power | Transmission & Distribution | TRANSMISSION SYSTEM FOR EVACUATION OF POWER FROM RAJASTHAN REZ PH -IV [PART-2 5.5 GW] [JAISALMER/BARMER COMPLEX] PART F [SPV Name POWERGRID BARMER I TRANSMISSION LIMITED] | Power Grid Corporation of India Limited [POWERGRID] | 615338 | Rajasthan | 11/2024 | 11/2024 | 11/2026 | - | 2735 | 2735 | 82.05 | 8
August 2025 | 241 | Ministry of Power | Transmission & Distribution | Augmentation at Fatehgarh-II PS, Fatehgarh-IV PS [Section-II] and Barmer-I PS [POWERGRID Fatehgarh Barmer Augmentation Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 617181 | Rajasthan | 03/2025 | 03/2025 | 12/2026 | - | 404 | 404 | 8.04 | 0
August 2025 | 242 | Ministry of Power | Transmission & Distribution | Transmission System under ISTS for evacuation of Power from Kudankulam Unit-3&4 [2x1000 MW] [SPV Name POWERGRID Kudankulam Tarnsmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 616671 | Tamil Nadu | 01/2025 | 01/2025 | 12/2026 | 12/2026 | 548 | 548 | 14.68 | 6
August 2025 | 243 | Ministry of Power | Transmission & Distribution | Transmission System for Strengthening to facilitate evacuation of power from Bhadla/Bikaner Complex | Power Grid Corporation of India Limited [POWERGRID] | 617269 | Uttar Pradesh | 12/2024 | 12/2024 | 06/2026 | - | 212.81 | 212.81 | 0.2 | 0
August 2025 | 244 | Ministry of Housing & Urban Affairs | Construction | C/o 184 MS Flats for Hon'ble MPs at BKS Marg, New Delhi | Central Public Works Department [CPWD] | 617282 | Delhi | 01/2022 | 05/2022 | 05/2025 | 08/2025 | 646.53 | 646.52 | 533.12 | 99
August 2025 | 245 | Ministry of Housing & Urban Affairs | Inland Waterways | Chennai Metro Rail Phase-II Development Project | Chennai Metro Rail Limited [CMRL] | 702668 | Tamil Nadu | 10/2024 | 11/2020 | 08/2029 | - | 63246 | 63246 | 26410.15 | 45
August 2025 | 246 | Ministry of Housing & Urban Affairs | Real Estate | Integrated Command control Center [ICCC] - Construction and Development of Integrated Command Control Center with Security, Surveillance, ITMS, Connecting Port, Ship Service, Smart Solid Waste Management, Smart Public Transport System | ministry of housing and urban affairs | 707229 | Andaman & Nicobar | 07/2021 | 11/2021 | 05/2023 | - | 209.88 | 209.88 | 0 | 70
August 2025 | 247 | Ministry of Housing & Urban Affairs | Real Estate | Redevelopment of Seven General Pool Residential Accommodation [GPRA] Colonies in Delhi | National Buildings Construction Corporation [NBCC] | 400188 | Delhi | 07/2016 | 05/2018 | 12/2025 | 12/2025 | 32850 | 32850 | 0 | 0
August 2025 | 248 | Ministry of Housing & Urban Affairs | Real Estate | Rehablitation in Junavadaj Area Smart City Project | ministry of housing and urban affairs | 701719 | Gujarat | NA | 06/2016 | 07/2022 | - | 539 | 539 | 39.63 | 50
August 2025 | 249 | Ministry of Housing & Urban Affairs | Real Estate | Green Building Development Project | ministry of housing and urban affairs | 701766 | Uttarakhand | NA | 08/2019 | 11/2023 | - | 150.97 | 150.97 | 18.95 | 31
August 2025 | 250 | Ministry of Housing & Urban Affairs | Urban Public Transport | Patna Metro Rail Project | Patna Metro Rail Corporation Ltd. [PMRCL] | 702627 | Bihar | 02/2019 | 02/2019 | 02/2024 | 06/2027 | 13365.77 | 13365.8 | 4039.77 | 40.07
August 2025 | 251 | Ministry of Housing & Urban Affairs | Urban Public Transport | Delhi Metro Rail Phase-IV [2 Corridors] | Delhi Metro Rail Corporation Limited [DMRC] | 617207 | Delhi | 03/2024 | 03/2024 | 03/2029 | - | 8399.81 | 8399.81 | 5.58 | 0
August 2025 | 252 | Ministry of Housing & Urban Affairs | Urban Public Transport | DMRTS Phase - IV [3 Priority Corridors] | Delhi Metro Rail Corporation Limited [DMRC] | 702632 | Delhi | NA | 07/2019 | 03/2025 | 03/2026 | 24948.65 | 24948.7 | 15785.39 | 69
August 2025 | 253 | Ministry of Housing & Urban Affairs | Urban Public Transport | Surat Metro Rail Project | Gujarat Metro Rail Corporation Limited [GMRCL] | 702630 | Gujarat | 03/2019 | 04/2019 | 03/2024 | 06/2026 | 12020.32 | 12020.3 | 7595.47 | 70
August 2025 | 254 | Ministry of Housing & Urban Affairs | Urban Public Transport | Ahmedabad Metro Rail Project, Phase-II | Gujarat Metro Rail Corporation Limited [GMRCL] | 702631 | Gujarat | 03/2019 | 03/2019 | 03/2024 | 12/2025 | 5384.17 | 5384.17 | 4180.43 | 88
August 2025 | 255 | Ministry of Housing & Urban Affairs | Urban Public Transport | Ahmedabad Metro Rail Project [Phase-I] | Gujarat Metro Rail Corporation Limited [GMRCL] | 702639 | Gujarat | 11/2014 | 02/2015 | 03/2018 | 10/2025 | 10773 | 12924.5 | 12174.41 | 99
August 2025 | 256 | Ministry of Housing & Urban Affairs | Urban Public Transport | Construction of Bangalore Metro Rail Project Phase 2. | Bengaluru Metro Rail | 702635 | Karnataka | 02/2014 | 02/2016 | 03/2021 | 09/2026 | 26405.14 | 30695.1 | 29477.97 | 94
August 2025 | 257 | Ministry of Housing & Urban Affairs | Urban Public Transport | Construction Bangalore Metro Rail Project Phase-2A & 2B | Bengaluru Metro Rail | 702665 | Karnataka | 06/2021 | 01/2019 | 06/2026 | 06/2026 | 14788.1 | 14788.1 | 8424.54 | 53
August 2025 | 258 | Ministry of Housing & Urban Affairs | Urban Public Transport | Kochi Metro Rail Phase 2 Development Project | CSPCC Projects | 702664 | Kerala | 11/2022 | 11/2022 | 11/2026 | 11/2026 | 1957.05 | 1957.05 | 329.94 | 12
August 2025 | 259 | Ministry of Housing & Urban Affairs | Urban Public Transport | Bhopal Metro Rail Project | Madhya Pradesh Metro Rail Co Limited [MPMRCL] | 702625 | Madhya Pradesh | 11/2018 | 11/2018 | 11/2022 | 06/2028 | 6941.4 | 6941.4 | 3164.15 | 43
August 2025 | 260 | Ministry of Housing & Urban Affairs | Urban Public Transport | Indore Metro Rail Project | Madhya Pradesh Metro Rail Co Limited [MPMRCL] | 702626 | Madhya Pradesh | 11/2018 | 11/2018 | 11/2022 | 12/2028 | 7500.8 | 7500.8 | 3931.4 | 55
August 2025 | 261 | Ministry of Housing & Urban Affairs | Urban Public Transport | PCMC To Nigdi- Extension Of North South Corridor Of Phase-1 | Maharashtra Metro Rail Corporation Limited [MMRCL] | 617225 | Maharashtra | 10/2023 | 10/2023 | 01/2027 | - | 910.18 | 910.18 | 119.88 | 22
August 2025 | 262 | Ministry of Housing & Urban Affairs | Urban Public Transport | Pune Metro Phase-1 Extension line towards south from Swargate to Katraj | Maharashtra Metro Rail Corporation Limited [MMRCL] | 617226 | Maharashtra | 09/2024 | 09/2024 | 03/2029 | - | 2954.53 | 2954.53 | 19.61 | 3
August 2025 | 263 | Ministry of Housing & Urban Affairs | Urban Public Transport | New Suburba Station Development Project | ministry of housing and urban affairs | 701745 | Maharashtra | NA | 03/2019 | 07/2022 | - | 262.76 | 262.76 | 17.62 | 6
August 2025 | 264 | Ministry of Housing & Urban Affairs | Urban Public Transport | Kalyan Station Precinct Imporvement Project | ministry of housing and urban affairs | 701991 | Maharashtra | NA | 07/2020 | 07/2023 | - | 600 | 600 | 272.42 | 70
August 2025 | 265 | Ministry of Housing & Urban Affairs | Urban Public Transport | Mumbai Metro Line 3 | Mumbai Metro Rail Corporation Limited [MMRC] | 702637 | Maharashtra | 07/2013 | 06/2016 | 03/2023 | 08/2025 | 23136 | 37276 | 27519.07 | 91.9
August 2025 | 266 | Ministry of Housing & Urban Affairs | Urban Public Transport | Nagpur Metro Rail Phase II Development Project | Maharashtra Metro Rail Corporation Limited [MMRCL] | 702658 | Maharashtra | 12/2022 | 12/2022 | 12/2027 | - | 6708 | 6708 | 1045.32 | 25
August 2025 | 267 | Ministry of Housing & Urban Affairs | Urban Public Transport | Delhi Metro Rail Phase-IV [Rithala - Kundli Corridor] | Delhi Metro Rail Corporation Limited [DMRC] | 617206 | Multi-States (Delhi, Haryana) | 01/2025 | 01/2025 | 01/2029 | - | 6230.99 | 6230.99 | 0.29 | 0
August 2025 | 268 | Ministry of Housing & Urban Affairs | Urban Public Transport | Delhi-Ghaziabad-Meerut Regional Rapid Transit System [RRTS] corridor | National Capital Region Transport Corporation [NCRTC] | 702633 | Multi-States (Delhi, Uttar Pradesh) | 03/2019 | 03/2019 | 06/2025 | 08/2025 | 30274 | 30274 | 26325.73 | 95
August 2025 | 269 | Ministry of Housing & Urban Affairs | Urban Public Transport | Kanpur Metro Rail Project | Uttar Pradesh metro rail corporation [UPMRC] | 702628 | Uttar Pradesh | 05/2019 | 11/2019 | 05/2024 | 03/2027 | 11076.48 | 11076.5 | 9083.27 | 73
August 2025 | 270 | Ministry of Housing & Urban Affairs | Urban Public Transport | Agra Metro Rail Project | Uttar Pradesh metro rail corporation [UPMRC] | 702629 | Uttar Pradesh | 05/2019 | 12/2020 | 05/2024 | 06/2027 | 8379.62 | 8379.62 | 6057.62 | 62
August 2025 | 271 | Ministry of Housing & Urban Affairs | Waste & Water | ESR - 8 nos., distribution system - 216 Km, new house service connections - 38760 nos. upgrading of feeder mains, pumping station etc. - Phase II | Ministry of Housing & Urban Affairs | 702674 | Andhra Pradesh | NA | 07/2018 | 03/2023 | 12/2025 | 172.22 | 172.22 | 622.02 | 82
August 2025 | 272 | Ministry of Housing & Urban Affairs | Waste & Water | Dibrugarh Water Supply Infrastructure Project | Ministry of Housing & Urban Affairs | 702682 | Assam | NA | 01/2020 | 03/2023 | 12/2025 | 186.8 | 186.8 | 1291.55 | 98
August 2025 | 273 | Ministry of Housing & Urban Affairs | Waste & Water | Muzaffarpur Storm Water Drainage Phase-I Project | Ministry of Housing & Urban Affairs | 702699 | Bihar | NA | 02/2019 | 10/2023 | 03/2024 | 158.78 | 158.78 | 48.61 | 51
August 2025 | 274 | Ministry of Housing & Urban Affairs | Waste & Water | Storm water drainag Development Project | ministry of housing and urban affairs | 702355 | Dadra & Nagar Haveli and Daman & Diu | NA | 12/2021 | 03/2024 | - | 210 | 210 | 0 | 20
August 2025 | 275 | Ministry of Housing & Urban Affairs | Waste & Water | Upgradation of Sewerage system in Gandhinagar City | ministry of housing and urban affairs | 707267 | Gujarat | NA | 03/2021 | 06/2023 | - | 200 | 200 | 100 | 10
August 2025 | 276 | Ministry of Housing & Urban Affairs | Waste & Water | Sewerage Management Scheme Part-3 Implementation | Ministry of Housing & Urban Affairs | 702734 | Haryana | NA | 11/2017 | 09/2023 | 03/2026 | 278.01 | 278.01 | 1548.15 | 88
August 2025 | 277 | Ministry of Housing & Urban Affairs | Waste & Water | Sewerage Management Scheme Part-3 Implementation | Ministry of Housing & Urban Affairs | 702735 | Haryana | NA | 10/2018 | 03/2023 | 12/2025 | 213.19 | 213.19 | 1069.74 | 91
August 2025 | 278 | Ministry of Housing & Urban Affairs | Waste & Water | Dhanbad Water Supply Infrastructure Project | Ministry of Housing & Urban Affairs | 702741 | Jharkhand | NA | 12/2018 | 03/2023 | 03/2026 | 216.55 | 216.55 | 696.48 | 72
August 2025 | 279 | Ministry of Housing & Urban Affairs | Waste & Water | SAAP-3 Water Supply Infrastructure SAAP-3 Project | Ministry of Housing & Urban Affairs | 702742 | Jharkhand | NA | 12/2018 | 10/2023 | 03/2026 | 159.31 | 159.31 | 612.5 | 65
August 2025 | 280 | Ministry of Housing & Urban Affairs | Waste & Water | Augmentation and Strenghthning of Urban Water Supply Phase 1 - SAAP 3 | Ministry of Housing & Urban Affairs | 702746 | Jharkhand | NA | 12/2018 | 03/2023 | 03/2026 | 278.28 | 278.28 | 1223.5 | 78
August 2025 | 281 | Ministry of Housing & Urban Affairs | Waste & Water | Belgavi Improvement in Sewerage System Project | Ministry of Housing & Urban Affairs | 702760 | Karnataka | NA | 10/2016 | 07/2023 | 12/2025 | 162.73 | 162.73 | 562.71 | 80
August 2025 | 282 | Ministry of Housing & Urban Affairs | Waste & Water | 24/7 water supply under AMRUT for Davanagere | Ministry of Housing & Urban Affairs | 702764 | Karnataka | NA | 01/2018 | 03/2023 | 12/2025 | 174.96 | 174.96 | 715.56 | 65
August 2025 | 283 | Ministry of Housing & Urban Affairs | Waste & Water | Indore Water Supply Infrastructure Project | Ministry of Housing & Urban Affairs | 702793 | Madhya Pradesh | NA | 11/2017 | 03/2023 | 12/2025 | 287.17 | 287.17 | 1766 | 99
August 2025 | 284 | Ministry of Housing & Urban Affairs | Waste & Water | Jabalpur Sewerage Management and Treatment Infrastructure Project | Ministry of Housing & Urban Affairs | 702798 | Madhya Pradesh | NA | 12/2017 | 03/2023 | 12/2025 | 362.31 | 362.31 | 2264.18 | 93
August 2025 | 285 | Ministry of Housing & Urban Affairs | Waste & Water | Satna Sewerage Management and Treatment Infrastructure Project | Ministry of Housing & Urban Affairs | 702808 | Madhya Pradesh | NA | 12/2016 | 03/2024 | 12/2025 | 191.56 | 191.56 | 501.71 | 86
August 2025 | 286 | Ministry of Housing & Urban Affairs | Waste & Water | Singrauli Sewerage Management and Treatment Infrastructure Project | Ministry of Housing & Urban Affairs | 702810 | Madhya Pradesh | NA | 11/2017 | 03/2023 | 12/2025 | 402.01 | 402.01 | 2424.71 | 90
August 2025 | 287 | Ministry of Housing & Urban Affairs | Waste & Water | Kalyan-Dombivali Water Supply Infrastructure Project | Ministry of Housing & Urban Affairs | 702833 | Maharashtra | NA | 09/2019 | 10/2023 | 12/2025 | 194.2 | 194.2 | 375.32 | 70
August 2025 | 288 | Ministry of Housing & Urban Affairs | Waste & Water | Mira-Bhayandar Water Supply Infrastructure Project | Ministry of Housing & Urban Affairs | 702840 | Maharashtra | NA | 08/2018 | 03/2023 | 12/2025 | 204.55 | 204.55 | 581.09 | 99
August 2025 | 289 | Ministry of Housing & Urban Affairs | Waste & Water | Nagpur Water Supply Infrastructure Project | Ministry of Housing & Urban Affairs | 702842 | Maharashtra | NA | 08/2018 | 03/2023 | 09/2025 | 273.78 | 273.78 | 266.11 | 99
August 2025 | 290 | Ministry of Housing & Urban Affairs | Waste & Water | Pune Water Supply Infrastructure Project | Ministry of Housing & Urban Affairs | 702851 | Maharashtra | NA | 07/2017 | 03/2023 | 10/2025 | 235.95 | 235.95 | 614.06 | 92
August 2025 | 291 | Ministry of Housing & Urban Affairs | Waste & Water | Solapur Sewerage Management Infrastructure Project | Ministry of Housing & Urban Affairs | 702854 | Maharashtra | NA | 04/2018 | 03/2023 | 12/2025 | 180.24 | 180.24 | 476.83 | 91
August 2025 | 292 | Ministry of Housing & Urban Affairs | Waste & Water | Jalandhar Water Supply Infrastructure Project | Ministry of Housing & Urban Affairs | 703021 | Punjab | NA | 08/2020 | 08/2023 | 03/2026 | 258.53 | 258.53 | 161.02 | 58
August 2025 | 293 | Ministry of Housing & Urban Affairs | Waste & Water | Patiala Water Supply Infrastructure Part-2 Project | Ministry of Housing & Urban Affairs | 703057 | Punjab | NA | 08/2020 | 10/2023 | 12/2025 | 287 | 287 | 451.94 | 74
August 2025 | 294 | Ministry of Housing & Urban Affairs | Waste & Water | Jaunpur Sewerage Management Infrastructure Project | Ministry of Housing & Urban Affairs | 702948 | Uttar Pradesh | NA | 08/2019 | 06/2023 | 12/2025 | 235.73 | 235.73 | 166 | 87
August 2025 | 295 | Ministry of Housing & Urban Affairs | Waste & Water | Jhansi Water Supply Infrastructure Phase-II Project | Ministry of Housing & Urban Affairs | 702949 | Uttar Pradesh | NA | 06/2019 | 07/2023 | 09/2025 | 561.74 | 561.74 | 523.15 | 100
August 2025 | 296 | Ministry of Mines | Construction | Construction of Basement + Ground Floor+ 10 Storeyed building for State of the Art Director General, GSI Building at plot No.GN-40, Sector-V, Salt Lake, Kolkata | Central Public Works Department (CPWD | 617280 | West Bengal | 04/2019 | 02/2020 | 08/2026 | - | 255.37 | 255.37 | 79.34 | 79
August 2025 | 297 | Ministry of Mines | Metals & Mining | Rakha Underground Mining Project | Hindustan Copper Limited [HCL] | 611798 | Jharkhand | 12/2022 | 03/2024 | 03/2033 | - | 2705 | 2705 | 0 | 0
August 2025 | 298 | Ministry of Mines | Metals & Mining | Surda Underground Copper Mining Project | Hindustan Copper Limited [HCL] | 611800 | Jharkhand | 02/2022 | 03/2024 | 03/2028 | - | 665.02 | 665.02 | 16.57 | 1
August 2025 | 299 | Ministry of Mines | Metals & Mining | Expansion of Malanjkhand Copper Project | Hindustan Copper Limited [HCL] | 400426 | Madhya Pradesh | 09/2011 | 04/2015 | 04/2020 | 04/2026 | 1856.36 | 1856.36 | 935.32 | 80
August 2025 | 300 | Ministry of Mines | Metals & Mining | Expansion of Alumina Refinery Plant with addition of 5th Stream having capacity enhancement of 1.0 Million Tonee Per Annum | National Aluminium Company Limited [NALCO] | 400141 | Odisha | 04/2017 | 04/2017 | 12/2022 | 09/2025 | 4103 | 5677.4 | 3984.99 | 76
August 2025 | 301 | Ministry of Mines | Metals & Mining | Pottangi Bauxite Mines Project | National Aluminium Company Limited [NALCO] | 400299 | Odisha | 05/2018 | 05/2018 | 03/2025 | 05/2026 | 1381 | 1960.77 | 650.04 | 51
August 2025 | 302 | Ministry of Mines | Metals & Mining | UTKAL D AND E COAL BLOCK | National Aluminium Company Limited [NALCO] | 709829 | Odisha | NA | 02/2016 | 03/2025 | - | 1021.97 | 1021.97 | 0 | 0
August 2025 | 303 | Ministry of Mines | Metals & Mining | CONVERSION OF FLAT BOTTOM SETTLERS AND WASHERS WITH A SINGLE TRAIN OF HRDS AND DCWS IN STREAMS 1 AND | Ministry of Mines | 709830 | Odisha | NA | 04/2017 | 11/2026 | - | 355 | 581 | 0 | 0
August 2025 | 304 | Ministry of Mines | Metals & Mining | SOURCING OF BAUXITE ARRANGEMENT FOR 5TH STREAM ALUMINA REFINERY FROM SOUTH BLOCK MINING LEASE OF PANCHPATMAILI MINES | National Aluminium Company Limited [NALCO] | 709831 | Odisha | 11/2017 | 11/2019 | 05/2025 | 06/2026 | 483 | 483 | 402.67 | 90
August 2025 | 305 | Ministry of Mines | Metals & Mining | 25.5 MW WIND POWER PROJECT AT KAYATHAR IN TAMILNADU | National Aluminium Company Limited [NALCO] | 709832 | Tamil Nadu | 09/2017 | 12/2017 | 03/2025 | 03/2026 | 166 | 166 | 135 | 65
August 2025 | 306 | Department of Higher Education | Education | Construction of Permanent Campus of Central Tribal University of Andhra Pradesh Phase-1 | Central Tribal University of Andhra Pradesh | 613008 | Andhra Pradesh | NA | 12/2023 | 06/2027 | - | 305 | 305 | 83.33 | 24
August 2025 | 307 | Department of Higher Education | Education | Construction of Permanent Campus of National Institute of Technology Arunachal Pradesh | National Institute of Technology, Arunachal Pradesh | 612898 | Arunachal Pradesh | NA | 03/2013 | 08/2026 | - | 592.61 | 592.61 | 549.96 | 75
August 2025 | 308 | Department of Higher Education | Education | Tezpur University Projects | Tezpur University | 606112 | Assam | 05/2019 | 06/2021 | 11/2023 | 08/2025 | 153.71 | 153.71 | 54.05 | 95
August 2025 | 309 | Department of Higher Education | Education | Additional Campus of NITPatna | NIT Patna | 606013 | Bihar | 07/2022 | 08/2022 | 07/2024 | 01/2026 | 499.21 | 499.21 | 425.47 | 91
August 2025 | 310 | Department of Higher Education | Education | Phase 1B - Construction of Academic Block, Hostel, Residential Tower, Directors Residence and External Development works at National Institute of Technology, Delhi Campus on Engineering, Procurement and Construction basis | Ministry of Education | 612851 | Delhi | NA | 11/2022 | 09/2025 | - | 333.49 | 333.49 | 277.75 | 91
August 2025 | 311 | Department of Higher Education | Education | Delhi University Eastern Campus at Surajmal Vihar | Delhi University | 616886 | Delhi | NA | 01/2025 | 10/2026 | - | 373 | 373 | 23.23 | 15
August 2025 | 312 | Department of Higher Education | Education | Construction of permanent campus of Central University of Gujarat at Village kundhela, Dist. Vadodara, Gujarat. | Gujarat | 612916 | Gujarat | NA | 02/2021 | 03/2025 | 03/2026 | 490.63 | 490.63 | 301.44 | 76
August 2025 | 313 | Department of Higher Education | Education | Establishment of Permanent campus Phase 1 of IIM Sirmaur | Indian Institute of Management, Sirmaur | 602099 | Himachal Pradesh | 09/2018 | 08/2020 | 10/2023 | 02/2026 | 392.51 | 454.78 | 323.64 | 92
August 2025 | 314 | Department of Higher Education | Education | Hostel blocks & dining hall block | Indian Institute of Technology, Mandi | 612128 | Himachal Pradesh | NA | 03/2024 | 03/2026 | 03/2026 | 166.66 | 166.66 | 72.09 | 65
August 2025 | 315 | Department of Higher Education | Education | Construction of Permanent Campus of Central University of Himachal Pradesh at Dehra, District - Kangra, [H.P.] on Engineering. Procurement and Construction [EPC Mode 1] Basis. | Central University, Himachal Pradesh | 612894 | Himachal Pradesh | 03/2021 | 08/2022 | 11/2024 | 11/2025 | 251.98 | 300.45 | 183.36 | 78
August 2025 | 316 | Department of Higher Education | Education | Construction of Permanent Campus for IIM Jammu Phase-1 at Jagti, Nagrota, Jammu, J&K | Indian Institute of Management, Jammu | 602098 | Jammu and Kashmir | 03/2019 | 10/2020 | 06/2023 | 09/2025 | 424.93 | 500.91 | 484.52 | 96
August 2025 | 317 | Department of Higher Education | Education | Additional Infrastructure at IISc Bangalore-RCC Monolithic for Men Hostel S14, Women Hostel S11 , Postdoctoral Hostel S12 2 Block , International Hostel S 12 , D&E Block S 12 2 Block FR. | IISC Bangalore | 610940 | Karnataka | 08/2021 | 08/2021 | 03/2024 | 09/2025 | 420.41 | 420.41 | 360.72 | 99
August 2025 | 318 | Department of Higher Education | Education | CONSTRUCTION OF PERMANENT CAMPUS FOR IIT PALAKKAD UNDER PHASE 1A | INDIAN INSTITUTE OF TECHNOLOGY PALAKKAD | 606431 | Kerala | 07/2017 | 03/2020 | 06/2022 | 11/2026 | 1006.45 | 1217.4 | 623.6 | 71
August 2025 | 319 | Department of Higher Education | Education | Phase III A works at IIT Indore [03 Hostels, 01 Studio Apartment, 01 Housing, Heavy & Sophisticated lab complex, Academic POD and Infrastructure for center of excellence] | Indian Institute of Technology, Indore | 611957 | Madhya Pradesh | NA | 11/2023 | 12/2026 | - | 496.28 | 496.28 | 143.95 | 35
August 2025 | 320 | Department of Higher Education | Education | Hostel 4 -Earlier Known as Hostel 20 | Indian Institute of Technology, Bombay | 612135 | Maharashtra | NA | 05/2022 | 09/2025 | - | 182.33 | 182.33 | 132.44 | 95
August 2025 | 321 | Department of Higher Education | Education | Academic Block 1 & 2 | Indian Institute of Technology, Bombay | 612203 | Maharashtra | NA | 01/2023 | 07/2026 | 03/2027 | 68 | 263.93 | 22.26 | 18
August 2025 | 322 | Department of Higher Education | Education | Construction and Developement of National Institute of Technology Meghalaya Permanent Campus at Sohra | National Institute of Technology, Meghalaya | 612885 | Meghalaya | 03/2020 | 09/2014 | 03/2022 | 07/2025 | 494.52 | 494.52 | 413.57 | 86
August 2025 | 323 | Department of Higher Education | Education | Construction of Permanent Campus for NIT Mizoram at Lengpui, Aizawl | Ministry of Education | 612876 | Mizoram | 03/2020 | 05/2014 | 12/2029 | 12/2029 | 474.23 | 474.23 | 167.55 | 4
August 2025 | 324 | Department of Higher Education | Education | Establishment of NIT Nagaland | NIT Nagaland | 613013 | Nagaland | NA | 09/2012 | 12/2025 | - | 275.63 | 275.63 | 260.1 | 95
August 2025 | 325 | Department of Higher Education | Education | IISER BERHAMPUR | Indian Institutes of Science Education and Research, Behrampur | 610315 | Odisha | 10/2018 | 09/2019 | 03/2021 | 12/2025 | 1229.32 | 773.76 | 837.04 | 97
August 2025 | 326 | Department of Higher Education | Education | Establishment of NIT Puducherry Permanent Campus [Phase-I and Phase-II] | National Institute of Technology, Puducherry | 612877 | Puducherry | 03/2020 | 07/2013 | 12/2024 | 08/2025 | 618.34 | 544.34 | 509.55 | 94
August 2025 | 327 | Department of Higher Education | Education | Construction of Permanent Campus of Indian Institute of Management [IIM] Amritsar, Punjab, Phase-I | Indian intitue of Management, Amritsar | 605292 | Punjab | 10/2019 | 07/2020 | 06/2023 | 12/2025 | 348.31 | 348.31 | 290.39 | 91
August 2025 | 328 | Department of Higher Education | Education | Construction of Girls Hostel 400 seater, Boys Hostel 600 seater, Academic Block, International Hostel 100 seater, VC Residence and Purchase of Equipment | Central University of Punjab | 617221 | Punjab | 08/2024 | 04/2025 | 10/2027 | - | 210.99 | 210.99 | 0 | 0
August 2025 | 329 | Department of Higher Education | Education | Construction of Sikkim University Campus Phase-I Package-II at Yangang, South Sikkim | Sikkim University | 609736 | Sikkim | 08/2020 | 01/2022 | 01/2025 | 09/2025 | 314.06 | 314.06 | 238.22 | 82
August 2025 | 330 | Department of Higher Education | Education | Establishment of Permanent Campus of NIT SIkkim at Khamdong-Gangtok District | Ministry of Education | 612883 | Sikkim | 02/2024 | 03/2024 | 02/2028 | 12/2026 | 685.76 | 610.76 | 121.56 | 9
August 2025 | 331 | Department of Higher Education | Education | Construction of Precast housing and hostels at IIT Hyderabad | Indian Institute of Technology, Hyderabad | 609996 | Telangana | NA | 11/2022 | 10/2024 | 01/2026 | 262 | 262 | 177.09 | 73
August 2025 | 332 | Department of Higher Education | Education | Banaras Hindu University [ Kayakalp of Institute of Medical Sciences] | Banaras Hindu University | 606479 | Uttar Pradesh | NA | 06/2020 | 09/2022 | 03/2026 | 246 | 246 | 193.38 | 95
August 2025 | 333 | Department of Higher Education | Education | Construction & Development of Infrastructural Facilities in the main campus of NIT Uttarakhand at Sumari, Pauri Garhwal | National Institute of Technology Uttarakhand | 611963 | Uttarakhand | 06/2020 | 04/2024 | 09/2027 | - | 650.85 | 650.85 | 195.52 | 24
August 2025 | 334 | Department of Higher Education | Education | HEFA projects on development of student hostels, playgrounds, departmental buildings, class room complex and other campus facilities in IIT Kharagpur | Indian Institute of Technology, Kharagpur | 609019 | West Bengal | 06/2018 | 04/2019 | 03/2023 | 03/2026 | 500 | 442 | 383.6 | 87
August 2025 | 335 | Department of Higher Education | Education | IoE Projects [Civil Works], IIT Kharagpur | Indian Institute of Technology, Kharagpur | 609041 | West Bengal | NA | 04/2019 | 03/2023 | 12/2026 | 287.2 | 287.2 | 310 | 86
August 2025 | 336 | Ministry of Petroleum & Natural Gas | Energy Storage | Construction of Aviation Fuel farm Facilities at Bhogapuram Airport | Ministry of Petroleum & Natural Gas | 616235 | Andhra Pradesh | NA | 08/2024 | 03/2026 | 03/2026 | 240 | 240 | 38.82 | 59
August 2025 | 337 | Ministry of Petroleum & Natural Gas | Energy Storage | Construction of LPG Facilities at Kamardanga, Assam | Hindustan Petroleum Corporation Limited | 709754 | Assam | NA | 03/2023 | 07/2027 | 07/2027 | 156.36 | 156.36 | 54.15 | 46
August 2025 | 338 | Ministry of Petroleum & Natural Gas | Energy Storage | Setting up of new rail fed POL facility at Kamardanga, Assam | Hindustan Petroleum Corporation Limited [HPCL] | 709755 | Assam | NA | 03/2023 | 07/2027 | 07/2027 | 384.04 | 384.04 | 120.4 | 52
August 2025 | 339 | Ministry of Petroleum & Natural Gas | Energy Storage | Setting up a common user Petroleum Terminal at Jammu, J&K for resitement of existing PSU OMC's Depots from Jammu City | Bharat Petroleum Corporation Limited [BPCL] | 400235 | Jammu and Kashmir | NA | 04/2023 | 03/2025 | 01/2026 | 676.89 | 676.89 | 526.1 | 79
August 2025 | 340 | Ministry of Petroleum & Natural Gas | Energy Storage | Andheri Residential Towers, Mumbai | Ministry of Petroleum & Natural Gas | 604833 | Maharashtra | NA | 06/2017 | 05/2025 | 06/2026 | 281.35 | 389.67 | 230.76 | 50
August 2025 | 341 | Ministry of Petroleum & Natural Gas | Energy Storage | Srikakulam Angul Gas Pipeline Project | Ministry of Petroleum & Natural Gas | 701343 | Multi-States (Andhra Pradesh, Odisha) | NA | 09/2019 | 07/2022 | 12/2025 | 2658.34 | 2810 | 2203.98 | 95
August 2025 | 342 | Ministry of Petroleum & Natural Gas | Energy Storage | Rajasthan Refinery Project | MinistryofPetroleumNaturalGas | 701263 | Multi-States (Arunachal Pradesh, Gujarat, Rajasthan) | NA | 10/2017 | 10/2022 | 03/2026 | 43129 | 79459 | 60295.14 | 88
August 2025 | 343 | Ministry of Petroleum & Natural Gas | Energy Storage | Paradip-Numaligarh Crude Oil Pipeline [PNCPL] & Crude Oil Import Terminal [COIT] at Paradip | Ministry of Petroleum & Natural Gas | 701349 | Multi-States (Assam, Bihar, Jharkhand, Odisha, West Bengal) | NA | 01/2019 | 07/2024 | 09/2025 | 10228 | 11407 | 9766.72 | 87
August 2025 | 344 | Ministry of Petroleum & Natural Gas | Energy Storage | New Mundra Panipat Crude Oil Pipeline | Ministry of Petroleum & Natural Gas | 400078 | Multi-States (Gujarat, Haryana, Rajasthan) | NA | 12/2021 | 12/2024 | 12/2025 | 9028 | 9028 | 7136.41 | 85
August 2025 | 345 | Ministry of Petroleum & Natural Gas | Energy Storage | Kandla Gorakhpur LPG Pipeline | Ministry of Petroleum & Natural Gas | 400012 | Multi-States (Gujarat, Madhya Pradesh, Uttar Pradesh) | NA | 12/2018 | 12/2021 | 12/2025 | 10088 | 10088 | 7672.23 | 92
August 2025 | 346 | Ministry of Petroleum & Natural Gas | Energy Storage | Multi Product Pipeline from Irugur to Devangonthi | Department of Water Resources, River Development & GR | 400301 | Multi-States (Karnataka, Tamil Nadu) | NA | 11/2012 | 02/2017 | 10/2025 | 678 | 1732 | 713.86 | 69
August 2025 | 347 | Ministry of Petroleum & Natural Gas | Energy Storage | Petrochemical evacuation marketing terminal at Barmer, Rajasthan | Hindustan Petroleum Corporation Limited [HPCL] | 709759 | Rajasthan | NA | 12/2023 | 12/2026 | 12/2026 | 461.05 | 461.05 | 116.48 | 54
August 2025 | 348 | Ministry of Petroleum & Natural Gas | Energy Storage | Laying of POL Pipelines in Common Corridor for proposed grass root terminal at Vallur [Chennai] | Ministry of Petroleum & Natural Gas | 400043 | Tamil Nadu | NA | 01/2022 | 05/2026 | 05/2026 | 829 | 829 | 301.71 | 63
August 2025 | 349 | Ministry of Petroleum & Natural Gas | Energy Storage | Grass root POL Terminal at Vallur, Chennai | Indian Oil Corporation Limited [IOCL] | 400077 | Tamil Nadu | NA | 01/2022 | 12/2024 | 03/2026 | 827 | 887.71 | 626.01 | 88
August 2025 | 350 | Ministry of Petroleum & Natural Gas | Energy Storage | Grass Root Rail-fed Depot at Sekerkote, Agartala as resitement of existing Dharmanagar Depot | Indian Oil Corporation Limited [IOCL] | 400035 | Tripura | NA | 06/2022 | 09/2025 | 06/2026 | 656 | 656 | 478.11 | 86
August 2025 | 351 | Ministry of Petroleum & Natural Gas | Energy Storage | Grass-root Terminal at Mirzapur, Uttar Pradesh | Ministry of Petroleum & Natural Gas | 604852 | Uttar Pradesh | NA | 09/2022 | 11/2026 | 11/2026 | 980.45 | 980.45 | 216.66 | 52
August 2025 | 352 | Ministry of Petroleum & Natural Gas | Oil & Gas | KG-DWN-98/2 Cluster - II Development Project - NELP Block | Oil and Natural Gas Corporation Limited [ONGC] | 400120 | Andhra Pradesh | NA | 03/2016 | 06/2020 | 06/2026 | 34012 | 34012 | 33238.47 | 96
August 2025 | 353 | Ministry of Petroleum & Natural Gas | Oil & Gas | HP-COAT [Crude to Olefins and Aromatics Technology] demo unit at Visakh Refinery | Hindustan Petroleum Corporation Limited | 709752 | Andhra Pradesh | NA | 09/2021 | 06/2024 | 03/2026 | 160 | 220 | 80.29 | 69
August 2025 | 354 | Ministry of Petroleum & Natural Gas | Oil & Gas | HP Trijet Unit in Visakh Refinery | Hindustan Petroleum Corporation Limited | 709761 | Andhra Pradesh | NA | 07/2024 | 07/2027 | 07/2027 | 193 | 193 | 0.43 | 23
August 2025 | 355 | Ministry of Petroleum & Natural Gas | Oil & Gas | City Gas Distribution Project at Kurnool, Guntur & Prakasam Districts | MinistryofPetroleumNaturalGas | 709766 | Andhra Pradesh | NA | 03/2022 | 03/2030 | 03/2030 | 1420 | 1420 | 165.65 | 6
August 2025 | 356 | Ministry of Petroleum & Natural Gas | Oil & Gas | Numaligarh Refinery Expansion Project | Ministry of Petroleum & Natural Gas | 604791 | Assam | NA | 07/2020 | 07/2024 | 12/2025 | 12366 | 22494 | 16764.09 | 76
August 2025 | 357 | Ministry of Petroleum & Natural Gas | Oil & Gas | Assam Bio Refinery, ABRPL | Ministry of Petroleum & Natural Gas | 604792 | Assam | NA | 02/2018 | 09/2021 | 09/2025 | 1750 | 4930 | 4710 | 99
August 2025 | 358 | Ministry of Petroleum & Natural Gas | Oil & Gas | Development of Surface Facilities for production and evacuation of Crude Oil and Natural Gas from Nadua and East Khagorija | Ministry of Petroleum & Natural Gas | 604863 | Assam | NA | 01/2018 | 02/2020 | 12/2025 | 682.9 | 726.93 | 489.3 | 94
August 2025 | 359 | Ministry of Petroleum & Natural Gas | Oil & Gas | Guwahati Refinery Expansion [1.0 to 1.2 MMTPA] along with installation of CRU, Guwahati Refinery | Ministry of Petroleum & Natural Gas | 607701 | Assam | NA | 05/2021 | 10/2023 | 05/2026 | 412.3 | 577 | 430.83 | 85
August 2025 | 360 | Ministry of Petroleum & Natural Gas | Oil & Gas | Construction of Field Gas Gathering Station at Baghjan area for collection, processing & transportation of natural Gas to be produced from Baghjan Field | Ministry of Petroleum & Natural Gas | 616858 | Assam | NA | 12/2020 | 03/2024 | 12/2025 | 430.76 | 430.76 | 327.27 | 85
August 2025 | 361 | Ministry of Petroleum & Natural Gas | Oil & Gas | Augmentation/Revamping of Facilities at existing Guwahati Terminal at Betkuchi | MinistryofPetroleumNaturalGas | 709776 | Assam | NA | 04/2022 | 09/2026 | 09/2026 | 277 | 323.09 | 185.18 | 68
August 2025 | 362 | Ministry of Petroleum & Natural Gas | Oil & Gas | Capacity Expansion of Digboi Refinery from 0.65 to 1.0 MMTPA | MinistryofPetroleumNaturalGas | 709779 | Assam | NA | 06/2022 | 03/2026 | 03/2026 | 768 | 740 | 107.72 | 39
August 2025 | 363 | Ministry of Petroleum & Natural Gas | Oil & Gas | Pipeline Network Project Rudrasagar | Ministry of Petroleum & Natural Gas | 709847 | Assam | NA | 01/2023 | 04/2026 | 04/2026 | 344.99 | 344.99 | 211.05 | 47
August 2025 | 364 | Ministry of Petroleum & Natural Gas | Oil & Gas | Borholla GGS Life Extension Project [BLEP] | Ministry of Petroleum & Natural Gas | 709850 | Assam | NA | 09/2023 | 05/2026 | 05/2026 | 198.7 | 198.7 | 36.8 | 30
August 2025 | 365 | Ministry of Petroleum & Natural Gas | Oil & Gas | DCU Revamp Project | NRL | 709864 | Assam | NA | 08/2021 | 07/2024 | 10/2025 | 370 | 370 | 253.17 | 60
August 2025 | 366 | Ministry of Petroleum & Natural Gas | Oil & Gas | Power Recovery Turbine [PRT] in PFCCU unit as an Energy Conservation Scheme | NRL | 709865 | Assam | NA | 04/2023 | 12/2024 | 10/2025 | 293.5 | 293.5 | 97.22 | 94
August 2025 | 367 | Ministry of Petroleum & Natural Gas | Oil & Gas | City Gas Distribution Project at Khagaria, Saharsa and Madhepura | Ministry of Petroleum & Natural Gas | 617303 | Bihar | NA | 03/2019 | 03/2030 | 03/2030 | 163 | 163 | 96.07 | 40
August 2025 | 368 | Ministry of Petroleum & Natural Gas | Oil & Gas | Setting up of LPG Plant with Rail Unloading Facility at Hathua, Dist. Gopalganj, Bihar | MinistryofPetroleumNaturalGas | 617304 | Bihar | NA | 10/2023 | 03/2027 | 03/2027 | 340.15 | 340.15 | 91.32 | 26
August 2025 | 369 | Ministry of Petroleum & Natural Gas | Oil & Gas | Barauni Refinery Capacity Expansion from 6.0 to 9.0 MMTPA | Ministry of Petroleum & Natural Gas | 701324 | Bihar | NA | 01/2020 | 04/2023 | 08/2026 | 14810 | 16724 | 11880.66 | 87
August 2025 | 370 | Ministry of Petroleum & Natural Gas | Oil & Gas | Installation of Bitumen Manufacturing Unit along with allied facilities at Barauni Refinery | MinistryofPetroleumNaturalGas | 709777 | Bihar | NA | 01/2022 | 04/2025 | 10/2026 | 389.35 | 340 | 50.48 | 40
August 2025 | 371 | Ministry of Petroleum & Natural Gas | Oil & Gas | City Gas Distribution Projects at Darbhanga, Madhubani, Supaul, Sitamarhi and Sheohar districts | Bharat Petroleum Corporation Limited [BPCL] | 709792 | Bihar | NA | 12/2022 | 03/2030 | 03/2030 | 3638 | 3638 | 407.18 | 29
August 2025 | 372 | Ministry of Petroleum & Natural Gas | Oil & Gas | City Gas Distribution Projects at Gopalganj, Siwan, West Champaran, East Champaran and Deoria districts | Bharat Petroleum Corporation Limited [BPCL] | 709793 | Bihar | NA | 12/2022 | 06/2030 | 06/2030 | 3919 | 3919 | 400.92 | 18
August 2025 | 373 | Ministry of Petroleum & Natural Gas | Oil & Gas | Redevelopment of Sobhasan Complex | Oil and Natural Gas Corporation Limited [ONGC] | 400087 | Gujarat | NA | 08/2021 | 02/2026 | 02/2026 | 885.63 | 1286.67 | 789.49 | 78
August 2025 | 374 | Ministry of Petroleum & Natural Gas | Oil & Gas | Redevelopment of Santhal Field [Onshore-Mehsana Asset] | Oil and Natural Gas Corporation Limited [ONGC] | 400167 | Gujarat | NA | 02/2017 | 03/2026 | 03/2026 | 1162.56 | 1162.56 | 1157 | 94
August 2025 | 375 | Ministry of Petroleum & Natural Gas | Oil & Gas | Redevelopment of Linch Field | Oil and Natural Gas Corporation Limited [ONGC] | 400169 | Gujarat | NA | 04/2021 | 03/2025 | 10/2025 | 631.03 | 860.04 | 505.15 | 79
August 2025 | 376 | Ministry of Petroleum & Natural Gas | Oil & Gas | Petrochemical and Lube Integration Project at Gujarat Refinery | Ministry of Petroleum & Natural Gas | 701329 | Gujarat | NA | 09/2020 | 08/2024 | 12/2025 | 18936 | 17825 | 12327.91 | 83
August 2025 | 377 | Ministry of Petroleum & Natural Gas | Oil & Gas | Installation of new Biturox Unit along with allied facilities at Gujarat Refinery | MinistryofPetroleumNaturalGas | 709778 | Gujarat | NA | 01/2022 | 08/2025 | 09/2026 | 328.29 | 287 | 151.53 | 58
August 2025 | 378 | Ministry of Petroleum & Natural Gas | Oil & Gas | Commercial Polymer Flooding Project in Bechraji field | Oil and Natural Gas Corporation Limited [ONGC] | 709838 | Gujarat | NA | 01/2022 | 11/2024 | 11/2025 | 621.4 | 621.4 | 137.71 | 21
August 2025 | 379 | Ministry of Petroleum & Natural Gas | Oil & Gas | Restoration of Gas Terminal, Phase-I [Part-A], Hazira | Oil and Natural Gas Corporation Limited [ONGC] | 709840 | Gujarat | NA | 05/2022 | 02/2025 | 12/2025 | 249.43 | 249.43 | 209.45 | 94
August 2025 | 380 | Ministry of Petroleum & Natural Gas | Oil & Gas | Old Pipe Line Replacement [OPRP] Group-A | Oil and Natural Gas Corporation Limited [ONGC] | 709841 | Gujarat | NA | 07/2021 | 07/2025 | 03/2026 | 173.03 | 169.84 | 147.02 | 87
August 2025 | 381 | Ministry of Petroleum & Natural Gas | Oil & Gas | Kalol Redevelopment Project, Ahmedabad Asset | Oil and Natural Gas Corporation Limited [ONGC] | 709842 | Gujarat | NA | 08/2022 | 03/2027 | 03/2027 | 1487.41 | 1487.41 | 927.5 | 62
August 2025 | 382 | Ministry of Petroleum & Natural Gas | Oil & Gas | Revamping of SV Stations, Gas Terminal & Kribhco Terminal | Oil and Natural Gas Corporation Limited [ONGC] | 709845 | Gujarat | NA | 11/2022 | 08/2026 | 08/2026 | 837.34 | 837.34 | 219.13 | 52
August 2025 | 383 | Ministry of Petroleum & Natural Gas | Oil & Gas | Indian Oil Technology Development and Deployment Centre at R&D Campus-II, Faridabad | Ministry of Petroleum & Natural Gas | 604853 | Haryana | NA | 06/2019 | 12/2022 | 03/2026 | 2281.94 | 3200 | 1800.61 | 63
August 2025 | 384 | Ministry of Petroleum & Natural Gas | Oil & Gas | Poly Butadiene Rubber plant at Panipat | Indian Oil Corporation Limited [IOCL] | 611917 | Haryana | NA | 03/2022 | 03/2025 | 06/2026 | 1459 | 2531.44 | 1072.59 | 70
August 2025 | 385 | Ministry of Petroleum & Natural Gas | Oil & Gas | Capacity Expansion of Panipat Refinery from 15 to 25 MMTPA | Ministry of Petroleum & Natural Gas | 701289 | Haryana | NA | 02/2021 | 09/2024 | 12/2025 | 34627 | 36225 | 24355.1 | 89
August 2025 | 386 | Ministry of Petroleum & Natural Gas | Oil & Gas | Installation of Multiple Effect Evaporator [MEE] for ETP-1, 2 & 4 of Panipat Refinery and Petrochemical Complex. | MinistryofPetroleumNaturalGas | 709783 | Haryana | NA | 12/2020 | 06/2023 | 06/2026 | 165.13 | 247.69 | 130.6 | 72
August 2025 | 387 | Ministry of Petroleum & Natural Gas | Oil & Gas | City Gas Distribution Project at Jammu, Udhampur, Reasi, Samba and Kathua Districts | MinistryofPetroleumNaturalGas | 709773 | Jammu and Kashmir | NA | 03/2022 | 03/2032 | 03/2032 | 538 | 538 | 3.72 | 0
August 2025 | 388 | Ministry of Petroleum & Natural Gas | Oil & Gas | Development of Jharia CBM Block [Phase-1] | Oil and Natural Gas Corporation Limited [ONGC] | 610984 | Jharkhand | NA | 11/2019 | 01/2024 | 11/2025 | 431 | 431 | 211.4 | 59
August 2025 | 389 | Ministry of Petroleum & Natural Gas | Oil & Gas | Laying of Natural Gas Pipeline from Hazaribagh to Ranchi [HRPL] | MinistryofPetroleumNaturalGas | 709785 | Jharkhand | NA | 02/2023 | 02/2026 | 02/2026 | 202.07 | 202.07 | 52.42 | 45
August 2025 | 390 | Ministry of Petroleum & Natural Gas | Oil & Gas | Power System Upgradation Project | Mangalore Refinary and Petrochemicals Limited | 612790 | Karnataka | NA | 10/2023 | 11/2025 | 05/2026 | 385 | 385 | 137 | 64
August 2025 | 391 | Ministry of Petroleum & Natural Gas | Oil & Gas | Demo Bio-ATF Project | Ministry of Petroleum & Natural Gas | 616879 | Karnataka | NA | 03/2024 | 01/2027 | 01/2027 | 364 | 364 | 27.02 | 12
August 2025 | 392 | Ministry of Petroleum & Natural Gas | Oil & Gas | Revamping/ Augmentation of facilities at existing port terminal at Mangalore | Ministry of Petroleum & Natural Gas | 709774 | Karnataka | NA | 01/2022 | 12/2025 | 12/2025 | 463 | 500.62 | 271.16 | 82
August 2025 | 393 | Ministry of Petroleum & Natural Gas | Oil & Gas | Replacement and Extension of Jetty Pipelines [REJP] at KR | Bharat Petroleum Corporation Limited [BPCL] | 709790 | Kerala | NA | 03/2023 | 03/2026 | 03/2026 | 621.87 | 621.87 | 193.19 | 85
August 2025 | 394 | Ministry of Petroleum & Natural Gas | Oil & Gas | Setting up Polypropylene Unit at Kochi Refinery | MinistryofPetroleumNaturalGas | 709799 | Kerala | NA | 12/2023 | 10/2027 | 10/2027 | 4460 | 4460 | 265.89 | 13
August 2025 | 395 | Ministry of Petroleum & Natural Gas | Oil & Gas | Ethylene Cracker Project at Bina Refinery including downstream Petrochemical Plants and expansion of Refinery | MinistryofPetroleumNaturalGas | 709798 | Madhya Pradesh | NA | 05/2023 | 05/2028 | 05/2028 | 43367 | 43367 | 1855.5 | 14
August 2025 | 396 | Ministry of Petroleum & Natural Gas | Oil & Gas | Debottlenecking and Augmentation of Cryogenic facilities at Uran LPG Import Terminal | Department of Water Resources, River Development & GR | 400158 | Maharashtra | NA | 04/2021 | 02/2024 | 12/2025 | 1164.69 | 1629.86 | 932.25 | 86
August 2025 | 397 | Ministry of Petroleum & Natural Gas | Oil & Gas | 500 KTA PDHPP Project, Usar | Ministry of Petroleum & Natural Gas | 400168 | Maharashtra | NA | 04/2021 | 04/2025 | 10/2025 | 8797 | 11256 | 6877.59 | 85
August 2025 | 398 | Ministry of Petroleum & Natural Gas | Oil & Gas | Construction of lube oil blending plant at Rasayani | Ministry of Petroleum & Natural Gas | 610985 | Maharashtra | NA | 05/2022 | 12/2023 | 12/2025 | 423.39 | 526.26 | 301.01 | 80
August 2025 | 399 | Ministry of Petroleum & Natural Gas | Oil & Gas | Lube Modernization & Bottom Upgradation Project at Mumbai Refinery | Ministry of Petroleum and Natural Gas | 616933 | Maharashtra | NA | 12/2024 | 03/2028 | 03/2028 | 4679 | 4679 | 194.44 | 5
August 2025 | 400 | Ministry of Petroleum & Natural Gas | Oil & Gas | HP TDAE Unit in Mumbai Refinery | Hindustan Petroleum Corporation Limited | 709760 | Maharashtra | NA | 06/2024 | 04/2026 | 04/2026 | 240 | 240 | 34.42 | 40
August 2025 | 401 | Ministry of Petroleum & Natural Gas | Oil & Gas | City Gas Distribution Project at Beed, Jalgaon and Jalna Districts | MinistryofPetroleumNaturalGas | 709771 | Maharashtra | NA | 03/2022 | 09/2031 | 09/2031 | 865 | 865 | 69.15 | 2
August 2025 | 402 | Ministry of Petroleum & Natural Gas | Oil & Gas | Construction of Additional Tankages and Allied Facilities at JNPT Terminal | MinistryofPetroleumNaturalGas | 709780 | Maharashtra | NA | 04/2022 | 08/2026 | 08/2026 | 341.43 | 436.14 | 282.95 | 51
August 2025 | 403 | Ministry of Petroleum & Natural Gas | Oil & Gas | ATF Pipeline from Jawaharlal Nehru Port Trust to Navi Mumbai International Airport | Indian Oil Corporation Limited [IOCL] | 709782 | Maharashtra | NA | 08/2022 | 08/2025 | 03/2026 | 165 | 165 | 90.75 | 74
August 2025 | 404 | Ministry of Petroleum & Natural Gas | Oil & Gas | Installation of Independent De- Aromatized Solvents [DAS] production facilities at MR | Bharat Petroleum Corporation Limited [BPCL] | 709789 | Maharashtra | NA | 03/2023 | 07/2025 | 12/2025 | 405 | 343 | 205.63 | 86
August 2025 | 405 | Ministry of Petroleum & Natural Gas | Oil & Gas | POL & LOBS Installations with Receipt Pipelines at Rasayani | Bharat Petroleum Corporation Limited [BPCL] | 709797 | Maharashtra | NA | 05/2023 | 05/2026 | 05/2026 | 2585 | 2585 | 612.7 | 61
August 2025 | 406 | Ministry of Petroleum & Natural Gas | Oil & Gas | Part Replacement Pipeline Project [PRPP] | Oil and Natural Gas Corporation Limited [ONGC] | 709846 | Maharashtra | NA | 11/2022 | 05/2024 | 11/2025 | 1219.48 | 1145.1 | 744.81 | 90
August 2025 | 407 | Ministry of Petroleum & Natural Gas | Oil & Gas | Visakh Raipur Pipeline Project | Ministry of Petroleum and Natural Gas | 616254 | Multi-States (Andhra Pradesh, Chhattisgarh, Odisha) | NA | 09/2024 | 09/2027 | 09/2027 | 2212 | 2212 | 13.45 | 8
August 2025 | 408 | Ministry of Petroleum & Natural Gas | Oil & Gas | North East Gas Grid | Ministry of Petroleum & Natural Gas | 701346 | Multi-States (Arunachal Pradesh, Assam, Manipur, Meghalaya, Mizoram, Nagaland, Sikkim, Tripura, West Bengal) | NA | 04/2020 | 03/2024 | 03/2026 | 9265 | 9265 | 6393.85 | 85
August 2025 | 409 | Ministry of Petroleum & Natural Gas | Oil & Gas | Upgradation of Facilities of Numaligarh-Siliguri Product Pipeline [NSPL] for transportation of additional products from existing 1.72 MMTPA to 5.5 MMTPA | Ministry of Petroleum & Natural Gas | 701350 | Multi-States (Assam, West Bengal) | NA | 06/2021 | 12/2024 | 10/2025 | 860 | 860 | 584.76 | 98
August 2025 | 410 | Ministry of Petroleum & Natural Gas | Oil & Gas | CGD Project in Banka, Dumka, Godda, Jamtara, Pakur, Sahibganj GA ID 11A.02 | Hindustan Petroleum Corporation Limited | 709757 | Multi-States (Bihar, Jharkhand) | NA | 06/2022 | 06/2030 | 06/2030 | 1377 | 1377 | 331.74 | 27
August 2025 | 411 | Ministry of Petroleum & Natural Gas | Oil & Gas | Mumbai Nagpur Jharsuguda Pipeline Project | Ministry of Petroleum & Natural Gas | 701354 | Multi-States (Chhattisgarh, Madhya Pradesh, Maharashtra, Odisha) | NA | 06/2020 | 05/2023 | 09/2025 | 7844.25 | 8255 | 6495.6 | 96
August 2025 | 412 | Ministry of Petroleum & Natural Gas | Oil & Gas | Mehsana-Bhatinda & Bhatinda-Jammu Natural Gas Pipeline | Ministry of Petroleum & Natural Gas | 701330 | Multi-States (Gujarat, Haryana, Punjab, Rajasthan) | NA | 07/2011 | 06/2024 | 12/2025 | 7392 | 7392 | 6308 | 90
August 2025 | 413 | Ministry of Petroleum & Natural Gas | Oil & Gas | Gurdaspur Jammu Pipeline | Gas Authority of India Limited [GAIL] | 612853 | Multi-States (Jammu and Kashmir, Punjab) | NA | 07/2023 | 07/2026 | 07/2026 | 521.9 | 521.9 | 190.1 | 36
August 2025 | 414 | Ministry of Petroleum & Natural Gas | Oil & Gas | Kochi - Koottanad - Bangalore - Mangalore Pipeline Phase-II | Ministry of Petroleum & Natural Gas | 701228 | Multi-States (Karnataka, Kerala, Tamil Nadu) | NA | 06/2009 | 12/2012 | 12/2025 | 2915 | 5909 | 4453.29 | 94
August 2025 | 415 | Ministry of Petroleum & Natural Gas | Oil & Gas | City Gas Distribution Maharashtra Natural Gas Limited | Ministry of Petroleum & Natural Gas | 701338 | Multi-States (Karnataka, Maharashtra) | NA | 01/2006 | 06/2031 | 06/2031 | 5535 | 5535 | 3861.49 | 0
August 2025 | 416 | Ministry of Petroleum & Natural Gas | Oil & Gas | Dhamra Haldia Pipeline Project | Ministry of Petroleum & Natural Gas | 701344 | Multi-States (Odisha, West Bengal) | NA | 03/2020 | 11/2022 | 12/2025 | 1030.65 | 1125 | 854.6 | 87
August 2025 | 417 | Ministry of Petroleum & Natural Gas | Oil & Gas | City Gas Distribution Projects at Fazilka [except area already authorized], Ganganagar and Hanumangarh districts | Bharat Petroleum Corporation Limited [BPCL] | 709794 | Multi-States (Punjab, Rajasthan) | NA | 12/2022 | 06/2030 | 06/2030 | 3207 | 3207 | 339.57 | 24
August 2025 | 418 | Ministry of Petroleum & Natural Gas | Oil & Gas | Augmentation/ Revamping of Dimapur Depot, Dimapur | MinistryofPetroleumNaturalGas | 709786 | Nagaland | NA | 08/2023 | 11/2027 | 11/2027 | 227.62 | 227.62 | 9.12 | 22
August 2025 | 419 | Ministry of Petroleum & Natural Gas | Oil & Gas | Integrated Para Xylene [PX] and Purified Terephthalic Acid [PTA] Project at Paradip Refinery | Ministry of Petroleum & Natural Gas | 604859 | Odisha | NA | 07/2020 | 01/2024 | 08/2026 | 13805 | 11783 | 8310.16 | 90
August 2025 | 420 | Ministry of Petroleum & Natural Gas | Oil & Gas | CUF POL Depot at Sadashibpur [Meramundali], Odisha | MinistryofPetroleumNaturalGas | 709800 | Odisha | NA | 04/2021 | 03/2026 | 03/2026 | 393.54 | 393.54 | 104.55 | 44
August 2025 | 421 | Ministry of Petroleum & Natural Gas | Oil & Gas | Life Extension of 48 well platforms of Mumbai High & Heera Fields | Oil and Natural Gas Corporation Limited [ONGC] | 400119 | Offshore | NA | 12/2015 | 04/2018 | 12/2025 | 3190.69 | 3375.9 | 3074.25 | 89
August 2025 | 422 | Ministry of Petroleum & Natural Gas | Oil & Gas | PRP-VIII [Group-A] | Ministry of Petroleum & Natural Gas | 616950 | Offshore | NA | 09/2024 | 02/2026 | 02/2026 | 1486.4 | 1486.4 | 272.3 | 19
August 2025 | 423 | Ministry of Petroleum & Natural Gas | Oil & Gas | Daman Upside Development Project | Oil and Natural Gas Corporation Limited [ONGC] | 709839 | Offshore | NA | 06/2022 | 10/2025 | 02/2026 | 4144.41 | 6406.9 | 3894.53 | 85
August 2025 | 424 | Ministry of Petroleum & Natural Gas | Oil & Gas | MHN TCPP PGC BGC Project [MTPBP] | Ministry of Petroleum & Natural Gas | 709848 | Offshore | NA | 06/2022 | 05/2026 | 05/2026 | 2329.45 | 2354.23 | 820.24 | 53
August 2025 | 425 | Ministry of Petroleum & Natural Gas | Oil & Gas | PRP-VIII Group B [NH & BS Asset] | Ministry of Petroleum & Natural Gas | 709849 | Offshore | NA | 06/2024 | 02/2026 | 02/2026 | 2379.84 | 3165.53 | 1675.65 | 62
August 2025 | 426 | Ministry of Petroleum & Natural Gas | Oil & Gas | Integrated Development of 4 Contract Areas under DSF-II | Ministry of Petroleum & Natural Gas | 709851 | Offshore | NA | 05/2023 | 04/2027 | 04/2027 | 6183.79 | 6183.79 | 474 | 20
August 2025 | 427 | Ministry of Petroleum & Natural Gas | Oil & Gas | 2G Ethanol Biorefinery at Bathinda | Hindustan Petroleum Corporation Limited [HPCL] | 400171 | Punjab | NA | 05/2020 | 02/2023 | 03/2026 | 1421.46 | 1421.46 | 1182.4 | 95
August 2025 | 428 | Ministry of Petroleum & Natural Gas | Oil & Gas | Bathinda Sangrur Pipeline | Ministry of Petroleum and Natural Gas | 612998 | Punjab | NA | 11/2021 | 05/2024 | 09/2025 | 367 | 397 | 346.18 | 93
August 2025 | 429 | Ministry of Petroleum & Natural Gas | Oil & Gas | City Gas Distribution Project at Pathankot District | MinistryofPetroleumNaturalGas | 709770 | Punjab | NA | 03/2022 | 09/2033 | 09/2033 | 151 | 151 | 8.73 | 2
August 2025 | 430 | Ministry of Petroleum & Natural Gas | Oil & Gas | CBR 9 MMTPA Project | Chennai Petroleum Corporation Limited [CPCL] | 604795 | Tamil Nadu | NA | 09/2021 | 06/2025 | 10/2028 | 31580 | 36354 | 1342.27 | 10
August 2025 | 431 | Ministry of Petroleum & Natural Gas | Oil & Gas | Laying of new 28 inch Desal Water Pipeline and 10 inch Reject Water Pipeline between CPCL Manali Refinery and CPCL Desalination plant at Ennore | Chennai Petroleum Corporation Limited [CPCL] | 709750 | Tamil Nadu | NA | 01/2024 | 09/2025 | 12/2025 | 205 | 205 | 38.14 | 42
August 2025 | 432 | Ministry of Petroleum & Natural Gas | Oil & Gas | City Gas Distribution Projects at the Nilgiris and Erode districts | Bharat Petroleum Corporation Limited [BPCL] | 709796 | Tamil Nadu | NA | 12/2022 | 03/2030 | 03/2030 | 3685 | 3685 | 226.87 | 17
August 2025 | 433 | Ministry of Petroleum & Natural Gas | Oil & Gas | Creation of Gas Dehydration Facilities, Tripura Asset | Oil and Natural Gas Corporation Limited [ONGC] | 709837 | Tripura | NA | 03/2022 | 05/2024 | 12/2025 | 209.33 | 131.51 | 68.88 | 62
August 2025 | 434 | Ministry of Petroleum & Natural Gas | Oil & Gas | PP Project, Pata | Gas Authority of India Limited [GAIL] | 400161 | Uttar Pradesh | NA | 03/2019 | 01/2024 | 09/2025 | 910.56 | 1299.02 | 1019 | 97
August 2025 | 435 | Ministry of Petroleum & Natural Gas | Oil & Gas | Revamping / Augmentation of Facilities at Mathura Bitumen Plant | MinistryofPetroleumNaturalGas | 709781 | Uttar Pradesh | NA | 04/2022 | 06/2027 | 12/2026 | 260.12 | 260.12 | 1.11 | 26
August 2025 | 436 | Ministry of Petroleum & Natural Gas | Oil & Gas | City Gas Distribution Projects at Lakhimpur Kheri , Sitapur, Bahraich, Shravasti,Balrampur, Siddharth Nagar & Maharajganj districts | Bharat Petroleum Corporation Limited [BPCL] | 709795 | Uttar Pradesh | NA | 12/2022 | 06/2030 | 06/2030 | 16654 | 16654 | 558.33 | 11
August 2025 | 437 | Ministry of Petroleum & Natural Gas | Oil & Gas | Durgapur - Haldia Pipeline [Section-3B of JHBDPL Project] | Ministry of Petroleum & Natural Gas | 617302 | West Bengal | NA | 03/2017 | 12/2020 | 12/2025 | 1740 | 2493.15 | 2239.7 | 90
August 2025 | 438 | Ministry of Petroleum & Natural Gas | Oil & Gas | Haldia Panagarh Pipeline Project | Hindustan Petroleum Corporation Limited | 709753 | West Bengal | NA | 11/2022 | 11/2025 | 11/2025 | 1010 | 1010 | 645.07 | 82
August 2025 | 439 | Ministry of Petroleum & Natural Gas | Oil & Gas | CGD Project in Malda, Birbhum, Murshidabad, Dakshin Dinajpur GA ID 11A.03 | Hindustan Petroleum Corporation Limited | 709758 | West Bengal | NA | 06/2022 | 06/2030 | 06/2030 | 2628 | 2628 | 335.96 | 27
August 2025 | 440 | Ministry of Petroleum & Natural Gas | Oil & Gas | City Gas Distribution Project at East Mednipore, West Mednipore & Jhargram Districts | MinistryofPetroleumNaturalGas | 709772 | West Bengal | NA | 03/2022 | 06/2031 | 06/2031 | 609 | 609 | 56.35 | 2
August 2025 | 441 | Ministry of Petroleum & Natural Gas | Oil & Gas | City Gas Distribution Projects at Alipurduar and Cooch Behar | Bharat Petroleum Corporation Limited [BPCL] | 709791 | West Bengal | NA | 12/2022 | 03/2030 | 03/2030 | 1017 | 1017 | 184.13 | 39
August 2025 | 442 | Ministry of Health & Family Welfare | Healthcare | AIIMS Majra Rewari Haryana | Ministry of Health & Family Welfare | 701173 | Haryana | NA | 02/2019 | 02/2023 | 12/2026 | 1299 | 1299 | 349.41 | 28
August 2025 | 443 | Ministry of Health & Family Welfare | Healthcare | AIIMS Kashmir at Awantipora Jammu & Kashmir | Central Public Works Department [CPWD] | 701167 | Jammu and Kashmir | 01/2019 | 01/2019 | 01/2025 | 12/2025 | 1828 | 1828 | 1531.86 | 66
August 2025 | 444 | Ministry of Health & Family Welfare | Healthcare | AIIMS Bibinagar | Ministry of Health & Family Welfare | 701171 | Telangana | 12/2018 | 12/2018 | 09/2022 | 12/2025 | 1028 | 1365.95 | 812.95 | 84
August 2025 | 445 | Ministry of Ports, Shipping and Waterways | Healthcare | Establishment of 600 bed super specialty hospital with optional development of Medical college and further expansion on PPP basis. | Mumbai Port Trust [MPT] | 708662 | Maharashtra | 08/2019 | 01/2022 | 06/2026 | 12/2027 | 693 | 693 | 58 | 0
August 2025 | 446 | Ministry of Ports, Shipping and Waterways | Inland Waterways | Development of Container Terminal at Tuna-Tekra, Deendayal Port on BOT Basis Under PPP Mode | Deendayal Port Trust [DPT] | 609424 | Gujarat | NA | 12/2023 | 12/2026 | - | 4243.64 | 4243.64 | 366.2 | 10
August 2025 | 447 | Ministry of Ports, Shipping and Waterways | Inland Waterways | Jal Marg Vikas Project | Inland Waterways Authority of India [IWAI] | 701565 | Multi-States (Bihar, Jharkhand, Uttar Pradesh, West Bengal) | 01/2018 | 02/2018 | 12/2023 | 12/2025 | 5369.18 | 5061.15 | 3510.72 | 71
August 2025 | 448 | Ministry of Ports, Shipping and Waterways | Shipping | Setting up of a Floating Storage and Regasification Unit [FSRU] - Mumbai | Mumbai Port Trust [MPT] | 701586 | Maharashtra | NA | 04/2021 | 11/2026 | 11/2026 | 900 | 900 | 65 | 0
August 2025 | 449 | Ministry of Ports, Shipping and Waterways | Shipping | Operationalization of Coastal Berth & Shallow Water Berth through PPP | Jawaharlal Nehru Port Authority [JNPA] | 708655 | Maharashtra | NA | 07/2021 | 01/2026 | - | 366.8 | 366.8 | 376.86 | 25
August 2025 | 450 | Ministry of Ports, Shipping and Waterways | Shipping | Deepening and Optimization of Inner Harbour facilities including development of Western Dock on BOT basis to handle Cape size vessels | Paradip Port Trust [PPT] | 701574 | Odisha | 05/2022 | 01/2023 | 12/2027 | 10/2028 | 3004.63 | 3004.63 | 1149.79 | 40
August 2025 | 451 | Ministry of Ports, Shipping and Waterways | Shipping | Berth No. 2 [previously Berth 3] of HDC Mechanization Project | Haldia Dock Complex, Syama Prasad Mookerjee Port Authority | 701576 | West Bengal | NA | 03/2023 | 09/2025 | 01/2026 | 298.26 | 298.26 | 420 | 91
August 2025 | 452 | Ministry of Ports, Shipping and Waterways | Shipping | Shalukkhali Liquid Cargo Handling Facility Development Project | Haldia Dock Complex, Syama Prasad Mookerjee Port Authority | 701577 | West Bengal | NA | 08/2022 | 08/2025 | - | 253.65 | 253.65 | 9.28 | 0
August 2025 | 453 | Ministry of Ports, Shipping and Waterways | Tourism, Hospitality & Wellness | National Maritime Heritage Complex [NMHC] Phase-I | Indian Port Rail & Ropeway Corporation Ltd. [IPRCL] | 707215 | Gujarat | 02/2019 | 01/2022 | 03/2024 | 09/2025 | 573 | 1238.05 | 496.63 | 66
August 2025 | 454 | Ministry of Steel | Metals & Mining | Capacity expansion of Deposit-14 and 14 NMZ at Kirandul | National Mineral Development Corporation Limited [NMDC] | 615202 | Chhattisgarh | 08/2021 | 07/2022 | 12/2028 | 03/2028 | 1700 | 1756.2 | 65.44 | 3
August 2025 | 455 | Ministry of Steel | Steel | Replacement of Hot Leveller No.1 of Plate Mill at Bhilai Steel Plant | Steel Authority of India Limited [SAIL] | 617243 | Chhattisgarh | 07/2024 | 08/2024 | 07/2026 | - | 198.62 | 198.62 | 10.9 | 10
August 2025 | 456 | Ministry of Steel | Steel | Replacement of Converter Vessels, Trunnion Rings, Support System & Installation of Secondary Emission at Bhilai Steel Plant | Steel Authority of India Limited [SAIL] | 617255 | Chhattisgarh | NA | 12/2023 | 06/2026 | - | 471.83 | 471.83 | 130.66 | 40
August 2025 | 457 | Ministry of Steel | Steel | Rebuilding of Coke Oven Battery No.7 & 8 at Bhilai Steel Plant | Steel Authority of India Limited [SAIL] | 617256 | Chhattisgarh | NA | 01/2024 | 10/2025 | - | 884.1 | 884.1 | 466.31 | 77
August 2025 | 458 | Ministry of Steel | Steel | NMDC Slurry Pipeline Project Phase-1 | National Mineral Development Corporation Limited [NMDC] | 706811 | Chhattisgarh | 11/2015 | 09/2020 | 06/2023 | 12/2025 | 2907 | 5427 | 3038.85 | 85
August 2025 | 459 | Ministry of Steel | Steel | SCREENING PLANT-III AT KIRANDUL | National Mineral Development Corporation Limited [NMDC] | 709826 | Chhattisgarh | NA | 10/2021 | 01/2026 | - | 2718.84 | 2718.84 | 1341.08 | 72
August 2025 | 460 | Ministry of Steel | Steel | CONSTRUCTION OF RESIDENTIAL TOWERS AT BIOM KIRANDUL COMPLEX | National Mineral Development Corporation Limited [NMDC] | 709827 | Chhattisgarh | NA | 10/2022 | 12/2025 | - | 349.75 | 349.75 | 282.52 | 88
August 2025 | 461 | Ministry of Steel | Steel | New Sinter Plant at BSL, SAIL | Steel Authority of India Limited [SAIL] | 400174 | Jharkhand | 03/2015 | 05/2015 | 10/2017 | 06/2027 | 1034.01 | 1752.3 | 883.44 | 51
August 2025 | 462 | Ministry of Steel | Steel | Replacement of existing Grinders in CRM-I & II at Bokaro Steel Plant | Steel Authority of India Limited [SAIL] | 617249 | Jharkhand | 01/2025 | 02/2025 | 01/2027 | - | 211.94 | 211.94 | 15.04 | 10
August 2025 | 463 | Ministry of Steel | Steel | Secondary Emission Control in Converters of SMS-II at Bokaro Steel Plant | Steel Authority of India Limited [SAIL] | 617250 | Jharkhand | NA | 02/2025 | 10/2026 | - | 207.13 | 207.13 | 15.76 | 8
August 2025 | 464 | Ministry of Steel | Steel | Revamping of old sub-systems of Blast Furnace 3 at Bokaro Steel Plant | Steel Authority of India Limited [SAIL] | 617253 | Jharkhand | 09/2023 | 10/2023 | 07/2025 | 11/2025 | 513.82 | 513.82 | 234.54 | 71
August 2025 | 465 | Ministry of Steel | Steel | Replacement of remaining 04 sets of Battery Cyclones with 04 Nos. of ESPs in Sinter Plant-1 at Bokaro Steel Plant | Steel Authority of India Limited [SAIL] | 617254 | Jharkhand | NA | 04/2024 | 06/2026 | - | 260.37 | 260.37 | 44.25 | 22
August 2025 | 466 | Ministry of Steel | Steel | Rebuilding of Coke Oven Battery No.6 at Bokaro Steel Plant | Steel Authority of India Limited [SAIL] | 617257 | Jharkhand | NA | 12/2023 | 11/2026 | - | 627.31 | 627.31 | 91.96 | 38
August 2025 | 467 | Ministry of Steel | Steel | Construction of Screening Plant-II for Donimalai and Kumaraswamy Iron Ore Mining Complex of NMDC Limited at Ballari Dt, Karnataka. | National Mineral Development Corporation Limited [NMDC] | 400121 | Karnataka | 11/2014 | 06/2024 | 08/2026 | - | 1043.63 | 1043.63 | 229.77 | 29
August 2025 | 468 | Ministry of Steel | Steel | Installation of 4th Slab Caster along with its Auxiliaries and a New Ladle Furnace in SMS-II at Rourkela Steel Plant | Steel Authority of India Limited [SAIL] | 400065 | Odisha | 01/2022 | 02/2022 | 05/2025 | 09/2025 | 1105.23 | 1105.23 | 769.08 | 97
August 2025 | 469 | Ministry of Steel | Steel | Rebuilding of COB 4 at Durgapur Steel Plant | Steel Authority of India Limited [SAIL] | 612781 | West Bengal | 11/2023 | 12/2023 | 12/2026 | - | 916.78 | 916.78 | 126.25 | 14
August 2025 | 470 | Ministry of Steel | Steel | Installation of New Bar Mill at Durgapur Steel Plant | Steel Authority of India Limited [SAIL] | 617242 | West Bengal | 09/2024 | 10/2024 | 06/2027 | - | 2115.44 | 2115.44 | 209.11 | 27
August 2025 | 471 | Ministry of Steel | Steel | Up-gradation of Blast Furnace No. 3 at Durgapur Steel Plant | Steel Authority of India Limited [SAIL] | 617246 | West Bengal | 09/2024 | 10/2024 | 06/2026 | - | 758.09 | 758.09 | 63.81 | 4
August 2025 | 472 | Ministry of Steel | Steel | Third Ladle Furnace in Secondary Refinery Unit at IISCO Steel Plant | Steel Authority of India Limited [SAIL] | 617248 | West Bengal | NA | 12/2024 | 07/2026 | - | 227.96 | 227.96 | 16.24 | 29
August 2025 | 473 | Ministry of Steel | Steel | Revamping of Air Pollution Control Systems of SP-1 at Durgapur Steel Plant | Steel Authority of India Limited [SAIL] | 617251 | West Bengal | 11/2024 | 12/2024 | 05/2026 | - | 196.4 | 196.4 | 0.19 | 3
August 2025 | 474 | Ministry of Railways | Railways | Nadikudi - Srikalahasti New Line | South Central Railway [SCR] - II | 400298 | Andhra Pradesh | 03/2012 | 12/2016 | 05/2027 | 03/2028 | 2312 | 5200 | 2179 | 54
August 2025 | 475 | Ministry of Railways | Railways | Malugur- Palasamudram New Line Project [17.975 Km] | South Western Railway [SWR] - II | 611615 | Andhra Pradesh | 09/2022 | 11/2025 | 11/2027 | 12/2027 | 342 | 342.14 | 0 | 0
August 2025 | 476 | Ministry of Railways | Railways | GOOTY-PENDEKALLU DOUBLING 29.225 Km | South Central Railway [SCR] - II | 611752 | Andhra Pradesh | 03/2023 | 06/2023 | 03/2027 | 03/2027 | 351.83 | 351.83 | 18 | 25
August 2025 | 477 | Ministry of Railways | Railways | GUNTAKAL WEST-MALLAPPA GATE RAIL OVER RAIL - ROR TRACK | South Central Railway [SCR] - II | 611754 | Andhra Pradesh | NA | 07/2023 | 07/2026 | - | 293.3 | 293.3 | 0 | 0
August 2025 | 478 | Ministry of Railways | Railways | Kurnool - Setting up facilities for coach midlife rehabilitation workshop | WPO/Patna | 611927 | Andhra Pradesh | 01/2014 | 10/2017 | 12/2023 | - | 560.72 | 560.72 | 276.66 | 65
August 2025 | 479 | Ministry of Railways | Railways | Flyover between Pendurthi and Simhachalam North to avoid surface crossing at Simhachalam 7.135 km PB 73 of 2023 24 NR | East Coast Railway [ECoR] - II | 612827 | Andhra Pradesh | NA | 05/2024 | 04/2027 | - | 183.65 | 183.65 | 4.2 | 11
August 2025 | 480 | Ministry of Railways | Railways | 3rd & 4th line between Vadlapudi -Gate Jn. cabin and Tie line between Gate Junction to Gangavaram port | East Coast Railway [ECoR] - II | 616697 | Andhra Pradesh | NA | 03/2024 | 06/2026 | - | 154.28 | 154.28 | 10.98 | 16
August 2025 | 481 | Ministry of Railways | Railways | Tiupati Katpadi 104.39 kms | South Central Railway [SCR] - II | 617210 | Andhra Pradesh | 04/2025 | 04/2025 | 03/2029 | - | 1215.56 | 1215.56 | 0 | 0
August 2025 | 482 | Ministry of Railways | Railways | 3rd Line between Gudur Renigunta 83.17 Km | South Central Railway [SCR] - II | 617216 | Andhra Pradesh | 10/2024 | 10/2024 | 03/2027 | - | 877.34 | 877.34 | 2.97 | 0
August 2025 | 483 | Ministry of Railways | Railways | Kurnool Coach Midlife Rehabilitation Project | WPO/Patna | 705253 | Andhra Pradesh | NA | 07/2014 | 12/2020 | - | 563 | 563 | 120 | 0
August 2025 | 484 | Ministry of Railways | Railways | Kotapalli - Narasapur New Line | South Central Railway [SCR] - II | 705436 | Andhra Pradesh | 03/2009 | 09/2013 | 03/2028 | 03/2028 | 2501 | 2501 | 1303.41 | 29
August 2025 | 485 | Ministry of Railways | Railways | Guntur-Guntakal Doubling Project | South Central Railway [SCR] - II | 705633 | Andhra Pradesh | 03/2017 | 11/2017 | 12/2025 | 12/2026 | 3733 | 4295 | 4213.01 | 92
August 2025 | 486 | Ministry of Railways | Railways | Vijaywada-Gudur 3rd Line | RVNL - II | 705648 | Andhra Pradesh | 08/2016 | 04/2018 | 11/2024 | 12/2025 | 6654 | 6654 | 5922 | 90
August 2025 | 487 | Ministry of Railways | Railways | Penukonda - Dharmavaram Doubling Project [41.5 Km] | South Western Railway [SWR] - II | 705789 | Andhra Pradesh | 04/2019 | 12/2018 | 03/2026 | 03/2026 | 307.66 | 307.66 | 270.52 | 61
August 2025 | 488 | Ministry of Railways | Railways | Doubling of New Bonggigaon to Kamakhya via Goalpara - 176 km | Northeast Frontier Railway [NFR] | 705572 | Assam | 09/2016 | 09/2016 | 03/2026 | 03/2026 | 4060 | 4961 | 3683.75 | 93
August 2025 | 489 | Ministry of Railways | Railways | Guwahati-Dibrugarh via Tinsukia & Simaluguri-Dibrugarh | Central Organisation for Railway Electrification [CORE] | 706922 | Assam | 09/2020 | 09/2018 | 09/2020 | 06/2024 | 890.36 | 889.36 | 391.73 | 89
August 2025 | 490 | Ministry of Railways | Railways | Mariani-Jorhat, Tinsukia-Dangri and Makum -TirapTrack Electrification Project | GM/C/ NFR | 706940 | Assam | NA | 01/2022 | 05/2024 | - | 183.99 | 183.99 | 0 | 0
August 2025 | 491 | Ministry of Railways | Railways | Harmuty-Murkongselek Branch Line Electrification Project | GM/C/ NFR | 706942 | Assam | NA | 01/2022 | 05/2024 | - | 237.52 | 237.52 | 0 | 0
August 2025 | 492 | Ministry of Railways | Railways | Sakri -Hasanpur [via Harnagar - Kusheshwar Asthan] New Railway line | East Central Railway [ECR] - I | 400254 | Bihar | 12/2023 | 08/1997 | 12/2024 | 03/2027 | 735.2 | 735.2 | 585.84 | 82
August 2025 | 493 | Ministry of Railways | Railways | Khagaria-Kusheshwar Asthan [42Km] new line project | East Central Railway [ECR] - I | 705364 | Bihar | 04/2019 | 12/1998 | 12/2024 | 03/2027 | 614 | 1384 | 484.29 | 55
August 2025 | 494 | Ministry of Railways | Railways | Hajipur-Sagauli New line | East Central Railway [ECR] - I | 705366 | Bihar | 10/2007 | 10/2004 | 03/2020 | 12/2026 | 2067 | 2087 | 1968.45 | 74
August 2025 | 495 | Ministry of Railways | Railways | Araria Supaul New BG Line | East Central Railway [ECR] - I | 705368 | Bihar | 06/2018 | 03/2009 | 03/2024 | 01/2027 | 1605 | 2514 | 1490.2 | 35
August 2025 | 496 | Ministry of Railways | Railways | Fatuha-Islampur incl. MM for extn.of NL from Neora to Daniawan , Daniawan to Biharsharif, Biharsharif to Barbigha , Barbigha to Shekhpura | East Central Railway [ECR] - I | 705373 | Bihar | 08/2002 | 03/2002 | 03/2023 | 08/2025 | 1473 | 2882 | 2522.41 | 94
August 2025 | 497 | Ministry of Railways | Railways | Jogbani-Biratnagar New Rail Line project | Indian Railway Construction International Limited [IRCON] | 705450 | Bihar | 06/2010 | 01/2011 | 03/2022 | 12/2026 | 402 | 486 | 367.54 | 86
August 2025 | 498 | Ministry of Railways | Railways | Samastipur-Darbhanga Doubling Railway Project | East Central Railway [ECR] - I | 705526 | Bihar | NA | 12/2015 | 03/2025 | 10/2025 | 519 | 519 | 344.23 | 84
August 2025 | 499 | Ministry of Railways | Railways | Sagauli-Valmiknagar | East Central Railway [ECR] - I | 705527 | Bihar | 03/2018 | 03/2017 | 12/2025 | 12/2025 | 1216 | 2222 | 2044.54 | 91
August 2025 | 500 | Ministry of Railways | Railways | Muzaffarpur-Sugauli | East Central Railway [ECR] - I | 705528 | Bihar | 03/2018 | 03/2017 | 06/2024 | 08/2025 | 1586 | 1586 | 1463.45 | 99
August 2025 | 501 | Ministry of Railways | Railways | Rampur Dumra-Tal-Rajendrapul Additional Bridge and Railway Line Doubling | Indian Railway Construction International Limited [IRCON] | 706759 | Bihar | 03/2016 | 05/2017 | 12/2024 | 12/2025 | 2373.64 | 1700.24 | 1402.95 | 95
August 2025 | 502 | Ministry of Railways | Railways | Barauni-Bachwara [16 km] - 3rd & 4th line incl. Barauni yard remodelling [32 km] | East Central Railway [ECR] - I | 706860 | Bihar | 10/2022 | 08/2025 | 08/2025 | 10/2026 | 645 | 645 | 0.77 | 55
August 2025 | 503 | Ministry of Railways | Railways | Kharsia-Dharamjaygarh with Spur line [East Corridor-Phase 1] | Indian Railway Construction International Limited [IRCON] | 400220 | Chhattisgarh | 03/2016 | 01/2014 | 09/2018 | 03/2026 | 3055 | 3438 | 2574.54 | 94
August 2025 | 504 | Ministry of Railways | Railways | Doubling of Kirandul-Jagdalpur Line [150 km] | East Coast Railway [ECoR] - II | 400291 | Chhattisgarh | 02/2013 | 03/2013 | 03/2020 | 12/2025 | 1589 | 1798 | 1542.79 | 92
August 2025 | 505 | Ministry of Railways | Railways | Gauge Conversion of Kendri-Dhamtari including Abhanpur - Rajim Branch line 67.20 Kms - 2nd Material Modification to Raipur Titlagarh doubling. | SECR | 602792 | Chhattisgarh | 07/2011 | 05/2021 | 02/2025 | 11/2025 | 1171 | 1171 | 848 | 82
August 2025 | 506 | Ministry of Railways | Railways | 4th line between Nipania Bhatapara 14.4 Km | South East Central Railway [SECR] - II | 612815 | Chhattisgarh | NA | 05/2024 | 03/2027 | - | 170.49 | 170.49 | 0 | 0
August 2025 | 507 | Ministry of Railways | Railways | Dharamjaigarh-Korba 63 km | CERL | 613003 | Chhattisgarh | NA | 07/2022 | 08/2026 | - | 1686.26 | 1686.26 | 288.83 | 18.5
August 2025 | 508 | Ministry of Railways | Railways | KHARSIA- NAYA RAIPUR-PARMALKASA 5th and 6th Line [278KM] | CAO/C/SECR | 617200 | Chhattisgarh | 04/2025 | 04/2025 | 03/2031 | - | 7853.84 | 7853.84 | 0 | 0
August 2025 | 509 | Ministry of Railways | Railways | Dallirajhra- Rowghat New Railway Line - Phase I [95 km] | RVNL - II | 705433 | Chhattisgarh | 07/2009 | 12/2009 | 09/2025 | 12/2025 | 1628 | 1628 | 1440.85 | 82
August 2025 | 510 | Ministry of Railways | Railways | Gevra Road-Pendra Road New Railway Line [135 km] | Indian Railway Construction International Limited [IRCON] | 705444 | Chhattisgarh | NA | 04/2014 | 03/2022 | 12/2025 | 4970 | 4970 | 4346.55 | 73
August 2025 | 511 | Ministry of Railways | Railways | Chirimiri-Nagpur Halt New Railway Line Project | South East Central Railway [SECR] - II | 705756 | Chhattisgarh | 10/2018 | 06/2020 | 06/2030 | 06/2030 | 241 | 656.52 | 71 | 0
August 2025 | 512 | Ministry of Railways | Railways | Boridand - Ambikapur Doubling Line Project | South East Central Railway [SECR] - II | 706854 | Chhattisgarh | 06/2022 | 04/2022 | 06/2030 | 06/2030 | 1376 | 1576.23 | 218 | 18
August 2025 | 513 | Ministry of Railways | Railways | NIPANIA-BHATAPRA [14.4 KM] 4TH LINE [PB-72/NR/2022-23] | SECR | 709814 | Chhattisgarh | NA | 05/2024 | 12/2026 | 12/2026 | 170 | 184 | 0 | 0
August 2025 | 514 | Ministry of Railways | Railways | 4TH LINE - BHATAPARA-HATHBAND [8.8 KM] [PB-72/NR/2022-23] | SECR | 709815 | Chhattisgarh | NA | 05/2024 | 01/2027 | 12/2027 | 177.03 | 177.03 | 0 | 2
August 2025 | 515 | Ministry of Railways | Railways | 4TH LINE - BHILAI-BHILAI NAGAR [8.8 KM] [PB-72/NR/2022-23] | SECR | 709816 | Chhattisgarh | NA | 05/2024 | 02/2027 | 02/2027 | 177.34 | 177.34 | 1.16 | 2
August 2025 | 516 | Ministry of Railways | Railways | 4TH LINE - DADHAPARA-BELHA [9.2 KM] [PB-72/NR/2022-23] | SECR | 709817 | Chhattisgarh | NA | 05/2024 | 11/2026 | 11/2026 | 169.06 | 169.06 | 14.42 | 60
August 2025 | 517 | Ministry of Railways | Railways | 4TH LINE RAJNANDGAON-DONGARHGARH [31.2 KM] [PB-72/NR/2022-23] | SECR | 709818 | Chhattisgarh | NA | 05/2024 | 01/2027 | 01/2027 | 328.34 | 328.34 | 50.58 | 25
August 2025 | 518 | Ministry of Railways | Railways | 3RD AND 4TH LINE - SARAGBUNDIA AND MADWARANI | SECR | 709819 | Chhattisgarh | 09/2022 | 05/2025 | 12/2026 | 12/2026 | 167.64 | 167.64 | 0 | 2
August 2025 | 519 | Ministry of Railways | Railways | Redevelopment of New Delhi Railway Station and construction of associated infrastructure | Ministry of Railways | 613785 | Delhi | 01/2023 | 06/2024 | 12/2028 | - | 4744 | 4744 | 35.09 | 0
August 2025 | 520 | Ministry of Railways | Railways | North Region Video Surveillance Project | RCIL | 705298 | Delhi | NA | 04/2023 | 03/2024 | - | 274.39 | 274.39 | 0 | 0
August 2025 | 521 | Ministry of Railways | Railways | Anand Vihar-Tilak Bridge 3rd & 4th line | CAO/C/NR | 705583 | Delhi | 03/2013 | 03/2013 | 03/2023 | 12/2027 | 667 | 667 | 285.44 | 62
August 2025 | 522 | Ministry of Railways | Railways | Provision of Work-site Tampers [WST] Railway Project | EDTK[MC]/RB | 705694 | Delhi | NA | 01/2016 | 12/2023 | 01/2026 | 187.72 | 187.72 | 141.91 | 100
August 2025 | 523 | Ministry of Railways | Railways | WST Machine Procurement Project | EDTK[MC]/RB | 705708 | Delhi | NA | 06/2018 | 03/2024 | 12/2027 | 176 | 176 | 0 | 0
August 2025 | 524 | Ministry of Railways | Railways | PCT Machine Procurement Project | EDTK[MC]/RB | 705710 | Delhi | NA | 04/2019 | 04/2024 | 06/2027 | 336 | 336 | 74.32 | 85
August 2025 | 525 | Ministry of Railways | Railways | RBMV Machine Procurement Project | EDTK[MC]/RB | 705712 | Delhi | NA | 10/2019 | 06/2024 | 12/2027 | 480 | 480 | 0.33 | 7
August 2025 | 526 | Ministry of Railways | Railways | SRGM Machine Procurement Project | EDTK[MC]/RB | 705717 | Delhi | NA | 10/2019 | 12/2023 | 03/2026 | 440 | 440 | 390.03 | 90
August 2025 | 527 | Ministry of Railways | Railways | WST Machine Procurement Project | EDTK[MC]/RB | 705720 | Delhi | NA | 12/2019 | 04/2024 | 12/2026 | 384 | 384 | 0 | 0
August 2025 | 528 | Ministry of Railways | Railways | DTS Machine Procurement Project | EDTK[MC]/RB | 705721 | Delhi | NA | 12/2019 | 12/2024 | 12/2026 | 447.6 | 447.6 | 0 | 0
August 2025 | 529 | Ministry of Railways | Railways | BRM Machine Procurement Project | EDTK[MC]/RB | 705722 | Delhi | NA | 09/2019 | 06/2024 | 12/2027 | 210 | 210 | 0.02 | 0
August 2025 | 530 | Ministry of Railways | Railways | Track Machine Procurement Project | EDTK[MC]/RB | 705726 | Delhi | NA | 04/2020 | 03/2025 | 01/2028 | 6339 | 6339 | 4166.47 | 41
August 2025 | 531 | Ministry of Railways | Railways | Kosamba Umarpada 70 Km | PCE/WR | 611918 | Gujarat | NA | 07/2022 | 03/2027 | - | 468 | 468 | 20 | 8
August 2025 | 532 | Ministry of Railways | Railways | Adraj Moti Vijapur 40 Kms | Western Railway [WR] - II | 611937 | Gujarat | 05/2022 | 05/2022 | 05/2026 | 05/2026 | 417.53 | 417.53 | 223 | 86
August 2025 | 533 | Ministry of Railways | Railways | Vijapur Ambliyasan 42 km | PCE/WR | 611938 | Gujarat | 05/2022 | 05/2022 | 05/2026 | 05/2026 | 415.38 | 415.38 | 364 | 96
August 2025 | 534 | Ministry of Railways | Railways | Himatnagar Khedbrahma 55 km | Railway | 611939 | Gujarat | 06/2022 | 04/2017 | 06/2001 | 06/2026 | 482.42 | 482.42 | 461 | 96
August 2025 | 535 | Ministry of Railways | Railways | New broad gauge line between Naliya Jakhau Port 25 Kms | PCE/WR | 611943 | Gujarat | 02/2023 | 02/2023 | 01/2028 | 01/2028 | 410.26 | 410.26 | 6 | 4
August 2025 | 536 | Ministry of Railways | Railways | Quadrupling between Gandhidham Adipur with Y connection at Adipur for providing direct entry towards Mundra Port and Bhuj and high level platform at Gopalpur 11Kms | PCE/WR | 611944 | Gujarat | 02/2023 | 02/2023 | 03/2026 | 03/2026 | 152.44 | 152.44 | 20 | 68
August 2025 | 537 | Ministry of Railways | Railways | Petlad Bhadran 23 Kms | PCE/WR | 611945 | Gujarat | 05/2022 | 05/2022 | 05/2030 | 05/2030 | 307.11 | 307.11 | 82 | 17
August 2025 | 538 | Ministry of Railways | Railways | Choranda Motikoral 18 Kms | PCE/WR | 611969 | Gujarat | NA | 08/2023 | 10/2026 | - | 246 | 246 | 0 | 0
August 2025 | 539 | Ministry of Railways | Railways | Samlaya Timba Road 54 km | PCE/WR | 611970 | Gujarat | 02/2023 | 02/2023 | 03/2030 | 03/2030 | 670.17 | 670.17 | 102 | 12
August 2025 | 540 | Ministry of Railways | Railways | Samni Jambusar 24 km | PCE/WR | 611971 | Gujarat | 05/2022 | 05/2022 | 03/2030 | 03/2030 | 350 | 349.93 | 87 | 31
August 2025 | 541 | Ministry of Railways | Railways | Jambusar Kavi 26 Kms | PCE/WR | 611972 | Gujarat | NA | 04/2023 | 12/2026 | - | 318 | 318 | 0 | 0
August 2025 | 542 | Ministry of Railways | Railways | miyagam karjan Choranda maalsar 37 kms | PCE/WR | 611973 | Gujarat | NA | 06/2023 | 12/2026 | - | 450 | 450 | 0 | 0
August 2025 | 543 | Ministry of Railways | Railways | Western Railway Samakhiali Gandhidham Quadrupiling 53 Kms | PCE/WR | 611974 | Gujarat | 08/2023 | 08/2023 | 12/2026 | - | 1430 | 1430 | 0 | 0
August 2025 | 544 | Ministry of Railways | Railways | Dahod Creation of Infrastructure facilities for 9000 HP Electric locomotives Manufacturing at | PCE/WR | 611977 | Gujarat | NA | 02/2023 | 02/2025 | - | 487 | 487 | 108.69 | 0
August 2025 | 545 | Ministry of Railways | Railways | Dahod Rolling Stock Workshop Provision of Infrastructure for CBS at | PCE/WR | 611978 | Gujarat | NA | 03/2023 | 03/2025 | - | 158 | 158 | 47.31 | 0
August 2025 | 546 | Ministry of Railways | Railways | Sabarmati Setting up of Maintenance Facilities for Train Sets Phase ii | PCE/WR | 611979 | Gujarat | NA | 04/2023 | 06/2025 | - | 250 | 250 | 0 | 0
August 2025 | 547 | Ministry of Railways | Railways | 4th LINE BETWEEN BAREJADI NANDEJ-SANAND-AHMEDABAD BYPASS | Western Railway | 612072 | Gujarat | 02/2023 | 02/2023 | 03/2027 | 03/2027 | 961.67 | 961.67 | 327.53 | 17
August 2025 | 548 | Ministry of Railways | Railways | Redevelopment of Ahmedabad railway station and associated infrastructure on engineering, procurement and construction mode | Ministry of Railways | 613786 | Gujarat | 01/2023 | 11/2023 | 03/2028 | - | 2379 | 2379 | 656.84 | 16
August 2025 | 549 | Ministry of Railways | Railways | Miyagam-Karjan-Dabhoi-Samlaya [GC] | Western Railway [WR] - II | 705458 | Gujarat | 01/2017 | 01/2017 | 03/2021 | 12/2026 | 483.88 | 844.1 | 620.98 | 41
August 2025 | 550 | Ministry of Railways | Railways | Modasa-Shamlaji Road Railway Line Project | SECR | 706757 | Gujarat | 09/2012 | 04/2008 | 03/2025 | 03/2027 | 262 | 262 | 203 | 58
August 2025 | 551 | Ministry of Railways | Railways | Rajkot - Kanalus Doubling Project [111.2 Kms] | Western Railway [WR] - II | 706763 | Gujarat | 10/2021 | 12/2021 | 10/2026 | 10/2026 | 1080.58 | 1080.58 | 787.69 | 76
August 2025 | 552 | Ministry of Railways | Railways | NADIAD-PETLAD [37.26 KM] | Railway | 709812 | Gujarat | NA |  | 06/2030 | 06/2030 | 461.91 | 461.91 | 75 | 7
August 2025 | 553 | Ministry of Railways | Railways | NEW BG LINE INTERSECTION [5 NOS] BETWEEN GERATPUR-SANAND & BOTAD-AHMEDABAD [16.51 KM] [PB#29/NR/202 | SECR | 709813 | Gujarat | NA |  | 10/2027 | 10/2027 | 437.21 | 437.21 | 43 | 15
August 2025 | 554 | Ministry of Railways | Railways | Bhiwani - Dobh Bahali Doubling Project [42.30 Km] | North Western Railway [NWR] | 611884 | Haryana | 02/2023 | 02/2023 | 02/2028 | 02/2028 | 471 | 471 | 191.39 | 59
August 2025 | 555 | Ministry of Railways | Railways | Gomoh - Flyover for DN trains | East Central Railway [ECR] - I | 705765 | Jharkhand | 01/2018 | 01/2018 | 03/2026 | 03/2026 | 686 | 686 | 538.66 | 59
August 2025 | 556 | Ministry of Railways | Railways | Lodhma - Piska - Link Line bypassing Hatia/Ranchi with Y connection | South Eastern Railway [SER] - I | 705785 | Jharkhand | 08/2021 | 03/2019 | 06/2026 | 05/2027 | 473 | 473 | 284.34 | 4
August 2025 | 557 | Ministry of Railways | Railways | Pradhan Kuntha Jn Line Doubling Project | East Central Railway [ECR] - I | 706837 | Jharkhand | 11/2022 | 11/2022 | 11/2027 | 11/2027 | 349.22 | 349.22 | 90.64 | 60
August 2025 | 558 | Ministry of Railways | Railways | Construction of New BG line between Hassan to Belur [27 Km] | South Western Railway [SWR] - II | 400023 | Karnataka | 03/2019 | 12/2025 | 04/2028 | 04/2027 | 749 | 749 | 0 | 0
August 2025 | 559 | Ministry of Railways | Railways | Yeshvanthpur - Channasandra Doubling Project [21.70 Km] | Karnataka Rail Infrastructure Development Company Limited [K-RIDE] | 703585 | Karnataka | NA | 10/2019 | 03/2024 | 08/2025 | 314.1 | 683.57 | 151.11 | 52
August 2025 | 560 | Ministry of Railways | Railways | New Railway Line between Ginigera and Raichur [165.57 km] | South Western Railway [SWR] - II | 705434 | Karnataka | 03/2008 | 05/2009 | 03/2019 | 03/2027 | 2565 | 3034.98 | 2073.98 | 66
August 2025 | 561 | Ministry of Railways | Railways | Gadag-Wadi New Railway Line [257 km] | South Western Railway [SWR] - II | 705490 | Karnataka | 04/2013 | 08/2017 | 03/2027 | 12/2027 | 2842 | 6700 | 1735.22 | 30
August 2025 | 562 | Ministry of Railways | Railways | Kadur - Chickamagalur - Sakleshpur [93km] | South Western Railway [SWR] - II | 705492 | Karnataka | 01/2014 | 11/2016 | 06/2025 | 12/2025 | 825 | 825 | 788.13 | 83
August 2025 | 563 | Ministry of Railways | Railways | Bagalkot-Kudachi New Railway Line [142 km] | South Western Railway [SWR] - II | 705495 | Karnataka | 11/2021 | 11/2012 | 03/2027 | 01/2027 | 1378 | 1649 | 683.48 | 35
August 2025 | 564 | Ministry of Railways | Railways | Tumkur-Chitradurga-Davangere New Rail Line Project [191 km] | South Western Railway [SWR] - II | 705496 | Karnataka | 10/2013 | 01/2017 | 03/2019 | 12/2027 | 1876 | 1876 | 523.07 | 13
August 2025 | 565 | Ministry of Railways | Railways | Bangalore-Whitefield-Bangalore City-Krishnarajapuram [23.08 km] - Quadrupling | South Western Railway [SWR] - II | 705663 | Karnataka | 02/2018 | 06/2022 | 02/2026 | 02/2026 | 493 | 493 | 252.45 | 82
August 2025 | 566 | Ministry of Railways | Railways | SHIMOGA - SHIKARIPURA - RANEBENNUR [96 Km] | South Western Railway [SWR] - II | 705761 | Karnataka | NA | 02/2023 | 12/2027 | 06/2028 | 1454 | 1454 | 69.82 | 11
August 2025 | 567 | Ministry of Railways | Railways | Belgaum-Dharwad via Kittur [73.10Km] | South Western Railway [SWR] - II | 706835 | Karnataka | 09/2020 | 03/2025 | 12/2027 | 03/2029 | 1591 | 1591 | 0.75 | 0
August 2025 | 568 | Ministry of Railways | Railways | Kumbalam-Turavur doubling project [15.59 Km] | Southern Railway [SR] - II | 705638 | Kerala | 04/2023 | 04/2023 | 03/2027 | 03/2027 | 813 | 813 | 292.15 | 15
August 2025 | 569 | Ministry of Railways | Railways | Ernakulam-Kumbalam doubling project [7.71 Km] | SR-ERS | 705639 | Kerala | 04/2023 | 04/2023 | 03/2028 | 03/2028 | 601 | 601 | 283 | 17
August 2025 | 570 | Ministry of Railways | Railways | Lalitpur-Satna, Rewa-Singrauli & Mahoba-Khajuraho | North Central Railway | 705480 | Madhya Pradesh | 01/2007 | 03/1998 | 03/2027 | 12/2027 | 8914 | 8914 | 5013.49 | 72
August 2025 | 571 | Ministry of Railways | Railways | Katni - Bina Third Railway Line [279 km] | West Central Railway WCR I | 705651 | Madhya Pradesh | 06/2016 | 01/2017 | 03/2022 | 12/2025 | 2478.23 | 4127.23 | 3301.89 | 90
August 2025 | 572 | Ministry of Railways | Railways | Satna-Rewa Railway Line Doubling Project | West Central Railway [WCR] - II | 705659 | Madhya Pradesh | 11/2015 | 08/2017 | 03/2026 | 03/2026 | 500 | 584 | 561.38 | 80
August 2025 | 573 | Ministry of Railways | Railways | Doubling of Katni - Singrauli Railway Line [261 km] | Indian Railway Construction International Limited [IRCON] | 705660 | Madhya Pradesh | 03/2016 | 03/2017 | 12/2025 | 12/2025 | 2445 | 4377 | 3201.67 | 100
August 2025 | 574 | Ministry of Railways | Railways | Katni Grade Separator/Bye Pass | Indian Railway Construction International Limited [IRCON] | 705661 | Madhya Pradesh | 03/2016 | 09/2017 | 09/2024 | 03/2026 | 1248 | 1248 | 1587.21 | 94
August 2025 | 575 | Ministry of Railways | Railways | Indore - Budni New Railway Line [198 kms] | RVNL - II | 705763 | Madhya Pradesh | 08/2019 | 10/2020 | 09/2030 | 09/2030 | 7474 | 7474 | 1685.25 | 23
August 2025 | 576 | Ministry of Railways | Railways | Nimach-Ratlam Doubling [133 Km] | Western Railway [WR] - II | 705933 | Madhya Pradesh | 10/2021 | 10/2021 | 10/2027 | 10/2027 | 1095.88 | 1095.88 | 1067.49 | 89
August 2025 | 577 | Ministry of Railways | Railways | DHULE [BORVIHIR] - NARDANA NEW LINE [50.60 KMS] | CR | 400019 | Maharashtra | 01/2019 | 04/2023 | 12/2026 | 09/2027 | 492.76 | 1170.83 | 245.11 | 16
August 2025 | 578 | Ministry of Railways | Railways | Wardha-Nanded Via Yavatmal New BG Line | Central Railway [CR] - II | 400271 | Maharashtra | 12/2017 | 04/2008 | 03/2028 | 03/2028 | 3445 | 3445 | 3002.93 | 50
August 2025 | 579 | Ministry of Railways | Railways | AURANGABAD-ANKAI - DOUBLING PROJECT 98.25 Km | South Central Railway [SCR] - II | 611751 | Maharashtra | 05/2023 | 05/2023 | 03/2027 | - | 960.64 | 960.64 | 0 | 0.01
August 2025 | 580 | Ministry of Railways | Railways | Western Railway Vasai bypass double line between Naigaon Juchandra 6 km | PCE/WR | 611975 | Maharashtra | NA | 07/2023 | 03/2026 | - | 176 | 176 | 0 | 0
August 2025 | 581 | Ministry of Railways | Railways | Jogeshwari AT Development of JOS-AT as Trainset Maintenance Depot for energy efficient Vande Bharat Sleeper Trains | PCE/WR | 611976 | Maharashtra | NA | 06/2023 | 10/2025 | - | 221 | 221 | 0 | 0
August 2025 | 582 | Ministry of Railways | Railways | Redevelopment of Chhatrapati Shivaji Maharaj Terminus [CSMT] and construction of associated infrastructure | Ministry of Railways | 613015 | Maharashtra | 04/2023 | 07/2023 | 03/2027 | - | 1813 | 1813 | 569.08 | 13
August 2025 | 583 | Ministry of Railways | Railways | Gondia-Balharshah [Chanda Fort] Doubling [240 Km] | South East Central Railway | 617201 | Maharashtra | 04/2025 | 04/2025 | 04/2030 | - | 4373.04 | 4373.04 | 0 | 0
August 2025 | 584 | Ministry of Railways | Railways | Doubling between Parbhani Parli Vaijanath stations 64.71 Km | South Central Railway [SCR] - II | 617215 | Maharashtra | 12/2023 | 12/2023 | 03/2028 | - | 769.93 | 769.93 | 0 | 0
August 2025 | 585 | Ministry of Railways | Railways | Western Region Video Surveillance Project | RCIL | 705300 | Maharashtra | NA | 04/2023 | 12/2023 | - | 227.59 | 227.59 | 0 | 0
August 2025 | 586 | Ministry of Railways | Railways | Ahmednagar - Beed - Parli - Vaijnath New Broad Gauge Line Railway Project [261.3 km] | Central Railways | 705356 | Maharashtra | 01/1999 | 10/2002 | 03/2026 | 03/2026 | 2538.67 | 4957.27 | 4975.74 | 98
August 2025 | 587 | Ministry of Railways | Railways | Baramati Lonand New Line Project | Central Railway [CR] - II | 705357 | Maharashtra | 03/2016 | 03/1999 | 03/2027 | 03/2027 | 138.48 | 1843.9 | 735.33 | 51
August 2025 | 588 | Ministry of Railways | Railways | Wadsa-Gadchiroli | South East Central Railway | 705479 | Maharashtra | 05/2017 | 03/2012 | 03/2027 | 03/2027 | 1886 | 1886 | 925.28 | 50
August 2025 | 589 | Ministry of Railways | Railways | 3rd Line Kalyan - Kasara [67.35 Kilometres] | Central Railway [CR] - II | 705498 | Maharashtra | 09/2015 | 09/2015 | 12/2026 | 12/2026 | 792.89 | 1395.79 | 899.47 | 51
August 2025 | 590 | Ministry of Railways | Railways | 3rd Line Wardha - Sewagram - Nagpur | Central Railway [CR] - II | 705500 | Maharashtra | 09/2015 | 05/2016 | 12/2025 | 12/2025 | 540.02 | 944.24 | 754.27 | 81
August 2025 | 591 | Ministry of Railways | Railways | 3rd Line Wardha - Ballarshah [132 Kilometres] | Central Railway [CR] - II | 705502 | Maharashtra | 03/2016 | 12/2016 | 12/2025 | 02/2026 | 1384.72 | 2033.59 | 1655.88 | 68
August 2025 | 592 | Ministry of Railways | Railways | Pune - Miraj-Londa [467 Kilometres] | Central Railway [CR] - II | 705503 | Maharashtra | 06/2016 | 06/2016 | 02/2025 | 08/2025 | 4027.53 | 4872.52 | 4833.04 | 85
August 2025 | 593 | Ministry of Railways | Railways | Doubling of Daund Manmad Line [247.6 km] | Central Railway [CR] - II | 705504 | Maharashtra | 10/2017 | 03/2017 | 12/2025 | 03/2026 | 2081.27 | 3267.06 | 2816.46 | 88
August 2025 | 594 | Ministry of Railways | Railways | 4th Line Wardha - Nagpur [78.7 Kilometres] | Central Railway [CR] - II | 705505 | Maharashtra | 04/2017 | 05/2018 | 12/2025 | 02/2026 | 637.95 | 1341.28 | 983.16 | 81
August 2025 | 595 | Ministry of Railways | Railways | 3rd Line Manmad - Jalgaon [160 Kilometres] | Central Railway [CR] - II | 705506 | Maharashtra | NA | 04/2018 | 12/2024 | 08/2025 | 1035.16 | 1558.75 | 1726.94 | 95
August 2025 | 596 | Ministry of Railways | Railways | Solapur-tuljapur-Osmanabad | Railway | 705735 | Maharashtra | NA | 12/2023 | 03/2027 | 03/2028 | 904.92 | 3295.74 | 1127.14 | 12
August 2025 | 597 | Ministry of Railways | Railways | Nagpur- Nagbhir Railway Line Gauge Conversion Project | MRIDC | 705799 | Maharashtra | 10/2019 | 04/2020 | 12/2025 | 12/2025 | 1400 | 1400 | 1472 | 80
August 2025 | 598 | Ministry of Railways | Railways | Mumbai Urban Transport Project [MUTP] - PHASE II | Mumbai Rail Vikas Corporation Ltd.[MRVC] | 706779 | Maharashtra | 05/2008 | 04/2008 | 03/2014 | 12/2027 | 8087 | 8087 | 7364 | 87
August 2025 | 599 | Ministry of Railways | Railways | Mumbai Urban Transport Project [MUTP] Phase-IIIA | Mumbai Rail Vikas Corporation Ltd.[MRVC] | 706780 | Maharashtra | 04/2019 | 04/2019 | 12/2027 | 12/2027 | 33690 | 33690 | 2303.4 | 16
August 2025 | 600 | Ministry of Railways | Railways | Mumbai Urban Transport Project Phase-III | Mumbai Rail Vikas Corporation Ltd.[MRVC] | 706781 | Maharashtra | 11/2016 | 12/2016 | 03/2022 | 12/2026 | 10947 | 10947 | 5152.7 | 60
August 2025 | 601 | Ministry of Railways | Railways | PACHORA-JAMNER WITH EXTENSION UPTO MALKAPUR NG TO BG | CR | 709808 | Maharashtra | NA | 01/2022 | 08/2027 | 03/2028 | 955.39 | 2093.82 | 130.42 | 11
August 2025 | 602 | Ministry of Railways | Railways | KALYAN-MURBAD VIA ULHASNAGAR [UMBRELLA WORK] | Central Railway [CR] - II | 709809 | Maharashtra | NA | 04/2023 | 03/2027 | 03/2027 | 726.46 | 836.12 | 9.29 | 0
August 2025 | 603 | Ministry of Railways | Railways | Jiribam-Imphal new line project | Northeast Frontier Railway [NFR] | 705391 | Manipur | 03/2013 | 12/2007 | 12/2026 | 06/2029 | 14323 | 21885.9 | 15598.11 | 69
August 2025 | 604 | Ministry of Railways | Railways | Marikuppam - Kuppam New Line Project [23.70 Km] | South Western Railway [SWR] - II | 705491 | Multi-States (Andhra Pradesh, Karnataka) | 04/2012 | 10/2018 | 06/2026 | 06/2026 | 297 | 297 | 123.38 | 15
August 2025 | 605 | Ministry of Railways | Railways | Rayadurg-Tumkur via Kalyandurg New Line [207 km] | South Western Railway [SWR] - II | 705494 | Multi-States (Andhra Pradesh, Karnataka) | 03/2008 | 07/2010 | 09/2015 | 02/2028 | 2496 | 2496 | 1706.31 | 68
August 2025 | 606 | Ministry of Railways | Railways | Renigunta, Wadi & Gooty Bypass Railway Project | South Central Railway [SCR] - I | 705610 | Multi-States (Andhra Pradesh, Karnataka) | 04/2016 | 04/2016 | 12/2025 | 12/2025 | 302 | 543 | 381 | 50
August 2025 | 607 | Ministry of Railways | Railways | Doubling between Mudkhed Medchal & Mahbubnagar Dhone section 417.88 Km | South Central Railway [SCR] - II | 617212 | Multi-States (Andhra Pradesh, Maharashtra, Telangana) | 08/2023 | 08/2023 | 03/2029 | - | 4686.09 | 4686.09 | 0 | 0
August 2025 | 608 | Ministry of Railways | Railways | Vizianagaram - Titlagarh 3rd line [272 Km including By - pass line of 7.68 KM] | RVNL - II | 400253 | Multi-States (Andhra Pradesh, Odisha) | 06/2016 | 11/2016 | 12/2026 | 12/2026 | 4803 | 6670 | 5722.01 | 89
August 2025 | 609 | Ministry of Railways | Railways | Doubling of Kottavalasa-Koraput Rail Line [189 KM] | East Coast Railway [ECoR] - II | 705512 | Multi-States (Andhra Pradesh, Odisha) | 12/2015 | 01/2016 | 03/2022 | 03/2028 | 2500 | 2500 | 1987.17 | 70
August 2025 | 610 | Ministry of Railways | Railways | Vizianagaram-Sambhalpur 3rd Line Project | RVNL | 705520 | Multi-States (Andhra Pradesh, Odisha) | NA | 12/2016 | 03/2025 | - | 4803.16 | 4803.16 | 2979.23 | 0
August 2025 | 611 | Ministry of Railways | Railways | Malkangiri Pandurangapuram new railway line project | Indian Railways | 616702 | Multi-States (Andhra Pradesh, Odisha, Telangana) | 08/2024 | 01/2027 | 11/2031 | - | 3591.76 | 3591.76 | 0 | 0
August 2025 | 612 | Ministry of Railways | Railways | Tindivanam-Nagari New Line Project [184.5 km] | Southern Railway [SR] - II | 400275 | Multi-States (Andhra Pradesh, Tamil Nadu) | 07/2008 | 10/2008 | 09/2016 | 03/2028 | 3631 | 3631 | 1113.53 | 18
August 2025 | 613 | Ministry of Railways | Railways | Doubling between Motumari Vishnupuram - 88.81 Km and Rail over Rail - RoR at Motumari - 10.877 Km | South Central Railway [SCR] - II | 616857 | Multi-States (Andhra Pradesh, Telangana) | NA | 03/2025 | 03/2029 | - | 1595.55 | 1595.55 | 7.69 | 1
August 2025 | 614 | Ministry of Railways | Railways | Doubling of Guntur Bibinagar 239 Km | South Central Railway [SCR] - II | 617211 | Multi-States (Andhra Pradesh, Telangana) | 08/2023 | 08/2023 | 03/2029 | - | 2853.23 | 2853.23 | 43.88 | 1
August 2025 | 615 | Ministry of Railways | Railways | Rail Connectivity to Errupalem Amravati Namburu 57 Km | South Central Railway [SCR] - II | 617214 | Multi-States (Andhra Pradesh, Telangana) | 11/2024 | 11/2024 | 03/2027 | - | 2047.4 | 2047.4 | 0 | 0
August 2025 | 616 | Ministry of Railways | Railways | Kazipet-Vijayawada 3rd line with electrification [220 km] | South Central Railway [SCR] - II | 705612 | Multi-States (Andhra Pradesh, Telangana) | 03/2013 | 08/2014 | 02/2025 | 12/2025 | 1953 | 3363 | 3073.74 | 91
August 2025 | 617 | Ministry of Railways | Railways | Vijayawada - Kazipet Byepass line | South Central Railway [SCR] - II | 705632 | Multi-States (Andhra Pradesh, Telangana) | 04/2016 | 04/2016 | 01/2025 | 12/2025 | 647 | 904 | 888.91 | 91
August 2025 | 618 | Ministry of Railways | Railways | Murkongselek-Pasighat | Northeast Frontier Railway (NFR) - II | 705401 | Multi-States (Arunachal Pradesh, Assam) | NA | 03/2012 | 03/2025 | 12/2025 | 435 | 1250 | 901 | 56
August 2025 | 619 | Ministry of Railways | Railways | Lumding Furkating Doubling Project 140 km | Northeast Frontier Railway [NFR] | 616701 | Multi-States (Assam, Nagaland) | NA | 01/2025 | 02/2028 | - | 2123.7 | 2123.7 | 13.74 | 0
August 2025 | 620 | Ministry of Railways | Railways | Dimapur [Dhansiri]-Sukhobi Kohima [Zubza] NL [82.5 Km] | Northeast Frontier Railway [NFR] | 705392 | Multi-States (Assam, Nagaland) | 08/2015 | 02/2016 | 03/2025 | 12/2025 | 6663 | 6663 | 5312.26 | 80
August 2025 | 621 | Ministry of Railways | Railways | New Delhi- Howrah Speed Booster[160Kmph] Project | PCE/NCR | 705794 | Multi-States (Bihar, Delhi, Jharkhand, Uttar Pradesh, West Bengal) | NA | 09/2019 | 03/2024 | - | 6684.81 | 6684.81 | 127.03 | 0
August 2025 | 622 | Ministry of Railways | Railways | Third Railway Line between Patratu-Sonnagar [281 kms] | RVNL - II | 400234 | Multi-States (Bihar, Jharkhand) | 11/2016 | 08/2018 | 03/2026 | 07/2026 | 8975 | 8975 | 4950 | 88
August 2025 | 623 | Ministry of Railways | Railways | Multi tracking of Son Nagar-Andal 374.53 rkm & 814.38 tkm | East Central Railway [ECR] - I | 616699 | Multi-States (Bihar, Jharkhand) | 08/2023 | 08/2023 | 03/2028 | - | 12333.57 | 12333.6 | 467.55 | 11
August 2025 | 624 | Ministry of Railways | Railways | Koderma-Tilaiya New Line | East Central Railway [ECR] - I | 705375 | Multi-States (Bihar, Jharkhand) | 11/2004 | 03/2002 | 02/2025 | 02/2026 | 1626 | 2020 | 2000.4 | 95
August 2025 | 625 | Ministry of Railways | Railways | Pirpainti - Jasidih [100.52 Km] New BG line | Eastern Railway [ER] - I | 705385 | Multi-States (Bihar, Jharkhand) | 03/2014 | 03/2022 | 03/2028 | 03/2028 | 2555 | 2555 | 767.04 | 48
August 2025 | 626 | Ministry of Railways | Railways | NER Provision of Automatic Block Signalling on Gorakhpur Cantt[Excl] Chhapra Gramin & Burhwal Jn [Excl] Sitapur Jn section of high density routes | North Eastern Railway [NER] | 611669 | Multi-States (Bihar, Uttar Pradesh) | NA | 06/2023 | 03/2027 | - | 380.47 | 380.47 | 24.53 | 0
August 2025 | 627 | Ministry of Railways | Railways | Gorakhpur-Valmikinagar Doubling project | NER | 617224 | Multi-States (Bihar, Uttar Pradesh) | NA | 03/2024 | 12/2027 | - | 1120 | 1120 | 204.59 | 20
August 2025 | 628 | Ministry of Railways | Railways | Chhapra-Ballia Patch Doubling | North Eastern Railway [NER] | 705562 | Multi-States (Bihar, Uttar Pradesh) | 03/2013 | 11/2015 | 02/2025 | 03/2025 | 963 | 1046 | 911.66 | 95
August 2025 | 629 | Ministry of Railways | Railways | Katihar - Kumedpur Doubling Line Project | GM/C/ NFR | 706844 | Multi-States (Bihar, West Bengal) | 08/2022 |  | 08/2027 | 08/2027 | 942 | 942 | 356 | 45
August 2025 | 630 | Ministry of Railways | Railways | Rajnandgaon - Nagpur [Kalumna] Third Railway Line [228.30 km] | South East Central Railway [SECR] - II | 705617 | Multi-States (Chhattisgarh, Maharashtra) | 09/2016 | 12/2016 | 12/2024 | 06/2026 | 3545 | 3545 | 3428.26 | 95
August 2025 | 631 | Ministry of Railways | Railways | Jagdalpur-Koraput | East Coast Railway [ECoR] - II | 705511 | Multi-States (Chhattisgarh, Odisha) | 12/2015 | 03/2016 | 03/2024 | 12/2026 | 1547 | 1547 | 1323.05 | 90
August 2025 | 632 | Ministry of Railways | Railways | Jharsuguda-Bilaspur Fourth Railway Line [206 km] | SECR | 705616 | Multi-States (Chhattisgarh, Odisha) | 09/2016 | 09/2016 | 10/2024 | 12/2025 | 2140 | 2979 | 2143.64 | 89
August 2025 | 633 | Ministry of Railways | Railways | Mumbai-Ahmedabad High Speed Rail Project- 508 km | National High Speed Rail Corporation [NHSRC] | 705728 | Multi-States (Dadra & Nagar Haveli and Daman & Diu, Gujarat, Maharashtra) | 03/2015 | 09/2017 | 08/2027 | 12/2029 | 108000 | 108000 | 79918.89 | 53
August 2025 | 634 | Ministry of Railways | Railways | New Delhi- Mumbai Speed Booster[160Kmph] Project | PCE/WR | 705793 | Multi-States (Delhi, Gujarat, Madhya Pradesh, Maharashtra, Rajasthan) | NA | 09/2019 | 03/2024 | - | 6806.44 | 6806.44 | 135.65 | 0
August 2025 | 635 | Ministry of Railways | Railways | Hospet - Tinaighat - Vasco Rail Doubling Project | RVNL - II | 705650 | Multi-States (Goa, Karnataka) | 03/2010 | 07/2012 | 03/2027 | 12/2027 | 5060 | 5060 | 5007.82 | 86
August 2025 | 636 | Ministry of Railways | Railways | Hospet-Hubli-Vasco da Gama Line Electrification Project | RVNL | 706950 | Multi-States (Goa, Karnataka) | NA | 05/2018 | 03/2023 | 03/2024 | 744.49 | 1122.62 | 969.05 | 95
August 2025 | 637 | Ministry of Railways | Railways | Western Dedicated Freight Corridor | DFCCIL | 705237 | Multi-States (Gujarat, Haryana, Maharashtra, Rajasthan, Uttar Pradesh) | 02/2008 | 01/2012 | 03/2022 | 12/2025 | 51101 | 124005 | 124623 | 96
August 2025 | 638 | Ministry of Railways | Railways | New line Dahod-Indore via Sardarpur, Jabuwa and Dhar | Western Railway [WR] - II | 705453 | Multi-States (Gujarat, Madhya Pradesh) | 06/2012 | 06/2012 | 02/2027 | 02/2027 | 456.07 | 1873.1 | 3412.33 | 46
August 2025 | 639 | Ministry of Railways | Railways | Chhota Udaipur - Dhar New Line Project [157 km] | Western Railway [WR] - II | 705454 | Multi-States (Gujarat, Madhya Pradesh) | 11/2008 | 01/2014 | 12/2025 | 12/2025 | 1794 | 1794 | 1804.05 | 80
August 2025 | 640 | Ministry of Railways | Railways | MUMBAI CENTRAL VIRAR VADODARA AHMEDABAAD TRAIN PROTECTION SYSTEM 500 RKM | Western Railway | 611452 | Multi-States (Gujarat, Maharashtra) | 09/2019 | 03/2023 | 12/2025 | 06/2025 | 311 | 311 | 208 | 92
August 2025 | 641 | Ministry of Railways | Railways | Taranga Hill-Abu Road via Ambaji | North Western Railway [NWR] | 400022 | Multi-States (Gujarat, Rajasthan) | 07/2022 | 07/2022 | 07/2030 | 07/2030 | 2798 | 2798 | 1915.38 | 15
August 2025 | 642 | Ministry of Railways | Railways | LUNI- SAMDARI- BHILDI DOUBLING | North Western Railway [NWR] | 616842 | Multi-States (Gujarat, Rajasthan) | 02/2024 | 02/2024 | 07/2027 | - | 3085.59 | 3085.59 | 171.32 | 7
August 2025 | 643 | Ministry of Railways | Railways | Chandigarh-Baddi New Rail Line- 36 km | Northen Railway [NR] | 705424 | Multi-States (Haryana, Himachal Pradesh) | 02/2018 | 02/2018 | 12/2026 | 12/2026 | 1540 | 1540.13 | 506.73 | 31
August 2025 | 644 | Ministry of Railways | Railways | Rewari - Kathuwas Doubling Project [27.72 Km] | North Western Railway [NWR] | 611861 | Multi-States (Haryana, Rajasthan) | 02/2023 | 12/2022 | 06/2027 | 06/2027 | 352 | 352 | 246.11 | 63
August 2025 | 645 | Ministry of Railways | Railways | Nangal Dam-Talwara New Broad Gauge Line [84 KM] and Taking Over Siding Mukerian-Talwara [29 KM] | Northen Railway [NR] | 705410 | Multi-States (Himachal Pradesh, Punjab) | 03/1983 | 05/1985 | 12/2025 | 01/2027 | 2018 | 2018 | 2053.9 | 45
August 2025 | 646 | Ministry of Railways | Railways | Bhanupalli-Bilaspur-Beri New Railway Line Project | RVNL - II | 705428 | Multi-States (Himachal Pradesh, Punjab) | 03/2009 | 04/2015 | 12/2026 | 12/2027 | 13447 | 13447 | 6805.81 | 60
August 2025 | 647 | Ministry of Railways | Railways | Doubling of Hatia [Ranchi]-Bondamunda Rail Line - 159 km | South Eastern Railway - JH | 705628 | Multi-States (Jharkhand, Odisha) | 03/2016 | 02/2017 | 06/2025 | 06/2026 | 3029 | 3029 | 2470.12 | 85
August 2025 | 648 | Ministry of Railways | Railways | Buramara-Chakulia new line [59.96 km] | South Eastern Railway [SER] - I | 616588 | Multi-States (Jharkhand, Odisha, West Bengal) | 08/2024 | 12/2024 | 12/2029 | - | 1459.13 | 1459.13 | 2.11 | 0
August 2025 | 649 | Ministry of Railways | Railways | Chandil - Anara - Damodar - 3rd line [121.26 km] | CAO/C/SER | 616227 | Multi-States (Jharkhand, West Bengal) | NA | 07/2025 | 09/2029 | - | 1932.01 | 1932.01 | 0.03 | 0
August 2025 | 650 | Ministry of Railways | Railways | KHARAGPUR-ADITYAPUR THIRD RAIL LINE- 132 KM | RVNL - II | 705668 | Multi-States (Jharkhand, West Bengal) | 09/2016 | 01/2018 | 03/2025 | 12/2025 | 3250 | 3250 | 3176.46 | 97
August 2025 | 651 | Ministry of Railways | Railways | Hotgi-Kudgi-Gadag Doubling Project | South Western Railway [SWR] - II | 705662 | Multi-States (Karnataka, Maharashtra) | 04/2014 | 01/2016 | 12/2024 | 03/2026 | 1878 | 2459 | 2642.04 | 92
August 2025 | 652 | Ministry of Railways | Railways | Baiyyappanahalli - Hosur Doubling Project [48 km] | Karnataka Rail Infrastructure Development Company Limited [K-RIDE] | 703586 | Multi-States (Karnataka, Tamil Nadu) | 04/2019 | 02/2019 | 12/2024 | 01/2026 | 499 | 499 | 595 | 97
August 2025 | 653 | Ministry of Railways | Railways | Trivandrum- Kanyakumari | Southern Railway (SR) - I | 705635 | Multi-States (Kerala, Tamil Nadu) | 08/2017 | 03/2016 | 03/2024 | 12/2027 | 1432 | 3785 | 2451 | 46
August 2025 | 654 | Ministry of Railways | Railways | Ratlam-Mhow-Khandwa-Akola Gauge Conversion | Western Railway [WR] - II | 705457 | Multi-States (Madhya Pradesh, Maharashtra) | 04/2008 | 03/2010 | 03/2027 | 09/2028 | 1656.25 | 5735.88 | 4428.77 | 80
August 2025 | 655 | Ministry of Railways | Railways | Itarsi - Nagpur Third Railway Line [280 km] | Central Railway [CR] - II | 705507 | Multi-States (Madhya Pradesh, Maharashtra) | 09/2016 | 09/2016 | 03/2027 | 03/2027 | 2449.91 | 2506.68 | 1843.76 | 51
August 2025 | 656 | Ministry of Railways | Railways | Gwalior - Seopurkala with extension to Kota [Gauge Conversion] | North Central Railway | 705419 | Multi-States (Madhya Pradesh, Rajasthan) | 03/2011 | 07/2018 | 03/2025 | 02/2026 | 2913 | 2913 | 2097.51 | 78
August 2025 | 657 | Ministry of Railways | Railways | Ramganjmandi-Bhopal New Line Project [262 km] | West Central Railway [WCR] - II | 705481 | Multi-States (Madhya Pradesh, Rajasthan) | 03/2001 | 10/2004 | 12/2025 | 12/2027 | 3032 | 5073 | 3621.79 | 70
August 2025 | 658 | Ministry of Railways | Railways | Nimach-Badi Sadri New Rail Line Project | Western Railway [WR] - II | 705764 | Multi-States (Madhya Pradesh, Rajasthan) | 04/2017 | 09/2021 | 03/2026 | 06/2026 | 495 | 825 | 79.55 | 53
August 2025 | 659 | Ministry of Railways | Railways | Mathura-Jhansi Third Railway Line [274 Km] | RVNL - II | 705667 | Multi-States (Madhya Pradesh, Rajasthan, Uttar Pradesh) | 12/2015 | 03/2018 | 12/2024 | 12/2026 | 5961 | 5961 | 4928.62 | 94
August 2025 | 660 | Ministry of Railways | Railways | Jhansi - Bina Third Railway Line [153 Km] | CAO/C/NCR | 705598 | Multi-States (Madhya Pradesh, Uttar Pradesh) | 09/2016 | 03/2018 | 03/2022 | 03/2026 | 2002 | 2002 | 1795.86 | 93
August 2025 | 661 | Ministry of Railways | Railways | Jhansi-Khairar-Manikpur & Khirar-Bhimsen | North Central Railway | 705608 | Multi-States (Madhya Pradesh, Uttar Pradesh) | 03/2018 | 03/2017 | 03/2026 | 03/2026 | 4330 | 4330 | 2184.56 | 55
August 2025 | 662 | Ministry of Railways | Railways | Third Line [new] between Kazipet - Balharshah with electrification [201.04 Km] | South Central Railway [SCR] - II | 705613 | Multi-States (Maharashtra, Telangana) | 09/2016 | 10/2016 | 01/2025 | 11/2025 | 2595 | 3071 | 3223.67 | 93
August 2025 | 663 | Ministry of Railways | Railways | Narayangarh-Bhadrak 3rd line | South Eastern Railway [SER] - I | 705629 | Multi-States (Odisha, West Bengal) | 03/2019 | 03/2017 | 12/2025 | 06/2026 | 2400 | 2400 | 2236.9 | 65
August 2025 | 664 | Ministry of Railways | Railways | Nagapattinam-Tiruturaipundi and Karaikal-Peralam New Line | Southern Railway [SR] - II | 400223 | Multi-States (Puducherry, Tamil Nadu) | 07/2008 | 01/2019 | 03/2026 | 03/2027 | 713 | 981 | 598.38 | 80
August 2025 | 665 | Ministry of Railways | Railways | Sivok-Rangpo New Rail Line | Indian Railway Construction International Limited [IRCON] | 705432 | Multi-States (Sikkim, West Bengal) | 10/2009 | 05/2010 | 05/2015 | 12/2027 | 7877 | 12133 | 9039.91 | 84
August 2025 | 666 | Ministry of Railways | Railways | Sainthia, Sitarampur, Mughalsarai, Allahabad & Etawah - Bypass Line Project | Eastern Railway [ER] - I | 602797 | Multi-States (Uttar Pradesh, West Bengal) | 08/2017 | 12/2017 | 03/2027 | 03/2027 | 461.64 | 461.64 | 186.03 | 7
August 2025 | 667 | Ministry of Railways | Railways | Proposed 6 nos Road Over Bridge [ROB] at different locations under MCL Talcher Under Deposit Scheme. | East Coast Railway [ECoR] - II | 400045 | Odisha | 08/2022 | 07/2022 | 03/2025 | 01/2025 | 168.32 | 168.32 | 69.85 | 82
August 2025 | 668 | Ministry of Railways | Railways | Brundamal-Jharsuguda- flyover connection for joining downline | East Coast Railway [ECoR] - II | 400232 | Odisha | 01/2014 | 01/2014 | 12/2026 | 12/2026 | 297 | 297 | 193.22 | 30
August 2025 | 669 | Ministry of Railways | Railways | 3rd & 4th line between Sarla - Sason [8 km] [PB 73/2023-24/NR] | East Coast Railway [ECoR] - II | 612834 | Odisha | 04/2023 | 04/2023 | 12/2025 | - | 252 | 252 | 79.55 | 45
August 2025 | 670 | Ministry of Railways | Railways | Bangriposi-Gorumahisani new line [ 85.60 km ] | CAO/C/SER | 616586 | Odisha | 08/2024 | 09/2025 | 12/2029 | - | 2269.49 | 2269.49 | 2.31 | 0
August 2025 | 671 | Ministry of Railways | Railways | Badampahar-Kendujhargarh new line [82.06 km] | CAO/C/SER | 616587 | Odisha | 08/2024 | 09/2025 | 12/2029 | - | 1875.72 | 1875.72 | 0.53 | 0
August 2025 | 672 | Ministry of Railways | Railways | Flyover between Siju and Paradeep coaching Yard to avoid Surface crossing of trains | East Coast Railway [ECoR] - II | 616694 | Odisha | 04/2023 | 10/2025 | 07/2028 | - | 200.77 | 200.77 | 0 | 0
August 2025 | 673 | Ministry of Railways | Railways | Paradeep - Badabandha 3rd & 4th Line / 18.51kms | East Coast Railway [ECoR] - II | 616695 | Odisha | 08/2023 | 04/2025 | 11/2028 | - | 300.15 | 300.15 | 0.01 | 0
August 2025 | 674 | Ministry of Railways | Railways | Khurda-Bolangir New Broad Gauge Rail Link [301km] | East Coast Railway [ECoR] - II | 705358 | Odisha | 03/1994 | 03/2001 | 12/2026 | 12/2026 | 3792 | 5089 | 5027.62 | 89
August 2025 | 675 | Ministry of Railways | Railways | Talcher-Bimlagarh New Railway Line | East Coast Railway [ECoR] - II | 705359 | Odisha | 03/2004 | 12/2004 | 03/2025 | 03/2027 | 1928 | 1928 | 1934.28 | 48
August 2025 | 676 | Ministry of Railways | Railways | Bhadrak-Nergundi Third Line | East Coast Railway [ECoR] - II | 705510 | Odisha | 10/2015 | 04/2015 | 11/2024 | 01/2026 | 1284 | 1284 | 1298 | 80
August 2025 | 677 | Ministry of Railways | Railways | Koraput - Singapur Railway Doubling | East Coast Railway [ECoR] - II | 705513 | Odisha | 12/2015 | 12/2015 | 12/2027 | 03/2028 | 2362 | 2362 | 1798.71 | 68
August 2025 | 678 | Ministry of Railways | Railways | Jarapada- Budhapank with flyover at Talcher road 3rd and 4th Line | East Coast Railway [ECoR] - II | 705514 | Odisha | NA | 12/2015 | 11/2018 | 03/2026 | 1000 | 810.02 | 401.61 | 36
August 2025 | 679 | Ministry of Railways | Railways | 3rd & 4th Railway Line Project from Salegaon to Budhapank via Rajathgarh. | East Coast Railway [ECoR] - II | 705515 | Odisha | 07/2013 | 12/2015 | 03/2026 | 03/2026 | 1173 | 2092 | 1971 | 80
August 2025 | 680 | Ministry of Railways | Railways | Jeypore-Navarangpur New Rail Line Project | East Coast Railway [ECoR] - II | 705741 | Odisha | 07/2017 | 04/2023 | 07/2028 | 12/2029 | 748 | 748 | 10.56 | 1
August 2025 | 681 | Ministry of Railways | Railways | Jeypore-Malkanagiri New Railway Line Project | East Coast Railway [ECoR] - II | 705742 | Odisha | 02/2018 | 12/2023 | 07/2033 | 07/2033 | 2344 | 2344 | 225.84 | 8
August 2025 | 682 | Ministry of Railways | Railways | Talcher-Angul New Line with Y-Connection at Talcher | CAO/C/ECoR | 705743 | Odisha | 07/2018 |  | 05/2027 | 05/2028 | 495 | 495 | 29.5 | 1
August 2025 | 683 | Ministry of Railways | Railways | Baghuapal Flyover Construction Project | CAO/C/ECoR | 705767 | Odisha | 08/2019 | 10/2022 | 03/2028 | 03/2028 | 257.97 | 258 | 0.83 | 0
August 2025 | 684 | Ministry of Railways | Railways | Khurda Road - Balangir Electrification of Railway Track Project | Ministry of Railways | 706898 | Odisha | NA | 09/2019 | 03/2021 | - | 267.61 | 267.61 | 0 | 0
August 2025 | 685 | Ministry of Railways | Railways | KODINGAMALI BAUXITE MINES TO SINGARAM RAILWAY STATION | Indian Railway | 709810 | Odisha | 08/2022 | 01/2026 | 08/2027 | 08/2027 | 190.9 | 190.9 | 0 | 0
August 2025 | 686 | Ministry of Railways | Railways | GANDHAMARDAN IRON ORE MINES TO GOALDIH STATION/12.76kms | East Coast Railway [ECoR] - II | 709811 | Odisha | 09/2022 | 05/2025 | 09/2027 | 09/2027 | 190 | 190 | 0 | 0
August 2025 | 687 | Ministry of Railways | Railways | Junagarh Visavadar 42 Kms | Railway | 611980 | Offshore | 06/2022 | 02/2023 | 09/2028 | 09/2028 | 492.83 | 492.83 | 3 | 1
August 2025 | 688 | Ministry of Railways | Railways | Jaynagar-Bijalpura, incl. extn. Bet, Bijalpura-Bardibas [Nepal] | East Central Railway [ECR] - I | 705362 | Offshore | 08/2015 | 03/2011 | 03/2022 | 03/2026 | 819 | 819 | 580.6 | 75
August 2025 | 689 | Ministry of Railways | Railways | Ludhiana- Killa Raipur Railway Doubling Project | Railway | 705783 | Punjab | 03/2019 | 12/2022 | 03/2025 | 03/2026 | 237.64 | 237.64 | 118 | 55
August 2025 | 690 | Ministry of Railways | Railways | Dedicated Test Track for RDSO Phase II | North Western Railway [NWR] | 611614 | Rajasthan | 11/2021 | 11/2021 | 11/2026 | 11/2026 | 819.48 | 967.06 | 471 | 86
August 2025 | 691 | Ministry of Railways | Railways | Devgarh Madariya - Nathdwara Gauge Conversion [82.54 Km] part of Marwar - Mavli Gauge Conversion [152 Km] | North Western Railway [NWR] | 611849 | Rajasthan | 01/2023 | 01/2023 | 06/2028 | 06/2028 | 968.92 | 968.92 | 98.62 | 51
August 2025 | 692 | Ministry of Railways | Railways | Maintenance cum workshop depot for Vande Bharat Sleeper Trains as per conditions under WTA 527 | WPO/Patna | 611929 | Rajasthan | NA | 06/2023 | 12/2024 | - | 166.86 | 166.86 | 0 | 0
August 2025 | 693 | Ministry of Railways | Railways | RINGUS KHATUSHYAMJI NEW LINE | North Western Railway [NWR] | 616696 | Rajasthan | 03/2024 | 03/2024 | 03/2028 | - | 254.06 | 254.06 | 2.94 | 0
August 2025 | 694 | Ministry of Railways | Railways | RAS- MERTA CITY NEW LINE INCL BYPASS AT MERTA ROAD | North Western Railway [NWR] | 616840 | Rajasthan | NA | 02/2024 | 03/2028 | - | 947 | 947 | 1.36 | 0
August 2025 | 695 | Ministry of Railways | Railways | PUSHKAR- MERTA CITY NEW LINE | North Western Railway [NWR] | 616841 | Rajasthan | 02/2024 | 02/2024 | 12/2026 | - | 799.64 | 799.64 | 14.5 | 4
August 2025 | 696 | Ministry of Railways | Railways | AJMER- CHANDERIYA DOUBLING | North Western Railway [NWR] | 616843 | Rajasthan | 02/2024 | 02/2024 | 06/2027 | - | 1634.79 | 1634.79 | 74.43 | 6
August 2025 | 697 | Ministry of Railways | Railways | Dholpur - Sirmuttra Gauge Conversion | North Central Railway | 705482 | Rajasthan | 03/2022 | 04/2020 | 02/2019 | 02/2027 | 747 | 747 | 355.13 | 43
August 2025 | 698 | Ministry of Railways | Railways | Gudha-Thatha Mithri Construction of Railway Track Project | North Western Railway [NWR] | 705752 | Rajasthan | 04/2019 | 04/2019 | 11/2026 | 11/2026 | 819.48 | 967.06 | 471 | 98
August 2025 | 699 | Ministry of Railways | Railways | Sawai Madhopur-Jaipur Railway Line Project | North Western Railway [NWR] | 705912 | Rajasthan | NA | 04/2023 | 03/2027 | - | 1203.89 | 1203.89 | 46.07 | 7
August 2025 | 700 | Ministry of Railways | Railways | Agra Fort-Bandikui Doubling Line Project | CAO/C/NCR | 705919 | Rajasthan | 06/2022 | 02/2021 | 06/2027 | 06/2027 | 1390 | 1390 | 123 | 25
August 2025 | 701 | Ministry of Railways | Railways | Sawaimadhopur Bye Pass Line Project | North Western Railway [NWR] | 706866 | Rajasthan | 12/2022 | 01/2023 | 03/2026 | 05/2027 | 304 | 304 | 43.07 | 44
August 2025 | 702 | Ministry of Railways | Railways | Ph II extension of MRTS from Velachery to St Thomas Mount | Southern Railways [SR] - construction | 400280 | Tamil Nadu | 11/2007 | 11/2008 | 07/2024 | 08/2025 | 734 | 982 | 475.73 | 99
August 2025 | 703 | Ministry of Railways | Railways | Redevelopment of Chennai Egmore Station | Railway | 613002 | Tamil Nadu | NA | 10/2022 | 03/2026 | - | 842 | 842 | 340 | 0
August 2025 | 704 | Ministry of Railways | Railways | Coach Production Factory Upgradation Project | CPM/ICF | 705244 | Tamil Nadu | NA | 07/2018 | 12/2021 | - | 520 | 520 | 192.25 | 0
August 2025 | 705 | Ministry of Railways | Railways | Morappur - Dharmpuri New Railway Line Project | Southern Railway [SR] - I | 705755 | Tamil Nadu | 05/2019 | 12/2016 | 03/2028 | 03/2028 | 359 | 359 | 40 | 1
August 2025 | 706 | Ministry of Railways | Railways | Doubling between Bhadrachalam Road and Dornakal | South Central Railway [SCR] - II | 616856 | Telangana | NA | 04/2025 | 04/2029 | - | 770.12 | 770.12 | 0 | 0
August 2025 | 707 | Ministry of Railways | Railways | Kazipet Wagon Overhauling Project | RVNL | 705252 | Telangana | NA | 07/2017 | 12/2023 | - | 385 | 385 | 0 | 0
August 2025 | 708 | Ministry of Railways | Railways | Manoharabad-Kothapalli New Rail Line [151 km] | South Central Railway [SCR] - II | 705437 | Telangana | 07/2016 | 01/2017 | 03/2027 | 12/2027 | 1160 | 2781 | 1771.32 | 71
August 2025 | 709 | Ministry of Railways | Railways | Bahraich-Shravasti-Balrampur-Siddharthnagar -Santkabir nagar | North Eastern Railway [NER] | 400204 | Uttar Pradesh | 10/2018 | 03/2017 | 10/2030 | 10/2030 | 4939.78 | 4939.78 | 1232.64 | 8
August 2025 | 710 | Ministry of Railways | Railways | Sahjanwa-Dohrighat | North Eastern Railway [NER] | 400205 | Uttar Pradesh | 08/2019 | 03/2017 | 03/2029 | 03/2029 | 1319.75 | 1319.75 | 460.2 | 3
August 2025 | 711 | Ministry of Railways | Railways | Anandnagar - Ghugli via Maharajganj New line 52.7 km | Construction NER | 617252 | Uttar Pradesh | 10/2023 | 11/2023 | 03/2028 | - | 958.27 | 958.27 | 436.95 | 23
August 2025 | 712 | Ministry of Railways | Railways | Chunar-Chopan doubling project | North Central Railway | 617284 | Uttar Pradesh | 08/2023 | 01/2025 | 03/2028 | - | 1423.96 | 1423.96 | 49.57 | 2
August 2025 | 713 | Ministry of Railways | Railways | Domingarh-Gorakhpur-Gorakhpur Cantt.-Kusumhi - 3rd Railway Line Project | North Eastern Railway [NER] | 705566 | Uttar Pradesh | 11/2016 | 06/2018 | 02/2025 | 09/2025 | 351 | 521.47 | 495.86 | 98
August 2025 | 714 | Ministry of Railways | Railways | Burhwal Gonda 3rd line | North Eastern Railway [NER] | 705567 | Uttar Pradesh | 11/2017 | 07/2019 | 03/2025 | 09/2025 | 1016 | 1118 | 1373.8 | 73
August 2025 | 715 | Ministry of Railways | Railways | Janghai-Pratapgarh- Amethi | CAO/C/II/NR | 705588 | Uttar Pradesh | 11/2017 | 03/2017 | 03/2025 | 03/2026 | 722 | 1194 | 1550 | 70
August 2025 | 716 | Ministry of Railways | Railways | Lalitpur-Birari with flyover at Lalitpur- 16 Km | North Central Railway | 705766 | Uttar Pradesh | 03/2017 | 03/2017 | 12/2024 | 11/2025 | 304.44 | 356 | 220.8 | 72
August 2025 | 717 | Ministry of Railways | Railways | Allahabad-Bamhrauli Flyover Construction & 4th Railway Line Project | North Central Railway | 705771 | Uttar Pradesh | 04/2019 | 10/2020 | 03/2026 | 03/2026 | 494 | 494 | 333 | 70
August 2025 | 718 | Ministry of Railways | Railways | Mughalsarai-Allahabad, 3rd line | North Central Railway | 705772 | Uttar Pradesh | 12/2015 | 03/2016 | 12/2026 | 03/2027 | 2649 | 2649.44 | 1561.89 | 62
August 2025 | 719 | Ministry of Railways | Railways | Aligarh -Daud Khan Flyover Construction & 3rd Railway Line Project | CAO/C/NCR | 705774 | Uttar Pradesh | 04/2019 | 09/2020 | 01/2025 | 03/2027 | 758 | 779.49 | 315.37 | 55
August 2025 | 720 | Ministry of Railways | Railways | Bhandai - Flyover for Etawah bound down train- 10 Km | North Central Railway (NCR) - II | 705777 | Uttar Pradesh | 07/2020 | 04/2021 | 02/2026 | 02/2027 | 250.18 | 250.18 | 113.94 | 3
August 2025 | 721 | Ministry of Railways | Railways | Phephna-Indara, Mau-Shahganj doubling excluding Indara-Mau | South Eastern Railway [SER] - I | 705779 | Uttar Pradesh | 05/2017 | 03/2017 | 12/2024 | 03/2026 | 1178 | 1777 | 1489.5 | 85
August 2025 | 722 | Ministry of Railways | Railways | Bhatni-Aurnihar with electrification excluding Indara-Mau | RVNL - II | 705780 | Uttar Pradesh | 03/2018 | 03/2017 | 12/2024 | 10/2025 | 2529 | 2529.46 | 2051.69 | 94
August 2025 | 723 | Ministry of Railways | Railways | Barabanki-Malhaur 3rd & 4th Railway Line Project | CAO/C/NR | 705782 | Uttar Pradesh | 01/2019 | 04/2017 | 03/2025 | 03/2026 | 407 | 407 | 317 | 75
August 2025 | 724 | Ministry of Railways | Railways | Janghai-Phaphamau Doubling Rail Line Project | RVNL | 705784 | Uttar Pradesh | 11/2018 | 03/2020 | 03/2025 | 03/2025 | 357 | 978.77 | 579 | 95
August 2025 | 725 | Ministry of Railways | Railways | Bahraich - Nanpara - Nepalganj Road Gauge Conversion | North Eastern Railway [NER] | 705863 | Uttar Pradesh | 07/2020 | 04/2021 | 07/2025 | 09/2025 | 950 | 550 | 511.18 | 90
August 2025 | 726 | Ministry of Railways | Railways | Allahabad division - Aligarh - Harduaganj Flyover | North Central Railway | 705918 | Uttar Pradesh | 04/2020 | 02/2021 | 06/2026 | 03/2027 | 1457 | 1457 | 50 | 14
August 2025 | 727 | Ministry of Railways | Railways | DOUBLING BETWEEN JAUNPUR JN-ZAFFARABAD [6.28 KM] | Northen Railway [NR] | 900872 | Uttar Pradesh | 01/2023 |  | 01/2027 | 12/2028 | 177 | 177 | 41 | 10
August 2025 | 728 | Ministry of Railways | Railways | Rishikesh-Karnaprayag New Rail Line- 125 km | RVNL - II | 705429 | Uttarakhand | 11/2016 | 08/2018 | 12/2025 | 03/2027 | 38953 | 38953 | 24645.15 | 65
August 2025 | 729 | Ministry of Railways | Railways | Kalinarayanpur-Krishnanagar Doubling Alongwith Krishnanagar - Chapra New Line And Naihati-Ranaghat 3rd Line. | Eastern Railway [ER] - I | 400247 | West Bengal | 07/2015 | 11/2005 | 02/2027 | 02/2027 | 1000 | 1000 | 1031.21 | 67
August 2025 | 730 | Ministry of Railways | Railways | Tarakeshwar-Bishnupur New Line [82.47 km] | Eastern Railway [ER] - I | 400273 | West Bengal | 03/2001 | 02/2008 | 03/2019 | 02/2026 | 1189 | 1542 | 1307.52 | 90
August 2025 | 731 | Ministry of Railways | Railways | Dum Dum Airport-New Garia via Rajarhat-Construction of Metro Railway | RVNL - II | 400277 | West Bengal | 03/2010 | 10/2011 | 12/2025 | 03/2026 | 8964 | 8964 | 8097.47 | 80
August 2025 | 732 | Ministry of Railways | Railways | Construction of Balurghat-Hilli new BG Line | Northeast Frontier Railway [NFR] | 612096 | West Bengal | 12/2010 | 12/2010 | 03/2027 | 03/2025 | 1209 | 1209 | 405.31 | 9
August 2025 | 733 | Ministry of Railways | Railways | Kalipahari Bakhtarnagar 5th line | Eastern Railway [ER] - I | 617322 | West Bengal | 08/2024 | 07/2025 | 06/2027 | 06/2027 | 350.46 | 350.46 | 0 | 0
August 2025 | 734 | Ministry of Railways | Railways | Joka-BBD Bag new metro project | RVNL - II | 705730 | West Bengal | 03/2010 | 04/2010 | 12/2026 | 12/2028 | 4835 | 10362 | 4373.24 | 60
August 2025 | 735 | Ministry of Railways | Railways | Noapara-Barasat via Bimanbandar - Construction of Metro railway [18 km] | Metro Railway, Kolkata | 706776 | West Bengal | 11/2010 | 03/2010 | 08/2026 | 03/2029 | 4830 | 4830 | 2764.13 | 32
August 2025 | 736 | Ministry of Railways | Railways | Baranagar-Barrackpore and Dakshineshwar- Construction of Metro Railway | RVNL - II | 706777 | West Bengal | 03/2010 | 03/2010 | 12/2026 | 12/2025 | 2298 | 2734 | 393 | 17
August 2025 | 737 | Department for Promotion of Industry & Internal Trade | Real Estate | Krishnapatnam Node - Phase 1 - Roads and Services Development | National Industrial Corridor Development Corporation | 701658 | Andhra Pradesh | 12/2020 | 02/2024 | 02/2028 | - | 2139.44 | 2139.44 | 406.05 | 17
August 2025 | 738 | Department for Promotion of Industry & Internal Trade | Real Estate | Tumakuru Node - Phase 1 - Roads and Services Development | National Highways & Infrastructure Development Corporation Ltd. [NHIDCL] | 701657 | Karnataka | 12/2020 | 02/2023 | 09/2026 | - | 1701.81 | 1701.81 | 88.25 | 8
August 2025 | 739 | Department of Telecommunications | Telecommunication | SETTING UP OF PHYSICAL INFRASTRUCTURE FOR THE NATIONAL INSTITUTE OF COMMUNICATION FINANCE [NICF] AT GHITORNI | National Communication Academy - Finance (Erstwhile NICF | 709859 | Delhi | 10/2014 | 04/2018 | 02/2020 | 10/2025 | 248.2 | 248.2 | 236.91 | 98
August 2025 | 740 | Department of Telecommunications | Telecommunication | Provision of 4G based Mobile Services in Uncovered Villages and National Highways of Meghalaya | Department of Telecommunications [DoT] | 701598 | Meghalaya | 09/2019 | 09/2020 | 03/2022 | 09/2025 | 971.96 | 971.96 | 208.25 | 99
August 2025 | 741 | Department of Telecommunications | Telecommunication | Mobile connectivity in Left Wing Extremism [LWE] affected areas-Phase2 | Department of Telecommunications [DoT] | 701599 | Multi-States (Andhra Pradesh, Bihar, Chhattisgarh, Jharkhand, Madhya Pradesh, Maharashtra, Odisha, Telangana, Uttar Pradesh, West Bengal) | NA | 09/2021 | 03/2023 | 11/2025 | 1577.57 | 1577.57 | 598.31 | 87
August 2025 | 742 | Department of Telecommunications | Telecommunication | Provision of 4G based mobile services in 7,287 uncovered villages of 44 Aspirational District across 5 states of Andhra Pradesh, Chhattisgarh, Jharkhand, Maharashtra & Odisha | Department of Telecommunications [DoT] | 701602 | Multi-States (Andhra Pradesh, Chhattisgarh, Jharkhand, Maharashtra, Odisha) | 11/2021 | 05/2022 | 11/2023 | 11/2025 | 3685 | 3685 | 1101.44 | 79
August 2025 | 743 | Department of Telecommunications | Telecommunication | Provision of 4G Mobile Services in Uncovered Villages of Arunachal Pradesh and 2 Districts of Assam | Department of Telecommunications [DoT] | 701597 | Multi-States (Arunachal Pradesh, Assam) | 12/2020 | 10/2021 | 04/2023 | 09/2025 | 1255.49 | 1255.49 | 284.04 | 89
August 2025 | 744 | Department of Telecommunications | Telecommunication | 354 Uncovered Villages Scheme | Department of Telecommunications [DoT] | 701600 | Multi-States (Bihar, Gujarat, Himachal Pradesh, Jammu and Kashmir, Ladakh, Rajasthan, Uttar Pradesh) | 12/2019 | 04/2020 | 10/2021 | 08/2025 | 336.89 | 301.13 | 227.82 | 97
August 2025 | 745 | Department of Telecommunications | Telecommunication | 502 Aspirational District Scheme in Four states - Bihar, Madhya Pradesh, Rajastha and Uttar Pradesh | Department of Telecommunications [DoT] | 704495 | Multi-States (Bihar, Madhya Pradesh, Rajasthan, Uttar Pradesh) | NA | 03/2021 | 03/2022 | 12/2025 | 421.65 | 228.94 | 134.08 | 96
August 2025 | 746 | Department of Telecommunications | Telecommunication | PHASE-I OF CONSOLIDATION OF EXISTING CDR DATA CENTERS AND NIB-P3 DATA CENTERS WITH STATE OF THE ART | BSNL | 709749 | Multi-States (Maharashtra, Telangana) | NA | 03/2020 | 06/2021 | 12/2025 | 461.42 | 461.42 | 166.02 | 81
August 2025 | 747 | Department of Telecommunications | Telecommunication | Saturation 4G mobile coverage of Uncovered Villages through USOF | Department of Telecommunications [DoT] | 400013 | PAN India | 07/2022 | 07/2022 | 06/2024 | 03/2026 | 26316 | 30620 | 9791.8 | 73
August 2025 | 748 | Department of Telecommunications | Telecommunication | 4G Services by BSNL | Department of Telecommunications [DoT] | 701593 | PAN India | 11/2020 | 11/2020 | 03/2024 | 03/2026 | 28466 | 19592 | 8390.32 | 96
August 2025 | 749 | Department of Telecommunications | Telecommunication | BharatNet | Department of Telecommunications [DoT] | 706775 | PAN India | 07/2017 | 10/2011 | 08/2023 | 03/2027 | 61109 | 188000 | 41486.14 | 81
August 2025 | 750 | Department of Telecommunications | Telecommunication | MPLS-IP BASED ACCESS AND AGGREGATION NETWORK [MAAN] IN BSNL ALONG WITH TEST AND MEASURING EQUIPMENT | BSNL | 709856 | PAN India | NA | 05/2023 | 08/2024 | 10/2025 | 645.13 | 645.13 | 364.34 | 91
August 2025 | 751 | Department of Telecommunications | Telecommunication | Planning, Engineering, Supply, Installation, Testing, Commissioning, Integration & Annual Maintenance of 4G mobile network at 1 Lakh sites on PAN India basis including Mumbai & Delhi LSA on turnkey basis under Phase IX.2 Project. | BSNL | 709857 | PAN India | NA | 06/2023 | 06/2025 | 03/2026 | 24544.55 | 24544.5 | 8391.17 | 96
August 2025 | 752 | Department of Telecommunications | Telecommunication | OPTICAL TRANSPORT NETWORK [OTN] PH-4 IN BSNL | BSNL | 709858 | PAN India | NA | 02/2024 | 08/2025 | 10/2025 | 810.99 | 810.99 | 741.9 | 100
August 2025 | 753 | Department of Water Resources, River Development & GR | Waste & Water | Interception and Diversion and STP works in Bhagalpur under Hybrid annuity based PPP mode-Namami Gange Programme | National Mission for Clean Ganga | 616600 | Bihar | 10/2017 | 03/2022 | 02/2025 | 12/2025 | 413.29 | 413.29 | 126.67 | 97
August 2025 | 754 | Department of Water Resources, River Development & GR | Waste & Water | Sewage Treatment Plant 100MLD and Sewerage Network 288 km in Digha-Patna under Hybrid annuity based PPP mode-Namami Gange Programme | National Mission for Clean Ganga | 616611 | Bihar | 08/2017 | 07/2019 | 12/2025 | - | 824 | 824 | 396.71 | 56
August 2025 | 755 | Department of Water Resources, River Development & GR | Waste & Water | Sewage Treatment Plant 50MLD and Sewerage Network 150 km in Kankarbagh- Patna under Hybrid annuity based PPP mode-Namami Gange Programme | National Mission for Clean Ganga | 616612 | Bihar | 08/2017 | 07/2019 | 12/2025 | - | 578.89 | 578.89 | 171.79 | 54
August 2025 | 756 | Department of Water Resources, River Development & GR | Waste & Water | Sewer Network, SPS and STP at Begusarai | National Mission for Clean Ganga | 616615 | Bihar | 03/2010 | 03/2018 | 04/2025 | 12/2025 | 230.06 | 230.06 | 261.82 | 97
August 2025 | 757 | Department of Water Resources, River Development & GR | Waste & Water | Sewer Networks, SPS and STP at Hajipur | National Mission for Clean Ganga | 616616 | Bihar | 03/2010 | 03/2018 | 06/2025 | 12/2025 | 305.19 | 305.19 | 346.46 | 95
August 2025 | 758 | Department of Water Resources, River Development & GR | Waste & Water | Interception & Diversion with Rehabilitation of sewerage scheme at Agra under Hybrid annuity based PPP model-Namami Gange Programme | National Mission for Clean Ganga | 616594 | Uttar Pradesh | 05/2020 | 04/2023 | 04/2025 | 12/2025 | 842.25 | 842.25 | 208.64 | 73
August 2025 | 759 | Department of Water Resources, River Development & GR | Waste & Water | Pollution Abatement Works for River Kali Meerut under Meerut Municipality Interception & Diversion with STP | National Mission for Clean Ganga | 616605 | Uttar Pradesh | 05/2020 | 11/2024 | 12/2024 | 05/2027 | 690.71 | 690.71 | 34.79 | 27
August 2025 | 760 | Department of Water Resources, River Development & GR | Waste & Water | Pollution Abatement works for River Ganga at Hooghly Chinsurah- Municipal Town Interception & Diversion with STP | National Mission for Clean Ganga | 616604 | West Bengal | 05/2018 | 12/2021 | 03/2025 | 12/2025 | 154.73 | 154.73 | 96.17 | 92
August 2025 | 761 | Department of Water Resources, River Development & GR | Water Resources | Sardar Gouthu Latchanna Thotapalli Barrage Project | Water Resources-AP | 400100 | Andhra Pradesh | NA | 01/2006 | 12/2019 | 06/2026 | 353.05 | 1023.24 | 869.11 | 95
August 2025 | 762 | Department of Water Resources, River Development & GR | Water Resources | Gundlakamma project | Water Resources-AP | 400101 | Andhra Pradesh | NA | 04/2005 | 12/2019 | 03/2027 | 397.41 | 697.39 | 610.89 | 98
August 2025 | 763 | Department of Water Resources, River Development & GR | Water Resources | Polavaram Irrigation Project | Water Resources-AP | 701415 | Andhra Pradesh | 02/2009 | 11/2004 | 04/2022 | 03/2026 | 10151.04 | 55548.9 | 24347.76 | 83
August 2025 | 764 | Department of Water Resources, River Development & GR | Water Resources | Borolia Irrigation Project | Department of Water Resources, River Development & GR | 701370 | Assam | NA | 12/1996 | 12/2022 | 03/2026 | 256.16 | 256.16 | 0 | 55
August 2025 | 765 | Department of Water Resources, River Development & GR | Water Resources | Punpun Barrage Project | Water Resources-BR | 400104 | Bihar | NA | 04/2007 | 12/2019 | 03/2026 | 571.07 | 658.12 | 469.66 | 44
August 2025 | 766 | Department of Water Resources, River Development & GR | Water Resources | Durgawati Reservoir Project | Irrigation and CAD-TG | 701371 | Bihar | NA | 04/1997 | 12/2019 | 12/2024 | 691.15 | 971.96 | 978.51 | 87
August 2025 | 767 | Department of Water Resources, River Development & GR | Water Resources | Kelo Irrigation Project | Water Resources-CT | 400111 | Chhattisgarh | NA | 04/2008 | 12/2019 | 06/2026 | 459.97 | 727.04 | 616.93 | 71
August 2025 | 768 | Department of Water Resources, River Development & GR | Water Resources | Kudali Irrigation Project | Department of Water Resources, River Development & GR | 701399 | Chhattisgarh | NA | 12/2009 | 12/2025 | - | 382.29 | 382.29 | 0 | 86
August 2025 | 769 | Department of Water Resources, River Development & GR | Water Resources | Sardar Sarovar CADWM Project | Narmada and Water Resources, Water Supply and Kalpsar Department-GJ | 400097 | Gujarat | NA | 04/2004 | 12/2019 | 03/2025 | 5021.76 | 6670.31 | 4954.99 | 90.3
August 2025 | 770 | Department of Water Resources, River Development & GR | Water Resources | Sardar Sarovar Project | Narmada and Water Resources, Water Supply and Kalpsar Department-GJ | 701372 | Gujarat | NA | 04/1996 | 12/2019 | 12/2025 | 20718.17 | 33412.5 | 31767.59 | 93
August 2025 | 771 | Department of Water Resources, River Development & GR | Water Resources | Subernarekha Multipurpose Project, Jharkhand | Department of Water Resources-JH | 701376 | Jharkhand | NA | 01/2012 | 12/2019 | 03/2026 | 3807.77 | 9579.58 | 5561.97 | 69
August 2025 | 772 | Department of Water Resources, River Development & GR | Water Resources | Upper Tunga Irrigation Project | Water Resources-KA | 701377 | Karnataka | NA | 04/2014 | 12/2019 | 12/2025 | 770.16 | 1606.07 | 1511.22 | 99
August 2025 | 773 | Department of Water Resources, River Development & GR | Water Resources | Omkareshwar CADWM Project | Water resource-mp | 400096 | Madhya Pradesh | NA | 04/2015 | 12/2019 | 03/2026 | 648.09 | 648.09 | 172.56 | 3
August 2025 | 774 | Department of Water Resources, River Development & GR | Water Resources | Bargi Diversion Project Phase - IV [km. 154 to km 197] | Water Resources-MP | 400115 | Madhya Pradesh | NA | 01/2009 | 12/2019 | 03/2025 | 751.03 | 893.35 | 746.19 | 75
August 2025 | 775 | Department of Water Resources, River Development & GR | Water Resources | Bargi Diversion Project Phase - III [km. 104 to km 154] | Water Resources-MP | 400116 | Madhya Pradesh | NA | 04/2007 | 12/2019 | 12/2025 | 1229.15 | 1399.7 | 1807.2 | 79
August 2025 | 776 | Department of Water Resources, River Development & GR | Water Resources | Gosikhurd CADWM Project | Department of water resources-MH - II | 400095 | Maharashtra | 04/2017 | 04/2017 | 12/2019 | 06/2026 | 743.73 | 743.73 | 252 | 50
August 2025 | 777 | Department of Water Resources, River Development & GR | Water Resources | Urmodi Irrigation Project | Department of water resources-MH - II | 400105 | Maharashtra | NA | 04/2018 | 06/2022 | 12/2026 | 580.79 | 895.81 | 713.46 | 76
August 2025 | 778 | Department of Water Resources, River Development & GR | Water Resources | Sulwade-Jamphal-Kanoli Lift Irrigation Scheme | Department of water resources-MH - II | 400107 | Maharashtra | NA | 02/2019 | 06/2023 | 06/2027 | 2407.67 | 2407.67 | 2436.43 | 80
August 2025 | 779 | Department of Water Resources, River Development & GR | Water Resources | Purna Barrage-2 [Ner Dhamana] Medium Irrigation Project | Department of water resources-MH - II | 400109 | Maharashtra | NA | 04/2018 | 06/2020 | 06/2026 | 848.07 | 888.43 | 690.49 | 69
August 2025 | 780 | Department of Water Resources, River Development & GR | Water Resources | Jigaon Irrigation Project | Department of water resources-MH - II | 400112 | Maharashtra | NA | 04/2018 | 06/2028 | - | 7222.95 | 7222.95 | 8501.45 | 90
August 2025 | 781 | Department of Water Resources, River Development & GR | Water Resources | Waghur Project | Department of water resources-MH - II | 701383 | Maharashtra | NA | 04/1996 | 12/2019 | 03/2026 | 1058.99 | 1758.51 | 1530.45 | 89
August 2025 | 782 | Department of Water Resources, River Development & GR | Water Resources | Gosikhurd Project | Department of water resources-MH - II | 701386 | Maharashtra | 12/2017 | 04/2008 | 12/2019 | 06/2026 | 7196.47 | 12770.1 | 13533.29 | 72
August 2025 | 783 | Department of Water Resources, River Development & GR | Water Resources | Aruna Medium Irrigation Project | Department of water resources-MH - II | 701391 | Maharashtra | NA | 01/2010 | 12/2019 | 12/2025 | 210.45 | 1472.14 | 1697.94 | 97
August 2025 | 784 | Department of Water Resources, River Development & GR | Water Resources | Lower Pedhi Project | Department of water resources-MH - II | 701396 | Maharashtra | NA | 04/2008 | 12/2019 | 06/2026 | 255.97 | 1480.7 | 1324.78 | 64
August 2025 | 785 | Department of Water Resources, River Development & GR | Water Resources | Nardave Medium Irrigation Project | Department of water resources-MH - II | 701398 | Maharashtra | NA | 04/2009 | 12/2019 | 06/2026 | 211.46 | 781.85 | 623.5 | 72
August 2025 | 786 | Department of Water Resources, River Development & GR | Water Resources | Thoubal Multipurpose Project | Water Resources Department-MN | 701400 | Manipur | 01/2022 | 04/1997 | 12/2019 | 03/2026 | 1449.44 | 1822.24 | 1837.91 | 98
August 2025 | 787 | Department of Water Resources, River Development & GR | Water Resources | North Koel Reservoir Project | Department of Water Resources, River Development & GR | 701412 | Multi-States (Bihar, Jharkhand) | NA | 01/2021 | 03/2021 | 03/2026 | 1622.27 | 2430.76 | 142.1 | 32
August 2025 | 788 | Department of Water Resources, River Development & GR | Water Resources | Integrated Anandpur Barrage Project | Water Resources-OR | 603945 | Odisha | NA | 01/1998 | 12/2019 | 06/2026 | 567.03 | 2990.05 | 2629.74 | 62
August 2025 | 789 | Department of Water Resources, River Development & GR | Water Resources | Kanupur Irrigation Project | Irrigation and CAD-TG | 701404 | Odisha | NA | 01/2004 | 12/2019 | 12/2024 | 989.43 | 2301.28 | 2563.56 | 79
August 2025 | 790 | Department of Water Resources, River Development & GR | Water Resources | Relining of Rajasthan feeder and Sirhind Feeder canal | Department of Water Resources-PB | 701410 | Punjab | 02/2016 | 04/2018 | 06/2021 | 06/2026 | 1441.26 | 2462.16 | 3000.36 | 80
August 2025 | 791 | Department of Water Resources, River Development & GR | Water Resources | Shahpur Kandi Dam Project | Department of Water Resources-PB | 701411 | Punjab | 02/2010 | 04/2018 | 06/2022 | 10/2025 | 2285.81 | 2715.7 | 2072.33 | 80
August 2025 | 792 | Department of Water Resources, River Development & GR | Water Resources | Sri Ram Sagar Project Stage - II | Irrigation and CAD-TG | 400102 | Telangana | NA | 04/2005 | 12/2019 | 03/2026 | 736.13 | 949.87 | 940.7 | 96
August 2025 | 793 | Department of Water Resources, River Development & GR | Water Resources | Indiramma Flood Flow Canal Project | Irrigation and CAD-TG | 400103 | Telangana | NA | 01/2006 | 12/2019 | 12/2026 | 1331.3 | 5940.09 | 4491.08 | 92
August 2025 | 794 | Department of Water Resources, River Development & GR | Water Resources | J. Chokka Rao Devadula Lift Irrigation Scheme | Irrigation and CAD-TG | 701405 | Telangana | NA | 04/2006 | 12/2019 | 12/2025 | 8200.71 | 14730 | 4558.89 | 87
August 2025 | 795 | Department of Water Resources, River Development & GR | Water Resources | Rajiv Bhima Lift Irrigation Scheme | Irrigation and CAD-TG | 701406 | Telangana | NA | 01/2008 | 12/2019 | 03/2026 | 1402 | 2509.66 | 1839.76 | 100
August 2025 | 796 | Department of Water Resources, River Development & GR | Water Resources | Saryu Nahar CADWM Project | Irrigation & Water Resources-UP | 400093 | Uttar Pradesh | NA | 04/2017 | 12/2019 | 03/2026 | 1672.7 | 1672.7 | 0 | 0
August 2025 | 797 | Department of Water Resources, River Development & GR | Water Resources | Arjun Sahayak Project | Irrigation & Water Resources-UP | 400117 | Uttar Pradesh | NA | 04/2009 | 12/2019 | 12/2019 | 741.38 | 2465.68 | 3218.3 | 100
August 2025 | 798 | Department of Water Resources, River Development & GR | Water Resources | Morna [Gureghar] Irrigation Project | Department of Water Resources, River Development & GR | 701395 | Uttar Pradesh | NA | 12/2007 | 12/2025 | - | 219.9 | 219.9 | 0 | 0
August 2025 | 799 | Department of Water Resources, River Development & GR | Water Resources | Madhya Ganga canal Phase-II | Irrigation & Water Resources-UP | 701408 | Uttar Pradesh | NA | 07/2007 | 12/2019 | 12/2025 | 1060.67 | 4417.21 | 4415.24 | 82
August 2025 | 800 | Department of Water Resources, River Development & GR | Water Resources | Jamrani Dam Multipurpose Project | Irrigation-UK | 613787 | Uttarakhand | 10/2023 | 04/2023 | 06/2029 | - | 2584.1 | 2584.1 | 968.52 | 16
October 2025 | 1 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Construction of New Domestic Terminal Building Building and miscellaneous works including maintenance, operations and AICMC at Kadapa Airport | Airport Authority of India [AAI] | 612786 | Andhra Pradesh | 03/2023 | 01/2024 | 01/2026 | 03/2026 | 265.91 | 265.91 | 67.22 | 39
October 2025 | 2 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Construction of New Integrated Terminal Building and associated works including apron to park 3 code E type of aircraft or 6 code C type of aircraft at Vijayawada Airport. | Airport Authority of India [AAI] | 701107 | Andhra Pradesh | 06/2020 | 09/2020 | 09/2022 | 12/2025 | 611.8 | 611.8 | 507.14 | 84
October 2025 | 3 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Construction of New Domestic Terminal Building at Rajahmundry Airport. | Airport Authority of India [AAI] | 701121 | Andhra Pradesh | 12/2022 | 08/2023 | 08/2025 | 12/2025 | 347.15 | 347.15 | 102.43 | 57
October 2025 | 4 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Guwahati Airport New Integrated Terminal Building Construction Project | Adani Airport Holdings Limited | 706724 | Assam | 12/2016 | 03/2018 | 03/2025 | 11/2025 | 1712 | 1712 | 2397.37 | 91
October 2025 | 5 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Development of New Civil Enclave at Bihta | Airport Authority of India [AAI] | 612183 | Bihar | 08/2024 | 03/2025 | 09/2027 | - | 1413 | 1413 | 0 | 1
October 2025 | 6 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Development of New Civil Enclave and associated works at Darbhanga Airport | Airport Authority of India [AAI] | 612194 | Bihar | 07/2024 | 07/2024 | 01/2026 | - | 911.66 | 911.66 | 213.22 | 38
October 2025 | 7 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Construction of New Domestic Terminal Building [Phase-I and II] and other allied structures at JPNI Airport, Patna | Airport Authority of India [AAI] | 701101 | Bihar | 12/2018 | 10/2018 | 07/2023 | 11/2025 | 1216.9 | 1216.9 | 1125.73 | 95
October 2025 | 8 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Goa Airport Terminal Building Extension Project | Airport Authority of India [AAI] | 701105 | Goa | 11/2017 | 12/2019 | 12/2021 | 09/2025 | 255.69 | 255.69 | 154.3 | 94
October 2025 | 9 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Development of Dholera International Greenfield Airport , Gujarat | Airport Authority of India [AAI] | 701126 | Gujarat | 06/2022 | 07/2022 | 06/2026 | 06/2026 | 1305 | 1551 | 718.2 | 67
October 2025 | 10 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Construction of NTB complex including apron, taxi track and other associated civil works and electrical & mechanical installations towards Tawi River side at CA Jammu. | Airport Authority of India [AAI] | 611047 | Jammu and Kashmir | 07/2022 | 07/2023 | 06/2026 | 06/2026 | 861.37 | 861.37 | 212.12 | 39
October 2025 | 11 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Construction of New Domestic Terminal Building and Miscellaneous works at Hubli Airport | Airport Authority of India [AAI] | 612787 | Karnataka | 06/2023 | 01/2024 | 01/2026 | 03/2026 | 320.47 | 320.47 | 81.22 | 45
October 2025 | 12 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Construction of New Domestic Terminal Building and Miscellaneous Works at Belagavi Airport. | Airport Authority of India [AAI] | 612788 | Karnataka | 06/2023 | 02/2024 | 01/2026 | 01/2026 | 322.45 | 322.45 | 140.4 | 59
October 2025 | 13 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Development of additional RESA on either end on Runway 10-28 at Calicut Airport. Construction of embankment with slope protection, drainage system and associated works for additional RESA on either end on Runway 10-28 | Airport Authority of India [AAI] | 612789 | Kerala | 06/2023 | 02/2024 | 09/2025 | 03/2026 | 484.57 | 484.57 | 91.67 | 23
October 2025 | 14 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Construction of Terminal Building & Associated works at Leh Airport, Ladakh | Airport Authority of India [AAI] | 400010 | Ladakh | 07/2018 | 09/2018 | 09/2021 | 10/2025 | 480 | 640 | 471.59 | 77
October 2025 | 15 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | C/o NITB Imphal Airport | Airport Authority of India [AAI] | 706718 | Manipur | 11/2021 | 07/2022 | 07/2024 | 12/2026 | 499 | 499 | 155.72 | 41
October 2025 | 16 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | SITC of ATM Automation System and ASMGCS [Including SMR & MLAT] for Mumbai, Navi Mumbai, Jewar [earlier MOPA, without ASMGCS], HIAL & BIAL | Airport Authority of India [AAI] | 611570 | Multi-States (Karnataka, Maharashtra, Telangana, Uttar Pradesh) | NA | 10/2022 | 09/2025 | 08/2026 | 500.48 | 500.48 | 332.26 | 75
October 2025 | 17 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Construction of New Passenger Terminal Building for Domestic Operations at Jodhpur Airport. | Airport Authority of India [AAI] | 701127 | Rajasthan | 05/2022 | 04/2023 | 11/2024 | 11/2025 | 480 | 480 | 317.88 | 96
October 2025 | 18 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Construction of New Integrated Passenger Terminal Building at Udaipur Airport | Airport Authority of India [AAI] | 701128 | Rajasthan | 06/2023 | 11/2022 | 03/2026 | 10/2026 | 887 | 887 | 378.81 | 50
October 2025 | 19 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Widening of basic strip at Western Side of Runway Chainage 80m to 920m i/c slope stabilization Measures [Balance work] of uphill and Improvement of Storm Water Drainage System at Pakyong Airport, Sikkim on design & build basis [EPC] with integrated 10 years maintenance. | Airport Authority of India [AAI] | 612793 | Sikkim | 11/2023 | 12/2023 | 02/2026 | - | 323.26 | 323.26 | 38.69 | 14
October 2025 | 20 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Modernization of Chennai Airport, Phase II, Part 2 | Airport Authority of India [AAI] | 611602 | Tamil Nadu | 05/2018 | 06/2023 | 07/2025 | 06/2026 | 1207 | 1207 | 183.02 | 25
October 2025 | 21 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Construction of New Terminal Building, Second Link Taxi Track, Apron Expansion, and associated works at Prayagraj Airport- On Design & Build Basis. | Airport Authority of India [AAI] | 612063 | Uttar Pradesh | NA | 08/2023 | 11/2024 | 08/2025 | 219.18 | 274.38 | 215.2 | 100
October 2025 | 22 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Lucknow Airport-Terminal 3- Phase 1 & Other Associated Works | Adani Airport Holdings Limited | 701091 | Uttar Pradesh | 06/2018 | 09/2018 | 03/2026 | - | 3100 | 3100 | 16024.42 | 100
October 2025 | 23 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Development of Lal Bahadur Shastri International airport, Varanasi including C/o New Terminal Building, Apron Extension, Runway Extension, PTT and allied works. | Airport Authority of India [AAI] | 701113 | Uttar Pradesh | 07/2024 | 07/2024 | 07/2027 | 07/2027 | 2869.65 | 2869.65 | 361.71 | 18
October 2025 | 24 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Development of New Integrated Civil Enclave at Agra Airport | Airport Authority of India [AAI] | 701122 | Uttar Pradesh | 06/2024 | 07/2024 | 07/2026 | - | 579 | 579 | 88.64 | 20
October 2025 | 25 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Development of New Civil Enclave at Bagdogra Airport | Airport Authority of India [AAI] | 611495 | West Bengal | 08/2024 | 10/2023 | 01/2027 | 01/2027 | 1549 | 1549 | 310.58 | 13
October 2025 | 26 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Re-Construction of Rigid portions of Secondary Runway, K and A Taxiway and Strengthening of C Taxiway at NSCBI Airport Kolkata. | Airport Authority of India [AAI] | 612791 | West Bengal | 04/2023 | 12/2023 | 02/2025 | 08/2026 | 328.3 | 328.3 | 107.6 | 49
October 2025 | 27 | Ministry of Coal | Coal | TIKAK EXTENSION OCP | MIS MoCoal Integration Logins | 615820 | Assam | 07/2022 | 07/2022 | 07/2031 | - | 159.77 | 159.77 | 81.47 | 0
October 2025 | 28 | Ministry of Coal | Coal | TIRAP OCP | MIS MoCoal Integration Logins | 615821 | Assam | 11/2022 | 11/2022 | 11/2030 | - | 289.46 | 289.46 | 105.6 | 3
October 2025 | 29 | Ministry of Coal | Coal | PORDA CHIMTAPANI OCP [10 MTY] | South Eastern Coalfields Limited [SECL] | 400144 | Chhattisgarh | 12/2020 | 12/2020 | 03/2029 | - | 2310.12 | 2310.12 | 87.97 | 10
October 2025 | 30 | Ministry of Coal | Coal | CHHAL OC SEAM III [6 MTY] | South Eastern Coalfields Limited [SECL] | 400145 | Chhattisgarh | 12/2013 | 12/2013 | 03/2022 | 11/2025 | 610.63 | 610.63 | 579.82 | 85
October 2025 | 31 | Ministry of Coal | Coal | BAROUD OC EXPANSION [3.0-10.0M | South Eastern Coalfields Limited [SECL] | 400149 | Chhattisgarh | 08/2020 | 08/2020 | 03/2029 | - | 2309.8 | 2309.8 | 937.38 | 50
October 2025 | 32 | Ministry of Coal | Coal | DIPKA EXPANSION OCP [40 MTY] | South Eastern Coalfields Limited [SECL] | 400354 | Chhattisgarh | 12/2020 | 12/2020 | 03/2029 | - | 5241.4 | 5241.4 | 2841.08 | 37
October 2025 | 33 | Ministry of Coal | Coal | GEVRA OC [70 MTY] | South Eastern Coalfields Limited [SECL] | 400424 | Chhattisgarh | 03/2016 | 03/2016 | 03/2023 | 03/2026 | 11816.4 | 11816.4 | 6687.44 | 78
October 2025 | 34 | Ministry of Coal | Coal | JAMPALI OC RCE [2.0 MTY] | South Eastern Coalfields Limited [SECL] | 613795 | Chhattisgarh | 05/2020 | 05/2020 | 03/2025 | 06/2025 | 278.64 | 278.64 | 210.07 | 82
October 2025 | 35 | Ministry of Coal | Coal | AMERA OC RCE [1.0 MTY] | South Eastern Coalfields Limited [SECL] | 613798 | Chhattisgarh | 02/2015 | 02/2015 | 03/2026 | - | 335.97 | 335.97 | 88.24 | 42
October 2025 | 36 | Ministry of Coal | Coal | AMGAON OC RCE [1.0 MTY] | South Eastern Coalfields Limited [SECL] | 613799 | Chhattisgarh | 07/2015 | 07/2015 | 03/2026 | - | 316.11 | 316.11 | 188.62 | 78
October 2025 | 37 | Ministry of Coal | Coal | JAGANNATHPUR OC RCE PROJECT | South Eastern Coalfields Limited [SECL] | 613800 | Chhattisgarh | 07/2016 | 07/2016 | 03/2025 | 03/2026 | 459.49 | 459.49 | 274.35 | 96
October 2025 | 38 | Ministry of Coal | Coal | MAHAMAYA OCP [1.50 MTY] | South Eastern Coalfields Limited [SECL] | 613801 | Chhattisgarh | 05/2018 | 05/2018 | 03/2026 | - | 410.26 | 410.26 | 182.83 | 54
October 2025 | 39 | Ministry of Coal | Coal | KATKONA RO UG MINE | South Eastern Coalfields Limited [SECL] | 615191 | Chhattisgarh | 01/2023 | 01/2023 | 03/2029 | - | 329.21 | 329.21 | 61.34 | 2
October 2025 | 40 | Ministry of Coal | Coal | PELMA OC MDO | South Eastern Coalfields Limited [SECL] | 616234 | Chhattisgarh | 10/2022 | 10/2022 | 03/2033 | - | 1725.04 | 1725.04 | 15.66 | 40
October 2025 | 41 | Ministry of Coal | Coal | KUSMUNDA OC EXPANSION PROJECT | SECL - CIL | 617287 | Chhattisgarh | 11/2024 | 11/2024 | 03/2030 | - | 4516.88 | 4516.88 | 775.13 | 21
October 2025 | 42 | Ministry of Coal | Coal | MANIKPUR OC EXPANSION PROJECT | South Eastern Coalfields Limited [SECL] | 617288 | Chhattisgarh | 01/2025 | 01/2025 | 03/2029 | - | 382.61 | 382.61 | 113.03 | 21
October 2025 | 43 | Ministry of Coal | Coal | HURA C OCP | ECL - CIL | 400018 | Jharkhand | 08/2022 | 08/2022 | 03/2029 | - | 859.41 | 859.41 | 451.62 | 62
October 2025 | 44 | Ministry of Coal | Coal | KONAR EXPANSION OCP | Ministry of Coal | 400073 | Jharkhand | 01/2022 | 01/2022 | 03/2032 | - | 799.34 | 799.34 | 429.65 | 45
October 2025 | 45 | Ministry of Coal | Coal | KARO EXPANSION OCP | Ministry of Coal | 400074 | Jharkhand | 01/2022 | 01/2022 | 03/2029 | - | 908.47 | 908.47 | 269.26 | 22
October 2025 | 46 | Ministry of Coal | Coal | SANGHMITRA OC | Ministry of Coal | 400136 | Jharkhand | 03/2024 | 03/2024 | 03/2032 | - | 2660 | 2660 | 0 | 0
October 2025 | 47 | Ministry of Coal | Coal | CHANDRAGUPT OCP | Ministry of Coal | 400138 | Jharkhand | 08/2020 | 08/2020 | 03/2032 | - | 973.5 | 973.5 | 440.56 | 24
October 2025 | 48 | Ministry of Coal | Coal | KOTRE BASANTPUR PACHMO OCP | Ministry of Coal | 400139 | Jharkhand | 08/2020 | 08/2020 | 03/2032 | - | 861.06 | 625.4 | 455.95 | 42
October 2025 | 49 | Ministry of Coal | Coal | Pachwara South Coal Block | NLC India Limited [NLCIL] | 400142 | Jharkhand | 03/2016 | 11/2019 | 09/2028 | - | 2242.9 | 2242.9 | 1220.76 | 74
October 2025 | 50 | Ministry of Coal | Coal | RPR MAGADH EXP OCP | Ministry of Coal | 400150 | Jharkhand | 08/2020 | 08/2020 | 03/2028 | - | 7254.37 | 7254.37 | 1600.77 | 38
October 2025 | 51 | Ministry of Coal | Coal | NORTH URIMARI EXPANSION OCP | Ministry of Coal | 400151 | Jharkhand | 07/2021 | 07/2021 | 03/2029 | - | 778.8 | 778.8 | 696.05 | 67
October 2025 | 52 | Ministry of Coal | Coal | EPR ROHINI - KARKETTA OCP | Ministry of Coal | 400153 | Jharkhand | 01/2021 | 01/2021 | 03/2028 | - | 1020.42 | 1020.42 | 84.74 | 21
October 2025 | 53 | Ministry of Coal | Coal | EPR PUNDI OCP | Ministry of Coal | 400154 | Jharkhand | 11/2020 | 11/2020 | 03/2027 | - | 713.35 | 713.35 | 236.58 | 10
October 2025 | 54 | Ministry of Coal | Coal | EPR ASHOK OC | Ministry of Coal | 400155 | Jharkhand | 05/2021 | 05/2021 | 03/2031 | - | 2898.28 | 2898.28 | 179.7 | 24
October 2025 | 55 | Ministry of Coal | Coal | EPR AMRAPALI OCP | Ministry of Coal | 400156 | Jharkhand | 02/2020 | 02/2020 | 03/2028 | - | 5136.15 | 5136.15 | 1168.11 | 42
October 2025 | 56 | Ministry of Coal | Coal | RAJRAPPA RCE OCP | Ministry of Coal | 400160 | Jharkhand | 12/2009 | 12/2009 | 03/2016 | 03/2027 | 510.85 | 510.85 | 488.69 | 76
October 2025 | 57 | Ministry of Coal | Coal | CHITRA EAST OC | Eastern Coal Fields Limited [ECL] | 400172 | Jharkhand | 08/2018 | 08/2018 | 03/2026 | 03/2028 | 513.99 | 513.99 | 229.86 | 51
October 2025 | 58 | Ministry of Coal | Coal | JHARKHAND-LAIYO OCP | Ministry of Coal | 400352 | Jharkhand | 08/2020 | 08/2020 | 03/2031 | - | 764.57 | 764.57 | 145.81 | 29
October 2025 | 59 | Ministry of Coal | Coal | MOONIDIH XV SEAM UG | Ministry of Coal | 400425 | Jharkhand | 08/2011 | 08/2011 | 03/2019 | 05/2026 | 1230.27 | 1230.27 | 631.73 | 81
October 2025 | 60 | Ministry of Coal | Coal | 2.5 MTPA PATHERDIH NLW WASHERY | Ministry of Coal | 611017 | Jharkhand | 10/2015 | 04/2016 | 04/2018 | 03/2026 | 334.27 | 334.27 | 142.64 | 48
October 2025 | 61 | Ministry of Coal | Coal | AMALAGAMATED NTST KUJAMA OCP 8.5MTY | Ministry of Coal | 611864 | Jharkhand | 01/2023 | 01/2023 | 03/2030 | - | 4011.85 | 4011.85 | 404.49 | 28
October 2025 | 62 | Ministry of Coal | Coal | MURAIDIH UG PROJECT | Ministry of Coal | 613808 | Jharkhand | 02/2011 | 02/2011 | 04/2014 | 12/2026 | 339.87 | 339.87 | 191 | 70
October 2025 | 63 | Ministry of Coal | Coal | TAPIN SOUTH EXPN | Ministry of Coal | 615349 | Jharkhand | 11/2020 | 11/2020 | 03/2028 | - | 230.41 | 230.41 | 22.02 | 20
October 2025 | 64 | Ministry of Coal | Coal | SIRKA OC | Ministry of Coal | 615822 | Jharkhand | 05/2020 | 05/2020 | 03/2028 | - | 222.82 | 222.82 | 140.58 | 53
October 2025 | 65 | Ministry of Coal | Coal | TETARIAKHAR OC | Ministry of Coal | 615843 | Jharkhand | 11/2019 | 11/2019 | 03/2025 | 03/2027 | 243.52 | 243.52 | 44.64 | 29
October 2025 | 66 | Ministry of Coal | Coal | CHUPERBHITA SIMLONG OCP MDO 6 | Eastern Coal Fields Limited [ECL] | 616225 | Jharkhand | 12/2023 | 12/2023 | 03/2037 | - | 979.08 | 979.08 | 0 | 0
October 2025 | 67 | Ministry of Coal | Coal | JARANGDIH EXPN. OCP 1.5 MTY | CCL - CIL | 616236 | Jharkhand | 02/2020 | 02/2020 | 03/2029 | - | 414.37 | 414.37 | 85.6 | 32
October 2025 | 68 | Ministry of Coal | Coal | BLOCK E OCP | Ministry of Coal | 616253 | Jharkhand | 03/2024 | 03/2024 | 03/2029 | - | 5850.83 | 5850.83 | 20.32 | 3
October 2025 | 69 | Ministry of Coal | Coal | Revised Jharia Master Plan for Dealing with Fire, Subsidence & Rehabilitation of affected families in Jharia Coalfield- Reg. | Bharat Coking Coal Limited (BCCL | 617416 | Jharkhand | 06/2025 | 07/2025 | 12/2028 | - | 5940.47 | 5940.47 | 0 | 8
October 2025 | 70 | Ministry of Coal | Coal | AMADAND OCP[4.0MTY] | Ministry of Coal | 400148 | Madhya Pradesh | 03/2016 | 03/2016 | 03/2021 | 03/2027 | 869.44 | 869.44 | 275.35 | 75
October 2025 | 71 | Ministry of Coal | Coal | RAMPUR BATURA OCP [4.0MTY] | South Eastern Coalfields Limited [SECL] | 400152 | Madhya Pradesh | 07/2019 | 07/2019 | 03/2026 | - | 1248.93 | 1248.93 | 498.04 | 44
October 2025 | 72 | Ministry of Coal | Coal | BLOCK B EXPANSION [3.5 TO 8.0 | Northern Coalfields Limited [NCL] | 400162 | Madhya Pradesh | 07/2019 | 07/2019 | 03/2023 | 03/2027 | 998.71 | 998.71 | 470.87 | 47
October 2025 | 73 | Ministry of Coal | Coal | NIGAHI EXPANSION [15 TO 25 MTP | Northern Coalfields Limited [NCL] | 400321 | Madhya Pradesh | 11/2020 | 11/2020 | 03/2025 | 03/2028 | 1729.68 | 1729.68 | 833.62 | 48
October 2025 | 74 | Ministry of Coal | Coal | KANCHAN OC EXP | South Eastern Coalfields Limited [SECL] | 613802 | Madhya Pradesh | 12/2014 | 12/2014 | 03/2026 | - | 371.04 | 371.04 | 144.61 | 58
October 2025 | 75 | Ministry of Coal | Coal | JHIRIA WEST OCP [1.5 MTY] | South Eastern Coalfields Limited [SECL] | 613803 | Madhya Pradesh | 01/2024 | 01/2024 | 03/2029 | - | 366.94 | 366.94 | 34.07 | 41
October 2025 | 76 | Ministry of Coal | Coal | RPR TAWA-III UG 0.84 MTY | Western Coalfields Limited [WCL] | 613804 | Madhya Pradesh | 12/2021 | 12/2021 | 03/2027 | - | 314.09 | 314.09 | 6.84 | 17
October 2025 | 77 | Ministry of Coal | Coal | AMALGAMATED DHANKASA & JAMUNIA | Western Coalfields Limited [WCL] | 615185 | Madhya Pradesh | 09/2022 | 09/2022 | 03/2027 | - | 399.2 | 399.2 | 93.52 | 66
October 2025 | 78 | Ministry of Coal | Coal | RPR OF VISHNUPURI UG TO OC | Western Coalfields Limited [WCL] | 615187 | Madhya Pradesh | 11/2022 | 11/2022 | 03/2029 | - | 220.62 | 220.62 | 0 | 11
October 2025 | 79 | Ministry of Coal | Coal | URDHAN EXPANSION OC COST PLUS | Western Coalfields Limited [WCL] | 615194 | Madhya Pradesh | 07/2022 | 01/2023 | 03/2031 | - | 206.88 | 206.88 | 27.19 | 0
October 2025 | 80 | Ministry of Coal | Coal | SHARDA UG MINE | Western Coalfields Limited [WCL] | 615195 | Madhya Pradesh | 07/2022 | 09/2023 | 03/2028 | - | 166.25 | 166.25 | 5.08 | 9
October 2025 | 81 | Ministry of Coal | Coal | GANDHIGRAM UG MINE | Western Coalfields Limited [WCL] | 615206 | Madhya Pradesh | 08/2019 | 08/2019 | 03/2026 | - | 414.15 | 414.15 | 15.52 | 56
October 2025 | 82 | Ministry of Coal | Coal | BHATADI EXPANSION OC | Western Coalfields Limited [WCL] | 400033 | Maharashtra | 02/2020 | 05/2022 | 03/2028 | - | 580.61 | 580.61 | 73.77 | 28
October 2025 | 83 | Ministry of Coal | Coal | AMALGAMATED YEKONA I & YEKONA | Western Coalfields Limited [WCL] | 400177 | Maharashtra | 08/2015 | 08/2015 | 03/2025 | 03/2026 | 727.28 | 727.28 | 539.93 | 80
October 2025 | 84 | Ministry of Coal | Coal | DINESH[MAKARDHOKRA-III] OC | Western Coalfields Limited [WCL] | 400178 | Maharashtra | 02/2020 | 02/2020 | 03/2027 | - | 822.88 | 822.88 | 621.94 | 34
October 2025 | 85 | Ministry of Coal | Coal | DHUPTALA OC [SASTI UG TO OC ] | Western Coalfields Limited [WCL] | 400353 | Maharashtra | 02/2019 | 10/2021 | 03/2028 | - | 711.01 | 711.01 | 169.11 | 19
October 2025 | 86 | Ministry of Coal | Coal | SAONER UG MINE -1 EXPANSION 1. | Western Coalfields Limited [WCL] | 615184 | Maharashtra | 01/2022 | 01/2022 | 03/2028 | - | 228.64 | 228.64 | 143.37 | 68
October 2025 | 87 | Ministry of Coal | Coal | SASTI EXPANSION OPENCAST | Western Coalfields Limited [WCL] | 615186 | Maharashtra | 08/2020 | 08/2020 | 03/2026 | - | 319.04 | 319.04 | 91.48 | 20
October 2025 | 88 | Ministry of Coal | Coal | NEW MAJRI UG TO OC 3 MTY COST | Western Coalfields Limited [WCL] | 615188 | Maharashtra | 05/2019 | 09/2022 | 03/2027 | - | 402.27 | 402.27 | 60.03 | 24
October 2025 | 89 | Ministry of Coal | Coal | MAKARDHOKRA EXPN OC 4.9 MTY | Western Coalfields Limited [WCL] | 615189 | Maharashtra | 06/2022 | 06/2022 | 03/2026 | - | 361.87 | 361.87 | 76.32 | 11
October 2025 | 90 | Ministry of Coal | Coal | SINGHORI DEEP OC MIN 2.0 MTY | Western Coalfields Limited [WCL] | 615190 | Maharashtra | 05/2022 | 05/2022 | 03/2029 | - | 335.75 | 335.75 | 26.98 | 6
October 2025 | 91 | Ministry of Coal | Coal | GOKUL EXTENSION OC MINE | Western Coalfields Limited [WCL] | 615192 | Maharashtra | 04/2021 | 04/2021 | 03/2026 | - | 309.58 | 309.58 | 43.88 | 8
October 2025 | 92 | Ministry of Coal | Coal | KOLGAON EXPANSION DEEP OC MINE | Western Coalfields Limited [WCL] | 615199 | Maharashtra | 01/2023 | 09/2023 | 03/2027 | - | 198.71 | 198.71 | 0.76 | 2
October 2025 | 93 | Ministry of Coal | Coal | BALLARPUR NORTH WEST OC MINE | Western Coalfields Limited [WCL] | 615330 | Maharashtra | 12/2022 | 12/2022 | 03/2029 | - | 360.81 | 360.81 | 0.02 | 4
October 2025 | 94 | Ministry of Coal | Coal | GADEGAON OC 3 MTY | Western Coalfields Limited [WCL] | 615331 | Maharashtra | 10/2023 | 10/2023 | 03/2030 | - | 497.41 | 497.41 | 0.08 | 0
October 2025 | 95 | Ministry of Coal | Coal | GHONSA EXPANSION DEEP OC MINE | Western Coalfields Limited [WCL] | 615914 | Maharashtra | 03/2021 | 03/2021 | 03/2029 | - | 184.71 | 184.71 | 14.48 | 5
October 2025 | 96 | Ministry of Coal | Coal | AMLG GAURI PAUNI EXPANSION OC | Western Coalfields Limited [WCL] | 615916 | Maharashtra | 04/2024 | 04/2024 | 03/2030 | - | 1225.21 | 1225.21 | 79.73 | 2
October 2025 | 97 | Ministry of Coal | Coal | GAURIDEEP/GAURI CENTRAL OCP 7. | Western Coalfields Limited [WCL] | 615917 | Maharashtra | 08/2023 | 06/2024 | 03/2030 | - | 973.07 | 973.07 | 0.24 | 0
October 2025 | 98 | Ministry of Coal | Coal | RPR OF BHANEGAON OC | Western Coalfields Limited [WCL] | 615918 | Maharashtra | 02/2017 | 09/2022 | 03/2028 | - | 405.2 | 405.2 | 12.39 | 7
October 2025 | 99 | Ministry of Coal | Coal | N. EXTN. MUNGOLI NIRGUDA D OCP | Western Coalfields Limited [WCL] | 615919 | Maharashtra | 06/2024 | 06/2024 | 03/2029 | - | 1024.91 | 1024.91 | 170.94 | 0
October 2025 | 100 | Ministry of Coal | Coal | NILJAI EXPANSION DEEP OCP | Western Coalfields Limited [WCL] | 615982 | Maharashtra | 08/2016 | 11/2018 | 03/2024 | 03/2026 | 319.75 | 319.75 | 367.6 | 79
October 2025 | 101 | Ministry of Coal | Coal | UKNI DEEP OC MINE -COST PLUS | Western Coalfields Limited [WCL] | 616044 | Maharashtra | 11/2018 | 01/2019 | 03/2021 | 03/2026 | 237.06 | 237.06 | 165.57 | 87
October 2025 | 102 | Ministry of Coal | Coal | AMALGAMATED INDER-KAMPTEE DEEP OC | Western Coalfields Limited [WCL] | 616050 | Maharashtra | 09/2018 | 09/2018 | 03/2024 | 03/2026 | 235.9 | 235.9 | 237.12 | 98
October 2025 | 103 | Ministry of Coal | Coal | ADASA UG TO OC MINE | Western Coalfields Limited [WCL] | 616223 | Maharashtra | 11/2018 | 11/2018 | 03/2024 | 03/2026 | 316 | 316 | 308.84 | 86
October 2025 | 104 | Ministry of Coal | Coal | AMAL GONDEGAON GHATROHANA EXPN | Western Coalfields Limited [WCL] | 616229 | Maharashtra | 09/2024 | 09/2024 | 03/2029 | - | 668.54 | 668.54 | 1.18 | 0
October 2025 | 105 | Ministry of Coal | Coal | WAGHODA UG MINE [1.02 MTY] | Western Coalfields Limited [WCL] | 617233 | Maharashtra | 01/2024 | 01/2025 | 03/2030 | - | 379.3 | 379.3 | 0 | 0
October 2025 | 106 | Ministry of Coal | Coal | KOLARPIMPRI EXPANSION OC [2.5 | Western Coalfields Limited [WCL] | 617278 | Maharashtra | 06/2024 | 02/2025 | 03/2030 | - | 630.37 | 630.37 | 0 | 0
October 2025 | 107 | Ministry of Coal | Coal | Master Plan for Jharia and Raniganj Coalfields | Bharat Coking Coal Limited [BCCL] | 400313 | Multi-States (Jharkhand, West Bengal) | 08/2009 | 08/2009 | 08/2019 | 12/2028 | 2661.73 | 2661.73 | 791.42 | 43
October 2025 | 108 | Ministry of Coal | Coal | BINA KAKRI AMALGAMATION EXPANS | Northern Coalfields Limited [NCL] | 400369 | Multi-States (Madhya Pradesh, Uttar Pradesh) | 08/2020 | 08/2020 | 03/2024 | 03/2027 | 836.42 | 836.42 | 809.2 | 89
October 2025 | 109 | Ministry of Coal | Coal | KHADIA EXPANSION [10 TO 16 MTP | Northern Coalfields Limited [NCL] | 615183 | Multi-States (Madhya Pradesh, Uttar Pradesh) | 06/2021 | 06/2021 | 03/2025 | 03/2027 | 491.67 | 491.67 | 243.56 | 47
October 2025 | 110 | Ministry of Coal | Coal | SUBHADRA OCP | Mahanadi Coalfields Limited [MCL] | 400165 | Odisha | 05/2021 | 05/2021 | 04/2032 | - | 1693.81 | 1693.81 | 1323.62 | 42
October 2025 | 111 | Ministry of Coal | Coal | SIARMAL OCP | Mahanadi Coalfields Limited [MCL] | 400166 | Odisha | 02/2021 | 02/2021 | 03/2029 | - | 5194.95 | 5194.95 | 3456.93 | 55
October 2025 | 112 | Ministry of Coal | Coal | BALARAM EXPANSION OCP | Mahanadi Coalfields Limited (MCL | 400183 | Odisha | 06/2020 | 08/2020 | 03/2029 | - | 3504.21 | 3504.21 | 922.92 | 53
October 2025 | 113 | Ministry of Coal | Coal | GOPALJI KANIHA OCP [10 TO 30 M | MCL - CIL | 400185 | Odisha | 04/2022 | 04/2022 | 03/2030 | - | 8416.19 | 6107.87 | 1734.86 | 17
October 2025 | 114 | Ministry of Coal | Coal | INTEGRATED LAKHANPUR-BELPAHAR- | Mahanadi Coalfields Limited [MCL] | 400187 | Odisha | 05/2018 | 05/2018 | 03/2027 | - | 2434.75 | 2434.75 | 1834.91 | 69
October 2025 | 115 | Ministry of Coal | Coal | BHARATPUR RE-ORGANIZATION OCP | Mahanadi Coalfields Limited (MCL | 400392 | Odisha | 11/2018 | 11/2018 | 03/2029 | - | 2838.86 | 2838.86 | 1673.49 | 47
October 2025 | 116 | Ministry of Coal | Coal | BASUNDHARA WEST EXTENSION OPEN | MCL - CIL | 615193 | Odisha | 05/2014 | 05/2014 | 03/2019 | 03/2029 | 479.15 | 479.15 | 274.52 | 64
October 2025 | 117 | Ministry of Coal | Coal | Naini Coal Mine | Singareni Collieries Company Limited [SCCL] | 615857 | Odisha | 03/2020 | 03/2020 | 03/2026 | - | 494.3 | 494.3 | 491.33 | 80
October 2025 | 118 | Ministry of Coal | Coal | INTEGRATED KULDA GARJANBAHAL O | Mahanadi Coalfields Limited [MCL] | 616226 | Odisha | 04/2023 | 04/2023 | 03/2033 | - | 3563.5 | 3563.5 | 568.97 | 3
October 2025 | 119 | Ministry of Coal | Coal | BHUBANESWARI EXPN OCP 50 MTY | MCL - CIL | 616231 | Odisha | 03/2024 | 03/2024 | 03/2033 | - | 5366.27 | 5366.27 | 466.28 | 14
October 2025 | 120 | Ministry of Coal | Coal | HINGULA II OC EXPN PH III 15 M | MCL - CIL | 616232 | Odisha | 11/2022 | 11/2022 | 03/2029 | - | 1561.85 | 1561.85 | 273.03 | 24
October 2025 | 121 | Ministry of Coal | Coal | BALABHADRA OCP | MCL - CIL | 616233 | Odisha | 04/2023 | 04/2023 | 03/2030 | - | 978.44 | 978.44 | 212.94 | 11
October 2025 | 122 | Ministry of Coal | Coal | Jawahar Khani Open Cast Mine | Singareni Collieries Company Limited [SCCL] | 615818 | Telangana | 12/2021 | 12/2021 | 03/2025 | 03/2027 | 297.88 | 297.88 | 46.83 | 20
October 2025 | 123 | Ministry of Coal | Coal | Kalyanikhani Opencast Project | Singareni Collieries Company Limited [SCCL] | 615858 | Telangana | 03/2016 | 05/2017 | 03/2026 | - | 384.32 | 384.32 | 283.94 | 75
October 2025 | 124 | Ministry of Coal | Coal | Kakathiya Khani Opencast - III Project Phase - I | Singareni Collieries Company Limited [SCCL] | 615859 | Telangana | 03/2017 | 05/2017 | 03/2026 | - | 413.84 | 413.84 | 397.55 | 79
October 2025 | 125 | Ministry of Coal | Coal | Godavarikhani Coal Mine - 5 | Singareni Collieries Company Limited [SCCL] | 615860 | Telangana | 07/2019 | 05/2019 | 03/2025 | 03/2026 | 607.04 | 607.04 | 191.37 | 71
October 2025 | 126 | Ministry of Coal | Coal | Indaram Opencast Project | Singareni Collieries Company Limited [SCCL] | 615861 | Telangana | 08/2017 | 12/2022 | 03/2025 | 03/2026 | 424.81 | 424.81 | 404.96 | 80
October 2025 | 127 | Ministry of Coal | Coal | Goleti Opencast Mine | Singareni Collieries Company Limited [SCCL] | 615862 | Telangana | 07/2021 | 08/2021 | 03/2026 | - | 345.6 | 345.6 | 76.19 | 21
October 2025 | 128 | Ministry of Coal | Coal | Venkatesh Khani Coal Mine | Singareni Collieries Company Limited [SCCL] | 615863 | Telangana | 10/2020 | 06/2020 | 03/2026 | - | 484.5 | 484.5 | 477.14 | 97
October 2025 | 129 | Ministry of Coal | Coal | Ramagundam OC-II Extension Project | Singareni Collieries Company Limited [SCCL] | 615864 | Telangana | 11/2015 | 06/2015 | 03/2026 | - | 489.62 | 489.62 | 405.54 | 77
October 2025 | 130 | Ministry of Coal | Coal | Kakatiyakhani OC - 2 Project | Singareni Collieries Company Limited [SCCL] | 615865 | Telangana | 08/2017 | 09/2017 | 03/2025 | 03/2026 | 442.42 | 442.42 | 230.28 | 63
October 2025 | 131 | Ministry of Coal | Coal | MOHANPUR EXPANSION OC -PHASE I | Eastern Coal Fields Limited [ECL] | 400173 | West Bengal | 11/2020 | 11/2020 | 03/2026 | 03/2030 | 888.99 | 888.99 | 115.8 | 30
October 2025 | 132 | Ministry of Coal | Coal | BONJEMEHARI EXPANSION OCP | Eastern Coal Fields Limited [ECL] | 400180 | West Bengal | 08/2021 | 08/2021 | 03/2026 | 03/2030 | 570.11 | 570.11 | 82.25 | 16
October 2025 | 133 | Ministry of Coal | Coal | NAKRAKONDA KUMARDIH- B OCP | Eastern Coal Fields Limited [ECL] | 400181 | West Bengal | 08/2018 | 08/2018 | 03/2029 | - | 502.68 | 502.67 | 71.11 | 26
October 2025 | 134 | Ministry of Coal | Coal | SIDULI [OC & UG] | ECL - CIL | 400182 | West Bengal | 05/2018 | 05/2018 | 03/2027 | 03/2030 | 535.18 | 535.17 | 5.28 | 14
October 2025 | 135 | Ministry of Coal | Coal | TILABONI UG | Eastern Coal Fields Limited [ECL] | 400186 | West Bengal | 01/2023 | 01/2023 | 03/2029 | - | 749.08 | 749.07 | 52.55 | 10
October 2025 | 136 | Ministry of Coal | Coal | JHANJRA EXPANSION UG | Eastern Coal Fields Limited [ECL] | 400312 | West Bengal | 04/2020 | 04/2020 | 03/2029 | - | 1210.12 | 1210.12 | 537.77 | 44
October 2025 | 137 | Ministry of Coal | Coal | SONEPUR BAZARI EXPANSION OCP [ | Eastern Coal Fields Limited [ECL] | 400315 | West Bengal | 07/2021 | 07/2021 | 03/2029 | - | 5365.88 | 5365.88 | 583.82 | 17
October 2025 | 138 | Ministry of Coal | Coal | 2.0 MTPA BHOJUDIH NLW WASHERY | Ministry of Coal | 611016 | West Bengal | 12/2015 | 03/2019 | 09/2020 | 12/2025 | 384.57 | 384.57 | 354.75 | 97
October 2025 | 139 | Ministry of Coal | Coal | ITAPARA OCP | Eastern Coal Fields Limited [ECL] | 612816 | West Bengal | 12/2023 | 12/2023 | 03/2030 | - | 929.1 | 929.1 | 68.9 | 7
October 2025 | 140 | Ministry of Coal | Coal | SHYAMSUNDARPUR UG INCLUDING SA | Eastern Coal Fields Limited [ECL] | 613793 | West Bengal | 04/2020 | 04/2020 | 03/2026 | 03/2028 | 483.65 | 483.65 | 60.46 | 12
October 2025 | 141 | Ministry of Coal | Coal | PARASEA-BELBAID UG PROJECT | Eastern Coal Fields Limited [ECL] | 613794 | West Bengal | 01/2023 | 01/2023 | 03/2028 | - | 389.1 | 389.1 | 132.48 | 21
October 2025 | 142 | Ministry of Coal | Coal | PARASCOLE JAMBAD OCP | Eastern Coal Fields Limited [ECL] | 616230 | West Bengal | 11/2024 | 11/2024 | 03/2037 | - | 1193.55 | 1193.55 | 9.53 | 0
October 2025 | 143 | Ministry of Coal | Electricity Generation | 50 MW Wind Power Project | NLC India Limited [NLCIL] | 617299 | Gujarat | 07/2022 | 01/2024 | 06/2025 | 01/2026 | 383.84 | 383.84 | 314.83 | 45
October 2025 | 144 | Ministry of Coal | Electricity Generation | 600 MW Khavda Solar Power Project | NLC India Limited [NLCIL] | 617730 | Gujarat | 08/2023 | 06/2024 | 06/2026 | - | 3335.85 | 3335.85 | 666.65 | 17
October 2025 | 145 | Ministry of Coal | Electricity Generation | NLC Talabira Thermal Power Project | NLC India Limited [NLCIL] | 400231 | Odisha | 01/2017 | 01/2024 | 03/2030 | - | 27212.96 | 27213 | 2549.31 | 1
October 2025 | 146 | Ministry of Coal | Electricity Generation | 300 MW SPP part of 510 MW CPSU scheme | NLC India Limited [NLCIL] | 612819 | Rajasthan | 07/2022 | 03/2023 | 09/2024 | 12/2025 | 1813 | 1813 | 1167.4 | 85
October 2025 | 147 | Ministry of Coal | Electricity Generation | 50 MW Solar PP Minedout Area | NLC India Limited [NLCIL] | 615327 | Tamil Nadu | 08/2023 | 02/2024 | 03/2025 | 12/2025 | 218.03 | 218.03 | 164.7 | 69
October 2025 | 148 | Ministry of Coal | Electricity Generation | Ghatampur Thermal Power Plant 3 X 660 MW | NLC India Limited [NLCIL] | 400259 | Uttar Pradesh | 07/2016 | 02/2016 | 11/2020 | 12/2025 | 17237.8 | 21780.9 | 20522.3 | 93
October 2025 | 149 | Ministry of Coal | Railways | Dharamjaigarh-Korba | Railway | 400203 | Chhattisgarh | 05/2018 | 03/2017 | 12/2026 | 08/2026 | 1686.22 | 1686.22 | 353.12 | 42
October 2025 | 150 | Ministry of Coal | Railways | Shivpur-Kathautia New Rail [BG] Line [49 km] [Package II of Tori-Shivpur-Kathautia line] | Ministry of Coal | 400416 | Jharkhand | 02/2018 | 05/2022 | 06/2025 | 06/2026 | 1799.64 | 2564.34 | 1462.35 | 61
October 2025 | 151 | Ministry of Power | Coal | Tubed Coal Mine | Damodar Valley Corporation | 400192 | Jharkhand | 07/2016 | 10/2016 | 05/2026 | 05/2026 | 1581 | 1581 | 598.06 | 35
October 2025 | 152 | Ministry of Power | Coal | Badam Coal Mining project of NTPC | National Thermal Power Corporation [NTPC] | 603293 | Jharkhand | 02/2019 | 09/2019 | 12/2056 | 04/2027 | 502 | 784 | 313.88 | 59
October 2025 | 153 | Ministry of Power | Electricity Generation | Dibang Multipurpose Project | National Hydroelectric Power Corporation Limited [NHPC] | 602182 | Arunachal Pradesh | 02/2023 | 02/2023 | 02/2032 | 02/2032 | 31876.39 | 31876.4 | 3708.61 | 16
October 2025 | 154 | Ministry of Power | Electricity Generation | 240MW Heo HE Project | North Eastern Electric Power Corporation Limited | 611698 | Arunachal Pradesh | 12/2024 | 05/2025 | 07/2029 | - | 1938.85 | 1938.85 | 64.36 | 3
October 2025 | 155 | Ministry of Power | Electricity Generation | 186 MW Tato-I H E Project | North Eastern Electric Power Corporation Limited | 611699 | Arunachal Pradesh | 12/2024 | 05/2025 | 07/2029 | - | 1750.07 | 1750.07 | 116.08 | 2
October 2025 | 156 | Ministry of Power | Electricity Generation | Buxar Thermal Power Project [1320 MW] | Satluj Jal Vidyut Nigam [SJVN] Thermal Limited | 602579 | Bihar | 03/2019 | 06/2019 | 01/2024 | 12/2025 | 10439.09 | 13756.6 | 12571.15 | 92
October 2025 | 157 | Ministry of Power | Electricity Generation | Lara Super Thermal Power Project Stage-II [2 x 800 MW] | National Thermal Power Corporation [NTPC] | 611930 | Chhattisgarh | 08/2023 | 08/2023 | 06/2028 | - | 15530 | 15530 | 2874 | 18
October 2025 | 158 | Ministry of Power | Electricity Generation | Sipat Super Thermal Power Project, Stage-III [1x800 MW] | National Thermal Power Corporation [NTPC] | 617188 | Chhattisgarh | 09/2024 | 09/2024 | 09/2029 | - | 9791 | 9791 | 856.56 | 8
October 2025 | 159 | Ministry of Power | Electricity Generation | Bagodara Solar Power Project | Satluj Jal Vidyut Nigam [SJVN] Thermal Limited | 709747 | Gujarat | 03/2021 | 05/2021 | 12/2025 | 12/2025 | 339.35 | 339.35 | 317.59 | 51
October 2025 | 160 | Ministry of Power | Electricity Generation | Dhaulasidh Hydro Electric Project [66 MW] | Satluj Jal Vidyut Nigam [SJVN] Thermal Limited | 602582 | Himachal Pradesh | 10/2020 | 05/2021 | 11/2025 | 03/2027 | 687.97 | 1561.21 | 986.12 | 70
October 2025 | 161 | Ministry of Power | Electricity Generation | Luhri Stage-I Hydro Electric Project [210 MW] | Satluj Jal Vidyut Nigam [SJVN] Thermal Limited | 602593 | Himachal Pradesh | 11/2020 | 11/2020 | 01/2026 | 10/2029 | 1810.56 | 3584.53 | 1793.11 | 51
October 2025 | 162 | Ministry of Power | Electricity Generation | 382 MW Sunni Dam HEP | Satluj Jal Vidyut Nigam [SJVN] Thermal Limited | 602633 | Himachal Pradesh | NA | 04/2018 | 03/2027 | - | 2615 | 2615 | 495.57 | 0.5
October 2025 | 163 | Ministry of Power | Electricity Generation | Sunni Dam Hydro Electric Project [382 MW] | Satluj Jal Vidyut Nigam [SJVN] Thermal Limited | 611586 | Himachal Pradesh | 01/2023 | 01/2023 | 04/2028 | 12/2029 | 2614.51 | 4540.71 | 1011.42 | 30
October 2025 | 164 | Ministry of Power | Electricity Generation | Pakal Dul [Drangdhuran] Hydroelectric Project, 1000 MW | National Hydroelectric Power Corporation Limited [NHPC] | 602525 | Jammu and Kashmir | 10/2014 | 02/2018 | 04/2020 | 12/2026 | 8112.12 | 12728 | 7581.19 | 74
October 2025 | 165 | Ministry of Power | Electricity Generation | Kiru HE Project | National Hydroelectric Power Corporation Limited [NHPC] | 602532 | Jammu and Kashmir | 03/2019 | 02/2020 | 09/2023 | 12/2026 | 4287.59 | 5409 | 3116.72 | 72
October 2025 | 166 | Ministry of Power | Electricity Generation | Ratle HE Project - 850 MW, Ratle Hydroelectric Power Corporation Limited. | National Hydroelectric Power Corporation Limited [NHPC] | 602535 | Jammu and Kashmir | 02/2021 | 01/2022 | 02/2026 | 11/2028 | 5281.94 | 5281.94 | 1112.08 | 25
October 2025 | 167 | Ministry of Power | Electricity Generation | Kwar HE Project | National Hydroelectric Power Corporation Limited [NHPC] | 605155 | Jammu and Kashmir | 05/2022 | 11/2022 | 11/2026 | 03/2028 | 4526.12 | 4526.12 | 1094.54 | 24
October 2025 | 168 | Ministry of Power | Electricity Generation | Patratu Thermal Power Station Expansion Project Phase-I [3x800 MW] | National Thermal Power Corporation [NTPC] | 400261 | Jharkhand | 07/2017 | 11/2017 | 03/2023 | 11/2026 | 17112 | 20302 | 17861.4 | 85
October 2025 | 169 | Ministry of Power | Electricity Generation | Koderma Thermal Power Station Phase II [2X800 MW] At Koderma, Jharkhand | Damodar Valley Corporation | 611509 | Jharkhand | 04/2023 | 11/2024 | 03/2029 | - | 14358 | 14358 | 1381.54 | 3
October 2025 | 170 | Ministry of Power | Electricity Generation | Subansiri Lower HE Project [2000 MW] | National Hydroelectric Power Corporation Limited [NHPC] | 602096 | Multi-States (Arunachal Pradesh, Assam) | 09/2003 | 01/2005 | 09/2010 | 05/2026 | 6285.33 | 26075.5 | 25244.57 | 97
October 2025 | 171 | Ministry of Power | Electricity Generation | Talcher Thermal Power Station Stage III [2 x 660 MW] Expansion | National Thermal Power Corporation [NTPC] | 602961 | Odisha | 08/2022 | 09/2022 | 05/2027 | 03/2028 | 11843.75 | 12543 | 4839.68 | 40
October 2025 | 172 | Ministry of Power | Electricity Generation | BIKANER SOLAR POWER PROJECT | Satluj Jal Vidyut Nigam [SJVN] Thermal Limited | 709748 | Rajasthan | 10/2021 | 05/2022 | 04/2024 | 12/2025 | 5491.89 | 5491.89 | 5084.68 | 88
October 2025 | 173 | Ministry of Power | Electricity Generation | TEESTA-VI HE PROJECT, SIKKIM [500 MW], executed by LANCO TEESTA HYDRO POWER LIMITED [A wholly owned Subsidiary of NHPC LTD. acquired through NCLT] | National Hydroelectric Power Corporation Limited [NHPC] | 602181 | Sikkim | 03/2019 | 03/2020 | 03/2024 | 12/2027 | 5748.04 | 5748.04 | 3817.49 | 70
October 2025 | 174 | Ministry of Power | Electricity Generation | Rangit-IV HE Project [120 MW] executed by Jal Power Corporation Ltd. [JPCL] -A wholly owned subsidiary of NHPC Ltd. acquired through NCLT | National Hydroelectric Power Corporation Limited [NHPC] | 605156 | Sikkim | 03/2021 | 08/2021 | 05/2024 | 12/2025 | 938.29 | 1828.11 | 1455.57 | 93
October 2025 | 175 | Ministry of Power | Electricity Generation | Khurja super Thermal Power Plant [2X660 MW] | THDC India Limited | 602194 | Uttar Pradesh | 03/2019 | 08/2019 | 02/2024 | 09/2025 | 11089.42 | 13276.2 | 12888.23 | 100
October 2025 | 176 | Ministry of Power | Electricity Generation | Singrauli Super Thermal Power Project, Stage-III [2x800 MW] | National Thermal Power Corporation [NTPC] | 612142 | Uttar Pradesh | 03/2024 | 03/2024 | 02/2030 | - | 17195 | 17195 | 1979 | 11
October 2025 | 177 | Ministry of Power | Electricity Generation | Tapovan-Vishnugad HEP [4x130 MW] | National Thermal Power Corporation [NTPC] | 602185 | Uttarakhand | NA | 11/2006 | 03/2013 | 04/2029 | 2978 | 10907.3 | 6769.58 | 77
October 2025 | 178 | Ministry of Power | Electricity Generation | Tehri Pumped Storage Plant Project [4x250 MW] | THDC India Limited | 602193 | Uttarakhand | 07/2006 | 06/2011 | 06/2022 | 12/2025 | 4825.6 | 8339 | 8149.63 | 98
October 2025 | 179 | Ministry of Power | Electricity Generation | Vishnugad Pipalkoti Hydro Electric Project [444 MW] | THDC India Limited | 602195 | Uttarakhand | 08/2008 | 01/2014 | 12/2022 | 03/2027 | 3860.35 | 6823.72 | 5245.01 | 73
October 2025 | 180 | Ministry of Power | Electricity Generation | Raghunathpur Thermal Power Station Phase II [2X660 MW] at Raghunathpur, Purulia, West Bengal | Damodar Valley Corporation | 400062 | West Bengal | 01/2023 | 02/2025 | 06/2029 | - | 17673 | 17673 | 1408.8 | 2
October 2025 | 181 | Ministry of Power | Electricity Generation | Rammam-III HEPP [3x40 MW] | National Thermal Power Corporation [NTPC] | 602184 | West Bengal | 10/2014 | 09/2014 | 09/2019 | 03/2029 | 1381.84 | 1381.84 | 1382.42 | 47
October 2025 | 182 | Ministry of Power | Electricity Generation | Installation of FGD for 4x210 & 2x250 MW MTPS U 1-6 | Damodar Valley Corporation | 602538 | West Bengal | 06/2019 | 02/2021 | 01/2024 | 12/2025 | 1037 | 1037 | 929.99 | 67
October 2025 | 183 | Ministry of Power | Transmission & Distribution | Transmission Scheme for Solar Energy Zone in Ananthpuram 2500MW and Kurnool 1000MW | Power Grid Corporation of India Limited [POWERGRID] | 611967 | Andhra Pradesh | 09/2023 | 09/2023 | 09/2025 | 03/2026 | 1248.69 | 1248.69 | 998.95 | 87
October 2025 | 184 | Ministry of Power | Transmission & Distribution | Augmentation of 1x1500 MVA 3rd 765/400 kV transformation capacity at Kurnool New Substation | Power Grid Corporation of India Limited [POWERGRID] | 612856 | Andhra Pradesh | 05/2023 | 12/2023 | 09/2025 | 01/2026 | 163.61 | 163.61 | 85.07 | 62
October 2025 | 185 | Ministry of Power | Transmission & Distribution | Transmission system strengthening at Kurnool- III PS for integration of additional RE generation projects [POWERGRID Kurnool III PS RE Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 617183 | Andhra Pradesh | 03/2025 | 03/2025 | 12/2027 | - | 2886 | 2886 | 131.31 | 1
October 2025 | 186 | Ministry of Power | Transmission & Distribution | North Eastern Region Expansion Scheme-XXIII [NERES-XXIII] | Power Grid Corporation of India Limited [POWERGRID] | 617375 | Arunachal Pradesh | 08/2025 | 08/2025 | 02/2028 | - | 209.38 | 209.38 | 0.03 | 0
October 2025 | 187 | Ministry of Power | Transmission & Distribution | Western Region Expansion Scheme-XXV | Power Grid Corporation of India Limited [POWERGRID] | 611737 | Chhattisgarh | 02/2023 | 02/2023 | 11/2023 | 10/2025 | 385.84 | 385.84 | 382.4 | 100
October 2025 | 188 | Ministry of Power | Transmission & Distribution | Transmission system strengthening scheme for evacuation of power from solar energy zones in Rajasthan 8.1 GW under Phase II- Part- G1 | Power Grid Corporation of India Limited [POWERGRID] | 608301 | Delhi | 02/2022 | 02/2022 | 09/2023 | 12/2025 | 359.47 | 359.47 | 341.49 | 97
October 2025 | 189 | Ministry of Power | Transmission & Distribution | Transmission scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase II- Part B | Power Grid Corporation of India Limited [POWERGRID] | 611656 | Gujarat | 03/2023 | 03/2023 | 03/2025 | 11/2025 | 1167.55 | 1167 | 1147.74 | 97
October 2025 | 190 | Ministry of Power | Transmission & Distribution | Transmission scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase II- Part C | Power Grid Corporation of India Limited [POWERGRID] | 611657 | Gujarat | 03/2023 | 03/2023 | 03/2025 | 12/2025 | 2820.99 | 2820.99 | 2736.36 | 93
October 2025 | 191 | Ministry of Power | Transmission & Distribution | Establishment of Khavda Pooling Station-2 KPS2 in Khavda RE Park KPS2 TRANSMISSION SYSTEM LIMITED | Power Grid Corporation of India Limited [POWERGRID] | 611660 | Gujarat | 03/2023 | 03/2023 | 12/2024 | 11/2025 | 966.79 | 966.79 | 936.24 | 97
October 2025 | 192 | Ministry of Power | Transmission & Distribution | Transmission system for Evacuation of Additional 7 GW RE power from Khavda RE park under Phase-III Part B [Vataman Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 612139 | Gujarat | 12/2023 | 12/2023 | 12/2025 | 12/2026 | 3751.82 | 3751.82 | 1688.32 | 28
October 2025 | 193 | Ministry of Power | Transmission & Distribution | Transmission System for Evacuation of Power from potential Renewable Energy zone in Khavda Area of Gujarat under Phase IV [7 GW] Part E3 | Power Grid Corporation of India Limited [POWERGRID] | 612151 | Gujarat | 07/2023 | 07/2023 | 07/2025 | 03/2026 | 334 | 334 | 118.1 | 36
October 2025 | 194 | Ministry of Power | Transmission & Distribution | Transmission System for Evacuation of Power from Potential Energy Renewable Zone in Khavda Area of Gujarat under Ph-IV [7GW] Part E2 | Power Grid Corporation of India Limited [POWERGRID] | 612855 | Gujarat | 05/2024 | 05/2024 | 05/2026 | 06/2026 | 679 | 679 | 135.8 | 27
October 2025 | 195 | Ministry of Power | Transmission & Distribution | Augmentation of Transformation Capacity at jam Khambhaliya PS [GIS] [SPV Name POWERGRID Jam Khambhaliya Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 615342 | Gujarat | 10/2024 | 10/2024 | 07/2026 | - | 329 | 329 | 13.17 | 3
October 2025 | 196 | Ministry of Power | Transmission & Distribution | Provision of Dynamic Reactive Compensation at Khavda pooling Station 1 [KPS1] and Khavda Pooling station 3 [KPS3] | Power Grid Corporation of India Limited [POWERGRID] | 615343 | Gujarat | 11/2024 | 11/2024 | 11/2026 | - | 501 | 501 | 8.11 | 2
October 2025 | 197 | Ministry of Power | Transmission & Distribution | Transmission System for Evacuation of Power from Potential Renewable Energy Zone in Khavda area of Gujarat under Phase-IV [7GW] Part B [SPV Name POWERGRID South Olpad Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 615345 | Gujarat | 10/2024 | 10/2024 | 10/2026 | 03/2027 | 4766 | 4766 | 714.9 | 9
October 2025 | 198 | Ministry of Power | Transmission & Distribution | Augmentation of Transformation Capacity at KPS1 [GIS] and KPS2 [GIS] [Phase-V Part B1 and Part B2 Scheme] [SPV Name- POWERGRID KPS1 and 2 Augmentation Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 617069 | Gujarat | 02/2025 | 02/2025 | 02/2027 | - | 466 | 466 | 24.3 | 2
October 2025 | 199 | Ministry of Power | Transmission & Distribution | Augmentation of Banaskantha [Raghanesda] PS [GIS] [POWERGRID Banaskantha Transco Limited] | Power Grid Corporation of India Limited [POWERGRID] | 617182 | Gujarat | 03/2025 | 03/2025 | 03/2027 | - | 172 | 172 | 17.27 | 15
October 2025 | 200 | Ministry of Power | Transmission & Distribution | Augmentation of Transformation Capacity at Bhuj-II PS [GIS] | Power Grid Corporation of India Limited [POWERGRID] | 617391 | Gujarat | 02/2025 | 02/2025 | 11/2026 | 03/2027 | 488.29 | 488.29 | 0.12 | 0
October 2025 | 201 | Ministry of Power | Transmission & Distribution | Jamnagar Transmission Limited | Adani Transmission Limited | 617405 | Gujarat | NA | 10/2024 | 10/2026 | - | 4000 | 4000 | 0 | 0
October 2025 | 202 | Ministry of Power | Transmission & Distribution | Provision of ICT Augmentation & Bus Reactor at Bhuj-II PS | Power Grid Corporation of India Limited [POWERGRID] | 617801 | Gujarat | 03/2025 | 03/2025 | 12/2026 | 03/2027 | 581.74 | 581.74 | 0.2 | 0
October 2025 | 203 | Ministry of Power | Transmission & Distribution | Implementation of LILO of both circuits of 400KV vindhyachal PS-Sasan D/C Line at Hindalco Switchyard | Power Grid Corporation of India Limited [POWERGRID] | 617272 | Haryana | 06/2024 | 06/2024 | 12/2026 | - | 370 | 370 | 18.55 | 6
October 2025 | 204 | Ministry of Power | Transmission & Distribution | Transmission system for evacuation of Power from Pakaldul HEP in Chenab Valley HEPs - LTA System | Power Grid Corporation of India Limited [POWERGRID] | 608302 | Jammu and Kashmir | 02/2022 | 02/2022 | 04/2025 | 11/2025 | 318.12 | 318.12 | 317.12 | 100
October 2025 | 205 | Ministry of Power | Transmission & Distribution | Transmission Scheme for evacuation of Power from Ratle HEP [850 MW] & kiru [624 MW] Part B | Power Grid Corporation of India Limited [POWERGRID] | 617179 | Jammu and Kashmir | 07/2024 | 07/2024 | 07/2026 | 03/2027 | 218.6 | 218.6 | 2.11 | 0
October 2025 | 206 | Ministry of Power | Transmission & Distribution | Implementation of Transmission Systems in the State of Jharkhand consisting of 400/220/132/33 kV transmission lines and substations under Jharkhand Consultancy Project | Power Grid Corporation of India Limited [POWERGRID] | 617326 | Jharkhand | 02/2012 | 02/2012 | 03/2026 | - | 1842.25 | 1842.25 | 1648.05 | 95
October 2025 | 207 | Ministry of Power | Transmission & Distribution | Transmission Scheme for Integration of Renewable Energy Zone [Phase II] in Koppal II [Phase A&B] and gadag II[Phase A] in Karnataka [POWERGRID KOPPAL GADAG TRANSMISSION LIMITED] | Power Grid Corporation of India Limited [POWERGRID] | 612140 | Karnataka | 12/2023 | 12/2023 | 12/2025 | 06/2026 | 2889.39 | 2889.39 | 1533.89 | 54
October 2025 | 208 | Ministry of Power | Transmission & Distribution | System Strengthening at Koppal-II and GadagII for integration of RE generation projects [SPV Name POWERGRID Koppal Gadag Augmentation Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 616672 | Karnataka | 01/2025 | 01/2025 | 06/2027 | - | 1354 | 1354 | 40.62 | 1
October 2025 | 209 | Ministry of Power | Transmission & Distribution | Augmentation of Transformation Capacity by 3x500 MVA, 400/220 KV ICTS [6th-8th] and 1x1500 MVA, 765/400 KV ICT [4th] at Bidar PS [SPV Name- POWERGRID Bidar Augmentation Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 617068 | Karnataka | 02/2025 | 02/2025 | 06/2027 | - | 288 | 288 | 6.91 | 1
October 2025 | 210 | Ministry of Power | Transmission & Distribution | Transmission Scheme for integration of Davanagere/ Chitradurga and Bellary REZ in Karnataka [POWERGRID Chitradurga Bellary REZ Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 617184 | Karnataka | 03/2025 | 03/2025 | 09/2027 | - | 3453 | 3453 | 52.48 | 1
October 2025 | 211 | Ministry of Power | Transmission & Distribution | Transmission System Strengthening at Davanagere for Integration of RE Generation [SPV Name - POWERGRID Davanagere Power Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 617803 | Karnataka | 09/2025 | 09/2025 | 09/2027 | - | 379 | 379 | 6.6 | 0
October 2025 | 212 | Ministry of Power | Transmission & Distribution | Transmission System for Evacuation of Power from Rajasthan REZ Ph-IV [Part-2 5.5GW] [Jaisalmer/Barmer Complex] Part H1 [POWERGRID KURAWAR TRANSMISSION LIMITED] | Power Grid Corporation of India Limited [POWERGRID] | 615344 | Madhya Pradesh | 10/2024 | 10/2024 | 10/2026 | 03/2027 | 3674 | 3674 | 624.58 | 17
October 2025 | 213 | Ministry of Power | Transmission & Distribution | Transmission System for Evacuation of Power from Rajasthan REZ Ph-IV [Part-2 5.5 GW] [Jaisalmer/Barmer Complex] Part C [SPV Name POWERGRID Mandsaur Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 615346 | Madhya Pradesh | 08/2024 | 08/2024 | 08/2026 | 12/2026 | 2708 | 2708 | 1029.04 | 41
October 2025 | 214 | Ministry of Power | Transmission & Distribution | Transmission System for evacuation of power from Mahan Energen Limited Generating Station in Madhya Pradesh [SPV Name - POWERGRID MEL Power Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 617279 | Madhya Pradesh | 06/2025 | 06/2025 | 12/2027 | - | 558 | 558 | 33.48 | 1
October 2025 | 215 | Ministry of Power | Transmission & Distribution | Augmentation of Transformation Capacity and Implementation of Line Bays at Mandsaur S/S for RE Interconnection [SPV Name- POWERGRID Mandsaur I RE Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 617802 | Madhya Pradesh | 10/2025 | 10/2025 | 03/2028 | - | 319 | 319 | 0.1 | 0
October 2025 | 216 | Ministry of Power | Transmission & Distribution | Transmission System for Evacuation of power from Potential RE Zone in Khavda Area of Gujarat under phase IV 7GW-Part E4 | Power Grid Corporation of India Limited [POWERGRID] | 611966 | Maharashtra | 11/2023 | 11/2023 | 07/2025 | 03/2026 | 224.41 | 224.41 | 33.66 | 18
October 2025 | 217 | Ministry of Power | Transmission & Distribution | Transmission System for Integration of Kurnool-IV REZ Phase-I [for 4.5 GW] [POWERGRID Kurnool-IV Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 617185 | Multi-States (Andhra Pradesh, Karnataka) | 03/2025 | 03/2025 | 03/2027 | - | 5550 | 5550 | 332.68 | 1
October 2025 | 218 | Ministry of Power | Transmission & Distribution | Transmission System for Kurnool Wind Energy Zone/ Solar Energy Zone Part-A and Part-B | Power Grid Corporation of India Limited [POWERGRID] | 900808 | Multi-States (Andhra Pradesh, Telangana) | 11/2022 | 03/2023 | 11/2024 | 01/2026 | 3546.94 | 3546.94 | 3369.59 | 97
October 2025 | 219 | Ministry of Power | Transmission & Distribution | Comprehensive Scheme for Strengthening of Transmission and Distribution [T&D] Systems [CSST&DS] in Arunachal Pradesh and Sikkim | Power Grid Corporation of India Limited [POWERGRID] | 602223 | Multi-States (Arunachal Pradesh, Sikkim) | 10/2014 | 10/2014 | 12/2018 | 03/2027 | 4754.42 | 9129.32 | 7705.14 | 82
October 2025 | 220 | Ministry of Power | Transmission & Distribution | NORTH EASTERN REGION POWER SYSTEM IMPROVEMENT PROJECT [NERPSIP] | Power Grid Corporation of India Limited [POWERGRID] | 607709 | Multi-States (Assam, Manipur, Meghalaya, Mizoram, Nagaland, Tripura) | 12/2014 | 03/2016 | 12/2018 | 03/2026 | 5111.33 | 6700 | 5317.79 | 96
October 2025 | 221 | Ministry of Power | Transmission & Distribution | Eastern Region Expansion Scheme-43 [ERES-43] | Power Grid Corporation of India Limited [POWERGRID] | 617271 | Multi-States (Bihar, Odisha, West Bengal) | 09/2024 | 09/2024 | 03/2026 | 06/2026 | 342.69 | 342.69 | 0.71 | 0
October 2025 | 222 | Ministry of Power | Transmission & Distribution | Eastern Region Expansion Scheme-44 [ERES-44] | Power Grid Corporation of India Limited [POWERGRID] | 617270 | Multi-States (Bihar, West Bengal) | 11/2024 | 11/2024 | 05/2026 | 03/2027 | 408.94 | 408.94 | 0.32 | 0
October 2025 | 223 | Ministry of Power | Transmission & Distribution | Transmission Network Expansion in Gujarat to increase its ATC from ISTS Part B | Power Grid Corporation of India Limited [POWERGRID] | 400005 | Multi-States (Dadra & Nagar Haveli and Daman & Diu, Gujarat, Maharashtra) | 01/2022 | 07/2022 | 06/2023 | 12/2025 | 4546.26 | 4546.26 | 4210.3 | 93
October 2025 | 224 | Ministry of Power | Transmission & Distribution | Transmission System Strengthening Scheme for evacuation of power from SEZ in Rajasthan 8.1 GW under Phase II Part G | Power Grid Corporation of India Limited [POWERGRID] | 608922 | Multi-States (Delhi, Haryana, Rajasthan) | 05/2022 | 05/2022 | 11/2023 | 11/2025 | 1666 | 2218 | 2129.28 | 96
October 2025 | 225 | Ministry of Power | Transmission & Distribution | Transmission system for evacuation of power from REZ in Rajasthan 20GW under Phase-III Part J | Power Grid Corporation of India Limited [POWERGRID] | 611735 | Multi-States (Delhi, Rajasthan) | 12/2022 | 12/2022 | 03/2025 | 07/2026 | 331 | 331 | 135.71 | 31
October 2025 | 226 | Ministry of Power | Transmission & Distribution | Transmission Scheme for Evacuation of power from REZ in Rajasthan [20 GW] under Phase-III Part D [Sikar Khetri Transmission Ltd] | Power Grid Corporation of India Limited [POWERGRID] | 612132 | Multi-States (Delhi, Rajasthan) | 02/2024 | 02/2024 | 08/2025 | 06/2026 | 2000 | 2000 | 1460 | 68
October 2025 | 227 | Ministry of Power | Transmission & Distribution | TRANSMISSION SYSTEM FOR EVACUATION OF POWER FROM POTENTIAL RENEWABLE ENERGY ZONE IN KHAVDA AREA OF GUJARAT UNDER PHASE-V [8 GW] PART A [SPV Name POWERGRID West Central Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 615347 | Multi-States (Gujarat, Maharashtra) | 11/2024 | 11/2024 | 05/2029 | - | 24819 | 24819 | 1985.46 | 2
October 2025 | 228 | Ministry of Power | Transmission & Distribution | Transmission system for evacuation of power from Rajasthan REZ Ph-IV [Part- 3/6GW] [Bikaner complex] Part A [SPV Name POWERGRID Bikaner IV Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 615339 | Multi-States (Haryana, Punjab, Rajasthan) | 11/2024 | 11/2024 | 11/2026 | 03/2027 | 5969 | 5969 | 485.87 | 9
October 2025 | 229 | Ministry of Power | Transmission & Distribution | TRANSMISSION SYSTEM FOR EVACUATION OF POWER FROM RAJASTHAN REZ PH-IV [PART-3/ 6 GW] [BIKANER COMPLEX] PART B [SPV Name POWERGRID Siwani Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 615340 | Multi-States (Haryana, Rajasthan) | 11/2024 | 11/2024 | 11/2026 | 03/2027 | 5357 | 5357 | 428.56 | 13
October 2025 | 230 | Ministry of Power | Transmission & Distribution | Transmission System for Strengthening of Srinagar-Leh Tr. System | Power Grid Corporation of India Limited [POWERGRID] | 606781 | Multi-States (Jammu and Kashmir, Ladakh) | 03/2022 | 03/2022 | 12/2024 | 11/2025 | 288.71 | 288.71 | 280.02 | 99
October 2025 | 231 | Ministry of Power | Transmission & Distribution | Transmission Scheme for Solar Energy Zone in Bidar [2500 MW], Karnataka [Bidar Transmission Ltd] | Power Grid Corporation of India Limited [POWERGRID] | 612138 | Multi-States (Karnataka, Telangana) | 02/2024 | 02/2024 | 02/2026 | 06/2026 | 2147.62 | 2147.62 | 1438.9 | 67
October 2025 | 232 | Ministry of Power | Transmission & Distribution | Transmission System for Evacuation of Power from Rajasthan REZ Ph-IV [Part-2 5.5 GW] [Jaisalmer/Barmer Complex] Part D [SPV Name POWERGRID Beawar Mandsaur Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 615333 | Multi-States (Madhya Pradesh, Rajasthan) | 08/2024 | 08/2024 | 08/2026 | - | 2227 | 2227 | 779.45 | 23
October 2025 | 233 | Ministry of Power | Transmission & Distribution | Transmission System for Evacuation of Power from Rajasthan REZ Ph-IV [Part-2 5.5 GW] [Jaisalmer/Barmer Complex] Part E [SPV Name POWERGRID Mewar Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 615334 | Multi-States (Madhya Pradesh, Rajasthan) | 08/2024 | 08/2024 | 08/2026 | 03/2027 | 3251 | 3251 | 942.79 | 26
October 2025 | 234 | Ministry of Power | Transmission & Distribution | Rajasthan REZ Ph-V [Part-1- 4 GW] [Sirohi/Nagaur] Complex [Rajasthan V Power Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 617186 | Multi-States (Madhya Pradesh, Rajasthan) | 03/2025 | 03/2025 | 03/2027 | - | 5028 | 5028 | 256.93 | 2
October 2025 | 235 | Ministry of Power | Transmission & Distribution | Transmission System for Evacuation of power from Rajasthan REZ Ph-IV [Part-1] [Bikaner Complex] Part D [Neemrana Bareilly Transmission Ltd] | Power Grid Corporation of India Limited [POWERGRID] | 612133 | Multi-States (Rajasthan, Uttar Pradesh) | 12/2023 | 12/2023 | 12/2025 | 06/2026 | 2056 | 2056 | 1603.68 | 62
October 2025 | 236 | Ministry of Power | Transmission & Distribution | Transmission System for evacuation of Power from Rajasthan REZ Ph-IV [Part-4 3.5 GW] Part A [SPV name POWERGRID Ghiror Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 616670 | Multi-States (Rajasthan, Uttar Pradesh) | 12/2024 | 12/2024 | 12/2026 | 03/2027 | 5846 | 5846 | 467.68 | 9
October 2025 | 237 | Ministry of Power | Transmission & Distribution | Transmission system strengthening scheme for evacuation of power from solar energy zones in Rajasthan[8.1 GW] under phase-II- Part E | Power Grid Corporation of India Limited [POWERGRID] | 611659 | Rajasthan | 03/2023 | 03/2023 | 09/2024 | 11/2025 | 1433.28 | 1433 | 1418.67 | 98
October 2025 | 238 | Ministry of Power | Transmission & Distribution | Transmission System for Evacuation of Power from REZ in Rajasthan 20GW under Phase III- Part E2 | Power Grid Corporation of India Limited [POWERGRID] | 611947 | Rajasthan | 11/2023 | 11/2023 | 06/2025 | 03/2026 | 428.3 | 428.3 | 291.24 | 73
October 2025 | 239 | Ministry of Power | Transmission & Distribution | Transmission system for evacuation of power from REZ in Rajasthan 20 GW under Phase-III part H | Power Grid Corporation of India Limited [POWERGRID] | 611948 | Rajasthan | 10/2023 | 10/2023 | 04/2025 | 01/2026 | 2211.29 | 2211.29 | 1945.93 | 88
October 2025 | 240 | Ministry of Power | Transmission & Distribution | Transmission system for evacuation of power from REZ in Rajasthan 20 GW under Phase-III part C1 | Power Grid Corporation of India Limited [POWERGRID] | 611949 | Rajasthan | 10/2023 | 10/2023 | 04/2025 | 03/2026 | 1796.02 | 1796.02 | 1436.81 | 89
October 2025 | 241 | Ministry of Power | Transmission & Distribution | Transmission system for evacuation of power from REZ in Rajasthan 20 GW under Phase-III part B1 | Power Grid Corporation of India Limited [POWERGRID] | 611950 | Rajasthan | 09/2023 | 09/2023 | 04/2025 | 12/2025 | 2190.54 | 2190.54 | 1949.58 | 91
October 2025 | 242 | Ministry of Power | Transmission & Distribution | Transmission system for evacuation of power from REZ in Rajasthan 20GW under Phase-III Part E1 | Power Grid Corporation of India Limited [POWERGRID] | 611951 | Rajasthan | 12/2021 | 08/2023 | 02/2025 | 12/2025 | 688.74 | 688.74 | 654.3 | 97
October 2025 | 243 | Ministry of Power | Transmission & Distribution | Transmission System for Evacuation of power from Rajasthan REZ Ph-IV [Part-1] [Bikaner Complex] Part A [Bikaner Neemrana Transmission Ltd] | Power Grid Corporation of India Limited [POWERGRID] | 612134 | Rajasthan | 12/2023 | 12/2023 | 12/2025 | 06/2026 | 2998.34 | 2998.34 | 2008.88 | 57
October 2025 | 244 | Ministry of Power | Transmission & Distribution | Transmission System for Evacuation of Power from Rajasthan REZ Ph-IV [Part-2 5.5 GW][Jaisalmer/Barmer Complex] Part B [SPV Name POWERGRID Sirohi Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 615332 | Rajasthan | 08/2024 | 08/2024 | 08/2026 | 12/2026 | 3279 | 3279 | 918.12 | 26
October 2025 | 245 | Ministry of Power | Transmission & Distribution | Transmission System Strengthening for Interconnections of Bhadla-III & Bikaner III Complex [SPV Name POWERGRID BHADLA BIKANER TRANSMISSION LIMITED] | Power Grid Corporation of India Limited [POWERGRID] | 615335 | Rajasthan | 08/2024 | 08/2024 | 08/2026 | 12/2026 | 1382 | 1382 | 138.2 | 9
October 2025 | 246 | Ministry of Power | Transmission & Distribution | Additional Transmission System for evacuation of Power from Bhadla-III PS as part of Rajasthan REZ Phase III Scheme [20 GW] [SPV Name POWERGRID Bhadla-III Power Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 615337 | Rajasthan | 08/2024 | 08/2024 | 02/2026 | 03/2026 | 369 | 369 | 103.32 | 22
October 2025 | 247 | Ministry of Power | Transmission & Distribution | TRANSMISSION SYSTEM FOR EVACUATION OF POWER FROM RAJASTHAN REZ PH -IV [PART-2 5.5 GW] [JAISALMER/BARMER COMPLEX] PART F [SPV Name POWERGRID BARMER I TRANSMISSION LIMITED] | Power Grid Corporation of India Limited [POWERGRID] | 615338 | Rajasthan | 11/2024 | 11/2024 | 11/2026 | 06/2027 | 2735 | 2735 | 324.64 | 11
October 2025 | 248 | Ministry of Power | Transmission & Distribution | Augmentation at Fatehgarh-II PS, Fatehgarh-IV PS [Section-II] and Barmer-I PS [POWERGRID Fatehgarh Barmer Augmentation Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 617181 | Rajasthan | 03/2025 | 03/2025 | 12/2026 | 03/2027 | 404 | 404 | 16.16 | 1
October 2025 | 249 | Ministry of Power | Transmission & Distribution | Transmission System under ISTS for evacuation of Power from Kudankulam Unit-3&4 [2x1000 MW] [SPV Name POWERGRID Kudankulam Tarnsmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 616671 | Tamil Nadu | 01/2025 | 01/2025 | 12/2026 | 12/2026 | 548 | 548 | 37.86 | 9
October 2025 | 250 | Ministry of Power | Transmission & Distribution | Transmission System for Strengthening to facilitate evacuation of power from Bhadla/Bikaner Complex | Power Grid Corporation of India Limited [POWERGRID] | 617269 | Uttar Pradesh | 12/2024 | 12/2024 | 06/2026 | 08/2026 | 212.81 | 212.81 | 2.1 | 0
October 2025 | 251 | Ministry of Housing & Urban Affairs | Construction | C/o 184 MS Flats for Hon'ble MPs at BKS Marg, New Delhi | Central Public Works Department [CPWD] | 617282 | Delhi | 01/2022 | 05/2022 | 05/2025 | 09/2025 | 646.53 | 646.52 | 545.86 | 100
October 2025 | 252 | Ministry of Housing & Urban Affairs | Construction | Construction of One Tower of Office Complex and another Tower of Residential quarters consisting of 10Nos. Type-V, 10Nos. Type-VI & 1No.Type-VII Quarters i/c internal water supply, sanitary installation and all development and bulk services, Horticulture works on EPC Mode-I basis i/c comprehensive operation and maintenance of Civil, E&M services for 7 years after completion of original construction work for Ranga Reddy, Secunderabad, Medchal, AuditI, Audit-II Commissionerates of Central Tax at Khajaguda, Serilingampally, Hyderabad. | Central Public Works Department - CPWD | 617412 | Telangana | 03/2024 | 11/2024 | 09/2027 | - | 644 | 644 | 87.6 | 6
October 2025 | 253 | Ministry of Housing & Urban Affairs | Inland Waterways | Chennai Metro Rail Phase-II Development Project | Chennai Metro Rail Limited [CMRL] | 702668 | Tamil Nadu | 10/2024 | 11/2020 | 08/2029 | - | 63246 | 63246 | 28778.98 | 47
October 2025 | 254 | Ministry of Housing & Urban Affairs | Real Estate | Integrated Command control Center [ICCC] - Construction and Development of Integrated Command Control Center with Security, Surveillance, ITMS, Connecting Port, Ship Service, Smart Solid Waste Management, Smart Public Transport System | ministry of housing and urban affairs | 707229 | Andaman & Nicobar | 07/2021 | 11/2021 | 05/2023 | - | 209.88 | 209.88 | 0 | 70
October 2025 | 255 | Ministry of Housing & Urban Affairs | Real Estate | Redevelopment of Seven General Pool Residential Accommodation [GPRA] Colonies in Delhi | National Buildings Construction Corporation [NBCC] | 400188 | Delhi | 07/2016 | 05/2018 | 12/2025 | 12/2025 | 32850 | 32850 | 0 | 0
October 2025 | 256 | Ministry of Housing & Urban Affairs | Real Estate | Rehablitation in Junavadaj Area Smart City Project | ministry of housing and urban affairs | 701719 | Gujarat | 02/2016 | 06/2016 | 07/2022 | - | 539 | 539 | 39.63 | 50
October 2025 | 257 | Ministry of Housing & Urban Affairs | Real Estate | Green Building Development Project | ministry of housing and urban affairs | 701766 | Uttarakhand | 11/2019 | 08/2019 | 11/2023 | - | 150.97 | 150.97 | 18.95 | 31
October 2025 | 258 | Ministry of Housing & Urban Affairs | Urban Public Transport | Patna Metro Rail Project | Patna Metro Rail Corporation Ltd. [PMRCL] | 702627 | Bihar | 02/2019 | 02/2019 | 02/2024 | 06/2027 | 13365.77 | 13365.8 | 4039.77 | 46
October 2025 | 259 | Ministry of Housing & Urban Affairs | Urban Public Transport | Delhi Metro Rail Phase-IV [2 Corridors] | Delhi Metro Rail Corporation Limited [DMRC] | 617207 | Delhi | 03/2024 | 03/2024 | 03/2029 | - | 8399.81 | 8399.81 | 55.92 | 0
October 2025 | 260 | Ministry of Housing & Urban Affairs | Urban Public Transport | DMRTS Phase - IV [3 Priority Corridors] | Delhi Metro Rail Corporation Limited [DMRC] | 702632 | Delhi | 07/2019 | 07/2019 | 03/2025 | 03/2026 | 24948.65 | 24948.7 | 17838.17 | 71
October 2025 | 261 | Ministry of Housing & Urban Affairs | Urban Public Transport | Surat Metro Rail Project | Gujarat Metro Rail Corporation Limited [GMRCL] | 702630 | Gujarat | 03/2019 | 04/2019 | 03/2024 | 06/2026 | 12020.32 | 12020.3 | 7977.03 | 72
October 2025 | 262 | Ministry of Housing & Urban Affairs | Urban Public Transport | Ahmedabad Metro Rail Project, Phase-II | Gujarat Metro Rail Corporation Limited [GMRCL] | 702631 | Gujarat | 03/2019 | 03/2019 | 03/2024 | 12/2025 | 5384.17 | 5384.17 | 4308.13 | 91
October 2025 | 263 | Ministry of Housing & Urban Affairs | Urban Public Transport | Ahmedabad Metro Rail Project [Phase-I] | Gujarat Metro Rail Corporation Limited [GMRCL] | 702639 | Gujarat | 11/2014 | 02/2015 | 03/2018 | 10/2025 | 10773 | 12924.5 | 12212.92 | 99
October 2025 | 264 | Ministry of Housing & Urban Affairs | Urban Public Transport | Construction of Bangalore Metro Rail Project Phase 2. | Bengaluru Metro Rail | 702635 | Karnataka | 02/2014 | 02/2016 | 03/2021 | 09/2026 | 26405.14 | 30695.1 | 29617.97 | 94
October 2025 | 265 | Ministry of Housing & Urban Affairs | Urban Public Transport | Construction Bangalore Metro Rail Project Phase-2A & 2B | Bengaluru Metro Rail | 702665 | Karnataka | 06/2021 | 01/2019 | 06/2026 | 06/2026 | 14788.1 | 14788.1 | 8915.63 | 57
October 2025 | 266 | Ministry of Housing & Urban Affairs | Urban Public Transport | Kochi Metro Rail Phase 2 Development Project | CSPCC Projects | 702664 | Kerala | 11/2022 | 11/2022 | 11/2026 | 11/2026 | 1957.05 | 1957.05 | 425.58 | 19
October 2025 | 267 | Ministry of Housing & Urban Affairs | Urban Public Transport | Bhopal Metro Rail Project | Madhya Pradesh Metro Rail Co Limited [MPMRCL] | 702625 | Madhya Pradesh | 11/2018 | 11/2018 | 11/2022 | 06/2028 | 6941.4 | 6941.4 | 3676.19 | 47
October 2025 | 268 | Ministry of Housing & Urban Affairs | Urban Public Transport | Indore Metro Rail Project | Madhya Pradesh Metro Rail Co Limited [MPMRCL] | 702626 | Madhya Pradesh | 11/2018 | 11/2018 | 11/2022 | 12/2028 | 7500.8 | 7500.8 | 4223.43 | 57
October 2025 | 269 | Ministry of Housing & Urban Affairs | Urban Public Transport | PCMC To Nigdi- Extension Of North South Corridor Of Phase-1 | Maharashtra Metro Rail Corporation Limited [MMRCL] | 617225 | Maharashtra | 10/2023 | 10/2023 | 01/2027 | - | 910.18 | 910.18 | 147.84 | 26
October 2025 | 270 | Ministry of Housing & Urban Affairs | Urban Public Transport | Pune Metro Phase-1 Extension line towards south from Swargate to Katraj | Maharashtra Metro Rail Corporation Limited [MMRCL] | 617226 | Maharashtra | 09/2024 | 09/2024 | 03/2029 | - | 2954.53 | 2954.53 | 22.17 | 3
October 2025 | 271 | Ministry of Housing & Urban Affairs | Urban Public Transport | Thane Integral Ring Metro Rail Project | Maharashtra Metro Rail Corporation Limited [MMRCL] | 617327 | Maharashtra | 09/2024 | 09/2024 | 09/2029 | - | 12200.1 | 12200.1 | 7.77 | 3
October 2025 | 272 | Ministry of Housing & Urban Affairs | Urban Public Transport | New Suburba Station Development Project | ministry of housing and urban affairs | 701745 | Maharashtra | 04/2018 | 03/2019 | 07/2022 | - | 262.76 | 262.76 | 17.62 | 6
October 2025 | 273 | Ministry of Housing & Urban Affairs | Urban Public Transport | Kalyan Station Precinct Imporvement Project | ministry of housing and urban affairs | 701991 | Maharashtra | 04/2018 | 07/2020 | 07/2023 | - | 600 | 600 | 272.42 | 70
October 2025 | 274 | Ministry of Housing & Urban Affairs | Urban Public Transport | Mumbai Metro Line 3 | Mumbai Metro Rail Corporation Limited [MMRC] | 702637 | Maharashtra | 07/2013 | 06/2016 | 03/2023 | 08/2025 | 23136 | 37276 | 31783.93 | 96
October 2025 | 275 | Ministry of Housing & Urban Affairs | Urban Public Transport | Nagpur Metro Rail Phase II Development Project | Maharashtra Metro Rail Corporation Limited [MMRCL] | 702658 | Maharashtra | 12/2022 | 12/2022 | 12/2027 | - | 6708 | 6708 | 1259.29 | 28
October 2025 | 276 | Ministry of Housing & Urban Affairs | Urban Public Transport | Delhi Metro Rail Phase-IV [Rithala - Kundli Corridor] | Delhi Metro Rail Corporation Limited [DMRC] | 617206 | Multi-States (Delhi, Haryana) | 01/2025 | 01/2025 | 01/2029 | - | 6230.99 | 6230.99 | 72.38 | 0
October 2025 | 277 | Ministry of Housing & Urban Affairs | Urban Public Transport | Delhi-Ghaziabad-Meerut Regional Rapid Transit System [RRTS] corridor | National Capital Region Transport Corporation [NCRTC] | 702633 | Multi-States (Delhi, Uttar Pradesh) | 03/2019 | 03/2019 | 06/2025 | 10/2025 | 30274 | 30274 | 26612.45 | 95
October 2025 | 278 | Ministry of Housing & Urban Affairs | Urban Public Transport | Kanpur Metro Rail Project | Uttar Pradesh metro rail corporation [UPMRC] | 702628 | Uttar Pradesh | 05/2019 | 11/2019 | 05/2024 | 03/2027 | 11076.48 | 11076.5 | 9093.83 | 76
October 2025 | 279 | Ministry of Housing & Urban Affairs | Urban Public Transport | Agra Metro Rail Project | Uttar Pradesh metro rail corporation [UPMRC] | 702629 | Uttar Pradesh | 05/2019 | 12/2020 | 05/2024 | 06/2027 | 8379.62 | 8379.62 | 6067.88 | 63
October 2025 | 280 | Ministry of Housing & Urban Affairs | Waste & Water | ESR - 8 nos., distribution system - 216 Km, new house service connections - 38760 nos. upgrading of feeder mains, pumping station etc. - Phase II | Ministry of Housing & Urban Affairs | 702674 | Andhra Pradesh | 02/2017 | 07/2018 | 03/2023 | 12/2025 | 172.22 | 172.22 | 799.74 | 82
October 2025 | 281 | Ministry of Housing & Urban Affairs | Waste & Water | Dibrugarh Water Supply Infrastructure Project | Ministry of Housing & Urban Affairs | 702682 | Assam | 02/2016 | 01/2020 | 03/2023 | 12/2025 | 186.8 | 186.8 | 1664.41 | 100
October 2025 | 282 | Ministry of Housing & Urban Affairs | Waste & Water | Muzaffarpur Storm Water Drainage Phase-I Project | Ministry of Housing & Urban Affairs | 702699 | Bihar | 11/2016 | 02/2019 | 10/2023 | 12/2025 | 158.78 | 158.78 | 602.5 | 83
October 2025 | 283 | Ministry of Housing & Urban Affairs | Waste & Water | Storm water drainag Development Project | ministry of housing and urban affairs | 702355 | Dadra & Nagar Haveli and Daman & Diu | 08/2020 | 12/2021 | 03/2024 | - | 210 | 210 | 0 | 20
October 2025 | 284 | Ministry of Housing & Urban Affairs | Waste & Water | Upgradation of Sewerage system in Gandhinagar City | ministry of housing and urban affairs | 707267 | Gujarat | 07/2020 | 03/2021 | 06/2023 | - | 200 | 200 | 100 | 10
October 2025 | 285 | Ministry of Housing & Urban Affairs | Waste & Water | Sewerage Management Scheme Part-3 Implementation | Ministry of Housing & Urban Affairs | 702734 | Haryana | 03/2017 | 11/2017 | 09/2023 | 03/2026 | 278.01 | 278.01 | 2005.13 | 88
October 2025 | 286 | Ministry of Housing & Urban Affairs | Waste & Water | Sewerage Management Scheme Part-3 Implementation | Ministry of Housing & Urban Affairs | 702735 | Haryana | 03/2017 | 10/2018 | 03/2023 | 12/2025 | 213.19 | 213.19 | 1430.38 | 91
October 2025 | 287 | Ministry of Housing & Urban Affairs | Waste & Water | Dhanbad Water Supply Infrastructure Project | Ministry of Housing & Urban Affairs | 702741 | Jharkhand | 02/2017 | 12/2018 | 03/2023 | 03/2026 | 216.55 | 216.55 | 1057.8 | 72
October 2025 | 288 | Ministry of Housing & Urban Affairs | Waste & Water | SAAP-3 Water Supply Infrastructure SAAP-3 Project | Ministry of Housing & Urban Affairs | 702742 | Jharkhand | 02/2017 | 12/2018 | 10/2023 | 03/2026 | 159.31 | 159.31 | 787.5 | 65
October 2025 | 289 | Ministry of Housing & Urban Affairs | Waste & Water | Augmentation and Strenghthning of Urban Water Supply Phase 1 - SAAP 3 | Ministry of Housing & Urban Affairs | 702746 | Jharkhand | 02/2017 | 12/2018 | 03/2023 | 03/2026 | 278.28 | 278.28 | 1410 | 78
October 2025 | 290 | Ministry of Housing & Urban Affairs | Waste & Water | Belgavi Improvement in Sewerage System Project | Ministry of Housing & Urban Affairs | 702760 | Karnataka | 12/2015 | 10/2016 | 07/2023 | 12/2025 | 162.73 | 162.73 | 721.71 | 80
October 2025 | 291 | Ministry of Housing & Urban Affairs | Waste & Water | 24/7 water supply under AMRUT for Davanagere | Ministry of Housing & Urban Affairs | 702764 | Karnataka | 11/2016 | 01/2018 | 03/2023 | 12/2025 | 174.96 | 174.96 | 923.02 | 65
October 2025 | 292 | Ministry of Housing & Urban Affairs | Waste & Water | Indore Water Supply Infrastructure Project | Ministry of Housing & Urban Affairs | 702793 | Madhya Pradesh | 12/2016 | 11/2017 | 03/2023 | 12/2025 | 287.17 | 287.17 | 2271 | 99
October 2025 | 293 | Ministry of Housing & Urban Affairs | Waste & Water | Jabalpur Sewerage Management and Treatment Infrastructure Project | Ministry of Housing & Urban Affairs | 702798 | Madhya Pradesh | 10/2018 | 12/2017 | 03/2023 | 12/2025 | 362.31 | 362.31 | 2930.96 | 93
October 2025 | 294 | Ministry of Housing & Urban Affairs | Waste & Water | Satna Sewerage Management and Treatment Infrastructure Project | Ministry of Housing & Urban Affairs | 702808 | Madhya Pradesh | 11/2015 | 12/2016 | 03/2024 | 12/2025 | 191.56 | 191.56 | 1469.73 | 86
October 2025 | 295 | Ministry of Housing & Urban Affairs | Waste & Water | Singrauli Sewerage Management and Treatment Infrastructure Project | Ministry of Housing & Urban Affairs | 702810 | Madhya Pradesh | 05/2016 | 11/2017 | 03/2023 | 12/2025 | 402.01 | 402.01 | 3175.93 | 90
October 2025 | 296 | Ministry of Housing & Urban Affairs | Waste & Water | Kalyan-Dombivali Water Supply Infrastructure Project | Ministry of Housing & Urban Affairs | 702833 | Maharashtra | 07/2016 | 09/2019 | 10/2023 | 12/2025 | 194.2 | 194.2 | 1055.02 | 70
October 2025 | 297 | Ministry of Housing & Urban Affairs | Waste & Water | Mira-Bhayandar Water Supply Infrastructure Project | Ministry of Housing & Urban Affairs | 702840 | Maharashtra | 11/2016 | 08/2018 | 03/2023 | 12/2025 | 204.55 | 204.55 | 1765.97 | 99
October 2025 | 298 | Ministry of Housing & Urban Affairs | Waste & Water | Nagpur Water Supply Infrastructure Project | Ministry of Housing & Urban Affairs | 702842 | Maharashtra | 12/2015 | 08/2018 | 03/2023 | 12/2025 | 273.78 | 273.78 | 2409.09 | 99
October 2025 | 299 | Ministry of Housing & Urban Affairs | Waste & Water | Pune Water Supply Infrastructure Project | Ministry of Housing & Urban Affairs | 702851 | Maharashtra | 03/2017 | 07/2017 | 03/2023 | 10/2025 | 235.95 | 235.95 | 1901.3 | 92
October 2025 | 300 | Ministry of Housing & Urban Affairs | Waste & Water | Solapur Sewerage Management Infrastructure Project | Ministry of Housing & Urban Affairs | 702854 | Maharashtra | 03/2017 | 04/2018 | 03/2023 | 12/2025 | 180.24 | 180.24 | 1442.29 | 91
October 2025 | 301 | Ministry of Housing & Urban Affairs | Waste & Water | Jalandhar Water Supply Infrastructure Project | Ministry of Housing & Urban Affairs | 703021 | Punjab | 11/2016 | 08/2020 | 08/2023 | 03/2026 | 258.53 | 258.53 | 1390.73 | 58
October 2025 | 302 | Ministry of Housing & Urban Affairs | Waste & Water | Patiala Water Supply Infrastructure Part-2 Project | Ministry of Housing & Urban Affairs | 703057 | Punjab | 11/2016 | 08/2020 | 10/2023 | 12/2025 | 287 | 287 | 1416.38 | 74
October 2025 | 303 | Ministry of Housing & Urban Affairs | Waste & Water | Jaunpur Sewerage Management Infrastructure Project | Ministry of Housing & Urban Affairs | 702948 | Uttar Pradesh | 03/2017 | 08/2019 | 06/2023 | 12/2025 | 235.73 | 235.73 | 1911.66 | 87
October 2025 | 304 | Ministry of Housing & Urban Affairs | Waste & Water | Jhansi Water Supply Infrastructure Phase-II Project | Ministry of Housing & Urban Affairs | 702949 | Uttar Pradesh | 03/2017 | 06/2019 | 07/2023 | 12/2025 | 561.74 | 561.74 | 4045.35 | 91
October 2025 | 305 | Ministry of Mines | Construction | Construction of Basement + Ground Floor+ 10 Storeyed building for State of the Art Director General, GSI Building at plot No.GN-40, Sector-V, Salt Lake, Kolkata | Central Public Works Department (CPWD | 617280 | West Bengal | 04/2019 | 02/2020 | 08/2026 | - | 255.37 | 255.37 | 85.9 | 42
October 2025 | 306 | Ministry of Mines | Metals & Mining | Rakha Underground Mining Project | Hindustan Copper Limited [HCL] | 611798 | Jharkhand | 12/2022 | 03/2024 | 03/2033 | - | 2705 | 2705 | 0 | 0
October 2025 | 307 | Ministry of Mines | Metals & Mining | Surda Underground Copper Mining Project | Hindustan Copper Limited [HCL] | 611800 | Jharkhand | 02/2022 | 03/2024 | 03/2028 | - | 665.02 | 665.02 | 23.43 | 1
October 2025 | 308 | Ministry of Mines | Metals & Mining | Expansion of Malanjkhand Copper Project | Hindustan Copper Limited [HCL] | 400426 | Madhya Pradesh | 09/2011 | 04/2015 | 04/2020 | 04/2026 | 1856.36 | 1856.36 | 940.27 | 81
October 2025 | 309 | Ministry of Mines | Metals & Mining | Expansion of Alumina Refinery Plant with addition of 5th Stream having capacity enhancement of 1.0 Million Tonee Per Annum | National Aluminium Company Limited [NALCO] | 400141 | Odisha | 04/2017 | 04/2017 | 12/2022 | 09/2025 | 4103 | 5677.4 | 4196.32 | 78
October 2025 | 310 | Ministry of Mines | Metals & Mining | Pottangi Bauxite Mines Project | National Aluminium Company Limited [NALCO] | 400299 | Odisha | 05/2018 | 05/2018 | 03/2025 | 05/2026 | 1381 | 1960.77 | 650.04 | 51
October 2025 | 311 | Ministry of Mines | Metals & Mining | UTKAL D AND E COAL BLOCK | National Aluminium Company Limited [NALCO] | 709829 | Odisha | NA | 02/2016 | 03/2025 | - | 1021.97 | 1021.97 | 0 | 0
October 2025 | 312 | Ministry of Mines | Metals & Mining | CONVERSION OF FLAT BOTTOM SETTLERS AND WASHERS WITH A SINGLE TRAIN OF HRDS AND DCWS IN STREAMS 1 AND | Ministry of Mines | 709830 | Odisha | NA | 04/2017 | 11/2026 | - | 355 | 581 | 0 | 0
October 2025 | 313 | Ministry of Mines | Metals & Mining | SOURCING OF BAUXITE ARRANGEMENT FOR 5TH STREAM ALUMINA REFINERY FROM SOUTH BLOCK MINING LEASE OF PANCHPATMAILI MINES | National Aluminium Company Limited [NALCO] | 709831 | Odisha | 11/2017 | 11/2019 | 05/2025 | 06/2026 | 483 | 483 | 411.79 | 90
October 2025 | 314 | Ministry of Mines | Metals & Mining | 25.5 MW WIND POWER PROJECT AT KAYATHAR IN TAMILNADU | National Aluminium Company Limited [NALCO] | 709832 | Tamil Nadu | 09/2017 | 12/2017 | 03/2025 | 03/2026 | 166 | 166 | 135 | 65
October 2025 | 315 | Department of Higher Education | Education | Construction of Permanent Campus of Central Tribal University of Andhra Pradesh Phase-1 | Central Tribal University of Andhra Pradesh | 613008 | Andhra Pradesh | 09/2019 | 12/2023 | 06/2027 | - | 305 | 305 | 19.96 | 32
October 2025 | 316 | Department of Higher Education | Education | Construction of Permanent Campus of National Institute of Technology Arunachal Pradesh | National Institute of Technology, Arunachal Pradesh | 612898 | Arunachal Pradesh | 09/2009 | 03/2013 | 08/2026 | - | 592.61 | 592.61 | 550.27 | 80
October 2025 | 317 | Department of Higher Education | Education | Tezpur University Projects | Tezpur University | 606112 | Assam | 05/2019 | 06/2021 | 11/2023 | 10/2025 | 153.71 | 153.71 | 124.33 | 97
October 2025 | 318 | Department of Higher Education | Education | Additional Campus of NITPatna | NIT Patna | 606013 | Bihar | 07/2022 | 08/2022 | 07/2024 | 01/2026 | 499.21 | 499.21 | 441.47 | 99
October 2025 | 319 | Department of Higher Education | Education | Phase 1B - Construction of Academic Block, Hostel, Residential Tower, Directors Residence and External Development works at National Institute of Technology, Delhi Campus on Engineering, Procurement and Construction basis | National Institute of Technology Delhi | 612851 | Delhi | 09/2009 | 11/2022 | 09/2025 | - | 333.49 | 336.42 | 291.33 | 97
October 2025 | 320 | Department of Higher Education | Education | Delhi University Eastern Campus at Surajmal Vihar | Delhi University | 616886 | Delhi | 09/2024 | 03/2025 | 10/2026 | - | 373 | 373 | 21.63 | 16
October 2025 | 321 | Department of Higher Education | Education | Construction of permanent campus of Central University of Gujarat at Village kundhela, Dist. Vadodara, Gujarat. | Central University of Gujarat | 612916 | Gujarat | 12/2020 | 02/2021 | 03/2025 | 03/2026 | 490.63 | 490.63 | 313.84 | 80
October 2025 | 322 | Department of Higher Education | Education | Establishment of Permanent campus Phase 1 of IIM Sirmaur | Indian Institute of Management, Sirmaur | 602099 | Himachal Pradesh | 09/2018 | 08/2020 | 10/2023 | 02/2026 | 392.51 | 454.78 | 326.24 | 93
October 2025 | 323 | Department of Higher Education | Education | Hostel blocks & dining hall block | Indian Institute of Technology, Mandi | 612128 | Himachal Pradesh | 03/2023 | 03/2024 | 03/2026 | 03/2026 | 166.66 | 166.66 | 85.92 | 73
October 2025 | 324 | Department of Higher Education | Education | Construction of Permanent Campus of Central University of Himachal Pradesh at Dehra, District - Kangra, [H.P.] on Engineering. Procurement and Construction [EPC Mode 1] Basis. | Central University, Himachal Pradesh | 612894 | Himachal Pradesh | 03/2021 | 08/2022 | 11/2024 | 11/2025 | 251.98 | 300.45 | 183.47 | 80
October 2025 | 325 | Department of Higher Education | Education | Construction of Permanent Campus for IIM Jammu Phase-1 at Jagti, Nagrota, Jammu, J&K | Indian Institute of Management, Jammu | 602098 | Jammu and Kashmir | 03/2019 | 10/2020 | 06/2023 | 11/2025 | 424.93 | 500.91 | 484.52 | 96
October 2025 | 326 | Department of Higher Education | Education | Additional Infrastructure at IISc Bangalore-RCC Monolithic for Men Hostel S14, Women Hostel S11 , Postdoctoral Hostel S12 2 Block , International Hostel S 12 , D&E Block S 12 2 Block FR. | IISC Bangalore | 610940 | Karnataka | 08/2021 | 08/2021 | 03/2024 | 12/2025 | 420.41 | 420.41 | 364.44 | 99
October 2025 | 327 | Department of Higher Education | Education | CONSTRUCTION OF PERMANENT CAMPUS FOR IIT PALAKKAD UNDER PHASE 1A | INDIAN INSTITUTE OF TECHNOLOGY PALAKKAD | 606431 | Kerala | 07/2017 | 03/2020 | 06/2022 | 11/2026 | 1006.45 | 1217.4 | 641.73 | 74
October 2025 | 328 | Department of Higher Education | Education | Phase III A works at IIT Indore [03 Hostels, 01 Studio Apartment, 01 Housing, Heavy & Sophisticated lab complex, Academic POD and Infrastructure for center of excellence] | Indian Institute of Technology, Indore | 611957 | Madhya Pradesh | 12/2023 | 04/2024 | 02/2027 | - | 496.28 | 496.28 | 38.62 | 37
October 2025 | 329 | Department of Higher Education | Education | Hostel 4 -Earlier Known as Hostel 20 | Indian Institute of Technology, Bombay | 612135 | Maharashtra | 09/2022 | 12/2023 | 09/2025 | 12/2025 | 182.33 | 182.33 | 156.51 | 98
October 2025 | 330 | Department of Higher Education | Education | Academic Block 1 & 2 | Indian Institute of Technology, Bombay | 612203 | Maharashtra | 09/2022 | 05/2023 | 07/2026 | 03/2027 | 68 | 263.93 | 27.4 | 20
October 2025 | 331 | Department of Higher Education | Education | Construction and Developement of National Institute of Technology Meghalaya Permanent Campus at Sohra | National Institute of Technology, Meghalaya | 612885 | Meghalaya | 09/2009 | 09/2014 | 03/2022 | 07/2025 | 494.52 | 494.52 | 419.57 | 89
October 2025 | 332 | Department of Higher Education | Education | Construction of Permanent Campus for NIT Mizoram at Lengpui, Aizawl | NIT Mizoram | 612876 | Mizoram | 09/2009 | 06/2014 | 12/2029 | 12/2029 | 474.23 | 474.23 | 167.55 | 4
October 2025 | 333 | Department of Higher Education | Education | Establishment of NIT Nagaland | NIT Nagaland | 613013 | Nagaland | 09/2009 | 12/2014 | 12/2025 | - | 275.63 | 275.63 | 261.24 | 97
October 2025 | 334 | Department of Higher Education | Education | IISER BERHAMPUR | Indian Institutes of Science Education and Research, Behrampur | 610315 | Odisha | 10/2018 | 09/2019 | 03/2021 | 12/2025 | 1229.32 | 773.76 | 838.21 | 97
October 2025 | 335 | Department of Higher Education | Education | Establishment of NIT Puducherry Permanent Campus [Phase-I and Phase-II] | National Institute of Technology, Puducherry | 612877 | Puducherry | 09/2009 | 07/2013 | 12/2024 | 08/2025 | 618.34 | 544.34 | 529.9 | 96
October 2025 | 336 | Department of Higher Education | Education | Construction of Permanent Campus of Indian Institute of Management [IIM] Amritsar, Punjab, Phase-I | Indian intitue of Management, Amritsar | 605292 | Punjab | 10/2019 | 07/2020 | 06/2023 | 12/2025 | 348.31 | 348.31 | 290.39 | 91
October 2025 | 337 | Department of Higher Education | Education | Construction of Girls Hostel 400 seater, Boys Hostel 600 seater, Academic Block, International Hostel 100 seater, VC Residence and Purchase of Equipment | Central University of Punjab | 617221 | Punjab | 08/2024 | 04/2025 | 10/2027 | - | 210.99 | 210.99 | 0 | 0
October 2025 | 338 | Department of Higher Education | Education | Construction of Sikkim University Campus Phase-I Package-II at Yangang, South Sikkim | Sikkim University | 609736 | Sikkim | 08/2020 | 01/2022 | 01/2025 | 03/2026 | 314.06 | 314.06 | 238.22 | 85
October 2025 | 339 | Department of Higher Education | Education | Establishment of Permanent Campus of NIT SIkkim at Khamdong-Gangtok District | NIT Sikkim | 612883 | Sikkim | 02/2024 | 03/2024 | 02/2028 | 12/2026 | 685.76 | 610.76 | 121.56 | 14
October 2025 | 340 | Department of Higher Education | Education | Construction of Precast housing and hostels at IIT Hyderabad | Indian Institute of Technology, Hyderabad | 609996 | Telangana | 09/2022 | 11/2022 | 10/2024 | 01/2026 | 262 | 262 | 186.49 | 79
October 2025 | 341 | Department of Higher Education | Education | Banaras Hindu University [ Kayakalp of Institute of Medical Sciences] | Banaras Hindu University | 606479 | Uttar Pradesh | 06/2020 | 06/2020 | 09/2022 | 03/2026 | 246 | 246 | 198.02 | 96
October 2025 | 342 | Department of Higher Education | Education | Construction & Development of Infrastructural Facilities in the main campus of NIT Uttarakhand at Sumari, Pauri Garhwal | National Institute of Technology Uttarakhand | 611963 | Uttarakhand | 06/2020 | 04/2024 | 09/2027 | - | 650.85 | 650.85 | 195.52 | 33
October 2025 | 343 | Department of Higher Education | Education | HEFA projects on development of student hostels, playgrounds, departmental buildings, class room complex and other campus facilities in IIT Kharagpur | Indian Institute of Technology, Kharagpur | 609019 | West Bengal | 06/2018 | 04/2019 | 03/2023 | 03/2026 | 500 | 442 | 390.6 | 89
October 2025 | 344 | Department of Sports | Education | National Sports University [NSU], Imphal [Manipur] | Department of Sports & Youth Affairs | 400081 | Manipur | NA | 01/2022 | 08/2024 | 11/2025 | 906.47 | 611.74 | 553.38 | 94
October 2025 | 345 | Ministry of Petroleum & Natural Gas | Energy Storage | Construction of Aviation Fuel farm Facilities at Bhogapuram Airport | Ministry of Petroleum & Natural Gas | 616235 | Andhra Pradesh | 08/2024 | 08/2024 | 03/2026 | 03/2026 | 240 | 240 | 61.94 | 77
October 2025 | 346 | Ministry of Petroleum & Natural Gas | Energy Storage | Construction of LPG Facilities at Kamardanga, Assam | Hindustan Petroleum Corporation Limited | 709754 | Assam | 03/2023 | 03/2023 | 07/2027 | 07/2027 | 156.36 | 156.36 | 63.31 | 50
October 2025 | 347 | Ministry of Petroleum & Natural Gas | Energy Storage | Setting up of new rail fed POL facility at Kamardanga, Assam | Hindustan Petroleum Corporation Limited [HPCL] | 709755 | Assam | 03/2023 | 03/2023 | 07/2027 | 07/2027 | 384.04 | 384.04 | 142.28 | 57
October 2025 | 348 | Ministry of Petroleum & Natural Gas | Energy Storage | Setting up a common user Petroleum Terminal at Jammu, J&K for resitement of existing PSU OMC's Depots from Jammu City | Bharat Petroleum Corporation Limited [BPCL] | 400235 | Jammu and Kashmir | 04/2023 | 04/2023 | 03/2025 | 01/2026 | 676.89 | 715.89 | 550.45 | 84
October 2025 | 349 | Ministry of Petroleum & Natural Gas | Energy Storage | Andheri Residential Towers, Mumbai | Ministry of Petroleum & Natural Gas | 604833 | Maharashtra | 06/2017 | 06/2017 | 05/2025 | 06/2026 | 281.35 | 389.67 | 238.39 | 51
October 2025 | 350 | Ministry of Petroleum & Natural Gas | Energy Storage | Srikakulam Angul Gas Pipeline Project | Ministry of Petroleum & Natural Gas | 701343 | Multi-States (Andhra Pradesh, Odisha) | 09/2019 | 09/2019 | 07/2022 | 12/2025 | 2658.34 | 2810 | 2282.98 | 96
October 2025 | 351 | Ministry of Petroleum & Natural Gas | Energy Storage | Rajasthan Refinery Project | MinistryofPetroleumNaturalGas | 701263 | Multi-States (Arunachal Pradesh, Gujarat, Rajasthan) | 10/2017 | 10/2017 | 10/2022 | 03/2026 | 43129 | 79459 | 61926.61 | 89
October 2025 | 352 | Ministry of Petroleum & Natural Gas | Energy Storage | Paradip-Numaligarh Crude Oil Pipeline [PNCPL] & Crude Oil Import Terminal [COIT] at Paradip | Ministry of Petroleum & Natural Gas | 701349 | Multi-States (Assam, Bihar, Jharkhand, Odisha, West Bengal) | 01/2019 | 01/2019 | 07/2024 | 03/2026 | 10228 | 11407 | 9921.29 | 88
October 2025 | 353 | Ministry of Petroleum & Natural Gas | Energy Storage | New Mundra Panipat Crude Oil Pipeline | Ministry of Petroleum & Natural Gas | 400078 | Multi-States (Gujarat, Haryana, Rajasthan) | 12/2021 | 12/2021 | 12/2024 | 12/2025 | 9028 | 9028 | 7292.34 | 86
October 2025 | 354 | Ministry of Petroleum & Natural Gas | Energy Storage | Kandla Gorakhpur LPG Pipeline | Ministry of Petroleum & Natural Gas | 400012 | Multi-States (Gujarat, Madhya Pradesh, Uttar Pradesh) | 12/2018 | 12/2018 | 12/2021 | 12/2025 | 10088 | 10088 | 8059.53 | 93
October 2025 | 355 | Ministry of Petroleum & Natural Gas | Energy Storage | Multi Product Pipeline from Irugur to Devangonthi | Department of Water Resources, River Development & GR | 400301 | Multi-States (Karnataka, Tamil Nadu) | 11/2012 | 11/2012 | 02/2017 | 09/2026 | 678 | 1732 | 800.88 | 73
October 2025 | 356 | Ministry of Petroleum & Natural Gas | Energy Storage | Petrochemical evacuation marketing terminal at Barmer, Rajasthan | Hindustan Petroleum Corporation Limited [HPCL] | 709759 | Rajasthan | 12/2023 | 12/2023 | 12/2026 | 12/2026 | 461.05 | 461.05 | 145.12 | 64
October 2025 | 357 | Ministry of Petroleum & Natural Gas | Energy Storage | Laying of POL Pipelines in Common Corridor for proposed grass root terminal at Vallur [Chennai] | Ministry of Petroleum & Natural Gas | 400043 | Tamil Nadu | 01/2022 | 01/2022 | 05/2026 | 05/2026 | 829 | 829 | 327.86 | 67
October 2025 | 358 | Ministry of Petroleum & Natural Gas | Energy Storage | Grass root POL Terminal at Vallur, Chennai | Indian Oil Corporation Limited [IOCL] | 400077 | Tamil Nadu | 01/2022 | 01/2022 | 12/2024 | 03/2026 | 827 | 887.71 | 638.71 | 89
October 2025 | 359 | Ministry of Petroleum & Natural Gas | Energy Storage | Grass Root Rail-fed Depot at Sekerkote, Agartala as resitement of existing Dharmanagar Depot | Indian Oil Corporation Limited [IOCL] | 400035 | Tripura | 06/2022 | 06/2022 | 09/2025 | 06/2026 | 656 | 656 | 509.92 | 89
October 2025 | 360 | Ministry of Petroleum & Natural Gas | Energy Storage | Grass-root Terminal at Mirzapur, Uttar Pradesh | Ministry of Petroleum & Natural Gas | 604852 | Uttar Pradesh | 09/2022 | 09/2022 | 11/2026 | 11/2026 | 980.45 | 980.45 | 227.04 | 57
October 2025 | 361 | Ministry of Petroleum & Natural Gas | Oil & Gas | KG-DWN-98/2 Cluster - II Development Project - NELP Block | Oil and Natural Gas Corporation Limited [ONGC] | 400120 | Andhra Pradesh | 03/2016 | 03/2016 | 06/2020 | 06/2026 | 34012 | 34012 | 32184.03 | 96
October 2025 | 362 | Ministry of Petroleum & Natural Gas | Oil & Gas | HP-COAT [Crude to Olefins and Aromatics Technology] demo unit at Visakh Refinery | Hindustan Petroleum Corporation Limited | 709752 | Andhra Pradesh | 09/2021 | 09/2021 | 06/2024 | 03/2026 | 160 | 220 | 92.6 | 76
October 2025 | 363 | Ministry of Petroleum & Natural Gas | Oil & Gas | City Gas Distribution Project at Kurnool, Guntur & Prakasam Districts | MinistryofPetroleumNaturalGas | 709766 | Andhra Pradesh | 03/2022 | 03/2022 | 03/2030 | 03/2030 | 1420 | 1420 | 167.02 | 6
October 2025 | 364 | Ministry of Petroleum & Natural Gas | Oil & Gas | Numaligarh Refinery Expansion Project | Ministry of Petroleum & Natural Gas | 604791 | Assam | 07/2020 | 07/2020 | 07/2024 | 12/2025 | 12366 | 22494 | 17659.09 | 78
October 2025 | 365 | Ministry of Petroleum & Natural Gas | Oil & Gas | Development of Surface Facilities for production and evacuation of Crude Oil and Natural Gas from Nadua and East Khagorija | Ministry of Petroleum & Natural Gas | 604863 | Assam | 01/2018 | 01/2018 | 02/2020 | 12/2025 | 682.9 | 726.93 | 491.64 | 94
October 2025 | 366 | Ministry of Petroleum & Natural Gas | Oil & Gas | Guwahati Refinery Expansion [1.0 to 1.2 MMTPA] along with installation of CRU, Guwahati Refinery | Ministry of Petroleum & Natural Gas | 607701 | Assam | 05/2021 | 05/2021 | 10/2023 | 05/2026 | 412.3 | 577 | 445.73 | 87
October 2025 | 367 | Ministry of Petroleum & Natural Gas | Oil & Gas | Construction of Field Gas Gathering Station at Baghjan area for collection, processing & transportation of natural Gas to be produced from Baghjan Field | Ministry of Petroleum & Natural Gas | 616858 | Assam | 12/2020 | 12/2020 | 03/2024 | 12/2025 | 430.76 | 430.76 | 330.99 | 87
October 2025 | 368 | Ministry of Petroleum & Natural Gas | Oil & Gas | Augmentation/Revamping of Facilities at existing Guwahati Terminal at Betkuchi | MinistryofPetroleumNaturalGas | 709776 | Assam | 04/2022 | 04/2022 | 09/2026 | 09/2026 | 277 | 323.09 | 188.04 | 68
October 2025 | 369 | Ministry of Petroleum & Natural Gas | Oil & Gas | Capacity Expansion of Digboi Refinery from 0.65 to 1.0 MMTPA | MinistryofPetroleumNaturalGas | 709779 | Assam | 06/2022 | 06/2022 | 03/2026 | 07/2027 | 768 | 740 | 123.97 | 44
October 2025 | 370 | Ministry of Petroleum & Natural Gas | Oil & Gas | Pipeline Network Project Rudrasagar | Ministry of Petroleum & Natural Gas | 709847 | Assam | 01/2023 | 01/2023 | 04/2026 | 04/2026 | 344.99 | 344.99 | 215.98 | 48
October 2025 | 371 | Ministry of Petroleum & Natural Gas | Oil & Gas | Borholla GGS Life Extension Project [BLEP] | Ministry of Petroleum & Natural Gas | 709850 | Assam | 09/2023 | 09/2023 | 05/2026 | 05/2026 | 198.7 | 198.7 | 50.26 | 40
October 2025 | 372 | Ministry of Petroleum & Natural Gas | Oil & Gas | DCU Revamp Project | NRL | 709864 | Assam | 08/2021 | 08/2021 | 07/2024 | 06/2026 | 370 | 370 | 266.35 | 64
October 2025 | 373 | Ministry of Petroleum & Natural Gas | Oil & Gas | Power Recovery Turbine [PRT] in PFCCU unit as an Energy Conservation Scheme | NRL | 709865 | Assam | 04/2023 | 04/2023 | 12/2024 | 12/2025 | 293.5 | 293.5 | 97.22 | 96
October 2025 | 374 | Ministry of Petroleum & Natural Gas | Oil & Gas | Setting up of LPG Plant with Rail Unloading Facility at Hathua, Dist. Gopalganj, Bihar | MinistryofPetroleumNaturalGas | 617304 | Bihar | 10/2023 | 10/2023 | 03/2027 | 03/2027 | 340.15 | 340.15 | 107.35 | 29
October 2025 | 375 | Ministry of Petroleum & Natural Gas | Oil & Gas | Barauni Refinery Capacity Expansion from 6.0 to 9.0 MMTPA | Ministry of Petroleum & Natural Gas | 701324 | Bihar | 01/2020 | 01/2020 | 04/2023 | 08/2026 | 14810 | 16724 | 12138.96 | 88
October 2025 | 376 | Ministry of Petroleum & Natural Gas | Oil & Gas | Installation of Bitumen Manufacturing Unit along with allied facilities at Barauni Refinery | MinistryofPetroleumNaturalGas | 709777 | Bihar | 01/2022 | 01/2022 | 04/2025 | 10/2026 | 389.35 | 340 | 73.97 | 47
October 2025 | 377 | Ministry of Petroleum & Natural Gas | Oil & Gas | City Gas Distribution Projects at Darbhanga, Madhubani, Supaul, Sitamarhi and Sheohar districts | Bharat Petroleum Corporation Limited [BPCL] | 709792 | Bihar | 12/2022 | 12/2022 | 03/2030 | 03/2030 | 3638 | 3638 | 422.37 | 29
October 2025 | 378 | Ministry of Petroleum & Natural Gas | Oil & Gas | City Gas Distribution Projects at Gopalganj, Siwan, West Champaran, East Champaran and Deoria districts | Bharat Petroleum Corporation Limited [BPCL] | 709793 | Bihar | 12/2022 | 12/2022 | 06/2030 | 06/2030 | 3919 | 3919 | 421.98 | 20
October 2025 | 379 | Ministry of Petroleum & Natural Gas | Oil & Gas | Redevelopment of Sobhasan Complex | Oil and Natural Gas Corporation Limited [ONGC] | 400087 | Gujarat | 08/2021 | 08/2021 | 02/2026 | 02/2026 | 885.63 | 1286.67 | 876.53 | 79
October 2025 | 380 | Ministry of Petroleum & Natural Gas | Oil & Gas | Redevelopment of Santhal Field [Onshore-Mehsana Asset] | Oil and Natural Gas Corporation Limited [ONGC] | 400167 | Gujarat | 02/2017 | 02/2017 | 03/2026 | 03/2026 | 1162.56 | 1162.56 | 1139.5 | 94
October 2025 | 381 | Ministry of Petroleum & Natural Gas | Oil & Gas | Redevelopment of Linch Field | Oil and Natural Gas Corporation Limited [ONGC] | 400169 | Gujarat | 04/2021 | 04/2021 | 03/2025 | 03/2026 | 631.03 | 860.04 | 572.74 | 85
October 2025 | 382 | Ministry of Petroleum & Natural Gas | Oil & Gas | Petrochemical and Lube Integration Project at Gujarat Refinery | Ministry of Petroleum & Natural Gas | 701329 | Gujarat | 09/2020 | 09/2020 | 08/2024 | 06/2026 | 18936 | 17825 | 12779.56 | 84
October 2025 | 383 | Ministry of Petroleum & Natural Gas | Oil & Gas | Installation of new Biturox Unit along with allied facilities at Gujarat Refinery | MinistryofPetroleumNaturalGas | 709778 | Gujarat | 01/2022 | 01/2022 | 08/2025 | 09/2026 | 328.29 | 287 | 172.32 | 65
October 2025 | 384 | Ministry of Petroleum & Natural Gas | Oil & Gas | Commercial Polymer Flooding Project in Bechraji field | Oil and Natural Gas Corporation Limited [ONGC] | 709838 | Gujarat | 01/2022 | 01/2022 | 11/2024 | 05/2027 | 621.4 | 739.02 | 137.73 | 24
October 2025 | 385 | Ministry of Petroleum & Natural Gas | Oil & Gas | Restoration of Gas Terminal, Phase-I [Part-A], Hazira | Oil and Natural Gas Corporation Limited [ONGC] | 709840 | Gujarat | 05/2022 | 05/2022 | 02/2025 | 12/2025 | 249.43 | 249.43 | 210.42 | 95
October 2025 | 386 | Ministry of Petroleum & Natural Gas | Oil & Gas | Old Pipe Line Replacement [OPRP] Group-A | Oil and Natural Gas Corporation Limited [ONGC] | 709841 | Gujarat | 07/2021 | 07/2021 | 07/2025 | 03/2026 | 173.03 | 169.84 | 152.39 | 89
October 2025 | 387 | Ministry of Petroleum & Natural Gas | Oil & Gas | Kalol Redevelopment Project, Ahmedabad Asset | Oil and Natural Gas Corporation Limited [ONGC] | 709842 | Gujarat | 08/2022 | 08/2022 | 03/2027 | 03/2027 | 1487.41 | 1487.41 | 937.5 | 62
October 2025 | 388 | Ministry of Petroleum & Natural Gas | Oil & Gas | Revamping of SV Stations, Gas Terminal & Kribhco Terminal | Oil and Natural Gas Corporation Limited [ONGC] | 709845 | Gujarat | 11/2022 | 11/2022 | 08/2026 | 08/2026 | 837.34 | 837.34 | 288.4 | 56
October 2025 | 389 | Ministry of Petroleum & Natural Gas | Oil & Gas | Indian Oil Technology Development and Deployment Centre at R&D Campus-II, Faridabad | Ministry of Petroleum & Natural Gas | 604853 | Haryana | 06/2019 | 06/2019 | 12/2022 | 10/2026 | 2281.94 | 3200 | 1841.09 | 64
October 2025 | 390 | Ministry of Petroleum & Natural Gas | Oil & Gas | Poly Butadiene Rubber plant at Panipat | Indian Oil Corporation Limited [IOCL] | 611917 | Haryana | 03/2022 | 03/2022 | 03/2025 | 06/2026 | 1459 | 2531.44 | 1381.16 | 74
October 2025 | 391 | Ministry of Petroleum & Natural Gas | Oil & Gas | Capacity Expansion of Panipat Refinery from 15 to 25 MMTPA | Ministry of Petroleum & Natural Gas | 701289 | Haryana | 02/2021 | 02/2021 | 09/2024 | 06/2026 | 34627 | 36225 | 26555.13 | 90
October 2025 | 392 | Ministry of Petroleum & Natural Gas | Oil & Gas | Installation of Multiple Effect Evaporator [MEE] for ETP-1, 2 & 4 of Panipat Refinery and Petrochemical Complex. | MinistryofPetroleumNaturalGas | 709783 | Haryana | 12/2020 | 12/2020 | 06/2023 | 06/2026 | 165.13 | 247.69 | 138.41 | 76
October 2025 | 393 | Ministry of Petroleum & Natural Gas | Oil & Gas | City Gas Distribution Project at Jammu, Udhampur, Reasi, Samba and Kathua Districts | MinistryofPetroleumNaturalGas | 709773 | Jammu and Kashmir | 03/2022 | 03/2022 | 03/2032 | 03/2032 | 538 | 538 | 4.1 | 0
October 2025 | 394 | Ministry of Petroleum & Natural Gas | Oil & Gas | Development of Jharia CBM Block [Phase-1] | Oil and Natural Gas Corporation Limited [ONGC] | 610984 | Jharkhand | 11/2019 | 11/2019 | 01/2024 | 01/2026 | 431 | 431 | 223.39 | 60
October 2025 | 395 | Ministry of Petroleum & Natural Gas | Oil & Gas | Laying of Natural Gas Pipeline from Hazaribagh to Ranchi [HRPL] | MinistryofPetroleumNaturalGas | 709785 | Jharkhand | 02/2023 | 02/2023 | 02/2026 | 02/2026 | 202.07 | 202.07 | 60.23 | 48
October 2025 | 396 | Ministry of Petroleum & Natural Gas | Oil & Gas | Power System Upgradation Project | Mangalore Refinary and Petrochemicals Limited | 612790 | Karnataka | 10/2023 | 10/2023 | 11/2025 | 05/2026 | 385 | 385 | 155.14 | 69
October 2025 | 397 | Ministry of Petroleum & Natural Gas | Oil & Gas | Demo Bio-ATF Project | Ministry of Petroleum & Natural Gas | 616879 | Karnataka | 03/2024 | 03/2024 | 01/2027 | 01/2027 | 364 | 364 | 32.59 | 19
October 2025 | 398 | Ministry of Petroleum & Natural Gas | Oil & Gas | Revamping/ Augmentation of facilities at existing port terminal at Mangalore | Ministry of Petroleum & Natural Gas | 709774 | Karnataka | 01/2022 | 01/2022 | 12/2025 | 12/2025 | 463 | 500.62 | 285.36 | 74
October 2025 | 399 | Ministry of Petroleum & Natural Gas | Oil & Gas | Replacement and Extension of Jetty Pipelines [REJP] at KR | Bharat Petroleum Corporation Limited [BPCL] | 709790 | Kerala | 03/2023 | 03/2023 | 03/2026 | 03/2026 | 621.87 | 621.87 | 203.68 | 88
October 2025 | 400 | Ministry of Petroleum & Natural Gas | Oil & Gas | Setting up Polypropylene Unit at Kochi Refinery | MinistryofPetroleumNaturalGas | 709799 | Kerala | 12/2023 | 12/2023 | 10/2027 | 10/2027 | 4460 | 4460 | 308.59 | 17
October 2025 | 401 | Ministry of Petroleum & Natural Gas | Oil & Gas | Ethylene Cracker Project at Bina Refinery including downstream Petrochemical Plants and expansion of Refinery | MinistryofPetroleumNaturalGas | 709798 | Madhya Pradesh | 05/2023 | 05/2023 | 05/2028 | 05/2028 | 43367 | 43367 | 1955 | 16
October 2025 | 402 | Ministry of Petroleum & Natural Gas | Oil & Gas | Debottlenecking and Augmentation of Cryogenic facilities at Uran LPG Import Terminal | Department of Water Resources, River Development & GR | 400158 | Maharashtra | 04/2021 | 04/2021 | 02/2024 | 12/2025 | 1164.69 | 1629.86 | 958.12 | 89
October 2025 | 403 | Ministry of Petroleum & Natural Gas | Oil & Gas | 500 KTA PDHPP Project, Usar | Ministry of Petroleum & Natural Gas | 400168 | Maharashtra | 04/2021 | 04/2021 | 04/2025 | 12/2025 | 8797 | 11256 | 7122.88 | 86
October 2025 | 404 | Ministry of Petroleum & Natural Gas | Oil & Gas | Construction of lube oil blending plant at Rasayani | Ministry of Petroleum & Natural Gas | 610985 | Maharashtra | 05/2022 | 05/2022 | 12/2023 | 12/2025 | 423.39 | 526.26 | 313 | 82
October 2025 | 405 | Ministry of Petroleum & Natural Gas | Oil & Gas | Lube Modernization & Bottom Upgradation Project at Mumbai Refinery | Ministry of Petroleum and Natural Gas | 616933 | Maharashtra | 12/2024 | 12/2024 | 03/2028 | 03/2028 | 4679 | 4679 | 211.77 | 5
October 2025 | 406 | Ministry of Petroleum & Natural Gas | Oil & Gas | HP TDAE Unit in Mumbai Refinery | Hindustan Petroleum Corporation Limited | 709760 | Maharashtra | 06/2024 | 06/2024 | 04/2026 | 04/2026 | 240 | 240 | 44.87 | 54
October 2025 | 407 | Ministry of Petroleum & Natural Gas | Oil & Gas | City Gas Distribution Project at Beed, Jalgaon and Jalna Districts | MinistryofPetroleumNaturalGas | 709771 | Maharashtra | 03/2022 | 03/2022 | 09/2031 | 09/2031 | 865 | 865 | 71.43 | 3
October 2025 | 408 | Ministry of Petroleum & Natural Gas | Oil & Gas | Construction of Additional Tankages and Allied Facilities at JNPT Terminal | MinistryofPetroleumNaturalGas | 709780 | Maharashtra | 04/2022 | 04/2022 | 08/2026 | 08/2026 | 341.43 | 436.14 | 289.06 | 52
October 2025 | 409 | Ministry of Petroleum & Natural Gas | Oil & Gas | ATF Pipeline from Jawaharlal Nehru Port Trust to Navi Mumbai International Airport | Indian Oil Corporation Limited [IOCL] | 709782 | Maharashtra | 08/2022 | 08/2022 | 08/2025 | 03/2026 | 165 | 165 | 94.21 | 78
October 2025 | 410 | Ministry of Petroleum & Natural Gas | Oil & Gas | Installation of Independent De- Aromatized Solvents [DAS] production facilities at MR | Bharat Petroleum Corporation Limited [BPCL] | 709789 | Maharashtra | 03/2023 | 03/2023 | 07/2025 | 12/2025 | 405 | 343 | 214.5 | 92
October 2025 | 411 | Ministry of Petroleum & Natural Gas | Oil & Gas | POL & LOBS Installations with Receipt Pipelines at Rasayani | Bharat Petroleum Corporation Limited [BPCL] | 709797 | Maharashtra | 05/2023 | 05/2023 | 05/2026 | 05/2026 | 2585 | 2585 | 711.91 | 65
October 2025 | 412 | Ministry of Petroleum & Natural Gas | Oil & Gas | Part Replacement Pipeline Project [PRPP] | Oil and Natural Gas Corporation Limited [ONGC] | 709846 | Maharashtra | 11/2022 | 11/2022 | 05/2024 | 12/2025 | 1219.48 | 1145.1 | 745 | 90
October 2025 | 413 | Ministry of Petroleum & Natural Gas | Oil & Gas | Visakh Raipur Pipeline Project | Ministry of Petroleum and Natural Gas | 616254 | Multi-States (Andhra Pradesh, Chhattisgarh, Odisha) | 09/2024 | 09/2024 | 09/2027 | 09/2027 | 2212 | 2212 | 21.1 | 11
October 2025 | 414 | Ministry of Petroleum & Natural Gas | Oil & Gas | North East Gas Grid | Ministry of Petroleum & Natural Gas | 701346 | Multi-States (Arunachal Pradesh, Assam, Manipur, Meghalaya, Mizoram, Nagaland, Sikkim, Tripura, West Bengal) | 04/2020 | 04/2020 | 03/2024 | 03/2026 | 9265 | 9265 | 6603.95 | 86
October 2025 | 415 | Ministry of Petroleum & Natural Gas | Oil & Gas | Upgradation of Facilities of Numaligarh-Siliguri Product Pipeline [NSPL] for transportation of additional products from existing 1.72 MMTPA to 5.5 MMTPA | Ministry of Petroleum & Natural Gas | 701350 | Multi-States (Assam, West Bengal) | 06/2021 | 06/2021 | 12/2024 | 12/2025 | 860 | 860 | 615.47 | 99
October 2025 | 416 | Ministry of Petroleum & Natural Gas | Oil & Gas | CGD Project in Banka, Dumka, Godda, Jamtara, Pakur, Sahibganj GA ID 11A.02 | Hindustan Petroleum Corporation Limited | 709757 | Multi-States (Bihar, Jharkhand) | 06/2022 | 06/2022 | 06/2030 | 06/2030 | 1377 | 1377 | 345.02 | 29
October 2025 | 417 | Ministry of Petroleum & Natural Gas | Oil & Gas | Mumbai Nagpur Jharsuguda Pipeline Project | Ministry of Petroleum & Natural Gas | 701354 | Multi-States (Chhattisgarh, Madhya Pradesh, Maharashtra, Odisha) | 06/2020 | 06/2020 | 05/2023 | 12/2025 | 7844.25 | 8255 | 6661.2 | 96
October 2025 | 418 | Ministry of Petroleum & Natural Gas | Oil & Gas | Mehsana-Bhatinda & Bhatinda-Jammu Natural Gas Pipeline | Ministry of Petroleum & Natural Gas | 701330 | Multi-States (Gujarat, Haryana, Punjab, Rajasthan) | 07/2011 | 07/2011 | 06/2024 | 12/2025 | 7392 | 7392 | 6308 | 90
October 2025 | 419 | Ministry of Petroleum & Natural Gas | Oil & Gas | Gurdaspur Jammu Pipeline | Gas Authority of India Limited [GAIL] | 612853 | Multi-States (Jammu and Kashmir, Punjab) | 07/2023 | 07/2023 | 07/2026 | 07/2026 | 521.9 | 521.9 | 230.2 | 40
October 2025 | 420 | Ministry of Petroleum & Natural Gas | Oil & Gas | Kochi - Koottanad - Bangalore - Mangalore Pipeline Phase-II | Ministry of Petroleum & Natural Gas | 701228 | Multi-States (Karnataka, Kerala, Tamil Nadu) | 06/2009 | 06/2009 | 12/2012 | 12/2025 | 2915 | 5909 | 4506.79 | 95
October 2025 | 421 | Ministry of Petroleum & Natural Gas | Oil & Gas | City Gas Distribution Maharashtra Natural Gas Limited | Ministry of Petroleum & Natural Gas | 701338 | Multi-States (Karnataka, Maharashtra) | 01/2006 | 01/2006 | 06/2031 | 06/2031 | 5535 | 5535 | 3986.49 | 0
October 2025 | 422 | Ministry of Petroleum & Natural Gas | Oil & Gas | Dhamra Haldia Pipeline Project | Ministry of Petroleum & Natural Gas | 701344 | Multi-States (Odisha, West Bengal) | 03/2020 | 03/2020 | 11/2022 | 12/2025 | 1030.65 | 1125 | 879.8 | 88
October 2025 | 423 | Ministry of Petroleum & Natural Gas | Oil & Gas | City Gas Distribution Projects at Fazilka [except area already authorized], Ganganagar and Hanumangarh districts | Bharat Petroleum Corporation Limited [BPCL] | 709794 | Multi-States (Punjab, Rajasthan) | 12/2022 | 12/2022 | 06/2030 | 06/2030 | 3207 | 3207 | 348.41 | 25
October 2025 | 424 | Ministry of Petroleum & Natural Gas | Oil & Gas | Augmentation/ Revamping of Dimapur Depot, Dimapur | MinistryofPetroleumNaturalGas | 709786 | Nagaland | 08/2023 | 08/2023 | 11/2027 | 11/2027 | 227.62 | 227.62 | 10.8 | 25
October 2025 | 425 | Ministry of Petroleum & Natural Gas | Oil & Gas | Integrated Para Xylene [PX] and Purified Terephthalic Acid [PTA] Project at Paradip Refinery | Ministry of Petroleum & Natural Gas | 604859 | Odisha | 07/2020 | 07/2020 | 01/2024 | 08/2026 | 13805 | 11783 | 8422.69 | 91
October 2025 | 426 | Ministry of Petroleum & Natural Gas | Oil & Gas | CUF POL Depot at Sadashibpur [Meramundali], Odisha | MinistryofPetroleumNaturalGas | 709800 | Odisha | 04/2021 | 04/2021 | 03/2026 | 03/2026 | 393.54 | 393.54 | 110.87 | 48
October 2025 | 427 | Ministry of Petroleum & Natural Gas | Oil & Gas | Life Extension of 48 well platforms of Mumbai High & Heera Fields | Oil and Natural Gas Corporation Limited [ONGC] | 400119 | Offshore | 12/2015 | 12/2015 | 04/2018 | 12/2025 | 3190.69 | 3375.9 | 3119.29 | 89
October 2025 | 428 | Ministry of Petroleum & Natural Gas | Oil & Gas | PRP-VIII [Group-A] | Ministry of Petroleum & Natural Gas | 616950 | Offshore | 09/2024 | 09/2024 | 02/2026 | 02/2026 | 1486.4 | 1486.4 | 272.3 | 23
October 2025 | 429 | Ministry of Petroleum & Natural Gas | Oil & Gas | Daman Upside Development Project | Oil and Natural Gas Corporation Limited [ONGC] | 709839 | Offshore | 06/2022 | 06/2022 | 10/2025 | 02/2026 | 4144.41 | 6406.9 | 4563.85 | 88
October 2025 | 430 | Ministry of Petroleum & Natural Gas | Oil & Gas | MHN TCPP PGC BGC Project [MTPBP] | Ministry of Petroleum & Natural Gas | 709848 | Offshore | 06/2022 | 06/2022 | 05/2026 | 05/2026 | 2329.45 | 2354.23 | 1148.9 | 59
October 2025 | 431 | Ministry of Petroleum & Natural Gas | Oil & Gas | PRP-VIII Group B [NH & BS Asset] | Ministry of Petroleum & Natural Gas | 709849 | Offshore | 06/2024 | 06/2024 | 02/2026 | 02/2026 | 2379.84 | 3165.53 | 1806.88 | 64
October 2025 | 432 | Ministry of Petroleum & Natural Gas | Oil & Gas | Integrated Development of 4 Contract Areas under DSF-II | Ministry of Petroleum & Natural Gas | 709851 | Offshore | 05/2023 | 05/2023 | 04/2027 | 04/2027 | 6183.79 | 6183.79 | 594.28 | 23
October 2025 | 433 | Ministry of Petroleum & Natural Gas | Oil & Gas | 2G Ethanol Biorefinery at Bathinda | Hindustan Petroleum Corporation Limited [HPCL] | 400171 | Punjab | 05/2020 | 05/2020 | 02/2023 | 03/2026 | 1421.46 | 1421.46 | 1201.66 | 95
October 2025 | 434 | Ministry of Petroleum & Natural Gas | Oil & Gas | City Gas Distribution Project at Pathankot District | MinistryofPetroleumNaturalGas | 709770 | Punjab | 03/2022 | 03/2022 | 09/2033 | 09/2033 | 151 | 151 | 8.75 | 2
October 2025 | 435 | Ministry of Petroleum & Natural Gas | Oil & Gas | CBR 9 MMTPA Project | Chennai Petroleum Corporation Limited [CPCL] | 604795 | Tamil Nadu | 09/2021 | 09/2021 | 06/2025 | 10/2028 | 31580 | 36354 | 1342.27 | 10
October 2025 | 436 | Ministry of Petroleum & Natural Gas | Oil & Gas | Laying of new 28 inch Desal Water Pipeline and 10 inch Reject Water Pipeline between CPCL Manali Refinery and CPCL Desalination plant at Ennore | Chennai Petroleum Corporation Limited [CPCL] | 709750 | Tamil Nadu | 01/2024 | 01/2024 | 09/2025 | 12/2025 | 205 | 205 | 56.22 | 51
October 2025 | 437 | Ministry of Petroleum & Natural Gas | Oil & Gas | City Gas Distribution Projects at the Nilgiris and Erode districts | Bharat Petroleum Corporation Limited [BPCL] | 709796 | Tamil Nadu | 12/2022 | 12/2022 | 03/2030 | 03/2030 | 3685 | 3685 | 244.45 | 20
October 2025 | 438 | Ministry of Petroleum & Natural Gas | Oil & Gas | Creation of Gas Dehydration Facilities, Tripura Asset | Oil and Natural Gas Corporation Limited [ONGC] | 709837 | Tripura | 03/2022 | 03/2022 | 05/2024 | 12/2025 | 209.33 | 131.51 | 70.1 | 66
October 2025 | 439 | Ministry of Petroleum & Natural Gas | Oil & Gas | PP Project, Pata | Gas Authority of India Limited [GAIL] | 400161 | Uttar Pradesh | 03/2019 | 03/2019 | 01/2024 | 11/2025 | 910.56 | 1299.02 | 1041 | 98
October 2025 | 440 | Ministry of Petroleum & Natural Gas | Oil & Gas | Revamping / Augmentation of Facilities at Mathura Bitumen Plant | MinistryofPetroleumNaturalGas | 709781 | Uttar Pradesh | 04/2022 | 04/2022 | 06/2027 | 12/2026 | 260.12 | 260.12 | 8.14 | 30
October 2025 | 441 | Ministry of Petroleum & Natural Gas | Oil & Gas | City Gas Distribution Projects at Lakhimpur Kheri , Sitapur, Bahraich, Shravasti,Balrampur, Siddharth Nagar & Maharajganj districts | Bharat Petroleum Corporation Limited [BPCL] | 709795 | Uttar Pradesh | 12/2022 | 12/2022 | 06/2030 | 06/2030 | 16654 | 16654 | 595.93 | 12
October 2025 | 442 | Ministry of Petroleum & Natural Gas | Oil & Gas | Durgapur - Haldia Pipeline [Section-3B of JHBDPL Project] | Ministry of Petroleum & Natural Gas | 617302 | West Bengal | 03/2017 | 03/2017 | 12/2020 | 12/2025 | 1740 | 2493.15 | 2285 | 90
October 2025 | 443 | Ministry of Petroleum & Natural Gas | Oil & Gas | Haldia Panagarh Pipeline Project | Hindustan Petroleum Corporation Limited | 709753 | West Bengal | 11/2022 | 11/2022 | 11/2025 | 05/2026 | 1010 | 1010 | 692.62 | 84
October 2025 | 444 | Ministry of Petroleum & Natural Gas | Oil & Gas | CGD Project in Malda, Birbhum, Murshidabad, Dakshin Dinajpur GA ID 11A.03 | Hindustan Petroleum Corporation Limited | 709758 | West Bengal | 06/2022 | 06/2022 | 06/2030 | 06/2030 | 2628 | 2628 | 348.91 | 29
October 2025 | 445 | Ministry of Petroleum & Natural Gas | Oil & Gas | City Gas Distribution Project at East Mednipore, West Mednipore & Jhargram Districts | MinistryofPetroleumNaturalGas | 709772 | West Bengal | 03/2022 | 03/2022 | 06/2031 | 06/2031 | 609 | 609 | 58.09 | 2
October 2025 | 446 | Ministry of Petroleum & Natural Gas | Oil & Gas | City Gas Distribution Projects at Alipurduar and Cooch Behar | Bharat Petroleum Corporation Limited [BPCL] | 709791 | West Bengal | 12/2022 | 12/2022 | 03/2030 | 03/2030 | 1017 | 1017 | 194.58 | 40
October 2025 | 447 | Ministry of Health & Family Welfare | Healthcare | AIIMS Majra Rewari Haryana | PMSSY AND Institute of NATIONAL Importance | 701173 | Haryana | 12/2023 | 02/2019 | 02/2023 | 12/2026 | 1299 | 1299 | 349.41 | 28
October 2025 | 448 | Ministry of Health & Family Welfare | Healthcare | AIIMS Kashmir at Awantipora Jammu & Kashmir | PMSSY AND Institute of NATIONAL Importance | 701167 | Jammu and Kashmir | 01/2019 | 11/2020 | 01/2025 | 12/2025 | 1828 | 1828 | 1321.7 | 68
October 2025 | 449 | Ministry of Health & Family Welfare | Healthcare | AIIMS Bibinagar | PMSSY AND Institute of NATIONAL Importance | 701171 | Telangana | 12/2018 | 07/2022 | 09/2022 | 12/2025 | 1028 | 1365.95 | 806.8 | 85
October 2025 | 450 | Ministry of Labour and Employment | Healthcare | Construction of 350 beds + 50 Super Specialty beds ESIC Hospital Sheelanagar, Visakhapatnam, Andhra Pradesh | Employee's State Insurance Company [ESIC] | 612167 | Andhra Pradesh | 02/2021 | 04/2023 | 10/2025 | 01/2026 | 384.27 | 384.27 | 105 | 40
October 2025 | 451 | Ministry of Labour and Employment | Healthcare | Construction of 200 bedded ESIC Hospital with 62 Nos Staff quarters , Beltola | Employee's State Insurance Company [ESIC] | 612201 | Assam | 12/2017 | 10/2021 | 04/2025 | 10/2025 | 143.23 | 154.75 | 101.83 | 93
October 2025 | 452 | Ministry of Labour and Employment | Healthcare | C/o Construction of 200 bedded [Up-gradable to 300 bedded] ESI Hospital at Surat Gujarat. | Employee's State Insurance Company [ESIC] | 612185 | Gujarat | 06/2019 | 03/2021 | 06/2025 | 05/2025 | 209.36 | 209.36 | 180.54 | 98
October 2025 | 453 | Ministry of Labour and Employment | Healthcare | 350 Bedded [Upgradable to 500 beds] ESI Hospital at Sanand | Employee's State Insurance Company [ESIC] | 612186 | Gujarat | 06/2022 | 04/2023 | 03/2026 | 02/2026 | 558.12 | 558.12 | 58.36 | 7
October 2025 | 454 | Ministry of Labour and Employment | Healthcare | Demolition, Construction and upgradation of ESI Hospital, Kalol, Gujarat from 50 beds to 150 beds. | Employee's State Insurance Company [ESIC] | 612211 | Gujarat | 08/2022 | 10/2023 | 10/2025 | 06/2026 | 205.87 | 205.87 | 31.49 | 16
October 2025 | 455 | Ministry of Labour and Employment | Healthcare | Construction of 100 bedded ESIC Hospital & 32 nos. of Staff qtrs at OMPURA J&K. | Employee's State Insurance Company [ESIC] | 612239 | Jammu and Kashmir | 09/2019 | 12/2021 | 09/2024 | 05/2025 | 131.05 | 164.93 | 1747.76 | 99
October 2025 | 456 | Ministry of Labour and Employment | Healthcare | Construction of 200 bed ESI Hospital at Bommasandra, Karnataka | Employee's State Insurance Company [ESIC] | 612745 | Karnataka | 02/2015 | 10/2024 | 01/2027 | - | 278 | 278 | 27.8 | 0
October 2025 | 457 | Ministry of Labour and Employment | Healthcare | Construction of 100 bed ESI Hospital and Staff Quarters [32 Nos.] at Harohalli, Karnataka | Employee's State Insurance Company [ESIC] | 612748 | Karnataka | 07/2019 | 03/2025 | 02/2027 | - | 150.92 | 150.92 | 0 | 0
October 2025 | 458 | Ministry of Labour and Employment | Healthcare | Construction of 200 Bedded [Upgradable to 500 Bedded including 50 beds of SST] ESIC Hospital at Bibewadi, Pune | Employee's State Insurance Company [ESIC] | 612188 | Maharashtra | 05/2018 | 03/2023 | 09/2025 | 02/2026 | 429.25 | 429.25 | 252.06 | 68
October 2025 | 459 | Ministry of Labour and Employment | Healthcare | Construction of 200 Bedded ESIC Hospital at Butibori, Nagpur, Maharashtra. | Employee's State Insurance Company [ESIC] | 612213 | Maharashtra | 10/2013 | 08/2022 | 08/2025 | 08/2025 | 194.93 | 196.7 | 86.6 | 60
October 2025 | 460 | Ministry of Labour and Employment | Healthcare | Upgradation & Extension of ESIC Hospital and Construction of PG Hostel / Staff Housing for ESIC Hospital at Andheri, Mumbai | Employee's State Insurance Company [ESIC] | 616691 | Maharashtra | NA | 06/2009 | 08/2025 | 12/2025 | 260.13 | 260.13 | 210.12 | 88
October 2025 | 461 | Ministry of Labour and Employment | Healthcare | Construction of 100 Bedded ESI Hospital at Duburi, Odisha. | Employee's State Insurance Company [ESIC] | 612513 | Odisha | 12/2010 | 02/2025 | 06/2027 | - | 164.6 | 164.6 | 16.4 | 1
October 2025 | 462 | Ministry of Labour and Employment | Healthcare | Construction of 100 Bedded ESIC Hospital building and 32 Nos Residential Quarters at Vallam Vadangal, SIPCOT, Sriperumbudur | Employee's State Insurance Company [ESIC] | 612178 | Tamil Nadu | 02/2015 | 03/2023 | 06/2025 | - | 152.95 | 152.95 | 107.83 | 98
October 2025 | 463 | Ministry of Labour and Employment | Healthcare | Construction of New OPD Block 200 Bed ward Basement + GF + 6 Floors at the location of old OPD block, at existing ESIC Hospital/ Medical college campus, Sanathnagar, Hyderabad | Employee's State Insurance Company [ESIC] | 612688 | Telangana | 11/2017 | 10/2021 | 06/2024 | 06/2025 | 211.13 | 211.13 | 198.95 | 100
October 2025 | 464 | Ministry of Labour and Employment | Healthcare | CONSTRUCTION OF 300 BEDDED HOSPITAL AT HARIDWAR | Employee's State Insurance Company [ESIC] | 612259 | Uttarakhand | 02/2021 | 12/2021 | 10/2024 | 06/2025 | 102.4 | 297.63 | 297.63 | 68
October 2025 | 465 | Ministry of Ports, Shipping and Waterways | Healthcare | Establishment of 600 bed super specialty hospital with optional development of Medical college and further expansion on PPP basis. | Mumbai Port Trust [MPT] | 708662 | Maharashtra | 08/2019 | 01/2022 | 06/2026 | 12/2027 | 693 | 693 | 58 | 0
October 2025 | 466 | Ministry of Ports, Shipping and Waterways | Inland Waterways | Jal Marg Vikas Project | Inland Waterways Authority of India [IWAI] | 701565 | Multi-States (Bihar, Jharkhand, Uttar Pradesh, West Bengal) | 01/2018 | 02/2018 | 12/2023 | 12/2025 | 5369.18 | 5061.15 | 3526.99 | 72
October 2025 | 467 | Ministry of Ports, Shipping and Waterways | Inland Waterways | Fairway Development in West Bengal Farakka - Kahelgaon | Inland Waterways Authority of India [IWAI] | 611142 | Offshore | NA | 08/2018 | 07/2023 | 04/2024 | 177 | 197 | 183.32 | 100
October 2025 | 468 | Ministry of Ports, Shipping and Waterways | Shipping | Development of Container Terminal at Tuna-Tekra, Deendayal Port on BOT Basis Under PPP Mode | Deendayal Port Trust [DPT] | 609424 | Gujarat | 10/2022 | 03/2024 | 03/2027 | - | 4243.64 | 4243.64 | 800.04 | 32
October 2025 | 469 | Ministry of Ports, Shipping and Waterways | Shipping | Construction of oil jetty No.8 at old kandla through internal resources | Deendayal Port Trust [DPT] | 701568 | Gujarat | NA | 02/2021 | 02/2023 | 07/2024 | 100 | 225.85 | 166.48 | 90
October 2025 | 470 | Ministry of Ports, Shipping and Waterways | Shipping | Replacement and revamping of pipeline projects in oil jetty area, Kandla | Deendayal Port Trust [DPT] | 701570 | Gujarat | 09/2021 | 09/2021 | 09/2023 | 03/2025 | 171 | 211.61 | 137.51 | 71
October 2025 | 471 | Ministry of Ports, Shipping and Waterways | Shipping | Mechanization of Berth No.14 for handling Containers and other cargo on DBFOT basis - Phase II | New Mangalore Port Authority | 617804 | Karnataka | NA | 06/2024 | 03/2027 | - | 153.23 | 153.23 | 50.1 | 33
October 2025 | 472 | Ministry of Ports, Shipping and Waterways | Shipping | Construction of new dry dock at exisitng Cochin Shipyard Limited premises at Perumanoor, Kochi 682 015 | Cochin Shipyard | 701564 | Kerala | 04/2018 | 05/2018 | 12/2022 | 03/2025 | 1799 | 1799 | 1558.39 | 96
October 2025 | 473 | Ministry of Ports, Shipping and Waterways | Shipping | Rewas Port Project | Reliance Industries Ltd | 400382 | Maharashtra | NA | 01/2020 | 03/2023 | - | 6000 | 6000 | 5999.89 | 0
October 2025 | 474 | Ministry of Ports, Shipping and Waterways | Shipping | Setting up of a Floating Storage and Regasification Unit [FSRU] - Mumbai | Mumbai Port Trust [MPT] | 701586 | Maharashtra | NA | 04/2021 | 11/2026 | 11/2026 | 900 | 900 | 65 | 0
October 2025 | 475 | Ministry of Ports, Shipping and Waterways | Shipping | Deepening and Optimization of Inner Harbour facilities including development of Western Dock on BOT basis to handle Cape size vessels | Paradip Port Trust [PPT] | 701574 | Odisha | 05/2022 | 01/2023 | 12/2027 | 10/2028 | 3004.63 | 3004.63 | 1149.79 | 40
October 2025 | 476 | Ministry of Ports, Shipping and Waterways | Shipping | Berth No. 2 [previously Berth 3] of HDC Mechanization Project | Haldia Dock Complex, Syama Prasad Mookerjee Port Authority | 701576 | West Bengal | NA | 03/2023 | 09/2025 | 01/2026 | 298.26 | 298.26 | 438.5 | 97
October 2025 | 477 | Ministry of Ports, Shipping and Waterways | Shipping | Shalukkhali Liquid Cargo Handling Facility Development Project | Haldia Dock Complex, Syama Prasad Mookerjee Port Authority | 701577 | West Bengal | NA | 08/2022 | 08/2025 | - | 253.65 | 253.65 | 9.28 | 0
October 2025 | 478 | Ministry of Ports, Shipping and Waterways | Tourism, Hospitality & Wellness | National Maritime Heritage Complex [NMHC] Phase-I | Indian Port Rail & Ropeway Corporation Ltd. [IPRCL] | 707215 | Gujarat | 02/2019 | 01/2022 | 03/2024 | 09/2025 | 573 | 1238.05 | 496.63 | 66
October 2025 | 479 | Ministry of Steel | Metals & Mining | Capacity expansion of Deposit-14 and 14 NMZ at Kirandul | National Mineral Development Corporation Limited [NMDC] | 615202 | Chhattisgarh | 08/2021 | 07/2022 | 12/2028 | 03/2028 | 1700 | 1756.2 | 133.22 | 6
October 2025 | 480 | Ministry of Steel | Steel | Stamp Charge Battery No.12 Battery Proper at IISCO Steel Plant | Steel Authority of India Limited [SAIL] | 617338 |  | 01/2025 | 02/2025 | 07/2028 | - | 2518.39 | 2518.39 | 152.23 | 4
October 2025 | 481 | Ministry of Steel | Steel | Replacement of Hot Leveller No.1 of Plate Mill at Bhilai Steel Plant | Steel Authority of India Limited [SAIL] | 617243 | Chhattisgarh | 07/2024 | 08/2024 | 07/2026 | - | 198.62 | 198.62 | 12.21 | 15
October 2025 | 482 | Ministry of Steel | Steel | Replacement of Converter Vessels, Trunnion Rings, Support System & Installation of Secondary Emission at Bhilai Steel Plant | Steel Authority of India Limited [SAIL] | 617255 | Chhattisgarh | 10/2023 | 12/2023 | 06/2026 | - | 471.83 | 471.83 | 158.07 | 46
October 2025 | 483 | Ministry of Steel | Steel | Rebuilding of Coke Oven Battery No.7 & 8 at Bhilai Steel Plant | Steel Authority of India Limited [SAIL] | 617256 | Chhattisgarh | 11/2023 | 01/2024 | 10/2025 | - | 884.1 | 884.1 | 506.96 | 80
October 2025 | 484 | Ministry of Steel | Steel | NMDC Slurry Pipeline Project Phase-1 | National Mineral Development Corporation Limited [NMDC] | 706811 | Chhattisgarh | 11/2015 | 09/2020 | 06/2023 | 12/2025 | 2907 | 5427 | 3179.93 | 88
October 2025 | 485 | Ministry of Steel | Steel | SCREENING PLANT-III AT KIRANDUL | National Mineral Development Corporation Limited [NMDC] | 709826 | Chhattisgarh | NA | 10/2021 | 01/2026 | - | 2718.84 | 2718.84 | 1384.73 | 77
October 2025 | 486 | Ministry of Steel | Steel | CONSTRUCTION OF RESIDENTIAL TOWERS AT BIOM KIRANDUL COMPLEX | National Mineral Development Corporation Limited [NMDC] | 709827 | Chhattisgarh | NA | 10/2022 | 12/2025 | - | 349.75 | 349.75 | 294.65 | 94
October 2025 | 487 | Ministry of Steel | Steel | New Sinter Plant at BSL, SAIL | Steel Authority of India Limited [SAIL] | 400174 | Jharkhand | 03/2015 | 10/2015 | 10/2017 | 06/2027 | 1034.01 | 1752.3 | 885.26 | 53
October 2025 | 488 | Ministry of Steel | Steel | Replacement of existing Grinders in CRM-I & II at Bokaro Steel Plant | Steel Authority of India Limited [SAIL] | 617249 | Jharkhand | 01/2025 | 02/2025 | 01/2027 | - | 211.94 | 211.94 | 16.04 | 11
October 2025 | 489 | Ministry of Steel | Steel | Secondary Emission Control in Converters of SMS-II at Bokaro Steel Plant | Steel Authority of India Limited [SAIL] | 617250 | Jharkhand | 01/2025 | 02/2025 | 10/2026 | - | 207.13 | 207.13 | 15.76 | 8
October 2025 | 490 | Ministry of Steel | Steel | Revamping of old sub-systems of Blast Furnace 3 at Bokaro Steel Plant | Steel Authority of India Limited [SAIL] | 617253 | Jharkhand | 08/2023 | 03/2023 | 07/2025 | 11/2025 | 513.82 | 513.82 | 257.89 | 74
October 2025 | 491 | Ministry of Steel | Steel | Replacement of remaining 04 sets of Battery Cyclones with 04 Nos. of ESPs in Sinter Plant-1 at Bokaro Steel Plant | Steel Authority of India Limited [SAIL] | 617254 | Jharkhand | 03/2024 | 04/2024 | 06/2026 | - | 260.37 | 260.37 | 54.89 | 23
October 2025 | 492 | Ministry of Steel | Steel | Rebuilding of Coke Oven Battery No.6 at Bokaro Steel Plant | Steel Authority of India Limited [SAIL] | 617257 | Jharkhand | 11/2023 | 12/2023 | 11/2026 | - | 627.31 | 627.31 | 153.32 | 46
October 2025 | 493 | Ministry of Steel | Steel | Construction of Screening Plant-II for Donimalai and Kumaraswamy Iron Ore Mining Complex of NMDC Limited at Ballari Dt, Karnataka. | National Mineral Development Corporation Limited [NMDC] | 400121 | Karnataka | 11/2014 | 06/2024 | 08/2026 | - | 1043.63 | 1043.63 | 288.87 | 35
October 2025 | 494 | Ministry of Steel | Steel | Installation of 4th Slab Caster along with its Auxiliaries and a New Ladle Furnace in SMS-II at Rourkela Steel Plant | Steel Authority of India Limited [SAIL] | 400065 | Odisha | 01/2022 | 02/2022 | 05/2025 | 09/2025 | 1105.23 | 1105.23 | 790.11 | 99
October 2025 | 495 | Ministry of Steel | Steel | Rebuilding of COB 4 at Durgapur Steel Plant | Steel Authority of India Limited [SAIL] | 612781 | West Bengal | 09/2023 | 09/2023 | 12/2026 | - | 916.78 | 916.78 | 146.64 | 20
October 2025 | 496 | Ministry of Steel | Steel | Installation of New Bar Mill at Durgapur Steel Plant | Steel Authority of India Limited [SAIL] | 617242 | West Bengal | 07/2024 | 08/2024 | 06/2027 | - | 2115.44 | 2115.44 | 236.73 | 32
October 2025 | 497 | Ministry of Steel | Steel | Up-gradation of Blast Furnace No. 3 at Durgapur Steel Plant | Steel Authority of India Limited [SAIL] | 617246 | West Bengal | 09/2024 | 08/2024 | 06/2026 | - | 758.09 | 758.09 | 85.89 | 7
October 2025 | 498 | Ministry of Steel | Steel | Third Ladle Furnace in Secondary Refinery Unit at IISCO Steel Plant | Steel Authority of India Limited [SAIL] | 617248 | West Bengal | 11/2024 | 12/2024 | 07/2026 | - | 227.96 | 227.96 | 27.2 | 33
October 2025 | 499 | Ministry of Steel | Steel | Revamping of Air Pollution Control Systems of SP-1 at Durgapur Steel Plant | Steel Authority of India Limited [SAIL] | 617251 | West Bengal | 07/2024 | 12/2024 | 05/2026 | - | 196.4 | 196.4 | 5.96 | 5
October 2025 | 500 | Ministry of Railways | Railways | Nadikudi - Srikalahasti New Line | South Central Railway [SCR] - II | 400298 | Andhra Pradesh | 03/2012 | 12/2016 | 05/2027 | 03/2028 | 2312 | 5200 | 2179 | 54
October 2025 | 501 | Ministry of Railways | Railways | Malugur- Palasamudram New Line Project [17.975 Km] | South Western Railway [SWR] - II | 611615 | Andhra Pradesh | 09/2022 | 07/2026 | 11/2027 | 12/2027 | 342 | 342 | 0 | 0
October 2025 | 502 | Ministry of Railways | Railways | GOOTY-PENDEKALLU DOUBLING 29.225 Km | South Central Railway [SCR] - II | 611752 | Andhra Pradesh | 03/2023 | 06/2023 | 03/2027 | 03/2027 | 351.83 | 351.83 | 18 | 25
October 2025 | 503 | Ministry of Railways | Railways | GUNTAKAL WEST-MALLAPPA GATE RAIL OVER RAIL - ROR TRACK | South Central Railway [SCR] - II | 611754 | Andhra Pradesh | 07/2023 | 07/2023 | 07/2026 | - | 293.3 | 293.3 | 0 | 0
October 2025 | 504 | Ministry of Railways | Railways | Kurnool - Setting up facilities for coach midlife rehabilitation workshop | WPO/Patna | 611927 | Andhra Pradesh | 01/2014 | 10/2017 | 12/2023 | - | 560.72 | 560.72 | 276.66 | 65
October 2025 | 505 | Ministry of Railways | Railways | Flyover between Pendurthi and Simhachalam North to avoid surface crossing at Simhachalam 7.135 km PB 73 of 2023 24 NR | East Coast Railway [ECoR] - II | 612827 | Andhra Pradesh | 04/2023 | 05/2024 | 04/2027 | - | 183.65 | 183.65 | 5.11 | 11
October 2025 | 506 | Ministry of Railways | Railways | 3rd & 4th line between Vadlapudi -Gate Jn. cabin and Tie line between Gate Junction to Gangavaram port | East Coast Railway [ECoR] - II | 616697 | Andhra Pradesh | 04/2023 | 03/2024 | 06/2026 | - | 154.28 | 154.28 | 20.15 | 21
October 2025 | 507 | Ministry of Railways | Railways | Tiupati Katpadi 104.39 kms | South Central Railway [SCR] - II | 617210 | Andhra Pradesh | 04/2025 | 04/2025 | 03/2029 | - | 1215.56 | 1215.56 | 0.1 | 0
October 2025 | 508 | Ministry of Railways | Railways | 3rd Line between Gudur Renigunta 83.17 Km | South Central Railway [SCR] - II | 617216 | Andhra Pradesh | 10/2024 | 10/2024 | 03/2027 | - | 877.34 | 877.34 | 23.35 | 0
October 2025 | 509 | Ministry of Railways | Railways | Kurnool Coach Midlife Rehabilitation Project | WPO/Patna | 705253 | Andhra Pradesh | 05/2016 | 07/2014 | 12/2020 | - | 563 | 563 | 120 | 0
October 2025 | 510 | Ministry of Railways | Railways | Kotapalli - Narasapur New Line | South Central Railway [SCR] - II | 705436 | Andhra Pradesh | 03/2009 | 09/2013 | 03/2028 | 03/2028 | 2501 | 2501 | 1318.88 | 29
October 2025 | 511 | Ministry of Railways | Railways | Guntur-Guntakal Doubling Project | South Central Railway [SCR] - II | 705633 | Andhra Pradesh | 03/2017 | 11/2017 | 12/2025 | 12/2026 | 3733 | 4295 | 4475.84 | 93
October 2025 | 512 | Ministry of Railways | Railways | Vijaywada-Gudur 3rd Line | RVNL - II | 705648 | Andhra Pradesh | 08/2016 | 04/2018 | 11/2024 | 12/2025 | 6654 | 6654 | 5922 | 90
October 2025 | 513 | Ministry of Railways | Railways | Penukonda - Dharmavaram Doubling Project [41.5 Km] | South Western Railway [SWR] - II | 705789 | Andhra Pradesh | 06/2018 | 12/2018 | 03/2026 | 03/2026 | 307.66 | 307.66 | 259.52 | 65
October 2025 | 514 | Ministry of Railways | Railways | Doubling of New Bonggigaon to Kamakhya via Goalpara - 176 km | Northeast Frontier Railway [NFR] | 705572 | Assam | 09/2016 | 09/2016 | 03/2026 | 03/2026 | 4060 | 4961 | 3727.78 | 93
October 2025 | 515 | Ministry of Railways | Railways | Guwahati-Dibrugarh via Tinsukia & Simaluguri-Dibrugarh | Central Organisation for Railway Electrification [CORE] | 706922 | Assam | 09/2020 | 09/2018 | 09/2020 | 06/2024 | 890.36 | 889.36 | 391.73 | 89
October 2025 | 516 | Ministry of Railways | Railways | Mariani-Jorhat, Tinsukia-Dangri and Makum -TirapTrack Electrification Project | GM/C/ NFR | 706940 | Assam | 09/2018 | 01/2022 | 05/2024 | - | 183.99 | 183.99 | 0 | 0
October 2025 | 517 | Ministry of Railways | Railways | Harmuty-Murkongselek Branch Line Electrification Project | GM/C/ NFR | 706942 | Assam | 09/2018 | 01/2022 | 05/2024 | - | 237.52 | 237.52 | 0 | 0
October 2025 | 518 | Ministry of Railways | Railways | Sakri -Hasanpur [via Harnagar - Kusheshwar Asthan] New Railway line | East Central Railway [ECR] - I | 400254 | Bihar | 12/2023 | 08/1997 | 12/2024 | 03/2027 | 735.2 | 735.2 | 588.66 | 84
October 2025 | 519 | Ministry of Railways | Railways | Construction of Bulb line at Nabinagar Ankorah of East Central Railway | East Central Railway [ECR] - I | 617231 | Bihar | 06/2024 | 06/2024 | 06/2028 | - | 611.74 | 611.74 | 0 | 0
October 2025 | 520 | Ministry of Railways | Railways | Jhajha-Batai New Line Project | East Central Railway [ECR] - I | 617373 | Bihar | 03/2023 | 03/2023 | 03/2027 | - | 588.18 | 588.18 | 3.05 | 0
October 2025 | 521 | Ministry of Railways | Railways | Khagaria-Kusheshwar Asthan [42Km] new line project | East Central Railway [ECR] - I | 705364 | Bihar | 04/2019 | 12/1998 | 12/2024 | 03/2027 | 614 | 1384 | 487.99 | 55
October 2025 | 522 | Ministry of Railways | Railways | Hajipur-Sagauli New line | East Central Railway [ECR] - I | 705366 | Bihar | 10/2007 | 10/2004 | 03/2020 | 12/2026 | 2067 | 2087 | 2013.82 | 74
October 2025 | 523 | Ministry of Railways | Railways | Araria Supaul New BG Line | East Central Railway [ECR] - I | 705368 | Bihar | 06/2018 | 03/2009 | 03/2024 | 01/2027 | 1605 | 2514 | 1547.96 | 35
October 2025 | 524 | Ministry of Railways | Railways | Fatuha-Islampur incl. MM for extn.of NL from Neora to Daniawan , Daniawan to Biharsharif, Biharsharif to Barbigha , Barbigha to Shekhpura | East Central Railway [ECR] - I | 705373 | Bihar | 08/2002 | 03/2002 | 03/2023 | 08/2025 | 1473 | 2882 | 2535.73 | 94
October 2025 | 525 | Ministry of Railways | Railways | Jogbani-Biratnagar New Rail Line project | Indian Railway Construction International Limited [IRCON] | 705450 | Bihar | 06/2010 | 01/2011 | 03/2022 | 12/2026 | 402 | 486 | 367.54 | 86
October 2025 | 526 | Ministry of Railways | Railways | Samastipur-Darbhanga Doubling Railway Project | East Central Railway [ECR] - I | 705526 | Bihar | 11/2015 | 12/2015 | 03/2025 | 10/2025 | 519 | 519 | 367.57 | 84
October 2025 | 527 | Ministry of Railways | Railways | Sagauli-Valmiknagar | East Central Railway [ECR] - I | 705527 | Bihar | 03/2018 | 03/2017 | 12/2025 | 12/2025 | 1216 | 2222 | 2072.37 | 91
October 2025 | 528 | Ministry of Railways | Railways | Muzaffarpur-Sugauli | East Central Railway [ECR] - I | 705528 | Bihar | 03/2018 | 03/2017 | 06/2024 | 02/2026 | 1586 | 1586 | 1470.4 | 99
October 2025 | 529 | Ministry of Railways | Railways | Rampur Dumra-Tal-Rajendrapul Additional Bridge and Railway Line Doubling | Indian Railway Construction International Limited [IRCON] | 706759 | Bihar | 03/2016 | 05/2017 | 12/2024 | 12/2025 | 2373.64 | 1700.24 | 1427.78 | 97
October 2025 | 530 | Ministry of Railways | Railways | Barauni-Bachwara [16 km] - 3rd & 4th line incl. Barauni yard remodelling [32 km] | East Central Railway [ECR] - I | 706860 | Bihar | 10/2022 | 08/2025 | 08/2025 | 10/2026 | 645 | 645 | 7.96 | 55
October 2025 | 531 | Ministry of Railways | Railways | JHAJHA - BATIA | East Central Railway [ECR] - I | 900874 | Bihar | 03/2023 | 03/2023 | 03/2028 | 01/2030 | 588.18 | 588.18 | 0.8 | 0
October 2025 | 532 | Ministry of Railways | Railways | Kharsia-Dharamjaygarh with Spur line [East Corridor-Phase 1] | Indian Railway Construction International Limited [IRCON] | 400220 | Chhattisgarh | 03/2016 | 01/2014 | 09/2018 | 03/2026 | 3055 | 3438 | 2594.89 | 94
October 2025 | 533 | Ministry of Railways | Railways | Doubling of Kirandul-Jagdalpur Line [150 km] | East Coast Railway [ECoR] - II | 400291 | Chhattisgarh | 02/2013 | 03/2013 | 03/2020 | 12/2025 | 1589 | 1798 | 1566.97 | 93
October 2025 | 534 | Ministry of Railways | Railways | Gauge Conversion of Kendri-Dhamtari including Abhanpur - Rajim Branch line 67.20 Kms - 2nd Material Modification to Raipur Titlagarh doubling. | SECR | 602792 | Chhattisgarh | 07/2011 | 05/2021 | 02/2025 | 03/2026 | 1171 | 1171 | 376 | 100
October 2025 | 535 | Ministry of Railways | Railways | 4th line between Nipania Bhatapara 14.4 Km | South East Central Railway [SECR] - II | 612815 | Chhattisgarh | 12/2022 | 05/2024 | 03/2027 | - | 170.49 | 170.49 | 1.34 | 5
October 2025 | 536 | Ministry of Railways | Railways | Dharamjaigarh-Korba 63 km | CERL | 613003 | Chhattisgarh | 08/2023 | 07/2022 | 08/2026 | - | 1686.26 | 1686.26 | 288.83 | 18.5
October 2025 | 537 | Ministry of Railways | Railways | KHARSIA- NAYA RAIPUR-PARMALKASA 5th and 6th Line [278KM] | CAO/C/SECR | 617200 | Chhattisgarh | 04/2025 | 04/2025 | 03/2031 | - | 7853.84 | 7853.84 | 0 | 0
October 2025 | 538 | Ministry of Railways | Railways | Dallirajhara - Rowghat New Rail Line Project, Phase-I | Rail Vikas Nigam Limited | 617374 | Chhattisgarh | NA | 11/2009 | 03/2025 | - | 1516.45 | 1516.45 | 873.79 | 92
October 2025 | 539 | Ministry of Railways | Railways | Dallirajhra- Rowghat New Railway Line - Phase I [95 km] | Rail Vikas Nigam Limited | 705433 | Chhattisgarh | 07/2009 | 12/2009 | 09/2025 | 12/2025 | 1628 | 1628 | 1440.85 | 82
October 2025 | 540 | Ministry of Railways | Railways | Gevra Road-Pendra Road New Railway Line [135 km] | Indian Railway Construction International Limited [IRCON] | 705444 | Chhattisgarh | 04/2014 | 04/2014 | 03/2022 | 12/2025 | 4970 | 4970 | 4449.99 | 73
October 2025 | 541 | Ministry of Railways | Railways | Boridand - Ambikapur Doubling Line Project | South East Central Railway [SECR] - II | 706854 | Chhattisgarh | 06/2022 | 04/2022 | 06/2030 | 06/2030 | 1376 | 1576.23 | 139.49 | 21
October 2025 | 542 | Ministry of Railways | Railways | 4TH LINE - BHATAPARA-HATHBAND [8.8 KM] [PB-72/NR/2022-23] | SECR | 709815 | Chhattisgarh | 09/2022 | 05/2024 | 01/2027 | 12/2027 | 177.03 | 177.03 | 0 | 3
October 2025 | 543 | Ministry of Railways | Railways | 4TH LINE - BHILAI-BHILAI NAGAR [8.8 KM] [PB-72/NR/2022-23] | SECR | 709816 | Chhattisgarh | 09/2022 | 05/2024 | 02/2027 | 02/2027 | 177.34 | 177.34 | 1.64 | 5
October 2025 | 544 | Ministry of Railways | Railways | 4TH LINE - DADHAPARA-BELHA [9.2 KM] [PB-72/NR/2022-23] | SECR | 709817 | Chhattisgarh | 09/2022 | 05/2024 | 11/2026 | 11/2026 | 169.06 | 169.06 | 17.84 | 60
October 2025 | 545 | Ministry of Railways | Railways | 4TH LINE RAJNANDGAON-DONGARHGARH [31.2 KM] [PB-72/NR/2022-23] | SECR | 709818 | Chhattisgarh | 09/2022 | 05/2024 | 01/2027 | 01/2027 | 328.34 | 328.34 | 56.1 | 26
October 2025 | 546 | Ministry of Railways | Railways | 3RD AND 4TH LINE - SARAGBUNDIA AND MADWARANI | SECR | 709819 | Chhattisgarh | 09/2022 | 05/2025 | 12/2026 | 12/2026 | 167.64 | 167.64 | 0.09 | 4
October 2025 | 547 | Ministry of Railways | Railways | Redevelopment of New Delhi Railway Station and construction of associated infrastructure | Rail Land Development Authority | 613785 | Delhi | 01/2023 | 06/2024 | 12/2028 | - | 4744 | 4744 | 119.95 | 1
October 2025 | 548 | Ministry of Railways | Railways | Development of New Bijwasan Railway Terminal | Northern Railways | 617379 | Delhi | 02/2008 | 03/2013 | 03/2020 | - | 446.21 | 446.21 | 511.94 | 80
October 2025 | 549 | Ministry of Railways | Railways | North Region Video Surveillance Project | RCIL | 705298 | Delhi | 06/2020 | 04/2023 | 03/2024 | - | 274.39 | 274.39 | 0 | 0
October 2025 | 550 | Ministry of Railways | Railways | Anand Vihar-Tilak Bridge 3rd & 4th line | CAO/C/NR | 705583 | Delhi | 03/2013 | 03/2013 | 03/2023 | 12/2027 | 667 | 667 | 287.26 | 62
October 2025 | 551 | Ministry of Railways | Railways | Provision of Work-site Tampers [WST] Railway Project | EDTK[MC]/RB | 705694 | Delhi | 01/2016 | 01/2016 | 12/2023 | 01/2026 | 187.72 | 187.72 | 141.91 | 100
October 2025 | 552 | Ministry of Railways | Railways | WST Machine Procurement Project | EDTK[MC]/RB | 705708 | Delhi | 06/2018 | 06/2018 | 03/2024 | 12/2027 | 176 | 176 | 0 | 0
October 2025 | 553 | Ministry of Railways | Railways | PCT Machine Procurement Project | EDTK[MC]/RB | 705710 | Delhi | 04/2019 | 04/2019 | 04/2024 | 06/2027 | 336 | 336 | 74.32 | 85
October 2025 | 554 | Ministry of Railways | Railways | RBMV Machine Procurement Project | EDTK[MC]/RB | 705712 | Delhi | 10/2019 | 10/2019 | 06/2024 | 12/2027 | 480 | 480 | 0.33 | 7
October 2025 | 555 | Ministry of Railways | Railways | SRGM Machine Procurement Project | EDTK[MC]/RB | 705717 | Delhi | 10/2019 | 10/2019 | 12/2023 | 03/2026 | 440 | 440 | 390.03 | 90
October 2025 | 556 | Ministry of Railways | Railways | WST Machine Procurement Project | EDTK[MC]/RB | 705720 | Delhi | 12/2019 | 12/2019 | 04/2024 | 12/2026 | 384 | 384 | 0 | 0
October 2025 | 557 | Ministry of Railways | Railways | DTS Machine Procurement Project | EDTK[MC]/RB | 705721 | Delhi | 12/2019 | 12/2019 | 12/2024 | 12/2026 | 447.6 | 447.6 | 0 | 0
October 2025 | 558 | Ministry of Railways | Railways | BRM Machine Procurement Project | EDTK[MC]/RB | 705722 | Delhi | 09/2019 | 09/2019 | 06/2024 | 12/2027 | 210 | 210 | 0.02 | 0
October 2025 | 559 | Ministry of Railways | Railways | Track Machine Procurement Project | EDTK[MC]/RB | 705726 | Delhi | 04/2020 | 04/2020 | 03/2025 | 01/2028 | 6339 | 6339 | 4166.47 | 41
October 2025 | 560 | Ministry of Railways | Railways | Kosamba Umarpada 70 Km | PCE/WR | 611918 | Gujarat | 07/2023 | 07/2022 | 03/2027 | - | 468 | 468 | 20.28 | 8
October 2025 | 561 | Ministry of Railways | Railways | Adraj Moti Vijapur 40 Kms | Western Railway (WR) - II | 611937 | Gujarat | 05/2022 | 05/2022 | 05/2026 | 12/2025 | 417.53 | 417.53 | 494.13 | 90
October 2025 | 562 | Ministry of Railways | Railways | New Broad Gauge line between Naliya to Jakhau Port | Western Railway (WR) - II | 611943 | Gujarat | 02/2023 | 02/2023 | 01/2028 | 01/2028 | 410.26 | 410.26 | 6.6 | 4
October 2025 | 563 | Ministry of Railways | Railways | Quadrupling between Gandhidham Adipur with Y connection at Adipur for providing direct entry towards Mundra Port and Bhuj and high level platform at Gopalpur 11Kms | Western Railway (WR) - II | 611944 | Gujarat | 02/2023 | 02/2023 | 03/2026 | 03/2026 | 152.44 | 152.44 | 101.74 | 75
October 2025 | 564 | Ministry of Railways | Railways | Petlad Bhadran 23 Kms | Western Railway | 611945 | Gujarat | 05/2022 | 05/2022 | 05/2030 | 05/2030 | 307.11 | 307.11 | 13.58 | 17
October 2025 | 565 | Ministry of Railways | Railways | Samlaya Timba Road 54 km | PCE/WR | 611970 | Gujarat | 02/2023 | 02/2023 | 03/2030 | 03/2030 | 670.17 | 670.17 | 44.8 | 12
October 2025 | 566 | Ministry of Railways | Railways | Samni Jambusar 24 km | PCE/WR | 611971 | Gujarat | 05/2022 | 05/2022 | 03/2030 | 03/2030 | 350 | 349.93 | 67.73 | 31
October 2025 | 567 | Ministry of Railways | Railways | Western Railway Samakhiali Gandhidham Quadrupiling 53 Kms | Western Railway (WR) - II | 611974 | Gujarat | 08/2023 | 08/2023 | 12/2026 | 06/2027 | 1430 | 1430 | 220.11 | 20
October 2025 | 568 | Ministry of Railways | Railways | Dahod Creation of Infrastructure facilities for 9000 HP Electric locomotives Manufacturing at | PCE/WR | 611977 | Gujarat | 05/2022 | 02/2023 | 02/2025 | - | 487 | 487 | 108.69 | 0
October 2025 | 569 | Ministry of Railways | Railways | Dahod Rolling Stock Workshop Provision of Infrastructure for CBS at | PCE/WR | 611978 | Gujarat | 11/2022 | 03/2023 | 03/2025 | - | 158 | 158 | 47.31 | 0
October 2025 | 570 | Ministry of Railways | Railways | Sabarmati Setting up of Maintenance Facilities for Train Sets Phase ii | PCE/WR | 611979 | Gujarat | 01/2023 | 04/2023 | 06/2025 | - | 250 | 250 | 0 | 0
October 2025 | 571 | Ministry of Railways | Railways | 4th LINE BETWEEN BAREJADI NANDEJ-SANAND-AHMEDABAD BYPASS | Western Railway (WR) - II | 612072 | Gujarat | 02/2023 | 02/2023 | 03/2027 | 07/2028 | 961.67 | 961.67 | 335.93 | 17
October 2025 | 572 | Ministry of Railways | Railways | Redevelopment of Ahmedabad railway station and associated infrastructure on engineering, procurement and construction mode | Rail Land Development Authority | 613786 | Gujarat | 01/2023 | 11/2023 | 03/2028 | - | 2379 | 2379 | 726.91 | 19
October 2025 | 573 | Ministry of Railways | Railways | Miyagam-Karjan-Dabhoi-Samlaya [GC] | Western Railway [WR] - II | 705458 | Gujarat | 01/2017 | 01/2017 | 03/2021 | 12/2026 | 483.88 | 1039.13 | 621.53 | 41
October 2025 | 574 | Ministry of Railways | Railways | Modasa-Shamlaji Road Railway Line Project | Western Railway (WR) - II | 706757 | Gujarat | 09/2012 | 04/2008 | 03/2025 | 03/2027 | 262 | 262 | 337.45 | 62
October 2025 | 575 | Ministry of Railways | Railways | Rajkot - Kanalus Doubling Project [111.2 Kms] | Western Railway (WR) - II | 706763 | Gujarat | 10/2021 | 12/2021 | 10/2026 | 10/2026 | 1080.58 | 1080.58 | 822.77 | 77
October 2025 | 576 | Ministry of Railways | Railways | NADIAD-PETLAD [37.26 KM] | Railway | 709812 | Gujarat | 05/2022 | 10/2023 | 06/2030 | 06/2030 | 461.91 | 461.91 | 92.88 | 7
October 2025 | 577 | Ministry of Railways | Railways | NEW BG LINE INTERSECTION [5 NOS] BETWEEN GERATPUR-SANAND & BOTAD-AHMEDABAD [16.51 KM] | Western Railway (WR) - II | 709813 | Gujarat | 10/2022 | 07/2025 | 06/2028 | 10/2027 | 437.21 | 437.21 | 19.06 | 17
October 2025 | 578 | Ministry of Railways | Railways | Bhiwani - Dobh Bahali Doubling Project [42.30 Km] | North Western Railway [NWR] | 611884 | Haryana | 02/2023 | 02/2023 | 02/2028 | 02/2028 | 471 | 471 | 215.11 | 65
October 2025 | 579 | Ministry of Railways | Railways | Doubling between Pradhankunta-Patherih-Bhojudih of East Central Railway | East Central Railway [ECR] - I | 617372 | Jharkhand | 11/2022 | 11/2022 | 12/2025 | - | 349.22 | 349.22 | 106.11 | 70
October 2025 | 580 | Ministry of Railways | Railways | Gomoh - Flyover for DN trains | East Central Railway [ECR] - I | 705765 | Jharkhand | 01/2018 | 01/2018 | 03/2026 | 03/2026 | 686 | 686 | 574.14 | 59
October 2025 | 581 | Ministry of Railways | Railways | Lodhma - Piska - Link Line bypassing Hatia/Ranchi with Y connection | South Eastern Railway [SER] - I | 705785 | Jharkhand | 08/2021 | 03/2019 | 06/2026 | 05/2027 | 473 | 473 | 288.59 | 5
October 2025 | 582 | Ministry of Railways | Railways | Pradhan Kuntha Jn Line Doubling Project | East Central Railway [ECR] - I | 706837 | Jharkhand | 11/2022 | 11/2022 | 11/2027 | 11/2027 | 349.22 | 349.22 | 106.11 | 62
October 2025 | 583 | Ministry of Railways | Railways | Construction of New BG line between Hassan to Belur [27 Km] | South Western Railway [SWR] - II | 400023 | Karnataka | 03/2019 | 12/2025 | 04/2028 | 04/2027 | 749 | 749 | 0 | 0
October 2025 | 584 | Ministry of Railways | Railways | Yeshvanthpur - Channasandra Doubling Project [21.70 Km] | Karnataka Rail Infrastructure Development Company Limited [K-RIDE] | 703585 | Karnataka | 04/2019 | 10/2019 | 03/2024 | 03/2026 | 314.1 | 683.57 | 152.31 | 53
October 2025 | 585 | Ministry of Railways | Railways | New Railway Line between Ginigera and Raichur [165.57 km] | South Western Railway [SWR] - II | 705434 | Karnataka | 03/2008 | 05/2009 | 03/2019 | 03/2027 | 2565 | 3034.98 | 2105.62 | 66
October 2025 | 586 | Ministry of Railways | Railways | Gadag-Wadi New Railway Line [257 km] | South Western Railway [SWR] - II | 705490 | Karnataka | 04/2013 | 08/2017 | 03/2027 | 12/2027 | 2842 | 6700 | 1400.27 | 30
October 2025 | 587 | Ministry of Railways | Railways | Kadur - Chickamagalur - Sakleshpur [93km] | South Western Railway [SWR] - II | 705492 | Karnataka | 01/2014 | 11/2016 | 06/2025 | 12/2025 | 825 | 825 | 699.12 | 83
October 2025 | 588 | Ministry of Railways | Railways | Bagalkot-Kudachi New Railway Line [142 km] | South Western Railway [SWR] - II | 705495 | Karnataka | 10/2013 | 11/2012 | 03/2027 | 01/2027 | 1378 | 1649 | 716.65 | 35
October 2025 | 589 | Ministry of Railways | Railways | Tumkur-Chitradurga-Davangere New Rail Line Project [191 km] | South Western Railway [SWR] - II | 705496 | Karnataka | 10/2013 | 01/2017 | 03/2019 | 12/2027 | 1876 | 1876 | 436.37 | 13
October 2025 | 590 | Ministry of Railways | Railways | Bangalore-Whitefield-Bangalore City-Krishnarajapuram [23.08 km] - Quadrupling | South Western Railway [SWR] - II | 705663 | Karnataka | 02/2018 | 06/2022 | 02/2026 | 02/2026 | 493 | 493 | 252.45 | 82
October 2025 | 591 | Ministry of Railways | Railways | SHIMOGA - SHIKARIPURA - RANEBENNUR [96 Km] | South Western Railway [SWR] - II | 705761 | Karnataka | 09/2019 | 02/2023 | 12/2027 | 06/2028 | 1454 | 1454 | 71.89 | 11
October 2025 | 592 | Ministry of Railways | Railways | Belgaum-Dharwad via Kittur [73.10Km] | South Western Railway [SWR] - II | 706835 | Karnataka | 09/2020 | 03/2025 | 12/2027 | 03/2029 | 1591 | 1591 | 0.38 | 0
October 2025 | 593 | Ministry of Railways | Railways | Kumbalam-Turavur doubling project [15.59 Km] | Southern Railway [SR] - II | 705638 | Kerala | 04/2023 | 04/2023 | 03/2027 | 03/2027 | 813 | 802.8 | 66.7 | 18
October 2025 | 594 | Ministry of Railways | Railways | Ernakulam-Kumbalam doubling project [7.71 Km] | SR-ERS | 705639 | Kerala | 04/2023 | 04/2023 | 03/2028 | 02/2027 | 601 | 595.39 | 289.52 | 19
October 2025 | 595 | Ministry of Railways | Railways | Lalitpur-Satna, Rewa-Singrauli & Mahoba-Khajuraho | North Central Railway | 705480 | Madhya Pradesh | 01/2007 | 03/1998 | 03/2027 | 12/2027 | 8914 | 8914 | 5013.49 | 72
October 2025 | 596 | Ministry of Railways | Railways | Katni - Bina Third Railway Line [279 km] | West Central Railway WCR I | 705651 | Madhya Pradesh | 06/2016 | 01/2017 | 03/2022 | 12/2025 | 2478.23 | 4127.23 | 3330.66 | 92
October 2025 | 597 | Ministry of Railways | Railways | Satna-Rewa Railway Line Doubling Project | West Central Railway [WCR] - II | 705659 | Madhya Pradesh | 11/2015 | 08/2017 | 03/2026 | 03/2026 | 500 | 584 | 565.61 | 80
October 2025 | 598 | Ministry of Railways | Railways | Doubling of Katni - Singrauli Railway Line [261 km] | Indian Railway Construction International Limited [IRCON] | 705660 | Madhya Pradesh | 03/2016 | 03/2017 | 12/2025 | 12/2025 | 2445 | 4377 | 3234.88 | 100
October 2025 | 599 | Ministry of Railways | Railways | Katni Grade Separator/Bye Pass | Indian Railway Construction International Limited [IRCON] | 705661 | Madhya Pradesh | 03/2016 | 09/2017 | 09/2024 | 03/2026 | 1248 | 1248 | 1651.34 | 95
October 2025 | 600 | Ministry of Railways | Railways | Indore - Budni New Railway Line [198 kms] | RVNL - II | 705763 | Madhya Pradesh | 08/2019 | 10/2020 | 09/2030 | 09/2030 | 7474 | 7474 | 1780.6 | 25
October 2025 | 601 | Ministry of Railways | Railways | Nimach-Ratlam Doubling [133 Km] | Western Railway [WR] - II | 705933 | Madhya Pradesh | 10/2021 | 10/2021 | 10/2027 | 10/2027 | 1095.88 | 1095.88 | 1067.49 | 89
October 2025 | 602 | Ministry of Railways | Railways | DHULE [BORVIHIR] - NARDANA NEW LINE [50.60 KMS] | Central Railway | 400019 | Maharashtra | 01/2019 | 04/2023 | 12/2026 | 09/2027 | 492.76 | 1170.83 | 276.86 | 16
October 2025 | 603 | Ministry of Railways | Railways | Wardha-Nanded Via Yavatmal New BG Line | Central Railway [CR] - II | 400271 | Maharashtra | 12/2017 | 04/2008 | 03/2028 | 03/2028 | 3445 | 3445 | 3002.93 | 50
October 2025 | 604 | Ministry of Railways | Railways | AURANGABAD-ANKAI - DOUBLING PROJECT 98.25 Km | South Central Railway [SCR] - II | 611751 | Maharashtra | 05/2023 | 05/2023 | 03/2027 | - | 960.64 | 960.64 | 511.61 | 1
October 2025 | 605 | Ministry of Railways | Railways | Redevelopment of Chhatrapati Shivaji Maharaj Terminus [CSMT] and construction of associated infrastructure | Rail Land Development Authority | 613015 | Maharashtra | 04/2023 | 07/2023 | 03/2027 | - | 1813 | 1813 | 600.75 | 16
October 2025 | 606 | Ministry of Railways | Railways | Gondia-Balharshah [Chanda Fort] Doubling [240 Km] | South East Central Railway | 617201 | Maharashtra | 04/2025 | 04/2025 | 03/2031 | - | 4373.04 | 4373.04 | 0 | 0
October 2025 | 607 | Ministry of Railways | Railways | Doubling between Parbhani Parli Vaijanath stations 64.71 Km | South Central Railway [SCR] - II | 617215 | Maharashtra | 12/2023 | 12/2023 | 03/2028 | - | 769.93 | 769.93 | 20.91 | 0
October 2025 | 608 | Ministry of Railways | Railways | Babupeth - Sasti New Rail Line [13.114 KMs] | Central Railway (CR) - II | 617361 | Maharashtra | 10/2024 | 10/2024 | 03/2028 | - | 362.81 | 362.81 | 0 | 0
October 2025 | 609 | Ministry of Railways | Railways | Double Chord line Between Nilaje-Kopar | Central Railway (CR) - II | 617364 | Maharashtra | 01/2025 | 01/2025 | 07/2028 | - | 338.33 | 205 | 3.42 | 0
October 2025 | 610 | Ministry of Railways | Railways | Western Region Video Surveillance Project | RCIL | 705300 | Maharashtra | 06/2020 | 04/2023 | 12/2023 | - | 227.59 | 227.59 | 0 | 0
October 2025 | 611 | Ministry of Railways | Railways | Ahmednagar - Beed - Parli - Vaijnath New Broad Gauge Line Railway Project [261.3 km] | Central Railway [CR] - II | 705356 | Maharashtra | 01/1999 | 10/2002 | 03/2026 | 03/2026 | 2538.67 | 4957.27 | 5091.94 | 98
October 2025 | 612 | Ministry of Railways | Railways | Baramati Lonand New Line Project | Central Railway | 705357 | Maharashtra | 03/2016 | 03/1999 | 03/2027 | 03/2027 | 138.48 | 1843.9 | 845.56 | 51
October 2025 | 613 | Ministry of Railways | Railways | Wadsa-Gadchiroli | South East Central Railway | 705479 | Maharashtra | 05/2017 | 03/2012 | 03/2027 | 03/2027 | 1886 | 1886 | 727.89 | 53
October 2025 | 614 | Ministry of Railways | Railways | 3rd Line Kalyan - Kasara [67.35 Kilometres] | Central Railway | 705498 | Maharashtra | 09/2015 | 09/2015 | 12/2026 | 12/2026 | 792.89 | 1395.79 | 931.97 | 51
October 2025 | 615 | Ministry of Railways | Railways | 3rd Line Wardha - Sewagram - Nagpur | Central Railway [CR] - II | 705500 | Maharashtra | 09/2015 | 05/2016 | 12/2025 | 12/2025 | 540.02 | 944.24 | 779.07 | 83
October 2025 | 616 | Ministry of Railways | Railways | 3rd Line Wardha - Ballarshah [132 Kilometres] | Central Railway [CR] - II | 705502 | Maharashtra | 03/2016 | 12/2016 | 12/2025 | 02/2026 | 1384.72 | 2033.59 | 1705.4 | 80
October 2025 | 617 | Ministry of Railways | Railways | Pune - Miraj-Londa [467 Kilometres] | Central Railway | 705503 | Maharashtra | 06/2016 | 06/2016 | 02/2025 | 08/2025 | 4027.53 | 4872.52 | 4924.05 | 85
October 2025 | 618 | Ministry of Railways | Railways | Doubling of Daund Manmad Line [247.6 km] | Central Railway | 705504 | Maharashtra | 10/2017 | 03/2017 | 12/2025 | 03/2026 | 2081.27 | 3267.06 | 2861.77 | 92
October 2025 | 619 | Ministry of Railways | Railways | 4th Line Wardha - Nagpur [78.7 Kilometres] | Central Railway [CR] - II | 705505 | Maharashtra | 04/2017 | 05/2018 | 12/2025 | 02/2026 | 637.95 | 1341.28 | 1010.3 | 83
October 2025 | 620 | Ministry of Railways | Railways | 3rd Line Manmad - Jalgaon [160 Kilometres] | Central Railway [CR] - II | 705506 | Maharashtra | 05/2017 | 04/2018 | 12/2024 | 08/2025 | 1035.16 | 1558.75 | 1726.94 | 95
October 2025 | 621 | Ministry of Railways | Railways | Solapur-tuljapur-Osmanabad | Central Railway | 705735 | Maharashtra | 08/2018 | 12/2023 | 03/2027 | 03/2028 | 904.92 | 3295.74 | 1153.7 | 12
October 2025 | 622 | Ministry of Railways | Railways | Nagpur- Nagbhir Railway Line Gauge Conversion Project | MRIDC | 705799 | Maharashtra | 10/2019 | 04/2020 | 12/2025 | 12/2025 | 1400 | 1400 | 1472 | 80
October 2025 | 623 | Ministry of Railways | Railways | Mumbai Urban Transport Project [MUTP] - PHASE II | Mumbai Rail Vikas Corporation Ltd.[MRVC] | 706779 | Maharashtra | 05/2008 | 04/2008 | 03/2014 | 12/2027 | 8087 | 8087 | 7364 | 87
October 2025 | 624 | Ministry of Railways | Railways | Mumbai Urban Transport Project [MUTP] Phase-IIIA | Mumbai Rail Vikas Corporation Ltd.[MRVC] | 706780 | Maharashtra | 04/2019 | 04/2019 | 12/2027 | 12/2027 | 33690 | 33690 | 2436.22 | 16
October 2025 | 625 | Ministry of Railways | Railways | Mumbai Urban Transport Project Phase-III | Mumbai Rail Vikas Corporation Ltd.[MRVC] | 706781 | Maharashtra | 11/2016 | 12/2016 | 03/2022 | 12/2026 | 10947 | 10947 | 5460.49 | 65
October 2025 | 626 | Ministry of Railways | Railways | PACHORA-JAMNER WITH EXTENSION UPTO MALKAPUR NG TO BG | CR | 709808 | Maharashtra | 08/2022 | 01/2022 | 08/2027 | 03/2028 | 955.39 | 2093.82 | 130.42 | 11
October 2025 | 627 | Ministry of Railways | Railways | Jiribam-Imphal new line project | Northeast Frontier Railway [NFR] | 705391 | Manipur | 03/2013 | 12/2007 | 12/2026 | 06/2029 | 14323 | 21885.9 | 15598.11 | 69
October 2025 | 628 | Ministry of Railways | Railways | Marikuppam - Kuppam New Line Project [23.70 Km] | South Western Railway [SWR] - II | 705491 | Multi-States (Andhra Pradesh, Karnataka) | 04/2012 | 10/2018 | 06/2026 | 06/2026 | 297 | 297 | 134.31 | 15
October 2025 | 629 | Ministry of Railways | Railways | Rayadurg-Tumkur via Kalyandurg New Line [207 km] | South Western Railway [SWR] - II | 705494 | Multi-States (Andhra Pradesh, Karnataka) | 03/2008 | 07/2010 | 09/2015 | 02/2028 | 2496 | 2496 | 1739.53 | 69
October 2025 | 630 | Ministry of Railways | Railways | Renigunta, Wadi & Gooty Bypass Railway Project | South Central Railway [SCR] - I | 705610 | Multi-States (Andhra Pradesh, Karnataka) | 04/2016 | 04/2016 | 12/2025 | 12/2025 | 302 | 543 | 381 | 50
October 2025 | 631 | Ministry of Railways | Railways | Doubling between Mudkhed Medchal & Mahbubnagar Dhone section 417.88 Km | South Central Railway [SCR] - II | 617212 | Multi-States (Andhra Pradesh, Maharashtra, Telangana) | 08/2023 | 08/2023 | 03/2029 | - | 4686.09 | 4686.09 | 668.81 | 1
October 2025 | 632 | Ministry of Railways | Railways | Vizianagaram - Titlagarh 3rd line [272 Km including By - pass line of 7.68 KM] | RVNL - II | 400253 | Multi-States (Andhra Pradesh, Odisha) | 06/2016 | 11/2016 | 12/2026 | 12/2026 | 4803 | 6670 | 5722.01 | 89
October 2025 | 633 | Ministry of Railways | Railways | Doubling of Kottavalasa-Koraput Rail Line [189 KM] | East Coast Railway [ECoR] - II | 705512 | Multi-States (Andhra Pradesh, Odisha) | 12/2015 | 01/2016 | 03/2022 | 03/2028 | 2500 | 2500 | 2023.97 | 71
October 2025 | 634 | Ministry of Railways | Railways | Vizianagaram-Sambhalpur 3rd Line Project | RVNL | 705520 | Multi-States (Andhra Pradesh, Odisha) | 06/2016 | 12/2016 | 03/2025 | - | 4803.16 | 4803.16 | 2979.23 | 0
October 2025 | 635 | Ministry of Railways | Railways | Tindivanam-Nagari New Line Project [184.5 km] | Southern Railway [SR] - II | 400275 | Multi-States (Andhra Pradesh, Tamil Nadu) | 07/2008 | 10/2008 | 09/2016 | 03/2028 | 3631 | 3631 | 1113.53 | 18
October 2025 | 636 | Ministry of Railways | Railways | Doubling between Motumari Vishnupuram - 88.81 Km and Rail over Rail - RoR at Motumari - 10.877 Km | South Central Railway [SCR] - II | 616857 | Multi-States (Andhra Pradesh, Telangana) | 02/2024 | 03/2025 | 03/2029 | - | 1595.55 | 1595.55 | 14.27 | 1
October 2025 | 637 | Ministry of Railways | Railways | Doubling of Guntur Bibinagar 239 Km | South Central Railway [SCR] - II | 617211 | Multi-States (Andhra Pradesh, Telangana) | 08/2023 | 08/2023 | 03/2029 | - | 2853.23 | 2853.23 | 62.29 | 1
October 2025 | 638 | Ministry of Railways | Railways | Rail Connectivity to Errupalem Amravati Namburu 57 Km | South Central Railway [SCR] - II | 617214 | Multi-States (Andhra Pradesh, Telangana) | 11/2024 | 11/2024 | 03/2027 | - | 2047.4 | 2047.4 | 14.49 | 0
October 2025 | 639 | Ministry of Railways | Railways | Kazipet-Vijayawada 3rd line with electrification [220 km] | South Central Railway [SCR] - II | 705612 | Multi-States (Andhra Pradesh, Telangana) | 03/2013 | 08/2014 | 02/2025 | 12/2025 | 1953 | 3363 | 3436.15 | 94
October 2025 | 640 | Ministry of Railways | Railways | Vijayawada - Kazipet Byepass line | South Central Railway [SCR] - II | 705632 | Multi-States (Andhra Pradesh, Telangana) | 04/2016 | 04/2016 | 01/2025 | 12/2025 | 647 | 904 | 945.51 | 92
October 2025 | 641 | Ministry of Railways | Railways | Murkongselek-Pasighat | Northeast Frontier Railway (NFR) - II | 705401 | Multi-States (Arunachal Pradesh, Assam) | 02/2011 | 03/2023 | 03/2025 | 05/2026 | 435 | 1250 | 542.07 | 61
October 2025 | 642 | Ministry of Railways | Railways | Lumding Furkating Doubling Project 140 km | Northeast Frontier Railway [NFR] | 616701 | Multi-States (Assam, Nagaland) | 02/2024 | 01/2025 | 02/2028 | - | 2123.7 | 2123.7 | 13.74 | 0
October 2025 | 643 | Ministry of Railways | Railways | Dimapur [Dhansiri]-Sukhobi Kohima [Zubza] NL [82.5 Km] | Northeast Frontier Railway [NFR] | 705392 | Multi-States (Assam, Nagaland) | 08/2015 | 02/2016 | 03/2025 | 12/2025 | 6663 | 6663 | 5571.82 | 81
October 2025 | 644 | Ministry of Railways | Railways | New Delhi- Howrah Speed Booster[160Kmph] Project | PCE/NCR | 705794 | Multi-States (Bihar, Delhi, Jharkhand, Uttar Pradesh, West Bengal) | 09/2019 | 09/2019 | 03/2024 | - | 6684.81 | 6684.81 | 127.03 | 0
October 2025 | 645 | Ministry of Railways | Railways | Third Railway Line between Patratu-Sonnagar [281 kms] | RVNL - II | 400234 | Multi-States (Bihar, Jharkhand) | 11/2016 | 08/2018 | 03/2026 | 07/2026 | 8975 | 8975 | 4950 | 88
October 2025 | 646 | Ministry of Railways | Railways | Multi tracking of Son Nagar-Andal 374.53 rkm & 814.38 tkm | East Central Railway [ECR] - I | 616699 | Multi-States (Bihar, Jharkhand) | 08/2023 | 08/2023 | 03/2028 | - | 12333.57 | 12333.6 | 520.39 | 13
October 2025 | 647 | Ministry of Railways | Railways | Koderma-Tilaiya New Line | East Central Railway [ECR] - I | 705375 | Multi-States (Bihar, Jharkhand) | 11/2004 | 03/2002 | 02/2025 | 02/2026 | 1626 | 2486.62 | 2113.82 | 93
October 2025 | 648 | Ministry of Railways | Railways | Pirpainti - Jasidih [100.52 Km] New BG line | Eastern Railway [ER] - I | 705385 | Multi-States (Bihar, Jharkhand) | 03/2014 | 03/2022 | 03/2028 | 03/2028 | 2555 | 2555 | 780.18 | 49
October 2025 | 649 | Ministry of Railways | Railways | NER Provision of Automatic Block Signalling on Gorakhpur Cantt[Excl] Chhapra Gramin & Burhwal Jn [Excl] Sitapur Jn section of high density routes | North Eastern Railway [NER] | 611669 | Multi-States (Bihar, Uttar Pradesh) | NA | 06/2023 | 03/2027 | - | 380.47 | 380.47 | 24.53 | 0
October 2025 | 650 | Ministry of Railways | Railways | Gorakhpur-Valmikinagar Doubling project | NER | 617224 | Multi-States (Bihar, Uttar Pradesh) | 08/2023 | 03/2024 | 12/2027 | - | 1120 | 1120 | 247.46 | 26
October 2025 | 651 | Ministry of Railways | Railways | Chhapra-Ballia Patch Doubling | North Eastern Railway [NER] | 705562 | Multi-States (Bihar, Uttar Pradesh) | 03/2013 | 12/2015 | 02/2025 | 03/2026 | 963 | 1046 | 911.66 | 95
October 2025 | 652 | Ministry of Railways | Railways | Katihar - Kumedpur Doubling Line Project | GM/C/ NFR | 706844 | Multi-States (Bihar, West Bengal) | 08/2022 |  | 08/2027 | 08/2027 | 942 | 942 | 356 | 45
October 2025 | 653 | Ministry of Railways | Railways | Rajnandgaon - Nagpur [Kalumna] Third Railway Line [228.30 km] | South East Central Railway [SECR] - II | 705617 | Multi-States (Chhattisgarh, Maharashtra) | 09/2016 | 12/2016 | 12/2024 | 06/2026 | 3545 | 3545 | 3507.04 | 96
October 2025 | 654 | Ministry of Railways | Railways | Sardega -Bhalumuda New Double line [37.24 Km] | SECR | 617390 | Multi-States (Chhattisgarh, Odisha) | 09/2024 | 09/2024 | 03/2028 | - | 1281.81 | 1281.81 | 128 | 1
October 2025 | 655 | Ministry of Railways | Railways | Jagdalpur-Koraput | East Coast Railway [ECoR] - II | 705511 | Multi-States (Chhattisgarh, Odisha) | 12/2015 | 03/2016 | 03/2024 | 12/2026 | 1547 | 1547 | 1329.73 | 90
October 2025 | 656 | Ministry of Railways | Railways | Jharsuguda-Bilaspur Fourth Railway Line [206 km] | SECR | 705616 | Multi-States (Chhattisgarh, Odisha) | 09/2016 | 09/2016 | 10/2024 | 12/2025 | 2140 | 2979 | 2196.74 | 93
October 2025 | 657 | Ministry of Railways | Railways | Mumbai-Ahmedabad High Speed Rail Project- 508 km | National High Speed Rail Corporation [NHSRC] | 705728 | Multi-States (Dadra & Nagar Haveli and Daman & Diu, Gujarat, Maharashtra) | 03/2015 | 09/2017 | 08/2027 | 12/2029 | 108000 | 108000 | 82967.89 | 55
October 2025 | 658 | Ministry of Railways | Railways | New Delhi- Mumbai Speed Booster[160Kmph] Project | PCE/WR | 705793 | Multi-States (Delhi, Gujarat, Madhya Pradesh, Maharashtra, Rajasthan) | 09/2019 | 09/2019 | 03/2024 | - | 6806.44 | 6806.44 | 135.65 | 0
October 2025 | 659 | Ministry of Railways | Railways | Hospet - Tinaighat - Vasco Rail Doubling Project | RVNL - II | 705650 | Multi-States (Goa, Karnataka) | 03/2010 | 07/2012 | 03/2027 | 12/2027 | 5060 | 5060 | 5246.91 | 86
October 2025 | 660 | Ministry of Railways | Railways | Hospet-Hubli-Vasco da Gama Line Electrification Project | RVNL | 706950 | Multi-States (Goa, Karnataka) | 07/2015 | 05/2018 | 03/2023 | 03/2024 | 744.49 | 1122.62 | 969.05 | 95
October 2025 | 661 | Ministry of Railways | Railways | Western Dedicated Freight Corridor | DFCCIL | 705237 | Multi-States (Gujarat, Haryana, Maharashtra, Rajasthan, Uttar Pradesh) | 02/2008 | 01/2012 | 03/2022 | 12/2025 | 51101 | 124005 | 124623 | 96
October 2025 | 662 | Ministry of Railways | Railways | New line Dahod-Indore via Sardarpur, Jabuwa and Dhar | Western Railway [WR] - II | 705453 | Multi-States (Gujarat, Madhya Pradesh) | 06/2012 | 06/2012 | 02/2027 | 02/2027 | 456.07 | 3516.77 | 3633.27 | 49
October 2025 | 663 | Ministry of Railways | Railways | Chhota Udaipur - Dhar New Line Project [157 km] | Western Railway [WR] - II | 705454 | Multi-States (Gujarat, Madhya Pradesh) | 11/2008 | 01/2014 | 12/2025 | 12/2025 | 1794 | 1794 | 1815.94 | 80
October 2025 | 664 | Ministry of Railways | Railways | MUMBAI CENTRAL VIRAR VADODARA AHMEDABAAD TRAIN PROTECTION SYSTEM 500 RKM | Western Railway | 611452 | Multi-States (Gujarat, Maharashtra) | 09/2019 | 03/2023 | 12/2025 | 06/2025 | 311 | 311 | 208 | 92
October 2025 | 665 | Ministry of Railways | Railways | Taranga Hill-Abu Road via Ambaji | North Western Railway [NWR] | 400022 | Multi-States (Gujarat, Rajasthan) | 07/2022 | 07/2022 | 07/2030 | 07/2030 | 2798 | 2798 | 2014.6 | 17
October 2025 | 666 | Ministry of Railways | Railways | LUNI- SAMDARI- BHILDI DOUBLING | North Western Railway [NWR] | 616842 | Multi-States (Gujarat, Rajasthan) | 02/2024 | 02/2024 | 07/2027 | - | 3085.59 | 3085.59 | 329.31 | 13
October 2025 | 667 | Ministry of Railways | Railways | Chandigarh-Baddi New Rail Line- 36 km | Northen Railway [NR] | 705424 | Multi-States (Haryana, Himachal Pradesh) | 02/2018 | 02/2018 | 12/2026 | 12/2026 | 1540 | 1540.13 | 527.66 | 34
October 2025 | 668 | Ministry of Railways | Railways | Rewari - Kathuwas Doubling Project [27.72 Km] | North Western Railway [NWR] | 611861 | Multi-States (Haryana, Rajasthan) | 02/2023 | 12/2022 | 06/2027 | 06/2027 | 352 | 352 | 271.93 | 65
October 2025 | 669 | Ministry of Railways | Railways | Nangal Dam-Talwara New Broad Gauge Line [84 KM] and Taking Over Siding Mukerian-Talwara [29 KM] | Northen Railway [NR] | 705410 | Multi-States (Himachal Pradesh, Punjab) | 03/1983 | 05/1985 | 12/2025 | 01/2027 | 2018 | 2018 | 2053.9 | 45
October 2025 | 670 | Ministry of Railways | Railways | Bhanupalli-Bilaspur-Beri New Railway Line Project | RVNL - II | 705428 | Multi-States (Himachal Pradesh, Punjab) | 03/2009 | 04/2015 | 12/2026 | 12/2027 | 13447 | 13447 | 6928.81 | 61
October 2025 | 671 | Ministry of Railways | Railways | Doubling of Hatia [Ranchi]-Bondamunda Rail Line - 159 km | South Eastern Railway - JH | 705628 | Multi-States (Jharkhand, Odisha) | 03/2016 | 02/2017 | 06/2025 | 06/2026 | 3029 | 3029.04 | 2501.09 | 86
October 2025 | 672 | Ministry of Railways | Railways | Buramara-Chakulia new line [59.96 km] | South Eastern Railway [SER] - I | 616588 | Multi-States (Jharkhand, Odisha, West Bengal) | 08/2024 | 12/2024 | 12/2029 | - | 1459.13 | 1459.13 | 3.32 | 0
October 2025 | 673 | Ministry of Railways | Railways | KHARAGPUR-ADITYAPUR THIRD RAIL LINE- 132 KM | RVNL - I | 705668 | Multi-States (Jharkhand, West Bengal) | 09/2016 | 01/2018 | 03/2025 | 12/2025 | 3250 | 3250 | 3176.46 | 97
October 2025 | 674 | Ministry of Railways | Railways | Hotgi-Kudgi-Gadag Doubling Project | South Western Railway [SWR] - II | 705662 | Multi-States (Karnataka, Maharashtra) | 04/2014 | 01/2016 | 12/2024 | 03/2026 | 1878 | 2459 | 2684.66 | 92
October 2025 | 675 | Ministry of Railways | Railways | Baiyyappanahalli - Hosur Doubling Project [48 km] | Karnataka Rail Infrastructure Development Company Limited [K-RIDE] | 703586 | Multi-States (Karnataka, Tamil Nadu) | 04/2019 | 02/2019 | 03/2024 | 01/2026 | 498.7 | 748.7 | 630.41 | 86
October 2025 | 676 | Ministry of Railways | Railways | Trivandrum- Kanyakumari | Southern Railway (SR) - I | 705635 | Multi-States (Kerala, Tamil Nadu) | 08/2017 | 03/2016 | 03/2025 | 12/2026 | 1432 | 3785.45 | 2505.8 | 50
October 2025 | 677 | Ministry of Railways | Railways | Ratlam-Mhow-Khandwa-Akola Gauge Conversion | Western Railway [WR] - II | 705457 | Multi-States (Madhya Pradesh, Maharashtra) | 04/2008 | 03/2010 | 03/2027 | 09/2028 | 1656.25 | 6499.86 | 4445.82 | 81
October 2025 | 678 | Ministry of Railways | Railways | Itarsi - Nagpur Third Railway Line [280 km] | Central Railway (CR) - II | 705507 | Multi-States (Madhya Pradesh, Maharashtra) | 09/2016 | 09/2016 | 03/2027 | 03/2027 | 2449.91 | 2506.68 | 1850.73 | 51
October 2025 | 679 | Ministry of Railways | Railways | RATLAM- DUNGARPUR VIA BANSWARA NEW LINE PROJECT | North Western Railway [NWR] | 617406 | Multi-States (Madhya Pradesh, Rajasthan) | 10/2015 | 05/2023 | 03/2028 | - | 2417.24 | 2417.24 | 5.66 | 7
October 2025 | 680 | Ministry of Railways | Railways | Gwalior - Seopurkala with extension to Kota [Gauge Conversion] | North Central Railway | 705419 | Multi-States (Madhya Pradesh, Rajasthan) | 03/2011 | 07/2018 | 03/2025 | 02/2026 | 2913 | 2913 | 2109.86 | 84
October 2025 | 681 | Ministry of Railways | Railways | Ramganjmandi-Bhopal New Line Project [262 km] | West Central Railway [WCR] - II | 705481 | Multi-States (Madhya Pradesh, Rajasthan) | 03/2001 | 10/2004 | 12/2025 | 12/2027 | 3032 | 5073 | 3723.61 | 70
October 2025 | 682 | Ministry of Railways | Railways | Nimach-Badi Sadri New Rail Line Project | Western Railway [WR] - II | 705764 | Multi-States (Madhya Pradesh, Rajasthan) | 04/2017 | 09/2021 | 03/2026 | 06/2026 | 495 | 825 | 123.77 | 57
October 2025 | 683 | Ministry of Railways | Railways | Mathura-Jhansi Third Railway Line [274 Km] | RVNL - II | 705667 | Multi-States (Madhya Pradesh, Rajasthan, Uttar Pradesh) | 12/2015 | 03/2018 | 12/2024 | 12/2026 | 5961 | 5961 | 4964.19 | 94
October 2025 | 684 | Ministry of Railways | Railways | Jhansi - Bina Third Railway Line [153 Km] | CAO/C/NCR | 705598 | Multi-States (Madhya Pradesh, Uttar Pradesh) | 09/2016 | 03/2018 | 03/2022 | 03/2026 | 2002 | 2002 | 1806.86 | 93
October 2025 | 685 | Ministry of Railways | Railways | Jhansi-Khairar-Manikpur & Khirar-Bhimsen | North Central Railway | 705608 | Multi-States (Madhya Pradesh, Uttar Pradesh) | 03/2018 | 04/2019 | 03/2026 | 03/2026 | 4330 | 4330 | 2417.11 | 60
October 2025 | 686 | Ministry of Railways | Railways | Third Line [new] between Kazipet - Balharshah with electrification [201.04 Km] | South Central Railway [SCR] - II | 705613 | Multi-States (Maharashtra, Telangana) | 09/2016 | 10/2016 | 01/2025 | 11/2025 | 2595 | 3071 | 3396.31 | 94
October 2025 | 687 | Ministry of Railways | Railways | Narayangarh-Bhadrak 3rd line | South Eastern Railway [SER] - I | 705629 | Multi-States (Odisha, West Bengal) | 03/2019 | 03/2017 | 12/2025 | 06/2026 | 2400 | 2400 | 2311.95 | 66
October 2025 | 688 | Ministry of Railways | Railways | Nagapattinam-Tiruturaipundi and Karaikal-Peralam New Line | Southern Railway [SR] - II | 400223 | Multi-States (Puducherry, Tamil Nadu) | 07/2008 | 01/2019 | 03/2026 | 03/2027 | 713 | 981 | 598.38 | 80
October 2025 | 689 | Ministry of Railways | Railways | Sivok-Rangpo New Rail Line | Indian Railway Construction International Limited [IRCON] | 705432 | Multi-States (Sikkim, West Bengal) | 10/2009 | 05/2010 | 05/2015 | 12/2027 | 7877 | 12133 | 9039.91 | 84
October 2025 | 690 | Ministry of Railways | Railways | Sainthia, Sitarampur, Mughalsarai, Allahabad & Etawah - Bypass Line Project | Eastern Railway [ER] - I | 602797 | Multi-States (Uttar Pradesh, West Bengal) | 08/2017 | 12/2017 | 03/2027 | 03/2027 | 461.64 | 461.64 | 192.72 | 8
October 2025 | 691 | Ministry of Railways | Railways | Proposed 6 nos Road Over Bridge [ROB] at different locations under MCL Talcher Under Deposit Scheme. | East Coast Railway [ECoR] - II | 400045 | Odisha | 08/2022 | 07/2022 | 03/2025 | 01/2025 | 168.32 | 168.32 | 69.85 | 82
October 2025 | 692 | Ministry of Railways | Railways | Brundamal-Jharsuguda- flyover connection for joining downline | East Coast Railway [ECoR] - II | 400232 | Odisha | 01/2014 | 01/2014 | 12/2026 | 12/2026 | 297 | 297 | 193.22 | 30
October 2025 | 693 | Ministry of Railways | Railways | 3rd & 4th line between Sarla - Sason [8 km] [PB 73/2023-24/NR] | East Coast Railway [ECoR] - II | 612834 | Odisha | 04/2023 | 04/2023 | 12/2025 | - | 252 | 252 | 88.95 | 48
October 2025 | 694 | Ministry of Railways | Railways | Bangriposi-Gorumahisani new line [ 85.60 km ] | CAO/C/SER | 616586 | Odisha | 08/2024 | 09/2025 | 12/2029 | - | 2269.49 | 2269.49 | 3.06 | 0
October 2025 | 695 | Ministry of Railways | Railways | Badampahar-Kendujhargarh new line [82.06 km] | CAO/C/SER | 616587 | Odisha | 08/2024 | 09/2025 | 12/2029 | - | 1875.72 | 1875.72 | 0.91 | 0
October 2025 | 696 | Ministry of Railways | Railways | Paradeep - Badabandha 3rd & 4th Line / 18.51kms | East Coast Railway [ECoR] - II | 616695 | Odisha | 08/2023 | 04/2025 | 11/2028 | - | 300.15 | 300.15 | 0 | 0
October 2025 | 697 | Ministry of Railways | Railways | Jeypore - Malkangiri New BG Line Project | Indian Railways | 617290 | Odisha | NA | 02/2018 | 12/2030 | - | 2343.64 | 2343.64 | 630.83 | 13
October 2025 | 698 | Ministry of Railways | Railways | New B.G Railway Line between Jeypore & Navarangpur [38 Km] with Electrification | Indian Railway and Govt of Odisha | 617320 | Odisha | 07/2017 | 09/2022 | 09/2025 | - | 747.91 | 747.91 | 7.21 | 0
October 2025 | 699 | Ministry of Railways | Railways | Khurda-Bolangir New Broad Gauge Rail Link [301km] | East Coast Railway [ECoR] - II | 705358 | Odisha | 03/1994 | 03/2001 | 12/2026 | 12/2026 | 3792 | 5089 | 5147.89 | 89
October 2025 | 700 | Ministry of Railways | Railways | Talcher-Bimlagarh New Railway Line | East Coast Railway [ECoR] - II | 705359 | Odisha | 03/2004 | 12/2004 | 03/2025 | 03/2027 | 1928 | 1928 | 1955.9 | 48
October 2025 | 701 | Ministry of Railways | Railways | Bhadrak-Nergundi Third Line | East Coast Railway [ECoR] - II | 705510 | Odisha | 10/2015 | 04/2015 | 11/2024 | 01/2026 | 1284 | 1284 | 1298 | 80
October 2025 | 702 | Ministry of Railways | Railways | Koraput - Singapur Railway Doubling | East Coast Railway [ECoR] - II | 705513 | Odisha | 12/2015 | 12/2015 | 12/2027 | 03/2028 | 2362 | 2362 | 1825.42 | 70
October 2025 | 703 | Ministry of Railways | Railways | Jarapada- Budhapank with flyover at Talcher road 3rd and 4th Line | East Coast Railway [ECoR] - II | 705514 | Odisha | 11/2015 | 12/2015 | 11/2018 | 03/2026 | 1000 | 810.02 | 415.46 | 58
October 2025 | 704 | Ministry of Railways | Railways | 3rd & 4th Railway Line Project from Salegaon to Budhapank via Rajathgarh. | East Coast Railway [ECoR] - II | 705515 | Odisha | 07/2013 | 12/2015 | 03/2026 | 03/2026 | 1173 | 2092 | 1971 | 80
October 2025 | 705 | Ministry of Railways | Railways | Jeypore-Navarangpur New Rail Line Project | East Coast Railway [ECoR] - II | 705741 | Odisha | 07/2017 | 04/2023 | 07/2028 | 12/2029 | 748 | 748 | 12.06 | 1
October 2025 | 706 | Ministry of Railways | Railways | Jeypore-Malkanagiri New Railway Line Project | East Coast Railway [ECoR] - II | 705742 | Odisha | 02/2018 | 12/2023 | 07/2033 | 07/2033 | 2344 | 2344 | 489.57 | 20
October 2025 | 707 | Ministry of Railways | Railways | Khurda Road - Balangir Electrification of Railway Track Project | Ministry of Railways | 706898 | Odisha | 09/2018 | 09/2019 | 03/2021 | - | 267.61 | 267.61 | 0 | 0
October 2025 | 708 | Ministry of Railways | Railways | Godhani-Kalumna Chord 13.7 km | Ministry of Railways | 617321 | Offshore | 07/2018 | 07/2018 | 07/2028 | - | 150000 | 150000 | 1940 | 11
October 2025 | 709 | Ministry of Railways | Railways | Jaynagar-Bijalpura, incl. extn. Bet, Bijalpura-Bardibas [Nepal] | East Central Railway [ECR] - I | 705362 | Offshore | 08/2015 | 03/2011 | 03/2022 | 03/2026 | 819 | 819 | 580.51 | 75
October 2025 | 710 | Ministry of Railways | Railways | Ludhiana- Killa Raipur Railway Doubling Project | Railway | 705783 | Punjab | 03/2019 | 12/2022 | 03/2025 | 03/2026 | 237.64 | 238 | 134.48 | 50
October 2025 | 711 | Ministry of Railways | Railways | Dedicated Test Track for RDSO Phase II | North Western Railway [NWR] | 611614 | Rajasthan | 11/2021 | 11/2021 | 11/2026 | 11/2026 | 819.48 | 967.06 | 471 | 86
October 2025 | 712 | Ministry of Railways | Railways | Devgarh Madariya - Nathdwara Gauge Conversion [82.54 Km] part of Marwar - Mavli Gauge Conversion [152 Km] | North Western Railway [NWR] | 611849 | Rajasthan | 01/2023 | 01/2023 | 06/2028 | 06/2028 | 968.92 | 968.92 | 137.16 | 51
October 2025 | 713 | Ministry of Railways | Railways | Maintenance cum workshop depot for Vande Bharat Sleeper Trains as per conditions under WTA 527 | WPO/Patna | 611929 | Rajasthan | 09/2022 | 06/2023 | 12/2024 | - | 166.86 | 166.86 | 0 | 0
October 2025 | 714 | Ministry of Railways | Railways | PUSHKAR- MERTA CITY NEW LINE | North Western Railway [NWR] | 616841 | Rajasthan | 02/2024 | 02/2024 | 12/2026 | - | 799.64 | 799.64 | 14.64 | 4
October 2025 | 715 | Ministry of Railways | Railways | AJMER- CHANDERIYA DOUBLING | North Western Railway [NWR] | 616843 | Rajasthan | 02/2024 | 02/2024 | 06/2027 | - | 1634.79 | 1634.79 | 123.05 | 7
October 2025 | 716 | Ministry of Railways | Railways | SADULPUR - CHURU DOUBLING PROJECT | North Western Railway [NWR] | 617403 | Rajasthan | 01/2024 | 01/2024 | 06/2026 | - | 468.64 | 468.64 | 125.08 | 50
October 2025 | 717 | Ministry of Railways | Railways | POKHRAN - RAMDEVRA New Line | North Western Railway [NWR] | 617404 | Rajasthan | 04/2025 | 04/2025 | 03/2028 | - | 189.21 | 189.21 | 0 | 0
October 2025 | 718 | Ministry of Railways | Railways | NATHDWARA- NATHDWARA TOWN NL | North Western Railway [NWR] | 617408 | Rajasthan | 03/2019 | 04/2024 | 03/2027 | - | 166.33 | 166.33 | 81.41 | 1
October 2025 | 719 | Ministry of Railways | Railways | Dholpur - Sirmuttra Gauge Conversion | North Central Railway | 705482 | Rajasthan | 03/2022 | 04/2020 | 02/2019 | 02/2027 | 747 | 747 | 378.05 | 44
October 2025 | 720 | Ministry of Railways | Railways | Gudha-Thatha Mithri Construction of Railway Track Project | North Western Railway [NWR] | 705752 | Rajasthan | 04/2019 | 04/2019 | 11/2026 | 11/2026 | 819.48 | 967.06 | 384.28 | 99
October 2025 | 721 | Ministry of Railways | Railways | Sawai Madhopur-Jaipur Railway Line Project | North Western Railway [NWR] | 705912 | Rajasthan | 02/2024 | 04/2023 | 03/2027 | - | 1203.89 | 1203.89 | 94.76 | 12
October 2025 | 722 | Ministry of Railways | Railways | Agra Fort-Bandikui Doubling Line Project | CAO/C/NCR | 705919 | Rajasthan | 06/2022 | 02/2021 | 06/2027 | 06/2027 | 1390 | 1390 | 123 | 25
October 2025 | 723 | Ministry of Railways | Railways | Sawaimadhopur Bye Pass Line Project | North Western Railway [NWR] | 706866 | Rajasthan | 12/2022 | 01/2023 | 03/2026 | 05/2027 | 304 | 304 | 51.64 | 45
October 2025 | 724 | Ministry of Railways | Railways | Ph II extension of MRTS from Velachery to St Thomas Mount | Southern Railways [SR] - construction | 400280 | Tamil Nadu | 11/2007 | 11/2008 | 07/2024 | 08/2025 | 734 | 982 | 475.73 | 99
October 2025 | 725 | Ministry of Railways | Railways | Redevelopment of Chennai Egmore Station | Railway | 613002 | Tamil Nadu | 05/2022 | 10/2022 | 03/2026 | - | 842 | 842 | 340 | 0
October 2025 | 726 | Ministry of Railways | Railways | Coach Production Factory Upgradation Project | CPM/ICF | 705244 | Tamil Nadu | 12/2017 | 07/2018 | 12/2021 | - | 520 | 520 | 192.25 | 0
October 2025 | 727 | Ministry of Railways | Railways | Doubling between Bhadrachalam Road and Dornakal | South Central Railway [SCR] - II | 616856 | Telangana | 08/2023 | 04/2025 | 04/2029 | - | 770.12 | 770.12 | 16.34 | 0
October 2025 | 728 | Ministry of Railways | Railways | Railway Manufacturing Unit | South Central Railway [SCR] - II | 617409 | Telangana | 07/2016 | 02/2023 | 12/2026 | - | 521.36 | 521.36 | 420 | 58
October 2025 | 729 | Ministry of Railways | Railways | Kazipet Wagon Overhauling Project | RVNL | 705252 | Telangana | 09/2017 | 07/2017 | 12/2023 | - | 385 | 385 | 0 | 0
October 2025 | 730 | Ministry of Railways | Railways | Manoharabad-Kothapalli New Rail Line [151 km] | South Central Railway [SCR] - II | 705437 | Telangana | 07/2016 | 01/2017 | 03/2027 | 12/2027 | 1160 | 2781 | 1985.73 | 71
October 2025 | 731 | Ministry of Railways | Railways | Bahraich-Shravasti-Balrampur-Siddharthnagar -Santkabir nagar | North Eastern Railway [NER] | 400204 | Uttar Pradesh | 10/2018 | 03/2017 | 10/2030 | 10/2030 | 4939.78 | 4939.78 | 1251.81 | 8
October 2025 | 732 | Ministry of Railways | Railways | Sahjanwa-Dohrighat | North Eastern Railway [NER] | 400205 | Uttar Pradesh | 08/2019 | 03/2017 | 03/2029 | 03/2029 | 1319.75 | 1319.75 | 475.67 | 3
October 2025 | 733 | Ministry of Railways | Railways | Anandnagar - Ghugli via Maharajganj New line 52.7 km | Construction NER | 617252 | Uttar Pradesh | 10/2023 | 11/2023 | 03/2028 | - | 958.27 | 958.27 | 449.37 | 23
October 2025 | 734 | Ministry of Railways | Railways | Chunar-Chopan doubling project | North Central Railway | 617284 | Uttar Pradesh | 08/2023 | 01/2025 | 03/2028 | - | 1423.96 | 1423.96 | 53.81 | 4
October 2025 | 735 | Ministry of Railways | Railways | Surface triangle line bet. Bhadura stn and new crossing stn Karma | East Central Railway [ECR] - I | 617333 | Uttar Pradesh | 10/2022 | 05/2024 | 02/2027 | - | 199.96 | 199.96 | 0 | 0
October 2025 | 736 | Ministry of Railways | Railways | Doubling between Jaunpur Jn - Zaffarabad 6.28 km | M/S SRC company Infra Private Limited | 617370 | Uttar Pradesh | 03/2023 | 02/2025 | 01/2027 | - | 180.66 | 180.66 | 4 | 11
October 2025 | 737 | Ministry of Railways | Railways | Burhwal Gonda 3rd line | North Eastern Railway [NER] | 705567 | Uttar Pradesh | 11/2017 | 07/2019 | 03/2025 | 01/2026 | 1016 | 1118 | 1410.08 | 88
October 2025 | 738 | Ministry of Railways | Railways | Janghai-Pratapgarh- Amethi | CAO/C/II/NR | 705588 | Uttar Pradesh | 11/2017 | 03/2017 | 03/2025 | 03/2026 | 722 | 1194 | 1567 | 70
October 2025 | 739 | Ministry of Railways | Railways | Lalitpur-Birari with flyover at Lalitpur- 16 Km | North Central Railway | 705766 | Uttar Pradesh | 03/2017 | 11/2017 | 12/2024 | 01/2026 | 304.44 | 356 | 231.37 | 78
October 2025 | 740 | Ministry of Railways | Railways | Allahabad-Bamhrauli Flyover Construction & 4th Railway Line Project | North Central Railway | 705771 | Uttar Pradesh | 04/2019 | 10/2020 | 03/2026 | 03/2026 | 494 | 494 | 333 | 70
October 2025 | 741 | Ministry of Railways | Railways | Mughalsarai-Allahabad, 3rd line | North Central Railway | 705772 | Uttar Pradesh | 12/2015 | 03/2016 | 12/2026 | 03/2027 | 2649 | 2649.44 | 1561.89 | 62
October 2025 | 742 | Ministry of Railways | Railways | Aligarh -Daud Khan Flyover Construction & 3rd Railway Line Project | CAO/C/NCR | 705774 | Uttar Pradesh | 04/2019 | 09/2020 | 01/2025 | 03/2027 | 758 | 779.49 | 387.73 | 69
October 2025 | 743 | Ministry of Railways | Railways | Bhandai - Flyover for Etawah bound down train- 10 Km | North Central Railway (NCR) - II | 705777 | Uttar Pradesh | 07/2020 | 04/2021 | 02/2026 | 02/2027 | 250.18 | 250.18 | 115.05 | 8
October 2025 | 744 | Ministry of Railways | Railways | Phephna-Indara, Mau-Shahganj doubling excluding Indara-Mau | RVNL - I | 705779 | Uttar Pradesh | 05/2017 | 10/2019 | 12/2024 | 03/2026 | 1178 | 1777 | 1489.5 | 85
October 2025 | 745 | Ministry of Railways | Railways | Bhatni-Aurnihar with electrification excluding Indara-Mau | RVNL - I | 705780 | Uttar Pradesh | 03/2018 | 03/2017 | 12/2024 | 10/2025 | 2529 | 2529.46 | 2051.69 | 94
October 2025 | 746 | Ministry of Railways | Railways | Barabanki-Malhaur 3rd & 4th Railway Line Project | CAO/C/NR | 705782 | Uttar Pradesh | 01/2019 | 04/2017 | 03/2025 | 03/2026 | 407 | 407 | 317 | 75
October 2025 | 747 | Ministry of Railways | Railways | Janghai-Phaphamau Doubling Rail Line Project | RVNL | 705784 | Uttar Pradesh | 11/2018 | 03/2020 | 03/2025 | 03/2025 | 357 | 978.77 | 579 | 95
October 2025 | 748 | Ministry of Railways | Railways | Rishikesh-Karnaprayag New Rail Line- 125 km | RVNL - I | 705429 | Uttarakhand | 11/2016 | 08/2018 | 12/2025 | 03/2027 | 38953 | 38953 | 24645.15 | 65
October 2025 | 749 | Ministry of Railways | Railways | Kalinarayanpur-Krishnanagar Doubling Alongwith Krishnanagar - Chapra New Line And Naihati-Ranaghat 3rd Line. | Eastern Railway [ER] - I | 400247 | West Bengal | 07/2015 | 11/2005 | 02/2027 | 02/2027 | 1000 | 1000 | 1053.4 | 69
October 2025 | 750 | Ministry of Railways | Railways | Tarakeshwar-Bishnupur New Line [82.47 km] | Eastern Railway [ER] - I | 400273 | West Bengal | 03/2001 | 02/2008 | 03/2019 | 02/2026 | 1189 | 1542 | 1323.68 | 91
October 2025 | 751 | Ministry of Railways | Railways | Dum Dum Airport-New Garia via Rajarhat-Construction of Metro Railway | RVNL - II | 400277 | West Bengal | 03/2010 | 10/2011 | 12/2025 | 03/2026 | 8964 | 8964 | 8316.32 | 81
October 2025 | 752 | Ministry of Railways | Railways | Construction of Balurghat-Hilli new BG Line | Northeast Frontier Railway [NFR] | 612096 | West Bengal | 12/2010 | 12/2010 | 03/2027 | 03/2025 | 1209 | 1209 | 405.31 | 9
October 2025 | 753 | Ministry of Railways | Railways | SER Upgradation of maintenance infrastructure at Shalimar into Vande Bharat Chair Car maintenance cum workshop depot. | South Eastern Railway - JH | 617345 | West Bengal | NA | 12/2024 | 10/2026 | - | 226.87 | 226.87 | 0.21 | 5
October 2025 | 754 | Ministry of Railways | Railways | Joka-BBD Bag new metro project | RVNL - II | 705730 | West Bengal | 03/2010 | 04/2010 | 12/2026 | 12/2029 | 4835 | 10362 | 4634.68 | 59
October 2025 | 755 | Ministry of Railways | Railways | Noapara-Barasat via Bimanbandar - Construction of Metro railway [18 km] | Metro Railway, Kolkata | 706776 | West Bengal | 11/2010 | 03/2010 | 08/2026 | 03/2029 | 4830 | 4830 | 2764.13 | 32
October 2025 | 756 | Ministry of Railways | Railways | Baranagar-Barrackpore and Dakshineshwar- Construction of Metro Railway | RVNL - II | 706777 | West Bengal | 03/2010 | 03/2010 | 12/2026 | 12/2025 | 2298 | 2734 | 393.01 | 17
October 2025 | 757 | Department for Promotion of Industry & Internal Trade | Real Estate | Krishnapatnam Node - Phase 1 - Roads and Services Development | National Industrial Corridor Development Corporation | 701658 | Andhra Pradesh | 12/2020 | 02/2024 | 02/2028 | - | 2139.44 | 2139.44 | 472.8 | 21
October 2025 | 758 | Department for Promotion of Industry & Internal Trade | Real Estate | Tumakuru Node - Phase 1 - Roads and Services Development | National Highways & Infrastructure Development Corporation Ltd. [NHIDCL] | 701657 | Karnataka | 12/2020 | 02/2023 | 09/2026 | - | 1701.81 | 1701.81 | 117.35 | 10
October 2025 | 759 | Department of Telecommunications | Telecommunication | SETTING UP OF PHYSICAL INFRASTRUCTURE FOR THE NATIONAL INSTITUTE OF COMMUNICATION FINANCE [NICF] AT GHITORNI | National Communication Academy - Finance (Erstwhile NICF | 709859 | Delhi | 10/2014 | 04/2018 | 02/2020 | 10/2025 | 248.2 | 248.2 | 236.91 | 98
October 2025 | 760 | Department of Telecommunications | Telecommunication | Provision of 4G based Mobile Services in Uncovered Villages and National Highways of Meghalaya | Department of Telecommunications | 701598 | Meghalaya | 09/2019 | 09/2020 | 03/2022 | 03/2026 | 971.96 | 971.96 | 208.25 | 99
October 2025 | 761 | Department of Telecommunications | Telecommunication | Mobile connectivity in Left Wing Extremism [LWE] affected areas-Phase 1 Upgradation | Department of Telecommunications [DoT] | 617413 | Multi-States (Andhra Pradesh, Bihar, Chhattisgarh, Jharkhand, Madhya Pradesh, Maharashtra, Odisha, Telangana, Uttar Pradesh, West Bengal) | 04/2022 | 05/2024 | 05/2025 | 11/2025 | 1884.6 | 1884.6 | 100 | 67
October 2025 | 762 | Department of Telecommunications | Telecommunication | Mobile connectivity in Left Wing Extremism [LWE] affected areas-Phase2 | Department of Telecommunications [DoT] | 701599 | Multi-States (Andhra Pradesh, Bihar, Chhattisgarh, Jharkhand, Madhya Pradesh, Maharashtra, Odisha, Telangana, Uttar Pradesh, West Bengal) | NA | 09/2021 | 03/2023 | 11/2025 | 1577.57 | 1577.57 | 600.6 | 87
October 2025 | 763 | Department of Telecommunications | Telecommunication | Provision of 4G based mobile services in 7,287 uncovered villages of 44 Aspirational District across 5 states of Andhra Pradesh, Chhattisgarh, Jharkhand, Maharashtra & Odisha | Department of Telecommunications [DoT] | 701602 | Multi-States (Andhra Pradesh, Chhattisgarh, Jharkhand, Maharashtra, Odisha) | 11/2021 | 05/2022 | 11/2023 | 11/2025 | 3685 | 3685 | 1135.28 | 81
October 2025 | 764 | Department of Telecommunications | Telecommunication | Provision of 4G Mobile Services in Uncovered Villages of Arunachal Pradesh and 2 Districts of Assam | Department of Telecommunications | 701597 | Multi-States (Arunachal Pradesh, Assam) | 12/2020 | 10/2021 | 04/2023 | 03/2026 | 1255.49 | 1255.49 | 284.04 | 91
October 2025 | 765 | Department of Telecommunications | Telecommunication | 354 Uncovered Villages Scheme | Department of Telecommunications [DoT] | 701600 | Multi-States (Bihar, Gujarat, Himachal Pradesh, Jammu and Kashmir, Ladakh, Rajasthan, Uttar Pradesh) | 12/2019 | 04/2020 | 10/2021 | 08/2025 | 336.89 | 301.13 | 227.82 | 97
October 2025 | 766 | Department of Telecommunications | Telecommunication | 502 Aspirational District Scheme in Four states - Bihar, Madhya Pradesh, Rajastha and Uttar Pradesh | Department of Telecommunications [DoT] | 704495 | Multi-States (Bihar, Madhya Pradesh, Rajasthan, Uttar Pradesh) | NA | 03/2021 | 03/2022 | 12/2025 | 421.65 | 228.94 | 142.01 | 96
October 2025 | 767 | Department of Telecommunications | Telecommunication | PHASE-I OF CONSOLIDATION OF EXISTING CDR DATA CENTERS AND NIB-P3 DATA CENTERS WITH STATE OF THE ART | BSNL | 709749 | Multi-States (Maharashtra, Telangana) | 03/2020 | 03/2020 | 06/2021 | 12/2025 | 461.42 | 461.42 | 166.02 | 81
October 2025 | 768 | Department of Telecommunications | Telecommunication | Saturation 4G mobile coverage of Uncovered Villages through USOF | Department of Telecommunications [DoT] | 400013 | PAN India | 07/2022 | 07/2022 | 06/2024 | 03/2026 | 26316 | 30620 | 9791.8 | 76
October 2025 | 769 | Department of Telecommunications | Telecommunication | 4G Services by BSNL | Department of Telecommunications [DoT] | 701593 | PAN India | 11/2020 | 11/2020 | 03/2024 | 03/2026 | 28466 | 19592 | 8419.04 | 96
October 2025 | 770 | Department of Telecommunications | Telecommunication | BharatNet | Department of Telecommunications [DoT] | 706775 | PAN India | 07/2017 | 10/2011 | 08/2023 | 03/2027 | 61109 | 188000 | 46431.54 | 81
October 2025 | 771 | Department of Telecommunications | Telecommunication | MPLS-IP BASED ACCESS AND AGGREGATION NETWORK [MAAN] IN BSNL ALONG WITH TEST AND MEASURING EQUIPMENT | BSNL | 709856 | PAN India | 05/2023 | 05/2023 | 08/2024 | 10/2025 | 645.13 | 645.13 | 377.27 | 92
October 2025 | 772 | Department of Telecommunications | Telecommunication | Planning, Engineering, Supply, Installation, Testing, Commissioning, Integration & Annual Maintenance of 4G mobile network at 1 Lakh sites on PAN India basis including Mumbai & Delhi LSA on turnkey basis under Phase IX.2 Project. | BSNL | 709857 | PAN India | 05/2023 | 06/2023 | 06/2025 | 03/2026 | 24544.55 | 24544.5 | 8448.06 | 97
October 2025 | 773 | Department of Telecommunications | Telecommunication | OPTICAL TRANSPORT NETWORK [OTN] PH-4 IN BSNL | BSNL | 709858 | PAN India | 02/2024 | 02/2024 | 08/2025 | 11/2025 | 810.99 | 810.99 | 786.3 | 100
October 2025 | 774 | Department of Water Resources, River Development & GR | Waste & Water | Interception and Diversion and STP works in Bhagalpur under Hybrid annuity based PPP mode-Namami Gange Programme | National Mission for Clean Ganga | 616600 | Bihar | 10/2017 | 03/2022 | 02/2025 | 12/2025 | 413.29 | 413.29 | 126.67 | 97
October 2025 | 775 | Department of Water Resources, River Development & GR | Waste & Water | Sewage Treatment Plant 100MLD and Sewerage Network 288 km in Digha-Patna under Hybrid annuity based PPP mode-Namami Gange Programme | National Mission for Clean Ganga | 616611 | Bihar | 08/2017 | 07/2019 | 12/2025 | - | 824 | 824 | 396.71 | 56
October 2025 | 776 | Department of Water Resources, River Development & GR | Waste & Water | Sewage Treatment Plant 50MLD and Sewerage Network 150 km in Kankarbagh- Patna under Hybrid annuity based PPP mode-Namami Gange Programme | National Mission for Clean Ganga | 616612 | Bihar | 08/2017 | 07/2019 | 12/2025 | - | 578.89 | 578.89 | 171.79 | 54
October 2025 | 777 | Department of Water Resources, River Development & GR | Waste & Water | Sewer Network, SPS and STP at Begusarai | National Mission for Clean Ganga | 616615 | Bihar | 03/2010 | 03/2018 | 04/2025 | 12/2025 | 230.06 | 230.06 | 261.82 | 97
October 2025 | 778 | Department of Water Resources, River Development & GR | Waste & Water | Sewer Networks, SPS and STP at Hajipur | National Mission for Clean Ganga | 616616 | Bihar | 03/2010 | 03/2018 | 06/2025 | 12/2025 | 305.19 | 305.19 | 346.46 | 95
October 2025 | 779 | Department of Water Resources, River Development & GR | Waste & Water | Interception & Diversion with Rehabilitation of sewerage scheme at Agra under Hybrid annuity based PPP model-Namami Gange Programme | National Mission for Clean Ganga | 616594 | Uttar Pradesh | 05/2020 | 04/2023 | 04/2025 | 12/2025 | 842.25 | 842.25 | 208.64 | 75
October 2025 | 780 | Department of Water Resources, River Development & GR | Waste & Water | Pollution Abatement Works for River Kali Meerut under Meerut Municipality Interception & Diversion with STP | National Mission for Clean Ganga | 616605 | Uttar Pradesh | 05/2020 | 11/2024 | 12/2024 | 05/2027 | 690.71 | 690.71 | 34.79 | 34
October 2025 | 781 | Department of Water Resources, River Development & GR | Waste & Water | Pollution Abatement works for River Ganga at Hooghly Chinsurah- Municipal Town Interception & Diversion with STP | National Mission for Clean Ganga | 616604 | West Bengal | 05/2018 | 12/2021 | 03/2025 | 12/2025 | 154.73 | 154.73 | 96.17 | 92
October 2025 | 782 | Department of Water Resources, River Development & GR | Water Resources | Sardar Gouthu Latchanna Thotapalli Barrage Project | Water Resources-AP | 400100 | Andhra Pradesh | 04/2005 | 01/2006 | 12/2019 | 06/2026 | 353.05 | 1023.24 | 869.11 | 95
October 2025 | 783 | Department of Water Resources, River Development & GR | Water Resources | Gundlakamma project | Water Resources-AP | 400101 | Andhra Pradesh | 04/2005 | 04/2005 | 12/2019 | 03/2027 | 397.41 | 697.39 | 619.09 | 98
October 2025 | 784 | Department of Water Resources, River Development & GR | Water Resources | Polavaram Irrigation Project | Water Resources-AP | 701415 | Andhra Pradesh | 01/2009 | 11/2009 | 04/2022 | 03/2026 | 10151.04 | 55548.9 | 24837.97 | 84
October 2025 | 785 | Department of Water Resources, River Development & GR | Water Resources | Borolia Irrigation Project | Department of Water Resources, River Development & GR | 701370 | Assam | 04/1996 | 12/1996 | 12/2022 | 03/2026 | 256.16 | 256.16 | 44.7 | 55
October 2025 | 786 | Department of Water Resources, River Development & GR | Water Resources | Punpun Barrage Project | Water Resources-BR | 400104 | Bihar | 04/2007 | 04/2007 | 12/2019 | 03/2026 | 571.07 | 658.12 | 447.68 | 44
October 2025 | 787 | Department of Water Resources, River Development & GR | Water Resources | Kelo Irrigation Project | Water Resources-CT | 400111 | Chhattisgarh | 04/2008 | 04/2008 | 12/2019 | 06/2026 | 459.97 | 727.04 | 616.93 | 72
October 2025 | 788 | Department of Water Resources, River Development & GR | Water Resources | Kudali Irrigation Project | Department of Water Resources, River Development & GR | 701399 | Chhattisgarh | 04/2009 | 12/2009 | 12/2025 | - | 382.29 | 382.29 | 239.03 | 86
October 2025 | 789 | Department of Water Resources, River Development & GR | Water Resources | Sardar Sarovar CADWM Project | Narmada and Water Resources, Water Supply and Kalpsar Department-GJ | 400097 | Gujarat | 04/2017 | 04/2017 | 12/2019 | 03/2026 | 5021.76 | 6670.31 | 4954.99 | 90
October 2025 | 790 | Department of Water Resources, River Development & GR | Water Resources | Sardar Sarovar Project | Narmada and Water Resources, Water Supply and Kalpsar Department-GJ | 701372 | Gujarat | 04/1996 | 04/1996 | 12/2019 | 03/2026 | 20718.17 | 33412.5 | 31860.86 | 93
October 2025 | 791 | Department of Water Resources, River Development & GR | Water Resources | Subernarekha Multipurpose Project, Jharkhand | Department of Water Resources-JH | 701376 | Jharkhand | 04/2011 | 01/2012 | 12/2019 | 03/2026 | 3807.77 | 9579.58 | 5790.29 | 70
October 2025 | 792 | Department of Water Resources, River Development & GR | Water Resources | Upper Tunga Irrigation Project | Water Resources-KA | 701377 | Karnataka | 04/2014 | 04/2014 | 12/2019 | 03/2026 | 770.16 | 1606.07 | 1515.32 | 99
October 2025 | 793 | Department of Water Resources, River Development & GR | Water Resources | Omkareshwar CADWM Project | Water resource-mp | 400096 | Madhya Pradesh | 04/2017 | 04/2017 | 12/2019 | 03/2026 | 648.09 | 648.09 | 172.56 | 3
October 2025 | 794 | Department of Water Resources, River Development & GR | Water Resources | Bargi Diversion Project Phase - IV [km. 154 to km 197] | Water Resources-MP | 400115 | Madhya Pradesh | 04/2008 | 01/2009 | 12/2019 | 03/2026 | 751.03 | 893.35 | 783.1 | 75
October 2025 | 795 | Department of Water Resources, River Development & GR | Water Resources | Bargi Diversion Project Phase - III [km. 104 to km 154] | Water Resources-MP | 400116 | Madhya Pradesh | 04/2007 | 04/2007 | 12/2019 | 03/2026 | 1229.15 | 1399.7 | 1937.25 | 80
October 2025 | 796 | Department of Water Resources, River Development & GR | Water Resources | Gosikhurd CADWM Project | Department of water resources-MH - II | 400095 | Maharashtra | 04/2017 | 04/2017 | 12/2019 | 06/2026 | 743.73 | 743.73 | 295.12 | 52
October 2025 | 797 | Department of Water Resources, River Development & GR | Water Resources | Urmodi Irrigation Project | Department of water resources-MH - II | 400105 | Maharashtra | 04/2017 | 04/2018 | 06/2022 | 12/2026 | 580.79 | 895.81 | 713.46 | 76
October 2025 | 798 | Department of Water Resources, River Development & GR | Water Resources | Sulwade-Jamphal-Kanoli Lift Irrigation Scheme | Department of water resources-MH - II | 400107 | Maharashtra | 04/2017 | 02/2019 | 06/2023 | 06/2027 | 2407.67 | 2407.67 | 2570.94 | 80
October 2025 | 799 | Department of Water Resources, River Development & GR | Water Resources | Purna Barrage-2 [Ner Dhamana] Medium Irrigation Project | Department of water resources-MH - II | 400109 | Maharashtra | 04/2017 | 04/2018 | 06/2020 | 06/2026 | 848.07 | 888.43 | 690.49 | 69
October 2025 | 800 | Department of Water Resources, River Development & GR | Water Resources | Jigaon Irrigation Project | Department of water resources-MH - II | 400112 | Maharashtra | 04/2017 | 04/2018 | 06/2028 | - | 7222.95 | 7222.95 | 8722.81 | 90
October 2025 | 801 | Department of Water Resources, River Development & GR | Water Resources | Bodwad Parisar Sinchan Yojna | Department of Water Resources-MH | 617422 | Maharashtra | 05/2002 | 01/2017 | 07/2027 | - | 1923.81 | 1923.81 | 1770.13 | 49
October 2025 | 802 | Department of Water Resources, River Development & GR | Water Resources | Waghur Project | Department of water resources-MH - II | 701383 | Maharashtra | 04/1996 | 04/1996 | 12/2019 | 03/2026 | 1058.99 | 1758.51 | 1557.45 | 89
October 2025 | 803 | Department of Water Resources, River Development & GR | Water Resources | Gosikhurd Project | Department of water resources-MH - II | 701386 | Maharashtra | 04/2008 | 04/2008 | 12/2019 | 06/2028 | 7196.47 | 12770.1 | 13765.22 | 72
October 2025 | 804 | Department of Water Resources, River Development & GR | Water Resources | Aruna Medium Irrigation Project | Department of water resources-MH - II | 701391 | Maharashtra | 04/2009 | 01/2010 | 12/2019 | 12/2025 | 210.45 | 1472.14 | 1697.94 | 97
October 2025 | 805 | Department of Water Resources, River Development & GR | Water Resources | Lower Pedhi Project | Department of water resources-MH - II | 701396 | Maharashtra | 04/2008 | 04/2008 | 12/2019 | 06/2026 | 255.97 | 1480.7 | 1324.98 | 65
October 2025 | 806 | Department of Water Resources, River Development & GR | Water Resources | Nardave Medium Irrigation Project | Department of water resources-MH - II | 701398 | Maharashtra | 04/2009 | 04/2009 | 12/2019 | 06/2026 | 211.46 | 781.85 | 623.5 | 72
October 2025 | 807 | Department of Water Resources, River Development & GR | Water Resources | Thoubal Multipurpose Project | Water Resources Department-MN | 701400 | Manipur | 04/1997 | 04/1997 | 12/2019 | 03/2026 | 1449.44 | 1822.24 | 1837.91 | 98
October 2025 | 808 | Department of Water Resources, River Development & GR | Water Resources | North Koel Reservoir Project | Department of Water Resources, River Development & GR | 701412 | Multi-States (Bihar, Jharkhand) | 08/2017 | 01/2021 | 03/2021 | 03/2026 | 1622.27 | 2430.76 | 151.04 | 32
October 2025 | 809 | Department of Water Resources, River Development & GR | Water Resources | Integrated Anandpur Barrage Project | Water Resources-OR | 603945 | Odisha | 04/1997 | 01/1998 | 12/2019 | 06/2026 | 567.03 | 2990.05 | 2629.74 | 62
October 2025 | 810 | Department of Water Resources, River Development & GR | Water Resources | Kanupur Irrigation Project | Irrigation and CAD-TG | 701404 | Odisha | 04/2003 | 01/2004 | 12/2019 | 06/2026 | 989.43 | 2301.28 | 2712.75 | 79
October 2025 | 811 | Department of Water Resources, River Development & GR | Water Resources | Relining of Rajasthan feeder and Sirhind Feeder canal | Department of Water Resources-PB | 701410 | Punjab | 02/2016 | 04/2018 | 06/2021 | 06/2026 | 1441.26 | 2462.16 | 3012.69 | 80
October 2025 | 812 | Department of Water Resources, River Development & GR | Water Resources | Shahpur Kandi Dam Project | Department of Water Resources-PB | 701411 | Punjab | 02/2010 | 04/2018 | 06/2022 | 10/2025 | 2285.81 | 2715.7 | 2169.72 | 88
October 2025 | 813 | Department of Water Resources, River Development & GR | Water Resources | Sri Ram Sagar Project Stage - II | Irrigation and CAD-TG | 400102 | Telangana | 04/2005 | 04/2005 | 12/2019 | 03/2026 | 736.13 | 949.87 | 940.7 | 96
October 2025 | 814 | Department of Water Resources, River Development & GR | Water Resources | Indiramma Flood Flow Canal Project | Irrigation and CAD-TG | 400103 | Telangana | 04/2005 | 01/2006 | 12/2019 | 12/2026 | 1331.3 | 5940.09 | 4491.08 | 92
October 2025 | 815 | Department of Water Resources, River Development & GR | Water Resources | J. Chokka Rao Devadula Lift Irrigation Scheme | Irrigation and CAD-TG | 701405 | Telangana | 04/2006 | 04/2006 | 12/2019 | 12/2025 | 8200.71 | 14730 | 4664.8 | 87
October 2025 | 816 | Department of Water Resources, River Development & GR | Water Resources | Rajiv Bhima Lift Irrigation Scheme | Irrigation and CAD-TG | 701406 | Telangana | 04/2007 | 01/2008 | 12/2019 | 03/2026 | 1402 | 2509.66 | 1839.76 | 100
October 2025 | 817 | Department of Water Resources, River Development & GR | Water Resources | Saryu Nahar CADWM Project | Irrigation & Water Resources-UP | 400093 | Uttar Pradesh | 04/2017 | 04/2017 | 12/2019 | 03/2026 | 1672.7 | 1672.7 | 22.24 | 1
October 2025 | 818 | Department of Water Resources, River Development & GR | Water Resources | Morna [Gureghar] Irrigation Project | Department of Water Resources, River Development & GR | 701395 | Uttar Pradesh | 04/2007 | 12/2007 | 12/2025 | - | 219.9 | 219.9 | 115.2 | 31
October 2025 | 819 | Department of Water Resources, River Development & GR | Water Resources | Madhya Ganga canal Phase-II | Irrigation & Water Resources-UP | 701408 | Uttar Pradesh | 04/2008 | 04/2008 | 12/2019 | 12/2025 | 1060.67 | 4417.21 | 4552.44 | 82
October 2025 | 820 | Department of Water Resources, River Development & GR | Water Resources | Jamrani Dam Multipurpose Project | Irrigation-UK | 613787 | Uttarakhand | 10/2023 | 11/2023 | 06/2029 | - | 2584.1 | 2584.1 | 968.52 | 16