## README
PAIMANA Flash Report Data - June & July 2025
About this workbook
This workbook contains the complete tabular data extracted from two PAIMANA (Project Assessment, Infrastructure Monitoring and Analytics for Nation-building) Flash Reports published by the Infrastructure & Project Monitoring Division (IPMD), Ministry of Statistics and Programme Implementation (MoSPI):
- Flash Report - June 2025 (legacy OCMS-style format, 234 pages)
- Flash Report - July 2025 (newer PAIMANA portal format, 67 pages)
Both reports cover Central Sector Infrastructure Projects costing Rs. 150 crore and above.
Note on the two report formats
The June 2025 report is structured differently from July 2025 onward (different table layout, and it additionally reports Anticipated cost/date figures and Completed/Added/Frozen project lists that July's report does not).
Because of this, sheet names are prefixed June_ or July_ and are NOT directly row-aligned between months - use the Project Code column to match the same project across months where it appears in both.
Sheet guide
Summary - headline KPIs for each month (ongoing project count, cost, expenditure).
July_Table1_Ministry_wise / July_Table2_State_wise - ministry- and state-level cost & count rollups (July).
July_Table3_NE_Region - the 51 ongoing North-East Region projects (July), a subset of Table 4.
July_Table4_All_Projects - all 791 ongoing projects (July), one row per project - the richest dataset.
June_Table1_Sector_wise / June_Table2_State_wise - sector- and state-level rollups (June).
June_Table3_Completed / June_Table4_Added / June_Table5_Frozen_Deleted - projects completed, newly added, or frozen/deleted during June 2025.
June_Table6_NE_Region - the 198 ongoing North-East Region projects (June), a subset of Table 7.
June_Table7_All_Projects - all 1,595 ongoing projects as of 30 June 2025, one row per project.
Data quality notes
All project lists were parsed programmatically from the source PDFs (Sl.No sequences were verified as complete and non-duplicated in every table).
'N.A.' or blank cost/date fields mean the report itself did not report a revised/anticipated value for that project.
State-wise tables (Table 2) sum to more than the total project count because projects spanning multiple states are counted once under each state - this matches the source report's own subtotals.
Source
Ministry of Statistics and Programme Implementation (MoSPI), PAIMANA portal: https://www.ipm.mospi.gov.in/

## Summary
Month | Ongoing Projects | Ministries/Depts | Original Cost (Rs. Cr) | Revised Cost (Rs. Cr) | Cumulative Expenditure (Rs. Cr)
June 2025 | 1595 | N/A (legacy OCMS format) | 2685568.07 | 2801018.15 | 1630750.12
July 2025 | 791 | 14 | 2386335.28 | 2899509 | 1510700.05

## July_Table1_Ministry_wise
Ministry/Department | Sector | Project Count | Original Cost (Rs. Crore) | Latest Revised Cost (Rs. Crore) | Cumulative Expenditure (Rs. Crore)
Department for Promotion of Industry & Internal Trade | Real Estate | 2 | 3841.25 | 3841.25 | 422.99
Department for Promotion of Industry & Internal Trade | Tourism, Hospitality & Wellness | 1 | 5178 | 5401 | 4470
Department of Higher Education | Education | 30 | 12754.41 | 12685.5 | 8277.36
Department of Telecommunications | Telecommunication | 15 | 151089.45 | 273182 | 71833.2
Department of Water Resources, River Development & GR | Waste & Water | 8 | 4039.12 | 4039.12 | 1590.56
Department of Water Resources, River Development & GR | Water Resources | 45 | 97037.25 | 215274 | 143186
Ministry of Civil Aviation | Aviation & Aviation Infrastructure | 27 | 23265.01 | 23726.2 | 5883.97
Ministry of Coal | Coal | 118 | 169952.27 | 170585 | 52990.5
Ministry of Coal | Electricity Generation | 5 | 46865.63 | 51408.8 | 23308.2
Ministry of Coal | Railways | 2 | 3485.86 | 3485.86 | 1636.67
Ministry of Health & Family Welfare | Healthcare | 3 | 4155 | 4492.95 | 2646.56
Ministry of Housing & Urban Affairs | Construction | 1 | 646.53 | 646.52 | 518.46
Ministry of Housing & Urban Affairs | Inland Waterways | 1 | 63246 | 63246 | 47162.7
Ministry of Housing & Urban Affairs | Real Estate | 10 | 44555.17 | 44555.2 | 6303.55
Ministry of Housing & Urban Affairs | Urban Public Transport | 21 | 223016.77 | 230264 | 157669
Ministry of Housing & Urban Affairs | Waste & Water | 2 | 410 | 410 | 100
Ministry of Mines | Construction | 1 | 255.37 | 255.37 | 78.34
Ministry of Mines | Metals & Mining | 9 | 12736.35 | 15116.5 | 6040.77
Ministry of Petroleum & Natural Gas | Energy Storage | 17 | 82155.48 | 114517 | 90143.8
Ministry of Petroleum & Natural Gas | Oil & Gas | 93 | 353990.1 | 385767 | 186037
Ministry of Ports, Shipping and Waterways | Healthcare | 1 | 693 | 693 | 58
Ministry of Ports, Shipping and Waterways | Inland Waterways | 2 | 9612.82 | 9304.79 | 3778.54
Ministry of Ports, Shipping and Waterways | Shipping | 5 | 4823.34 | 4823.34 | 1812.05
Ministry of Ports, Shipping and Waterways | Tourism, Hospitality & Wellness | 1 | 573 | 1238.05 | 487.35
Ministry of Power | Coal | 2 | 2083 | 2365 | 901.38
Ministry of Power | Electricity Generation | 31 | 224064.24 | 273137 | 129610
Ministry of Power | Transmission & Distribution | 61 | 142976.51 | 145116 | 49396.5
Ministry of Railways | Inland Waterways | 3 | 4265 | 5184 | 2178.18
Ministry of Railways | Railways | 252 | 673330.1 | 809778 | 503708
Ministry of Railways | Real Estate | 1 | 493 | 493 | 252.45
Ministry of Railways | Urban Public Transport | 1 | 2298 | 2734 | 393
Ministry of Steel | Metals & Mining | 1 | 1700 | 1756.2 | 65.44
Ministry of Steel | Steel | 19 | 16748.25 | 19986.5 | 7759.53

## July_Table2_State_wise
State | Allocated To | Sector | Project Count | Original Cost (Rs. Crore) | Latest Revised Cost (Rs. Crore) | Cumulative Expenditure (Rs. Crore)
Offshore | Ministry of Petroleum & Natural Gas | Oil & Gas | 6 | 19714.58 | 22972.8 | 9861.58
Offshore | Ministry of Railways | Railways | 2 | 1311.83 | 1311.83 | 591.32
PAN India | Department of Telecommunications | Telecommunication | 7 | 142131.27 | 264452 | 68888.24
Andaman & Nicobar | Ministry of Housing & Urban Affairs | Real Estate | 1 | 209.88 | 209.88 | 0
Andhra Pradesh | Department for Promotion of Industry & Internal Trade | Real Estate | 1 | 2139.44 | 2139.44 | 327.99
Andhra Pradesh | Department of Higher Education | Education | 1 | 305 | 305 | 83.33
Andhra Pradesh | Department of Telecommunications | Telecommunication | 2 | 5262.57 | 5262.57 | 1697.56
Andhra Pradesh | Department of Water Resources, River Development & GR | Water Resources | 3 | 10901.5 | 57269.5 | 25827.76
Andhra Pradesh | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | 4 | 1440.03 | 1440.03 | 696.24
Andhra Pradesh | Ministry of Petroleum & Natural Gas | Energy Storage | 2 | 2898.34 | 3050 | 2223.91
Andhra Pradesh |  | Oil & Gas | 6 | 39929 | 40265 | 37302.2
Andhra Pradesh | Ministry of Power | Transmission & Distribution | 5 | 13395.24 | 13395.2 | 4132.14
Andhra Pradesh | Ministry of Railways | Railways | 26 | 50889.37 | 58114.5 | 28960.14
Arunachal Pradesh | Department of Higher Education | Education | 1 | 592.61 | 592.61 | 549.96
Arunachal Pradesh | Department of Telecommunications | Telecommunication | 1 | 1255.49 | 1255.49 | 284.04
Arunachal Pradesh | Ministry of Petroleum & Natural Gas | Energy Storage | 1 | 43129 | 72937 | 59524.37
Arunachal Pradesh |  | Oil & Gas | 1 | 9265 | 9265 | 6375.02
Arunachal Pradesh | Ministry of Power | Electricity Generation | 4 | 41850.64 | 61640.8 | 28273.61
Arunachal Pradesh |  | Transmission & Distribution | 1 | 4754.42 | 4754.42 | 7321.07
Arunachal Pradesh | Ministry of Railways | Railways | 1 | 435 | 1250 | 901
Assam | Department of Higher Education | Education | 1 | 153.71 | 153.71 | 288.87
Assam | Department of Telecommunications | Telecommunication | 1 | 1255.49 | 1255.49 | 284.04
Assam | Department of Water Resources, River Development & GR | Water Resources | 1 | 256.16 | 256.16 | 0
Assam | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | 1 | 1712 | 1712 | 0
Assam | Ministry of Coal | Coal | 2 | 449.23 | 449.23 | 186.31
Assam | Ministry of Petroleum & Natural Gas | Energy Storage | 3 | 10768.4 | 11947.4 | 9862.17
Assam |  | Oil & Gas | 13 | 28019.15 | 40824 | 30217.38
Assam | Ministry of Power | Electricity Generation | 1 | 6285.33 | 26075.5 | 24685.13
Assam |  | Transmission & Distribution | 1 | 5111.33 | 6700 | 5253.47
Assam | Ministry of Railways | Railways | 6 | 15645.83 | 17360.8 | 10192.51
Bihar | Department of Higher Education | Education | 1 | 499.21 | 499.21 | 425.47
Bihar | Department of Telecommunications | Telecommunication | 3 | 2336.11 | 2107.64 | 948.33
Bihar | Department of Water Resources, River Development & GR | Waste & Water | 5 | 2351.43 | 2351.43 | 1285.75
Bihar |  | Water Resources | 3 | 2884.49 | 4060.84 | 1590.27
Bihar | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | 4 | 3756.73 | 3756.73 | 1284.41
Bihar | Ministry of Housing & Urban Affairs | Real Estate | 1 | 454.65 | 454.65 | 204.64
Bihar |  | Urban Public Transport | 1 | 13365.77 | 13365.8 | 4039.77
Bihar | Ministry of Petroleum & Natural Gas | Energy Storage | 1 | 10228 | 11407 | 9701.95
Bihar |  | Oil & Gas | 7 | 24636.5 | 26501.2 | 13077.01
Bihar | Ministry of Ports, Shipping and Waterways | Inland Waterways | 1 | 5369.18 | 5061.15 | 3432.34
Bihar | Ministry of Power | Electricity Generation | 1 | 10439.09 | 13756.6 | 11970.96
Bihar | Ministry of Power | Transmission & Distribution | 2 | 751.63 | 751.63 | 0.4
Bihar | Ministry of Railways | Railways | 21 | 51225.79 | 57662.8 | 27425.45
Chandigarh | Ministry of Housing & Urban Affairs | Real Estate | 1 | 285.85 | 285.85 | 127.58
Chhattisgarh | Department of Telecommunications | Telecommunication | 2 | 5262.57 | 5262.57 | 1697.56
Chhattisgarh | Department of Water Resources, River Development & GR | Water Resources | 2 | 842.26 | 1109.33 | 616.93
Chhattisgarh | Ministry of Coal | Coal | 15 | 38654.89 | 38654.9 | 15299.54
Chhattisgarh |  | Railways | 1 | 1686.22 | 1686.22 | 342.96
Chhattisgarh | Ministry of Housing & Urban Affairs | Real Estate | 1 | 3797.69 | 3797.69 | 2694
Chhattisgarh | Ministry of Petroleum & Natural Gas | Oil & Gas | 2 | 10056.25 | 10467 | 6507.12
Chhattisgarh | Ministry of Power | Electricity Generation | 2 | 25321 | 25321 | 2288
Chhattisgarh |  | Transmission & Distribution | 1 | 385.84 | 385.84 | 378.16
Chhattisgarh | Ministry of Railways | Railways | 19 | 32171.36 | 34232.1 | 17908.81
Chhattisgarh | Ministry of Steel | Metals & Mining | 1 | 1700 | 1756.2 | 65.44
Chhattisgarh |  | Steel | 6 | 7530.14 | 10050.1 | 5162.03
Dadra & Nagar Haveli and Daman & Diu | Ministry of Housing & Urban Affairs | Waste & Water | 1 | 210 | 210 | 0
Dadra & Nagar Haveli and Daman & Diu | Ministry of Power | Transmission & Distribution | 1 | 4546.26 | 4546.26 | 4148.46
Dadra & Nagar Haveli and Daman & Diu | Ministry of Railways | Railways | 1 | 108000 | 108000 | 78690.89
Delhi | Department for Promotion of Industry & Internal Trade | Tourism, Hospitality & Wellness | 1 | 5178 | 5401 | 4470
Delhi | Department of Higher Education | Education | 2 | 706.49 | 706.49 | 290.98
Delhi | Department of Telecommunications | Telecommunication | 1 | 248.2 | 248.2 | 236.91
Delhi | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | 1 | 215.17 | 215.17 | 104.92
Delhi | Ministry of Housing & Urban Affairs | Construction | 1 | 646.53 | 646.52 | 518.46
Delhi |  | Real Estate | 1 | 32850 | 32850 | 0
Delhi |  | Urban Public Transport | 4 | 69853.45 | 69853.4 | 41241.03
Delhi | Ministry of Power | Transmission & Distribution | 4 | 4356.47 | 4908.47 | 3860.71
Delhi | Ministry of Railways | Railways | 13 | 27509.96 | 27510 | 5067.53
Goa | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | 2 | 756.17 | 756.17 | 436.21
Goa | Ministry of Railways | Railways | 2 | 5804.49 | 6182.62 | 5976.87
Gujarat | Department of Higher Education | Education | 1 | 490.63 | 490.63 | 301.44
Gujarat | Department of Telecommunications | Telecommunication | 1 | 336.89 | 301.13 | 225.71
Gujarat | Department of Water Resources, River Development & GR | Water Resources | 2 | 25739.93 | 40082.8 | 36722.58
Gujarat | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | 2 | 1520.17 | 1766.17 | 771.34
Gujarat | Ministry of Coal | Coal | 1 | 7580 | 7580 | 3091
Gujarat |  | Electricity Generation | 1 | 383.84 | 383.84 | 303.5
Gujarat | Ministry of Housing & Urban Affairs | Real Estate | 2 | 6016.4 | 6016.4 | 3075.44
Gujarat |  | Urban Public Transport | 3 | 28177.49 | 30329 | 23395.89
Gujarat |  | Waste & Water | 1 | 200 | 200 | 100
Gujarat | Ministry of Petroleum & Natural Gas | Energy Storage | 3 | 62245 | 92053 | 74193.58
Gujarat |  | Oil & Gas | 11 | 32704.12 | 32178.7 | 22543.16
Gujarat | Ministry of Ports, Shipping and Waterways | Inland Waterways | 1 | 4243.64 | 4243.64 | 346.2
Gujarat | Ministry of Ports, Shipping and Waterways | Tourism, Hospitality & Wellness | 1 | 573 | 1238.05 | 487.35
Gujarat | Ministry of Power | Electricity Generation | 1 | 339.35 | 339.35 | 317.59
Gujarat |  | Transmission & Distribution | 13 | 45319.41 | 45318.9 | 12189.63
Gujarat | Ministry of Railways | Railways | 31 | 189276.71 | 263686 | 214924.05
Haryana | Ministry of Health & Family Welfare | Healthcare | 1 | 1299 | 1299 | 349.41
Haryana | Ministry of Housing & Urban Affairs | Urban Public Transport | 1 | 6230.99 | 6230.99 | 0.14
Haryana | Ministry of Petroleum & Natural Gas | Energy Storage | 1 | 9028 | 9028 | 7071.08
Haryana |  | Oil & Gas | 5 | 45925.07 | 49596.1 | 33255.25
Haryana | Ministry of Power | Transmission & Distribution | 4 | 13362 | 13914 | 2575.26
Haryana | Ministry of Railways | Railways | 4 | 53464 | 126368 | 125556.07
Himachal Pradesh | Department of Higher Education | Education | 3 | 811.15 | 921.89 | 576.2
Himachal Pradesh | Department of Telecommunications | Telecommunication | 1 | 336.89 | 301.13 | 225.71
Himachal Pradesh | Ministry of Power | Electricity Generation | 4 | 7728.04 | 12252.1 | 4103.9
Himachal Pradesh | Ministry of Railways | Railways | 3 | 17005 | 17005 | 8745.88
Jammu and Kashmir | Department of Higher Education | Education | 1 | 424.93 | 500.91 | 484.52
Jammu and Kashmir | Department of Telecommunications | Telecommunication | 1 | 336.89 | 301.13 | 225.71
Jammu and Kashmir | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | 1 | 861.37 | 861.37 | 154.3
Jammu and Kashmir | Ministry of Health & Family Welfare | Healthcare | 1 | 1828 | 1828 | 1504.91
Jammu and Kashmir | Ministry of Petroleum & Natural Gas | Energy Storage | 1 | 676.89 | 676.89 | 518.22
Jammu and Kashmir |  | Oil & Gas | 2 | 1059.9 | 1059.9 | 194.19
Jammu and Kashmir | Ministry of Power | Electricity Generation | 4 | 22207.77 | 22207.8 | 12060.37
Jammu and Kashmir |  | Transmission & Distribution | 3 | 825.43 | 825.43 | 488.41
Jharkhand | Department of Telecommunications | Telecommunication | 2 | 5262.57 | 5262.57 | 1697.56
Jharkhand | Department of Water Resources, River Development & GR | Water Resources | 2 | 5430.04 | 12010.3 | 5692.84
Jharkhand | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | 1 | 215.17 | 215.17 | 104.92
Jharkhand | Ministry of Coal | Coal | 27 | 45414.48 | 45178.8 | 10320.88
Jharkhand |  | Railways | 1 | 1799.64 | 1799.64 | 1293.71
Jharkhand | Ministry of Housing & Urban Affairs | Real Estate | 1 | 212.74 | 212.74 | 41
Jharkhand | Ministry of Mines | Metals & Mining | 2 | 3370.02 | 3370.02 | 13.33
Jharkhand | Ministry of Petroleum & Natural Gas | Energy Storage | 1 | 10228 | 11407 | 9701.95
Jharkhand |  | Oil & Gas | 3 | 2010.07 | 2010.07 | 596.23
Jharkhand | Ministry of Ports, Shipping and Waterways | Inland Waterways | 1 | 5369.18 | 5061.15 | 3432.34
Jharkhand | Ministry of Power | Coal | 2 | 2083 | 2365 | 901.38
Jharkhand |  | Electricity Generation | 2 | 31470 | 34660 | 18481.7
Jharkhand | Ministry of Railways | Railways | 12 | 43938.71 | 44332.7 | 14801.8
Jharkhand | Ministry of Steel | Steel | 6 | 2854.58 | 3572.87 | 1251.51
Karnataka | Department for Promotion of Industry & Internal Trade | Real Estate | 1 | 1701.81 | 1701.81 | 95
Karnataka | Department of Higher Education | Education | 1 | 420.41 | 420.41 | 360.72
Karnataka | Department of Water Resources, River Development & GR | Water Resources | 1 | 770.16 | 1606.07 | 1511.22
Karnataka | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | 4 | 1358.57 | 1358.57 | 583.49
Karnataka | Ministry of Housing & Urban Affairs | Urban Public Transport | 2 | 41193.24 | 45483.2 | 37902.51
Karnataka | Ministry of Petroleum & Natural Gas | Energy Storage | 2 | 1532 | 2586 | 1387.55
Karnataka |  | Oil & Gas | 5 | 9662 | 12693.6 | 8687.98
Karnataka | Ministry of Power | Transmission & Distribution | 6 | 15682.01 | 15682 | 2377.07
Karnataka | Ministry of Railways | Railways | 16 | 24870.49 | 30669.6 | 17352.85
Karnataka |  | Real Estate | 1 | 493 | 493 | 252.45
Karnataka | Ministry of Steel | Steel | 1 | 1043.63 | 1043.63 | 214.48
Kerala | Department of Higher Education | Education | 1 | 1006.45 | 1217.4 | 615.95
Kerala | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | 2 | 699.74 | 699.74 | 179.59
Kerala | Ministry of Housing & Urban Affairs | Urban Public Transport | 1 | 1957.05 | 1957.05 | 306.45
Kerala | Ministry of Petroleum & Natural Gas | Oil & Gas | 3 | 7996.87 | 10990.9 | 4880.2
Kerala | Ministry of Railways | Railways | 3 | 2846 | 5199 | 3026.15
Ladakh | Department of Telecommunications | Telecommunication | 1 | 336.89 | 301.13 | 225.71
Ladakh | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | 1 | 480 | 640 | 427.04
Ladakh | Ministry of Power | Transmission & Distribution | 1 | 288.71 | 288.71 | 202.1
Madhya Pradesh | Department of Higher Education | Education | 1 | 496.28 | 496.28 | 138.6
Madhya Pradesh | Department of Telecommunications | Telecommunication | 2 | 1999.22 | 1806.51 | 722.62
Madhya Pradesh | Department of Water Resources, River Development & GR | Water Resources | 3 | 2628.27 | 2941.14 | 2757.75
Madhya Pradesh | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | 1 | 215.17 | 215.17 | 104.92
Madhya Pradesh | Ministry of Coal | Coal | 14 | 8634.02 | 8634.02 | 3268.58
Madhya Pradesh | Ministry of Housing & Urban Affairs | Urban Public Transport | 2 | 14442.2 | 14442.2 | 6956.02
Madhya Pradesh | Ministry of Mines | Metals & Mining | 1 | 1856.36 | 1856.36 | 924.98
Madhya Pradesh | Ministry of Petroleum & Natural Gas | Energy Storage | 1 | 10088 | 10088 | 7598.13
Madhya Pradesh |  | Oil & Gas | 2 | 51211.25 | 51622 | 8284.2
Madhya Pradesh | Ministry of Power | Electricity Generation | 1 | 646.17 | 646.17 | 0
Madhya Pradesh |  | Transmission & Distribution | 6 | 17446 | 17446 | 2423.32
Madhya Pradesh | Ministry of Railways | Railways | 18 | 61558.55 | 69197.5 | 43133.73
Maharashtra | Department of Higher Education | Education | 2 | 250.33 | 446.26 | 154.59
Maharashtra | Department of Telecommunications | Telecommunication | 3 | 5723.99 | 5723.99 | 1863.58
Maharashtra | Department of Water Resources, River Development & GR | Water Resources | 14 | 23764.91 | 37142.8 | 36591.47
Maharashtra | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | 1 | 500.48 | 500.48 | 306.21
Maharashtra | Ministry of Coal | Coal | 25 | 12455.88 | 12455.9 | 2983.36
Maharashtra | Ministry of Housing & Urban Affairs | Urban Public Transport | 6 | 34571.47 | 35377.5 | 28692.48
Maharashtra | Ministry of Petroleum & Natural Gas | Energy Storage | 1 | 281.35 | 389.67 | 227.54
Maharashtra |  | Oil & Gas | 13 | 34264.24 | 37660.4 | 20460.79
Maharashtra | Ministry of Ports, Shipping and Waterways | Healthcare | 1 | 693 | 693 | 58
Maharashtra |  | Shipping | 2 | 1266.8 | 1266.8 | 253.46
Maharashtra | Ministry of Power | Transmission & Distribution | 3 | 29589.67 | 29589.7 | 5660.04
Maharashtra | Ministry of Railways | Railways | 36 | 271609.73 | 360035 | 260743.99
Manipur | Department of Water Resources, River Development & GR | Water Resources | 1 | 1449.44 | 1822.24 | 1837.91
Manipur | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | 1 | 499 | 499 | 160.48
Manipur | Ministry of Petroleum & Natural Gas | Oil & Gas | 1 | 9265 | 9265 | 6375.02
Manipur | Ministry of Power | Transmission & Distribution | 1 | 5111.33 | 6700 | 5253.47
Meghalaya | Department of Higher Education | Education | 1 | 494.52 | 494.52 | 413.57
Meghalaya | Department of Telecommunications | Telecommunication | 1 | 971.96 | 971.96 | 208.25
Meghalaya | Ministry of Petroleum & Natural Gas | Oil & Gas | 1 | 9265 | 9265 | 6375.02
Meghalaya | Ministry of Power | Transmission & Distribution | 1 | 5111.33 | 6700 | 5253.47
Mizoram | Department of Higher Education | Education | 1 | 474.23 | 474.23 | 167.55
Mizoram | Ministry of Petroleum & Natural Gas | Oil & Gas | 1 | 9265 | 9265 | 6375.02
Mizoram | Ministry of Power | Transmission & Distribution | 1 | 5111.33 | 6700 | 5253.47
Nagaland | Department of Higher Education | Education | 1 | 275.63 | 275.63 | 257.82
Nagaland | Ministry of Petroleum & Natural Gas | Oil & Gas | 2 | 9492.62 | 9492.62 | 6384.03
Nagaland | Ministry of Power | Transmission & Distribution | 1 | 5111.33 | 6700 | 5253.47
Nagaland | Ministry of Railways | Railways | 2 | 8786.7 | 8786.7 | 5216.03
Odisha | Department of Higher Education | Education | 1 | 1229.32 | 773.76 | 835.55
Odisha | Department of Telecommunications | Telecommunication | 2 | 5262.57 | 5262.57 | 1697.56
Odisha | Department of Water Resources, River Development & GR | Water Resources | 2 | 1556.46 | 5291.33 | 5193.3
Odisha | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | 1 | 215.17 | 215.17 | 104.92
Odisha | Ministry of Coal | Coal | 13 | 39671.73 | 40539.7 | 13423.8
Odisha |  | Electricity Generation | 1 | 27212.96 | 27213 | 1938.68
Odisha | Ministry of Mines | Metals & Mining | 5 | 7343.97 | 9724.14 | 4967.46
Odisha | Ministry of Petroleum & Natural Gas | Energy Storage | 2 | 12886.34 | 14217 | 11894.63
Odisha |  | Oil & Gas | 5 | 25285.44 | 23768.5 | 15711.67
Odisha | Ministry of Ports, Shipping and Waterways | Shipping | 1 | 3004.63 | 3004.63 | 1149.79
Odisha | Ministry of Power | Electricity Generation | 1 | 11843.75 | 12543 | 3975
Odisha |  | Transmission & Distribution | 1 | 342.69 | 342.69 | 0.2
Odisha | Ministry of Railways | Inland Waterways | 3 | 4265 | 5184 | 2178.18
Odisha |  | Railways | 25 | 38578.21 | 42391.3 | 26663.28
Odisha |  | Railways | 1 | 267.61 | 267.61 | 0
Odisha | Ministry of Steel | Steel | 1 | 1105.23 | 1105.23 | 736.47
Puducherry | Department of Higher Education | Education | 1 | 618.34 | 544.34 | 509.24
Puducherry | Ministry of Railways | Railways | 1 | 713 | 981 | 598.38
Punjab | Department of Higher Education | Education | 2 | 559.3 | 559.3 | 290.39
Punjab | Department of Water Resources, River Development & GR | Water Resources | 2 | 3727.07 | 5177.86 | 5035.32
Punjab | Ministry of Petroleum & Natural Gas | Oil & Gas | 6 | 13060.36 | 13090.4 | 8357.79
Punjab | Ministry of Power | Transmission & Distribution | 1 | 5969 | 5969 | 167.13
Punjab | Ministry of Railways | Railways | 3 | 15702.64 | 15702.6 | 8357.15
Rajasthan | Department of Telecommunications | Telecommunication | 2 | 758.54 | 530.07 | 352.16
Rajasthan | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | 2 | 1367 | 1367 | 567.11
Rajasthan | Ministry of Coal | Electricity Generation | 1 | 1813 | 1813 | 769.57
Rajasthan | Ministry of Petroleum & Natural Gas | Energy Storage | 3 | 52618.05 | 82426.1 | 66707.02
Rajasthan | Ministry of Petroleum & Natural Gas | Oil & Gas | 2 | 10599 | 10599 | 6638.82
Rajasthan | Ministry of Power | Electricity Generation | 1 | 5491.89 | 5491.89 | 4606.84
Rajasthan |  | Transmission & Distribution | 22 | 53646.51 | 54198.2 | 15938.13
Rajasthan | Ministry of Railways | Railways | 21 | 86599.23 | 162169 | 140736.04
Sikkim | Department of Higher Education | Education | 2 | 999.82 | 924.82 | 359.78
Sikkim | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | 1 | 323.26 | 323.26 | 29.69
Sikkim | Ministry of Petroleum & Natural Gas | Oil & Gas | 1 | 9265 | 9265 | 6375.02
Sikkim | Ministry of Power | Electricity Generation | 2 | 6686.33 | 7576.15 | 6049.43
Sikkim |  | Transmission & Distribution | 1 | 4754.42 | 4754.42 | 7321.07
Sikkim | Ministry of Railways | Railways | 1 | 7877 | 12133 | 8883.6
Tamil Nadu | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | 2 | 1422.17 | 1422.17 | 481.39
Tamil Nadu | Ministry of Coal | Electricity Generation | 1 | 218.03 | 218.03 | 160.93
Tamil Nadu | Ministry of Housing & Urban Affairs | Inland Waterways | 1 | 63246 | 63246 | 47162.73
Tamil Nadu | Ministry of Mines | Metals & Mining | 1 | 166 | 166 | 135
Tamil Nadu | Ministry of Petroleum & Natural Gas | Energy Storage | 3 | 2334 | 3448.71 | 1592.52
Tamil Nadu |  | Oil & Gas | 5 | 38886 | 46654 | 6139.7
Tamil Nadu | Ministry of Power | Transmission & Distribution | 1 | 548 | 548 | 10.96
Tamil Nadu | Ministry of Railways | Railways | 8 | 8730 | 11599 | 5805.89
Telangana | Department of Higher Education | Education | 1 | 262 | 262 | 164.4
Telangana | Department of Telecommunications | Telecommunication | 2 | 2038.99 | 2038.99 | 762.19
Telangana | Department of Water Resources, River Development & GR | Water Resources | 5 | 12430.08 | 37575 | 11830.43
Telangana | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | 2 | 715.65 | 715.65 | 411.13
Telangana | Ministry of Coal | Coal | 9 | 3890.03 | 3890.03 | 2423.61
Telangana | Ministry of Health & Family Welfare | Healthcare | 1 | 1028 | 1365.95 | 792.24
Telangana | Ministry of Petroleum & Natural Gas | Oil & Gas | 1 | 1932 | 2208 | 1552.37
Telangana | Ministry of Power | Transmission & Distribution | 2 | 5694.56 | 5694.56 | 4189.95
Telangana | Ministry of Railways | Railways | 10 | 21899.15 | 25663.2 | 8692.79
Tripura | Ministry of Petroleum & Natural Gas | Energy Storage | 1 | 656 | 656 | 465.73
Tripura |  | Oil & Gas | 2 | 9474.33 | 9396.51 | 6440.99
Tripura | Ministry of Power | Transmission & Distribution | 1 | 5111.33 | 6700 | 5253.47
Uttar Pradesh | Department of Higher Education | Education | 1 | 246 | 246 | 185.83
Uttar Pradesh | Department of Telecommunications | Telecommunication | 3 | 2336.11 | 2107.64 | 948.33
Uttar Pradesh | Department of Water Resources, River Development & GR | Waste & Water | 2 | 1532.96 | 1532.96 | 208.64
Uttar Pradesh |  | Water Resources | 4 | 3694.65 | 8775.49 | 7633.54
Uttar Pradesh | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | 5 | 6983 | 7038.2 | 687.85
Uttar Pradesh | Ministry of Coal | Coal | 2 | 1328.09 | 1328.09 | 980.95
Uttar Pradesh |  | Electricity Generation | 1 | 17237.8 | 21780.9 | 20135.48
Uttar Pradesh | Ministry of Housing & Urban Affairs | Real Estate | 1 | 576.99 | 576.99 | 141.94
Uttar Pradesh |  | Urban Public Transport | 3 | 49730.1 | 49730.1 | 40947.26
Uttar Pradesh | Ministry of Petroleum & Natural Gas | Energy Storage | 2 | 11068.45 | 11068.5 | 7834.35
Uttar Pradesh |  | Oil & Gas | 4 | 18133 | 18521.5 | 1791.69
Uttar Pradesh | Ministry of Ports, Shipping and Waterways | Inland Waterways | 1 | 5369.18 | 5061.15 | 3432.34
Uttar Pradesh | Ministry of Power | Electricity Generation | 2 | 28284.42 | 30471.2 | 14055.05
Uttar Pradesh |  | Transmission & Distribution | 4 | 8474.28 | 8474.28 | 1903.49
Uttar Pradesh | Ministry of Railways | Railways | 26 | 94574.3 | 169600 | 146724.15
Uttarakhand | Department of Higher Education | Education | 1 | 650.85 | 650.85 | 130
Uttarakhand | Department of Water Resources, River Development & GR | Water Resources | 1 | 2584.1 | 2584.1 | 486.52
Uttarakhand | Ministry of Housing & Urban Affairs | Real Estate | 1 | 150.97 | 150.97 | 18.95
Uttarakhand | Ministry of Power | Electricity Generation | 3 | 11663.95 | 26070 | 19892.29
Uttarakhand | Ministry of Railways | Railways | 1 | 38953 | 38953 | 24645.15
West Bengal | Department of Higher Education | Education | 2 | 787.2 | 729.2 | 692.6
West Bengal | Department of Telecommunications | Telecommunication | 1 | 1577.57 | 1577.57 | 596.17
West Bengal | Department of Water Resources, River Development & GR | Waste & Water | 1 | 154.73 | 154.73 | 96.17
West Bengal | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | 3 | 2092.47 | 2092.47 | 465.48
West Bengal | Ministry of Coal | Coal | 13 | 15863.74 | 15863.7 | 2781.17
West Bengal | Ministry of Mines | Construction | 1 | 255.37 | 255.37 | 78.34
West Bengal | Ministry of Petroleum & Natural Gas | Energy Storage | 1 | 10228 | 11407 | 9701.95
West Bengal |  | Oil & Gas | 8 | 18159.65 | 19007.2 | 11226.34
West Bengal | Ministry of Ports, Shipping and Waterways | Inland Waterways | 1 | 5369.18 | 5061.15 | 3432.34
West Bengal |  | Shipping | 2 | 551.91 | 551.91 | 408.8
West Bengal | Ministry of Power | Electricity Generation | 3 | 20091.84 | 20160.8 | 3535.09
West Bengal |  | Transmission & Distribution | 2 | 751.63 | 751.63 | 0.4
West Bengal | Ministry of Railways | Railways | 15 | 47377.24 | 57513.2 | 32499.77
West Bengal |  | Urban Public Transport | 1 | 2298 | 2734 | 393
West Bengal | Ministry of Steel | Steel | 5 | 4214.67 | 4214.67 | 395.04

## July_Table3_NE_Region
Sl.No | Ministry/Department | Sector | Project Name | Agency | Project Code | State | Date of Approval (MM/YYYY) | Target DoC (MM/YYYY) | Revised DoC (MM/YYYY) | Original Cost (Rs. Crore) | Revised Cost (Rs. Crore) | Cumulative Expenditure (Rs. Crore) | Physical Progress (%)
1 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Guwahati Airport New Integrated Terminal Building Construction Project | Adani Airport Holdings Limited | 706724 | Assam | 03/2018 | 03/2025 |  | 1712 | 1712 | 0 | 94.1
2 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | C/o NITB Imphal Airport | Airport Authority of India [AAI] | 706718 | Manipur | 07/2022 | 07/2024 | 12/2026 | 499 | 499 | 160.48 | 41
3 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Widening of basic strip at Western Side of Runway Chainage 80m to 920m i/c slope stabilization Measures [Balance work] of uphill and Improvement of Storm Water Drainage System at Pakyong Airport, Sikkim on design & build basis [EPC] with integrated 10 years maintenance. | Airport Authority of India [AAI] | 612793 | Sikkim | 12/2023 | 02/2026 |  | 323.26 | 323.26 | 29.69 | 12
4 | Ministry of Coal | Coal | TIKAK EXTENSION OCP | MIS MoCoal Integration Logins | 615820 | Assam | 07/2022 | 07/2031 |  | 159.77 | 159.77 | 80.84 | 0
5 | Ministry of Coal | Coal | TIRAP OCP | MIS MoCoal Integration Logins | 615821 | Assam | 11/2022 | 11/2030 |  | 289.46 | 289.46 | 105.47 | 0
6 | Department of Higher Education | Education | Construction of Permanent Campus of National Institute of Technology Arunachal Pradesh | National Institute of Technology, Arunachal Pradesh | 612898 | Arunachal Pradesh | 03/2013 | 08/2026 |  | 592.61 | 592.61 | 549.96 | 75
7 | Department of Higher Education | Education | Tezpur University Projects | Tezpur University | 606112 | Assam | 06/2021 | 11/2023 | 08/2025 | 153.71 | 153.71 | 288.87 | 93
8 | Department of Higher Education | Education | Construction and Developement of National Institute of Technology Meghalaya Permanent Campus at Sohra | National Institute of Technology, Meghalaya | 612885 | Meghalaya | 09/2014 | 03/2022 | 07/2025 | 494.52 | 494.52 | 413.57 | 86
9 | Department of Higher Education | Education | Construction of Permanent Campus for NIT Mizoram at Lengpui, Aizawl | Ministry of Education | 612876 | Mizoram | 05/2014 | 12/2029 | 12/2029 | 474.23 | 474.23 | 167.55 | 4
10 | Department of Higher Education | Education | Establishment of NIT Nagaland | NIT Nagaland | 613013 | Nagaland | 09/2012 | 12/2025 |  | 275.63 | 275.63 | 257.82 | 93
11 | Department of Higher Education | Education | Construction of Sikkim University Campus Phase-I Package-II at Yangang, South Sikkim | Sikkim University | 609736 | Sikkim | 01/2022 | 01/2025 | 09/2025 | 314.06 | 314.06 | 238.22 | 82
12 | Department of Higher Education | Education | Establishment of Permanent Campus of NIT SIkkim at Khamdong-Gangtok District | Ministry of Education | 612883 | Sikkim | 03/2024 | 02/2028 | 12/2026 | 685.76 | 610.76 | 121.56 | 7
13 | Ministry of Power | Electricity Generation | Dibang Multipurpose Project | National Highways & Infrastructure Development Corporation Ltd. [NHIDCL] | 602182 | Arunachal Pradesh | 02/2023 | 02/2032 | 02/2032 | 31876.39 | 31876.4 | 3436.38 | 16
14 | Ministry of Power | Electricity Generation | 240MW Heo HE Project | North Eastern Electric Power Corporation Limited | 611698 | Arunachal Pradesh | 05/2025 | 07/2029 |  | 1938.85 | 1938.85 | 49.31 | 3
15 | Ministry of Power | Electricity Generation | 186 MW Tato-I H E Project | North Eastern Electric Power Corporation Limited | 611699 | Arunachal Pradesh | 05/2025 | 07/2029 |  | 1750.07 | 1750.07 | 102.79 | 2
16 | Ministry of Power | Electricity Generation | Subansiri Lower HE Project [2000 MW] | National Highways & Infrastructure Development Corporation Ltd. [NHIDCL] | 602096 | Multi-States (Arunachal Pradesh, Assam) | 09/2003 | 09/2010 | 05/2026 | 6285.33 | 26075.5 | 24685.13 | 96
17 | Ministry of Power | Electricity Generation | TEESTA-VI HE PROJECT, SIKKIM [500 MW], executed by LANCO TEESTA HYDRO POWER LIMITED [A wholly owned Subsidiary of NHPC LTD. acquired through NCLT] | National Highways & Infrastructure Development Corporation Ltd. [NHIDCL] | 602181 | Sikkim | 03/2019 | 03/2024 | 12/2027 | 5748.04 | 5748.04 | 4495.28 | 68
18 | Ministry of Power | Electricity Generation | Rangit-IV HE Project [120 MW] executed by Jal Power Corporation Ltd. [JPCL] - A wholly owned subsidiary of NHPC Ltd. acquired through NCLT | National Highways & Infrastructure Development Corporation Ltd. [NHIDCL] | 605156 | Sikkim | 03/2021 | 05/2024 | 12/2025 | 938.29 | 1828.11 | 1554.15 | 90
19 | Ministry of Power | Transmission & Distribution | NORTH EASTERN REGION POWER SYSTEM IMPROVEMENT PROJECT [NERPSIP] | Power Grid Corporation of India Limited [POWERGRID] | 607709 | Multi-States (Meghalaya, Manipur, Mizoram, Tripura, Nagaland, Assam) | 03/2016 | 12/2018 | 09/2025 | 5111.33 | 6700 | 5253.47 | 96
20 | Ministry of Power | Transmission & Distribution | Comprehensive Scheme for Strengthening of Transmission and Distribution [T&D] Systems [CSST&DS] in Arunachal Pradesh and Sikkim | Power Grid Corporation of India Limited [POWERGRID] | 602223 | Multi-States (Sikkim, Arunachal Pradesh) | 01/2016 | 12/2018 | 03/2027 | 4754.42 | 4754.42 | 7321.07 | 81
21 | Ministry of Petroleum & Natural Gas | Energy Storage | Rajasthan Refinery Project | MinistryofPetroleumNaturalGas | 701263 | Arunachal Pradesh | 10/2017 | 10/2022 | 03/2026 | 43129 | 72937 | 59524.37 | 87
22 | Ministry of Petroleum & Natural Gas | Energy Storage | Paradip-Numaligarh Crude Oil Pipeline [PNCPL] & Crude Oil Import Terminal [COIT] at Paradip | Ministry of Petroleum & Natural Gas | 701349 | Assam | 01/2019 | 07/2024 | 09/2025 | 10228 | 11407 | 9701.95 | 86
23 | Ministry of Petroleum & Natural Gas | Energy Storage | Construction of LPG Facilities at Kamardanga, Assam | Hindustan Petroleum Corporation Limited | 709754 | Assam | 03/2023 | 07/2027 | 07/2027 | 156.36 | 156.36 | 49.78 | 39
24 | Ministry of Petroleum & Natural Gas | Energy Storage | Setting up of new rail fed POL facility at Kamardanga, Assam | Hindustan Petroleum Corporation Limited [HPCL] | 709755 | Assam | 03/2023 | 07/2027 | 07/2027 | 384.04 | 384.04 | 110.44 | 48
25 | Ministry of Petroleum & Natural Gas | Energy Storage | Grass Root Rail-fed Depot at Sekerkote, Agartala as resitement of existing Dharmanagar Depot | Indian Oil Corporation Limited [IOCL] | 400035 | Tripura | 06/2022 | 09/2025 | 09/2025 | 656 | 656 | 465.73 | 84
26 | Ministry of Petroleum & Natural Gas | Oil & Gas | Numaligarh Refinery Expansion Project | Ministry of Petroleum & Natural Gas | 604791 | Assam | 07/2020 | 07/2024 | 12/2025 | 12366 | 22494 | 16502.36 | 75
27 | Ministry of Petroleum & Natural Gas | Oil & Gas | Assam Bio Refinery, ABRPL | Ministry of Petroleum & Natural Gas | 604792 | Assam | 02/2018 | 09/2021 | 07/2025 | 1750 | 4200 | 4650 | 99
28 | Ministry of Petroleum & Natural Gas | Oil & Gas | Development of Surface Facilities for production and evacuation of Crude Oil and Natural Gas from Nadua and East Khagorija | Ministry of Petroleum & Natural Gas | 604863 | Assam | 01/2018 | 02/2020 | 12/2025 | 682.9 | 726.93 | 488.37 | 94
29 | Ministry of Petroleum & Natural Gas | Oil & Gas | Guwahati Refinery Expansion [1.0 to 1.2 MMTPA] along with installation of CRU, Guwahati Refinery | Ministry of Petroleum & Natural Gas | 607701 | Assam | 05/2021 | 10/2023 | 05/2026 | 412.3 | 577 | 430.83 | 84
30 | Ministry of Petroleum & Natural Gas | Oil & Gas | Construction of Field Gas Gathering Station at Baghjan area for collection, processing & transportation of natural Gas to be produced from Baghjan Field | Ministry of Petroleum & Natural Gas | 616858 | Assam | 12/2020 | 03/2024 | 12/2025 | 430.76 | 430.76 | 326.12 | 85
31 | Ministry of Petroleum & Natural Gas | Oil & Gas | Upgradation of Facilities of Numaligarh-Siliguri Product Pipeline [NSPL] for transportation of additional products from existing 1.72 MMTPA to 5.5 MMTPA | Ministry of Petroleum & Natural Gas | 701350 | Assam | 06/2021 | 12/2024 | 10/2025 | 860 | 860 | 566.18 | 98
32 | Ministry of Petroleum & Natural Gas | Oil & Gas | Augmentation/Revamping of Facilities at existing Guwahati Terminal at Betkuchi | MinistryofPetroleumNaturalGas | 709776 | Assam | 04/2022 | 09/2026 | 09/2026 | 277 | 323.09 | 185.18 | 67
33 | Ministry of Petroleum & Natural Gas | Oil & Gas | Capacity Expansion of Digboi Refinery from 0.65 to 1.0 MMTPA | MinistryofPetroleumNaturalGas | 709779 | Assam | 06/2022 | 03/2026 | 03/2026 | 768 | 740 | 99.02 | 35
34 | Ministry of Petroleum & Natural Gas | Oil & Gas | Pipeline Network Project Rudrasagar | Ministry of Petroleum & Natural Gas | 709847 | Assam | 01/2023 | 04/2026 | 04/2026 | 344.99 | 344.99 | 210.89 | 46
35 | Ministry of Petroleum & Natural Gas | Oil & Gas | Borholla GGS Life Extension Project [BLEP] | Ministry of Petroleum & Natural Gas | 709850 | Assam | 09/2023 | 05/2026 | 05/2026 | 198.7 | 198.7 | 36.78 | 29
36 | Ministry of Petroleum & Natural Gas | Oil & Gas | DCU Revamp Project | NRL | 709864 | Assam | 08/2021 | 07/2024 | 10/2025 | 370 | 370 | 249.41 | 57
37 | Ministry of Petroleum & Natural Gas | Oil & Gas | Power Recovery Turbine [PRT] in PFCCU unit as an Energy Conservation Scheme | NRL | 709865 | Assam | 04/2023 | 12/2024 | 10/2025 | 293.5 | 293.5 | 97.22 | 93
38 | Ministry of Petroleum & Natural Gas | Oil & Gas | North East Gas Grid | Ministry of Petroleum & Natural Gas | 701346 | Multi-States (Sikkim, Arunachal Pradesh, Nagaland, Meghalaya, Assam, Mizoram, Tripura, Manipur) | 04/2020 | 03/2024 | 03/2026 | 9265 | 9265 | 6375.02 | 85
39 | Ministry of Petroleum & Natural Gas | Oil & Gas | Augmentation/ Revamping of Dimapur Depot, Dimapur | MinistryofPetroleumNaturalGas | 709786 | Nagaland | 08/2023 | 11/2027 | 11/2027 | 227.62 | 227.62 | 9.01 | 20
40 | Ministry of Petroleum & Natural Gas | Oil & Gas | Creation of Gas Dehydration Facilities, Tripura Asset | Oil and Natural Gas Corporation Limited [ONGC] | 709837 | Tripura | 03/2022 | 05/2024 | 12/2025 | 209.33 | 131.51 | 65.97 | 62
41 | Ministry of Railways | Railways | AGTHORI KAMAKHYA SECTION WITH CONSTRUCTION OF NEW RAIL CUM- ROAD BRIDGE AT SARAIGHAT - 7.062KM | Northeast Frontier Railway [NFR] | 613788 | Assam | 05/2025 | 12/2029 |  | 1473.77 | 1473.77 | 0 | 0
42 | Ministry of Railways | Railways | Doubling of New Bonggigaon to Kamakhya via Goalpara - 176 km | Northeast Frontier Railway [NFR] | 705572 | Assam | 09/2016 | 03/2026 | 03/2026 | 4060 | 4961 | 3683.75 | 93
43 | Ministry of Railways | Railways | Guwahati-Dibrugarh via Tinsukia & Simaluguri-Dibrugarh | Central Organisation for Railway Electrification [CORE] | 706922 | Assam | 09/2018 | 09/2020 | 06/2024 | 890.36 | 889.36 | 391.73 | 89
44 | Ministry of Railways | Railways | Murkongselek-Pasighat | Northeast Frontier Railway [NFR] | 705401 | Multi-States (Arunachal Pradesh, Assam) | 03/2012 | 03/2025 | 12/2025 | 435 | 1250 | 901 | 56
45 | Ministry of Railways | Railways | Lumding Furkating Doubling Project 140 km | Northeast Frontier Railway [NFR] | 616701 | Multi-States (Assam, Nagaland) | 01/2025 | 02/2028 |  | 2123.7 | 2123.7 | 13.74 | 0
46 | Ministry of Railways | Railways | Dimapur [Dhansiri]-Sukhobi Kohima [Zubza] NL [82.5 Km] | Northeast Frontier Railway [NFR] | 705392 | Multi-States (Nagaland, Assam) | 02/2016 | 03/2025 | 12/2025 | 6663 | 6663 | 5202.29 | 79
47 | Ministry of Railways | Railways | Sivok-Rangpo New Rail Line | Indian Railway Construction International Limited [IRCON] | 705432 | Sikkim | 05/2010 | 05/2015 | 12/2027 | 7877 | 12133 | 8883.6 | 80
48 | Department of Telecommunications | Telecommunication | Provision of 4G based Mobile Services in Uncovered Villages and National Highways of Meghalaya | Department of Telecommunications [DoT] | 701598 | Meghalaya | 09/2020 | 03/2022 | 03/2025 | 971.96 | 971.96 | 208.25 | 98
49 | Department of Telecommunications | Telecommunication | Provision of 4G Mobile Services in Uncovered Villages of Arunachal Pradesh and 2 Districts of Assam | Department of Telecommunications [DoT] | 701597 | Multi-States (Assam, Arunachal Pradesh) | 10/2021 | 04/2023 | 09/2025 | 1255.49 | 1255.49 | 284.04 | 89
50 | Department of Water Resources, River Development & GR | Water Resources | Borolia Irrigation Project | Department of Water Resources, River Development & GR | 701370 | Assam | 12/1996 | 12/2022 | 03/2025 | 256.16 | 256.16 | 0 | 0
51 | Department of Water Resources, River Development & GR | Water Resources | Thoubal Multipurpose Project | Water Resources Department-MN | 701400 | Manipur | 04/1997 | 12/2019 | 03/2026 | 1449.44 | 1822.24 | 1837.91 | 98

## July_Table4_All_Projects
Sl.No | Ministry/Department | Sector | Project Name | Agency | Project Code | State | Date of Approval (MM/YYYY) | Target DoC (MM/YYYY) | Revised DoC (MM/YYYY) | Original Cost (Rs. Crore) | Revised Cost (Rs. Crore) | Cumulative Expenditure (Rs. Crore) | Physical Progress (%)
1 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Construction of New Domestic Terminal Building Building and miscellaneous works including maintenance, operations and AICMC at Kadapa Airport | Airport Authority of India [AAI] | 612786 | Andhra Pradesh | 01/2024 | 01/2026 | 03/2026 | 265.91 | 265.91 | 45.54 | 31
2 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Construction of New Integrated Terminal Building and associated works including apron to park 3 code E type of aircraft or 6 code C type of aircraft at Vijayawada Airport. | Airport Authority of India [AAI] | 701107 | Andhra Pradesh | 09/2020 | 09/2022 | 12/2025 | 611.8 | 611.8 | 464.55 | 77
3 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Construction of New Domestic Terminal Building at Rajahmundry Airport. | Airport Authority of India [AAI] | 701121 | Andhra Pradesh | 08/2023 | 08/2025 | 12/2025 | 347.15 | 347.15 | 81.23 | 49
4 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Guwahati Airport New Integrated Terminal Building Construction Project | Adani Airport Holdings Limited | 706724 | Assam | 03/2018 | 03/2025 |  | 1712 | 1712 | 0 | 94.1
5 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Development of New Civil Enclave at Bihta | Airport Authority of India [AAI] | 612183 | Bihar | 03/2025 | 09/2027 |  | 1413 | 1413 | 0 | 1
6 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Development of New Civil Enclave and associated works at Darbhanga Airport | Airport Authority of India [AAI] | 612194 | Bihar | 07/2024 | 01/2026 |  | 911.66 | 911.66 | 133.01 | 23
7 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Construction of New Domestic Terminal Building [Phase-I and II] and other allied structures at JPNI Airport, Patna | Airport Authority of India [AAI] | 701101 | Bihar | 10/2018 | 07/2023 | 11/2025 | 1216.9 | 1216.9 | 1046.48 | 94
8 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Goa Airport Terminal Building Extension Project | Airport Authority of India [AAI] | 701105 | Goa | 12/2019 | 12/2021 | 09/2025 | 255.69 | 255.69 | 130 | 88
9 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Development of Dholera International Greenfield Airport , Gujarat | Airport Authority of India [AAI] | 701126 | Gujarat | 07/2022 | 06/2026 | 06/2026 | 1305 | 1551 | 666.42 | 63
10 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Construction of NTB complex including apron, taxi track and other associated civil works and electrical & mechanical installations towards Tawi River side at CA Jammu. | Airport Authority of India [AAI] | 611047 | Jammu and Kashmir | 07/2023 | 06/2026 | 06/2026 | 861.37 | 861.37 | 154.3 | 30
11 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Construction of New Domestic Terminal Building and Miscellaneous works at Hubli Airport | Airport Authority of India [AAI] | 612787 | Karnataka | 01/2024 | 01/2026 | 03/2026 | 320.47 | 320.47 | 56.54 | 36
12 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Construction of New Domestic Terminal Building and Miscellaneous Works at Belagavi Airport. | Airport Authority of India [AAI] | 612788 | Karnataka | 02/2024 | 01/2026 | 01/2026 | 322.45 | 322.45 | 115.82 | 48
13 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Development of additional RESA on either end on Runway 10-28 at Calicut Airport. Construction of embankment with slope protection, drainage system and associated works for additional RESA on either end on Runway 10-28 | Airport Authority of India [AAI] | 612789 | Kerala | 02/2024 | 09/2025 | 03/2026 | 484.57 | 484.57 | 74.67 | 19
14 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Construction of Terminal Building & Associated works at Leh Airport, Ladakh | Airport Authority of India [AAI] | 400010 | Ladakh | 09/2018 | 09/2021 | 10/2025 | 480 | 640 | 427.04 | 67
15 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | C/o NITB Imphal Airport | Airport Authority of India [AAI] | 706718 | Manipur | 07/2022 | 07/2024 | 12/2026 | 499 | 499 | 160.48 | 41
16 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Procurment of 30 Nos ACFTs of WT Capacity 10KL at Various Airports | Airport Authority of India [AAI] | 611440 | Multi-States (Andhra Pradesh, Bihar, Delhi, Gujarat, Jharkhand, Karnataka, Kerala, Madhya Pradesh, Odisha, Tamil Nadu, Telangana, Uttar Pradesh, West Bengal) | 05/2023 | 06/2025 |  | 215.17 | 215.17 | 104.92 | 53
17 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | SITC of ATM Automation System and ASMGCS [Including SMR & MLAT] for Mumbai, Navi Mumbai, MOPA [without ASMGCS], HIAL & BIAL | Airport Authority of India [AAI] | 611570 | Multi-States (Goa, Karnataka, Maharashtra, Telangana) | 10/2022 | 09/2025 |  | 500.48 | 500.48 | 306.21 | 74
18 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Construction of New Passenger Terminal Building for Domestic Operations at Jodhpur Airport. | Airport Authority of India [AAI] | 701127 | Rajasthan | 04/2023 | 11/2024 | 10/2025 | 480 | 480 | 254.71 | 77
19 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Construction of New Integrated Passenger Terminal Building at Udaipur Airport | Airport Authority of India [AAI] | 701128 | Rajasthan | 11/2022 | 03/2026 | 10/2026 | 887 | 887 | 312.4 | 44
20 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Widening of basic strip at Western Side of Runway Chainage 80m to 920m i/c slope stabilization Measures [Balance work] of uphill and Improvement of Storm Water Drainage System at Pakyong Airport, Sikkim on design & build basis [EPC] with integrated 10 years maintenance. | Airport Authority of India [AAI] | 612793 | Sikkim | 12/2023 | 02/2026 |  | 323.26 | 323.26 | 29.69 | 12
21 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Modernization of Chennai Airport, Phase II, Part 2 | Airport Authority of India [AAI] | 611602 | Tamil Nadu | 06/2023 | 07/2025 | 03/2026 | 1207 | 1207 | 376.47 | 21
22 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Construction of New Terminal Building, Second Link Taxi Track, Apron Expansion, and associated works at Prayagraj Airport- On Design & Build Basis. | Airport Authority of India [AAI] | 612063 | Uttar Pradesh | 08/2023 | 11/2024 | 08/2025 | 219.18 | 274.38 | 206.33 | 97
23 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Lucknow Airport-Terminal 3- Phase 1 & Other Associated Works | Adani Airport Holdings Limited | 701091 | Uttar Pradesh | 09/2018 | 03/2026 |  | 3100 | 3100 | 0 | 99.96
24 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Development of Lal Bahadur Shastri International airport, Varanasi including C/o New Terminal Building, Apron Extension, Runway Extension, PTT and allied works. | Airport Authority of India [AAI] | 701113 | Uttar Pradesh | 07/2024 | 07/2027 | 07/2027 | 2869.65 | 2869.65 | 302.3 | 14
25 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Development of New Integrated Civil Enclave at Agra Airport | Airport Authority of India [AAI] | 701122 | Uttar Pradesh | 07/2024 | 07/2026 |  | 579 | 579 | 74.3 | 14
26 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Development of New Civil Enclave at Bagdogra Airport | Airport Authority of India [AAI] | 611495 | West Bengal | 10/2023 | 01/2027 | 01/2027 | 1549 | 1549 | 262.41 | 10
27 | Ministry of Civil Aviation | Aviation & Aviation Infrastructure | Re-Construction of Rigid portions of Secondary Runway, K and A Taxiway and Strengthening of C Taxiway at NSCBI Airport Kolkata. | Airport Authority of India [AAI] | 612791 | West Bengal | 12/2023 | 02/2025 | 08/2026 | 328.3 | 328.3 | 98.15 | 44
28 | Ministry of Coal | Coal | TIKAK EXTENSION OCP | MIS MoCoal Integration Logins | 615820 | Assam | 07/2022 | 07/2031 |  | 159.77 | 159.77 | 80.84 | 0
29 | Ministry of Coal | Coal | TIRAP OCP | MIS MoCoal Integration Logins | 615821 | Assam | 11/2022 | 11/2030 |  | 289.46 | 289.46 | 105.47 | 0
30 | Ministry of Coal | Coal | PORDA CHIMTAPANI OCP [10 MTY] | South Eastern Coalfields Limited [SECL] | 400144 | Chhattisgarh | 12/2020 | 03/2029 |  | 2310.12 | 2310.12 | 83.66 | 10
31 | Ministry of Coal | Coal | CHHAL OC SEAM III [6 MTY] | South Eastern Coalfields Limited [SECL] | 400145 | Chhattisgarh | 12/2013 | 03/2022 | 09/2025 | 610.63 | 610.63 | 577.46 | 85
32 | Ministry of Coal | Coal | KUSMUNDA OC EXPANSION [15 TO 50 MTY] | South Eastern Coalfields Limited [SECL] | 400147 | Chhattisgarh | 08/2013 | 03/2023 | 03/2030 | 7612.33 | 7612.33 | 4697.95 | 81
33 | Ministry of Coal | Coal | BAROUD OC EXPANSION [3.0-10.0MTY] | South Eastern Coalfields Limited [SECL] | 400149 | Chhattisgarh | 08/2020 | 03/2029 |  | 2309.8 | 2309.8 | 913.03 | 47
34 | Ministry of Coal | Coal | DIPKA EXPANSION OCP [40 MTY] | South Eastern Coalfields Limited [SECL] | 400354 | Chhattisgarh | 12/2020 | 03/2029 |  | 5241.4 | 5241.4 | 2675 | 37
35 | Ministry of Coal | Coal | GEVRA OC [70 MTY] | South Eastern Coalfields Limited [SECL] | 400424 | Chhattisgarh | 03/2016 | 03/2023 | 03/2026 | 11816.4 | 11816.4 | 5328.96 | 77
36 | Ministry of Coal | Coal | JAMPALI OC RCE [2.0 MTY] | SECL - CIL | 613795 | Chhattisgarh | 05/2020 | 03/2025 | 06/2025 | 278.64 | 278.64 | 210.07 | 82
37 | Ministry of Coal | Coal | AMERA OC RCE [1.0 MTY] | South Eastern Coalfields Limited [SECL] | 613798 | Chhattisgarh | 02/2015 | 03/2026 |  | 335.97 | 335.97 | 87.47 | 42
38 | Ministry of Coal | Coal | AMGAON OC RCE [1.0 MTY] | South Eastern Coalfields Limited [SECL] | 613799 | Chhattisgarh | 07/2015 | 03/2026 |  | 316.11 | 316.11 | 188.53 | 71
39 | Ministry of Coal | Coal | JAGANNATHPUR OC RCE PROJECT[3.0 MTY] | South Eastern Coalfields Limited [SECL] | 613800 | Chhattisgarh | 07/2016 | 03/2025 | 03/2026 | 459.49 | 459.49 | 274.35 | 92
40 | Ministry of Coal | Coal | MAHAMAYA OCP [1.50 MTY] | South Eastern Coalfields Limited [SECL] | 613801 | Chhattisgarh | 05/2018 | 03/2026 |  | 410.26 | 410.26 | 169.3 | 38
41 | Ministry of Coal | Coal | KATKONA RO UG MINE | South Eastern Coalfields Limited [SECL] | 615191 | Chhattisgarh | 01/2023 | 03/2029 |  | 329.21 | 329.21 | 60.3 | 2
42 | Ministry of Coal | Coal | PELMA OC MDO | South Eastern Coalfields Limited [SECL] | 616234 | Chhattisgarh | 10/2022 | 03/2033 |  | 1725.04 | 1725.04 | 15.63 | 17
43 | Ministry of Coal | Coal | KUSMUNDA OC EXPANSION PROJECT 50-75 MTY | SECL - CIL | 617287 | Chhattisgarh | 11/2024 | 03/2030 |  | 4516.88 | 4516.88 | 16.97 | 3
44 | Ministry of Coal | Coal | MANIKPUR OC EXPANSION PROJECT 7 MTY | South Eastern Coalfields Limited [SECL] | 617288 | Chhattisgarh | 01/2025 | 03/2029 |  | 382.61 | 382.61 | 0.86 | 1
45 | Ministry of Coal | Coal | DIPKA OC | SECL - CIL | 612838 | Gujarat | 01/2017 | 03/2025 |  | 7580 | 7580 | 3091 | 65
46 | Ministry of Coal | Coal | HURA C OCP | ECL - CIL | 400018 | Jharkhand | 08/2022 | 03/2029 |  | 859.41 | 859.41 | 450.47 | 62
47 | Ministry of Coal | Coal | KONAR EXPANSION OCP | Ministry of Coal | 400073 | Jharkhand | 01/2022 | 03/2032 |  | 799.34 | 799.34 | 426.16 | 46
48 | Ministry of Coal | Coal | KARO EXPANSION OCP | Ministry of Coal | 400074 | Jharkhand | 01/2022 | 03/2029 |  | 908.47 | 908.47 | 251.79 | 22
49 | Ministry of Coal | Coal | SANGHMITRA OC | Ministry of Coal | 400136 | Jharkhand | 03/2027 | 03/2032 |  | 2660 | 2660 | 0 | 0
50 | Ministry of Coal | Coal | CHANDRAGUPT OCP | Ministry of Coal | 400138 | Jharkhand | 08/2020 | 03/2032 |  | 973.5 | 973.5 | 440.32 | 15
51 | Ministry of Coal | Coal | KOTRE BASANTPUR PACHMO OCP | Ministry of Coal | 400139 | Jharkhand | 08/2020 | 03/2032 |  | 861.06 | 625.4 | 441.05 | 41
52 | Ministry of Coal | Coal | Pachwara South Coal Block | NLC India Limited [NLCIL] | 400142 | Jharkhand | 12/2019 | 09/2028 |  | 2242.9 | 2242.9 | 1165.64 | 54
53 | Ministry of Coal | Coal | RPR MAGADH EXP OCP | Ministry of Coal | 400150 | Jharkhand | 08/2020 | 03/2028 |  | 7254.37 | 7254.37 | 1534.64 | 38
54 | Ministry of Coal | Coal | NORTH URIMARI EXPANSION OCP | Ministry of Coal | 400151 | Jharkhand | 07/2021 | 03/2029 |  | 778.8 | 778.8 | 695.11 | 67
55 | Ministry of Coal | Coal | EPR ROHINI - KARKETTA OCP | Ministry of Coal | 400153 | Jharkhand | 01/2021 | 03/2028 |  | 1020.42 | 1020.42 | 83.95 | 20
56 | Ministry of Coal | Coal | EPR PUNDI OCP | Ministry of Coal | 400154 | Jharkhand | 11/2020 | 03/2027 |  | 713.35 | 713.35 | 236.57 | 10
57 | Ministry of Coal | Coal | EPR ASHOK OC | Ministry of Coal | 400155 | Jharkhand | 05/2021 | 03/2028 |  | 2898.28 | 2898.28 | 176.6 | 21
58 | Ministry of Coal | Coal | EPR AMRAPALI OCP | Ministry of Coal | 400156 | Jharkhand | 02/2020 | 03/2028 |  | 5136.15 | 5136.15 | 1125.18 | 43
59 | Ministry of Coal | Coal | RAJRAPPA RCE OCP | Ministry of Coal | 400160 | Jharkhand | 12/2009 | 03/2016 | 03/2027 | 510.85 | 510.85 | 488.57 | 76
60 | Ministry of Coal | Coal | CHITRA EAST OC | Eastern Coal Fields Limited [ECL] | 400172 | Jharkhand | 08/2018 | 03/2026 |  | 513.99 | 513.99 | 228.71 | 51
61 | Ministry of Coal | Coal | JHARKHAND-LAIYO OCP | Ministry of Coal | 400352 | Jharkhand | 08/2020 | 03/2031 |  | 764.57 | 764.57 | 145.81 | 25
62 | Ministry of Coal | Coal | MOONIDIH XV SEAM UG | BCCL - CIL | 400425 | Jharkhand | 08/2011 | 03/2019 | 05/2026 | 1230.27 | 1230.27 | 624.17 | 81
63 | Ministry of Coal | Coal | 2.5 MTPA PATHERDIH NLW WASHERY | Ministry of Coal | 611017 | Jharkhand | 04/2016 | 04/2018 | 03/2026 | 334.27 | 334.27 | 138.69 | 48
64 | Ministry of Coal | Coal | AMALAGAMATED NTST KUJAMA OCP 8.5MTY | Ministry of Coal | 611864 | Jharkhand | 01/2023 | 03/2030 |  | 4011.85 | 4011.85 | 398.5 | 28
65 | Ministry of Coal | Coal | MURAIDIH UG PROJECT | Ministry of Coal | 613808 | Jharkhand | 02/2011 | 04/2014 | 12/2026 | 339.87 | 339.87 | 190.65 | 70
66 | Ministry of Coal | Coal | TAPIN SOUTH EXPN | Ministry of Coal | 615349 | Jharkhand | 11/2020 | 03/2028 |  | 230.41 | 230.41 | 21 | 20
67 | Ministry of Coal | Coal | SIRKA OC | Ministry of Coal | 615822 | Jharkhand | 05/2020 | 03/2028 |  | 222.82 | 222.82 | 139.31 | 60
68 | Ministry of Coal | Coal | TETARIAKHAR OC | Ministry of Coal | 615843 | Jharkhand | 11/2019 | 03/2025 | 03/2027 | 243.52 | 243.52 | 44.64 | 28
69 | Ministry of Coal | Coal | CHUPERBHITA SIMLONG OCP MDO 6 MTY | Eastern Coal Fields Limited [ECL] | 616225 | Jharkhand | 12/2023 | 03/2037 |  | 979.08 | 979.08 | 0 | 0
70 | Ministry of Coal | Coal | JARANGDIH EXPN. OCP 1.5 MTY | CCL - CIL | 616236 | Jharkhand | 02/2020 | 03/2029 |  | 414.37 | 414.37 | 85.6 | 26
71 | Ministry of Coal | Coal | BLOCK E OCP | Ministry of Coal | 616253 | Jharkhand | 03/2024 | 03/2029 |  | 5850.83 | 5850.83 | 0 | 2
72 | Ministry of Coal | Coal | AMADAND OCP[4.0MTY] | Ministry of Coal | 400148 | Madhya Pradesh | 03/2016 | 03/2021 | 03/2027 | 869.44 | 869.44 | 274.45 | 75
73 | Ministry of Coal | Coal | RAMPUR BATURA OCP [4.0MTY] | South Eastern Coalfields Limited [SECL] | 400152 | Madhya Pradesh | 07/2019 | 03/2026 |  | 1248.93 | 1248.93 | 495.4 | 44
74 | Ministry of Coal | Coal | BLOCK B EXPANSION [3.5 TO 8.0 MTPA] OPENCAST COAL MINING PROJECT | Northern Coalfields Limited [NCL] | 400162 | Madhya Pradesh | 07/2019 | 03/2023 | 03/2027 | 998.71 | 998.71 | 458.01 | 46
75 | Ministry of Coal | Coal | NIGAHI EXPANSION [15 TO 25 MTPA] OPENCAST MINING PROJECT | Northern Coalfields Limited [NCL] | 400321 | Madhya Pradesh | 11/2020 | 03/2025 | 03/2028 | 1729.68 | 1729.68 | 772.91 | 44
76 | Ministry of Coal | Coal | KANCHAN OC EXP | South Eastern Coalfields Limited [SECL] | 613802 | Madhya Pradesh | 12/2014 | 03/2026 |  | 371.04 | 371.04 | 144.61 | 47
77 | Ministry of Coal | Coal | JHIRIA WEST OCP [1.5 MTY] | South Eastern Coalfields Limited [SECL] | 613803 | Madhya Pradesh | 01/2024 | 03/2026 |  | 366.94 | 366.94 | 25.07 | 41
78 | Ministry of Coal | Coal | RPR TAWA-III UG 0.84 MTY | WCL - CIL | 613804 | Madhya Pradesh | 12/2021 | 03/2027 |  | 314.09 | 314.09 | 5.7 | 17
79 | Ministry of Coal | Coal | AMALGAMATED DHANKASA & JAMUNIA UG | Western Coalfields Limited [WCL] | 615185 | Madhya Pradesh | 09/2022 | 03/2027 |  | 399.2 | 399.2 | 72.21 | 67
80 | Ministry of Coal | Coal | RPR OF VISHNUPURI UG TO OC | Western Coalfields Limited [WCL] | 615187 | Madhya Pradesh | 11/2022 | 03/2029 |  | 220.62 | 220.62 | 0 | 11
81 | Ministry of Coal | Coal | URDHAN EXPANSION OC COST PLUS | Western Coalfields Limited [WCL] | 615194 | Madhya Pradesh | 01/2023 | 03/2031 |  | 206.88 | 206.88 | 23.22 | 1
82 | Ministry of Coal | Coal | SHARDA UG MINE | Western Coalfields Limited [WCL] | 615195 | Madhya Pradesh | 09/2023 | 03/2028 |  | 166.25 | 166.25 | 2.78 | 9
83 | Ministry of Coal | Coal | GANDHIGRAM UG MINE | Western Coalfields Limited [WCL] | 615206 | Madhya Pradesh | 08/2019 | 03/2026 |  | 414.15 | 414.15 | 13.27 | 57
84 | Ministry of Coal | Coal | BHATADI EXPANSION OC | Western Coalfields Limited [WCL] | 400033 | Maharashtra | 05/2022 | 03/2028 |  | 580.61 | 580.61 | 20.52 | 26
85 | Ministry of Coal | Coal | AMALGAMATED YEKONA I & YEKONA II OC | Western Coalfields Limited [WCL] | 400177 | Maharashtra | 08/2015 | 03/2025 | 03/2026 | 727.28 | 727.28 | 524.54 | 80
86 | Ministry of Coal | Coal | DINESH[MAKARDHOKRA-III] OC | Western Coalfields Limited [WCL] | 400178 | Maharashtra | 02/2020 | 03/2027 |  | 822.88 | 822.88 | 621.73 | 35
87 | Ministry of Coal | Coal | DHUPTALA OC [SASTI UG TO OC ] | Western Coalfields Limited [WCL] | 400353 | Maharashtra | 10/2021 | 03/2028 |  | 711.01 | 711.01 | 80.33 | 17
88 | Ministry of Coal | Coal | SAONER UG MINE -1 EXPANSION 1.2 MTY | Western Coalfields Limited [WCL] | 615184 | Maharashtra | 01/2022 | 03/2028 |  | 228.64 | 228.64 | 139.81 | 68
89 | Ministry of Coal | Coal | SASTI EXPANSION OPENCAST | Western Coalfields Limited [WCL] | 615186 | Maharashtra | 08/2020 | 03/2026 |  | 319.04 | 319.04 | 90.96 | 20
90 | Ministry of Coal | Coal | NEW MAJRI UG TO OC 3 MTY COST PLUS | Western Coalfields Limited [WCL] | 615188 | Maharashtra | 09/2022 | 03/2027 |  | 402.27 | 402.27 | 41.08 | 24
91 | Ministry of Coal | Coal | MAKARDHOKRA EXPN OC 4.9 MTY | Western Coalfields Limited [WCL] | 615189 | Maharashtra | 06/2022 | 03/2026 |  | 361.87 | 361.87 | 67.64 | 12
92 | Ministry of Coal | Coal | SINGHORI DEEP OC MIN 2.0 MTY | Western Coalfields Limited [WCL] | 615190 | Maharashtra | 05/2022 | 03/2029 |  | 335.75 | 335.75 | 26.64 | 6
93 | Ministry of Coal | Coal | GOKUL EXTENSION OC MINE | Western Coalfields Limited [WCL] | 615192 | Maharashtra | 04/2021 | 03/2026 |  | 309.58 | 309.58 | 29.85 | 8
94 | Ministry of Coal | Coal | KOLGAON EXPANSION DEEP OC MINE 0.80 MTY | Western Coalfields Limited [WCL] | 615199 | Maharashtra | 09/2023 | 03/2027 |  | 198.71 | 198.71 | 0.71 | 3
95 | Ministry of Coal | Coal | BALLARPUR NORTH WEST OC MINE | Western Coalfields Limited [WCL] | 615330 | Maharashtra | 12/2022 | 03/2029 |  | 360.81 | 360.81 | 0 | 4
96 | Ministry of Coal | Coal | GADEGAON OC 3 MTY | Western Coalfields Limited [WCL] | 615331 | Maharashtra | 10/2023 | 03/2030 |  | 497.41 | 497.41 | 0 | 0
97 | Ministry of Coal | Coal | GHONSA EXPANSION DEEP OC MINE 1.5 MTY | Western Coalfields Limited [WCL] | 615914 | Maharashtra | 03/2021 | 03/2029 |  | 184.71 | 184.71 | 10.48 | 6
98 | Ministry of Coal | Coal | AMLG GAURI PAUNI EXPANSION OC - 9.0 MTY | Western Coalfields Limited [WCL] | 615916 | Maharashtra | 04/2024 | 03/2030 |  | 1225.21 | 1225.21 | 78.41 | 1
99 | Ministry of Coal | Coal | GAURIDEEP/GAURI CENTRAL OCP 7.00 MTY CP | Western Coalfields Limited [WCL] | 615917 | Maharashtra | 06/2024 | 03/2030 |  | 973.07 | 973.07 | 0.11 | 0
100 | Ministry of Coal | Coal | RPR OF BHANEGAON OC | Western Coalfields Limited [WCL] | 615918 | Maharashtra | 09/2022 | 03/2028 |  | 405.2 | 405.2 | 11.71 | 8
101 | Ministry of Coal | Coal | N. EXTN. MUNGOLI NIRGUDA D OCP 6.125 MTY | Western Coalfields Limited [WCL] | 615919 | Maharashtra | 06/2024 | 03/2030 |  | 1024.91 | 1024.91 | 165.54 | 0
102 | Ministry of Coal | Coal | NILJAI EXPANSION DEEP OCP | Western Coalfields Limited [WCL] | 615982 | Maharashtra | 08/2016 | 03/2022 | 03/2026 | 319.75 | 319.75 | 367.6 | 79
103 | Ministry of Coal | Coal | UKNI DEEP OC MINE -COST PLUS | Western Coalfields Limited [WCL] | 616044 | Maharashtra | 01/2019 | 03/2021 | 03/2026 | 237.06 | 237.06 | 159.21 | 87
104 | Ministry of Coal | Coal | AMALGAMATED INDER-KAMPTEE DEEP OC | Western Coalfields Limited [WCL] | 616050 | Maharashtra | 09/2018 | 03/2024 | 03/2026 | 235.9 | 235.9 | 237.12 | 98
105 | Ministry of Coal | Coal | ADASA UG TO OC MINE | Western Coalfields Limited [WCL] | 616223 | Maharashtra | 11/2018 | 03/2024 | 03/2026 | 316 | 316 | 308.84 | 86
106 | Ministry of Coal | Coal | AMAL GONDEGAON GHATROHANA EXPN OCP | Western Coalfields Limited [WCL] | 616229 | Maharashtra | 09/2024 | 03/2030 |  | 668.54 | 668.54 | 0.53 | 0
107 | Ministry of Coal | Coal | WAGHODA UG MINE [1.02 MTY] | Western Coalfields Limited [WCL] | 617233 | Maharashtra | 01/2025 | 03/2030 |  | 379.3 | 379.3 | 0 | 0
108 | Ministry of Coal | Coal | KOLARPIMPRI EXPANSION OC [2.5 MTY] | Western Coalfields Limited [WCL] | 617278 | Maharashtra | 02/2025 | 03/2030 |  | 630.37 | 630.37 | 0 | 0
109 | Ministry of Coal | Coal | Master Plan for Jharia and Raniganj Coalfields | Bharat Coking Coal Limited [BCCL] | 400313 | Multi-States (Jharkhand, West Bengal) | 08/2009 | 08/2019 | 12/2028 | 2661.73 | 2661.73 | 787.75 | 43
110 | Ministry of Coal | Coal | BINA KAKRI AMALGAMATION EXPANSION OPENCAST MINING PROJECT [14 MTPA] | Northern Coalfields Limited [NCL] | 400369 | Multi-States (Madhya Pradesh, Uttar Pradesh) | 08/2020 | 03/2024 | 03/2027 | 836.42 | 836.42 | 778.77 | 89
111 | Ministry of Coal | Coal | KHADIA EXPANSION [10 TO 16 MTPA] OPENCAST MINING PROJECT | Northern Coalfields Limited [NCL] | 615183 | Multi-States (Madhya Pradesh, Uttar Pradesh) | 06/2021 | 03/2025 | 03/2027 | 491.67 | 491.67 | 202.18 | 40
112 | Ministry of Coal | Coal | SUBHADRA OCP (Mahanadi Coalfields Limited (MCL)) |  | 400165 | Odisha | 05/2021 | 03/2029 | 03/2029 | 1693.81 | 1693.81 | 1278.66 | 42
113 | Ministry of Coal | Coal | SIARMAL OCP (Mahanadi Coalfields Limited (MCL)) |  | 400166 | Odisha | 02/2021 | 03/2029 | 03/2028 | 5194.95 | 5194.95 | 3455.65 | 54
114 | Ministry of Coal | Coal | BHUBANESWARI EXPANSION OCP (Mahanadi Coalfields Limited (MCL)) |  | 400179 | Odisha | 01/2023 | 03/2031 |  | 3145.45 | 6321.73 | 1250.66 | 21
115 | Ministry of Coal | Coal | BALARAM EXPANSION OCP (Mahanadi Coalfields Limited (MCL)) |  | 400183 | Odisha | 08/2020 | 03/2029 |  | 3504.21 | 3504.21 | 1027.23 | 52
116 | Ministry of Coal | Coal | GOPALJI KANIHA OCP [10 TO 30 MTY] (Mahanadi Coalfields Limited (MCL)) |  | 400185 | Odisha | 04/2022 | 03/2030 |  | 8416.19 | 6107.87 | 1694.31 | 17
117 | Ministry of Coal | Coal | INTEGRATED LAKHANPUR-BELPAHAR-LILARI OCP (Mahanadi Coalfields Limited (MCL)) |  | 400187 | Odisha | 05/2018 | 03/2027 |  | 2434.75 | 2434.75 | 1805.65 | 61
118 | Ministry of Coal | Coal | BHARATPUR RE-ORGANIZATION OCP (Mahanadi Coalfields Limited (MCL)) |  | 400392 | Odisha | 11/2018 | 03/2029 |  | 2838.86 | 2838.86 | 1748.9 | 47
119 | Ministry of Coal | Coal | BASUNDHARA WEST EXTENSION OPENCAST PRO (Mahanadi Coalfields Limited (MCL)) |  | 615193 | Odisha | 05/2014 | 03/2027 |  | 479.15 | 479.15 | 259.2 | 62
120 | Ministry of Coal | Coal | Naini Coal Mine | Singareni Collieries Company Limited [SCCL] | 615857 | Odisha | 03/2020 | 03/2026 |  | 494.3 | 494.3 | 491.33 | 80
121 | Ministry of Coal | Coal | INTEGRATED KULDA GARJANBAHAL OCP 40 MTY (Mahanadi Coalfields Limited (MCL)) |  | 616226 | Odisha | 04/2023 | 03/2033 |  | 3563.5 | 3563.5 | 150.7 | 3
122 | Ministry of Coal | Coal | BHUBANESWARI EXPN OCP 50 MTY (Mahanadi Coalfields Limited (MCL)) |  | 616231 | Odisha | 03/2024 | 03/2033 |  | 5366.27 | 5366.27 | 0 | 3
123 | Ministry of Coal | Coal | HINGULA II OC EXPN PH III 15 MTY (Mahanadi Coalfields Limited (MCL)) |  | 616232 | Odisha | 11/2022 | 03/2029 |  | 1561.85 | 1561.85 | 50.15 | 23
124 | Ministry of Coal | Coal | BALABHADRA OCP (Mahanadi Coalfields Limited (MCL)) |  | 616233 | Odisha | 04/2023 | 03/2030 |  | 978.44 | 978.44 | 211.36 | 8
125 | Ministry of Coal | Coal | Jawahar Khani Open Cast Mine | Singareni Collieries Company Limited [SCCL] | 615818 | Telangana | 12/2021 | 03/2025 | 03/2027 | 297.88 | 297.88 | 46.39 | 20
126 | Ministry of Coal | Coal | Kalyanikhani Opencast Project | Singareni Collieries Company Limited [SCCL] | 615858 | Telangana | 05/2017 | 03/2026 |  | 384.32 | 384.32 | 281.83 | 75
127 | Ministry of Coal | Coal | Kakathiya Khani Opencast - III Project Phase - I | Singareni Collieries Company Limited [SCCL] | 615859 | Telangana | 05/2017 | 03/2026 |  | 413.84 | 413.84 | 397.55 | 79
128 | Ministry of Coal | Coal | Godavarikhani Coal Mine - 5 | Singareni Collieries Company Limited [SCCL] | 615860 | Telangana | 05/2019 | 03/2025 | 03/2026 | 607.04 | 607.04 | 178.82 | 71
129 | Ministry of Coal | Coal | Indaram Opencast Project | Singareni Collieries Company Limited [SCCL] | 615861 | Telangana | 12/2022 | 03/2025 | 03/2026 | 424.81 | 424.81 | 402.64 | 80
130 | Ministry of Coal | Coal | Goleti Opencast Mine | Singareni Collieries Company Limited [SCCL] | 615862 | Telangana | 08/2021 | 03/2026 |  | 345.6 | 345.6 | 73.25 | 20
131 | Ministry of Coal | Coal | Venkatesh Khani Coal Mine | Singareni Collieries Company Limited [SCCL] | 615863 | Telangana | 06/2020 | 03/2026 |  | 484.5 | 484.5 | 434.44 | 75
132 | Ministry of Coal | Coal | Ramagundam OC-II Extension Project | Singareni Collieries Company Limited [SCCL] | 615864 | Telangana | 06/2015 | 03/2026 |  | 489.62 | 489.62 | 405.54 | 77
133 | Ministry of Coal | Coal | Kakatiyakhani OC - 2 Project | Singareni Collieries Company Limited [SCCL] | 615865 | Telangana | 09/2017 | 03/2025 | 03/2026 | 442.42 | 442.42 | 203.15 | 63
134 | Ministry of Coal | Coal | MOHANPUR EXPANSION OC -PHASE II | Eastern Coal Fields Limited [ECL] | 400173 | West Bengal | 11/2020 | 03/2026 |  | 888.99 | 888.99 | 85.51 | 30
135 | Ministry of Coal | Coal | BONJEMEHARI EXPANSION OCP | Eastern Coal Fields Limited [ECL] | 400180 | West Bengal | 08/2021 | 03/2026 | 03/2026 | 570.11 | 570.11 | 81.29 | 16
136 | Ministry of Coal | Coal | NAKRAKONDA KUMARDIH- B OCP | Eastern Coal Fields Limited [ECL] | 400181 | West Bengal | 08/2018 | 03/2029 |  | 502.68 | 502.68 | 70.97 | 25
137 | Ministry of Coal | Coal | SIDULI [OC & UG] | ECL - CIL | 400182 | West Bengal | 05/2018 | 03/2027 |  | 535.18 | 535.18 | 5.05 | 14
138 | Ministry of Coal | Coal | TILABONI UG | Eastern Coal Fields Limited [ECL] | 400186 | West Bengal | 03/2023 | 03/2029 | 03/2029 | 749.08 | 749.08 | 51.73 | 10
139 | Ministry of Coal | Coal | JHANJRA EXPANSION UG | Eastern Coal Fields Limited [ECL] | 400312 | West Bengal | 04/2020 | 03/2029 |  | 1210.12 | 1210.12 | 514.93 | 40
140 | Ministry of Coal | Coal | SONEPUR BAZARI EXPANSION OCP [12 MTY] | Eastern Coal Fields Limited [ECL] | 400315 | West Bengal | 07/2021 | 03/2029 |  | 5365.88 | 5365.88 | 571.02 | 17
141 | Ministry of Coal | Coal | 2.0 MTPA BHOJUDIH NLW WASHERY | Ministry of Coal | 611016 | West Bengal | 03/2019 | 09/2020 | 09/2025 | 384.57 | 384.57 | 353.21 | 97
142 | Ministry of Coal | Coal | ITAPARA OCP | Eastern Coal Fields Limited [ECL] | 612816 | West Bengal | 12/2023 | 03/2030 |  | 929.1 | 929.1 | 65.61 | 7
143 | Ministry of Coal | Coal | SHYAMSUNDARPUR UG INCLUDING SARPI | Eastern Coal Fields Limited [ECL] | 613793 | West Bengal | 04/2020 | 03/2026 |  | 483.65 | 483.65 | 55.89 | 12
144 | Ministry of Coal | Coal | PARASEA-BELBAID UG PROJECT | Eastern Coal Fields Limited [ECL] | 613794 | West Bengal | 01/2023 | 03/2028 |  | 389.1 | 389.1 | 131.42 | 16
145 | Ministry of Coal | Coal | PARASCOLE JAMBAD OCP | Eastern Coal Fields Limited [ECL] | 616230 | West Bengal | 11/2024 | 03/2037 |  | 1193.55 | 1193.55 | 6.79 | 0
146 | Ministry of Coal | Electricity Generation | 50 MW Wind Power Project | NLC India Limited [NLCIL] | 617299 | Gujarat | 02/2024 | 06/2025 | 01/2026 | 383.84 | 383.84 | 303.5 | 41
147 | Ministry of Coal | Electricity Generation | NLC Talabira Thermal Power Project | NLC India Limited [NLCIL] | 400231 | Odisha | 01/2024 | 03/2030 |  | 27212.96 | 27213 | 1938.68 | 1
148 | Ministry of Coal | Electricity Generation | 300 MW SPP part of 510 MW CPSU scheme | NLC India Limited [NLCIL] | 612819 | Rajasthan | 03/2023 | 09/2024 | 09/2025 | 1813 | 1813 | 769.57 | 68
149 | Ministry of Coal | Electricity Generation | 50 MW Solar PP Minedout Area | NLC India Limited [NLCIL] | 615327 | Tamil Nadu | 02/2024 | 03/2025 | 09/2025 | 218.03 | 218.03 | 160.93 | 46
150 | Ministry of Coal | Electricity Generation | Ghatampur Thermal Power Plant 3 X 660 MW | NLC India Limited [NLCIL] | 400259 | Uttar Pradesh | 08/2016 | 11/2020 | 10/2025 | 17237.8 | 21780.9 | 20135.48 | 92
151 | Ministry of Coal | Railways | Dharamjaigarh-Korba | WR | 400203 | Chhattisgarh | 03/2017 | 12/2026 | 08/2026 | 1686.22 | 1686.22 | 342.96 | 40
152 | Ministry of Coal | Railways | Shivpur-Kathautia New Rail [BG] Line [49 km] [Package II of Tori-Shivpur-Kathautia line] | Ministry of Coal | 400416 | Jharkhand | 05/2022 | 06/2025 |  | 1799.64 | 1799.64 | 1293.71 | 60
153 | Ministry of Power | Coal | Tubed Coal Mine | Damodar Valley Corporation | 400192 | Jharkhand | 10/2016 | 05/2026 | 05/2026 | 1581 | 1581 | 599.18 | 34
154 | Ministry of Power | Coal | Badam Coal Mining project of NTPC | National Thermal Power Corporation [NTPC] | 603293 | Jharkhand | 09/2019 | 12/2056 | 04/2027 | 502 | 784 | 302.2 | 59
155 | Ministry of Power | Electricity Generation | Dibang Multipurpose Project | National Highways & Infrastructure Development Corporation Ltd. [NHIDCL] | 602182 | Arunachal Pradesh | 02/2023 | 02/2032 | 02/2032 | 31876.39 | 31876.4 | 3436.38 | 16
156 | Ministry of Power | Electricity Generation | 240MW Heo HE Project | North Eastern Electric Power Corporation Limited | 611698 | Arunachal Pradesh | 05/2025 | 07/2029 |  | 1938.85 | 1938.85 | 49.31 | 3
157 | Ministry of Power | Electricity Generation | 186 MW Tato-I H E Project | North Eastern Electric Power Corporation Limited | 611699 | Arunachal Pradesh | 05/2025 | 07/2029 |  | 1750.07 | 1750.07 | 102.79 | 2
158 | Ministry of Power | Electricity Generation | Buxar Thermal Power Project [1320 MW] | Satluj Jal Vidyut Nigam [SJVN] Thermal Limited | 602579 | Bihar | 06/2019 | 01/2024 | 11/2025 | 10439.09 | 13756.6 | 11970.96 | 92
159 | Ministry of Power | Electricity Generation | Lara Super Thermal Power Project Stage-II [2 x 800 MW] | National Thermal Power Corporation [NTPC] | 611930 | Chhattisgarh | 08/2023 | 06/2028 |  | 15530 | 15530 | 2288 | 14
160 | Ministry of Power | Electricity Generation | Sipat Super Thermal Power Project, Stage-III [1x800 MW] | National Thermal Power Corporation [NTPC] | 617188 | Chhattisgarh | 09/2024 | 09/2029 |  | 9791 | 9791 | 0 | 0
161 | Ministry of Power | Electricity Generation | Bagodara Solar Power Project | Satluj Jal Vidyut Nigam [SJVN] Thermal Limited | 709747 | Gujarat | 05/2021 | 12/2025 | 12/2025 | 339.35 | 339.35 | 317.59 | 51
162 | Ministry of Power | Electricity Generation | Dhaulasidh Hydro Electric Project [66 MW] | Satluj Jal Vidyut Nigam [SJVN] Thermal Limited | 602582 | Himachal Pradesh | 05/2021 | 11/2025 | 03/2027 | 687.97 | 1511.87 | 908.65 | 67
163 | Ministry of Power | Electricity Generation | Luhri Stage-I Hydro Electric Project [210 MW] | Satluj Jal Vidyut Nigam [SJVN] Thermal Limited | 602593 | Himachal Pradesh | 11/2020 | 01/2026 | 08/2029 | 1810.56 | 3584.53 | 1742.92 | 51
164 | Ministry of Power | Electricity Generation | 382 MW Sunni Dam HEP | Satluj Jal Vidyut Nigam [SJVN] Thermal Limited | 602633 | Himachal Pradesh | 04/2018 | 03/2027 |  | 2615 | 2615 | 495.57 | 0.5
165 | Ministry of Power | Electricity Generation | Sunni Dam Hydro Electric Project [382 MW] | Satluj Jal Vidyut Nigam [SJVN] Thermal Limited | 611586 | Himachal Pradesh | 01/2023 | 04/2028 | 12/2028 | 2614.51 | 4540.71 | 956.76 | 29
166 | Ministry of Power | Electricity Generation | Pakal Dul [Drangdhuran] Hydroelectric Project, 1000 MW | National Highways & Infrastructure Development Corporation Ltd. [NHIDCL] | 602525 | Jammu and Kashmir | 02/2018 | 04/2020 | 09/2026 | 8112.12 | 8112.12 | 6916.1 | 71
167 | Ministry of Power | Electricity Generation | Kiru HE Project | National Highways & Infrastructure Development Corporation Ltd. [NHIDCL] | 602532 | Jammu and Kashmir | 03/2019 | 09/2023 | 03/2026 | 4287.59 | 4287.59 | 3055.87 | 66
168 | Ministry of Power | Electricity Generation | Ratle HE Project - 850 MW, Ratle Hydroelectric Power Corporation Limited. | National Highways & Infrastructure Development Corporation Ltd. [NHIDCL] | 602535 | Jammu and Kashmir | 02/2021 | 02/2026 | 08/2029 | 5281.94 | 5281.94 | 1009.79 | 24
169 | Ministry of Power | Electricity Generation | Kwar HE Project | National Highways & Infrastructure Development Corporation Ltd. [NHIDCL] | 605155 | Jammu and Kashmir | 05/2022 | 11/2026 |  | 4526.12 | 4526.12 | 1078.61 | 23
170 | Ministry of Power | Electricity Generation | Patratu Thermal Power Station Expansion Project Phase-I [3x800 MW] | National Thermal Power Corporation [NTPC] | 400261 | Jharkhand | 11/2017 | 03/2023 | 11/2026 | 17112 | 20302 | 17365 | 81
171 | Ministry of Power | Electricity Generation | Koderma Thermal Power Station Phase II [2X800 MW] At Koderma, Jharkhand | Damodar Valley Corporation | 611509 | Jharkhand | 11/2024 | 03/2029 |  | 14358 | 14358 | 1116.7 | 1
172 | Ministry of Power | Electricity Generation | OMKARESHWAR FLOATING SOLAR POWER PROJECT [90 MW] | Satluj Jal Vidyut Nigam [SJVN] Thermal Limited | 709820 | Madhya Pradesh | 11/2022 | 08/2024 |  | 646.17 | 646.17 | 0 | 0
173 | Ministry of Power | Electricity Generation | Subansiri Lower HE Project [2000 MW] | National Highways & Infrastructure Development Corporation Ltd. [NHIDCL] | 602096 | Multi-States (Arunachal Pradesh, Assam) | 09/2003 | 09/2010 | 05/2026 | 6285.33 | 26075.5 | 24685.13 | 96
174 | Ministry of Power | Electricity Generation | Talcher Thermal Power Station Stage III [2 x 660 MW] Expansion | National Thermal Power Corporation [NTPC] | 602961 | Odisha | 09/2022 | 05/2027 | 03/2028 | 11843.75 | 12543 | 3975 | 26
175 | Ministry of Power | Electricity Generation | BIKANER SOLAR POWER PROJECT | Satluj Jal Vidyut Nigam [SJVN] Thermal Limited | 709748 | Rajasthan | 05/2022 | 04/2024 | 12/2025 | 5491.89 | 5491.89 | 4606.84 | 82
176 | Ministry of Power | Electricity Generation | TEESTA-VI HE PROJECT, SIKKIM [500 MW], executed by LANCO TEESTA HYDRO POWER LIMITED [A wholly owned Subsidiary of NHPC LTD. acquired through NCLT] | National Highways & Infrastructure Development Corporation Ltd. [NHIDCL] | 602181 | Sikkim | 03/2019 | 03/2024 | 12/2027 | 5748.04 | 5748.04 | 4495.28 | 68
177 | Ministry of Power | Electricity Generation | Rangit-IV HE Project [120 MW] executed by Jal Power Corporation Ltd. [JPCL] -A wholly owned subsidiary of NHPC Ltd. acquired through NCLT | National Highways & Infrastructure Development Corporation Ltd. [NHIDCL] | 605156 | Sikkim | 03/2021 | 05/2024 | 12/2025 | 938.29 | 1828.11 | 1554.15 | 90
178 | Ministry of Power | Electricity Generation | Khurja super Thermal Power Plant [2X660 MW] | THDC India Limited | 602194 | Uttar Pradesh | 08/2019 | 02/2024 | 08/2025 | 11089.42 | 13276.2 | 12429.05 | 96
179 | Ministry of Power | Electricity Generation | Singrauli Super Thermal Power Project, Stage-III [2x800 MW] | National Thermal Power Corporation [NTPC] | 612142 | Uttar Pradesh | 03/2024 | 02/2030 |  | 17195 | 17195 | 1626 | 8
180 | Ministry of Power | Electricity Generation | Tapovan-Vishnugad HEP [4x130 MW] | National Thermal Power Corporation [NTPC] | 602185 | Uttarakhand | 11/2006 | 03/2013 | 04/2029 | 2978 | 10907.3 | 7123.58 | 77
181 | Ministry of Power | Electricity Generation | Tehri Pumped Storage Plant Project [4x250 MW] | THDC India Limited | 602193 | Uttarakhand | 06/2011 | 06/2022 | 11/2025 | 4825.6 | 8339 | 7939.82 | 98
182 | Ministry of Power | Electricity Generation | Vishnugad Pipalkoti Hydro Electric Project [444 MW] | THDC India Limited | 602195 | Uttarakhand | 01/2014 | 12/2022 | 03/2027 | 3860.35 | 6823.72 | 4828.89 | 72
183 | Ministry of Power | Electricity Generation | Raghunathpur Thermal Power Station Phase II [2X660 MW] at Raghunathpur, Purulia, West Bengal | Damodar Valley Corporation | 400062 | West Bengal | 02/2025 | 06/2029 |  | 17673 | 17673 | 1183.7 | 1
184 | Ministry of Power | Electricity Generation | Rammam-III HEPP [3x40 MW] | National Thermal Power Corporation [NTPC] | 602184 | West Bengal | 09/2014 | 09/2019 | 03/2029 | 1381.84 | 1381.84 | 1266 | 45
185 | Ministry of Power | Electricity Generation | Installation of FGD for 4x210 & 2x250 MW MTPS U 1-6 | Damodar Valley Corporation | 602538 | West Bengal | 02/2021 | 01/2024 | 12/2025 | 1037 | 1106 | 1085.39 | 91
186 | Ministry of Power | Transmission & Distribution | Transmission Scheme for Solar Energy Zone in Ananthpuram 2500MW and Kurnool 1000MW | Power Grid Corporation of India Limited [POWERGRID] | 611967 | Andhra Pradesh | 09/2023 | 09/2025 | 04/2026 | 1248.69 | 1248.69 | 820.26 | 78
187 | Ministry of Power | Transmission & Distribution | Augmentation of 1x1500 MVA 3rd 765/400 kV transformation capacity at Kurnool New Substation | Power Grid Corporation of India Limited [POWERGRID] | 612856 | Andhra Pradesh | 12/2023 | 09/2025 | 11/2025 | 163.61 | 163.61 | 50.72 | 39
188 | Ministry of Power | Transmission & Distribution | Transmission system strengthening at Kurnool- III PS for integration of additional RE generation projects [POWERGRID Kurnool III PS RE Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 617183 | Andhra Pradesh | 03/2025 | 12/2027 |  | 2886 | 2886 | 28.86 | 0
189 | Ministry of Power | Transmission & Distribution | Western Region Expansion Scheme-XXV | Power Grid Corporation of India Limited [POWERGRID] | 611737 | Chhattisgarh | 02/2023 | 11/2023 | 09/2025 | 385.84 | 385.84 | 378.16 | 96
190 | Ministry of Power | Transmission & Distribution | Transmission scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase II- Part B | Power Grid Corporation of India Limited [POWERGRID] | 611656 | Gujarat | 03/2023 | 03/2025 | 10/2025 | 1167.55 | 1167 | 1013.39 | 91
191 | Ministry of Power | Transmission & Distribution | Transmission scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase II- Part C | Power Grid Corporation of India Limited [POWERGRID] | 611657 | Gujarat | 03/2023 | 03/2025 | 11/2025 | 2820.99 | 2820.99 | 2454.26 | 84
192 | Ministry of Power | Transmission & Distribution | Establishment of Khavda Pooling Station-2 KPS2 in Khavda RE Park KPS2 TRANSMISSION SYSTEM LIMITED | Power Grid Corporation of India Limited [POWERGRID] | 611660 | Gujarat | 03/2023 | 12/2024 | 08/2025 | 966.79 | 966.79 | 894.76 | 95
193 | Ministry of Power | Transmission & Distribution | Transmission system for Evacuation of Additional 7 GW RE power from Khavda RE park under Phase-III Part B [Vataman Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 612139 | Gujarat | 12/2023 | 12/2025 | 06/2026 | 3751.82 | 3751.82 | 1500.72 | 21
194 | Ministry of Power | Transmission & Distribution | Transmission System for Evacuation of Power from potential Renewable Energy zone in Khavda Area of Gujarat under Phase IV [7 GW] Part E3 | Power Grid Corporation of India Limited [POWERGRID] | 612151 | Gujarat | 07/2023 | 07/2025 | 10/2025 | 334 | 334 | 70.44 | 22
195 | Ministry of Power | Transmission & Distribution | Transmission System for Evacuation of Power from Potential Energy Renewable Zone in Khavda Area of Gujarat under Ph-IV [7GW] Part E2 | Power Grid Corporation of India Limited [POWERGRID] | 612855 | Gujarat | 05/2024 | 05/2026 | 02/2026 | 679 | 679 | 81.48 | 18
196 | Ministry of Power | Transmission & Distribution | Augmentation of Transformation Capacity at jam Khambhaliya PS [GIS] [SPV Name POWERGRID Jam Khambhaliya Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 615342 | Gujarat | 10/2024 | 07/2026 |  | 329 | 329 | 9.97 | 1
197 | Ministry of Power | Transmission & Distribution | Provision of Dynamic Reactive Compensation at Khavda pooling Station 1 [KPS1] and Khavda Pooling station 3 [KPS3] | Power Grid Corporation of India Limited [POWERGRID] | 615343 | Gujarat | 11/2024 | 11/2026 |  | 501 | 501 | 5.01 | 1
198 | Ministry of Power | Transmission & Distribution | Transmission System for Evacuation of Power from Potential Renewable Energy Zone in Khavda area of Gujarat under Phase-IV [7GW] Part B [SPV Name POWERGRID South Olpad Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 615345 | Gujarat | 10/2024 | 10/2026 |  | 4766 | 4766 | 513.29 | 5
199 | Ministry of Power | Transmission & Distribution | Augmentation of Transformation Capacity at KPS1 [GIS] and KPS2 [GIS] [Phase-V Part B1 and Part B2 Scheme] [SPV Name- POWERGRID KPS1 and 2 Augmentation Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 617069 | Gujarat | 02/2025 | 02/2027 |  | 466 | 466 | 6.99 | 0
200 | Ministry of Power | Transmission & Distribution | Augmentation of Banaskantha [Raghanesda] PS [GIS] [POWERGRID Banaskantha Transco Limited] | Power Grid Corporation of India Limited [POWERGRID] | 617182 | Gujarat | 03/2025 | 03/2027 |  | 172 | 172 | 1.72 | 0
201 | Ministry of Power | Transmission & Distribution | Implementation of LILO of both circuits of 400KV vindhyachal PS-Sasan D/C Line at Hindalco Switchyard | Power Grid Corporation of India Limited [POWERGRID] | 617272 | Haryana | 06/2024 | 12/2026 |  | 370 | 370 | 1 | 1
202 | Ministry of Power | Transmission & Distribution | Transmission system for evacuation of Power from Pakaldul HEP in Chenab Valley HEPs - LTA System | Power Grid Corporation of India Limited [POWERGRID] | 608302 | Jammu and Kashmir | 02/2022 | 04/2025 | 08/2025 | 318.12 | 318.12 | 286.31 | 99
203 | Ministry of Power | Transmission & Distribution | Transmission Scheme for evacuation of Power from Ratle HEP [850 MW] & kiru [624 MW] Part B | Power Grid Corporation of India Limited [POWERGRID] | 617179 | Jammu and Kashmir | 07/2024 | 07/2026 |  | 218.6 | 218.6 | 0 | 0
204 | Ministry of Power | Transmission & Distribution | Transmission Scheme for Integration of Renewable Energy Zone [Phase II] in Koppal II [Phase A&B] and gadag II[Phase A] in Karnataka [POWERGRID KOPPAL GADAG TRANSMISSION LIMITED] | Power Grid Corporation of India Limited [POWERGRID] | 612140 | Karnataka | 12/2023 | 12/2025 |  | 2889.39 | 2889.39 | 1154.31 | 37
205 | Ministry of Power | Transmission & Distribution | System Strengthening at Koppal-II and GadagII for integration of RE generation projects [SPV Name POWERGRID Koppal Gadag Augmentation Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 616672 | Karnataka | 01/2025 | 06/2027 |  | 1354 | 1354 | 16.65 | 0
206 | Ministry of Power | Transmission & Distribution | Augmentation of Transformation Capacity by 3x500 MVA, 400/220 KV ICTS [6th-8th] and 1x1500 MVA, 765/400 KV ICT [4th] at Bidar PS [SPV Name- POWERGRID Bidar Augmentation Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 617068 | Karnataka | 02/2025 | 06/2027 |  | 288 | 288 | 5.76 | 0
207 | Ministry of Power | Transmission & Distribution | Transmission Scheme for integration of Davanagere/ Chitradurga and Bellary REZ in Karnataka [POWERGRID Chitradurga Bellary REZ Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 617184 | Karnataka | 03/2025 | 09/2027 |  | 3453 | 3453 | 20.7 | 0
208 | Ministry of Power | Transmission & Distribution | Transmission System for Evacuation of Power from Rajasthan REZ Ph-IV [Part-2 5.5GW] [Jaisalmer/Barmer Complex] Part H1 [POWERGRID KURAWAR TRANSMISSION LIMITED] | Power Grid Corporation of India Limited [POWERGRID] | 615344 | Madhya Pradesh | 10/2024 | 10/2026 |  | 3674 | 3674 | 408.18 | 13
209 | Ministry of Power | Transmission & Distribution | Transmission System for Evacuation of Power from Rajasthan REZ Ph-IV [Part-2 5.5 GW] [Jaisalmer/Barmer Complex] Part C [SPV Name POWERGRID Mandsaur Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 615346 | Madhya Pradesh | 08/2024 | 08/2026 |  | 2708 | 2708 | 649.92 | 26
210 | Ministry of Power | Transmission & Distribution | Transmission System for evacuation of power from Mahan Energen Limited Generating Station in Madhya Pradesh [SPV Name - POWERGRID MEL Power Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 617279 | Madhya Pradesh | 06/2025 | 12/2027 |  | 558 | 558 | 5.58 | 0
211 | Ministry of Power | Transmission & Distribution | Transmission System for Evacuation of power from Potential RE Zone in Khavda Area of Gujarat under phase IV 7GW-Part E4 | Power Grid Corporation of India Limited [POWERGRID] | 611966 | Maharashtra | 11/2023 | 07/2025 | 11/2025 | 224.41 | 224.41 | 22.44 | 9
212 | Ministry of Power | Transmission & Distribution | Transmission System for Integration of Kurnool-IV REZ Phase-I [for 4.5 GW] [POWERGRID Kurnool-IV Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 617185 | Multi-States (Andhra Pradesh, Karnataka) | 03/2025 | 03/2027 |  | 5550 | 5550 | 111 | 0
213 | Ministry of Power | Transmission & Distribution | Transmission System for Kurnool Wind Energy Zone/ Solar Energy Zone Part-A and Part-B | Power Grid Corporation of India Limited [POWERGRID] | 900808 | Multi-States (Andhra Pradesh, Telangana) | 03/2023 | 11/2024 | 12/2025 | 3546.94 | 3546.94 | 3121.3 | 94
214 | Ministry of Power | Transmission & Distribution | Comprehensive Scheme for Strengthening of Transmission and Distribution [T&D] Systems [CSST&DS] in Arunachal Pradesh and Sikkim | Power Grid Corporation of India Limited [POWERGRID] | 602223 | Multi-States (Arunachal Pradesh, Sikkim) | 01/2016 | 12/2018 | 03/2027 | 4754.42 | 4754.42 | 7321.07 | 81
215 | Ministry of Power | Transmission & Distribution | NORTH EASTERN REGION POWER SYSTEM IMPROVEMENT PROJECT [NERPSIP] | Power Grid Corporation of India Limited [POWERGRID] | 607709 | Multi-States (Assam, Manipur, Meghalaya, Mizoram, Nagaland, Tripura) | 03/2016 | 12/2018 | 09/2025 | 5111.33 | 6700 | 5253.47 | 96
216 | Ministry of Power | Transmission & Distribution | Eastern Region Expansion Scheme-43 [ERES-43] | Power Grid Corporation of India Limited [POWERGRID] | 617271 | Multi-States (Bihar, Odisha, West Bengal) | 09/2024 | 03/2026 |  | 342.69 | 342.69 | 0.2 | 0
217 | Ministry of Power | Transmission & Distribution | Eastern Region Expansion Scheme-44 [ERES-44] | Power Grid Corporation of India Limited [POWERGRID] | 617270 | Multi-States (Bihar, West Bengal) | 11/2024 | 05/2026 |  | 408.94 | 408.94 | 0.2 | 0
218 | Ministry of Power | Transmission & Distribution | Transmission Network Expansion in Gujarat to increase its ATC from ISTS Part B | Power Grid Corporation of India Limited [POWERGRID] | 400005 | Multi-States (Dadra & Nagar Haveli and Daman & Diu, Gujarat, Maharashtra) | 07/2022 | 06/2023 | 12/2025 | 4546.26 | 4546.26 | 4148.46 | 93
219 | Ministry of Power | Transmission & Distribution | Transmission System Strengthening Scheme for evacuation of power from SEZ in Rajasthan 8.1 GW under Phase II Part G | Power Grid Corporation of India Limited [POWERGRID] | 608922 | Multi-States (Delhi, Haryana, Rajasthan) | 05/2022 | 11/2023 | 11/2025 | 1666 | 2218 | 2139.28 | 95
220 | Ministry of Power | Transmission & Distribution | Transmission system for evacuation of power from REZ in Rajasthan 20GW under Phase-III Part J | Power Grid Corporation of India Limited [POWERGRID] | 611735 | Multi-States (Delhi, Rajasthan) | 12/2022 | 03/2025 | 04/2026 | 331 | 331 | 75.92 | 28
221 | Ministry of Power | Transmission & Distribution | Transmission Scheme for Evacuation of power from REZ in Rajasthan [20 GW] under Phase-III Part D [Sikar Khetri Transmission Ltd] | Power Grid Corporation of India Limited [POWERGRID] | 612132 | Multi-States (Delhi, Rajasthan) | 02/2024 | 08/2025 | 05/2026 | 2000 | 2000 | 1314.8 | 59
222 | Ministry of Power | Transmission & Distribution | Transmission system strengthening scheme for evacuation of power from solar energy zones in Rajasthan 8.1 GW under Phase II- Part- G1 | Power Grid Corporation of India Limited [POWERGRID] | 608301 | Multi-States (Delhi, Uttar Pradesh) | 02/2022 | 09/2023 | 11/2025 | 359.47 | 359.47 | 330.71 | 93
223 | Ministry of Power | Transmission & Distribution | TRANSMISSION SYSTEM FOR EVACUATION OF POWER FROM POTENTIAL RENEWABLE ENERGY ZONE IN KHAVDA AREA OF GUJARAT UNDER PHASE-V [8 GW] PART A [SPV Name POWERGRID West Central Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 615347 | Multi-States (Gujarat, Maharashtra) | 11/2024 | 05/2029 |  | 24819 | 24819 | 1489.14 | 1
224 | Ministry of Power | Transmission & Distribution | Transmission system for evacuation of power from Rajasthan REZ Ph-IV [Part- 3/6GW] [Bikaner complex] Part A [SPV Name POWERGRID Bikaner IV Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 615339 | Multi-States (Haryana, Punjab, Rajasthan) | 11/2024 | 11/2026 |  | 5969 | 5969 | 167.13 | 4
225 | Ministry of Power | Transmission & Distribution | TRANSMISSION SYSTEM FOR EVACUATION OF POWER FROM RAJASTHAN REZ PH-IV [PART-3/ 6 GW] [BIKANER COMPLEX] PART B [SPV Name POWERGRID Siwani Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 615340 | Multi-States (Haryana, Rajasthan) | 11/2024 | 11/2026 |  | 5357 | 5357 | 267.85 | 8
226 | Ministry of Power | Transmission & Distribution | Transmission System for Strengthening of Srinagar-Leh Tr. System | Power Grid Corporation of India Limited [POWERGRID] | 606781 | Multi-States (Jammu and Kashmir, Ladakh) | 03/2022 | 12/2024 | 09/2025 | 288.71 | 288.71 | 202.1 | 59
227 | Ministry of Power | Transmission & Distribution | Transmission Scheme for Solar Energy Zone in Bidar [2500 MW], Karnataka [Bidar Transmission Ltd] | Power Grid Corporation of India Limited [POWERGRID] | 612138 | Multi-States (Karnataka, Telangana) | 02/2024 | 02/2026 |  | 2147.62 | 2147.62 | 1068.65 | 55
228 | Ministry of Power | Transmission & Distribution | Transmission System for Evacuation of Power from Rajasthan REZ Ph-IV [Part-2 5.5 GW] [Jaisalmer/Barmer Complex] Part D [SPV Name POWERGRID Beawar Mandsaur Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 615333 | Multi-States (Madhya Pradesh, Rajasthan) | 08/2024 | 08/2026 |  | 2227 | 2227 | 534.48 | 19
229 | Ministry of Power | Transmission & Distribution | Transmission System for Evacuation of Power from Rajasthan REZ Ph-IV [Part-2 5.5 GW] [Jaisalmer/Barmer Complex] Part E [SPV Name POWERGRID Mewar Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 615334 | Multi-States (Madhya Pradesh, Rajasthan) | 08/2024 | 08/2026 |  | 3251 | 3251 | 685.96 | 17
230 | Ministry of Power | Transmission & Distribution | Rajasthan REZ Ph-V [Part-1- 4 GW] [Sirohi/Nagaur] Complex [Rajasthan V Power Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 617186 | Multi-States (Madhya Pradesh, Rajasthan) | 03/2025 | 03/2027 |  | 5028 | 5028 | 139.2 | 1
231 | Ministry of Power | Transmission & Distribution | Transmission System for Evacuation of power from Rajasthan REZ Ph-IV [Part-1] [Bikaner Complex] Part D [Neemrana Bareilly Transmission Ltd] | Power Grid Corporation of India Limited [POWERGRID] | 612133 | Multi-States (Rajasthan, Uttar Pradesh) | 12/2023 | 12/2025 | 06/2026 | 2056 | 2056 | 1336.4 | 55
232 | Ministry of Power | Transmission & Distribution | Transmission System for evacuation of Power from Rajasthan REZ Ph-IV [Part-4 3.5 GW] Part A [SPV name POWERGRID Ghiror Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 616670 | Multi-States (Rajasthan, Uttar Pradesh) | 12/2024 | 12/2026 |  | 5846 | 5846 | 236.18 | 3
233 | Ministry of Power | Transmission & Distribution | Transmission system strengthening scheme for evacuation of power from solar energy zones in Rajasthan[8.1 GW] under phase-II- Part E | Power Grid Corporation of India Limited [POWERGRID] | 611659 | Rajasthan | 03/2023 | 09/2024 | 10/2025 | 1433.28 | 1433 | 1341.7 | 93
234 | Ministry of Power | Transmission & Distribution | Transmission System for Evacuation of Power from REZ in Rajasthan 20GW under Phase III- Part E2 | Power Grid Corporation of India Limited [POWERGRID] | 611947 | Rajasthan | 11/2023 | 06/2025 | 09/2025 | 428.3 | 428.3 | 107.07 | 46
235 | Ministry of Power | Transmission & Distribution | Transmission system for evacuation of power from REZ in Rajasthan 20 GW under Phase-III part H | Power Grid Corporation of India Limited [POWERGRID] | 611948 | Rajasthan | 10/2023 | 04/2025 | 12/2025 | 2211.29 | 2211.29 | 1780.53 | 72
236 | Ministry of Power | Transmission & Distribution | Transmission system for evacuation of power from REZ in Rajasthan 20 GW under Phase-III part C1 | Power Grid Corporation of India Limited [POWERGRID] | 611949 | Rajasthan | 10/2023 | 04/2025 | 10/2025 | 1796.02 | 1796.02 | 1201.17 | 79
237 | Ministry of Power | Transmission & Distribution | Transmission system for evacuation of power from REZ in Rajasthan 20 GW under Phase-III part B1 | Power Grid Corporation of India Limited [POWERGRID] | 611950 | Rajasthan | 09/2023 | 04/2025 | 12/2025 | 2190.54 | 2190.54 | 1740.6 | 77
238 | Ministry of Power | Transmission & Distribution | Transmission system for evacuation of power from REZ in Rajasthan 20GW under Phase-III Part E1 | Power Grid Corporation of India Limited [POWERGRID] | 611951 | Rajasthan | 08/2023 | 02/2025 | 09/2025 | 688.74 | 688.74 | 585.42 | 93
239 | Ministry of Power | Transmission & Distribution | Transmission System for Evacuation of power from Rajasthan REZ Ph-IV [Part-1] [Bikaner Complex] Part A [Bikaner Neemrana Transmission Ltd] | Power Grid Corporation of India Limited [POWERGRID] | 612134 | Rajasthan | 12/2023 | 12/2025 | 03/2026 | 2998.34 | 2998.34 | 1592.11 | 49
240 | Ministry of Power | Transmission & Distribution | Transmission System for Evacuation of Power from Rajasthan REZ Ph-IV [Part-2 5.5 GW][Jaisalmer/Barmer Complex] Part B [SPV Name POWERGRID Sirohi Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 615332 | Rajasthan | 08/2024 | 08/2026 |  | 3279 | 3279 | 547.59 | 19
241 | Ministry of Power | Transmission & Distribution | Transmission System Strengthening for Interconnections of Bhadla-III & Bikaner III Complex [SPV Name POWERGRID BHADLA BIKANER TRANSMISSION LIMITED] | Power Grid Corporation of India Limited [POWERGRID] | 615335 | Rajasthan | 08/2024 | 08/2026 |  | 1382 | 1382 | 41.46 | 2
242 | Ministry of Power | Transmission & Distribution | Additional Transmission System for evacuation of Power from Bhadla-III PS as part of Rajasthan REZ Phase III Scheme [20 GW] [SPV Name POWERGRID Bhadla-III Power Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 615337 | Rajasthan | 08/2024 | 02/2026 |  | 369 | 369 | 17.82 | 6
243 | Ministry of Power | Transmission & Distribution | TRANSMISSION SYSTEM FOR EVACUATION OF POWER FROM RAJASTHAN REZ PH -IV [PART-2 5.5 GW] [JAISALMER/BARMER COMPLEX] PART F [SPV Name POWERGRID BARMER I TRANSMISSION LIMITED] | Power Grid Corporation of India Limited [POWERGRID] | 615338 | Rajasthan | 11/2024 | 11/2026 |  | 2735 | 2735 | 81.42 | 5
244 | Ministry of Power | Transmission & Distribution | Augmentation at Fatehgarh-II PS, Fatehgarh-IV PS [Section-II] and Barmer-I PS [POWERGRID Fatehgarh Barmer Augmentation Transmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 617181 | Rajasthan | 03/2025 | 12/2026 |  | 404 | 404 | 4.04 | 0
245 | Ministry of Power | Transmission & Distribution | Transmission System under ISTS for evacuation of Power from Kudankulam Unit-3&4 [2x1000 MW] [SPV Name POWERGRID Kudankulam Tarnsmission Limited] | Power Grid Corporation of India Limited [POWERGRID] | 616671 | Tamil Nadu | 01/2025 | 12/2026 | 12/2026 | 548 | 548 | 10.96 | 4
246 | Ministry of Power | Transmission & Distribution | Transmission System for Strengthening to facilitate evacuation of power from Bhadla/Bikaner Complex | Power Grid Corporation of India Limited [POWERGRID] | 617269 | Uttar Pradesh | 12/2024 | 06/2026 |  | 212.81 | 212.81 | 0.2 | 0
247 | Ministry of Housing & Urban Affairs | Construction | C/o 184 MS Flats for Hon'ble MPs at BKS Marg, New Delhi | Central Public Works Department [CPWD] | 617282 | Delhi | 05/2022 | 05/2025 | 08/2025 | 646.53 | 646.52 | 518.46 | 98
248 | Ministry of Housing & Urban Affairs | Inland Waterways | Chennai Metro Rail Phase-II Development Project | Chennai Metro Rail Limited [CMRL] | 702668 | Tamil Nadu | 11/2020 | 08/2029 |  | 63246 | 63246 | 47162.73 | 0
249 | Ministry of Housing & Urban Affairs | Real Estate | Integrated Command control Center [ICCC] - Construction and Development of Integrated Command Control Center with Security, Surveillance, ITMS, Connecting Port, Ship Service, Smart Solid Waste Management, Smart Public Transport System | Smart City Mission | 707229 | Andaman & Nicobar | 11/2021 | 05/2023 |  | 209.88 | 209.88 | 0 | 0
250 | Ministry of Housing & Urban Affairs | Real Estate | In-Situ Slum Redevelopment Project in Bihar | PMAY, Ministry of Housing and Urban Affairs | 702522 | Bihar | 06/2015 | 03/2024 |  | 454.65 | 454.65 | 204.64 | 0
251 | Ministry of Housing & Urban Affairs | Real Estate | In-Situ Slum Redevelopment Project in Haryana | PMAY, Ministry of Housing and Urban Affairs | 702544 | Chandigarh | 06/2015 | 03/2024 |  | 285.85 | 285.85 | 127.58 | 0
252 | Ministry of Housing & Urban Affairs | Real Estate | Affordable Housing Construction Project in Chhattisgarh | PMAY, Ministry of Housing and Urban Affairs | 702524 | Chhattisgarh | 06/2015 | 03/2024 |  | 3797.69 | 3797.69 | 2694 | 0
253 | Ministry of Housing & Urban Affairs | Real Estate | Redevelopment of Seven General Pool Residential Accommodation [GPRA] Colonies in Delhi | National Buildings Construction Corporation [NBCC] | 400188 | Delhi | 05/2018 | 12/2022 | 12/2025 | 32850 | 32850 | 0 | 0
254 | Ministry of Housing & Urban Affairs | Real Estate | Rehablitation in Junavadaj Area Smart City Project | Ministry of Housing & Urban Affairs | 701719 | Gujarat | 06/2016 | 07/2022 |  | 539 | 539 | 39.63 | 50
255 | Ministry of Housing & Urban Affairs | Real Estate | In-Situ Slum Redevelopment Project in Gujarat | PMAY, Ministry of Housing and Urban Affairs | 702540 | Gujarat | 06/2015 | 03/2024 |  | 5477.4 | 5477.4 | 3035.81 | 0
256 | Ministry of Housing & Urban Affairs | Real Estate | In-Situ Slum Redevelopment Project in Jharkhand | PMAY, Ministry of Housing and Urban Affairs | 702555 | Jharkhand | 06/2015 | 03/2024 |  | 212.74 | 212.74 | 41 | 0
257 | Ministry of Housing & Urban Affairs | Real Estate | In-Situ Slum Redevelopment Project in Uttar Pradesh | PMAY, Ministry of Housing and Urban Affairs | 702612 | Uttar Pradesh | 06/2015 | 03/2024 |  | 576.99 | 576.99 | 141.94 | 0
258 | Ministry of Housing & Urban Affairs | Real Estate | Green Building Development Project | Ministry of Housing & Urban Affairs | 701766 | Uttarakhand | 08/2019 | 11/2023 |  | 150.97 | 150.97 | 18.95 | 0
259 | Ministry of Housing & Urban Affairs | Urban Public Transport | Patna Metro Rail Project | Patna Metro Rail Corporation Ltd. [PMRCL] | 702627 | Bihar | 02/2019 | 02/2024 | 06/2027 | 13365.77 | 13365.8 | 4039.77 | 40.07
260 | Ministry of Housing & Urban Affairs | Urban Public Transport | Delhi Metro Rail Phase-IV [2 Corridors] | Delhi Metro Rail Corporation Limited [DMRC] | 617207 | Delhi | 03/2024 | 03/2029 |  | 8399.81 | 8399.81 | 5.57 | 0
261 | Ministry of Housing & Urban Affairs | Urban Public Transport | DMRTS Phase - IV [3 Priority Corridors] | Delhi Metro Rail Corporation Limited [DMRC] | 702632 | Delhi | 07/2019 | 03/2025 | 03/2026 | 24948.65 | 24948.7 | 15423.06 | 68
262 | Ministry of Housing & Urban Affairs | Urban Public Transport | Surat Metro Rail Project | Gujarat Metro Rail Corporation Limited [GMRCL] | 702630 | Gujarat | 04/2019 | 03/2024 | 06/2026 | 12020.32 | 12020.3 | 7386.41 | 68
263 | Ministry of Housing & Urban Affairs | Urban Public Transport | Ahmedabad Metro Rail Project, Phase-II | Gujarat Metro Rail Corporation Limited [GMRCL] | 702631 | Gujarat | 03/2019 | 03/2024 | 12/2025 | 5384.17 | 5384.17 | 4151.57 | 87
264 | Ministry of Housing & Urban Affairs | Urban Public Transport | Ahmedabad Metro Rail Project [Phase-I] | Gujarat Metro Rail Corporation Limited [GMRCL] | 702639 | Gujarat | 03/2018 | 03/2018 | 08/2025 | 10773 | 12924.5 | 11857.91 | 99.34
265 | Ministry of Housing & Urban Affairs | Urban Public Transport | Construction of Bangalore Metro Rail Project Phase 2. | Bengaluru Metro Rail | 702635 | Karnataka | 02/2016 | 03/2021 | 09/2026 | 26405.14 | 30695.1 | 29477.97 | 94
266 | Ministry of Housing & Urban Affairs | Urban Public Transport | Construction Bangalore Metro Rail Project Phase-2A & 2B | Bengaluru Metro Rail | 702665 | Karnataka | 01/2019 | 06/2026 | 06/2026 | 14788.1 | 14788.1 | 8424.54 | 53
267 | Ministry of Housing & Urban Affairs | Urban Public Transport | Kochi Metro Rail Phase 2 Development Project | CSPCC Projects | 702664 | Kerala | 11/2022 | 11/2026 | 11/2026 | 1957.05 | 1957.05 | 306.45 | 10
268 | Ministry of Housing & Urban Affairs | Urban Public Transport | Bhopal Metro Rail Project | Madhya Pradesh Metro Rail Co Limited [MPMRCL] | 702625 | Madhya Pradesh | 11/2018 | 11/2022 | 06/2028 | 6941.4 | 6941.4 | 3116.75 | 43
269 | Ministry of Housing & Urban Affairs | Urban Public Transport | Indore Metro Rail Project | Madhya Pradesh Metro Rail Co Limited [MPMRCL] | 702626 | Madhya Pradesh | 11/2018 | 11/2022 | 12/2028 | 7500.8 | 7500.8 | 3839.27 | 54
270 | Ministry of Housing & Urban Affairs | Urban Public Transport | PCMC To Nigdi- Extension Of North South Corridor Of Phase-1 | Maharashtra Metro Rail Corporation Limited [MMRCL] | 617225 | Maharashtra | 10/2023 | 01/2027 |  | 910.18 | 910.18 | 110.33 | 21
271 | Ministry of Housing & Urban Affairs | Urban Public Transport | Pune Metro Phase-1 Extension line towards south from Swargate to Katraj | Maharashtra Metro Rail Corporation Limited [MMRCL] | 617226 | Maharashtra | 09/2024 | 03/2029 |  | 2954.53 | 2954.53 | 18.66 | 3
272 | Ministry of Housing & Urban Affairs | Urban Public Transport | New Suburba Station Development Project | Ministry of Housing & Urban Affairs | 701745 | Maharashtra | 03/2019 | 07/2022 |  | 262.76 | 262.76 | 17.62 | 6
273 | Ministry of Housing & Urban Affairs | Urban Public Transport | Kalyan Station Precinct Imporvement Project | Ministry of Housing & Urban Affairs | 701991 | Maharashtra | 07/2020 | 07/2023 |  | 600 | 600 | 49.42 | 0
274 | Ministry of Housing & Urban Affairs | Urban Public Transport | Mumbai Metro Line 3 | Mumbai Metro Rail Corporation Limited [MMRC] | 702637 | Maharashtra | 06/2016 | 03/2023 | 06/2024 | 23136 | 23942 | 27519.07 | 91.9
275 | Ministry of Housing & Urban Affairs | Urban Public Transport | Nagpur Metro Rail Phase II Development Project | Maharashtra Metro Rail Corporation Limited [MMRCL] | 702658 | Maharashtra | 12/2022 | 12/2027 |  | 6708 | 6708 | 977.38 | 24
276 | Ministry of Housing & Urban Affairs | Urban Public Transport | Delhi Metro Rail Phase-IV [Rithala - Kundli Corridor] | Delhi Metro Rail Corporation Limited [DMRC] | 617206 | Multi-States (Delhi, Haryana) | 01/2025 | 01/2029 |  | 6230.99 | 6230.99 | 0.14 | 0
277 | Ministry of Housing & Urban Affairs | Urban Public Transport | Delhi-Ghaziabad-Meerut Regional Rapid Transit System [RRTS] corridor | National Capital Region Transport Corporation [NCRTC] | 702633 | Multi-States (Delhi, Uttar Pradesh) | 03/2019 | 06/2025 |  | 30274 | 30274 | 25812.26 | 86
278 | Ministry of Housing & Urban Affairs | Urban Public Transport | Kanpur Metro Rail Project | Uttar Pradesh metro rail corporation [UPMRC] | 702628 | Uttar Pradesh | 11/2019 | 05/2024 | 03/2027 | 11076.48 | 11076.5 | 9079.81 | 73
279 | Ministry of Housing & Urban Affairs | Urban Public Transport | Agra Metro Rail Project | Uttar Pradesh metro rail corporation [UPMRC] | 702629 | Uttar Pradesh | 12/2020 | 05/2024 | 06/2027 | 8379.62 | 8379.62 | 6055.19 | 57
280 | Ministry of Housing & Urban Affairs | Waste & Water | Storm water drainag Development Project | Ministry of Housing & Urban Affairs | 702355 | Dadra & Nagar Haveli and Daman & Diu | 12/2021 | 03/2024 |  | 210 | 210 | 0 | 0
281 | Ministry of Housing & Urban Affairs | Waste & Water | Upgradation of Sewerage system in Gandhinagar City | Smart City Mission | 707267 | Gujarat | 03/2021 | 06/2023 |  | 200 | 200 | 100 | 10
282 | Ministry of Mines | Construction | Construction of Basement + Ground Floor+ 10 Storeyed building for State of the Art Director General, GSI Building at plot No.GN-40, Sector-V, Salt Lake, Kolkata (Central Public Works Department (CPWD)) |  | 617280 | West Bengal | 02/2020 | 08/2026 |  | 255.37 | 255.37 | 78.34 | 35
283 | Ministry of Mines | Metals & Mining | Rakha Underground Mining Project | Hindustan Copper Limited [HCL] | 611798 | Jharkhand | 03/2024 | 03/2033 |  | 2705 | 2705 | 0 | 0
284 | Ministry of Mines | Metals & Mining | Surda Underground Copper Mining Project | Hindustan Copper Limited [HCL] | 611800 | Jharkhand | 03/2024 | 03/2028 |  | 665.02 | 665.02 | 13.33 | 1
285 | Ministry of Mines | Metals & Mining | Expansion of Malanjkhand Copper Project | Hindustan Copper Limited [HCL] | 400426 | Madhya Pradesh | 04/2015 | 04/2020 | 04/2026 | 1856.36 | 1856.36 | 924.98 | 79
286 | Ministry of Mines | Metals & Mining | Expansion of Alumina Refinery Plant with addition of 5th Stream having capacity enhancement of 1.0 Million Tonee Per Annum | National Aluminium Company Limited [NALCO] | 400141 | Odisha | 04/2017 | 12/2022 | 09/2025 | 4103 | 5677.4 | 3913.98 | 75
287 | Ministry of Mines | Metals & Mining | Pottangi Bauxite Mines Project | National Aluminium Company Limited [NALCO] | 400299 | Odisha | 05/2018 | 03/2025 | 05/2026 | 1381 | 1960.77 | 650.04 | 51
288 | Ministry of Mines | Metals & Mining | UTKAL D AND E COAL BLOCK | National Aluminium Company Limited [NALCO] | 709829 | Odisha | 02/2016 | 03/2025 |  | 1021.97 | 1021.97 | 0 | 0
289 | Ministry of Mines | Metals & Mining | CONVERSION OF FLAT BOTTOM SETTLERS AND WASHERS WITH A SINGLE TRAIN OF HRDS AND DCWS IN STREAMS 1 AND | Ministry of Mines | 709830 | Odisha | 04/2017 | 11/2026 |  | 355 | 581 | 0 | 0
290 | Ministry of Mines | Metals & Mining | SOURCING OF BAUXITE ARRANGEMENT FOR 5TH STREAM ALUMINA REFINERY FROM SOUTH BLOCK MINING LEASE OF PANCHPATMAILI MINES | National Aluminium Company Limited [NALCO] | 709831 | Odisha | 11/2019 | 05/2025 | 06/2026 | 483 | 483 | 403.44 | 90
291 | Ministry of Mines | Metals & Mining | 25.5 MW WIND POWER PROJECT AT KAYATHAR IN TAMILNADU | National Aluminium Company Limited [NALCO] | 709832 | Tamil Nadu | 12/2017 | 03/2025 | 03/2026 | 166 | 166 | 135 | 65
292 | Department of Higher Education | Education | Construction of Permanent Campus of Central Tribal University of Andhra Pradesh Phase-1 | Central Tribal University of Andhra Pradesh | 613008 | Andhra Pradesh | 12/2023 | 06/2027 |  | 305 | 305 | 83.33 | 24
293 | Department of Higher Education | Education | Construction of Permanent Campus of National Institute of Technology Arunachal Pradesh | National Institute of Technology, Arunachal Pradesh | 612898 | Arunachal Pradesh | 03/2013 | 08/2026 |  | 592.61 | 592.61 | 549.96 | 75
294 | Department of Higher Education | Education | Tezpur University Projects | Tezpur University | 606112 | Assam | 06/2021 | 11/2023 | 08/2025 | 153.71 | 153.71 | 288.87 | 93
295 | Department of Higher Education | Education | Additional Campus of NITPatna | NIT Patna | 606013 | Bihar | 08/2022 | 07/2024 | 01/2026 | 499.21 | 499.21 | 425.47 | 91
296 | Department of Higher Education | Education | Phase 1B - Construction of Academic Block, Hostel, Residential Tower, Directors Residence and External Development works at National Institute of Technology, Delhi Campus on Engineering, Procurement and Construction basis | Ministry of Education | 612851 | Delhi | 11/2022 | 09/2025 |  | 333.49 | 333.49 | 272.95 | 88
297 | Department of Higher Education | Education | Delhi University Eastern Campus at Surajmal Vihar | Delhi University | 616886 | Delhi | 01/2025 | 10/2026 |  | 373 | 373 | 18.03 | 15
298 | Department of Higher Education | Education | Construction of permanent campus of Central University of Gujarat at Village kundhela, Dist. Vadodara, Gujarat. | Gujarat | 612916 | Gujarat | 02/2021 | 03/2025 | 03/2026 | 490.63 | 490.63 | 301.44 | 76
299 | Department of Higher Education | Education | Establishment of Permanent campus Phase 1 of IIM Sirmaur | Indian Institute of Management, Sirmaur | 602099 | Himachal Pradesh | 08/2020 | 10/2023 | 02/2026 | 392.51 | 454.78 | 320.75 | 92
300 | Department of Higher Education | Education | Hostel blocks & dining hall block | Indian Institute of Technology, Mandi | 612128 | Himachal Pradesh | 03/2024 | 03/2026 | 03/2026 | 166.66 | 166.66 | 72.09 | 58
301 | Department of Higher Education | Education | Construction of Permanent Campus of Central University of Himachal Pradesh at Dehra, District - Kangra, [H.P.] on Engineering. Procurement and Construction [EPC Mode 1] Basis. | Central University, Himachal Pradesh | 612894 | Himachal Pradesh | 08/2022 | 11/2024 | 11/2025 | 251.98 | 300.45 | 183.36 | 78
302 | Department of Higher Education | Education | Construction of Permanent Campus for IIM Jammu Phase-1 at Jagti, Nagrota, Jammu, J&K | Indian Institute of Management, Jammu | 602098 | Jammu and Kashmir | 10/2020 | 06/2023 | 08/2025 | 424.93 | 500.91 | 484.52 | 96
303 | Department of Higher Education | Education | Additional Infrastructure at IISc Bangalore-RCC Monolithic for Men Hostel S14, Women Hostel S11 , Postdoctoral Hostel S12 2 Block , International Hostel S 12 , D&E Block S 12 2 Block FR. | IISC Bangalore | 610940 | Karnataka | 08/2021 | 03/2024 | 09/2025 | 420.41 | 420.41 | 360.72 | 99
304 | Department of Higher Education | Education | CONSTRUCTION OF PERMANENT CAMPUS FOR IIT PALAKKAD UNDER PHASE 1A | INDIAN INSTITUTE OF TECHNOLOGY PALAKKAD | 606431 | Kerala | 03/2020 | 06/2022 | 11/2026 | 1006.45 | 1217.4 | 615.95 | 66
305 | Department of Higher Education | Education | Phase III A works at IIT Indore [03 Hostels, 01 Studio Apartment, 01 Housing, Heavy & Sophisticated lab complex, Academic POD and Infrastructure for center of excellence] | Indian Institute of Technology, Indore | 611957 | Madhya Pradesh | 11/2023 | 12/2026 |  | 496.28 | 496.28 | 138.6 | 30
306 | Department of Higher Education | Education | Hostel 4 -Earlier Known as Hostel 20 | Indian Institute of Technology, Bombay | 612135 | Maharashtra | 05/2022 | 09/2025 |  | 182.33 | 182.33 | 132.44 | 94
307 | Department of Higher Education | Education | Academic Block 1 & 2 | Indian Institute of Technology, Bombay | 612203 | Maharashtra | 01/2023 | 07/2026 | 03/2027 | 68 | 263.93 | 22.15 | 16
308 | Department of Higher Education | Education | Construction and Developement of National Institute of Technology Meghalaya Permanent Campus at Sohra | National Institute of Technology, Meghalaya | 612885 | Meghalaya | 09/2014 | 03/2022 | 07/2025 | 494.52 | 494.52 | 413.57 | 86
309 | Department of Higher Education | Education | Construction of Permanent Campus for NIT Mizoram at Lengpui, Aizawl | Ministry of Education | 612876 | Mizoram | 05/2014 | 12/2029 | 12/2029 | 474.23 | 474.23 | 167.55 | 4
310 | Department of Higher Education | Education | Establishment of NIT Nagaland | NIT Nagaland | 613013 | Nagaland | 09/2012 | 12/2025 |  | 275.63 | 275.63 | 257.82 | 93
311 | Department of Higher Education | Education | IISER BERHAMPUR | Indian Institutes of Science Education and Research, Behrampur | 610315 | Odisha | 09/2019 | 03/2021 | 11/2025 | 1229.32 | 773.76 | 835.55 | 97
312 | Department of Higher Education | Education | Establishment of NIT Puducherry Permanent Campus [Phase-I and Phase-II] | National Institute of Technology, Puducherry | 612877 | Puducherry | 07/2013 | 12/2024 | 08/2025 | 618.34 | 544.34 | 509.24 | 94
313 | Department of Higher Education | Education | Construction of Permanent Campus of Indian Institute of Management [IIM] Amritsar, Punjab, Phase-I | Indian intitue of Management, Amritsar | 605292 | Punjab | 07/2020 | 06/2023 | 12/2025 | 348.31 | 348.31 | 290.39 | 91
314 | Department of Higher Education | Education | Construction of Girls Hostel 400 seater, Boys Hostel 600 seater, Academic Block, International Hostel 100 seater, VC Residence and Purchase of Equipment | Central University of Punjab | 617221 | Punjab | 04/2025 | 10/2027 |  | 210.99 | 210.99 | 0 | 0
315 | Department of Higher Education | Education | Construction of Sikkim University Campus Phase-I Package-II at Yangang, South Sikkim | Sikkim University | 609736 | Sikkim | 01/2022 | 01/2025 | 09/2025 | 314.06 | 314.06 | 238.22 | 82
316 | Department of Higher Education | Education | Establishment of Permanent Campus of NIT SIkkim at Khamdong-Gangtok District | Ministry of Education | 612883 | Sikkim | 03/2024 | 02/2028 | 12/2026 | 685.76 | 610.76 | 121.56 | 7
317 | Department of Higher Education | Education | Construction of Precast housing and hostels at IIT Hyderabad | Indian Institute of Technology, Hyderabad | 609996 | Telangana | 11/2022 | 10/2024 | 01/2026 | 262 | 262 | 164.4 | 71
318 | Department of Higher Education | Education | Banaras Hindu University [ Kayakalp of Institute of Medical Sciences] | Banaras Hindu University | 606479 | Uttar Pradesh | 06/2020 | 09/2022 | 03/2026 | 246 | 246 | 185.83 | 93
319 | Department of Higher Education | Education | Construction & Development of Infrastructural Facilities in the main campus of NIT Uttarakhand at Sumari, Pauri Garhwal | National Institute of Technology Uttarakhand | 611963 | Uttarakhand | 04/2024 | 09/2027 |  | 650.85 | 650.85 | 130 | 24
320 | Department of Higher Education | Education | HEFA projects on development of student hostels, playgrounds, departmental buildings, class room complex and other campus facilities in IIT Kharagpur | Indian Institute of Technology, Kharagpur | 609019 | West Bengal | 04/2019 | 03/2023 | 03/2026 | 500 | 442 | 382.6 | 87
321 | Department of Higher Education | Education | IoE Projects [Civil Works], IIT Kharagpur | Indian Institute of Technology, Kharagpur | 609041 | West Bengal | 04/2019 | 03/2023 | 12/2026 | 287.2 | 287.2 | 310 | 86
322 | Ministry of Petroleum & Natural Gas | Energy Storage | Construction of Aviation Fuel farm Facilities at Bhogapuram Airport | Ministry of Petroleum & Natural Gas | 616235 | Andhra Pradesh | 08/2024 | 03/2026 | 03/2026 | 240 | 240 | 31.23 | 50
323 | Ministry of Petroleum & Natural Gas | Energy Storage | Construction of LPG Facilities at Kamardanga, Assam | Hindustan Petroleum Corporation Limited | 709754 | Assam | 03/2023 | 07/2027 | 07/2027 | 156.36 | 156.36 | 49.78 | 39
324 | Ministry of Petroleum & Natural Gas | Energy Storage | Setting up of new rail fed POL facility at Kamardanga, Assam | Hindustan Petroleum Corporation Limited [HPCL] | 709755 | Assam | 03/2023 | 07/2027 | 07/2027 | 384.04 | 384.04 | 110.44 | 48
325 | Ministry of Petroleum & Natural Gas | Energy Storage | Setting up a common user Petroleum Terminal at Jammu, J&K for resitement of existing PSU OMC's Depots from Jammu City | Bharat Petroleum Corporation Limited [BPCL] | 400235 | Jammu and Kashmir | 04/2023 | 03/2025 | 09/2025 | 676.89 | 676.89 | 518.22 | 77
326 | Ministry of Petroleum & Natural Gas | Energy Storage | Construction of 80,000 MT LPG Cavern at Mangalore | Ministry of Petroleum & Natural Gas | 701269 | Karnataka | 12/2018 | 12/2022 | 08/2025 | 854 | 854 | 712.3 | 99
327 | Ministry of Petroleum & Natural Gas | Energy Storage | Andheri Residential Towers, Mumbai | Ministry of Petroleum & Natural Gas | 604833 | Maharashtra | 06/2017 | 05/2025 | 06/2026 | 281.35 | 389.67 | 227.54 | 50
328 | Ministry of Petroleum & Natural Gas | Energy Storage | Srikakulam Angul Gas Pipeline Project | Ministry of Petroleum & Natural Gas | 701343 | Multi-States (Andhra Pradesh, Odisha) | 09/2019 | 07/2022 | 12/2025 | 2658.34 | 2810 | 2192.68 | 94
329 | Ministry of Petroleum & Natural Gas | Energy Storage | Rajasthan Refinery Project | MinistryofPetroleumNaturalGas | 701263 | Multi-States (Arunachal Pradesh, Gujarat, Rajasthan) | 10/2017 | 10/2022 | 03/2026 | 43129 | 72937 | 59524.37 | 87
330 | Ministry of Petroleum & Natural Gas | Energy Storage | Paradip-Numaligarh Crude Oil Pipeline [PNCPL] & Crude Oil Import Terminal [COIT] at Paradip | Ministry of Petroleum & Natural Gas | 701349 | Multi-States (Assam, Bihar, Jharkhand, Odisha, West Bengal) | 01/2019 | 07/2024 | 09/2025 | 10228 | 11407 | 9701.95 | 86
331 | Ministry of Petroleum & Natural Gas | Energy Storage | New Mundra Panipat Crude Oil Pipeline | Ministry of Petroleum & Natural Gas | 400078 | Multi-States (Gujarat, Haryana, Rajasthan) | 12/2021 | 12/2024 | 12/2025 | 9028 | 9028 | 7071.08 | 84
332 | Ministry of Petroleum & Natural Gas | Energy Storage | Kandla Gorakhpur LPG Pipeline | Ministry of Petroleum & Natural Gas | 400012 | Multi-States (Gujarat, Madhya Pradesh, Uttar Pradesh) | 12/2018 | 12/2021 | 12/2025 | 10088 | 10088 | 7598.13 | 92
333 | Ministry of Petroleum & Natural Gas | Energy Storage | Multi Product Pipeline from Irugur to Devangonthi | Department of Water Resources, River Development & GR | 400301 | Multi-States (Karnataka, Tamil Nadu) | 11/2012 | 02/2017 | 10/2025 | 678 | 1732 | 675.25 | 67
334 | Ministry of Petroleum & Natural Gas | Energy Storage | Petrochemical evacuation marketing terminal at Barmer, Rajasthan | Hindustan Petroleum Corporation Limited [HPCL] | 709759 | Rajasthan | 12/2023 | 12/2026 | 12/2026 | 461.05 | 461.05 | 111.57 | 51
335 | Ministry of Petroleum & Natural Gas | Energy Storage | Laying of POL Pipelines in Common Corridor for proposed grass root terminal at Vallur [Chennai] | Ministry of Petroleum & Natural Gas | 400043 | Tamil Nadu | 01/2022 | 05/2026 | 05/2026 | 829 | 829 | 297.77 | 62
336 | Ministry of Petroleum & Natural Gas | Energy Storage | Grass root POL Terminal at Vallur, Chennai | Indian Oil Corporation Limited [IOCL] | 400077 | Tamil Nadu | 01/2022 | 12/2024 | 03/2026 | 827 | 887.71 | 619.5 | 85
337 | Ministry of Petroleum & Natural Gas | Energy Storage | Grass Root Rail-fed Depot at Sekerkote, Agartala as resitement of existing Dharmanagar Depot | Indian Oil Corporation Limited [IOCL] | 400035 | Tripura | 06/2022 | 09/2025 | 09/2025 | 656 | 656 | 465.73 | 84
338 | Ministry of Petroleum & Natural Gas | Energy Storage | Grass-root Terminal at Mirzapur, Uttar Pradesh | Ministry of Petroleum & Natural Gas | 604852 | Uttar Pradesh | 09/2022 | 11/2026 | 11/2026 | 980.45 | 980.45 | 236.22 | 50
339 | Ministry of Petroleum & Natural Gas | Oil & Gas | KG-DWN-98/2 Cluster - II Development Project - NELP Block | Oil and Natural Gas Corporation Limited [ONGC] | 400120 | Andhra Pradesh | 03/2016 | 06/2020 | 06/2026 | 34012 | 34012 | 35498.35 | 96
340 | Ministry of Petroleum & Natural Gas | Oil & Gas | HP-COAT [Crude to Olefins and Aromatics Technology] demo unit at Visakh Refinery | Hindustan Petroleum Corporation Limited | 709752 | Andhra Pradesh | 09/2021 | 06/2024 | 03/2026 | 160 | 220 | 77.06 | 64
341 | Ministry of Petroleum & Natural Gas | Oil & Gas | HP Trijet Unit in Visakh Refinery | Hindustan Petroleum Corporation Limited | 709761 | Andhra Pradesh | 07/2024 | 07/2027 | 07/2027 | 193 | 193 | 0.43 | 23
342 | Ministry of Petroleum & Natural Gas | Oil & Gas | City Gas Distribution Project at Kurnool, Guntur & Prakasam Districts | MinistryofPetroleumNaturalGas | 709766 | Andhra Pradesh | 03/2022 | 03/2030 | 03/2030 | 1420 | 1420 | 162.47 | 6
343 | Ministry of Petroleum & Natural Gas | Oil & Gas | Numaligarh Refinery Expansion Project | Ministry of Petroleum & Natural Gas | 604791 | Assam | 07/2020 | 07/2024 | 12/2025 | 12366 | 22494 | 16502.36 | 75
344 | Ministry of Petroleum & Natural Gas | Oil & Gas | Assam Bio Refinery, ABRPL | Ministry of Petroleum & Natural Gas | 604792 | Assam | 02/2018 | 09/2021 | 07/2025 | 1750 | 4200 | 4650 | 99
345 | Ministry of Petroleum & Natural Gas | Oil & Gas | Development of Surface Facilities for production and evacuation of Crude Oil and Natural Gas from Nadua and East Khagorija | Ministry of Petroleum & Natural Gas | 604863 | Assam | 01/2018 | 02/2020 | 12/2025 | 682.9 | 726.93 | 488.37 | 94
346 | Ministry of Petroleum & Natural Gas | Oil & Gas | Guwahati Refinery Expansion [1.0 to 1.2 MMTPA] along with installation of CRU, Guwahati Refinery | Ministry of Petroleum & Natural Gas | 607701 | Assam | 05/2021 | 10/2023 | 05/2026 | 412.3 | 577 | 430.83 | 84
347 | Ministry of Petroleum & Natural Gas | Oil & Gas | Construction of Field Gas Gathering Station at Baghjan area for collection, processing & transportation of natural Gas to be produced from Baghjan Field | Ministry of Petroleum & Natural Gas | 616858 | Assam | 12/2020 | 03/2024 | 12/2025 | 430.76 | 430.76 | 326.12 | 85
348 | Ministry of Petroleum & Natural Gas | Oil & Gas | Augmentation/Revamping of Facilities at existing Guwahati Terminal at Betkuchi | MinistryofPetroleumNaturalGas | 709776 | Assam | 04/2022 | 09/2026 | 09/2026 | 277 | 323.09 | 185.18 | 67
349 | Ministry of Petroleum & Natural Gas | Oil & Gas | Capacity Expansion of Digboi Refinery from 0.65 to 1.0 MMTPA | MinistryofPetroleumNaturalGas | 709779 | Assam | 06/2022 | 03/2026 | 03/2026 | 768 | 740 | 99.02 | 35
350 | Ministry of Petroleum & Natural Gas | Oil & Gas | Pipeline Network Project Rudrasagar | Ministry of Petroleum & Natural Gas | 709847 | Assam | 01/2023 | 04/2026 | 04/2026 | 344.99 | 344.99 | 210.89 | 46
351 | Ministry of Petroleum & Natural Gas | Oil & Gas | Borholla GGS Life Extension Project [BLEP] | Ministry of Petroleum & Natural Gas | 709850 | Assam | 09/2023 | 05/2026 | 05/2026 | 198.7 | 198.7 | 36.78 | 29
352 | Ministry of Petroleum & Natural Gas | Oil & Gas | DCU Revamp Project | NRL | 709864 | Assam | 08/2021 | 07/2024 | 10/2025 | 370 | 370 | 249.41 | 57
353 | Ministry of Petroleum & Natural Gas | Oil & Gas | Power Recovery Turbine [PRT] in PFCCU unit as an Energy Conservation Scheme | NRL | 709865 | Assam | 04/2023 | 12/2024 | 10/2025 | 293.5 | 293.5 | 97.22 | 93
354 | Ministry of Petroleum & Natural Gas | Oil & Gas | City Gas Distribution Project at Khagaria, Saharsa and Madhepura | Ministry of Petroleum & Natural Gas | 617303 | Bihar | 03/2019 | 03/2030 | 03/2030 | 163 | 163 | 95.54 | 40
355 | Ministry of Petroleum & Natural Gas | Oil & Gas | Setting up of LPG Plant with Rail Unloading Facility at Hathua, Dist. Gopalganj, Bihar | MinistryofPetroleumNaturalGas | 617304 | Bihar | 10/2023 | 03/2027 | 03/2027 | 340.15 | 340.15 | 88.08 | 24
356 | Ministry of Petroleum & Natural Gas | Oil & Gas | Barauni Refinery Capacity Expansion from 6.0 to 9.0 MMTPA | Ministry of Petroleum & Natural Gas | 701324 | Bihar | 01/2020 | 04/2023 | 08/2026 | 14810 | 16724 | 11728.01 | 87
357 | Ministry of Petroleum & Natural Gas | Oil & Gas | Installation of Bitumen Manufacturing Unit along with allied facilities at Barauni Refinery | MinistryofPetroleumNaturalGas | 709777 | Bihar | 01/2022 | 04/2025 | 10/2026 | 389.35 | 340 | 46.94 | 37
358 | Ministry of Petroleum & Natural Gas | Oil & Gas | City Gas Distribution Projects at Darbhanga, Madhubani, Supaul, Sitamarhi and Sheohar districts | Bharat Petroleum Corporation Limited [BPCL] | 709792 | Bihar | 12/2022 | 03/2030 | 03/2030 | 3638 | 3638 | 396.42 | 21
359 | Ministry of Petroleum & Natural Gas | Oil & Gas | City Gas Distribution Projects at Gopalganj, Siwan, West Champaran, East Champaran and Deoria districts | Bharat Petroleum Corporation Limited [BPCL] | 709793 | Bihar | 12/2022 | 06/2030 | 06/2030 | 3919 | 3919 | 392.59 | 14
360 | Ministry of Petroleum & Natural Gas | Oil & Gas | Redevelopment of Sobhasan Complex | Oil and Natural Gas Corporation Limited [ONGC] | 400087 | Gujarat | 08/2021 | 02/2026 | 02/2026 | 885.63 | 1286.67 | 765.43 | 73
361 | Ministry of Petroleum & Natural Gas | Oil & Gas | Redevelopment of Santhal Field [Onshore-Mehsana Asset] | Oil and Natural Gas Corporation Limited [ONGC] | 400167 | Gujarat | 02/2017 | 03/2026 | 03/2026 | 1162.56 | 1162.56 | 1156.9 | 94
362 | Ministry of Petroleum & Natural Gas | Oil & Gas | Redevelopment of Linch Field | Oil and Natural Gas Corporation Limited [ONGC] | 400169 | Gujarat | 04/2021 | 03/2025 | 10/2025 | 631.03 | 860.04 | 505.07 | 77
363 | Ministry of Petroleum & Natural Gas | Oil & Gas | Petrochemical and Lube Integration Project at Gujarat Refinery | Ministry of Petroleum & Natural Gas | 701329 | Gujarat | 09/2020 | 08/2024 | 12/2025 | 18936 | 17825 | 12190.08 | 83
364 | Ministry of Petroleum & Natural Gas | Oil & Gas | Installation of new Biturox Unit along with allied facilities at Gujarat Refinery | MinistryofPetroleumNaturalGas | 709778 | Gujarat | 01/2022 | 08/2025 | 09/2026 | 328.29 | 287 | 144.16 | 55
365 | Ministry of Petroleum & Natural Gas | Oil & Gas | Commercial Polymer Flooding Project in Bechraji field | Oil and Natural Gas Corporation Limited [ONGC] | 709838 | Gujarat | 01/2022 | 11/2024 | 11/2025 | 621.4 | 621.4 | 137.71 | 21
366 | Ministry of Petroleum & Natural Gas | Oil & Gas | Restoration of Gas Terminal, Phase-I [Part-A], Hazira | Oil and Natural Gas Corporation Limited [ONGC] | 709840 | Gujarat | 05/2022 | 02/2025 | 12/2025 | 249.43 | 249.43 | 209.42 | 93
367 | Ministry of Petroleum & Natural Gas | Oil & Gas | Old Pipe Line Replacement [OPRP] Group-A | Oil and Natural Gas Corporation Limited [ONGC] | 709841 | Gujarat | 07/2021 | 07/2025 | 03/2026 | 173.03 | 169.84 | 148 | 87
368 | Ministry of Petroleum & Natural Gas | Oil & Gas | Kalol Redevelopment Project, Ahmedabad Asset | Oil and Natural Gas Corporation Limited [ONGC] | 709842 | Gujarat | 08/2022 | 03/2027 | 03/2027 | 1487.41 | 1487.41 | 776.61 | 61
369 | Ministry of Petroleum & Natural Gas | Oil & Gas | Revamping of SV Stations, Gas Terminal & Kribhco Terminal | Oil and Natural Gas Corporation Limited [ONGC] | 709845 | Gujarat | 11/2022 | 08/2026 | 08/2026 | 837.34 | 837.34 | 205.78 | 49
370 | Ministry of Petroleum & Natural Gas | Oil & Gas | Indian Oil Technology Development and Deployment Centre at R&D Campus-II, Faridabad | Ministry of Petroleum & Natural Gas | 604853 | Haryana | 06/2019 | 12/2022 | 03/2026 | 2281.94 | 3200 | 1800.61 | 63
371 | Ministry of Petroleum & Natural Gas | Oil & Gas | Poly Butadiene Rubber plant at Panipat | Indian Oil Corporation Limited [IOCL] | 611917 | Haryana | 03/2022 | 03/2025 | 06/2026 | 1459 | 2531.44 | 1043.9 | 70
372 | Ministry of Petroleum & Natural Gas | Oil & Gas | Capacity Expansion of Panipat Refinery from 15 to 25 MMTPA | Ministry of Petroleum & Natural Gas | 701289 | Haryana | 02/2021 | 09/2024 | 12/2025 | 34627 | 36225 | 23977.47 | 88
373 | Ministry of Petroleum & Natural Gas | Oil & Gas | Installation of Multiple Effect Evaporator [MEE] for ETP-1, 2 & 4 of Panipat Refinery and Petrochemical Complex. | MinistryofPetroleumNaturalGas | 709783 | Haryana | 12/2020 | 06/2023 | 06/2026 | 165.13 | 247.69 | 129.27 | 70
374 | Ministry of Petroleum & Natural Gas | Oil & Gas | City Gas Distribution Project at Jammu, Udhampur, Reasi, Samba and Kathua Districts | MinistryofPetroleumNaturalGas | 709773 | Jammu and Kashmir | 03/2022 | 03/2032 | 03/2032 | 538 | 538 | 4.09 | 0
375 | Ministry of Petroleum & Natural Gas | Oil & Gas | Development of Jharia CBM Block [Phase-1] | Oil and Natural Gas Corporation Limited [ONGC] | 610984 | Jharkhand | 11/2019 | 01/2024 | 08/2025 | 431 | 431 | 211.34 | 58
376 | Ministry of Petroleum & Natural Gas | Oil & Gas | Laying of Natural Gas Pipeline from Hazaribagh to Ranchi [HRPL] | MinistryofPetroleumNaturalGas | 709785 | Jharkhand | 02/2023 | 02/2026 | 02/2026 | 202.07 | 202.07 | 55.46 | 45
377 | Ministry of Petroleum & Natural Gas | Oil & Gas | Power System Upgradation Project | Mangalore Refinary and Petrochemicals Limited | 612790 | Karnataka | 10/2023 | 11/2025 | 11/2025 | 385 | 385 | 132.73 | 63
378 | Ministry of Petroleum & Natural Gas | Oil & Gas | Demo Bio-ATF Project | Ministry of Petroleum & Natural Gas | 616879 | Karnataka | 03/2024 | 01/2027 | 01/2027 | 364 | 364 | 22.82 | 10
379 | Ministry of Petroleum & Natural Gas | Oil & Gas | Revamping/ Augmentation of facilities at existing port terminal at Mangalore | Ministry of Petroleum & Natural Gas | 709774 | Karnataka | 01/2022 | 12/2025 | 12/2025 | 463 | 500.62 | 264.44 | 82
380 | Ministry of Petroleum & Natural Gas | Oil & Gas | Replacement and Extension of Jetty Pipelines [REJP] at KR | Bharat Petroleum Corporation Limited [BPCL] | 709790 | Kerala | 03/2023 | 03/2026 | 03/2026 | 621.87 | 621.87 | 192.66 | 83
381 | Ministry of Petroleum & Natural Gas | Oil & Gas | Setting up Polypropylene Unit at Kochi Refinery | MinistryofPetroleumNaturalGas | 709799 | Kerala | 12/2023 | 10/2027 | 10/2027 | 4460 | 4460 | 255.64 | 12
382 | Ministry of Petroleum & Natural Gas | Oil & Gas | Ethylene Cracker Project at Bina Refinery including downstream Petrochemical Plants and expansion of Refinery | MinistryofPetroleumNaturalGas | 709798 | Madhya Pradesh | 05/2023 | 05/2028 | 05/2028 | 43367 | 43367 | 1788.6 | 13
383 | Ministry of Petroleum & Natural Gas | Oil & Gas | Debottlenecking and Augmentation of Cryogenic facilities at Uran LPG Import Terminal | Department of Water Resources, River Development & GR | 400158 | Maharashtra | 04/2021 | 02/2024 | 12/2025 | 1164.69 | 1629.86 | 901.73 | 84
384 | Ministry of Petroleum & Natural Gas | Oil & Gas | 500 KTA PDHPP Project, Usar | Ministry of Petroleum & Natural Gas | 400168 | Maharashtra | 04/2021 | 04/2025 | 10/2025 | 8797 | 11256 | 6768.36 | 85
385 | Ministry of Petroleum & Natural Gas | Oil & Gas | Construction of lube oil blending plant at Rasayani | Ministry of Petroleum & Natural Gas | 610985 | Maharashtra | 05/2022 | 12/2023 | 12/2025 | 423.39 | 526.26 | 287.49 | 78
386 | Ministry of Petroleum & Natural Gas | Oil & Gas | Lube Modernization & Bottom Upgradation Project at Mumbai Refinery | Ministry of Petroleum and Natural Gas | 616933 | Maharashtra | 12/2024 | 03/2028 | 03/2028 | 4679 | 4679 | 188.88 | 4
387 | Ministry of Petroleum & Natural Gas | Oil & Gas | HP TDAE Unit in Mumbai Refinery | Hindustan Petroleum Corporation Limited | 709760 | Maharashtra | 06/2024 | 04/2026 | 04/2026 | 240 | 240 | 34.4 | 37
388 | Ministry of Petroleum & Natural Gas | Oil & Gas | City Gas Distribution Project at Beed, Jalgaon and Jalna Districts | MinistryofPetroleumNaturalGas | 709771 | Maharashtra | 03/2022 | 09/2031 | 09/2031 | 865 | 865 | 68.01 | 2
389 | Ministry of Petroleum & Natural Gas | Oil & Gas | Construction of Additional Tankages and Allied Facilities at JNPT Terminal | MinistryofPetroleumNaturalGas | 709780 | Maharashtra | 04/2022 | 08/2026 | 08/2026 | 341.43 | 436.14 | 279.19 | 50
390 | Ministry of Petroleum & Natural Gas | Oil & Gas | ATF Pipeline from Jawaharlal Nehru Port Trust to Navi Mumbai International Airport | Indian Oil Corporation Limited [IOCL] | 709782 | Maharashtra | 08/2022 | 08/2025 | 03/2026 | 165 | 165 | 89.94 | 72
391 | Ministry of Petroleum & Natural Gas | Oil & Gas | Installation of Independent De- Aromatized Solvents [DAS] production facilities at MR | Bharat Petroleum Corporation Limited [BPCL] | 709789 | Maharashtra | 03/2023 | 07/2025 | 12/2025 | 405 | 343 | 201.28 | 84
392 | Ministry of Petroleum & Natural Gas | Oil & Gas | POL & LOBS Installations with Receipt Pipelines at Rasayani | Bharat Petroleum Corporation Limited [BPCL] | 709797 | Maharashtra | 05/2023 | 05/2026 | 05/2026 | 2585 | 2585 | 564.58 | 58
393 | Ministry of Petroleum & Natural Gas | Oil & Gas | Part Replacement Pipeline Project [PRPP] | Oil and Natural Gas Corporation Limited [ONGC] | 709846 | Maharashtra | 11/2022 | 05/2024 | 11/2025 | 1219.48 | 1145.1 | 745.24 | 90
394 | Ministry of Petroleum & Natural Gas | Oil & Gas | Visakh Raipur Pipeline Project | Ministry of Petroleum and Natural Gas | 616254 | Multi-States (Andhra Pradesh, Chhattisgarh, Odisha) | 09/2024 | 09/2027 | 09/2027 | 2212 | 2212 | 11.52 | 7
395 | Ministry of Petroleum & Natural Gas | Oil & Gas | Multi-product Pipeline from Krishnapatnam Coastal Installation to the proposed Installation at Hyderabad [Malkapur] | Ministry of Petroleum & Natural Gas | 701341 | Multi-States (Andhra Pradesh, Telangana) | 09/2019 | 03/2025 | 08/2025 | 1932 | 2208 | 1552.37 | 98
396 | Ministry of Petroleum & Natural Gas | Oil & Gas | North East Gas Grid | Ministry of Petroleum & Natural Gas | 701346 | Multi-States (Arunachal Pradesh, Assam, Manipur, Meghalaya, Mizoram, Nagaland, Sikkim, Tripura, West Bengal) | 04/2020 | 03/2024 | 03/2026 | 9265 | 9265 | 6375.02 | 85
397 | Ministry of Petroleum & Natural Gas | Oil & Gas | Upgradation of Facilities of Numaligarh-Siliguri Product Pipeline [NSPL] for transportation of additional products from existing 1.72 MMTPA to 5.5 MMTPA | Ministry of Petroleum & Natural Gas | 701350 | Multi-States (Assam, West Bengal) | 06/2021 | 12/2024 | 10/2025 | 860 | 860 | 566.18 | 98
398 | Ministry of Petroleum & Natural Gas | Oil & Gas | CGD Project in Banka, Dumka, Godda, Jamtara, Pakur, Sahibganj GA ID 11A.02 | Hindustan Petroleum Corporation Limited | 709757 | Multi-States (Bihar, Jharkhand) | 06/2022 | 06/2030 | 06/2030 | 1377 | 1377 | 329.43 | 26
399 | Ministry of Petroleum & Natural Gas | Oil & Gas | Mumbai Nagpur Jharsuguda Pipeline Project | Ministry of Petroleum & Natural Gas | 701354 | Multi-States (Chhattisgarh, Madhya Pradesh, Maharashtra, Odisha) | 06/2020 | 05/2023 | 09/2025 | 7844.25 | 8255 | 6495.6 | 95
400 | Ministry of Petroleum & Natural Gas | Oil & Gas | Mehsana-Bhatinda & Bhatinda-Jammu Natural Gas Pipeline | Ministry of Petroleum & Natural Gas | 701330 | Multi-States (Gujarat, Haryana, Punjab, Rajasthan) | 07/2011 | 06/2024 | 12/2025 | 7392 | 7392 | 6304 | 90
401 | Ministry of Petroleum & Natural Gas | Oil & Gas | Gurdaspur Jammu Pipeline | Gas Authority of India Limited [GAIL] | 612853 | Multi-States (Jammu and Kashmir, Punjab) | 07/2023 | 07/2026 | 07/2026 | 521.9 | 521.9 | 190.1 | 36
402 | Ministry of Petroleum & Natural Gas | Oil & Gas | Kochi - Koottanad - Bangalore - Mangalore Pipeline Phase-II | Ministry of Petroleum & Natural Gas | 701228 | Multi-States (Karnataka, Kerala, Tamil Nadu) | 06/2009 | 12/2012 | 12/2025 | 2915 | 5909 | 4431.9 | 94
403 | Ministry of Petroleum & Natural Gas | Oil & Gas | City Gas Distribution Maharashtra Natural Gas Limited | Ministry of Petroleum & Natural Gas | 701338 | Multi-States (Karnataka, Maharashtra) | 01/2006 | 06/2031 | 06/2031 | 5535 | 5535 | 3836.09 | 0
404 | Ministry of Petroleum & Natural Gas | Oil & Gas | Dhamra Haldia Pipeline Project | Ministry of Petroleum & Natural Gas | 701344 | Multi-States (Odisha, West Bengal) | 03/2020 | 11/2022 | 12/2025 | 1030.65 | 1125 | 853.7 | 87
405 | Ministry of Petroleum & Natural Gas | Oil & Gas | City Gas Distribution Projects at Fazilka [except area already authorized], Ganganagar and Hanumangarh districts | Bharat Petroleum Corporation Limited [BPCL] | 709794 | Multi-States (Punjab, Rajasthan) | 12/2022 | 06/2030 | 06/2030 | 3207 | 3207 | 334.82 | 22
406 | Ministry of Petroleum & Natural Gas | Oil & Gas | Augmentation/ Revamping of Dimapur Depot, Dimapur | MinistryofPetroleumNaturalGas | 709786 | Nagaland | 08/2023 | 11/2027 | 11/2027 | 227.62 | 227.62 | 9.01 | 20
407 | Ministry of Petroleum & Natural Gas | Oil & Gas | Integrated Para Xylene [PX] and Purified Terephthalic Acid [PTA] Project at Paradip Refinery | Ministry of Petroleum & Natural Gas | 604859 | Odisha | 07/2020 | 01/2024 | 08/2026 | 13805 | 11783 | 8250.46 | 90
408 | Ministry of Petroleum & Natural Gas | Oil & Gas | CUF POL Depot at Sadashibpur [Meramundali], Odisha | MinistryofPetroleumNaturalGas | 709800 | Odisha | 04/2021 | 03/2026 | 03/2026 | 393.54 | 393.54 | 100.39 | 43
409 | Ministry of Petroleum & Natural Gas | Oil & Gas | Life Extension of 48 well platforms of Mumbai High & Heera Fields | Oil and Natural Gas Corporation Limited [ONGC] | 400119 | Offshore | 12/2015 | 04/2018 | 12/2025 | 3190.69 | 3375.9 | 3074.01 | 89
410 | Ministry of Petroleum & Natural Gas | Oil & Gas | PRP-VIII [Group-A] | Ministry of Petroleum & Natural Gas | 616950 | Offshore | 09/2024 | 02/2026 | 02/2026 | 1486.4 | 1486.4 | 184.56 | 17
411 | Ministry of Petroleum & Natural Gas | Oil & Gas | Daman Upside Development Project | Oil and Natural Gas Corporation Limited [ONGC] | 709839 | Offshore | 06/2022 | 10/2025 | 02/2026 | 4144.41 | 6406.9 | 3770.15 | 83
412 | Ministry of Petroleum & Natural Gas | Oil & Gas | MHN TCPP PGC BGC Project [MTPBP] | Ministry of Petroleum & Natural Gas | 709848 | Offshore | 06/2022 | 05/2026 | 05/2026 | 2329.45 | 2354.23 | 820.24 | 48
413 | Ministry of Petroleum & Natural Gas | Oil & Gas | PRP-VIII Group B [NH & BS Asset] | Ministry of Petroleum & Natural Gas | 709849 | Offshore | 06/2024 | 02/2026 | 02/2026 | 2379.84 | 3165.53 | 1652.62 | 61
414 | Ministry of Petroleum & Natural Gas | Oil & Gas | Integrated Development of 4 Contract Areas under DSF-II | Ministry of Petroleum & Natural Gas | 709851 | Offshore | 05/2023 | 04/2027 | 04/2027 | 6183.79 | 6183.79 | 360 | 17
415 | Ministry of Petroleum & Natural Gas | Oil & Gas | 2G Ethanol Biorefinery at Bathinda | Hindustan Petroleum Corporation Limited [HPCL] | 400171 | Punjab | 05/2020 | 02/2023 | 03/2026 | 1421.46 | 1421.46 | 1180.91 | 95
416 | Ministry of Petroleum & Natural Gas | Oil & Gas | Bathinda Sangrur Pipeline | Ministry of Petroleum and Natural Gas | 612998 | Punjab | 11/2021 | 05/2024 | 08/2025 | 367 | 397 | 339.19 | 93
417 | Ministry of Petroleum & Natural Gas | Oil & Gas | City Gas Distribution Project at Pathankot District | MinistryofPetroleumNaturalGas | 709770 | Punjab | 03/2022 | 09/2033 | 09/2033 | 151 | 151 | 8.77 | 2
418 | Ministry of Petroleum & Natural Gas | Oil & Gas | CBR 9 MMTPA Project | Chennai Petroleum Corporation Limited [CPCL] | 604795 | Tamil Nadu | 09/2021 | 06/2025 | 10/2028 | 31580 | 36354 | 1342.27 | 10
419 | Ministry of Petroleum & Natural Gas | Oil & Gas | Laying of new 28 inch Desal Water Pipeline and 10 inch Reject Water Pipeline between CPCL Manali Refinery and CPCL Desalination plant at Ennore | Chennai Petroleum Corporation Limited [CPCL] | 709750 | Tamil Nadu | 01/2024 | 09/2025 | 12/2025 | 205 | 205 | 19.86 | 39
420 | Ministry of Petroleum & Natural Gas | Oil & Gas | City Gas Distribution Project at Dharmapuri and Krishnagiri Districts | MinistryofPetroleumNaturalGas | 709768 | Tamil Nadu | 03/2022 | 12/2030 | 12/2030 | 501 | 501 | 111.55 | 5
421 | Ministry of Petroleum & Natural Gas | Oil & Gas | City Gas Distribution Projects at the Nilgiris and Erode districts | Bharat Petroleum Corporation Limited [BPCL] | 709796 | Tamil Nadu | 12/2022 | 03/2030 | 03/2030 | 3685 | 3685 | 234.12 | 11
422 | Ministry of Petroleum & Natural Gas | Oil & Gas | Creation of Gas Dehydration Facilities, Tripura Asset | Oil and Natural Gas Corporation Limited [ONGC] | 709837 | Tripura | 03/2022 | 05/2024 | 12/2025 | 209.33 | 131.51 | 65.97 | 62
423 | Ministry of Petroleum & Natural Gas | Oil & Gas | PP Project, Pata | Gas Authority of India Limited [GAIL] | 400161 | Uttar Pradesh | 03/2019 | 01/2024 | 08/2025 | 910.56 | 1299.02 | 1004 | 97
424 | Ministry of Petroleum & Natural Gas | Oil & Gas | Revamping / Augmentation of Facilities at Mathura Bitumen Plant | MinistryofPetroleumNaturalGas | 709781 | Uttar Pradesh | 04/2022 | 06/2027 | 12/2026 | 260.12 | 260.12 | 1.11 | 25
425 | Ministry of Petroleum & Natural Gas | Oil & Gas | City Gas Distribution Projects at Lakhimpur Kheri , Sitapur, Bahraich, Shravasti,Balrampur, Siddharth Nagar & Maharajganj districts | Bharat Petroleum Corporation Limited [BPCL] | 709795 | Uttar Pradesh | 12/2022 | 06/2030 | 06/2030 | 16654 | 16654 | 603.21 | 9
426 | Ministry of Petroleum & Natural Gas | Oil & Gas | 71 MWp [DC] Solar power project at Prayagraj | Bharat Petroleum Corporation Limited [BPCL] | 709801 | Uttar Pradesh | 02/2024 | 08/2025 |  | 308.32 | 308.32 | 183.37 | 95
427 | Ministry of Petroleum & Natural Gas | Oil & Gas | Durgapur - Haldia Pipeline [Section-3B of JHBDPL Project] | Ministry of Petroleum & Natural Gas | 617302 | West Bengal | 03/2017 | 12/2020 | 12/2025 | 1740 | 2493.15 | 2237.5 | 90
428 | Ministry of Petroleum & Natural Gas | Oil & Gas | Haldia Panagarh Pipeline Project | Hindustan Petroleum Corporation Limited | 709753 | West Bengal | 11/2022 | 11/2025 | 11/2025 | 1010 | 1010 | 627.12 | 81
429 | Ministry of Petroleum & Natural Gas | Oil & Gas | CGD Project in Malda, Birbhum, Murshidabad, Dakshin Dinajpur GA ID 11A.03 | Hindustan Petroleum Corporation Limited | 709758 | West Bengal | 06/2022 | 06/2030 | 06/2030 | 2628 | 2628 | 332.52 | 26
430 | Ministry of Petroleum & Natural Gas | Oil & Gas | City Gas Distribution Project at East Mednipore, West Mednipore & Jhargram Districts | MinistryofPetroleumNaturalGas | 709772 | West Bengal | 03/2022 | 06/2031 | 06/2031 | 609 | 609 | 58.15 | 2
431 | Ministry of Petroleum & Natural Gas | Oil & Gas | City Gas Distribution Projects at Alipurduar and Cooch Behar | Bharat Petroleum Corporation Limited [BPCL] | 709791 | West Bengal | 12/2022 | 03/2030 | 03/2030 | 1017 | 1017 | 176.15 | 32
432 | Ministry of Health & Family Welfare | Healthcare | AIIMS Majra Rewari Haryana | Ministry of Health & Family Welfare | 701173 | Haryana | 02/2019 | 02/2023 | 12/2026 | 1299 | 1299 | 349.41 | 28
433 | Ministry of Health & Family Welfare | Healthcare | AIIMS Kashmir at Awantipora Jammu & Kashmir | Central Public Works Department [CPWD] | 701167 | Jammu and Kashmir | 01/2019 | 01/2025 | 12/2025 | 1828 | 1828 | 1504.91 | 65
434 | Ministry of Health & Family Welfare | Healthcare | AIIMS Bibinagar | Ministry of Health & Family Welfare | 701171 | Telangana | 12/2018 | 09/2022 | 12/2025 | 1028 | 1365.95 | 792.24 | 83
435 | Ministry of Ports, Shipping and Waterways | Healthcare | Establishment of 600 bed super specialty hospital with optional development of Medical college and further expansion on PPP basis. | Mumbai Port Trust [MPT] | 708662 | Maharashtra | 01/2022 | 06/2026 | 12/2027 | 693 | 693 | 58 | 0
436 | Ministry of Ports, Shipping and Waterways | Inland Waterways | Development of Container Terminal at Tuna-Tekra, Deendayal Port on BOT Basis Under PPP Mode | Deendayal Port Trust [DPT] | 609424 | Gujarat | 12/2023 | 12/2026 |  | 4243.64 | 4243.64 | 346.2 | 10
437 | Ministry of Ports, Shipping and Waterways | Inland Waterways | Jal Marg Vikas Project | Inland Waterways Authority of India [IWAI] | 701565 | Multi-States (Bihar, Jharkhand, Uttar Pradesh, West Bengal) | 02/2018 | 12/2023 | 12/2025 | 5369.18 | 5061.15 | 3432.34 | 70
438 | Ministry of Ports, Shipping and Waterways | Shipping | Setting up of a Floating Storage and Regasification Unit [FSRU] - Mumbai | Mumbai Port Trust [MPT] | 701586 | Maharashtra | 04/2021 | 11/2026 | 11/2026 | 900 | 900 | 65 | 0
439 | Ministry of Ports, Shipping and Waterways | Shipping | Operationalization of Coastal Berth & Shallow Water Berth through PPP | Jawaharlal Nehru Port Authority [JNPA] | 708655 | Maharashtra | 07/2021 | 01/2026 |  | 366.8 | 366.8 | 188.46 | 25
440 | Ministry of Ports, Shipping and Waterways | Shipping | Deepening and Optimization of Inner Harbour facilities including development of Western Dock on BOT basis to handle Cape size vessels | Paradip Port Trust [PPT] | 701574 | Odisha | 01/2023 | 12/2027 | 10/2028 | 3004.63 | 3004.63 | 1149.79 | 40
441 | Ministry of Ports, Shipping and Waterways | Shipping | Berth No. 2 [previously Berth 3] of HDC Mechanization Project | Haldia Dock Complex, Syama Prasad Mookerjee Port Authority | 701576 | West Bengal | 03/2023 | 09/2025 | 01/2026 | 298.26 | 298.26 | 399.52 | 83
442 | Ministry of Ports, Shipping and Waterways | Shipping | Shalukkhali Liquid Cargo Handling Facility Development Project | Haldia Dock Complex, Syama Prasad Mookerjee Port Authority | 701577 | West Bengal | 08/2022 | 08/2025 |  | 253.65 | 253.65 | 9.28 | 0
443 | Ministry of Ports, Shipping and Waterways | Tourism, Hospitality & Wellness | National Maritime Heritage Complex [NMHC] Phase-I | Indian Port Rail & Ropeway Corporation Ltd. [IPRCL] | 707215 | Gujarat | 01/2022 | 03/2024 | 09/2025 | 573 | 1238.05 | 487.35 | 66
444 | Ministry of Railways | Inland Waterways | 3rd & 4th Railway Line Project from Salegaon to Budhapank via Rajathgarh. | East Coast Railway [ECoR] - II | 705515 | Odisha | 12/2015 | 03/2026 | 03/2026 | 1173 | 2092 | 1971 | 80
445 | Ministry of Railways | Inland Waterways | Jeypore-Navarangpur New Rail Line Project | East Coast Railway [ECoR] - II | 705741 | Odisha | 04/2023 | 07/2028 | 12/2029 | 748 | 748 | 10.43 | 1
446 | Ministry of Railways | Inland Waterways | Jeypore-Malkanagiri New Railway Line Project | East Coast Railway [ECoR] - II | 705742 | Odisha | 12/2023 | 07/2033 | 07/2033 | 2344 | 2344 | 196.75 | 8
447 | Ministry of Railways | Railways | Khurda Road - Balangir Electrification of Railway Track Project | CORE | 706898 |  | 09/2019 | 03/2021 |  | 267.61 | 267.61 | 0 | 0
448 | Ministry of Railways | Railways | Nadikudi - Srikalahasti New Line | South Central Railway [SCR] - II | 400298 | Andhra Pradesh | 12/2016 | 05/2027 | 03/2028 | 2312 | 5200 | 2179 | 54
449 | Ministry of Railways | Railways | Malugur- Palasamudram New Line Project [17.975 Km] | South Western Railway [SWR] - II | 611615 | Andhra Pradesh | 11/2025 | 11/2027 | 12/2027 | 342 | 342.14 | 0 | 0
450 | Ministry of Railways | Railways | GOOTY-PENDEKALLU DOUBLING 29.225 Km | South Central Railway [SCR] - II | 611752 | Andhra Pradesh | 06/2023 | 03/2027 | 03/2027 | 351.83 | 351.83 | 18 | 25
451 | Ministry of Railways | Railways | GUNTAKAL WEST-MALLAPPA GATE RAIL OVER RAIL - ROR TRACK | South Central Railway [SCR] - II | 611754 | Andhra Pradesh | 07/2023 | 07/2026 |  | 293.3 | 293.3 | 0 | 0
452 | Ministry of Railways | Railways | Kurnool - Setting up facilities for coach midlife rehabilitation workshop | WPO/Patna | 611927 | Andhra Pradesh | 10/2017 | 12/2023 |  | 560.72 | 560.72 | 276.66 | 65
453 | Ministry of Railways | Railways | Flyover between Pendurthi and Simhachalam North to avoid surface crossing at Simhachalam 7.135 km PB 73 of 2023 24 NR | East Coast Railway [ECoR] - II | 612827 | Andhra Pradesh | 05/2024 | 04/2027 |  | 183.65 | 183.65 | 4.16 | 11
454 | Ministry of Railways | Railways | 3rd & 4th line between Vadlapudi -Gate Jn. cabin and Tie line between Gate Junction to Gangavaram port | East Coast Railway [ECoR] - II | 616697 | Andhra Pradesh | 03/2024 | 06/2026 |  | 154.28 | 154.28 | 10.79 | 16
455 | Ministry of Railways | Railways | Tiupati Katpadi 104.39 kms | South Central Railway [SCR] - II | 617210 | Andhra Pradesh | 04/2025 | 03/2029 |  | 1215.56 | 1215.56 | 0 | 0
456 | Ministry of Railways | Railways | 3rd Line between Gudur Renigunta 83.17 Km | South Central Railway [SCR] - II | 617216 | Andhra Pradesh | 10/2024 | 03/2027 |  | 877.34 | 877.34 | 2.97 | 0
457 | Ministry of Railways | Railways | Kotapalli - Narasapur New Line | South Central Railway [SCR] - II | 705436 | Andhra Pradesh | 09/2013 | 03/2028 | 03/2028 | 2501 | 2501 | 1264.18 | 29
458 | Ministry of Railways | Railways | Guntur-Guntakal Doubling Project | South Central Railway [SCR] - II | 705633 | Andhra Pradesh | 11/2017 | 12/2025 | 12/2026 | 3733 | 4295 | 4112.59 | 92
459 | Ministry of Railways | Railways | Vijaywada-Gudur 3rd Line | RVNL - II | 705648 | Andhra Pradesh | 04/2018 | 11/2024 | 12/2025 | 6654 | 6654 | 5922 | 90
460 | Ministry of Railways | Railways | Penukonda - Dharmavaram Doubling Project [41.5 Km] | South Western Railway [SWR] - II | 705789 | Andhra Pradesh | 12/2018 | 03/2026 | 03/2026 | 307.66 | 307.66 | 267.83 | 60
461 | Ministry of Railways | Railways | AGTHORI KAMAKHYA SECTION WITH CONSTRUCTION OF NEW RAIL CUM- ROAD BRIDGE AT SARAIGHAT - 7.062KM | Northeast Frontier Railway [NFR] | 613788 | Assam | 05/2025 | 12/2029 |  | 1473.77 | 1473.77 | 0 | 0
462 | Ministry of Railways | Railways | Doubling of New Bonggigaon to Kamakhya via Goalpara - 176 km | Northeast Frontier Railway [NFR] | 705572 | Assam | 09/2016 | 03/2026 | 03/2026 | 4060 | 4961 | 3683.75 | 93
463 | Ministry of Railways | Railways | Guwahati-Dibrugarh via Tinsukia & Simaluguri-Dibrugarh | Central Organisation for Railway Electrification [CORE] | 706922 | Assam | 09/2018 | 09/2020 | 06/2024 | 890.36 | 889.36 | 391.73 | 89
464 | Ministry of Railways | Railways | Sakri -Hasanpur [via Harnagar - Kusheshwar Asthan] New Railway line | East Central Railway [ECR] - I | 400254 | Bihar | 08/1997 | 12/2024 | 03/2027 | 735.2 | 735.2 | 585.09 | 81
465 | Ministry of Railways | Railways | Construction of Bulb line at Nabinagar Ankorah of East Central Railway | East Central Railway [ECR] - I | 617231 | Bihar | 05/2026 | 06/2028 |  | 611.74 | 611.74 | 0 | 0
466 | Ministry of Railways | Railways | Sakri-Hasanpur Road New Rail Line Project | East Central Railway [ECR] - I | 705363 | Bihar | 03/2011 | 12/2024 | 03/2025 | 735 | 735 | 605 | 78
467 | Ministry of Railways | Railways | Khagaria-Kusheshwar Asthan [42Km] new line project | East Central Railway [ECR] - I | 705364 | Bihar | 12/1998 | 12/2024 | 03/2027 | 614 | 1384 | 479.22 | 55
468 | Ministry of Railways | Railways | Hajipur-Sagauli New line | East Central Railway [ECR] - I | 705366 | Bihar | 10/2004 | 03/2020 | 12/2026 | 2067 | 2087 | 1908.49 | 74
469 | Ministry of Railways | Railways | Araria Supaul New BG Line | East Central Railway [ECR] - II | 705368 | Bihar | 03/2009 | 03/2024 | 01/2027 | 1605 | 2514 | 1311.39 | 33
470 | Ministry of Railways | Railways | Fatuha-Islampur incl. MM for extn.of NL from Neora to Daniawan , Daniawan to Biharsharif, Biharsharif to Barbigha , Barbigha to Shekhpura | East Central Railway [ECR] - II | 705373 | Bihar | 03/2002 | 03/2023 | 08/2025 | 1473 | 2882 | 2824.8 | 91
471 | Ministry of Railways | Railways | New B.G. Railway Line- Araria to Galgalia [Thakurgunj] | Northeast Frontier Railway [NFR] | 705400 | Bihar | 06/2007 | 12/2024 | 07/2025 | 2650 | 4412 | 4152.4 | 96
472 | Ministry of Railways | Railways | Jogbani-Biratnagar New Rail Line project | Indian Railway Construction International Limited [IRCON] | 705450 | Bihar | 01/2011 | 03/2022 | 12/2026 | 402 | 486 | 361 | 86
473 | Ministry of Railways | Railways | Samastipur-Darbhanga Doubling Railway Project | East Central Railway [ECR] - I | 705526 | Bihar | 12/2015 | 03/2025 | 10/2025 | 519 | 519 | 337.03 | 82
474 | Ministry of Railways | Railways | Sagauli-Valmiknagar | East Central Railway [ECR] - II | 705527 | Bihar | 03/2017 | 12/2025 | 12/2025 | 1216 | 2222 | 2039 | 91
475 | Ministry of Railways | Railways | Muzaffarpur-Sugauli | East Central Railway [ECR] - II | 705528 | Bihar | 03/2017 | 06/2024 | 08/2025 | 1586 | 1586 | 1586.82 | 99
476 | Ministry of Railways | Railways | Rampur Dumra-Tal-Rajendrapul Additional Bridge and Railway Line Doubling | Indian Railway Construction International Limited [IRCON] | 706759 | Bihar | 05/2017 | 12/2024 | 12/2025 | 2374 | 2374 | 1777 | 85
477 | Ministry of Railways | Railways | Kharsia-Dharamjaygarh with Spur line [East Corridor-Phase 1] | Indian Railway Construction International Limited [IRCON] | 400220 | Chhattisgarh | 01/2014 | 09/2018 | 03/2026 | 3055 | 3438 | 2574.54 | 94
478 | Ministry of Railways | Railways | Doubling of Kirandul-Jagdalpur Line [150 km] | East Coast Railway [ECoR] - II | 400291 | Chhattisgarh | 03/2013 | 03/2020 | 12/2025 | 1589 | 1798 | 1541.7 | 92
479 | Ministry of Railways | Railways | Gauge Conversion of Kendri-Dhamtari including Abhanpur - Rajim Branch line 67.20 Kms - 2nd Material Modification to Raipur Titlagarh doubling. | SECR | 602792 | Chhattisgarh | 05/2021 | 02/2025 | 11/2025 | 1171 | 1171 | 848 | 82
480 | Ministry of Railways | Railways | 4th line between Nipania Bhatapara 14.4 Km | South East Central Railway [SECR] - II | 612815 | Chhattisgarh | 05/2024 | 03/2027 |  | 170.49 | 170.49 | 0 | 0
481 | Ministry of Railways | Railways | Dharamjaigarh-Korba 63 km | CERL | 613003 | Chhattisgarh | 07/2022 | 08/2026 |  | 1686.26 | 1686.26 | 288.83 | 18.5
482 | Ministry of Railways | Railways | KHARSIA- NAYA RAIPUR-PARMALKASA 5th and 6th Line [278KM] | CAO/C/SECR | 617200 | Chhattisgarh | 04/2025 | 03/2031 |  | 7853.84 | 7853.84 | 0 | 0
483 | Ministry of Railways | Railways | Dallirajhra- Rowghat New Railway Line - Phase I [95 km] | RVNL - II | 705433 | Chhattisgarh | 12/2009 | 09/2025 | 12/2025 | 1628 | 1628 | 1440.85 | 82
484 | Ministry of Railways | Railways | Gevra Road-Pendra Road New Railway Line [135 km] | Indian Railway Construction International Limited [IRCON] | 705444 | Chhattisgarh | 04/2014 | 03/2022 | 12/2025 | 4970 | 4970 | 4271.55 | 72
485 | Ministry of Railways | Railways | Chirimiri-Nagpur Halt New Railway Line Project | South East Central Railway [SECR] - II | 705756 | Chhattisgarh | 06/2020 | 06/2030 | 06/2030 | 241 | 656.52 | 71 | 0
486 | Ministry of Railways | Railways | Boridand - Ambikapur Doubling Line Project | South East Central Railway [SECR] - II | 706854 | Chhattisgarh | 04/2022 | 06/2030 | 06/2030 | 1376 | 1576.23 | 218 | 18
487 | Ministry of Railways | Railways | NIPANIA-BHATAPRA [14.4 KM] 4TH LINE [PB-72/NR/2022-23] | SECR | 709814 | Chhattisgarh | 05/2024 | 12/2026 | 12/2026 | 170 | 184 | 0 | 0
488 | Ministry of Railways | Railways | 4TH LINE - BHATAPARA-HATHBAND [8.8 KM] [PB-72/NR/2022-23] | SECR | 709815 | Chhattisgarh | 05/2024 | 01/2027 | 12/2027 | 177.03 | 177.03 | 0 | 0
489 | Ministry of Railways | Railways | 4TH LINE - BHILAI-BHILAI NAGAR [8.8 KM] [PB-72/NR/2022-23] | SECR | 709816 | Chhattisgarh | 05/2024 | 02/2027 | 02/2027 | 177.34 | 177.34 | 0.76 | 2
490 | Ministry of Railways | Railways | 4TH LINE - DADHAPARA-BELHA [9.2 KM] [PB-72/NR/2022-23] | SECR | 709817 | Chhattisgarh | 05/2024 | 11/2026 | 11/2026 | 169.06 | 169.06 | 10.13 | 4
491 | Ministry of Railways | Railways | 4TH LINE RAJNANDGAON-DONGARHGARH [31.2 KM] [PB-72/NR/2022-23] | SECR | 709818 | Chhattisgarh | 05/2024 | 01/2027 | 01/2027 | 328.34 | 328.34 | 48.02 | 25
492 | Ministry of Railways | Railways | 3RD AND 4TH LINE - SARAGBUNDIA AND MADWARANI | SECR | 709819 | Chhattisgarh | 09/2022 | 12/2026 | 12/2026 | 177 | 177 | 0 | 0
493 | Ministry of Railways | Railways | Redevelopment of New Delhi Railway Station and construction of associated infrastructure | Ministry of Railways | 613785 | Delhi | 06/2024 | 12/2028 |  | 4744 | 4744 | 31.77 | 0
494 | Ministry of Railways | Railways | North Region Video Surveillance Project | RCIL | 705298 | Delhi | 04/2023 | 03/2024 |  | 274.39 | 274.39 | 0 | 0
495 | Ministry of Railways | Railways | Provision of Work-site Tampers [WST] Railway Project | EDTK[MC]/RB | 705694 | Delhi | 01/2016 | 12/2023 | 01/2026 | 187.72 | 187.72 | 141.91 | 100
496 | Ministry of Railways | Railways | WST Machine Procurement Project | EDTK[MC]/RB | 705708 | Delhi | 06/2018 | 03/2024 | 12/2027 | 176 | 176 | 0 | 0
497 | Ministry of Railways | Railways | PCT Machine Procurement Project | EDTK[MC]/RB | 705710 | Delhi | 04/2019 | 04/2024 | 06/2027 | 336 | 336 | 74.32 | 81.25
498 | Ministry of Railways | Railways | RBMV Machine Procurement Project | EDTK[MC]/RB | 705712 | Delhi | 10/2019 | 06/2024 | 12/2027 | 480 | 480 | 0.33 | 3.75
499 | Ministry of Railways | Railways | SRGM Machine Procurement Project | EDTK[MC]/RB | 705717 | Delhi | 10/2019 | 12/2023 | 03/2026 | 440 | 440 | 390.03 | 75
500 | Ministry of Railways | Railways | WST Machine Procurement Project | EDTK[MC]/RB | 705720 | Delhi | 12/2019 | 04/2024 | 12/2026 | 384 | 384 | 0 | 0
501 | Ministry of Railways | Railways | DTS Machine Procurement Project | EDTK[MC]/RB | 705721 | Delhi | 12/2019 | 12/2024 | 12/2026 | 447.6 | 447.6 | 0 | 0
502 | Ministry of Railways | Railways | BRM Machine Procurement Project | EDTK[MC]/RB | 705722 | Delhi | 09/2019 | 06/2024 | 12/2027 | 210 | 210 | 0.02 | 0
503 | Ministry of Railways | Railways | Track Machine Procurement Project | EDTK[MC]/RB | 705726 | Delhi | 04/2020 | 03/2025 | 01/2028 | 6339 | 6339 | 4166.47 | 41
504 | Ministry of Railways | Railways | Kosamba Umarpada 70 Km | PCE/WR | 611918 | Gujarat | 07/2022 | 03/2027 |  | 468 | 468 | 20 | 0
505 | Ministry of Railways | Railways | Adraj Moti Vijapur 40 Kms | Western Railway [WR] - II | 611937 | Gujarat | 05/2022 | 05/2026 | 05/2026 | 417.53 | 417.53 | 223 | 86
506 | Ministry of Railways | Railways | Vijapur Ambliyasan 42 km | PCE/WR | 611938 | Gujarat | 05/2022 | 05/2026 | 05/2026 | 415.38 | 415.38 | 364 | 96
507 | Ministry of Railways | Railways | Himatnagar Khedbrahma 55 km | WR | 611939 | Gujarat | 04/2017 | 06/2001 | 06/2026 | 482.42 | 482.42 | 461 | 96
508 | Ministry of Railways | Railways | New broad gauge line between Naliya Jakhau Port 25 Kms | PCE/WR | 611943 | Gujarat | 02/2023 | 01/2028 | 01/2028 | 410.26 | 410.26 | 6 | 4
509 | Ministry of Railways | Railways | Quadrupling between Gandhidham Adipur with Y connection at Adipur for providing direct entry towards Mundra Port and Bhuj and high level platform at Gopalpur 11Kms | PCE/WR | 611944 | Gujarat | 02/2023 | 03/2026 | 03/2026 | 152.44 | 152.44 | 20 | 68
510 | Ministry of Railways | Railways | Petlad Bhadran 23 Kms | PCE/WR | 611945 | Gujarat | 05/2022 | 05/2030 | 05/2030 | 307.11 | 307.11 | 82 | 8
511 | Ministry of Railways | Railways | Choranda Motikoral 18 Kms | PCE/WR | 611969 | Gujarat | 08/2023 | 10/2026 |  | 246 | 246 | 0 | 0
512 | Ministry of Railways | Railways | Samlaya Timba Road 54 km | PCE/WR | 611970 | Gujarat | 02/2023 | 03/2030 | 03/2030 | 670.17 | 670.17 | 102 | 12
513 | Ministry of Railways | Railways | Samni Jambusar 24 km | PCE/WR | 611971 | Gujarat | 05/2022 | 03/2030 | 03/2030 | 350 | 349.93 | 87 | 32
514 | Ministry of Railways | Railways | Jambusar Kavi 26 Kms | PCE/WR | 611972 | Gujarat | 04/2023 | 12/2026 |  | 318 | 318 | 0 | 0
515 | Ministry of Railways | Railways | miyagam karjan Choranda maalsar 37 kms | PCE/WR | 611973 | Gujarat | 06/2023 | 12/2026 |  | 450 | 450 | 0 | 0
516 | Ministry of Railways | Railways | Western Railway Samakhiali Gandhidham Quadrupiling 53 Kms | PCE/WR | 611974 | Gujarat | 08/2023 | 12/2026 |  | 1430 | 1430 | 0 | 0
517 | Ministry of Railways | Railways | Dahod Creation of Infrastructure facilities for 9000 HP Electric locomotives Manufacturing at | PCE/WR | 611977 | Gujarat | 02/2023 | 02/2025 |  | 487 | 487 | 108.69 | 0
518 | Ministry of Railways | Railways | Dahod Rolling Stock Workshop Provision of Infrastructure for CBS at | PCE/WR | 611978 | Gujarat | 03/2023 | 03/2025 |  | 158 | 158 | 47.31 | 0
519 | Ministry of Railways | Railways | Sabarmati Setting up of Maintenance Facilities for Train Sets Phase ii | PCE/WR | 611979 | Gujarat | 04/2023 | 06/2025 |  | 250 | 250 | 0 | 0
520 | Ministry of Railways | Railways | 4th LINE BETWEEN BAREJADI NANDEJ-SANAND-AHMEDABAD BYPASS | Western Railway | 612072 | Gujarat | 02/2023 | 03/2027 | 03/2027 | 961.67 | 961.67 | 132.63 | 16
521 | Ministry of Railways | Railways | Redevelopment of Ahmedabad railway station and associated infrastructure on engineering, procurement and construction mode | Ministry of Railways | 613786 | Gujarat | 11/2023 | 03/2028 |  | 2379 | 2379 | 607.69 | 15
522 | Ministry of Railways | Railways | Miyagam-Karjan-Dabhoi-Samlaya [GC] | Western Railway [WR] - II | 705458 | Gujarat | 01/2017 | 03/2021 | 12/2026 | 844 | 1600 | 693 | 68
523 | Ministry of Railways | Railways | Modasa-Shamlaji Road Railway Line Project | SECR | 706757 | Gujarat | 04/2008 | 03/2025 | 03/2027 | 262 | 262 | 203 | 58
524 | Ministry of Railways | Railways | Rajkot - Kanalus Doubling Project [111.2 Kms] | Western Railway [WR] - II | 706763 | Gujarat | 12/2021 | 10/2026 | 10/2026 | 1080.58 | 1080.58 | 731 | 72
525 | Ministry of Railways | Railways | NADIAD-PETLAD [37.26 KM] | WR | 709812 | Gujarat |  | 06/2030 | 06/2030 | 461.91 | 461.91 | 75 | 7
526 | Ministry of Railways | Railways | NEW BG LINE INTERSECTION [5 NOS] BETWEEN GERATPUR-SANAND & BOTAD-AHMEDABAD [16.51 KM] [PB#29/NR/202 | SECR | 709813 | Gujarat |  | 10/2027 | 10/2027 | 437.21 | 437.21 | 43 | 15
527 | Ministry of Railways | Railways | Bhiwani - Dobh Bahali Doubling Project [42.30 Km] | North Western Railway [NWR] | 611884 | Haryana | 02/2023 | 02/2028 | 02/2028 | 471 | 471 | 187.33 | 57
528 | Ministry of Railways | Railways | Gomoh - Flyover for DN trains | East Central Railway [ECR] - II | 705765 | Jharkhand | 01/2018 | 03/2026 | 03/2026 | 686 | 686 | 536.04 | 59
529 | Ministry of Railways | Railways | Lodhma - Piska - Link Line bypassing Hatia/Ranchi with Y connection | South Eastern Railway [SER] - I | 705785 | Jharkhand | 03/2019 | 06/2026 | 05/2027 | 473 | 473 | 284.26 | 4
530 | Ministry of Railways | Railways | Construction of New BG line between Hassan to Belur [27 Km] | South Western Railway [SWR] - II | 400023 | Karnataka | 12/2025 | 04/2028 | 04/2027 | 749 | 749 | 0 | 0
531 | Ministry of Railways | Railways | Yeshvanthpur - Channasandra Doubling Project [21.70 Km] | Karnataka Rail Infrastructure Development Company Limited [K-RIDE] | 703585 | Karnataka | 10/2019 | 12/2024 | 06/2026 | 314 | 314 | 144 | 59
532 | Ministry of Railways | Railways | New Railway Line between Ginigera and Raichur [165.57 km] | South Western Railway [SWR] - II | 705434 | Karnataka | 05/2009 | 03/2019 | 03/2027 | 2565 | 3034.98 | 2063.57 | 66
533 | Ministry of Railways | Railways | Gadag-Wadi New Railway Line [257 km] | South Western Railway [SWR] - II | 705490 | Karnataka | 08/2017 | 03/2027 | 12/2027 | 2842 | 6700 | 1721.14 | 30
534 | Ministry of Railways | Railways | Kadur - Chickamagalur - Sakleshpur [93km] | South Western Railway [SWR] - II | 705492 | Karnataka | 11/2016 | 06/2025 | 12/2025 | 825 | 825 | 770.18 | 83
535 | Ministry of Railways | Railways | Bagalkot-Kudachi New Railway Line [142 km] | South Western Railway [SWR] - II | 705495 | Karnataka | 11/2012 | 03/2027 | 01/2027 | 1378 | 1649 | 670.74 | 35
536 | Ministry of Railways | Railways | Tumkur-Chitradurga-Davangere New Rail Line Project [191 km] | South Western Railway [SWR] - II | 705496 | Karnataka | 01/2017 | 03/2019 | 12/2027 | 1876 | 1876 | 516.17 | 13
537 | Ministry of Railways | Railways | SHIMOGA - SHIKARIPURA - RANEBENNUR [96 Km] | South Western Railway [SWR] - II | 705761 | Karnataka | 02/2023 | 12/2027 | 06/2028 | 1454 | 1454 | 69.58 | 11
538 | Ministry of Railways | Railways | Belgaum-Dharwad via Kittur [73.10Km] | South Western Railway [SWR] - II | 706835 | Karnataka | 03/2025 | 12/2027 | 03/2029 | 1591 | 1591 | 0.75 | 0
539 | Ministry of Railways | Railways | Kumbalam-Turavur doubling project [15.59 Km] | Southern Railway [SR] - II | 705638 | Kerala | 04/2023 | 03/2027 | 03/2027 | 813 | 813 | 292.15 | 15
540 | Ministry of Railways | Railways | Ernakulam-Kumbalam doubling project [7.71 Km] | SR-ERS | 705639 | Kerala | 04/2023 | 03/2028 | 03/2028 | 601 | 601 | 283 | 17
541 | Ministry of Railways | Railways | Lalitpur-Satna, Rewa-Singrauli & Mahoba-Khajuraho | North Central Railway | 705480 | Madhya Pradesh | 03/1998 | 03/2027 | 12/2027 | 8914 | 8914 | 4971.65 | 70
542 | Ministry of Railways | Railways | Katni - Bina Third Railway Line [279 km] | West Central Railway WCR I | 705651 | Madhya Pradesh | 01/2017 | 03/2022 | 12/2025 | 2478.23 | 4127.23 | 3295.49 | 90
543 | Ministry of Railways | Railways | Satna-Rewa Railway Line Doubling Project | West Central Railway [WCR] - II | 705659 | Madhya Pradesh | 08/2017 | 03/2026 | 03/2026 | 500 | 584 | 561.26 | 80
544 | Ministry of Railways | Railways | Doubling of Katni - Singrauli Railway Line [261 km] | Indian Railway Construction International Limited [IRCON] | 705660 | Madhya Pradesh | 03/2017 | 12/2026 | 12/2027 | 2445 | 4377 | 3122 | 100
545 | Ministry of Railways | Railways | Katni Grade Separator/Bye Pass | Indian Railway Construction International Limited [IRCON] | 705661 | Madhya Pradesh | 09/2017 | 09/2024 | 03/2026 | 1248 | 1248 | 1537.77 | 92
546 | Ministry of Railways | Railways | Indore - Budni New Railway Line [198 kms] | RVNL - II | 705763 | Madhya Pradesh | 10/2020 | 09/2030 | 09/2030 | 7474 | 7474 | 1658.03 | 22
547 | Ministry of Railways | Railways | Nimach-Ratlam Doubling [133 Km] | Western Railway [WR] - II | 705933 | Madhya Pradesh | 10/2021 | 10/2027 | 10/2027 | 1095.88 | 1095.88 | 1056.18 | 89
548 | Ministry of Railways | Railways | DHULE [BORVIHIR] - NARDANA NEW LINE [50.60 KMS] | CR | 400019 | Maharashtra | 04/2023 | 12/2026 | 09/2027 | 493 | 1171 | 234.48 | 9
549 | Ministry of Railways | Railways | Wardha-Nanded Via Yavatmal New BG Line | Central Railway [CR] - II | 400271 | Maharashtra | 04/2008 | 03/2028 | 03/2028 | 3445 | 3445 | 3002.93 | 50
550 | Ministry of Railways | Railways | AURANGABAD-ANKAI - DOUBLING PROJECT 98.25 Km | South Central Railway [SCR] - II | 611751 | Maharashtra | 05/2023 | 03/2027 |  | 960.64 | 960.64 | 0 | 0.01
551 | Ministry of Railways | Railways | Western Railway Vasai bypass double line between Naigaon Juchandra 6 km | PCE/WR | 611975 | Maharashtra | 07/2023 | 03/2026 |  | 176 | 176 | 0 | 0
552 | Ministry of Railways | Railways | Jogeshwari AT Development of JOS-AT as Trainset Maintenance Depot for energy efficient Vande Bharat Sleeper Trains | PCE/WR | 611976 | Maharashtra | 06/2023 | 10/2025 |  | 221 | 221 | 0 | 0
553 | Ministry of Railways | Railways | Redevelopment of Chhatrapati Shivaji Maharaj Terminus [CSMT] and construction of associated infrastructure | Ministry of Railways | 613015 | Maharashtra | 07/2023 | 03/2027 |  | 1813 | 1813 | 525.2 | 12
554 | Ministry of Railways | Railways | Gondia-Balharshah [Chanda Fort] Doubling [240 Km] | South East Central Railway | 617201 | Maharashtra | 04/2025 | 04/2030 |  | 4373.04 | 4373.04 | 0 | 0
555 | Ministry of Railways | Railways | Doubling between Parbhani Parli Vaijanath stations 64.71 Km | South Central Railway [SCR] - II | 617215 | Maharashtra | 12/2023 | 03/2028 |  | 769.93 | 769.93 | 0 | 0
556 | Ministry of Railways | Railways | Western Region Video Surveillance Project | RCIL | 705300 | Maharashtra | 04/2023 | 12/2023 |  | 227.59 | 227.59 | 0 | 0
557 | Ministry of Railways | Railways | Ahmednagar - Beed - Parli - Vaijnath New Broad Gauge Line Railway Project [261.3 km] | Central Railways | 705356 | Maharashtra | 10/2002 | 03/2026 | 03/2026 | 2539 | 4957 | 4725.34 | 92
558 | Ministry of Railways | Railways | Baramati Lonand New Line Project | Central Railway [CR] - II | 705357 | Maharashtra | 03/1999 | 03/2027 | 03/2027 | 736 | 1844 | 712 | 50
559 | Ministry of Railways | Railways | Wadsa-Gadchiroli | South East Central Railway | 705479 | Maharashtra | 03/2012 | 03/2027 | 03/2027 | 1886 | 1886 | 706.28 | 49
560 | Ministry of Railways | Railways | 3rd Line Kalyan - Kasara [67.35 Kilometres] | Central Railway [CR] - II | 705498 | Maharashtra | 09/2015 | 12/2026 | 12/2026 | 793 | 1432 | 894.16 | 50
561 | Ministry of Railways | Railways | 3rd Line Wardha - Sewagram - Nagpur | Central Railway [CR] - II | 705500 | Maharashtra | 05/2016 | 12/2025 | 12/2025 | 540 | 698 | 724.75 | 80
562 | Ministry of Railways | Railways | 3rd Line Wardha - Ballarshah [132 Kilometres] | Central Railway [CR] - II | 705502 | Maharashtra | 12/2016 | 12/2025 | 02/2026 | 1385 | 1385 | 1102.48 | 77
563 | Ministry of Railways | Railways | Pune - Miraj-Londa [467 Kilometres] | Central Railway [CR] - II | 705503 | Maharashtra | 06/2016 | 02/2025 | 08/2025 | 3627 | 6689 | 6548 | 84
564 | Ministry of Railways | Railways | Doubling of Daund Manmad Line [247.6 km] | Central Railway [CR] - II | 705504 | Maharashtra | 03/2017 | 12/2025 | 12/2025 | 2081 | 3075 | 2769 | 88
565 | Ministry of Railways | Railways | 4th Line Wardha - Nagpur [78.7 Kilometres] | Central Railway [CR] - II | 705505 | Maharashtra | 05/2018 | 12/2025 | 02/2026 | 638 | 1137 | 969 | 80
566 | Ministry of Railways | Railways | 3rd Line Manmad - Jalgaon [160 Kilometres] | Central Railway [CR] - II | 705506 | Maharashtra | 04/2018 | 12/2024 | 08/2025 | 1035 | 1559 | 1692 | 97
567 | Ministry of Railways | Railways | Solapur-tuljapur-Osmanabad | WR | 705735 | Maharashtra | 12/2023 | 03/2028 | 03/2028 | 905 | 3296 | 1150 | 10
568 | Ministry of Railways | Railways | Nagpur- Nagbhir Railway Line Gauge Conversion Project | MRIDC | 705799 | Maharashtra | 04/2020 | 12/2025 | 12/2025 | 1400 | 1400 | 1472 | 80
569 | Ministry of Railways | Railways | Mumbai Urban Transport Project [MUTP] - PHASE II | Mumbai Rail Vikas Corporation Ltd.[MRVC] | 706779 | Maharashtra | 04/2008 | 03/2014 | 12/2027 | 8087 | 8087 | 7364 | 87
570 | Ministry of Railways | Railways | Mumbai Urban Transport Project [MUTP] Phase-IIIA | Mumbai Rail Vikas Corporation Ltd.[MRVC] | 706780 | Maharashtra | 04/2019 | 12/2027 | 12/2027 | 33690 | 33690 | 2246.15 | 16
571 | Ministry of Railways | Railways | Mumbai Urban Transport Project Phase-III | Mumbai Rail Vikas Corporation Ltd.[MRVC] | 706781 | Maharashtra | 12/2016 | 03/2022 | 12/2026 | 10947 | 10947 | 5057.67 | 60
572 | Ministry of Railways | Railways | PACHORA-JAMNER WITH EXTENSION UPTO MALKAPUR NG TO BG | CR | 709808 | Maharashtra | 01/2022 | 08/2027 | 03/2028 | 955 | 2094 | 118 | 2
573 | Ministry of Railways | Railways | KALYAN-MURBAD VIA ULHASNAGAR [UMBRELLA WORK] | Central Railway [CR] - II | 709809 | Maharashtra | 04/2023 | 03/2027 | 03/2027 | 836 | 836 | 9.29 | 1
574 | Ministry of Railways | Railways | Marikuppam - Kuppam New Line Project [23.70 Km] | South Western Railway [SWR] - II | 705491 | Multi-States (Andhra Pradesh, Karnataka) | 10/2018 | 06/2026 | 06/2026 | 297 | 297 | 123.17 | 15
575 | Ministry of Railways | Railways | Rayadurg-Tumkur via Kalyandurg New Line [207 km] | South Western Railway [SWR] - II | 705494 | Multi-States (Andhra Pradesh, Karnataka) | 07/2010 | 09/2015 | 02/2028 | 2496 | 2496 | 1691.88 | 67
576 | Ministry of Railways | Railways | Renigunta, Wadi & Gooty Bypass Railway Project | South Central Railway [SCR] - I | 705610 | Multi-States (Andhra Pradesh, Karnataka) | 04/2016 | 12/2025 | 12/2025 | 302 | 543 | 381 | 50
577 | Ministry of Railways | Railways | Doubling between Mudkhed Medchal & Mahbubnagar Dhone section 417.88 Km | South Central Railway [SCR] - II | 617212 | Multi-States (Andhra Pradesh, Maharashtra, Telangana) | 08/2023 | 03/2029 |  | 4686.09 | 4686.09 | 0 | 0
578 | Ministry of Railways | Railways | Vizianagaram - Titlagarh 3rd line [272 Km including By - pass line of 7.68 KM] | RVNL - II | 400253 | Multi-States (Andhra Pradesh, Odisha) | 11/2016 | 12/2026 | 12/2026 | 4803 | 6670 | 5722.01 | 89
579 | Ministry of Railways | Railways | Doubling of Kottavalasa-Koraput Rail Line [189 KM] | East Coast Railway [ECoR] - II | 705512 | Multi-States (Andhra Pradesh, Odisha) | 01/2016 | 03/2022 | 03/2028 | 2500 | 2500 | 2033.31 | 70
580 | Ministry of Railways | Railways | Malkangiri Pandurangapuram new railway line project | Indian Railways | 616702 | Multi-States (Andhra Pradesh, Odisha, Telangana) | 01/2027 | 11/2031 |  | 3591.76 | 3591.76 | 0 | 0
581 | Ministry of Railways | Railways | Tindivanam-Nagari New Line Project [184.5 km] | Southern Railway [SR] - II | 400275 | Multi-States (Andhra Pradesh, Tamil Nadu) | 10/2008 | 09/2016 | 03/2028 | 3631 | 3631 | 1113.53 | 18
582 | Ministry of Railways | Railways | Doubling between Motumari Vishnupuram - 88.81 Km and Rail over Rail - RoR at Motumari - 10.877 Km | South Central Railway [SCR] - II | 616857 | Multi-States (Andhra Pradesh, Telangana) | 03/2025 | 03/2029 |  | 1595.55 | 1595.55 | 7.69 | 1
583 | Ministry of Railways | Railways | Doubling of Guntur Bibinagar 239 Km | South Central Railway [SCR] - II | 617211 | Multi-States (Andhra Pradesh, Telangana) | 08/2023 | 03/2029 |  | 2853.23 | 2853.23 | 43.88 | 1
584 | Ministry of Railways | Railways | Rail Connectivity to Errupalem Amravati Namburu 57 Km | South Central Railway [SCR] - II | 617214 | Multi-States (Andhra Pradesh, Telangana) | 11/2024 | 03/2027 |  | 2047.4 | 2047.4 | 0 | 0
585 | Ministry of Railways | Railways | Kazipet-Vijayawada 3rd line with electrification [220 km] | South Central Railway [SCR] - II | 705612 | Multi-States (Andhra Pradesh, Telangana) | 08/2014 | 02/2025 | 12/2025 | 1953 | 3363 | 2915.49 | 90
586 | Ministry of Railways | Railways | Vijayawada - Kazipet Byepass line | South Central Railway [SCR] - II | 705632 | Multi-States (Andhra Pradesh, Telangana) | 04/2016 | 01/2025 | 12/2025 | 647 | 904 | 870 | 91
587 | Ministry of Railways | Railways | Murkongselek-Pasighat | Northeast Frontier Railway [NFR] | 705401 | Multi-States (Arunachal Pradesh, Assam) | 03/2012 | 03/2025 | 12/2025 | 435 | 1250 | 901 | 56
588 | Ministry of Railways | Railways | Lumding Furkating Doubling Project 140 km | Northeast Frontier Railway [NFR] | 616701 | Multi-States (Assam, Nagaland) | 01/2025 | 02/2028 |  | 2123.7 | 2123.7 | 13.74 | 0
589 | Ministry of Railways | Railways | Dimapur [Dhansiri]-Sukhobi Kohima [Zubza] NL [82.5 Km] | Northeast Frontier Railway [NFR] | 705392 | Multi-States (Assam, Nagaland) | 02/2016 | 03/2025 | 12/2025 | 6663 | 6663 | 5202.29 | 79
590 | Ministry of Railways | Railways | New Delhi- Howrah Speed Booster[160Kmph] Project | PCE/NCR | 705794 | Multi-States (Bihar, Delhi, Jharkhand, Uttar Pradesh, West Bengal) | 09/2019 | 03/2024 |  | 6684.81 | 6684.81 | 127.03 | 0
591 | Ministry of Railways | Railways | Third Railway Line between Patratu-Sonnagar [281 kms] | RVNL - II | 400234 | Multi-States (Bihar, Jharkhand) | 08/2018 | 03/2026 | 07/2026 | 8975 | 8975 | 4950 | 88
592 | Ministry of Railways | Railways | Multi tracking of Son Nagar-Andal [374.53 rkm & 814.38 tkm] | East Central Railway [ECR] - I | 616699 | Multi-States (Bihar, Jharkhand) | 08/2023 | 03/2028 |  | 12333.57 | 12333.6 | 444.74 | 10
593 | Ministry of Railways | Railways | Koderma-Tilaiya New Line | East Central Railway [ECR] - II | 705375 | Multi-States (Bihar, Jharkhand) | 03/2002 | 02/2025 | 02/2026 | 1626 | 2020 | 2060.97 | 92
594 | Ministry of Railways | Railways | Pirpainti - Jasidih [100.52 Km] New BG line | Eastern Railway [ER] - I | 705385 | Multi-States (Bihar, Jharkhand) | 03/2022 | 03/2028 | 03/2028 | 2555 | 2555 | 763.08 | 48
595 | Ministry of Railways | Railways | NER Provision of Automatic Block Signalling on Gorakhpur Cantt[Excl] Chhapra Gramin & Burhwal Jn [Excl] Sitapur Jn section of high density routes | North Eastern Railway [NER] | 611669 | Multi-States (Bihar, Uttar Pradesh) | 06/2023 | 03/2027 |  | 380.47 | 380.47 | 24.53 | 0
596 | Ministry of Railways | Railways | Gorakhpur-Valmikinagar Doubling project | NER | 617224 | Multi-States (Bihar, Uttar Pradesh) | 03/2024 | 12/2027 |  | 1120 | 1120 | 181.86 | 20
597 | Ministry of Railways | Railways | Chhapra-Ballia Patch Doubling | North Eastern Railway [NER] | 705562 | Multi-States (Bihar, Uttar Pradesh) | 11/2015 | 02/2025 | 03/2026 | 963 | 1046 | 906 | 95.4
598 | Ministry of Railways | Railways | Rajnandgaon - Nagpur [Kalumna] Third Railway Line [228.30 km] | South East Central Railway [SECR] - II | 705617 | Multi-States (Chhattisgarh, Maharashtra) | 12/2016 | 12/2024 | 06/2026 | 3545 | 3545 | 3163.08 | 95
599 | Ministry of Railways | Railways | Jagdalpur-Koraput | East Coast Railway [ECoR] - II | 705511 | Multi-States (Chhattisgarh, Odisha) | 03/2016 | 03/2024 | 12/2026 | 1547 | 1547 | 1308.2 | 90
600 | Ministry of Railways | Railways | Jharsuguda-Bilaspur Fourth Railway Line [206 km] | SECR | 705616 | Multi-States (Chhattisgarh, Odisha) | 09/2016 | 10/2024 | 12/2025 | 2140 | 2979 | 2124.15 | 88
601 | Ministry of Railways | Railways | Mumbai-Ahmedabad High Speed Rail Project- 508 km | National High Speed Rail Corporation [NHSRC] | 705728 | Multi-States (Dadra & Nagar Haveli and Daman & Diu, Gujarat, Maharashtra) | 09/2017 | 08/2027 | 12/2029 | 108000 | 108000 | 78690.89 | 53
602 | Ministry of Railways | Railways | New Delhi- Mumbai Speed Booster[160Kmph] Project | PCE/WR | 705793 | Multi-States (Delhi, Gujarat, Madhya Pradesh, Maharashtra, Rajasthan) | 09/2019 | 03/2024 |  | 6806.44 | 6806.44 | 135.65 | 0
603 | Ministry of Railways | Railways | Hospet - Tinaighat - Vasco Rail Doubling Project | RVNL - II | 705650 | Multi-States (Goa, Karnataka) | 07/2012 | 03/2027 | 12/2027 | 5060 | 5060 | 5007.82 | 86
604 | Ministry of Railways | Railways | Hospet-Hubli-Vasco da Gama Line Electrification Project | RVNL | 706950 | Multi-States (Goa, Karnataka) | 05/2018 | 03/2023 | 03/2024 | 744.49 | 1122.62 | 969.05 | 95
605 | Ministry of Railways | Railways | Western Dedicated Freight Corridor | DFCCIL | 705237 | Multi-States (Gujarat, Haryana, Maharashtra, Rajasthan, Uttar Pradesh) | 01/2012 | 03/2022 | 12/2025 | 51101 | 124005 | 124623 | 96
606 | Ministry of Railways | Railways | New line Dahod-Indore via Sardarpur, Jabuwa and Dhar | Western Railway [WR] - II | 705453 | Multi-States (Gujarat, Madhya Pradesh) | 06/2012 | 02/2027 | 02/2027 | 1942 | 2691 | 3412.98 | 67
607 | Ministry of Railways | Railways | Chhota Udaipur - Dhar New Line Project [157 km] | Western Railway [WR] - II | 705454 | Multi-States (Gujarat, Madhya Pradesh) | 01/2014 | 12/2025 | 12/2025 | 1794 | 1794 | 1800.85 | 80
608 | Ministry of Railways | Railways | MUMBAI CENTRAL VIRAR VADODARA AHMEDABAAD TRAIN PROTECTION SYSTEM 500 RKM | Western Railway | 611452 | Multi-States (Gujarat, Maharashtra) | 03/2023 | 12/2025 | 06/2025 | 311 | 311 | 208 | 92
609 | Ministry of Railways | Railways | Taranga Hill-Abu Road via Ambaji | North Western Railway [NWR] | 400022 | Multi-States (Gujarat, Rajasthan) | 07/2022 | 07/2030 | 07/2030 | 2798 | 2798 | 1891.9 | 14
610 | Ministry of Railways | Railways | LUNI- SAMDARI- BHILDI DOUBLING | North Western Railway [NWR] | 616842 | Multi-States (Gujarat, Rajasthan) | 02/2024 | 07/2027 |  | 3085.59 | 3085.59 | 154.46 | 7
611 | Ministry of Railways | Railways | Chandigarh-Baddi New Rail Line- 36 km | Northen Railway [NR] | 705424 | Multi-States (Haryana, Himachal Pradesh) | 02/2018 | 12/2026 | 12/2026 | 1540 | 1540 | 506.73 | 31
612 | Ministry of Railways | Railways | Rewari - Kathuwas Doubling Project [27.72 Km] | North Western Railway [NWR] | 611861 | Multi-States (Haryana, Rajasthan) | 12/2022 | 06/2027 | 06/2027 | 352 | 352 | 239.01 | 59
613 | Ministry of Railways | Railways | Nangal Dam-Talwara New Broad Gauge Line [84 KM] and Taking Over Siding Mukerian-Talwara [29 KM] | Northen Railway [NR] | 705410 | Multi-States (Himachal Pradesh, Punjab) | 05/1985 | 12/2025 | 01/2027 | 2018 | 2018 | 1848 | 74
614 | Ministry of Railways | Railways | Bhanupalli-Bilaspur-Beri New Railway Line Project | RVNL - II | 705428 | Multi-States (Himachal Pradesh, Punjab) | 04/2015 | 12/2026 | 12/2027 | 13447 | 13447 | 6391.15 | 59
615 | Ministry of Railways | Railways | Doubling of Hatia [Ranchi]-Bondamunda Rail Line - 159 km | South Eastern Railway - JH | 705628 | Multi-States (Jharkhand, Odisha) | 02/2017 | 06/2025 | 06/2026 | 3029 | 3029 | 2458.15 | 85
616 | Ministry of Railways | Railways | Buramara-Chakulia new line [59.96 km] | South Eastern Railway [SER] - I | 616588 | Multi-States (Jharkhand, Odisha, West Bengal) | 12/2024 | 12/2029 |  | 1459.13 | 1459.13 | 1.04 | 0
617 | Ministry of Railways | Railways | Chandil - Anara - Damodar - 3rd line [121.26 km] | CAO/C/SER | 616227 | Multi-States (Jharkhand, West Bengal) | 07/2025 | 09/2029 |  | 1932.01 | 1932.01 | 0.03 | 0
618 | Ministry of Railways | Railways | Murarai - Barharwa 3rd line | Eastern Railway [ER] - II | 617240 | Multi-States (Jharkhand, West Bengal) | 01/2026 | 05/2028 |  | 935.19 | 935.19 | 0 | 0
619 | Ministry of Railways | Railways | KHARAGPUR-ADITYAPUR THIRD RAIL LINE- 132 KM | RVNL - II | 705668 | Multi-States (Jharkhand, West Bengal) | 01/2018 | 03/2025 | 12/2025 | 3250 | 3250 | 3176.46 | 97
620 | Ministry of Railways | Railways | Hotgi-Kudgi-Gadag Doubling Project | South Western Railway [SWR] - II | 705662 | Multi-States (Karnataka, Maharashtra) | 01/2016 | 12/2024 | 03/2026 | 1878 | 2459 | 2628.8 | 89
621 | Ministry of Railways | Railways | Baiyyappanahalli - Hosur Doubling Project [48 km] | Karnataka Rail Infrastructure Development Company Limited [K-RIDE] | 703586 | Multi-States (Karnataka, Tamil Nadu) | 02/2019 | 12/2024 | 01/2026 | 499 | 499 | 595 | 97
622 | Ministry of Railways | Railways | Trivandrum- Kanyakumari | SR-ERS | 705635 | Multi-States (Kerala, Tamil Nadu) | 03/2016 | 03/2024 | 12/2027 | 1432 | 3785 | 2451 | 46
623 | Ministry of Railways | Railways | Ratlam-Mhow-Khandwa-Akola Gauge Conversion | Western Railway [WR] - II | 705457 | Multi-States (Madhya Pradesh, Maharashtra) | 03/2010 | 03/2027 | 09/2028 | 5678 | 6531.9 | 4314 | 87
624 | Ministry of Railways | Railways | Itarsi - Nagpur Third Railway Line [280 km] | Central Railway [CR] - II | 705507 | Multi-States (Madhya Pradesh, Maharashtra) | 09/2016 | 03/2027 | 03/2027 | 2450 | 2450 | 1815.49 | 52
625 | Ministry of Railways | Railways | Gwalior - Seopurkala with extension to Kota [Gauge Conversion] | North Central Railway | 705419 | Multi-States (Madhya Pradesh, Rajasthan) | 07/2018 | 03/2025 | 02/2026 | 2913 | 2913 | 2751 | 83
626 | Ministry of Railways | Railways | Ramganjmandi-Bhopal New Line Project [262 km] | West Central Railway [WCR] - II | 705481 | Multi-States (Madhya Pradesh, Rajasthan) | 10/2004 | 12/2025 | 12/2027 | 3032 | 5073 | 3592.92 | 70
627 | Ministry of Railways | Railways | Nimach-Badi Sadri New Rail Line Project | Western Railway [WR] - II | 705764 | Multi-States (Madhya Pradesh, Rajasthan) | 09/2021 | 03/2026 | 12/2025 | 495 | 825 | 306 | 46
628 | Ministry of Railways | Railways | Mathura-Jhansi Third Railway Line [274 Km] | RVNL - II | 705667 | Multi-States (Madhya Pradesh, Rajasthan, Uttar Pradesh) | 03/2018 | 12/2024 | 12/2026 | 5961 | 5961 | 4928.62 | 94
629 | Ministry of Railways | Railways | Jhansi - Bina Third Railway Line [153 Km] | CAO/C/NCR | 705598 | Multi-States (Madhya Pradesh, Uttar Pradesh) | 03/2018 | 03/2022 | 03/2026 | 2002 | 2002 | 1884.84 | 93
630 | Ministry of Railways | Railways | Jhansi-Khairar-Manikpur & Khirar-Bhimsen | North Central Railway | 705608 | Multi-States (Madhya Pradesh, Uttar Pradesh) | 03/2017 | 03/2026 | 03/2026 | 4330 | 4330 | 1989 | 53
631 | Ministry of Railways | Railways | Third Line [new] between Kazipet - Balharshah with electrification [201.04 Km] | South Central Railway [SCR] - II | 705613 | Multi-States (Maharashtra, Telangana) | 10/2016 | 01/2025 | 11/2025 | 2595 | 3071 | 3142.35 | 92
632 | Ministry of Railways | Railways | Narayangarh-Bhadrak 3rd line | South Eastern Railway [SER] - I | 705629 | Multi-States (Odisha, West Bengal) | 03/2017 | 12/2025 | 06/2026 | 2400 | 2400 | 2188 | 65
633 | Ministry of Railways | Railways | Nagapattinam-Tiruturaipundi and Karaikal-Peralam New Line | Southern Railway [SR] - II | 400223 | Multi-States (Puducherry, Tamil Nadu) | 01/2019 | 03/2026 | 03/2027 | 713 | 981 | 598.38 | 80
634 | Ministry of Railways | Railways | Sivok-Rangpo New Rail Line | Indian Railway Construction International Limited [IRCON] | 705432 | Multi-States (Sikkim, West Bengal) | 05/2010 | 05/2015 | 12/2027 | 7877 | 12133 | 8883.6 | 80
635 | Ministry of Railways | Railways | Sainthia, Sitarampur, Mughalsarai, Allahabad & Etawah - Bypass Line Project | Eastern Railway [ER] - I | 602797 | Multi-States (Uttar Pradesh, West Bengal) | 12/2017 | 03/2027 | 03/2027 | 461.64 | 461.64 | 178.45 | 6
636 | Ministry of Railways | Railways | Proposed 6 nos Road Over Bridge [ROB] at different locations under MCL Talcher Under Deposit Scheme. | East Coast Railway [ECoR] - II | 400045 | Odisha | 07/2022 | 03/2025 | 01/2025 | 168.32 | 168.32 | 69.85 | 82
637 | Ministry of Railways | Railways | Brundamal-Jharsuguda- flyover connection for joining downline | East Coast Railway [ECoR] - II | 400232 | Odisha | 01/2014 | 12/2026 | 12/2026 | 297 | 297 | 193.22 | 30
638 | Ministry of Railways | Railways | 3rd & 4th line between Sarla - Sason [8 km] [PB 73/2023-24/NR] | East Coast Railway [ECoR] - II | 612834 | Odisha | 04/2023 | 12/2025 |  | 252 | 252 | 79.55 | 45
639 | Ministry of Railways | Railways | Bangriposi-Gorumahisani new line [ 85.60 km ] | CAO/C/SER | 616586 | Odisha | 09/2025 | 12/2029 |  | 2269.49 | 2269.49 | 0 | 0
640 | Ministry of Railways | Railways | Badampahar-Kendujhargarh new line [82.06 km] | CAO/C/SER | 616587 | Odisha | 09/2025 | 12/2029 |  | 1875.72 | 1875.72 | 0 | 0
641 | Ministry of Railways | Railways | Flyover between Siju and Paradeep coaching Yard to avoid Surface crossing of trains | East Coast Railway [ECoR] - II | 616694 | Odisha | 10/2025 | 07/2028 |  | 200.77 | 200.77 | 0 | 0
642 | Ministry of Railways | Railways | Paradeep - Badabandha 3rd & 4th Line / 18.51kms | East Coast Railway [ECoR] - II | 616695 | Odisha | 04/2025 | 11/2028 |  | 300.15 | 300.15 | 0.01 | 0
643 | Ministry of Railways | Railways | Khurda-Bolangir New Broad Gauge Rail Link [301km] | East Coast Railway [ECoR] - II | 705358 | Odisha | 03/2001 | 12/2026 | 12/2026 | 3792 | 5089 | 4983.45 | 89
644 | Ministry of Railways | Railways | Talcher-Bimlagarh New Railway Line | East Coast Railway [ECoR] - II | 705359 | Odisha | 12/2004 | 03/2025 | 03/2027 | 1928 | 1928 | 1902.91 | 47
645 | Ministry of Railways | Railways | Bhadrak-Nergundi Third Line | East Coast Railway [ECoR] - II | 705510 | Odisha | 04/2015 | 11/2024 | 01/2026 | 1284 | 1284 | 1298 | 80
646 | Ministry of Railways | Railways | Koraput - Singapur Railway Doubling | East Coast Railway [ECoR] - II | 705513 | Odisha | 12/2015 | 12/2027 | 03/2028 | 2362 | 2362 | 1787.49 | 68
647 | Ministry of Railways | Railways | Jarapada- Budhapank with flyover at Talcher road 3rd and 4th Line | East Coast Railway [ECoR] - II | 705514 | Odisha | 12/2015 | 11/2018 | 03/2026 | 1000 | 810.02 | 401.61 | 36
648 | Ministry of Railways | Railways | Talcher-Angul New Line with Y-Connection at Talcher | CAO/C/ECoR | 705743 | Odisha |  | 05/2027 | 05/2028 | 495 | 495 | 29.5 | 1
649 | Ministry of Railways | Railways | Baghuapal Flyover Construction Project | CAO/C/ECoR | 705767 | Odisha | 10/2022 | 03/2028 | 03/2028 | 257.97 | 258 | 0.83 | 0
650 | Ministry of Railways | Railways | Rourkela - Bondamunda 5th Line Doubling Project | South Eastern Railway [SER] - I | 706856 | Odisha | 03/2022 | 09/2026 | 09/2026 | 245 | 245 | 82 | 35
651 | Ministry of Railways | Railways | KODINGAMALI BAUXITE MINES TO SINGARAM RAILWAY STATION | Indian Railway | 709810 | Odisha | 01/2026 | 08/2027 | 08/2027 | 190.9 | 190.9 | 0 | 0
652 | Ministry of Railways | Railways | GANDHAMARDAN IRON ORE MINES TO GOALDIH STATION/12.76kms | East Coast Railway [ECoR] - II | 709811 | Odisha | 05/2025 | 09/2027 | 09/2027 | 190 | 190 | 0 | 0
653 | Ministry of Railways | Railways | Junagarh Visavadar 42 Kms | WR | 611980 | Offshore | 02/2023 | 09/2028 | 09/2028 | 492.83 | 492.83 | 3 | 1
654 | Ministry of Railways | Railways | Jaynagar-Bijalpura, incl. extn. Bet, Bijalpura-Bardibas [Nepal] | East Central Railway [ECR] - I | 705362 | Offshore | 03/2011 | 03/2022 | 03/2026 | 819 | 819 | 588.32 | 75
655 | Ministry of Railways | Railways | Ludhiana- Killa Raipur Railway Doubling Project | CAO/C/NR | 705783 | Punjab | 12/2022 | 03/2025 | 03/2026 | 237.64 | 237.64 | 118 | 55
656 | Ministry of Railways | Railways | Dedicated Test Track for RDSO Phase II | North Western Railway [NWR] | 611614 | Rajasthan | 11/2021 | 11/2026 | 11/2026 | 819.48 | 967.06 | 471 | 86
657 | Ministry of Railways | Railways | Devgarh Madariya - Nathdwara Gauge Conversion [82.54 Km] part of Marwar - Mavli Gauge Conversion [152 Km] | North Western Railway [NWR] | 611849 | Rajasthan | 01/2023 | 06/2028 | 06/2028 | 969 | 969 | 411 | 45
658 | Ministry of Railways | Railways | Maintenance cum workshop depot for Vande Bharat Sleeper Trains as per conditions under WTA 527 | WPO/Patna | 611929 | Rajasthan | 06/2023 | 12/2024 |  | 166.86 | 166.86 | 0 | 0
659 | Ministry of Railways | Railways | RINGUS KHATUSHYAMJI NEW LINE | North Western Railway [NWR] | 616696 | Rajasthan | 03/2024 | 03/2028 |  | 254.06 | 254.06 | 1.65 | 0
660 | Ministry of Railways | Railways | RAS- MERTA CITY NEW LINE INCL BYPASS AT MERTA ROAD | North Western Railway [NWR] | 616840 | Rajasthan | 02/2024 | 03/2028 |  | 947 | 947 | 1.36 | 0
661 | Ministry of Railways | Railways | PUSHKAR- MERTA CITY NEW LINE | North Western Railway [NWR] | 616841 | Rajasthan | 02/2024 | 12/2026 |  | 799.64 | 799.64 | 13.91 | 3
662 | Ministry of Railways | Railways | AJMER- CHANDERIYA DOUBLING | North Western Railway [NWR] | 616843 | Rajasthan | 02/2024 | 06/2027 |  | 1634.79 | 1634.79 | 59.51 | 5
663 | Ministry of Railways | Railways | Dholpur - Sirmuttra Gauge Conversion | North Central Railway | 705482 | Rajasthan | 04/2020 | 02/2019 | 02/2027 | 747 | 747 | 392 | 39
664 | Ministry of Railways | Railways | Gudha-Thatha Mithri Construction of Railway Track Project | North Western Railway [NWR] | 705752 | Rajasthan | 04/2019 | 11/2026 | 11/2026 | 819.48 | 967.06 | 471 | 98
665 | Ministry of Railways | Railways | Sawai Madhopur-Jaipur Railway Line Project | North Western Railway [NWR] | 705912 | Rajasthan | 04/2023 | 03/2027 |  | 1203.89 | 1203.89 | 35.05 | 9
666 | Ministry of Railways | Railways | Agra Fort-Bandikui Doubling Line Project | CAO/C/NCR | 705919 | Rajasthan | 02/2021 | 06/2027 | 06/2027 | 1390 | 1390 | 123 | 25
667 | Ministry of Railways | Railways | Sawaimadhopur Bye Pass Line Project | North Western Railway [NWR] | 706866 | Rajasthan | 01/2023 | 03/2026 | 05/2027 | 304 | 304 | 134 | 35
668 | Ministry of Railways | Railways | Ph II extension of MRTS from Velachery to St Thomas Mount | Southern Railways [SR] - construction | 400280 | Tamil Nadu | 11/2008 | 07/2024 | 08/2025 | 734 | 982 | 475.73 | 99
669 | Ministry of Railways | Railways | Redevelopment of Chennai Egmore Station | WR | 613002 | Tamil Nadu | 10/2022 | 03/2026 |  | 842 | 842 | 340 | 0
670 | Ministry of Railways | Railways | Coach Production Factory Upgradation Project | CPM/ICF | 705244 | Tamil Nadu | 07/2018 | 12/2021 |  | 520 | 520 | 192.25 | 0
671 | Ministry of Railways | Railways | Morappur - Dharmpuri New Railway Line Project | Southern Railway [SR] - I | 705755 | Tamil Nadu | 12/2016 | 03/2028 | 03/2028 | 359 | 359 | 40 | 1
672 | Ministry of Railways | Railways | Doubling between Bhadrachalam Road and Dornakal | South Central Railway [SCR] - II | 616856 | Telangana | 04/2025 | 04/2029 |  | 770.12 | 770.12 | 0 | 0
673 | Ministry of Railways | Railways | Manoharabad-Kothapalli New Rail Line [151 km] | South Central Railway [SCR] - II | 705437 | Telangana | 01/2017 | 03/2027 | 12/2027 | 1160 | 2781 | 1713.38 | 71
674 | Ministry of Railways | Railways | Bahraich-Shravasti-Balrampur-Siddharthnagar -Santkabir nagar | North Eastern Railway [NER] | 400204 | Uttar Pradesh | 03/2017 | 10/2030 | 10/2030 | 4939.78 | 4939.78 | 1217.13 | 8
675 | Ministry of Railways | Railways | Sahjanwa-Dohrighat | North Eastern Railway [NER] | 400205 | Uttar Pradesh | 03/2017 | 03/2029 | 03/2029 | 1319.75 | 1319.75 | 457.35 | 3
676 | Ministry of Railways | Railways | Anandnagar - Ghugli via Maharajganj 50 km | Construction NER | 617252 | Uttar Pradesh | 11/2023 | 03/2028 |  | 958.27 | 958.27 | 432.01 | 23
677 | Ministry of Railways | Railways | Chunar-Chopan doubling project | North Central Railway | 617284 | Uttar Pradesh | 01/2025 | 03/2028 |  | 1423.96 | 1423.96 | 26 | 2
678 | Ministry of Railways | Railways | Domingarh-Gorakhpur-Gorakhpur Cantt.-Kusumhi - 3rd Railway Line Project | North Eastern Railway [NER] | 705566 | Uttar Pradesh | 06/2018 | 02/2025 | 09/2025 | 351 | 521.47 | 494 | 98
679 | Ministry of Railways | Railways | Burhwal Gonda 3rd line | North Eastern Railway [NER] | 705567 | Uttar Pradesh | 07/2019 | 03/2025 | 09/2025 | 1016 | 1118 | 1113.75 | 70
680 | Ministry of Railways | Railways | Janghai-Pratapgarh- Amethi | CAO/C/II/NR | 705588 | Uttar Pradesh | 03/2017 | 03/2025 | 03/2026 | 722 | 1194 | 1100 | 70
681 | Ministry of Railways | Railways | Lalitpur-Birari with flyover at Lalitpur- 16 Km | North Central Railway | 705766 | Uttar Pradesh | 03/2017 | 12/2024 | 11/2025 | 304.44 | 356 | 214 | 65
682 | Ministry of Railways | Railways | Mughalsarai-Allahabad, 3rd line | North Central Railway | 705772 | Uttar Pradesh | 03/2016 | 12/2026 | 03/2027 | 2649 | 2649 | 1399 | 62
683 | Ministry of Railways | Railways | Aligarh -Daud Khan Flyover Construction & 3rd Railway Line Project | CAO/C/NCR | 705774 | Uttar Pradesh | 09/2020 | 01/2025 | 03/2027 | 758 | 779.49 | 315.37 | 55
684 | Ministry of Railways | Railways | Bhandai Flyover Construction Project | CAO/C/NCR | 705777 | Uttar Pradesh | 04/2021 | 02/2026 | 02/2027 | 250.18 | 250.18 | 118 | 15
685 | Ministry of Railways | Railways | Phephna-Indara, Mau-Shahganj doubling excluding Indara-Mau | South Eastern Railway [SER] - I | 705779 | Uttar Pradesh | 03/2017 | 12/2024 | 03/2026 | 1178 | 1777 | 1489.5 | 85
686 | Ministry of Railways | Railways | Bhatni-Aurnihar with electrification excluding Indara-Mau | RVNL - II | 705780 | Uttar Pradesh | 03/2017 | 12/2024 | 10/2025 | 2529 | 2529.46 | 2051.69 | 94
687 | Ministry of Railways | Railways | Barabanki-Malhaur 3rd & 4th Railway Line Project | CAO/C/NR | 705782 | Uttar Pradesh | 04/2017 | 03/2025 | 03/2026 | 407 | 407 | 317 | 75
688 | Ministry of Railways | Railways | Janghai-Phaphamau Doubling Rail Line Project | RVNL | 705784 | Uttar Pradesh | 03/2020 | 03/2025 | 03/2025 | 357 | 978.77 | 579 | 95
689 | Ministry of Railways | Railways | Bahraich - Nanpara - Nepalganj Road Gauge Conversion | North Eastern Railway [NER] | 705863 | Uttar Pradesh | 04/2021 | 07/2025 | 08/2025 | 950 | 950 | 507.02 | 86
690 | Ministry of Railways | Railways | Allahabad division - Aligarh - Harduaganj Flyover | North Central Railway | 705918 | Uttar Pradesh | 02/2021 | 06/2026 | 03/2027 | 1457 | 1457 | 50 | 8
691 | Ministry of Railways | Railways | Rishikesh-Karnaprayag New Rail Line- 125 km | RVNL - II | 705429 | Uttarakhand | 08/2018 | 12/2025 | 03/2027 | 38953 | 38953 | 24645.15 | 65
692 | Ministry of Railways | Railways | Kalinarayanpur-Krishnanagar Doubling Alongwith Krishnanagar - Chapra New Line And Naihati-Ranaghat 3rd Line. | Eastern Railway [ER] - I | 400247 | West Bengal | 11/2005 | 02/2027 | 02/2027 | 1000 | 1000 | 1029.97 | 67
693 | Ministry of Railways | Railways | Tarakeshwar-Bishnupur New Line [82.47 km] | Eastern Railway [ER] - I | 400273 | West Bengal | 02/2008 | 03/2019 | 02/2026 | 1189 | 1542 | 1287.05 | 90
694 | Ministry of Railways | Railways | Dum Dum Airport-New Garia via Rajarhat-Construction of Metro Railway | RVNL - II | 400277 | West Bengal | 10/2011 | 12/2025 | 03/2026 | 8964 | 8964 | 8097.47 | 80
695 | Ministry of Railways | Railways | Construction of Balurghat-Hilli new BG Line | Northeast Frontier Railway [NFR] | 612096 | West Bengal | 12/2010 | 03/2027 | 03/2025 | 1209 | 1209 | 405.31 | 9
696 | Ministry of Railways | Railways | Kalipahari Bakhtarnagar 5th line | Eastern Railway [ER] - I | 617322 | West Bengal | 07/2025 | 06/2027 | 06/2027 | 350.46 | 350.46 | 0 | 0
697 | Ministry of Railways | Railways | Joka-BBD Bag new metro project | RVNL - II | 705730 | West Bengal | 04/2010 | 12/2026 | 12/2028 | 4835 | 10362 | 4361.23 | 59
698 | Ministry of Railways | Railways | Noapara-Barasat via Bimanbandar - Construction of Metro railway [18 km] | Metro Railway, Kolkata | 706776 | West Bengal | 03/2010 | 08/2026 | 03/2029 | 4830 | 4830 | 2764.13 | 32
699 | Ministry of Railways | Real Estate | Bangalore-Whitefield-Bangalore City-Krishnarajapuram [23.08 km] - Quadrupling | South Western Railway [SWR] - II | 705663 | Karnataka | 06/2022 | 02/2026 | 02/2026 | 493 | 493 | 252.45 | 82
700 | Ministry of Railways | Urban Public Transport | Baranagar-Barrackpore and Dakshineshwar- Construction of Metro Railway | RVNL - II | 706777 | West Bengal | 03/2010 | 12/2026 | 12/2025 | 2298 | 2734 | 393 | 17
701 | Ministry of Steel | Metals & Mining | Capacity expansion of Deposit-14 and 14 NMZ at Kirandul | National Mineral Development Corporation Limited [NMDC] | 615202 | Chhattisgarh | 07/2022 | 12/2028 | 03/2028 | 1700 | 1756.2 | 65.44 | 2
702 | Ministry of Steel | Steel | Replacement of Hot Leveller No.1 of Plate Mill at Bhilai Steel Plant | Steel Authority of India Limited [SAIL] | 617243 | Chhattisgarh | 08/2024 | 07/2026 |  | 198.62 | 198.62 | 10.53 | 8
703 | Ministry of Steel | Steel | Replacement of Converter Vessels, Trunnion Rings, Support System & Installation of Secondary Emission at Bhilai Steel Plant | Steel Authority of India Limited [SAIL] | 617255 | Chhattisgarh | 12/2023 | 06/2026 |  | 471.83 | 471.83 | 111.75 | 35
704 | Ministry of Steel | Steel | Rebuilding of Coke Oven Battery No.7 & 8 at Bhilai Steel Plant | Steel Authority of India Limited [SAIL] | 617256 | Chhattisgarh | 01/2024 | 10/2025 |  | 884.1 | 884.1 | 453.2 | 75
705 | Ministry of Steel | Steel | NMDC Slurry Pipeline Project Phase-1 | National Mineral Development Corporation Limited [NMDC] | 706811 | Chhattisgarh | 09/2020 | 06/2023 | 12/2025 | 2907 | 5427 | 3012.02 | 84
706 | Ministry of Steel | Steel | SCREENING PLANT-III AT KIRANDUL | National Mineral Development Corporation Limited [NMDC] | 709826 | Chhattisgarh | 10/2021 | 01/2026 |  | 2718.84 | 2718.84 | 1327.11 | 72
707 | Ministry of Steel | Steel | CONSTRUCTION OF RESIDENTIAL TOWERS AT BIOM KIRANDUL COMPLEX | National Mineral Development Corporation Limited [NMDC] | 709827 | Chhattisgarh | 10/2022 | 12/2025 |  | 349.75 | 349.75 | 247.42 | 85
708 | Ministry of Steel | Steel | New Sinter Plant at BSL, SAIL | Steel Authority of India Limited [SAIL] | 400174 | Jharkhand | 05/2015 | 10/2017 | 06/2027 | 1034.01 | 1752.3 | 883.23 | 51
709 | Ministry of Steel | Steel | Replacement of existing Grinders in CRM-I & II at Bokaro Steel Plant | Steel Authority of India Limited [SAIL] | 617249 | Jharkhand | 02/2025 | 01/2027 |  | 211.94 | 211.94 | 7.52 | 6
710 | Ministry of Steel | Steel | Secondary Emission Control in Converters of SMS-II at Bokaro Steel Plant | Steel Authority of India Limited [SAIL] | 617250 | Jharkhand | 02/2025 | 10/2026 |  | 207.13 | 207.13 | 7.91 | 6
711 | Ministry of Steel | Steel | Revamping of old sub-systems of Blast Furnace 3 at Bokaro Steel Plant | Steel Authority of India Limited [SAIL] | 617253 | Jharkhand | 10/2023 | 07/2025 | 11/2025 | 513.82 | 513.82 | 220.42 | 69
712 | Ministry of Steel | Steel | Replacement of remaining 04 sets of Battery Cyclones with 04 Nos. of ESPs in Sinter Plant-1 at Bokaro Steel Plant | Steel Authority of India Limited [SAIL] | 617254 | Jharkhand | 04/2024 | 06/2026 |  | 260.37 | 260.37 | 44.22 | 22
713 | Ministry of Steel | Steel | Rebuilding of Coke Oven Battery No.6 at Bokaro Steel Plant | Steel Authority of India Limited [SAIL] | 617257 | Jharkhand | 12/2023 | 11/2026 |  | 627.31 | 627.31 | 88.21 | 37
714 | Ministry of Steel | Steel | Construction of Screening Plant-II for Donimalai and Kumaraswamy Iron Ore Mining Complex of NMDC Limited at Ballari Dt, Karnataka. | National Mineral Development Corporation Limited [NMDC] | 400121 | Karnataka | 06/2024 | 08/2026 |  | 1043.63 | 1043.63 | 214.48 | 25
715 | Ministry of Steel | Steel | Installation of 4th Slab Caster along with its Auxiliaries and a New Ladle Furnace in SMS-II at Rourkela Steel Plant | Steel Authority of India Limited [SAIL] | 400065 | Odisha | 02/2022 | 05/2025 | 07/2025 | 1105.23 | 1105.23 | 736.47 | 96
716 | Ministry of Steel | Steel | Rebuilding of COB 4 at Durgapur Steel Plant | Steel Authority of India Limited [SAIL] | 612781 | West Bengal | 12/2023 | 12/2026 |  | 916.78 | 916.78 | 118.63 | 12
717 | Ministry of Steel | Steel | Installation of New Bar Mill at Durgapur Steel Plant | Steel Authority of India Limited [SAIL] | 617242 | West Bengal | 10/2024 | 06/2027 |  | 2115.44 | 2115.44 | 206.67 | 24
718 | Ministry of Steel | Steel | Up-gradation of Blast Furnace No. 3 at Durgapur Steel Plant | Steel Authority of India Limited [SAIL] | 617246 | West Bengal | 10/2024 | 06/2026 |  | 758.09 | 758.09 | 53.31 | 3
719 | Ministry of Steel | Steel | Third Ladle Furnace in Secondary Refinery Unit at IISCO Steel Plant | Steel Authority of India Limited [SAIL] | 617248 | West Bengal | 12/2024 | 07/2026 |  | 227.96 | 227.96 | 16.24 | 29
720 | Ministry of Steel | Steel | Revamping of Air Pollution Control Systems of SP-1 at Durgapur Steel Plant | Steel Authority of India Limited [SAIL] | 617251 | West Bengal | 12/2024 | 05/2026 |  | 196.4 | 196.4 | 0.19 | 2
721 | Ministry of Steel | Real Estate | Krishnapatnam Node - Phase 1 - Roads and Services Development | National Industrial Corridor Development Corporation | 701658 | Andhra Pradesh | 02/2024 | 02/2028 |  | 2139.44 | 2139.44 | 327.99 | 14
722 | Ministry of Steel | Real Estate | Tumakuru Node - Phase 1 - Roads and Services Development | National Highways & Infrastructure Development Corporation Ltd. [NHIDCL] | 701657 | Karnataka | 02/2023 | 09/2026 |  | 1701.81 | 1701.81 | 95 | 8
723 | Ministry of Steel | Tourism, Hospitality & Wellness | Exhibition cum Convention Centre Dwarka [Phase I] | India International Convention & Expo Centre | 400429 | Delhi | 12/2017 | 10/2019 | 01/2025 | 5178 | 5401 | 4470 | 97.4
724 | Department of Telecommunications | Telecommunication | SETTING UP OF PHYSICAL INFRASTRUCTURE FOR THE NATIONAL INSTITUTE OF COMMUNICATION FINANCE [NICF] AT GHITORNI (National Communication Academy - Finance (Erstwhile NICF)) |  | 709859 | Delhi | 04/2018 | 02/2020 | 10/2025 | 248.2 | 248.2 | 236.91 | 98
725 | Department of Telecommunications | Telecommunication | Provision of 4G based Mobile Services in Uncovered Villages and National Highways of Meghalaya | Department of Telecommunications [DoT] | 701598 | Meghalaya | 09/2020 | 03/2022 | 03/2025 | 971.96 | 971.96 | 208.25 | 98
726 | Department of Telecommunications | Telecommunication | Mobile connectivity in Left Wing Extremism [LWE] affected areas-Phase2 | Department of Telecommunications [DoT] | 701599 | Multi-States (Andhra Pradesh, Bihar, Chhattisgarh, Jharkhand, Madhya Pradesh, Maharashtra, Odisha, Telangana, Uttar Pradesh, West Bengal) | 09/2021 | 03/2023 | 11/2025 | 1577.57 | 1577.57 | 596.17 | 87
727 | Department of Telecommunications | Telecommunication | Provision of 4G based mobile services in 7,287 uncovered villages of 44 Aspirational District across 5 states of Andhra Pradesh, Chhattisgarh, Jharkhand, Maharashtra & Odisha | Department of Telecommunications [DoT] | 701602 | Multi-States (Andhra Pradesh, Chhattisgarh, Jharkhand, Maharashtra, Odisha) | 05/2022 | 11/2023 | 11/2025 | 3685 | 3685 | 1101.39 | 79
728 | Department of Telecommunications | Telecommunication | Provision of 4G Mobile Services in Uncovered Villages of Arunachal Pradesh and 2 Districts of Assam | Department of Telecommunications [DoT] | 701597 | Multi-States (Arunachal Pradesh, Assam) | 10/2021 | 04/2023 | 09/2025 | 1255.49 | 1255.49 | 284.04 | 89
729 | Department of Telecommunications | Telecommunication | 354 Uncovered Villages Scheme | Department of Telecommunications [DoT] | 701600 | Multi-States (Bihar, Gujarat, Himachal Pradesh, Jammu and Kashmir, Ladakh, Rajasthan, Uttar Pradesh) | 04/2020 | 10/2021 | 08/2025 | 336.89 | 301.13 | 225.71 | 97
730 | Department of Telecommunications | Telecommunication | 502 Aspirational District Scheme in Four states - Bihar, Madhya Pradesh, Rajastha and Uttar Pradesh | Department of Telecommunications [DoT] | 704495 | Multi-States (Bihar, Madhya Pradesh, Rajasthan, Uttar Pradesh) | 03/2021 | 03/2022 | 12/2025 | 421.65 | 228.94 | 126.45 | 96
731 | Department of Telecommunications | Telecommunication | PHASE-I OF CONSOLIDATION OF EXISTING CDR DATA CENTERS AND NIB-P3 DATA CENTERS WITH STATE OF THE ART | BSNL | 709749 | Multi-States (Maharashtra, Telangana) | 03/2020 | 06/2021 | 12/2025 | 461.42 | 461.42 | 166.02 | 81
732 | Department of Telecommunications | Telecommunication | Saturation 4G mobile coverage of Uncovered Villages through USOF | Department of Telecommunications [DoT] | 400013 | PAN India | 07/2022 | 06/2024 | 03/2026 | 26316 | 30620 | 9291.8 | 72
733 | Department of Telecommunications | Telecommunication | 4G Services by BSNL | Department of Telecommunications [DoT] | 701593 | PAN India | 11/2020 | 03/2024 | 03/2026 | 28466 | 19592 | 8332.52 | 92
734 | Department of Telecommunications | Telecommunication | BharatNet | Department of Telecommunications [DoT] | 706775 | PAN India | 10/2011 | 08/2023 | 03/2027 | 61109 | 188000 | 41486.14 | 80.52
735 | Department of Telecommunications | Telecommunication | SUPER EDGE ROUTERS FOR BSNL INTERNET PROTOCOL - MULTI PROTOCOL LEBEL SWITCHING [IPMPLS] NETWORK | BSNL | 709855 | PAN India | 03/2023 | 03/2024 | 03/2025 | 239.6 | 239.6 | 179.63 | 100
736 | Department of Telecommunications | Telecommunication | MPLS-IP BASED ACCESS AND AGGREGATION NETWORK [MAAN] IN BSNL ALONG WITH TEST AND MEASURING EQUIPMENT | BSNL | 709856 | PAN India | 05/2023 | 08/2024 | 08/2025 | 645.13 | 645.13 | 522.88 | 90
737 | Department of Telecommunications | Telecommunication | Planning, Engineering, Supply, Installation, Testing, Commissioning, Integration & Annual Maintenance of 4G mobile network at 1 Lakh sites on PAN India basis including Mumbai & Delhi LSA on turnkey basis under Phase IX.2 Project. | BSNL | 709857 | PAN India | 06/2023 | 06/2025 | 03/2026 | 24544.55 | 24544.5 | 8333.37 | 96
738 | Department of Telecommunications | Telecommunication | OPTICAL TRANSPORT NETWORK [OTN] PH-4 IN BSNL | BSNL | 709858 | PAN India | 02/2024 | 08/2025 |  | 810.99 | 810.99 | 741.9 | 100
739 | Department of Water Resources, River Development & GR | Waste & Water | Interception and Diversion and STP works in Bhagalpur under Hybrid annuity based PPP mode-Namami Gange Programme | National Mission for Clean Ganga | 616600 | Bihar | 03/2022 | 02/2025 | 12/2025 | 413.29 | 413.29 | 126.67 | 0
740 | Department of Water Resources, River Development & GR | Waste & Water | Sewage Treatment Plant 100MLD and Sewerage Network 288 km in Digha-Patna under Hybrid annuity based PPP mode-Namami Gange Programme | National Mission for Clean Ganga | 616611 | Bihar | 07/2019 | 12/2025 |  | 824 | 824 | 385.32 | 55
741 | Department of Water Resources, River Development & GR | Waste & Water | Sewage Treatment Plant 50MLD and Sewerage Network 150 km in Kankarbagh- Patna under Hybrid annuity based PPP mode-Namami Gange Programme | National Mission for Clean Ganga | 616612 | Bihar | 07/2019 | 12/2025 |  | 578.89 | 578.89 | 165.84 | 53
742 | Department of Water Resources, River Development & GR | Waste & Water | Sewer Network, SPS and STP at Begusarai | National Mission for Clean Ganga | 616615 | Bihar | 03/2018 | 04/2025 | 12/2025 | 230.06 | 230.06 | 261.48 | 97
743 | Department of Water Resources, River Development & GR | Waste & Water | Sewer Networks, SPS and STP at Hajipur | National Mission for Clean Ganga | 616616 | Bihar | 03/2018 | 06/2025 | 12/2025 | 305.19 | 305.19 | 346.44 | 95
744 | Department of Water Resources, River Development & GR | Waste & Water | Interception & Diversion with Rehabilitation of sewerage scheme at Agra under Hybrid annuity based PPP model-Namami Gange Programme | National Mission for Clean Ganga | 616594 | Uttar Pradesh | 04/2023 | 04/2025 | 12/2025 | 842.25 | 842.25 | 208.64 | 69
745 | Department of Water Resources, River Development & GR | Waste & Water | Pollution Abatement Works for River Kali Meerut under Meerut Municipality Interception & Diversion with STP | National Mission for Clean Ganga | 616605 | Uttar Pradesh | 11/2024 | 12/2024 | 05/2027 | 690.71 | 690.71 | 0 | 27
746 | Department of Water Resources, River Development & GR | Waste & Water | Pollution Abatement works for River Ganga at Hooghly Chinsurah- Municipal Town Interception & Diversion with STP | National Mission for Clean Ganga | 616604 | West Bengal | 12/2021 | 03/2025 | 12/2025 | 154.73 | 154.73 | 96.17 | 92
747 | Department of Water Resources, River Development & GR | Water Resources | Sardar Gouthu Latchanna Thotapalli Barrage Project | Water Resources-AP | 400100 | Andhra Pradesh | 01/2006 | 12/2019 | 03/2025 | 353.05 | 1023.24 | 869.11 | 95
748 | Department of Water Resources, River Development & GR | Water Resources | Gundlakamma project | Water Resources-AP | 400101 | Andhra Pradesh | 04/2005 | 12/2019 | 03/2027 | 397.41 | 697.39 | 610.89 | 98
749 | Department of Water Resources, River Development & GR | Water Resources | Polavaram Irrigation Project | Water Resources-AP | 701415 | Andhra Pradesh | 11/2004 | 04/2022 | 03/2026 | 10151.04 | 55548.9 | 24347.76 | 83
750 | Department of Water Resources, River Development & GR | Water Resources | Borolia Irrigation Project | Department of Water Resources, River Development & GR | 701370 | Assam | 12/1996 | 12/2022 | 03/2025 | 256.16 | 256.16 | 0 | 0
751 | Department of Water Resources, River Development & GR | Water Resources | Punpun Barrage Project | Water Resources-BR | 400104 | Bihar | 04/2007 | 12/2019 | 03/2026 | 571.07 | 658.12 | 469.66 | 44
752 | Department of Water Resources, River Development & GR | Water Resources | Durgawati Reservoir Project | Irrigation and CAD-TG | 701371 | Bihar | 04/1997 | 12/2019 | 12/2024 | 691.15 | 971.96 | 978.51 | 87
753 | Department of Water Resources, River Development & GR | Water Resources | Kelo Irrigation Project | Water Resources-CT | 400111 | Chhattisgarh | 04/2008 | 12/2019 | 06/2025 | 459.97 | 727.04 | 616.93 | 71
754 | Department of Water Resources, River Development & GR | Water Resources | Kudali Irrigation Project | Department of Water Resources, River Development & GR | 701399 | Chhattisgarh | 12/2009 | 12/2022 |  | 382.29 | 382.29 | 0 | 81.8
755 | Department of Water Resources, River Development & GR | Water Resources | Sardar Sarovar CADWM Project | Narmada and Water Resources, Water Supply and Kalpsar Department-GJ | 400097 | Gujarat | 04/2004 | 12/2019 | 03/2025 | 5021.76 | 6670.31 | 4954.99 | 90.3
756 | Department of Water Resources, River Development & GR | Water Resources | Sardar Sarovar Project | Narmada and Water Resources, Water Supply and Kalpsar Department-GJ | 701372 | Gujarat | 04/1996 | 12/2019 | 03/2025 | 20718.17 | 33412.5 | 31767.59 | 93
757 | Department of Water Resources, River Development & GR | Water Resources | Subernarekha Multipurpose Project, Jharkhand | Department of Water Resources-JH | 701376 | Jharkhand | 01/2012 | 12/2019 | 04/2025 | 3807.77 | 9579.58 | 5550.74 | 69
758 | Department of Water Resources, River Development & GR | Water Resources | Upper Tunga Irrigation Project | Water Resources-KA | 701377 | Karnataka | 04/2014 | 12/2019 | 03/2025 | 770.16 | 1606.07 | 1511.22 | 99
759 | Department of Water Resources, River Development & GR | Water Resources | Omkareshwar CADWM Project | Water resource-mp | 400096 | Madhya Pradesh | 04/2015 | 12/2019 | 03/2026 | 648.09 | 648.09 | 172.56 | 3
760 | Department of Water Resources, River Development & GR | Water Resources | Bargi Diversion Project Phase - IV [km. 154 to km 197] | Water Resources-MP | 400115 | Madhya Pradesh | 01/2009 | 12/2019 | 07/2025 | 751.03 | 893.35 | 777.99 | 74
761 | Department of Water Resources, River Development & GR | Water Resources | Bargi Diversion Project Phase - III [km. 104 to km 154] | Water Resources-MP | 400116 | Madhya Pradesh | 04/2007 | 12/2019 | 07/2025 | 1229.15 | 1399.7 | 1807.2 | 79
762 | Department of Water Resources, River Development & GR | Water Resources | Gosikhurd CADWM Project | Department of water resources-MH - II | 400095 | Maharashtra | 04/2017 | 12/2019 | 06/2026 | 743.73 | 743.73 | 252 | 50
763 | Department of Water Resources, River Development & GR | Water Resources | Urmodi Irrigation Project | Department of water resources-MH - II | 400105 | Maharashtra | 04/2018 | 06/2022 | 06/2025 | 580.79 | 895.81 | 713.46 | 76.22
764 | Department of Water Resources, River Development & GR | Water Resources | Sulwade-Jamphal-Kanoli Lift Irrigation Scheme | Department of water resources-MH - II | 400107 | Maharashtra | 02/2019 | 06/2023 | 06/2027 | 2407.67 | 2407.67 | 2436.43 | 80
765 | Department of Water Resources, River Development & GR | Water Resources | Purna Barrage-2 [Ner Dhamana] Medium Irrigation Project | Department of water resources-MH - II | 400109 | Maharashtra | 04/2018 | 06/2020 | 06/2025 | 848.07 | 888.43 | 690.49 | 69
766 | Department of Water Resources, River Development & GR | Water Resources | Jigaon Irrigation Project | Department of water resources-MH - II | 400112 | Maharashtra | 04/2018 | 06/2028 |  | 7222.95 | 7222.95 | 8501.45 | 90
767 | Department of Water Resources, River Development & GR | Water Resources | Waghur Project | Department of water resources-MH - II | 701383 | Maharashtra | 04/1996 | 12/2019 | 03/2026 | 1058.99 | 1758.51 | 1530.36 | 89
768 | Department of Water Resources, River Development & GR | Water Resources | Tillari Irrigation Project | Department of water resources-MH - II | 701384 | Maharashtra | 01/2006 | 12/2019 | 01/2025 | 368.34 | 649.6 | 724.36 | 99
769 | Department of Water Resources, River Development & GR | Water Resources | Gosikhurd Project | Department of water resources-MH - II | 701386 | Maharashtra | 04/2008 | 12/2019 | 06/2026 | 7196.47 | 12770.1 | 13533.29 | 72
770 | Department of Water Resources, River Development & GR | Water Resources | Bembla Irrigation Project | Department of water resources-MH - II | 701388 | Maharashtra | 04/2007 | 12/2019 | 06/2025 | 1352.53 | 2685.41 | 2689.7 | 98
771 | Department of Water Resources, River Development & GR | Water Resources | Arjuna Medium Irrigation project | Department of water resources-MH - II | 701390 | Maharashtra | 01/2008 | 12/2019 | 12/2024 | 333.87 | 611 | 803.89 | 100
772 | Department of Water Resources, River Development & GR | Water Resources | Aruna Medium Irrigation Project | Department of water resources-MH - II | 701391 | Maharashtra | 01/2010 | 12/2019 | 01/2025 | 210.45 | 1472.14 | 1697.94 | 97
773 | Department of Water Resources, River Development & GR | Water Resources | Krishna Koyana Lift Irrigation Project | Department of water resources-MH - II | 701392 | Maharashtra | 04/2009 | 12/2019 | 12/2023 | 973.62 | 2774.9 | 1069.82 | 90
774 | Department of Water Resources, River Development & GR | Water Resources | Lower Pedhi Project | Department of water resources-MH - II | 701396 | Maharashtra | 04/2008 | 12/2019 | 06/2026 | 255.97 | 1480.7 | 1324.78 | 64
775 | Department of Water Resources, River Development & GR | Water Resources | Nardave Medium Irrigation Project | Department of water resources-MH - II | 701398 | Maharashtra | 04/2009 | 12/2019 | 03/2025 | 211.46 | 781.85 | 623.5 | 72.59
776 | Department of Water Resources, River Development & GR | Water Resources | Thoubal Multipurpose Project | Water Resources Department-MN | 701400 | Manipur | 04/1997 | 12/2019 | 03/2026 | 1449.44 | 1822.24 | 1837.91 | 98
777 | Department of Water Resources, River Development & GR | Water Resources | North Koel Reservoir Project | Department of Water Resources, River Development & GR | 701412 | Multi-States (Bihar, Jharkhand) | 01/2021 | 03/2021 | 03/2026 | 1622.27 | 2430.76 | 142.1 | 32
778 | Department of Water Resources, River Development & GR | Water Resources | Integrated Anandpur Barrage Project | Water Resources-OR | 603945 | Odisha | 01/1998 | 12/2019 | 06/2025 | 567.03 | 2990.05 | 2629.74 | 62
779 | Department of Water Resources, River Development & GR | Water Resources | Kanupur Irrigation Project | Irrigation and CAD-TG | 701404 | Odisha | 01/2004 | 12/2019 | 12/2024 | 989.43 | 2301.28 | 2563.56 | 79
780 | Department of Water Resources, River Development & GR | Water Resources | Relining of Rajasthan feeder and Sirhind Feeder canal | Department of Water Resources-PB | 701410 | Punjab | 04/2018 | 06/2021 | 06/2025 | 1441.26 | 2462.16 | 2962.99 | 80
781 | Department of Water Resources, River Development & GR | Water Resources | Shahpur Kandi Dam Project | Department of Water Resources-PB | 701411 | Punjab | 04/2018 | 06/2022 | 10/2025 | 2285.81 | 2715.7 | 2072.33 | 80
782 | Department of Water Resources, River Development & GR | Water Resources | J. ChokhaRao LIS CADWM Project | Irrigation and CAD-TG | 400094 | Telangana | 04/2016 | 12/2019 | 03/2023 | 759.94 | 13445.4 | 0 | 0
783 | Department of Water Resources, River Development & GR | Water Resources | Sri Ram Sagar Project Stage - II | Irrigation and CAD-TG | 400102 | Telangana | 04/2005 | 12/2019 | 12/2024 | 736.13 | 949.87 | 940.7 | 96
784 | Department of Water Resources, River Development & GR | Water Resources | Indiramma Flood Flow Canal Project | Irrigation and CAD-TG | 400103 | Telangana | 01/2006 | 12/2019 | 03/2025 | 1331.3 | 5940.09 | 4491.08 | 92
785 | Department of Water Resources, River Development & GR | Water Resources | J. Chokka Rao Devadula Lift Irrigation Scheme | Irrigation and CAD-TG | 701405 | Telangana | 04/2006 | 12/2019 | 12/2025 | 8200.71 | 14730 | 4558.89 | 87
786 | Department of Water Resources, River Development & GR | Water Resources | Rajiv Bhima Lift Irrigation Scheme | Irrigation and CAD-TG | 701406 | Telangana | 01/2008 | 12/2019 | 03/2026 | 1402 | 2509.66 | 1839.76 | 100
787 | Department of Water Resources, River Development & GR | Water Resources | Saryu Nahar CADWM Project | Irrigation & Water Resources-UP | 400093 | Uttar Pradesh | 04/2017 | 12/2019 | 03/2026 | 1672.7 | 1672.7 | 0 | 0
788 | Department of Water Resources, River Development & GR | Water Resources | Arjun Sahayak Project | Irrigation & Water Resources-UP | 400117 | Uttar Pradesh | 04/2009 | 12/2019 | 12/2019 | 741.38 | 2465.68 | 3218.3 | 100
789 | Department of Water Resources, River Development & GR | Water Resources | Morna [Gureghar] Irrigation Project | Department of Water Resources, River Development & GR | 701395 | Uttar Pradesh | 12/2007 | 06/2023 |  | 219.9 | 219.9 | 0 | 0
790 | Department of Water Resources, River Development & GR | Water Resources | Madhya Ganga canal Phase-II | Irrigation & Water Resources-UP | 701408 | Uttar Pradesh | 07/2007 | 12/2019 | 12/2024 | 1060.67 | 4417.21 | 4415.24 | 82
791 | Department of Water Resources, River Development & GR | Water Resources | Jamrani Dam Multipurpose Project | Irrigation-UK | 613787 | Uttarakhand | 04/2023 | 06/2029 |  | 2584.1 | 2584.1 | 486.52 | 16

## June_Table1_Sector_wise
Sector | Project Count | Original Cost (Rs. Crore) | Revised Cost (Rs. Crore) | Anticipated Cost (Rs. Crore) | Cumulative Expenditure (Rs. Crore)
CIVIL AVIATION | 38 | 26,718.18 | 27,878.25 | 30,487.46 | 18,038.38
COAL | 116 | 187,533.87 | 192,077.91 | 196,907.16 | 67,974.52
DEPARTMENT OF HIGHER EDUCATION | 20 | 9,680.92 | 10,072.78 | 10,271.25 | 7,214.67
DPIIT | 2 | 24,857.00 | 31,457.00 | 32,085.00 | 16,231.95
FINANCE | 2 | 577.27 | 577.27 | 569.04 | 399.67
HEALTH AND FAMILY WELFARE | 7 | 7,150.98 | 7,459.11 | 7,194.19 | 4,974.49
HOME AFFAIRS | 3 | 1,663.54 | 2,539.11 | 2,539.11 | 2,209.10
MINES | 8 | 7,559.78 | 9,356.73 | 9,845.57 | 6,076.89
PETROLEUM | 102 | 415,375.80 | 466,585.36 | 476,738.57 | 2,47,728.10
POWER | 105 | 376,149.61 | 399,127.37 | 454,133.11 | 2,30,429.15
RAILWAYS | 203 | 580,517.44 | 570,567.02 | 600,296.37 | 4,05,391.57
ROAD TRANSPORT AND HIGHWAYS | 923 | 730,133.91 | 757,547.67 | 768,280.94 | 3,87,153.65
SHIPPING AND PORTS | 1 | 5,369.18 | 5,061.15 | 5,061.15 | 3,472.54
STEEL | 20 | 16,297.20 | 20,228.73 | 20,228.73 | 8,030.85
TELECOMMUNICATIONS | 6 | 26,961.69 | 26,949.89 | 26,949.89 | 9,777.17
URBAN DEVELOPMENT | 24 | 253,593.42 | 258,103.77 | 271,961.41 | 1,88,202.04
WATER RESOURCES | 15 | 15,428.28 | 15,429.03 | 61,880.31 | 27,445.38

## June_Table2_State_wise
State | Project Count | Original Cost (Rs. Crore) | Revised Cost (Rs. Crore) | Anticipated Cost (Rs. Crore) | Cumulative Expenditure (Rs. Crore)
ANDAMAN AND NICOBAR ISLANDS | 9 | 2,555.02 | 2,628.18 | 2,609.04 | 1,570.91
ANDHRA PRADESH | 100 | 137,562.41 | 138,061.74 | 185,913.61 | 1,03,214.40
ARUNACHAL PRADESH | 14 | 45,061.06 | 45,210.96 | 64,937.64 | 30,494.52
ASSAM | 68 | 72,160.68 | 72,644.55 | 80,115.95 | 51,124.39
BIHAR | 90 | 128,697.89 | 141,442.84 | 153,894.78 | 98,886.26
CHHATTISGARH | 50 | 75,244.87 | 79,134.30 | 79,609.36 | 36,041.06
DELHI | 21 | 90,609.18 | 96,063.03 | 94,869.54 | 76,898.76
GOA | 3 | 1,201.05 | 1,201.05 | 1,287.55 | 485.92
GUJARAT | 89 | 166,904.62 | 172,995.69 | 173,705.16 | 87,806.46
HARYANA | 24 | 60,500.88 | 69,284.79 | 69,434.48 | 35,685.89
HIMACHAL PRADESH | 27 | 33,945.98 | 34,975.66 | 33,959.82 | 18,520.60
JAMMU AND KASHMIR | 53 | 73,422.59 | 74,733.70 | 81,014.68 | 37,490.59
JHARKHAND | 64 | 113,658.99 | 117,419.60 | 116,571.41 | 67,421.35
KARNATAKA | 79 | 103,071.74 | 104,231.19 | 103,281.26 | 49,083.86
KERALA | 29 | 62,476.65 | 67,557.87 | 68,138.39 | 34,596.89
LADAKH | 6 | 2,474.97 | 2,634.64 | 2,634.64 | 1,349.63
MADHYA PRADESH | 53 | 111,280.15 | 110,681.55 | 117,479.56 | 40,730.40
MAHARASHTRA | 157 | 218,215.39 | 219,727.02 | 244,735.03 | 1,25,686.25
MANIPUR | 31 | 25,573.90 | 23,525.17 | 33,485.71 | 19,617.15
MEGHALAYA | 14 | 6,669.20 | 6,671.16 | 6,679.40 | 3,297.68
MIZORAM | 16 | 14,026.44 | 12,520.44 | 18,053.36 | 15,684.86
MULTI STATE | 49 | 331,697.08 | 337,250.07 | 350,472.22 | 2,53,221.50
NAGALAND | 23 | 13,242.51 | 14,429.85 | 14,128.82 | 7,970.58
ODISHA | 76 | 141,702.20 | 143,692.35 | 146,380.41 | 66,140.85
PUNJAB | 37 | 37,339.85 | 37,800.41 | 38,239.81 | 15,087.38
RAJASTHAN | 59 | 133,461.98 | 163,301.66 | 162,895.85 | 91,952.19
SIKKIM | 18 | 20,007.02 | 24,489.69 | 25,331.78 | 18,325.74
TAMIL NADU | 58 | 86,711.11 | 92,401.36 | 97,359.99 | 23,782.67
TELANGANA | 52 | 29,124.48 | 29,461.83 | 31,449.35 | 15,398.11
TRIPURA | 14 | 7,910.17 | 7,947.06 | 8,032.54 | 1,403.56
UTTAR PRADESH | 126 | 206,693.32 | 215,027.99 | 219,300.59 | 1,08,471.35
UTTARAKHAND | 30 | 58,506.75 | 63,252.30 | 63,200.39 | 45,102.40
WEST BENGAL | 56 | 73,857.94 | 78,618.45 | 86,227.14 | 48,205.96

## June_Table3_Completed
Sector | Project Name | Agency | Project Code | State | Original Cost (Rs. Crore) | Date of Commissioning - Original (MM/YYYY) | Cumulative Expenditure (Rs. Crore)
PETROLEUM | CITY GAS DISTRIBUTION IN WEST BENGAL | HPCL | N16000392 | WEST BENGAL | 5,830.20 | 03/2031 | 875.27
PETROLEUM | CGD PROJECT AT NAWADA AND KODERMA DISTRICTS | IOCL | N16000426 | MULTI STATE | 169.00 | 12/2029 | 71.00
PETROLEUM | CGD PROJECT IN TONK, SAWAI MADHOPUR, DAUSA, KARAULI | HPCL | N16000496 | RAJASTHAN | 1,751.00 | 03/2030 | 301.39
POWER | BHENSARA 320 MW | NTPC | N18000293 | RAJASTHAN | 1,221.73 | 07/2022 | 1,139.42
POWER | 150 MW SOLAR PV PROJECT IN GUJARAT (LIMBDI, MESANKA AND RADHANPUR) | NTPC | N18000296 | GUJARAT | 674.92 | 09/2022 | 572.53
POWER | SAMBHU KI BHURJ-II SOLAR 300MW | NTPC | N18000286 | RAJASTHAN | 1,782.00 | 09/2021 | 1,369.88
RAILWAYS | KARAIKAL PERALAM(23KM)-NEW LINE PROJECT | SR | N22000625 | TAMIL NADU | 304.22 | 03/2026 | 292.65
RAILWAYS | REHABILITATION AND UPGRADATION OF BHOKARDAN TO KUMBHARI FATA DESIGN CH. (KM 13+500 TO 17+00) AND RAJ | MoRTH | N24001887 | MAHARASHTRA | 291.37 | 06/2024 | 157.59
RAILWAYS | UP-GRADATION OF TIRORA-GONDIA, STATE HIGHWAY FROM EXISTING KM 163+213 (ON SH-335, TIRORA) TO KM 191+ | MoRTH | N24001888 | MAHARASHTRA | 288.14 | 04/2023 | 72.78
RAILWAYS | 2 LANE + PS PIMPLNER TO SATANA -[DESIGN CHAINAGE KM 21.427 TO 64.00 ] OF NH-752G] | MoRTH | N24001889 | MAHARASHTRA | 277.81 | 07/2021 | 155.01
RAILWAYS | 2 LANE + PS ASTHAMODE - TIVATYAL [DESIGN CH. KM 24.300 - 62.00] [KM 134.98-172.95 OF NH-63] | MoRTH | N24001894 | MAHARASHTRA | 228.82 | 07/2021 | 145.50
RAILWAYS | REHABILATION AND UPGRADATION TO TWO LANES WITH PAVED SHOULDER CONFIGURATION FROM WATUR TO CHARTHANA | MoRTH | N24001895 | MAHARASHTRA | 228.01 | 09/2023 | 106.11
RAILWAYS | CONSTRUCTION OF MAJOR BRIDGE ACROSS MANJRA RIVER NEAR YESGI VILLAGE @ KM, 166/500 ON NH 63 TQ BILOLI | MoRTH | N24001905 | MAHARASHTRA | 188.69 | 08/2023 | 111.25
RAILWAYS | STRENGTHING AND WIDINING OF EXISTING CARRIAGEWAY TO 10 M IN KM, 156/160 TO 229/160 (TEMBHURNI - KUSL | MoRTH | N24001909 | MAHARASHTRA | 157.72 | 06/2024 | 80.37
RAILWAYS | KEIFANG - TUVAI PKG-1 | NHIDCL | N24001440 | MIZORAM | 492.94 | 05/2023 | 365.86
RAILWAYS | BALANCE WORK 2-LANE WITH PAVED SHOULDERS OF NAGAPATTINAM - THANJAVUR SECTION OF NH-67 (NEW NH-83) | NHAI | N24001600 | TAMIL NADU | 434.12 | 05/2023 | 268.92
RAILWAYS | 4-LANING OF ODDANCHATRAM - MADATHUKULAM SECTION OF NH-209 (NEW NH-83) | NHAI | N24001603 | TAMIL NADU | 1,518.53 | 10/2022 | 915.40
RAILWAYS | STRENGTHENING OF 6-LANE PIMPALGAON-NASHIK- GONDE (KM. 380 - KM. 440) SECTION OF NH-3 IN MAHARASHTRA U | NHAI | N24002137 | MAHARASHTRA | 175.00 | 03/2025 | 201.00
RAILWAYS | CONSTUCTION/UPGRADATION OF EXISTING HIGHWAY TO 2 LANE WITH PAVED SHOULDER FROM KM 26.10 TO KM 40.00 | NHIDCL | N24001254 | SIKKIM | 242.97 | 06/2022 | 246.91
RAILWAYS | 2-LANING OF CHANGTONGYA TO LONGLENG ROAD OF NH-702 (PKG-I) | NHIDCL | N24001286 | NAGALAND | 278.95 | 06/2022 | 166.29
RAILWAYS | RANIKOR-MAHESHKHOLA- BAGHMARA (RMB) PKG-4 (KANAI-RONGARA) | NHIDCL | N24001339 | MEGHALAYA | 157.86 | 04/2022 | 152.95
RAILWAYS | REHABILITATION AND UPGRADATION OF NH-219 FROM KM 58-600 TO KM 140-750 IN THE STATE OF ANDHRA PRADES | MoRTH | N24000301 | ANDHRA PRADESH | 271.45 | 10/2015 | 240.23
RAILWAYS | REHABILITATION AND UPGRADATION OF END OF AHMEDNAGAR BYPASS TO KHARWANDI KASAR SECTION OF NH-222 FROM | MoRTH | N24000332 | MAHARASHTRA | 225.81 | N.A. | 118.84
RAILWAYS | 4-LANNING OF WARANGA-MAHAGAON SECTION(KM 253.7000 TO 320.580) | NHAI | N24000659 | MAHARASHTRA | 1,059.73 | 03/2017 | 928.19
RAILWAYS | 4-LANNING OF THALSERRY -MAHE BYPASS | NHAI | N24000704 | KERALA | 1,124.11 | 05/2020 | 1,527.28
RAILWAYS | CONSTRUCTION AND UPGRADATION OF EXISTING ROAD TO 2 LANE WITH PAVED SHOULDER FROM KM 368.00 TO KM 399 | NHIDCL | N24000741 | UTTARAKHAND | 274.31 | 11/2020 | 253.61
RAILWAYS | CONSTRUCTION OF 2-LANE WITH PAVED SHOULDER INCLUDING GEOMETRIC IMPROVEMENT FROM KM 16.000 TO KM 32.5 | NHIDCL | N24000768 | SIKKIM | 290.05 | 10/2020 | 218.36
RAILWAYS | AKOLA TO AKOT | MoRTH | N24001003 | MAHARASHTRA | 313.95 | 06/2019 | 270.02
RAILWAYS | AJANTHA TO BULDHANA | MoRTH | N24001008 | ANDAMAN AND NICOBAR ISLANDS | 401.00 | 07/2019 | 246.39
RAILWAYS | BHANDARA TO GHOTITOK | MoRTH | N24001018 | MAHARASHTRA | 392.83 | 06/2019 | 264.35
RAILWAYS | AMDI TO SAONER | MoRTH | N24001021 | MAHARASHTRA | 396.91 | 06/2019 | 253.59
RAILWAYS | RALEGAON TO RAMTIRTH | MoRTH | N24001046 | MAHARASHTRA | 210.81 | 07/2019 | 132.00
RAILWAYS | PUNE TO MALE VILLAGE | MoRTH | N24001078 | MAHARASHTRA | 228.31 | 12/2019 | 113.29
RAILWAYS | ARDHAPUR TO HIMAYATNAGAR | MoRTH | N24001079 | MAHARASHTRA | 426.06 | 06/2020 | 268.96
RAILWAYS | MALE VILLAGE TO PUNE RAIGARH DISTRICT BORDER | MoRTH | N24001080 | MAHARASHTRA | 256.15 | 12/2019 | 115.53
RAILWAYS | KOLDE TO KHETIYA | MoRTH | N24001090 | MAHARASHTRA | 509.18 | 07/2019 | 246.83
RAILWAYS | KURUDWADI TO PANDHARPUR | MoRTH | N24001101 | MAHARASHTRA | 307.63 | 07/2019 | 208.22
RAILWAYS | PANDHARPUR TO SANGOLA | MoRTH | N24001102 | MAHARASHTRA | 218.38 | 07/2019 | 176.99
RAILWAYS | PARLI PIMPLA DAHIGUDA | MoRTH | N24001138 | MAHARASHTRA | 205.72 | 06/2019 | 813.50
SOCIAL JUSTICE | CENTRE FOR DISABILITY SPORTS | CPWD | N38000001 | MADHYA PRADESH | 170.99 | 03/2024 | 162.63
URBAN DEVELOPMENT | KOCHI METRO RAIL PROJECT PHASE IB SECTION FROM S N JUNCTION TO THRIPUNITHURA | KMRCL | N28000159 | KERALA | 355.70 | 09/2023 | 448.39
URBAN DEVELOPMENT | PUNE METRO RAIL PROJECT (PHASE 1) | MMRC | N28000121 | MAHARASHTRA | 11,420.00 | 11/2021 | 13,088.19

## June_Table4_Added
Sector | Project Name | Agency | Project Code | State | Date of Approval (MM/YYYY) | Original Cost (Rs. Crore) | Revised Cost (Rs. Crore) | Anticipated Cost (Rs. Crore) | DoC - Original (MM/YYYY) | DoC - Revised (MM/YYYY) | DoC - Anticipated (MM/YYYY)
COAL | WAGHODA UG | WCL | N06000293 | MAHARASHTRA | 1-2025 | 379.30 | N.A. | 379.30 | 3/2030 | N.A. | 3/2030
COAL | KOLARPIMPRI EXPANSION OCM (2.50 MTY) | WCL | N06000294 | MAHARASHTRA | 2-2025 | 630.37 | N.A. | 630.37 | 3/2030 | N.A. | 3/2030
COAL | JARANGDIH OCP | CCL | N06000295 | JHARKHAND | 2-2020 | 414.37 | N.A. | 414.37 | 3/2029 | N.A. | 3/2029
RAILWAYS | MURARAI - BARHARWA 3RD LINE (48.90 KM) | ER | N22000632 | WEST BENGAL | 5-2025 | 935.19 | N.A. | 935.19 | 5/2028 | N.A. | 5/2028
ROAD TRANSPORT AND HIGHWAYS | CONSTRUCTION OF BASTI RING ROAD (PHASE-I) WITH 4L CONFIGURATION FOR BASTI CITY IN THE STATE OF UTTAR | MoRTH | N24002245 | UTTAR PRADESH | 12-2022 | 1,138.72 | N.A. | 1,138.72 | 6/2027 | N.A. | 6/2027

## June_Table5_Frozen_Deleted
Sector | Project Name | Agency | Project Code | State | Original Cost (Rs. Crore) | Date of Commissioning - Original (MM/YYYY) | Cumulative Expenditure (Rs. Crore) | Physical Progress (%)
ROAD TRANSPORT AND HIGHWAYS | FOUR LANING OF DIMAPUR KOHIMA ROAD FROM DESIGN KM 123.840 TO KM 138.775 (EXISTING KM 124.100 TO KM 1 | NHIDCL | N24000686 | NAGALAND | 373.07 | 09/2019 | 382.50 | 99.81
ROAD TRANSPORT AND HIGHWAYS | 2-LANING OF CHURACHANDPUR TUIVAI SECTION OF NH- 102B (PKG- 4A) | NHIDCL | N24001272 | MANIPUR | 167.95 | 06/2022 | 88.05 | 69.89
ROAD TRANSPORT AND HIGHWAYS | 2-LANING OF CHURACHANDPUR TUIVAI SECTION OF NH- 102B (PKG- 4B) | NHIDCL | N24001273 | MANIPUR | 177.76 | 08/2022 | 89.67 | 80.53
ROAD TRANSPORT AND HIGHWAYS | BALANCE WORK FOR REHABILITATION AND UP- GRADATION OF SIDHI-SINGRAULI FROM KM 82.400 TO KM 187.993 SEC | MoRTH | N24001966 | MADHYA PRADESH | 529.44 | 04/2023 | 378.40 | 0
URBAN DEVELOPMENT | CONSTRUCTION OF PERMANENT CAMPUS OF CENTRAL UNIVERSITY OF HIMACHAL PRADESH AT DEHRA AND JADRANGAL (D | CPWD | N28000154 | HIMACHAL PRADESH | 512.34 | 11/2024 | - | 0

## June_Table6_NE_Region
Sl.No | State | Sector | Project Name | Agency | Project Code | Date of Approval (MM/YYYY) | DoC - Original (MM/YYYY) | DoC - Revised (MM/YYYY) | DoC - Anticipated (MM/YYYY) | Original Cost (Rs. Crore) | Revised Cost (Rs. Crore) | Anticipated Cost (Rs. Crore) | Cumulative Expenditure (Rs. Crore) | Physical Progress (%)
1 | ARUNACHAL PRADESH | CIVIL AVIATION | CONSTRUCTION OF NEW GREEN FIELD AIRPORT AT HOLLONGI ITANAGAR ARUNACHAL PRADESH | AAI | N04000092 | 2-2019 | 8/2022 | Jul-2025 | 7/2025 | 645.63 | 732.00 | 732.00 | 694.26 | 99.89
2 | ARUNACHAL PRADESH | POWER | SUBANSIRI LOWER H.E.P (8X250 MW) (NHPC) | NHPC | 180100221 | 9-2003 | 9/2010 | N.A. | 5/2026 | 6,285.33 | N.A. | 26,075.54 | 24,484.77 | 96.6
3 | ARUNACHAL PRADESH | POWER | DIBANG MULTIPURPOSE PROJECT 2880 MW ARUNACHAL PRADESH | NHPC | N18000362 | 2-2023 | 2/2032 | N.A. | 2/2032 | 31,876.39 | N.A. | 31,876.39 | 3,380.24 | 15.81
4 | ARUNACHAL PRADESH | ROAD TRANSPORT | HUNLI TO HAYULIANG PKG-1 | NHIDCL | N24002222 | 2-2024 | 2/2028 | N.A. | 2/2028 | 1,262.43 | N.A. | 1,262.43 | 12.12 | 2.76
5 | ARUNACHAL PRADESH | ROAD TRANSPORT | HUNLI TO ITHUN BRIDGE SECTION | NHIDCL | N24002223 | 2-2024 | 1/2027 | N.A. | 1/2027 | 275.50 | N.A. | 275.50 | 7.61 | 7.88
6 | ARUNACHAL PRADESH | ROAD TRANSPORT | PANGO TO JORGING ROAD PKG-1 | NHIDCL | N24002224 | 1-2024 | 7/2027 | N.A. | 7/2027 | 898.19 | N.A. | 898.19 | 16.01 | 4.25
7 | ARUNACHAL PRADESH | ROAD TRANSPORT | TWO LANING OF JORAM KOLORIANG ROAD (NH 713) ON EPC BASIS FROM DESIGN KM. 138+000 TO KM. 154+036 [EX | NHIDCL | N24000683 | 2-2017 | 11/2023 | Mar-2024 | 12/2024 | 180.57 | 244.10 | 180.57 | 160.46 | 96.62
8 | ARUNACHAL PRADESH | ROAD TRANSPORT | CONSTRUCTION OF 2-LANE ROAD WITH PAVED SHOULDERS FROM KM16.00 OF ROING-HUNLI SECTION TO KM 21.500 OF | NHIDCL | N24000946 | 3-2017 | 3/2022 | Jun-2025 | 12/2025 | 1,718.59 | 1,718.59 | 1,718.59 | 742.36 | 73.84
9 | ARUNACHAL PRADESH | ROAD TRANSPORT | TWO-LANING OF HAYULIANG? HAWAI BYPASS ROAD ON EPC BASIS FROM DESIGN KM. 51.825 TO KM. 63.131 EXISTI | NHIDCL | N24000979 | 1-2017 | 5/2023 | May-2023 | 3/2025 | 256.66 | N.A. | 256.66 | 0.00 | 63.59
10 | ARUNACHAL PRADESH | ROAD TRANSPORT | CONSTRUCTION OF 2-LANING WITH HARD SHOULDERS OF ARROWA-KHUPA- HAYULIANG SECTION OF NH-113 FROM CH.68. | NHIDCL | N24001244 | 8-2020 | 4/2022 | Apr-2025 | 4/2025 | 301.06 | N.A. | 301.06 | 205.71 | 100
11 | ARUNACHAL PRADESH | ROAD TRANSPORT | CONSTRUCTION OF 2 LANE ROAD OF POTIN TO PANGIN SECTION OF NH 13 FROM KM 163.59 TO KM 206.66 (PACKAGE | MoRTH | N24001297 | 3-2019 | 3/2027 | N.A. | 3/2027 | 450.65 | N.A. | 450.65 | 398.18 | 95.84
12 | ARUNACHAL PRADESH | ROAD TRANSPORT | 4 LANING OF ITANAGAR TO BANDARDEWA SECTION OF NH-415 FROM KM 40+430 TO KM 51+735 (PACKAGE B) ON EPC | MoRTH | N24001375 | 6-2020 | 3/2027 | N.A. | 3/2027 | 496.47 | N.A. | 496.47 | 194.62 | 44.56
13 | ARUNACHAL PRADESH | ROAD TRANSPORT | JORAM ? KOLORIANG ROAD FROM EXISTING KM 50.050 TO KM 70.00 (PKG-3) | NHIDCL | N24001390 | 8-2020 | 4/2022 | Aug-2024 | 9/2024 | 228.71 | N.A. | 228.71 | 98.86 | 99.52
14 | ARUNACHAL PRADESH | ROAD TRANSPORT | JORAM ? KOLORIANG ROAD FROM EXISTING KM122.600 TO KM138.00 (PKG-7) | NHIDCL | N24001393 | 8-2020 | 4/2022 | Feb-2024 | 7/2025 | 184.88 | N.A. | 184.88 | 99.32 | 97.42
15 | ASSAM | CIVIL AVIATION | CONSTRUCTION OF NEW INTEGRATED TERMINAL BUILDING AT LGBI AIRPORT GUWAHATI | AAI | N04000083 | 12-2016 | 3/2021 | Sep-2025 | 9/2025 | 1,142.00 | N.A. | 2,333.00 | 1,948.45 | 89.66
16 | ASSAM | COAL | TIKAK EXTENSION OCP - 0.2 MTY | CIL | N06000290 | 7-2022 | 11/2030 | N.A. | 11/2030 | 159.77 | N.A. | 159.77 | 81.45 | 0
17 | ASSAM | COAL | TIRAP OCP | CIL | N06000291 | 11-2022 | 11/2027 | N.A. | 11/2027 | 289.46 | N.A. | 289.46 | 105.59 | 0
18 | ASSAM | HEALTH AND FAMILY WELFARE | ALL INDIA INSTITUTE OF MEDICAL SCIENCE AT GUWAHATI, ASSAM | HITES | N21000027 | 5-2017 | 5/2021 | Apr-2023 | 6/2025 | 875.00 | 873.92 | 860.00 | 796.74 | 99.62
19 | ASSAM | HEALTH AND FAMILY WELFARE | POWER RECOVERY TURBINE IN PFCCU | NRL | N16000510 | 3-2023 | 7/2025 | N.A. | 7/2025 | 293.50 | N.A. | 293.50 | 97.22 | 92
20 | ASSAM | HEALTH AND FAMILY WELFARE | DCU REVAMP PROJECT | NRL | N16000511 | 8-2021 | 3/2025 | N.A. | 10/2025 | 370.00 | N.A. | 370.00 | 255.51 | 55
21 | ASSAM | HEALTH AND FAMILY WELFARE | PIPELINE NETWORK PROJECT RUDRASAGAR | ONGC | N16000528 | 1-2023 | 4/2026 | N.A. | 4/2026 | 344.99 | N.A. | 344.99 | 208.56 | 46.3
22 | ASSAM | HEALTH AND FAMILY WELFARE | BORHOLLA GGS LIFE EXTENSION PROJECT | ONGC | N16000532 | 9-2023 | 5/2026 | N.A. | 5/2026 | 198.70 | N.A. | 198.70 | 99.52 | 27.3
23 | ASSAM | HEALTH AND FAMILY WELFARE | DEVELOPMENT OF SURFACE FACILITIES FOR PRODUCTION AND EVACUATION OF CRUDE OIL AND NATURAL GAS FROM NA | OIL | N16000331 | 1-2018 | 2/2020 | Jun-2025 | 12/2025 | 543.91 | 726.93 | 726.93 | 491.56 | 93.98
24 | ASSAM | HEALTH AND FAMILY WELFARE | NUMALIGARH REFINERY EXPANSION PROJECT 6 MMTPA REFINARY | NRL | N16000379 | 1-2019 | 10/2024 | N.A. | 12/2025 | 12,366.00 | N.A. | 18,968.00 | 16,357.82 | 74.92
25 | ASSAM | HEALTH AND FAMILY WELFARE | NUMALIGARH REFINERY EXPANSION PROJECT COIT AND PIPELINES | NRL | N16000394 | 1-2019 | 10/2024 | N.A. | 9/2025 | 10,228.00 | N.A. | 9,058.00 | 9,579.31 | 85.1
26 | ASSAM | HEALTH AND FAMILY WELFARE | EXPANSION OF GUWAHATI REFINERY FROM 1 TO 1.2 MMTPA ALONG WITH INSTALLATION OF CATALYTIC REFORMING UN | IOCL | N16000414 | 5-2021 | 10/2023 | May-2026 | 5/2026 | 412.00 | 595.20 | 595.20 | 396.15 | 83.4
27 | ASSAM | HEALTH AND FAMILY WELFARE | REVAMPING OF FACILITIES AT EXISTING GUWAHATI TERMINAL, ASSAM | IOCL | N16000441 | 3-2022 | 7/2026 | Sep-2026 | 9/2026 | 277.00 | N.A. | 277.00 | 181.63 | 67.67
28 | ASSAM | HEALTH AND FAMILY WELFARE | UPGRADATION OF FACILITIES OF NUMALIGARH-SILIGURI PRODUCT PIPELINE (NSPL) FOR TRANSPORTATION OF ADDIT | OIL | N16000449 | 6-2021 | 12/2024 | Jul-2025 | 10/2025 | 860.00 | N.A. | 860.00 | 535.46 | 97.5
29 | ASSAM | HEALTH AND FAMILY WELFARE | PROJECT TO CONSTRUCT A FIELD GAS GATHERING STATION AT BAGHJAN AREA FOR COLLECTION,PROCESSING | OIL | N16000450 | 12-2020 | 7/2024 | Jun-2025 | 12/2025 | 430.76 | N.A. | 430.76 | 320.71 | 83.94
30 | ASSAM | HEALTH AND FAMILY WELFARE | CAPACITY EXPANSION OF DIGBOI REFINERY FROM 0.65 TO 1.0 MMTPA | IOCL | N16000457 | 6-2022 | 10/2025 | N.A. | 3/2026 | 768.00 | N.A. | 768.00 | 101.15 | 34.6
31 | ASSAM | HEALTH AND FAMILY WELFARE | CONSTRUCTION OF LPG FACILITIES AT KAMARDANGA, ASSAM | HPCL | N16000484 | 3-2023 | 7/2027 | Jul-2027 | 7/2027 | 156.36 | 156.36 | 156.36 | 44.33 | 35.4
32 | ASSAM | HEALTH AND FAMILY WELFARE | SETTING UP OF NEW RAIL FED POL FACILITY AT KAMARDANGA, ASSAM | HPCL | N16000494 | 3-2023 | 7/2027 | Jul-2027 | 7/2027 | 384.04 | N.A. | 384.04 | 97.54 | 44
33 | ASSAM | RAILWAYS | BONGAIGAON-GOALPARA-GUWAHATI (176 KM) | NFR | N22000388 | 4-2015 | 3/2026 | N.A. | 3/2027 | 4,059.65 | N.A. | 4,962.40 | 3,668.09 | 92.31
34 | ASSAM | ROAD TRANSPORT | DABOKA KATHKATI PACKAGE-5 | NHIDCL | N24001366 | 3-2021 | 1/2023 | N.A. | 11/2024 | 288.85 | N.A. | 288.85 | 247.78 | 100
35 | ASSAM | ROAD TRANSPORT | TULUNGIA-JOGIGHOPA-PAIKAN ROAD PKG- 7 | NHIDCL | N24001368 | 3-2021 | 1/2024 | N.A. | 10/2025 | 286.72 | N.A. | 286.72 | 159.30 | 82.9
36 | ASSAM | ROAD TRANSPORT | CONSTRUCTION OF 2-LANE MAJOR BRIDGE INCLUDING APPROACHESOVER BRAHMAPUTRA BETWEEN MAJULI ON NORTH BAN | MoRTH | N24001408 | 2-2021 | 7/2025 | N.A. | 7/2025 | 925.47 | 1,019.17 | 925.47 | 192.50 | 30.65
37 | ASSAM | ROAD TRANSPORT | 4-L DHUBRI PHULBARI BRIDGE WITH APPROACH ROAD | NHIDCL | N24001326 | 11-2020 | 9/2028 | N.A. | 9/2028 | 4,997.04 | N.A. | 4,997.04 | 2,464.49 | 62.82
38 | ASSAM | ROAD TRANSPORT | 2-LANING FROM YAINGANGPOKPI TO FINCH CORNER (PKG-I) | NHIDCL | N24001331 | 3-2020 | 6/2022 | May-2025 | 12/2025 | 261.13 | N.A. | 261.13 | 70.08 | 57.5
39 | ASSAM | ROAD TRANSPORT | 2-LANING FROM YAINGANGPOKPI TO FINCH CORNER (PKG-II) | NHIDCL | N24001332 | 3-2020 | 6/2022 | Apr-2025 | 12/2025 | 217.50 | N.A. | 217.50 | 89.21 | 68.03
40 | ASSAM | ROAD TRANSPORT | 2-LANING OF CHURACHANDPUR TUIVAI SECTION OF NH-102B (PKG- IB) | NHIDCL | N24001269 | 3-2020 | 3/2022 | Jun-2025 | 8/2025 | 216.49 | 241.52 | 216.49 | 114.38 | 87.02
41 | ASSAM | ROAD TRANSPORT | 4-LANING OF HAPACHARA - TULUNGIA SECTION | NHIDCL | N24001246 | 3-2020 | 12/2022 | N.A. | 6/2024 | 220.20 | N.A. | 220.20 | 217.31 | 97.76
42 | ASSAM | ROAD TRANSPORT | 4 LANING OF JORHAT TO JHANJI SECTION FROM KM. 453.00 TO KM. 491.08 (DESIGN KM 403.200 TO KM 454.240) | NHIDCL | N24000319 | 6-2015 | 8/2023 | N.A. | 7/2025 | 437.39 | N.A. | 437.39 | 586.89 | 97.43
43 | ASSAM | ROAD TRANSPORT | FOUR LANING OF JHANJHI JN TO DEMOW SECTION FROM KM. 491.050 TO KM. 535.250(DESIGN KM 490.800 TO KM 5 | NHIDCL | N24000320 | 6-2015 | 3/2024 | N.A. | 10/2025 | 463.49 | N.A. | 463.49 | 517.62 | 78.19
44 | ASSAM | ROAD TRANSPORT | 4 LANING FROM JAMUGURI TO BISWANATH CHARIALI FROM KM 182 TO KM 208 OF NH- 52 | NHIDCL | N24000431 | 1-1991 | 6/2019 | Jun-2019 | 7/2025 | 520.01 | N.A. | 520.01 | 306.13 | 98.42
45 | ASSAM | ROAD TRANSPORT | 4 LANING FROM RANGAGARA TO KALIABHOR TINALI FROM KM 297.00 TO KM 315.315 OF NH-37 ON EPC BASIS. | NHIDCL | N24000438 | 12-2015 | 12/2018 | Jul-2021 | 12/2025 | 289.99 | N.A. | 289.99 | 233.23 | 88.03
46 | ASSAM | ROAD TRANSPORT | 4 LANING OF NH-37 SECTION BETWEEN DEMOW TO END OF MORAN BYPASS (FROM KM. 534.800 TO KM. 561.700) O | NHIDCL | N24000582 | 1-2016 | 1/2016 | N.A. | 7/2025 | 294.17 | N.A. | 294.17 | 396.49 | 98.4
47 | ASSAM | ROAD TRANSPORT | 4 LANING OF NH 37 SECTION BETWEEN END OF MORAN BYPASS TO BOGIBEEL JUNCTION NEAR LAPETKETA (KM. 561 | NHIDCL | N24000583 | 1-2016 | 12/2021 | N.A. | 7/2025 | 252.00 | N.A. | 330.30 | 242.97 | 95.42
48 | ASSAM | ROAD TRANSPORT | SILCHAR- CHURAIBARI PKG-5 | NHIDCL | N24002243 | 2-2024 | 10/2027 | N.A. | 10/2027 | 1,258.13 | N.A. | 1,258.13 | 0.00 | 0
49 | ASSAM | ROAD TRANSPORT | BILASIPURA- GUWAHATI ROAD PKG-1 | NHIDCL | N24002225 | 2-2024 | 8/2027 | N.A. | 8/2027 | 1,081.15 | N.A. | 1,081.15 | 33.93 | 2.76
50 | ASSAM | ROAD TRANSPORT | SILCHAR-JIRIBAM PKG-1 | NHIDCL | N24002226 | 1-2024 | 1/2028 | N.A. | 1/2028 | 957.95 | N.A. | 957.95 | 0.00 | 21.98
51 | ASSAM | ROAD TRANSPORT | BILASIPURA- GUWAHATI ROAD PKG-2 | NHIDCL | N24002229 | 11-2023 | 6/2027 | N.A. | 6/2027 | 1,338.61 | N.A. | 1,338.61 | 0.50 | 0
52 | ASSAM | ROAD TRANSPORT | BADARPUR ? CHURAIBARI PKG-6 | NHIDCL | N24002230 | 3-2024 | 3/2027 | N.A. | 3/2027 | 870.00 | N.A. | 870.00 | 0.00 | 5.86
53 | ASSAM | ROAD TRANSPORT | KARIMGANI - SUTARKANDI SECTION ON SILCHAR-CHURAIBARI PKG-7 | NHIDCL | N24002231 | 2-2024 | 2/2027 | N.A. | 2/2027 | 791.79 | N.A. | 791.79 | 0.00 | 1.02
54 | ASSAM | ROAD TRANSPORT | CONSTRUCTION OF 4 LANE GAURIPUR BYPASS ON NH-17 IN THE STATE OF ASSAM | MoRTH | N24002237 | 3-2024 | 10/2026 | N.A. | 10/2026 | 421.15 | N.A. | 421.15 | 0.00 | 0
55 | ASSAM | ROAD TRANSPORT | CONSTRUCTION OF 2 LANE BARPETA BYPASS FROM KM 77+900(BARADI) TO KM 86+150( DEURIKUCHI) (LENGTH=8.25K | MoRTH | N24002238 | 3-2023 | 8/2026 | N.A. | 8/2026 | 173.65 | N.A. | 173.65 | 0.00 | 0
56 | ASSAM | ROAD TRANSPORT | BILASIPURA-GUWAHATI ROAD PKG-8 | NHIDCL | N24002021 | 3-2023 | 12/2026 | N.A. | 12/2026 | 1,457.59 | N.A. | 1,457.59 | 551.88 | 47.5
57 | ASSAM | ROAD TRANSPORT | BILASIPURA-GUWAHATI ROAD PKG-9 | NHIDCL | N24002022 | 3-2023 | 6/2026 | N.A. | 6/2026 | 1,000.27 | N.A. | 1,000.27 | 308.11 | 29.01
58 | ASSAM | ROAD TRANSPORT | BILASIPURA-GUWAHATI ROAD PKG-10 | NHIDCL | N24002023 | 3-2023 | 6/2026 | N.A. | 6/2026 | 1,264.90 | N.A. | 1,264.90 | 425.17 | 27.99
59 | ASSAM | ROAD TRANSPORT | DABOKA BYPASS OF DABOKA - PAROKHAOWA PKG -1 | NHIDCL | N24002024 | 1-2023 | 11/2025 | N.A. | 11/2025 | 516.88 | N.A. | 516.88 | 242.92 | 75.51
60 | ASSAM | ROAD TRANSPORT | 2 LANE WITH PAVED SHOULDER FROM KM 16+900 (BOGAPANI) TO KM 27+150 (GOLAI GAON) ON EXISTING DIBRUGARH | NHIDCL | N24002025 | 1-2023 | 12/2025 | N.A. | 12/2026 | 356.65 | N.A. | 356.65 | 134.02 | 18.15
61 | ASSAM | ROAD TRANSPORT | DEVELOPMENT OF EXTERNAL TRUNK CONNECTIVITY AND INTERNAL INFRASTRUCTURE WORKS AT MULTI MODEL LOGISTIC | NHIDCL | N24002030 | 2-2020 | 3/2022 | N.A. | 9/2024 | 592.06 | N.A. | 592.06 | 308.87 | 100
62 | ASSAM | ROAD TRANSPORT | SILCHAR VAIRENGTE SAIRANG ROAD PKG- 1 | NHIDCL | N24002127 | 2-2023 | 7/2026 | N.A. | 7/2026 | 1,256.90 | N.A. | 1,256.90 | 539.19 | 40.36
63 | ASSAM | ROAD TRANSPORT | SILCHAR VAIRENGTE SAIRANG ROAD PKG- 2 | NHIDCL | N24002128 | 3-2023 | 8/2026 | N.A. | 8/2026 | 1,716.21 | N.A. | 1,716.21 | 989.94 | 64.56
64 | ASSAM | ROAD TRANSPORT | FOUR LANNING OF BADARPUR BYPASS FROM DESIGN CHAINAGE KM 27+300 AT CROSSING WITH NH-6 | NHIDCL | N24002129 | 2-2023 | 8/2026 | N.A. | 8/2026 | 574.26 | N.A. | 574.26 | 297.70 | 54.97
65 | ASSAM | ROAD TRANSPORT | TAMENGLONG- MAHUR ROAD PKG-7 | NHIDCL | N24002130 | 12-2023 | 3/2026 | N.A. | 3/2026 | 846.82 | N.A. | 846.82 | 407.11 | 68.95
66 | ASSAM | ROAD TRANSPORT | CONSTRUCTION OF 4-LANE PANCHGRAM BYPASS FROM DESIGN CHAINAGE KM 15+500 ON NH-37 (OLD NH-53) AT KALIN | NHIDCL | N24002154 | 3-2023 | 2/2027 | N.A. | 2/2027 | 728.97 | N.A. | 728.97 | 290.90 | 43.16
67 | ASSAM | ROAD TRANSPORT | WIDENING/IMPROVEMENT TO 4-LANE WITH PAVED SHOULDER FROM KM 55+000 (NAGABANG GAMSUK) TO KM 82+514 (OY | NHIDCL | N24002155 | 3-2023 | 3/2027 | N.A. | 3/2027 | 665.47 | N.A. | 665.47 | 213.67 | 50.88
68 | ASSAM | ROAD TRANSPORT | JOGIGHOPA BRIDGE | NHIDCL | N24001434 | 8-2021 | 11/2024 | N.A. | 12/2026 | 746.76 | N.A. | 746.76 | 344.27 | 67.85
69 | ASSAM | ROAD TRANSPORT | DABOKA KATHKATI PACKAGE-6 | NHIDCL | N24001450 | 9-2021 | 7/2024 | N.A. | 5/2025 | 625.64 | N.A. | 625.64 | 556.44 | 100
70 | ASSAM | ROAD TRANSPORT | DABOKA KATHKATI PACKAGE-7 | NHIDCL | N24001537 | 11-2021 | 7/2024 | N.A. | 7/2025 | 204.10 | N.A. | 204.10 | 143.66 | 96.8
71 | ASSAM | ROAD TRANSPORT | FOUR LANING OF SRIRAMPUR-DHUBRI PKG- 2 | NHIDCL | N24001544 | 3-2022 | 1/2025 | N.A. | 6/2025 | 909.02 | N.A. | 909.02 | 532.44 | 100
72 | ASSAM | ROAD TRANSPORT | 6L STANDALONE FLYOVERS AT RAHA, DEMOW, BORGHAT, KATHIATALI JUNCTIONS AND ROB AT JAGIROAD ON STRETCHE | NHAI | N24001545 | 8-2022 | 12/2022 | Sep-2024 | 6/2024 | 175.00 | N.A. | 175.00 | 209.02 | 100
73 | ASSAM | ROAD TRANSPORT | BALANCE WORK OF 4L OF NARIMBANGLO?JATINGA JUNCTION- HARANGAJO ROAD SECTION FROM KM 0.000 TO KM 49.23 | NHAI | N24001547 | 3-2022 | 1/2026 | N.A. | 1/2026 | 1,909.98 | N.A. | 1,909.98 | 683.00 | 78.92
74 | ASSAM | ROAD TRANSPORT | 6L STANDALONE FLYOVERS AT BONGAIGAON, CHAPAGURI, PATHSALA, SIMLAGURI CHOWK AND BAIHATA BYPASS JUNCTI | NHAI | N24001548 | 3-2022 | 6/2024 | N.A. | 5/2025 | 457.72 | N.A. | 457.72 | 366.34 | 100
75 | ASSAM | ROAD TRANSPORT | SRIRAMPUR - DHUBRI PKG-1 | NHIDCL | N24001831 | 3-2022 | 2/2025 | N.A. | 11/2026 | 613.89 | N.A. | 613.89 | 110.76 | 35.77
76 | ASSAM | ROAD TRANSPORT | DIBRUGARH-LAHOAL-CHABUA BYPASS PACKAGE-3 | NHIDCL | N24001832 | 1-2023 | 5/2025 | N.A. | 11/2025 | 458.59 | N.A. | 458.59 | 205.87 | 66.12
77 | ASSAM | ROAD TRANSPORT | CONSTRUCTION OF MANGALDOI BYPASS (NH-15) STARTING AT CH 26+400 AND TERMINATING AT CH 41+505 UNDER RA | MoRTH | N24001840 | 3-2022 | 4/2025 | N.A. | 3/2026 | 535.03 | N.A. | 535.03 | 102.23 | 34.54
78 | ASSAM | ROAD TRANSPORT | WIDENING AND UPGRADATION TO TWO LANES WITH PAVED SHOULDERS ROAD FROM TAMENGLONG TO MAHUR (NH-137) I | NHIDCL | N24001969 | 3-2023 | 8/2025 | N.A. | 8/2025 | 904.04 | N.A. | 904.04 | 409.15 | 68.26
79 | ASSAM | ROAD TRANSPORT | WIDENING AND UPGRADATION TO TWO LANES WITH PAVED SHOULDERS ROAD FROM TAMENGLONG TO MAHUR (NH-137) IN | NHIDCL | N24001970 | 3-2023 | 8/2025 | N.A. | 8/2025 | 860.37 | N.A. | 860.37 | 417.17 | 68.6
80 | ASSAM | ROAD TRANSPORT | WIDENING AND UPGRADATION TO TWO LANES WITH PAVED SHOULDERS ROAD FROM TAMENGLONG TO MAHUR (NH-137) IN | NHIDCL | N24001971 | 3-2023 | 8/2025 | N.A. | 8/2025 | 890.33 | N.A. | 890.33 | 467.83 | 65.56
81 | ASSAM | ROAD TRANSPORT | WIDENING/IMPROVEMENT TO 4-LANE WITH PAVED SHOULDER FROM KM 0+800 (KANDULIJAN GAON) TO KM 27+701 (SI | NHIDCL | N24001972 | 3-2023 | 4/2026 | N.A. | 4/2026 | 609.16 | N.A. | 609.16 | 323.24 | 98.48
82 | ASSAM | ROAD TRANSPORT | WIDENING/IMPROVEMENT TO 4-LANE WITH PAVED SHOULDER FROM KM 27+701 (SIMEN CHAPORI) TO KM 55+000 (NAG | NHIDCL | N24001973 | 3-2023 | 2/2026 | N.A. | 2/2026 | 562.05 | N.A. | 562.05 | 303.89 | 99.06
83 | MANIPUR | CIVIL AVIATION | CONSTRUCTION OF NEW INTEGRATED TERMINAL BUILDING, CONTROL TOWER CUM TECHNICAL BLOCK, APRON, LINK TAX | AAI | N04000100 | 11-2021 | 7/2024 | Dec-2025 | 12/2025 | 499.00 | N.A. | 499.00 | 154.47 | 40.82
84 | MANIPUR | RAILWAYS | JIRIBAM TO IMPHAL (TUPUI)(NL)(NEFR) | NFR | 220100288 | 4-2003 | 12/2026 | Mar-2028 | 3/2028 | 14,322.79 | 12,274.06 | 22,234.60 | 15,485.02 | 69.2
85 | MANIPUR | ROAD TRANSPORT | CONSTRUCTION OF 2-LANING WITH HARD SHOULDER ROAD OF UKHRUL - TOLOI - TADUBI SECTION OF NH-102A FROM | NHIDCL | N24001974 | 9-2021 | 1/2025 | Aug-2025 | 8/2025 | 315.56 | N.A. | 315.56 | 137.81 | 88.74
86 | MANIPUR | ROAD TRANSPORT | IMPHAL - KHONGSANG PKG-5 | NHIDCL | N24001538 | 12-2021 | 5/2024 | Jan-2026 | 3/2026 | 410.68 | N.A. | 410.68 | 152.34 | 70.11
87 | MANIPUR | ROAD TRANSPORT | IMPHAL - KHONGSANG PKG-6 | NHIDCL | N24001539 | 12-2021 | 2/2025 | Sep-2025 | 12/2025 | 504.76 | N.A. | 504.76 | 190.26 | 78.25
88 | MANIPUR | ROAD TRANSPORT | AKASH BRIDGE - JESSAMI SECTION PKG-2 | NHIDCL | N24001540 | 3-2022 | 2/2025 | Feb-2025 | 3/2025 | 152.11 | N.A. | 152.11 | 73.48 | 100
89 | MANIPUR | ROAD TRANSPORT | MARAM - PEREN PKG-3 | NHIDCL | N24001439 | 8-2021 | 5/2023 | Oct-2024 | 2/2025 | 467.41 | N.A. | 467.41 | 264.83 | 100
90 | MANIPUR | ROAD TRANSPORT | CONSTRUCTION OF 2-LANING WITH HARD SHOULDER ROAD OF UKHRUL - TOLOI - TADUBI SECTION OF NH-102A FROM | NHIDCL | N24001473 | 9-2021 | 2/2024 | Mar-2025 | 7/2025 | 310.76 | N.A. | 310.76 | 129.15 | 96.77
91 | MANIPUR | ROAD TRANSPORT | IMPHAL - KHONGSANG PKG-4 | NHIDCL | N24001453 | 8-2021 | 12/2023 | Jul-2025 | 12/2025 | 579.63 | N.A. | 579.63 | 180.72 | 72.5
92 | MANIPUR | ROAD TRANSPORT | TAMENGLONG - MAHUR PKG-5 | NHIDCL | N24001436 | 8-2021 | 5/2023 | Jan-2025 | 1/2026 | 477.86 | N.A. | 477.86 | 246.09 | 84.87
93 | MANIPUR | ROAD TRANSPORT | TAMENGLONG - MAHUR PKG-6 | NHIDCL | N24001437 | 9-2021 | 5/2023 | Nov-2024 | 12/2025 | 311.18 | N.A. | 311.18 | 190.96 | 83.78
94 | MANIPUR | ROAD TRANSPORT | UKHRUL TOLOI TADUBI PKG-2 | NHIDCL | N24002131 | 3-2023 | 2/2026 | Mar-2026 | 3/2026 | 578.98 | N.A. | 578.98 | 153.92 | 71.25
95 | MANIPUR | ROAD TRANSPORT | LMPHAL TO JIRIBAM PKG-7 | NHIDCL | N24002028 | 1-2023 | 12/2025 | Dec-2025 | 3/2026 | 760.16 | N.A. | 760.16 | 157.48 | 62.92
96 | MANIPUR | ROAD TRANSPORT | CHOITHAR TO MARREM KHULLEN SECTION IMPHAL- UKHRUL - JESSAMI PKG-5 | NHIDCL | N24002242 | 3-2023 | 3/2027 | N.A. | 3/2027 | 564.05 | N.A. | 564.05 | 0.00 | 0
97 | MANIPUR | ROAD TRANSPORT | IMPHAL-KOHIMA ROAD PKG-5A | NHIDCL | N24002232 | 9-2020 | 8/2026 | N.A. | 8/2026 | 228.97 | N.A. | 228.97 | 0.00 | 10.13
98 | MANIPUR | ROAD TRANSPORT | JESSAMI TO LAYNEN BRIDGE UKHRUL - JESSAMI PKG-7 | NHIDCL | N24002227 | 3-2023 | 6/2026 | N.A. | 6/2026 | 164.89 | N.A. | 164.89 | 3.83 | 9.78
99 | MANIPUR | ROAD TRANSPORT | MARREM KHULLEN TO JESSAMI SECTION IMPHAL- UKHRUL - JESSAMI PKG-6 (DESIGN CHAINAGE KM 95.700 TO KM 14 | NHIDCL | N24002202 | 3-2023 | 12/2026 | N.A. | 12/2026 | 554.66 | N.A. | 554.66 | 17.79 | 15
100 | MANIPUR | ROAD TRANSPORT | IMPHAL-KOHIMA ROAD PKG-4B | NHIDCL | N24002203 | 9-2020 | 6/2026 | N.A. | 6/2026 | 268.98 | N.A. | 268.98 | 13.14 | 18.04
101 | MANIPUR | ROAD TRANSPORT | IMPHAL - KHONGSANG - JIRIBAM PKG-2 | NHIDCL | N24002244 | 3-2021 | 3/2026 | N.A. | 3/2026 | 195.14 | N.A. | 195.14 | 4.42 | 11.53
102 | MANIPUR | ROAD TRANSPORT | 2-LANING OF CHURACHANDPUR TUIVAI SECTION OF NH-102B (PKG- 2A) | NHIDCL | N24001270 | 3-2020 | 6/2022 | Jun-2025 | 9/2025 | 292.24 | N.A. | 292.24 | 130.66 | 90.69
103 | MANIPUR | ROAD TRANSPORT | 2-LANING OF CHURACHANDPUR TUIVAI SECTION OF NH-102B (PKG- 2B) | NHIDCL | N24001271 | 6-2020 | 8/2022 | Jun-2025 | 10/2025 | 365.53 | N.A. | 365.53 | 156.31 | 77.69
104 | MANIPUR | ROAD TRANSPORT | IMPROVEMENT/UPGRADATION OF EXISTING 2-LANE TO 4-LANE DIVIDED HIGHWAY FROM TAPHOU KUKI TO DAILI SECTI | NHIDCL | N24001274 | 8-2020 | 4/2022 | Jun-2025 | 12/2025 | 379.39 | N.A. | 379.39 | 218.03 | 70.94
105 | MANIPUR | ROAD TRANSPORT | MARIAM - PEREN PKG-1A | NHIDCL | N24001349 | 2-2021 | 12/2022 | Mar-2025 | 12/2025 | 226.32 | N.A. | 226.32 | 105.78 | 74.48
106 | MANIPUR | ROAD TRANSPORT | MARIAM - PEREN (PKG 1B) | NHIDCL | N24001350 | 2-2021 | 12/2022 | Jan-2025 | 9/2025 | 188.36 | N.A. | 188.36 | 126.71 | 99.02
107 | MANIPUR | ROAD TRANSPORT | TAMENGLONG - MAHUR PKG-3 | NHIDCL | N24001354 | 3-2021 | 12/2022 | Sep-2024 | 11/2025 | 234.08 | N.A. | 234.08 | 139.45 | 92.82
108 | MANIPUR | ROAD TRANSPORT | SENAPATI- IMPHAL PKG-5B | NHIDCL | N24001400 | 3-2021 | 1/2023 | May-2025 | 10/2025 | 211.70 | N.A. | 211.70 | 83.79 | 71.06
109 | MANIPUR | ROAD TRANSPORT | IMPHAL - KHONGSANG PKG-3 | NHIDCL | N24001401 | 7-2021 | 3/2023 | Mar-2025 | 10/2025 | 467.00 | N.A. | 467.00 | 193.81 | 79.81
110 | MANIPUR | ROAD TRANSPORT | TAMENGLONG - MAHUR PKG-1 | NHIDCL | N24001402 | 7-2021 | 3/2023 | Jan-2025 | 1/2025 | 185.80 | N.A. | 185.80 | 117.78 | 100
111 | MANIPUR | ROAD TRANSPORT | TAMENGLONG - MAHUR PKG-2 | NHIDCL | N24001403 | 7-2021 | 3/2023 | Jan-2025 | 12/2025 | 483.87 | N.A. | 483.87 | 278.89 | 92.94
112 | MANIPUR | ROAD TRANSPORT | TAMENGLONG - MAHUR PKG-4 | NHIDCL | N24001404 | 7-2021 | 3/2023 | Feb-2025 | 3/2025 | 198.77 | N.A. | 198.77 | 127.86 | 100
113 | MANIPUR | ROAD TRANSPORT | CHURACHANPUR TUIVAI PKG-3 | NHIDCL | N24001405 | 7-2021 | 10/2023 | Mar-2025 | 12/2025 | 673.27 | N.A. | 673.27 | 382.37 | 80.28
114 | MEGHALAYA | DEPARTMENT OF HIGHER EDUCATION | CONSTRUCTION AND DEVELOPMENT OF NATINAL INSTITUTE OF TECHNOLOGY MEGHALAYA PERMANENT CAMPUS AT SOHRA | RITES OF HIGHER | N42000001 | 9-2013 | 9/2014 | Jul-2025 | 7/2025 | 484.32 | 429.70 | 494.52 | 270.55 | 84
115 | MEGHALAYA | ROAD TRANSPORT | IMPROVEMENT/WIDENING TO 2-LANE WITH PAVED SHOULDER FROM (DESIGN KM 45.760 TO KM 63.530) BETWEEN SHIL | NHIDCL | N24001334 | 11-2020 | 12/2023 | N.A. | 4/2026 | 445.51 | N.A. | 445.51 | 214.34 | 30.3
116 | MEGHALAYA | ROAD TRANSPORT | IMPROVEMENT/WIDENING TO 2-LANE WITH PAVED SHOULDER / 4-LANING FROM (DESIGN KM 63.530 TO KM 71.520) B | NHIDCL | N24001335 | 11-2020 | 12/2023 | N.A. | 11/2026 | 284.21 | N.A. | 284.21 | 107.86 | 24
117 | MEGHALAYA | ROAD TRANSPORT | IMPROVEMENT/WIDENING TO 2-L WITH PAVED SHOULDER FROM (DESIGN KM 0.00 TO KM 10.670) / 4-LANING FROM ( | NHIDCL | N24001313 | 11-2020 | 12/2023 | Oct-2025 | 10/2025 | 351.12 | N.A. | 351.12 | 299.22 | 63
118 | MEGHALAYA | ROAD TRANSPORT | IMPROVEMENT/WIDENING TO 2-LANE WITH PAVED SHOULDER FROM (DESIGN KM 10.670 TO KM 37.550) BETWEEN SHIL | NHIDCL | N24001314 | 11-2020 | 12/2023 | N.A. | 8/2026 | 525.68 | N.A. | 525.68 | 434.50 | 32
119 | MEGHALAYA | ROAD TRANSPORT | WIDENING TO 2-LANE WITH GEOMETRIC IMPROVEMENTS OF TURA DALU ROAD UNDER JICA FUNDING FROM KM 85.000 T | NHIDCL | N24000771 | 4-2017 | 9/2021 | Jun-2025 | 6/2025 | 553.51 | 610.09 | 553.51 | 438.16 | 88.07
120 | MEGHALAYA | ROAD TRANSPORT | DAINADUBI-DARUGIRI PKG-1B | NHIDCL | N24002233 | 3-2023 | 3/2027 | N.A. | 3/2027 | 705.83 | N.A. | 705.83 | 0.32 | 2.13
121 | MEGHALAYA | ROAD TRANSPORT | IMPROVEMENT AND WIDENING TWO LANNIG WITH PAVED SHOULDER OF NATIONAL HIGHWAY 127B FROM KM 31.500 (GOE | MoRTH | N24002239 | 12-2023 | 5/2027 | N.A. | 5/2027 | 504.00 | N.A. | 504.00 | 0.00 | 0
122 | MEGHALAYA | ROAD TRANSPORT | CONSTRUCTION OF 2-LANE WITH PAVED SHOULDER OF SHILLONG WESTERN BYPASS STARTING FROM NH-06 NEAR LADUM | NHIDCL | N24002156 | 3-2023 | 9/2026 | N.A. | 9/2026 | 620.30 | N.A. | 620.30 | 222.26 | 30
123 | MEGHALAYA | ROAD TRANSPORT | SHILLONG WESTERN BYPASS PACKAGE-2 | NHIDCL | N24002157 | 3-2023 | 9/2026 | N.A. | 9/2026 | 686.00 | N.A. | 686.00 | 293.36 | 25.52
124 | MEGHALAYA | ROAD TRANSPORT | CONSTRUCTION OF 2-LANE WITH PAVED SHOULDERS OF SHILLONG WESTERN BYPASS STARTING FROM NH-06 NEAR LADU | NHIDCL | N24002158 | 3-2023 | 9/2026 | N.A. | 9/2026 | 562.48 | N.A. | 562.48 | 297.91 | 25.27
125 | MEGHALAYA | ROAD TRANSPORT | REHABITITATION AND UP GRADATION OF NONGSTOIN-RAMBRAI-KYRSHAI ROAD UP TO MEGHALAYA-ASSAM BORDER FROM | NHIDCL | N24001474 | 9-2021 | 5/2024 | May-2026 | 5/2026 | 359.86 | N.A. | 359.86 | 233.26 | 60.81
126 | MEGHALAYA | ROAD TRANSPORT | REHABILITATION AND UPGRADATION OF NONGSTOIN TO WAHKAJI SECTION OF PROJECT ROAD KM 0.000 TO KM 43.06 | MoRTH | N24001441 | 8-2020 | 2/2022 | N.A. | 7/2025 | 302.88 | N.A. | 302.88 | 228.68 | 96
127 | MEGHALAYA | ROAD TRANSPORT | RANIKOR- MAHESHKHOLA- BAGHMARA PKG-2 | NHIDCL | N24001541 | 11-2021 | 6/2024 | Dec-2024 | 5/2025 | 283.50 | N.A. | 283.50 | 257.26 | 100
128 | MIZORAM | RAILWAYS | BHAIRABI SAIRONG, NL, NEFR | NFR | N22000100 | 4-2008 | 3/2025 | N.A. | 6/2025 | 6,527.45 | 5,021.45 | 8,071.30 | 8,066.76 | 97
129 | MIZORAM | ROAD TRANSPORT | UP-GRADATION TO 2-LANE WITH PAVED SHOULDERS OF NGOPA - PAWLRANG SECTION OF NH 102B OF AIZAWL - IMPHA | NHIDCL | N24001975 | 9-2021 | 2/2025 | N.A. | 12/2025 | 523.78 | N.A. | 523.78 | 379.40 | 95.31
130 | MIZORAM | ROAD TRANSPORT | KEIFANG - TUVAI PKG-3 | NHIDCL | N24002027 | 12-2021 | 2/2025 | N.A. | 12/2025 | 500.88 | N.A. | 500.88 | 279.44 | 75.4
131 | MIZORAM | ROAD TRANSPORT | ZORINPUI- HMAWNGBU-LONGMASU (NH- 502A) | NHIDCL | N24002204 | 2-2023 | 12/2026 | N.A. | 12/2026 | 781.85 | N.A. | 781.85 | 33.77 | 3
132 | MIZORAM | ROAD TRANSPORT | WIDENING AND UP-GRADATION TO 2-LANE WITH PAVED SHOULDER CONFIGURATION AND GEOMETRIC IMPROVEMENTS FRO | NHIDCL | N24000857 | 4-2017 | 4/2023 | N.A. | 4/2025 | 519.09 | N.A. | 785.65 | 670.91 | 97.51
133 | MIZORAM | ROAD TRANSPORT | WIDENING AND UP-GRADATION TO 2-LANE WITH PAVED SHOULDER CONFIGURATION AND GEOMETRIC IMPROVEMENTS FRO | NHIDCL | N24000858 | 4-2017 | 7/2023 | N.A. | 5/2024 | 640.07 | N.A. | 1,286.35 | 1,195.84 | 98.9
134 | MIZORAM | ROAD TRANSPORT | WIDENING AND UP-GRADATION TO 2-LANE WITH PAVED SHOULDER CONFIGURATION AND GEOMETRIC IMPROVEMENTS FRO | NHIDCL | N24000861 | 4-2017 | 4/2023 | N.A. | 4/2025 | 473.18 | N.A. | 688.25 | 541.04 | 95
135 | MIZORAM | ROAD TRANSPORT | WIDENING AND UP-GRADATION TO 2-LANE WITH PAVED SHOULDER CONFIGURATION AND GEOMETRIC IMPROVEMENTS FRO | NHIDCL | N24000862 | 4-2017 | 4/2023 | N.A. | 4/2025 | 537.82 | N.A. | 789.05 | 779.37 | 99.88
136 | MIZORAM | ROAD TRANSPORT | WIDENING AND UP-GRADATION TO 2-LANE WITH PAVED SHOULDER CONFIGURATION AND GEOMETRIC IMPROVEMENTS FRO | NHIDCL | N24000863 | 4-2017 | 6/2023 | N.A. | 5/2025 | 518.53 | N.A. | 906.76 | 849.68 | 97.9
137 | MIZORAM | ROAD TRANSPORT | WIDENING AND UP-GRADATION TO 2-LANE WITH PAVED SHOULDER CONFIGURATION AND GEOMETRIC IMPROVEMENTS FRO | NHIDCL | N24000864 | 4-2017 | 4/2024 | N.A. | 5/2025 | 404.29 | N.A. | 750.32 | 666.58 | 100
138 | MIZORAM | ROAD TRANSPORT | WIDENING AND UP-GRADATION TO 2-LANE WITH PAVED SHOULDER CONFIGURATION AND GEOMETRIC IMPROVEMENTS FRO | NHIDCL | N24000865 | 4-2017 | 9/2023 | N.A. | 5/2025 | 428.11 | N.A. | 746.39 | 613.69 | 99.82
139 | MIZORAM | ROAD TRANSPORT | CONSTRUCTION OF TWO LANE WITH PAVED SHOULDER OF SELLING-DULTE SECTION OF NH-06 (PKG-I) | NHIDCL | N24001278 | 3-2020 | 7/2022 | N.A. | 6/2024 | 206.88 | N.A. | 219.33 | 265.38 | 100
140 | MIZORAM | ROAD TRANSPORT | CONSTRUCTION OF TWO LANE WITH PAVED SHOULDER OF SELLING-DULTE SECTION OF NH-06 (PKG-III) | NHIDCL | N24001281 | 3-2020 | 7/2022 | N.A. | 10/2024 | 292.24 | N.A. | 331.17 | 294.78 | 94.4
141 | MIZORAM | ROAD TRANSPORT | DULTE- KWALKULH - CHAMPAI PKG.2 | NHIDCL | N24001356 | 3-2021 | 12/2022 | Apr-2024 | 4/2024 | 233.25 | N.A. | 233.25 | 172.09 | 100
142 | MIZORAM | ROAD TRANSPORT | TLABUNG - LUNGLEI PKG-A | NHIDCL | N24001358 | 3-2021 | 12/2022 | N.A. | 3/2026 | 698.44 | N.A. | 698.45 | 502.24 | 63.7
143 | MIZORAM | ROAD TRANSPORT | TLABUNG - LUNGLEI PKG-B | NHIDCL | N24001359 | 3-2021 | 1/2023 | N.A. | 3/2026 | 740.58 | N.A. | 740.58 | 373.89 | 61
144 | NAGALAND | PETROLEUM | AUGMENTATION OF DIMAPUR DEPOT, DIMAPUR | IOCL | N16000529 | 8-2023 | 11/2027 | N.A. | 11/2027 | 227.62 | N.A. | 227.62 | 6.62 | 19
145 | NAGALAND | RAILWAYS | NEW LINE FROM DIMAPUR TO ZUBZA(KOHIMA) NATIONAL PROJECT (NEFR) | NFR | N22000124 | 4-2006 | 3/2026 | N.A. | 12/2029 | 6,663.20 | 6,663.20 | 6,663.20 | 4,942.71 | 74
146 | NAGALAND | ROAD TRANSPORT | PEREN-DIMAPUR SECTION PKG-2 | NHIDCL | N24001406 | 7-2021 | 3/2023 | Sep-2025 | 9/2025 | 258.52 | N.A. | 258.52 | 89.46 | 81.4
147 | NAGALAND | ROAD TRANSPORT | 2 LANING OF KOHIMA - JESSAMI SECTION (PACKAGE II) | NHIDCL | N24001282 | 3-2020 | 6/2022 | N.A. | 1/2026 | 355.79 | N.A. | 355.79 | 119.20 | 65.06
148 | NAGALAND | ROAD TRANSPORT | 2 LANING OF KOHIMA - JESSAMI SECTION (PACKAGE V) | NHIDCL | N24001287 | 4-2020 | 12/2021 | Nov-2025 | 11/2025 | 330.80 | N.A. | 330.80 | 171.89 | 92.44
149 | NAGALAND | ROAD TRANSPORT | CONSTRUCTION OF 2-LANE WITH PAVED SHOULDER OF KOHIMA-BYPASS ROAD FROM DESIGN KM 0.00 TO KM 10.500 [D | NHIDCL | N24001288 | 8-2020 | 4/2022 | Nov-2026 | 11/2026 | 232.29 | 350.88 | 232.29 | 79.69 | 17.31
150 | NAGALAND | ROAD TRANSPORT | CONSTRUCTION OF 2-LANE WITH PAVED SHOULDER OF KOHIMA-BYPASS ROAD FROM DESIGN KM10.500 TO 21.00KM [D | NHIDCL | N24001255 | 9-2020 | 10/2022 | Sep-2024 | 6/2026 | 277.44 | N.A. | 277.44 | 169.46 | 67.91
151 | NAGALAND | ROAD TRANSPORT | CONSTRUCTION OF 2-LANE WITH PAVED SHOULDER OF KOHIMA-BYPASS ROAD FROM DESIGN KM21.0 TO KM32.0 [DESIG | NHIDCL | N24001257 | 8-2020 | 10/2022 | Jun-2025 | 12/2025 | 159.85 | 342.29 | 159.85 | 108.15 | 33.55
152 | NAGALAND | ROAD TRANSPORT | CONSTRUCTION OF 2-LANE WITH PAVED SHOULDER OF KOHIMA-BYPASS ROAD FROM DSIGN KM32.0 TO KM43.454 [DES | NHIDCL | N24001258 | 8-2020 | 4/2022 | Apr-2023 | 8/2025 | 202.36 | N.A. | 202.36 | 75.39 | 32.67
153 | NAGALAND | ROAD TRANSPORT | FOUR LANING OF EXISTING DIMAPUR KOHIMA ROAD FROM DESIGN KM 152.490 TO KM 166.700 (EXISTING KM 156.00 | NHIDCL | N24000688 | 3-2016 | 8/2022 | Sep-2025 | 9/2025 | 429.52 | 794.74 | 794.74 | 321.40 | 92.46
154 | NAGALAND | ROAD TRANSPORT | (I) CONSTRUCTION OF FOUR/SIX LANING FROM KM 132.375 TO KM 158.058 (TOTAL NEW ALIGNMENT LENGTH OF 20. | NHIDCL | N24000752 | 2-2017 | 9/2020 | Feb-2023 | 4/2025 | 387.00 | 688.12 | 688.12 | 392.01 | 100
155 | NAGALAND | ROAD TRANSPORT | (II) CONSTRUCTION OF DIMAPUR BYPASS (ASSAM PORTION) OF 4/6 LANE PAVEMENT ON EPC BASIS FROM EXISTING | NHIDCL | N24000753 | 3-2018 | 11/2022 | Aug-2024 | 4/2025 | 500.09 | 698.81 | 698.81 | 393.53 | 100
156 | NAGALAND | ROAD TRANSPORT | CONSTRUCTION OF TWO LANE WITH HARD SHOULDERS OF MERANGKONG-TAMLU- MON ROAD FROM EXISTING KM 20.456 TO | NHIDCL | N24000763 | 3-2018 | 12/2021 | Aug-2022 | 8/2025 | 215.79 | N.A. | 215.79 | 132.93 | 80.38
157 | NAGALAND | ROAD TRANSPORT | CONSTRUCTION OF TWO LANE WITH HARD SHOULDERS OF MERANGKONG-TAMLU- MON ROAD FROM EXISTING KM 60.345 TO | NHIDCL | N24000765 | 3-2018 | 9/2018 | Jun-2023 | 9/2025 | 323.98 | N.A. | 323.98 | 119.94 | 60.11
158 | NAGALAND | ROAD TRANSPORT | WIDENING TO 2 LANE WITH HARD SHOULDER OF AKEGWO-AVANGKHU SECTION OF NH-202K FOR PACKAGE-I (DESIGN CH | NHIDCL | N24001976 | 12-2022 | 2/2026 | N.A. | 2/2026 | 430.24 | N.A. | 430.24 | 100.51 | 58.57
159 | NAGALAND | ROAD TRANSPORT | WIDENING TO 2 LANE WITH HARD SHOULDER OF AKEGWO-AVANGKHU SECTION OF NH-202K FOR PACKAGE-II (DESIGN C | NHIDCL | N24001977 | 12-2022 | 2/2026 | N.A. | 2/2026 | 442.54 | N.A. | 442.54 | 50.60 | 28.05
160 | NAGALAND | ROAD TRANSPORT | WIDENING TO 2 LANE WITH HARD SHOULDER OF AKEGWO-AVANGKHU SECTION OF NH-202K FOR PACKAGE-III (DESIGN | NHIDCL | N24001978 | 12-2022 | 2/2026 | N.A. | 2/2026 | 497.18 | N.A. | 497.18 | 168.20 | 66.03
161 | NAGALAND | ROAD TRANSPORT | WIDENING OF EXISTING SINGLE LANE ROAD TO INTERMEDIATE LANE ROAD FROM MOKOKCHUNG TO CHARE VIA DIKHU I | MoRTH | N24001855 | 2-2021 | 6/2025 | Sep-2025 | 9/2025 | 192.93 | N.A. | 192.93 | 112.09 | 93.38
162 | NAGALAND | ROAD TRANSPORT | PEREN-DIMAPUR PKG-3 | NHIDCL | N24001912 | 2-2021 | 6/2025 | N.A. | 12/2025 | 177.77 | 199.02 | 199.02 | 46.94 | 63.33
163 | NAGALAND | ROAD TRANSPORT | MERANGKONG-TAMLU-MON (MTM) PKG-5 | NHIDCL | N24001438 | 7-2021 | 12/2023 | N.A. | 9/2025 | 161.73 | N.A. | 161.73 | 65.19 | 73.34
164 | NAGALAND | ROAD TRANSPORT | WIDENING OF EXISTING SINGLE LANE / INTERMEDIATE LANE ROAD TO 2 LANE FROM KM 101 TO KM 125 OF NH 61 I | MoRTH | N24001465 | 6-2020 | 9/2024 | Jun-2026 | 6/2026 | 252.19 | N.A. | 252.19 | 14.33 | 20.27
165 | NAGALAND | ROAD TRANSPORT | WIDENING TO EXISTING SINGLE LANE /INTERMEDIATE LANE TO 2 LANE FROM KM185.00 TO KM 220.00 OF NH-61 (N | MoRTH | N24001466 | 3-2021 | 7/2024 | Dec-2025 | 12/2025 | 297.24 | N.A. | 297.24 | 150.10 | 80.31
166 | NAGALAND | ROAD TRANSPORT | WIDENING TO EXISTING SINGRE/INTERMEDIATE RANE TO 2 LANE FROM KM 135 TO KM 147 AND FROM KM 156.00 TO | MoRTH | N24001467 | 3-2021 | 2/2024 | Mar-2025 | 3/2025 | 226.44 | N.A. | 226.44 | 140.24 | 100
167 | SIKKIM | CIVIL AVIATION | PAKYONG AIRPORT- WIDENING OF BASIC STRIP AT WESTERN SIDE OF RUNWAY CHAINAGE 80M TO 920M I/C SLOPE ST | AAI | N04000110 | 11-2023 | 6/2026 | N.A. | 6/2026 | 323.26 | N.A. | 323.26 | 29.68 | 12.5
168 | SIKKIM | DEPARTMENT OF HIGHER EDUCATION | CONSTRUCTION OF SIKKIM UNIVERSITY CAMPUS PHASE-I, PACKAGE -II AT YANGANG SOUTH SIKKIM | Sikkim Universi | N44000002 | 8-2020 | 1/2025 | N.A. | 1/2025 | 314.06 | N.A. | 303.55 | 157.24 | 80
169 | SIKKIM | POWER | TEESTA VI HE PROJECT | NHPC | N18000325 | 3-2019 | 3/2024 | N.A. | 12/2027 | 5,748.04 | N.A. | 5,748.04 | 4,424.21 | 68.17
170 | SIKKIM | POWER | RANGIT IV HE PROJECT | NHPC | N18000326 | 3-2021 | 5/2024 | N.A. | 12/2025 | 938.29 | N.A. | 1,828.11 | 1,524.17 | 89.45
171 | SIKKIM | RAILWAYS | SEVOK RANGPO, NEFR | NFR | N22000102 | 4-2008 | 5/2015 | Dec-2027 | 12/2027 | 7,876.92 | 11,963.43 | 11,963.43 | 8,743.57 | 79.5
172 | SIKKIM | ROAD TRANSPORT | CONSTRUCTION OF 2-LANE WITH PAVED SHOULDER GANGTOK BYPASS ROAD FROM RANIPOOL TO BURTUK (L=23.316KM) | MoRTH | N24001442 | 10-2021 | 5/2024 | Mar-2026 | 3/2026 | 385.15 | N.A. | 385.15 | 175.16 | 83.3
173 | SIKKIM | ROAD TRANSPORT | CONSTRUCTION OF 2-LANE WITH PAVED SHOULDER INCLUDING GEOMETRIC IMPROVEMENT FROM KM 0.000 TO KM 16.00 | NHIDCL | N24000767 | 3-2017 | 4/2022 | May-2022 | 12/2023 | 375.80 | N.A. | 375.80 | 288.56 | 96.55
174 | SIKKIM | ROAD TRANSPORT | CONSTUCTION/UPGRADATION OF EXISTING HIGHWAY TO 2 LANE WITH PAVED SHOULDER FROM KM 0.00 TO KM 13.00 N | NHIDCL | N24001251 | 3-2019 | 4/2022 | N.A. | 10/2025 | 402.94 | N.A. | 402.94 | 247.12 | 76.54
175 | SIKKIM | ROAD TRANSPORT | CONSTUCTION/UPGRADATION OF EXISTING HIGHWAY TO 2 LANE WITH PAVED SHOULDER FROM KM 13.00 TO KM 25.600 | NHIDCL | N24001252 | 8-2020 | 4/2023 | Nov-2024 | 10/2025 | 295.97 | N.A. | 295.97 | 249.97 | 95.71
176 | SIKKIM | ROAD TRANSPORT | CONSTRUCTION AND UPGRADATION OFEXISTINGROAD TO 2-LANE WITH PAVED SHOULDER INCLUDING GEOMETRIC IMPROV | NHIDCL | N24001261 | 8-2020 | 4/2023 | N.A. | 10/2025 | 311.00 | N.A. | 273.78 | 257.86 | 95.12
177 | SIKKIM | ROAD TRANSPORT | CONSTRUCTION AND UPGRADATION OFEXISTINGROAD TO 2-LANE WITH PAVED SHOULDER INCLUDING GEOMETRIC IMPROV | NHIDCL | N24001262 | 7-2020 | 4/2023 | Aug-2024 | 10/2025 | 345.38 | 395.59 | 395.59 | 362.61 | 89.81
178 | SIKKIM | ROAD TRANSPORT | RISHI BORDER- ROLEP- MENLA PKG- 3B | NHIDCL | N24001362 | 12-2020 | 2/2024 | Dec-2025 | 12/2025 | 410.60 | 379.30 | 379.30 | 238.13 | 74.82
179 | SIKKIM | ROAD TRANSPORT | CONSTRUCTION AND UPGRADATION OF EXISTING ROAD TO 2-LANE WITH PAVED SHOULDER FROM KM27.200 (END OF RO | NHIDCL | N24001336 | 8-2020 | 4/2023 | Oct-2024 | 3/2026 | 230.45 | 244.91 | 244.91 | 206.95 | 82.8
180 | SIKKIM | ROAD TRANSPORT | CONSTRUCTION AND UPGRADATION OF EXISTING ROAD TO 2-LANE WITH PAVED SHOULDER FROM NEW ROLEP BRIDGE AT | NHIDCL | N24001337 | 10-2020 | 11/2023 | Jul-2025 | 3/2026 | 493.42 | 478.79 | 478.79 | 308.18 | 59.49
181 | SIKKIM | ROAD TRANSPORT | CONSTRUCTION OF 2-LANE WITH PAVED SHOULDER OF NEW GREEN FIELD ALIGNMENT FROM CHOCHENPHERI AT KM 52.0 | NHIDCL | N24001338 | 10-2020 | 12/2023 | Jun-2025 | 12/2026 | 816.79 | 786.60 | 786.60 | 332.24 | 45.9
182 | SIKKIM | ROAD TRANSPORT | REHABILITATION AND UPGRADATION OF EXISTING ROAD TO 2-LANE WITH PAVED SHOULDER INCLUDING GEOMETRIC IM | NHIDCL | N24001327 | 8-2020 | 5/2022 | Oct-2023 | 12/2025 | 292.80 | N.A. | 292.80 | 202.92 | 61.41
183 | SIKKIM | ROAD TRANSPORT | CONSTRUCTION OF 2-LANE ROAD WITH PAVED SHOULDER (GREENFIELD ALIGNMENT) OF EXISTING STRETCH BETWEEN L | NHIDCL | N24001322 | 9-2020 | 5/2022 | Oct-2023 | 12/2025 | 183.31 | 439.56 | 439.56 | 355.31 | 51.85
184 | SIKKIM | ROAD TRANSPORT | CONSTRUCTION OF 2-LANE SPECIFICATION ROAD WITH PAVED SHOULDER AS REALIGNMENT (GREENFIELD ALIGNMENT) | NHIDCL | N24001325 | 9-2020 | 5/2023 | Aug-2024 | 12/2025 | 262.84 | 414.20 | 414.20 | 221.86 | 49.2
185 | TRIPURA | PETROLEUM | GRASS ROOT RAIL FED DEPOT AT SEKERKOTE, AGARTALA AS RESITEMENT OF EXISTING DHARMANAGAR DEPOT | IOCL | N16000495 | 6-2022 | 8/2025 | Sep-2025 | 9/2025 | 656.00 | N.A. | 656.00 | 427.77 | 83.17
186 | TRIPURA | ROAD TRANSPORT | MANU-SIMLUNG ( PKG 4) | NHIDCL | N24001363 | 3-2021 | 12/2022 | N.A. | 12/2025 | 354.79 | N.A. | 354.79 | 34.08 | 0
187 | TRIPURA | ROAD TRANSPORT | REHABILITATION AND UPGRADATION OF ROAD FROM KM 0.00 TO KM 18.600 OF KUMARGHAT-KAILASHAHAR SECTION | NHIDCL | N24001263 | 6-2020 | 1/2022 | Feb-2024 | 12/2024 | 277.50 | 302.02 | 302.02 | 262.91 | 99.94
188 | TRIPURA | ROAD TRANSPORT | 2-LANING FROM JOLAIBARI - BELONIA | NHIDCL | N24001317 | 6-2020 | 1/2022 | N.A. | 4/2025 | 201.99 | N.A. | 287.47 | 148.22 | 100
189 | TRIPURA | ROAD TRANSPORT | KAILASHAHAR TO KHOWAI PKG-4 | NHIDCL | N24001309 | 11-2020 | 6/2022 | Oct-2023 | 11/2024 | 159.13 | 171.50 | 171.50 | 84.33 | 100
190 | TRIPURA | ROAD TRANSPORT | 2 LANING FROM MANU-SIMLUNG PKG-2 | NHIDCL | N24001542 | 2-2022 | 1/2025 | May-2025 | 5/2025 | 456.88 | N.A. | 456.88 | 122.67 | 50.18
191 | TRIPURA | ROAD TRANSPORT | IMPROVEMENT AND WIDENING TO 2-LANE WITH EARTHEN PAVED SHOULDER FROM UDAIPUR TO SRIMANTAPUR | NHIDCL | N24001914 | 5-2023 | 11/2024 | N.A. | 12/2025 | 195.95 | N.A. | 195.95 | 46.46 | 45.42
192 | TRIPURA | ROAD TRANSPORT | CHAMPAK NAGAR TO KHAYERPUR SECTION (DESIGN KM 242+500 TO KM 261+610) | NHIDCL | N24002205 | 12-2023 | 9/2026 | N.A. | 9/2026 | 920.66 | N.A. | 920.66 | 81.54 | 24.56
193 | TRIPURA | ROAD TRANSPORT | KHOWAI ?TELIAMURA-AMARPUR-HARINA- SABROOM SECTION PKG-4 | NHIDCL | N24002228 | 1-2024 | 12/2026 | N.A. | 12/2026 | 726.90 | N.A. | 726.90 | 7.36 | 3.85
194 | TRIPURA | ROAD TRANSPORT | 4 LANE WITH PAVED SHOULDER AGARTALA BYPASS (WESTERN SIDE) CONNECTING NH- 8 | NHIDCL | N24002132 | 3-2023 | 3/2027 | N.A. | 3/2027 | 2,026.05 | N.A. | 2,026.05 | 26.34 | 8.82
195 | TRIPURA | ROAD TRANSPORT | REHABILITATION AND UP-GRADATION OF ROAD FROM DESIGN KM 25.250 TO KM 36.460 (TOTAL LENGH: 11.210 KM) | NHIDCL | N24002159 | 2-2020 | 3/2026 | N.A. | 3/2026 | 174.43 | N.A. | 174.43 | 9.54 | 16.61
196 | TRIPURA | ROAD TRANSPORT | IMPROVEMENT AND WIDENING TO 2-LANE WITH PAVED SHOULDER OF ROAD FROM KM 101.300 TO KM 127.319 (TOTAL | NHIDCL | N24002160 | 1-2024 | 7/2026 | N.A. | 7/2026 | 431.78 | N.A. | 431.78 | 52.82 | 34.61
197 | TRIPURA | ROAD TRANSPORT | KHOWAI ?TELIAMURA-AMARPUR-HARINA- SABROOM PACKAGE-2 | NHIDCL | N24002161 | 1-2024 | 9/2026 | N.A. | 9/2026 | 657.21 | N.A. | 657.21 | 95.71 | 32.85
198 | TRIPURA | ROAD TRANSPORT | KHOWAI ?TELIAMURA-AMARPUR-HARINA- SABROOM PACKAGE-3 | NHIDCL | N24002162 | 1-2024 | 9/2026 | N.A. | 9/2026 | 670.90 | N.A. | 670.90 | 3.81 | 3.05

## June_Table7_All_Projects
Sl.No | State | Sector | Project Name | Agency | Project Code | Date of Approval (MM/YYYY) | DoC - Original (MM/YYYY) | DoC - Revised (MM/YYYY) | DoC - Anticipated (MM/YYYY) | Original Cost (Rs. Crore) | Revised Cost (Rs. Crore) | Anticipated Cost (Rs. Crore) | Cumulative Expenditure (Rs. Crore) | Physical Progress (%)
1 | ANDAMAN AND NICOBAR ISLANDS | CIVIL AVIATION | CONSTRUCTION OF NEW INTEGRATED TERMINAL BUILDING AT VSI AIRPORT, PORTBLAIR | AAI | N04000073 | 10-2013 | 9/2018 | Jun-2023 | 6/2023 | 417.23 | 707.73 | 707.73 | 698.80 | 100.00
2 | ANDAMAN AND NICOBAR ISLANDS | RAILWAYS | LUDHIANA KILA RAIPUR (19 KMS) WITH FREIGHT LINE AT GILL STATION ON LDH-JHL SECTION | NR | N22000584 | 3-2019 | 3/2025 | Aug-2025 | 3/2026 | 235.72 | N.A. | 235.72 | 59.78 | 55.00
3 | ANDAMAN AND NICOBAR ISLANDS | RAILWAYS | MAJOR BRIDGE OVER MIDDLE STRAIT CREEK | NHIDCL | N24002207 | 12-2024 | 2/2026 | N.A. | 2/2026 | 371.80 | 207.99 | 207.99 | 0.00 | 5.23
4 | ANDAMAN AND NICOBAR ISLANDS | RAILWAYS | PACKAGE-3A | NHIDCL | N24002208 | 2-2018 | 9/2025 | Mar-2024 | 9/2025 | 207.54 | 154.01 | 154.01 | 16.21 | 39.27
5 | ANDAMAN AND NICOBAR ISLANDS | RAILWAYS | PACKAGE-3B | NHIDCL | N24002209 | 2-2018 | 11/2025 | N.A. | 11/2025 | 183.47 | N.A. | 183.47 | 18.36 | 34.01
6 | ANDAMAN AND NICOBAR ISLANDS | RAILWAYS | 2 LANE WITH HARD SHOLDER , REHABILITATION AND UP GRADATION OF SECTION FROM KM 242.0 TO KM 298.0 OF N | NHIDCL | N24000745 | 3-2017 | 12/2019 | Mar-2023 | 6/2025 | 409.85 | N.A. | 409.85 | 214.23 | 95.23
7 | ANDAMAN AND NICOBAR ISLANDS | RAILWAYS | REHABILITATION AND UP GRADATION OF SECTION FROM KM 206.00 TO KM 242.00 (NIMBUTALA TO AUSTIN CREEK) O | NHIDCL | N24000749 | 3-2018 | 9/2020 | Nov-2022 | 7/2025 | 234.27 | N.A. | 234.27 | 126.50 | 83.00
8 | ANDAMAN AND NICOBAR ISLANDS | RAILWAYS | Rehabilitation and up gradation to 2 lane with paved shoulder configuration from existing km. 122.00 | MoRTH | N24000820 | 11-2017 | 11/2019 | N.A. | 11/2019 | 237.80 | N.A. | 238.00 | 222.13 | 98.23
9 | ANDAMAN AND NICOBAR ISLANDS | RAILWAYS | RECONSTRUCTION WITH GEOMETRIC IMPROVEMENT OF EXISTING 2 LANE/INTERMEDIATE LANE TO 2LANE WITH PAVED S | MoRTH | N24000821 | 11-2017 | 11/2019 | N.A. | 11/2019 | 257.34 | N.A. | 238.00 | 214.90 | 100.00
10 | ANDAMAN AND NICOBAR ISLANDS | CIVIL AVIATION | C/O OF NITB AND ASSOCIATED WORK AT VIJAYAWADA AIRPORT | AAI | N04000091 | 4-2020 | 3/2023 | Aug-2025 | 8/2025 | 611.80 | N.A. | 611.80 | 449.66 | 75.25
11 | ANDHRA PRADESH | CIVIL AVIATION | RAJAHMUNDRY AIRPORT: CONSTRUCTION OF NEW DOMESTIC TERMINAL BUILDING AND MISCELLANEOUS WORKS INCLUD | AAI | N04000103 | 12-2022 | 8/2025 | N.A. | 8/2025 | 347.15 | 347.15 | 347.15 | 76.86 | 46.00
12 | ANDHRA PRADESH | CIVIL AVIATION | KADAPPA AIRPORT- CONSTRUCTION OF NEW DOMESTIC TERMINAL BUILDING AND MISCELLANEOUS WORKS INCLUDING MA | AAI | N04000106 | 3-2023 | 1/2026 | Mar-2026 | 3/2026 | 265.91 | 265.91 | 265.91 | 39.54 | 29.00
13 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | CONSTRUCTION OF PERMANENT CAMPUS FOR INDIAN INSTITUTE OF TECHNOLOGY TIRUPATI AT MERLAPAKA VILLAGE YE | CPWD EDUCATION | N42000005 | 2-2019 | 6/2020 | N.A. | 6/2020 | 655.34 | N.A. | 655.34 | 366.21 | 95.00
14 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | CONSTRUCTION OF PERMANENT CAMPUS FOR IISER AT JANGALAPALLI VILLAGE, YERPEDU MANDAL, CHITTOOR DISTRIC | CPWD EDUCATION | N42000007 | 9-2019 | 9/2022 | N.A. | 6/2024 | 588.72 | 656.39 | 656.39 | 630.55 | 100.00
15 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | KG-DWN-98-2 CLUSTER II DEVELOPMENT PROJECT | ONGC | N16000247 | 3-2016 | 6/2020 | Mar-2025 | 6/2025 | 34,012.00 | N.A. | 34,012.00 | 33,167.16 | 96.40
16 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | HP CRUDE TO OLEFINS AND AROMATICS TECHNOLOGY DEMO UNIT AT VISAKH REFINERY | HPCL | N16000432 | 9-2021 | 6/2024 | Mar-2026 | 3/2026 | 160.00 | 220.00 | 220.00 | 75.86 | 59.40
17 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | CGD PROJECT AT KURNOOL, GUNTUR AND PRAKASAM DISTRICTS | IOCL | N16000485 | 3-2022 | 3/2030 | N.A. | 3/2030 | 1,420.00 | N.A. | 1,420.00 | 153.86 | 6.20
18 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | MULTI-PRODUCT PIPELINE FROM KRISHNAPATNAM COASTAL INSTALLATION TO THE PROPOSED INSTALLATION AT HYDER | BPCL | N16000499 | 9-2019 | 3/2025 | N.A. | 10/2025 | 1,932.00 | N.A. | 1,932.00 | 1,498.21 | 94.30
19 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | HP TRIJET UNIT IN VR | HPCL | N16000535 | 7-2024 | 7/2027 | N.A. | 7/2027 | 193.00 | N.A. | 193.00 | 0.43 | 23.00
20 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | CONSTRUCTION OF AVIATION FUEL FARM FACILITIES AT BHOGAPURAM AIRPORT | HPCL | N16000538 | 8-2024 | 3/2026 | N.A. | 3/2026 | 240.00 | N.A. | 240.00 | 22.34 | 42.80
21 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | VISAKHA RAIPUR PIPELINE PROJECT | HPCL | N16000539 | 9-2024 | 9/2027 | N.A. | 9/2027 | 2,212.00 | N.A. | 2,212.00 | 8.32 | 6.03
22 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | TRANSMISSION SCHEME FOR SOLAR ENERGY ZONE IN ANANTHPURAM (2500MW) AND KURNOOL (1000MW) | PGCIL | N18000380 | 9-2023 | 3/2025 | N.A. | 9/2025 | 1,249.00 | N.A. | 1,249.00 | 761.69 | 67.50
23 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | AUGMENTATION OF 1500MVA 3RD 765/400KV TRANSFORMATION CAPACITY AT KURNOOL NEW SUBSTATION | PGCIL | N18000395 | 5-2023 | 9/2025 | N.A. | 9/2025 | 164.00 | N.A. | 164.00 | 60.00 | 33.00
24 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | TRANSMISSION SYSTEM FOR INTEGRATION OF KURNOOL-IV REZ PHASE-I (FOR 4.5 GW) | PGCIL | N18000413 | 3-2025 | 3/2027 | N.A. | 3/2027 | 5,000.00 | N.A. | 5,000.00 | 20.00 | -
25 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | TRANSMISSION SYSTEM STRENGTHENING AT KURNOOL- III PS FOR INTEGRATION OF ADDITIONAL RE GENERATION PRO | PGCIL | N18000416 | 3-2025 | 3/2027 | N.A. | 3/2027 | 2,886.00 | N.A. | 2,886.00 | 20.20 | -
26 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | KOTLPALLI-NARASAPUR (NL) (SCR) | SCR | 220100265 | 12-2001 | 3/2028 | N.A. | 3/2027 | 2,500.98 | N.A. | 2,500.98 | 1,141.44 | 18.00
27 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | NADIKUDE-SRI KALAHASTI | SCR | N22000286 | 4-2011 | 5/2027 | N.A. | 5/2027 | 2,312.00 | N.A. | 3,122.35 | 1,977.09 | -
28 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | GUNTUR-GUNTAKAL | SCR | N22000368 | 4-2016 | 12/2025 | N.A. | 12/2025 | 3,733.37 | N.A. | 3,887.48 | 3,606.85 | -
29 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | VIJAYAWADA-GUDUR | RVNL | N22000369 | 4-2015 | 11/2024 | N.A. | 12/2024 | 6,654.00 | N.A. | 6,238.67 | 5,883.89 | -
30 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | KOTTAVALSA - KORAPUT DOUBLING | ECOR | N22000377 | 4-2015 | 3/2022 | N.A. | 3/2022 | 2,499.71 | N.A. | 2,499.71 | 1,965.11 | 70.00
31 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | PENUKONDA-DHARMAVARAM, EXCL. DHARMAVARAM (41.5 KM) | SWR | N22000555 | 4-2019 | 3/2026 | N.A. | 12/2025 | 294.67 | 307.66 | 307.66 | 213.03 | 60.00
32 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | MALUGUR-PALASAMUDRAM (17.98 KM) (PB#29/NR/2022-23) | SWR | N22000556 | 9-2022 | 12/2025 | N.A. | 12/2026 | 323.14 | 342.41 | 342.41 | 46.89 | 12.00
33 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | DOUBLING BETWEEN GOOTY- PENDAKALLU (29.225) | SCR | N22000585 | 3-2023 | 3/2027 | N.A. | 3/2027 | 351.83 | N.A. | 351.83 | 0.00 | -
34 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | VIJAYAWADA KAZIPET BYEPASS LINE | SCR | N22000586 | 4-2016 | 12/2025 | N.A. | 12/2025 | 647.37 | N.A. | 226.72 | 261.07 | -
35 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | RENIGUNTA WADI GOOTY - BYPASS | SCR | N22000587 | 4-2016 | 12/2025 | N.A. | 12/2025 | 302.00 | N.A. | 302.00 | 226.67 | 50.00
36 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | CONSTRUCTION OF 4 LANE ACCESS CONTROLLED NEW GREENFIELD HIGHWAY SECTION OF NH 365BG FROM RECHARLA VI | NHAI | N24001476 | 9-2021 | 9/2022 | Sep-2024 | 7/2025 | 517.05 | N.A. | 655.06 | 543.03 | 94.50
37 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | CONSTRUCTION OF 4 LANE ACCESS CONTROLLED NEW GREENFIELD HIGHWAY SECTION OF NH-365BG (KHAMMAM-DEVARAP | NHAI | N24001477 | 9-2021 | 9/2022 | Sep-2024 | 6/2025 | 622.00 | N.A. | 817.91 | 541.73 | 75.96
38 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | 6L OF CHILKARARUPET BYPASS FROM KM. 357.400 TO KM. 371.920 OF NH-16 | NHAI | N24001817 | 2-2019 | 3/2023 | Oct-2024 | 10/2024 | 757.45 | N.A. | 757.45 | 711.37 | 99.61
39 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | 6L OF PONDAVAKKAM TO KANNIGAIPAIR FROM KM 96.040 TO KM 116.100 OF NH 716B (PKG-IV) | NHAI | N24001818 | 2-2021 | 1/2025 | N.A. | 1/2025 | 818.73 | N.A. | 1,105.00 | 564.03 | 25.32
40 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | 6L OF VEERA KAVERI RAJA PURAM TO PONDAVAKKAM FROM KM 61.380 TO KM 96.040 OF NH 716B (PKG-III) | NHAI | N24001819 | 3-2021 | 1/2025 | N.A. | 1/2025 | 1,102.63 | N.A. | 1,303.00 | 1,171.71 | 97.26
41 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | 6L OF VARADHARAJULA TO KUMARAJAPET FROM KM 0.000 TO KM 43.800 OF NH-716B (PKG-I) | NHAI | N24001820 | 2-2021 | 12/2024 | N.A. | 12/2024 | 1,484.83 | N.A. | 1,768.00 | 1,544.65 | 93.29
42 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | BANGALORE CHENNAI EXPRESSWAY (PHASE-II PKG-III) FROM KM.127.000 TO KM 156.000 (BANGARUPALEM TO GUDIP | NHAI | N24001821 | 11-2020 | 10/2024 | N.A. | 10/2024 | 1,137.74 | N.A. | 1,289.00 | 1,256.44 | 97.43
43 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | BANGALORE CHENNAI EXPRESSWAY (PHASE-II PKG-I) FROM KM.71.000 TO KM 96.000 (BETHAMANGALA IN THE STATE | NHAI | N24001822 | 12-2020 | 10/2024 | N.A. | 10/2024 | 1,075.27 | N.A. | 1,307.00 | 1,132.36 | 85.89
44 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | 4L OF MADANAPALLE TO PILERU SECTION FROM KM 0.000 TO KM 55.900 OF NH-71(PACKAGE-I) - N/05060/01002/A | NHAI | N24001823 | 1-2022 | 1/2025 | Jan-2023 | 1/2025 | 1,852.12 | N.A. | 1,787.00 | 777.18 | 93.00
45 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | RENIGUNTA - POYYA - NAIDUPETA KM 124.60 TO KM 183.4 OF NH 71 - N/04027/06001/AP | NHAI | N24001824 | 3-2020 | 1/2024 | Dec-2024 | 12/2024 | 1,863.09 | N.A. | 2,238.00 | 1,227.61 | 98.76
46 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | 6L KANTAKAPALLE ? SABBAVARAM SECTION OF NH-130CD ROAD FROM KM 445.100 TO KM 464.662 (PKG-4) | NHAI | N24001836 | 2-2021 | 10/2024 | N.A. | 3/2026 | 824.29 | N.A. | 924.00 | 521.51 | 76.13
47 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | 6L JAKKUVA ? KORLAM SECTION OF NH-130CD ROAD FROM KM 396.800 TO KM 421.100 (PKG 2) | NHAI | N24001837 | 2-2021 | 3/2024 | Jul-2024 | 12/2025 | 663.60 | N.A. | 768.00 | 464.74 | 98.84
48 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | 6L ALURU - JAKKUVA SECTION OF NH- 130CD ROAD FROM KM 365.033 TO KM 396.800 (PKG. 1) | NHAI | N24001838 | 2-2021 | 3/2024 | N.A. | 12/2025 | 922.50 | N.A. | 1,128.68 | 534.51 | 84.38
49 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | 6L ACCESS CONTROLLED GREENFIELD HIGHWAY FROM KODUR 0.000 KMS TO VANAVOLU 24.300 KMS OF NH 544G PACKA | NHAI | N24001841 | 12-2022 | 9/2025 | N.A. | 2/2026 | 912.94 | N.A. | 912.94 | 238.84 | 59.65
50 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | 6L ACCESS CONTROLLED GREENFIELD HIGHWAY FROM VANAVOLU 24.300 KM. TO VANKARAKUNTA 45.700 KM. OF NH 5 | NHAI | N24001842 | 12-2022 | 11/2025 | N.A. | 11/2025 | 750.81 | N.A. | 750.81 | 145.15 | 50.78
51 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | 6L ACCESS CONTROLLED GREENFIELD HIGHWAY FROM VANKARAKUNTA 45.700 KM. TO ODULAPALLE 72.000 KM. OF NH | NHAI | N24001843 | 12-2022 | 11/2025 | N.A. | 11/2025 | 992.89 | N.A. | 992.89 | 197.36 | 47.00
52 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | 6L ACCESS CONTROLLED GREENFIELD HIGHWAY FROM ODULAPALLE 72.000 KM. TO NALLACHERUVUPALLI 96.300 KM. | NHAI | N24001844 | 12-2022 | 10/2025 | N.A. | 10/2025 | 1,058.90 | N.A. | 1,058.90 | 251.41 | 47.64
53 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | 6L ACCESS CONTROLLED GREENFIELD HIGHWAY FROM NALLACHERUVU PALLI 96.300 KM. TO YERRAGUDIPADU 129.000 | NHAI | N24001845 | 2-2023 | 10/2025 | N.A. | 10/2025 | 1,253.24 | N.A. | 1,253.24 | 197.29 | 23.20
54 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | 6L ACCESS CONTROLLED GREENFIELD HIGHWAY FROM YERRAGUDIPADU 129.000 KM. TO AUDIREDDIPALLE 160.000 KM. | NHAI | N24001846 | 2-2023 | 10/2025 | N.A. | 10/2025 | 1,200.42 | N.A. | 1,200.42 | 98.82 | 8.90
55 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | 6L ACCESS CONTROLLED GREENFIELD HIGHWAY FROM AUDIREDDIPALLE 160.000 KM. TO MALLAPALLE 176.000 KM. PA | NHAI | N24001847 | 1-2023 | 11/2025 | N.A. | 11/2025 | 956.14 | N.A. | 956.14 | 215.17 | 43.11
56 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | 6L ACCESS CONTROLLED GREENFIELD HIGHWAY FROM MALLAPALLE 176.000 KM. TO KAVULAKUNTLA 196.000 KM. PACK | NHAI | N24001848 | 2-2023 | 10/2025 | N.A. | 10/2025 | 909.02 | N.A. | 909.02 | 161.56 | 23.44
57 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | 4L PS MYDUKUR BADVEL FROM KM 585.820 TO KM 630.960 SECTION OF NH 67 | NHAI | N24001849 | 5-2022 | 7/2025 | N.A. | 9/2025 | 1,063.72 | N.A. | 1,063.72 | 467.94 | 82.10
58 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | CONSTRUCTION OF 4-LANE HIGHWAY FROM SAMARLAKOTA TO ACHAMPETA JUNCTION (FROM KM. 0.000 TO KM. 12.250 | NHAI | N24001856 | 5-2023 | 8/2025 | N.A. | 8/2025 | 648.75 | N.A. | 648.75 | 253.96 | 64.67
59 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | 2L+PS FROM KM. 0+000 TO KM. 32+000 (MUDIGUBBA TO PUTTAPARTHI) OF NH- 342 | MoRTH | N24001932 | 3-2022 | 9/2024 | N.A. | 6/2025 | 401.72 | N.A. | 401.72 | 190.74 | 80.00
60 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | NH440 RAYACHOTY TOVEMPALLI 2LPS | MoRTH | N24001934 | 12-2021 | 5/2024 | N.A. | 7/2025 | 439.82 | N.A. | 439.82 | 174.96 | -
61 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | 4 LANE WITH PAVED SHOULDER FROM KM 0.000 TO KM 51.119 OF TADIPATRI TO MUDDANUR OF NH67 | MoRTH | N24001935 | 3-2022 | 8/2025 | N.A. | 8/2025 | 724.17 | N.A. | 724.17 | 464.48 | -
62 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | NH165 FROM KM 0.000 TO KM 64.020 PAMARRU TO AKIVEEDU SECTION TO TWO LANE WITH PAVED SHOULDERS | MoRTH | N24001939 | 3-2020 | 9/2023 | N.A. | 12/2026 | 529.24 | N.A. | 529.24 | 353.88 | 62.70
63 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | 2LPS FROM KM36.400 TO KM. 107.224 OF NH167BG FROM DUTTALUR TO KAVALI SECTION | MoRTH | N24001942 | 3-2021 | 7/2024 | N.A. | 6/2026 | 423.67 | N.A. | 423.67 | 222.39 | 83.59
64 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | NH167AD FROM MACHERLA TO DACHEPALLI FROM KM.0.000 TO 43.659 TO 2LPS | MoRTH | N24001951 | 1-2022 | 1/2025 | N.A. | 1/2025 | 403.22 | N.A. | 403.22 | 296.69 | 98.82
65 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | NH 167 B KADAPA NELLORE BORDER TO CSPURAM I.E. FROM KM 58.635 TO KM 99.409 | MoRTH | N24001952 | 3-2022 | 8/2025 | N.A. | 8/2025 | 285.50 | N.A. | 285.50 | 204.29 | 95.00
66 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | NH-30-BHADRACHALAM TO KONTA SECTION 2LPS | MoRTH | N24001953 | 12-2021 | 9/2024 | N.A. | 9/2025 | 388.71 | N.A. | 388.71 | 242.09 | 89.60
67 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | WIDENING TO 2LPS OF RAMPACHODAVARAM - KOYYURU SECTION OF NH516E FROM KM.43.700 TO KM 113.820 | MoRTH | N24001954 | 3-2022 | 1/2025 | N.A. | 1/2025 | 568.12 | N.A. | 568.12 | 350.64 | 91.05
68 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | GUDIWADA TOWN 2 LANE ROB AND ROAD IMPROVEMENT OF NH165 IN REPLACEMENT OF LC NO 3ESPL3 AT KM 231.700 | MoRTH | N24001955 | 3-2022 | 5/2025 | N.A. | 5/2025 | 317.22 | N.A. | 317.22 | 190.90 | 80.00
69 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | 2LPS FROM GONDIGUDA TO ARAKU BHALLAGUDA KM 27.480 TO KM 51.772 SECTION OF NH 516E | MoRTH | N24001956 | 8-2020 | 9/2023 | N.A. | 12/2024 | 296.66 | N.A. | 296.66 | 246.11 | 87.49
70 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | 2LPS OF KOYYURU TO CHAPRATHIPALEM SECTION OF NH 516E | MoRTH | N24001957 | 8-2020 | 7/2024 | N.A. | 7/2024 | 349.29 | N.A. | 349.29 | 216.90 | -
71 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | 2LPS OF CHAPRATHIPALEM TO LAMBASINGI SECTION OF NH 516E | MoRTH | N24001958 | 8-2020 | 10/2024 | N.A. | 6/2025 | 311.22 | N.A. | 311.22 | 151.24 | 72.00
72 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | 4 LANE FROM KM 56.400 TO KM 120.300 FROM B.KOTHAPALLI JUNCTION TO GORANTLA OF NH 716G | MoRTH | N24001959 | 3-2022 | 9/2025 | N.A. | 9/2025 | 839.98 | N.A. | 839.98 | 418.51 | -
73 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | 4L GREENFIELD ROAD CONNECTING NORTH AND SOUTH INDUSTRIAL CLUSTER OF KHANDALERU CREEK NEAR KRISHNAPAT | NHAI | N24001979 | 8-2022 | 9/2025 | N.A. | 9/2025 | 609.43 | N.A. | 609.43 | 25.24 | 56.70
74 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | 4 LANING OF NH 544D FROM EXISTING KM 346.300 OF NH 44 (DESIGN CHAINAGE KM 0.000) TO KM 39.380 (DESIG | NHAI | N24001980 | 10-2022 | 7/2025 | N.A. | 7/2025 | 907.76 | N.A. | 907.76 | 388.70 | 84.29
75 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | CONSTRUCTION OF SIX LANING OF NAIDUPETA JUNCTION - TURPUKANUPUR SECTION FROM KM.57+046 TO KM.91+927 | NHAI | N24001981 | 7-2022 | 10/2025 | N.A. | 10/2025 | 1,398.84 | N.A. | 1,398.84 | 58.68 | 19.10
76 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | 4L PS FROM KURNOOL (EXISTING KM. 5.400 OF NH-40/DESIGN KM.0.000) TO MANDLEM (EXISTING KM.38.000/DESI | NHAI | N24001982 | 3-2023 | 10/2025 | N.A. | 10/2025 | 827.39 | N.A. | 827.39 | 333.88 | 99.65
77 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | 4 LANING FROM EXISTING KM 39.380 (DESIGN CH. 37.000) TO KM 74.450 (DESIGN CH. 69.000) OF MUCHUKOTA ? | NHAI | N24001983 | 10-2022 | 8/2025 | N.A. | 8/2025 | 972.63 | N.A. | 1,055.23 | 310.77 | 54.96
78 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | 4L PS FROM MANDLEM (EXISTING KM. 38.000/DESIGN KM.30.600) TO ATMAKUR (EXISTING KM.73.000/DESIGN KM 6 | NHAI | N24001984 | 3-2023 | 10/2025 | N.A. | 10/2025 | 887.28 | N.A. | 887.28 | 297.95 | 89.20
79 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | BANGALORE CHENNAI EXPRESSWAY (PHASE-II PKG-II) FROM KM.96.000 TO KM 127.000 (BAIREDDYPALLE TO BANGAR | NHAI | N24001985 | 3-2021 | 6/2025 | N.A. | 6/2025 | 1,942.94 | 2,171.00 | 2,171.00 | 1,736.95 | 64.50
80 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | 4L OF PILERU TO KALUR SECTION FROM KM 55.900 TO KM 92.800 AND KM 94.500 TO KM 95.717 | NHAI | N24001986 | 10-2023 | 4/2025 | N.A. | 4/2025 | 1,047.32 | N.A. | 1,047.32 | 301.20 | 93.00
81 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | CONSTRUCTION OF 1 NOS ROB, 2 NOS VUPS, SERVICE ROADS, PROVISION OF LIGHTING AND CONSTRUCTION OF OTHE | NHAI | N24001987 | 6-2023 | 12/2024 | N.A. | 12/2024 | 152.05 | N.A. | 152.05 | 139.12 | 76.83
82 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | 6L OF CHITTOOR TO THATCHUR FROM KUMARAJAPET TO VEERA KAVERI RAJA PURAM FROM KM 43.800 TO KM 61.380 O | NHAI | N24001988 | 2-2021 | 10/2025 | N.A. | 10/2025 | 591.99 | 703.00 | 703.00 | 506.67 | 70.95
83 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | CONSTRUCTION OF 4 LANE ACCESS CONTROLLED HIGHWAY FROM CHILLAKURU CROSS ROAD TO TURPUKANUPUR KM 0+000 | NHAI | N24002033 | 7-2022 | 12/2025 | N.A. | 12/2025 | 909.47 | N.A. | 909.47 | 97.03 | 32.30
84 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | COMPLETION OF BALANCE WORKS PENDING IN BIT AND PIECES (INCOMPLETE STRETCH AT 7 LOCATIONS) AND LISTED | NHAI | N24002103 | 9-2022 | 1/2025 | N.A. | 6/2025 | 166.52 | N.A. | 166.52 | 60.34 | 98.00
85 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | 6L ACCESS CONTROLLED GREENFIELD HIGHWAY FROM NARAYANMPET (CH. 203+500) TO CHANDRASEKHARPURAM (CH. 22 | NHAI | N24002122 | 2-2024 | 2/2026 | N.A. | 2/2026 | 813.66 | N.A. | 813.66 | 91.93 | 24.20
86 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | 6L ACCESS CONTROLLED GREENFIELD HIGHWAY FROM CHANDRASEKHARAPURAM (CH. 228+000) TO POLAVARAM (CH. 260 | NHAI | N24002123 | 2-2024 | 2/2026 | N.A. | 2/2026 | 1,292.65 | N.A. | 1,292.65 | 135.27 | 18.96
87 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | 6L ACCESS CONTROLLED GREENFIELD HIGHWAY FROM POLAVARAM (CH. 260+000) TO MARRIPUDI (CH. 285+500) OF [ | NHAI | N24002124 | 2-2024 | 2/2026 | N.A. | 2/2026 | 747.29 | N.A. | 747.29 | 142.65 | 32.02
88 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | 6L ACCESS CONTROLLED GREENFIELD HIGHWAY FROM MARRIPUDI (CH. 285+500) TO SOMAVARAPPADU (CH. 314+600) | NHAI | N24002125 | 2-2024 | 2/2026 | N.A. | 2/2026 | 976.40 | N.A. | 976.40 | 229.68 | 43.60
89 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | 6L ACCESS CONTROLLED GREENFIELD HIGHWAY FROM SOMAVARAPPADU (CH.314.600) TO MUPPAVARAM (CH.343+240) O | NHAI | N24002126 | 2-2024 | 2/2026 | N.A. | 2/2026 | 1,103.89 | N.A. | 1,103.89 | 133.89 | 15.98
90 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | 4-LANE WITH PAVED SHOULDERS FROM KM 32/0 TO KM 79/650 (DESIGN CHAINAGE KM 32+000 TO KM 78+760) PUTTA | MoRTH | N24002139 | 3-2023 | 12/2025 | N.A. | 11/2025 | 1,318.57 | N.A. | 1,318.57 | 424.42 | -
91 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | SOMAYAJULAPALLI ? DHONE SECTION OF NH ? 340B FROM KM.0/0 TO 56/200 [DESIGN CH. KM 0/00 TO KM 53/33] | MoRTH | N24002140 | 4-2023 | 12/2025 | N.A. | 12/2025 | 629.73 | N.A. | 629.73 | 369.43 | -
92 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | 2-LANE WITH PAVED SHOULDER CONFIGURATION OF LAMBASINGI TO PADERU SECTION (KM 205+000 TO KM 253+974) | MoRTH | N24002142 | 8-2023 | 11/2025 | N.A. | 11/2025 | 361.24 | N.A. | 361.24 | 63.54 | -
93 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | BYPASS ROAD TO ADONI TOWN CONNECTING NH-167 (HAGARI - JADCHARLA ROAD) FROM KM.62/700 TO 71/400 IN KU | MoRTH | N24002143 | 8-2023 | 2/2026 | N.A. | 2/2026 | 361.24 | N.A. | 361.24 | 109.65 | 56.00
94 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | VODAREVU-CHILAKALURIPET SECTION (DESIGN CHAINAGE 0+00 TO 47+000) OF NH-167A (PACKAGE-I) | MoRTH | N24002144 | 8-2023 | 2/2026 | N.A. | 2/2026 | 1,064.24 | N.A. | 1,064.24 | 584.25 | -
95 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | TADIPATRI BYPASS (KM 0+000 TO KM 6+285) OF 4-LANE ON NH-67 IN ANANTAPURAMU | MoRTH | N24002145 | 11-2023 | 3/2026 | N.A. | 3/2026 | 159.66 | N.A. | 159.66 | 60.51 | 63.50
96 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | KURNOOL/KADAPA BORDER- JAMMALAMADUGU SECTION OF NH- 167K I.E. DESIGN CH. KM 248+010 TO KM 269+900 | MoRTH | N24002146 | 11-2023 | 11/2025 | N.A. | 11/2025 | 292.63 | N.A. | 292.63 | 81.57 | -
97 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | DORNALA TO KUNTA JUNCTION FROM DESIGN CHAINAGE KM 244+000 TO 267+990 SECTION OF NH-765 (PACKAGE-2) | MoRTH | N24002147 | 12-2022 | 1/2024 | N.A. | 3/2026 | 244.83 | N.A. | 244.83 | 111.65 | -
98 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | PADERU BYPASS (KM 0+000 TO KM 13+000) OF 2- LANE WITH PAVED SHOULDER ON NH-516E | MoRTH | N24002148 | 3-2023 | 3/2024 | N.A. | 2/2026 | 244.43 | N.A. | 244.43 | 23.40 | -
99 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | DAVUALAPALLY TO MALLAPALEM SECTION {DESIGN CH. KM 133+922 TO KM 154+216 (EXISTING CH. KM 133+922 TO | MoRTH | N24002149 | 1-2024 | 2/2024 | N.A. | 2/2026 | 393.61 | N.A. | 393.61 | 135.13 | -
100 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | DEVELOPMENT OF SIX LANE ACCESS CONTROLLED GREEN FIELD HIGHWAY FROM KAVULAKUNTLA (KM.196+000) TO NARA | NHAI | N24002215 | 2-2023 | 2/2027 | N.A. | 2/2027 | 1,092.18 | N.A. | 1,092.18 | 0.14 | -
101 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | ACCESS CONTROLLED HIGHWAY OF 4 LANE WITH PAVED SHOULDERS FROM TN/AP BORDER (DESIGN CHAINAGE KM 61+51 | NHAI | N24002217 | 12-2024 | 12/2026 | N.A. | 12/2026 | 1,346.82 | N.A. | 1,346.82 | 37.35 | 8.20
102 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | CONSTRUCTION OF SIX LANING OF DEDICATED PORT ROAD TO KRISHNAPATNAM PORT (PACKAGE-I) KM 0+000 TO KM 1 | NHAI | N24000811 | 3-2018 | 12/2020 | Dec-2022 | 12/2024 | 314.43 | N.A. | 348.72 | 85.61 | 71.49
103 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | REHABILITATION AND UPGRADATION OF EXISTING NH-167 FROM KM 14.900 TO KM 70.00 (DESIGN CH.14.900 TO 69 | MoRTH | N24000931 | 11-2016 | 5/2017 | N.A. | 11/2024 | 290.15 | N.A. | 236.16 | 205.03 | 90.00
104 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | REHABILITATION AND UPGRADATION OF NEW NH-544DD FROM DESIGN CHAINAGE KM 56.00 TO 102.20 OF KALYANDURG | MoRTH | N24000937 | 3-2018 | 8/2018 | N.A. | 11/2024 | 289.67 | 290.00 | 285.29 | 256.60 | 98.50
105 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | CONSTRUCTION OF TIMMAPURAM TO GURJANAPALLE SECTION FROM KM 26.150 TO 41.161 OF NH- 214(NH216)(KAKINAD | MoRTH | N24000964 | 8-2016 | 1/2017 | N.A. | 5/2025 | 350.61 | N.A. | 411.18 | 390.28 | 98.20
106 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | CONSTRUCTION OF 2L+PS FROM PASARLAPUDI-DHINDI (105/700 TO 127.500 OF NH-214) OF NH-216 | MoRTH | N24000969 | 1-2017 | 9/2017 | N.A. | 6/2025 | 263.45 | N.A. | 263.45 | 265.51 | 85.00
107 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | 6-LANING OF VIJAYAWADA BYPASS FROM GOLLAPUDI (DESIGN CH. 30+000) TO CHINNAKAKANI (DESIGN CH. 47+881) | NHAI | N24001301 | 11-2019 | 1/2024 | N.A. | 7/2024 | 1,601.10 | N.A. | 1,601.10 | 1,445.67 | 92.34
108 | ANDHRA PRADESH | DEPARTMENT OF HIGHER EDUCATION | REHABILITATION AND UPGRADATION TO 2-LANE WITH PAVED SHOULDERS CONFIGURATION OF PADERU- GONDIGUDA SECT | MoRTH | N24001386 | 8-2020 | 3/2021 | N.A. | 6/2025 | 222.61 | N.A. | 222.61 | 183.91 | 95.00
109 | ANDHRA PRADESH | WATER RESOURCES | POLAVARAM IRRIGATION PROJECT | PPA | N30000002 | 2-2009 | 3/2020 | Mar-2027 | 12/2027 | 10,151.04 | N.A. | 55,548.87 | 23,775.68 | 76.00
110 | ANDHRA PRADESH | CIVIL AVIATION | CONSTRUCTION OF NEW GREEN FIELD AIRPORT AT HOLLONGI ITANAGAR ARUNACHAL PRADESH | AAI | N04000092 | 2-2019 | 8/2022 | Jul-2025 | 7/2025 | 645.63 | 732.00 | 732.00 | 694.26 | 99.89
111 | ARUNACHAL PRADESH | POWER | SUBANSIRI LOWER H.E.P (8X250 MW) (NHPC) | NHPC | 180100221 | 9-2003 | 9/2010 | N.A. | 5/2026 | 6,285.33 | N.A. | 26,075.54 | 24,484.77 | 96.60
112 | ARUNACHAL PRADESH | POWER | DIBANG MULTIPURPOSE PROJECT 2880 MW ARUNACHAL PRADESH | NHPC | N18000362 | 2-2023 | 2/2032 | N.A. | 2/2032 | 31,876.39 | N.A. | 31,876.39 | 3,380.24 | 15.81
113 | ARUNACHAL PRADESH | POWER | HUNLI TO HAYULIANG PKG-1 | NHIDCL | N24002222 | 2-2024 | 2/2028 | N.A. | 2/2028 | 1,262.43 | N.A. | 1,262.43 | 12.12 | 2.76
114 | ARUNACHAL PRADESH | POWER | HUNLI TO ITHUN BRIDGE SECTION | NHIDCL | N24002223 | 2-2024 | 1/2027 | N.A. | 1/2027 | 275.50 | N.A. | 275.50 | 7.61 | 7.88
115 | ARUNACHAL PRADESH | POWER | PANGO TO JORGING ROAD PKG-1 | NHIDCL | N24002224 | 1-2024 | 7/2027 | N.A. | 7/2027 | 898.19 | N.A. | 898.19 | 16.01 | 4.25
116 | ARUNACHAL PRADESH | POWER | TWO LANING OF JORAM KOLORIANG ROAD (NH 713) ON EPC BASIS FROM DESIGN KM. 138+000 TO KM. 154+036 [EX | NHIDCL | N24000683 | 2-2017 | 11/2023 | Mar-2024 | 12/2024 | 180.57 | 244.10 | 180.57 | 160.46 | 96.62
117 | ARUNACHAL PRADESH | POWER | CONSTRUCTION OF 2-LANE ROAD WITH PAVED SHOULDERS FROM KM16.00 OF ROING-HUNLI SECTION TO KM 21.500 OF | NHIDCL | N24000946 | 3-2017 | 3/2022 | Jun-2025 | 12/2025 | 1,718.59 | 1,718.59 | 1,718.59 | 742.36 | 73.84
118 | ARUNACHAL PRADESH | POWER | TWO-LANING OF HAYULIANG? HAWAI BYPASS ROAD ON EPC BASIS FROM DESIGN KM. 51.825 TO KM. 63.131 EXISTI | NHIDCL | N24000979 | 1-2017 | 5/2023 | May-2023 | 3/2025 | 256.66 | N.A. | 256.66 | 0.00 | 63.59
119 | ARUNACHAL PRADESH | POWER | CONSTRUCTION OF 2-LANING WITH HARD SHOULDERS OF ARROWA- KHUPA-HAYULIANG SECTION OF NH- 113 FROM CH.68. | NHIDCL | N24001244 | 8-2020 | 4/2022 | Apr-2025 | 4/2025 | 301.06 | N.A. | 301.06 | 205.71 | 100.00
120 | ARUNACHAL PRADESH | POWER | CONSTRUCTION OF 2 LANE ROAD OF POTIN TO PANGIN SECTION OF NH 13 FROM KM 163.59 TO KM 206.66 (PACKAGE | MoRTH | N24001297 | 3-2019 | 3/2027 | N.A. | 3/2027 | 450.65 | N.A. | 450.65 | 398.18 | 95.84
121 | ARUNACHAL PRADESH | POWER | 4 LANING OF ITANAGAR TO BANDARDEWA SECTION OF NH-415 FROM KM 40+430 TO KM 51+735 (PACKAGE B) ON EPC | MoRTH | N24001375 | 6-2020 | 3/2027 | N.A. | 3/2027 | 496.47 | N.A. | 496.47 | 194.62 | 44.56
122 | ARUNACHAL PRADESH | POWER | JORAM ? KOLORIANG ROAD FROM EXISTING KM 50.050 TO KM 70.00 (PKG- 3) | NHIDCL | N24001390 | 8-2020 | 4/2022 | Aug-2024 | 9/2024 | 228.71 | N.A. | 228.71 | 98.86 | 99.52
123 | ARUNACHAL PRADESH | POWER | JORAM ? KOLORIANG ROAD FROM EXISTING KM122.600 TO KM138.00 (PKG-7) | NHIDCL | N24001393 | 8-2020 | 4/2022 | Feb-2024 | 7/2025 | 184.88 | N.A. | 184.88 | 99.32 | 97.42
124 | ASSAM | CIVIL AVIATION | CONSTRUCTION OF NEW INTEGRATED TERMINAL BUILDING AT LGBI AIRPORT GUWAHATI | AAI | N04000083 | 12-2016 | 3/2021 | Sep-2025 | 9/2025 | 1,142.00 | N.A. | 2,333.00 | 1,948.45 | 89.66
125 | ASSAM | COAL | TIKAK EXTENSION OCP - 0.2 MTY | CIL | N06000290 | 7-2022 | 11/2030 | N.A. | 11/2030 | 159.77 | N.A. | 159.77 | 81.45 | -
126 | ASSAM | COAL | TIRAP OCP | CIL | N06000291 | 11-2022 | 11/2027 | N.A. | 11/2027 | 289.46 | N.A. | 289.46 | 105.59 | -
127 | ASSAM | HEALTH AND FAMILY WELFARE | ALL INDIA INSTITUTE OF MEDICAL SCIENCE AT GUWAHATI, ASSAM | HITES | N21000027 | 5-2017 | 5/2021 | Apr-2023 | 6/2025 | 875.00 | 873.92 | 860.00 | 796.74 | 99.62
128 | ASSAM | HEALTH AND FAMILY WELFARE | DEVELOPMENT OF SURFACE FACILITIES FOR PRODUCTION AND EVACUATION OF CRUDE OIL AND NATURAL GAS FROM NA | OIL | N16000331 | 1-2018 | 2/2020 | Jun-2025 | 12/2025 | 543.91 | 726.93 | 726.93 | 491.56 | 93.98
129 | ASSAM | HEALTH AND FAMILY WELFARE | NUMALIGARH REFINERY EXPANSION PROJECT 6 MMTPA REFINARY | NRL | N16000379 | 1-2019 | 10/2024 | N.A. | 12/2025 | 12,366.00 | N.A. | 18,968.00 | 16,357.82 | 74.92
130 | ASSAM | HEALTH AND FAMILY WELFARE | NUMALIGARH REFINERY EXPANSION PROJECT COIT AND PIPELINES | NRL | N16000394 | 1-2019 | 10/2024 | N.A. | 9/2025 | 10,228.00 | N.A. | 9,058.00 | 9,579.31 | 85.10
131 | ASSAM | HEALTH AND FAMILY WELFARE | EXPANSION OF GUWAHATI REFINERY FROM 1 TO 1.2 MMTPA ALONG WITH INSTALLATION OF CATALYTIC REFORMING UN | IOCL | N16000414 | 5-2021 | 10/2023 | May-2026 | 5/2026 | 412.00 | 595.20 | 595.20 | 396.15 | 83.40
132 | ASSAM | HEALTH AND FAMILY WELFARE | REVAMPING OF FACILITIES AT EXISTING GUWAHATI TERMINAL, ASSAM | IOCL | N16000441 | 3-2022 | 7/2026 | Sep-2026 | 9/2026 | 277.00 | N.A. | 277.00 | 181.63 | 67.67
133 | ASSAM | HEALTH AND FAMILY WELFARE | UPGRADATION OF FACILITIES OF NUMALIGARH-SILIGURI PRODUCT PIPELINE (NSPL) FOR TRANSPORTATION OF ADDIT | OIL | N16000449 | 6-2021 | 12/2024 | Jul-2025 | 10/2025 | 860.00 | N.A. | 860.00 | 535.46 | 97.50
134 | ASSAM | HEALTH AND FAMILY WELFARE | PROJECT TO CONSTRUCT A FIELD GAS GATHERING STATION AT BAGHJAN AREA FOR COLLECTION,PROCESSING | OIL | N16000450 | 12-2020 | 7/2024 | Jun-2025 | 12/2025 | 430.76 | N.A. | 430.76 | 320.71 | 83.94
135 | ASSAM | HEALTH AND FAMILY WELFARE | CAPACITY EXPANSION OF DIGBOI REFINERY FROM 0.65 TO 1.0 MMTPA | IOCL | N16000457 | 6-2022 | 10/2025 | N.A. | 3/2026 | 768.00 | N.A. | 768.00 | 101.15 | 34.60
136 | ASSAM | HEALTH AND FAMILY WELFARE | CONSTRUCTION OF LPG FACILITIES AT KAMARDANGA, ASSAM | HPCL | N16000484 | 3-2023 | 7/2027 | Jul-2027 | 7/2027 | 156.36 | 156.36 | 156.36 | 44.33 | 35.40
137 | ASSAM | HEALTH AND FAMILY WELFARE | SETTING UP OF NEW RAIL FED POL FACILITY AT KAMARDANGA, ASSAM | HPCL | N16000494 | 3-2023 | 7/2027 | Jul-2027 | 7/2027 | 384.04 | N.A. | 384.04 | 97.54 | 44.00
138 | ASSAM | HEALTH AND FAMILY WELFARE | POWER RECOVERY TURBINE IN PFCCU | NRL | N16000510 | 3-2023 | 7/2025 | N.A. | 7/2025 | 293.50 | N.A. | 293.50 | 97.22 | 92.00
139 | ASSAM | HEALTH AND FAMILY WELFARE | DCU REVAMP PROJECT | NRL | N16000511 | 8-2021 | 3/2025 | N.A. | 10/2025 | 370.00 | N.A. | 370.00 | 255.51 | 55.00
140 | ASSAM | HEALTH AND FAMILY WELFARE | PIPELINE NETWORK PROJECT RUDRASAGAR | ONGC | N16000528 | 1-2023 | 4/2026 | N.A. | 4/2026 | 344.99 | N.A. | 344.99 | 208.56 | 46.30
141 | ASSAM | HEALTH AND FAMILY WELFARE | BORHOLLA GGS LIFE EXTENSION PROJECT | ONGC | N16000532 | 9-2023 | 5/2026 | N.A. | 5/2026 | 198.70 | N.A. | 198.70 | 99.52 | 27.30
142 | ASSAM | RAILWAYS | BONGAIGAON-GOALPARA-GUWAHATI (176 KM) | NFR | N22000388 | 4-2015 | 3/2026 | N.A. | 3/2027 | 4,059.65 | N.A. | 4,962.40 | 3,668.09 | 92.31
143 | ASSAM | RAILWAYS | JOGIGHOPA BRIDGE | NHIDCL | N24001434 | 8-2021 | 11/2024 | N.A. | 12/2026 | 746.76 | N.A. | 746.76 | 344.27 | 67.85
144 | ASSAM | RAILWAYS | DABOKA KATHKATI PACKAGE-6 | NHIDCL | N24001450 | 9-2021 | 7/2024 | N.A. | 5/2025 | 625.64 | N.A. | 625.64 | 556.44 | 100.00
145 | ASSAM | RAILWAYS | DABOKA KATHKATI PACKAGE-7 | NHIDCL | N24001537 | 11-2021 | 7/2024 | N.A. | 7/2025 | 204.10 | N.A. | 204.10 | 143.66 | 96.80
146 | ASSAM | RAILWAYS | FOUR LANING OF SRIRAMPUR-DHUBRI PKG-2 | NHIDCL | N24001544 | 3-2022 | 1/2025 | N.A. | 6/2025 | 909.02 | N.A. | 909.02 | 532.44 | 100.00
147 | ASSAM | RAILWAYS | 6L STANDALONE FLYOVERS AT RAHA, DEMOW, BORGHAT, KATHIATALI JUNCTIONS AND ROB AT JAGIROAD ON STRETCHE | NHAI | N24001545 | 8-2022 | 12/2022 | Sep-2024 | 6/2024 | 175.00 | N.A. | 175.00 | 209.02 | 100.00
148 | ASSAM | RAILWAYS | BALANCE WORK OF 4L OF NARIMBANGLO?JATINGA JUNCTION- HARANGAJO ROAD SECTION FROM KM 0.000 TO KM 49.23 | NHAI | N24001547 | 3-2022 | 1/2026 | N.A. | 1/2026 | 1,909.98 | N.A. | 1,909.98 | 683.00 | 78.92
149 | ASSAM | RAILWAYS | 6L STANDALONE FLYOVERS AT BONGAIGAON, CHAPAGURI, PATHSALA, SIMLAGURI CHOWK AND BAIHATA BYPASS JUNCTI | NHAI | N24001548 | 3-2022 | 6/2024 | N.A. | 5/2025 | 457.72 | N.A. | 457.72 | 366.34 | 100.00
150 | ASSAM | RAILWAYS | SRIRAMPUR - DHUBRI PKG-1 | NHIDCL | N24001831 | 3-2022 | 2/2025 | N.A. | 11/2026 | 613.89 | N.A. | 613.89 | 110.76 | 35.77
151 | ASSAM | RAILWAYS | DIBRUGARH-LAHOAL-CHABUA BYPASS PACKAGE-3 | NHIDCL | N24001832 | 1-2023 | 5/2025 | N.A. | 11/2025 | 458.59 | N.A. | 458.59 | 205.87 | 66.12
152 | ASSAM | RAILWAYS | CONSTRUCTION OF MANGALDOI BYPASS (NH-15) STARTING AT CH 26+400 AND TERMINATING AT CH 41+505 UNDER RA | MoRTH | N24001840 | 3-2022 | 4/2025 | N.A. | 3/2026 | 535.03 | N.A. | 535.03 | 102.23 | 34.54
153 | ASSAM | RAILWAYS | WIDENING AND UPGRADATION TO TWO LANES WITH PAVED SHOULDERS ROAD FROM TAMENGLONG TO MAHUR (NH-137) I | NHIDCL | N24001969 | 3-2023 | 8/2025 | N.A. | 8/2025 | 904.04 | N.A. | 904.04 | 409.15 | 68.26
154 | ASSAM | RAILWAYS | WIDENING AND UPGRADATION TO TWO LANES WITH PAVED SHOULDERS ROAD FROM TAMENGLONG TO MAHUR (NH-137) IN | NHIDCL | N24001970 | 3-2023 | 8/2025 | N.A. | 8/2025 | 860.37 | N.A. | 860.37 | 417.17 | 68.60
155 | ASSAM | RAILWAYS | WIDENING AND UPGRADATION TO TWO LANES WITH PAVED SHOULDERS ROAD FROM TAMENGLONG TO MAHUR (NH-137) IN | NHIDCL | N24001971 | 3-2023 | 8/2025 | N.A. | 8/2025 | 890.33 | N.A. | 890.33 | 467.83 | 65.56
156 | ASSAM | RAILWAYS | WIDENING/IMPROVEMENT TO 4-LANE WITH PAVED SHOULDER FROM KM 0+800 (KANDULIJAN GAON) TO KM 27+701 (SI | NHIDCL | N24001972 | 3-2023 | 4/2026 | N.A. | 4/2026 | 609.16 | N.A. | 609.16 | 323.24 | 98.48
157 | ASSAM | RAILWAYS | WIDENING/IMPROVEMENT TO 4-LANE WITH PAVED SHOULDER FROM KM 27+701 (SIMEN CHAPORI) TO KM 55+000 (NAG | NHIDCL | N24001973 | 3-2023 | 2/2026 | N.A. | 2/2026 | 562.05 | N.A. | 562.05 | 303.89 | 99.06
158 | ASSAM | RAILWAYS | BILASIPURA-GUWAHATI ROAD PKG-8 | NHIDCL | N24002021 | 3-2023 | 12/2026 | N.A. | 12/2026 | 1,457.59 | N.A. | 1,457.59 | 551.88 | 47.50
159 | ASSAM | RAILWAYS | BILASIPURA-GUWAHATI ROAD PKG-9 | NHIDCL | N24002022 | 3-2023 | 6/2026 | N.A. | 6/2026 | 1,000.27 | N.A. | 1,000.27 | 308.11 | 29.01
160 | ASSAM | RAILWAYS | BILASIPURA-GUWAHATI ROAD PKG-10 | NHIDCL | N24002023 | 3-2023 | 6/2026 | N.A. | 6/2026 | 1,264.90 | N.A. | 1,264.90 | 425.17 | 27.99
161 | ASSAM | RAILWAYS | DABOKA BYPASS OF DABOKA - PAROKHAOWA PKG -1 | NHIDCL | N24002024 | 1-2023 | 11/2025 | N.A. | 11/2025 | 516.88 | N.A. | 516.88 | 242.92 | 75.51
162 | ASSAM | RAILWAYS | 2 LANE WITH PAVED SHOULDER FROM KM 16+900 (BOGAPANI) TO KM 27+150 (GOLAI GAON) ON EXISTING DIBRUGARH | NHIDCL | N24002025 | 1-2023 | 12/2025 | N.A. | 12/2026 | 356.65 | N.A. | 356.65 | 134.02 | 18.15
163 | ASSAM | RAILWAYS | DEVELOPMENT OF EXTERNAL TRUNK CONNECTIVITY AND INTERNAL INFRASTRUCTURE WORKS AT MULTI MODEL LOGISTIC | NHIDCL | N24002030 | 2-2020 | 3/2022 | N.A. | 9/2024 | 592.06 | N.A. | 592.06 | 308.87 | 100.00
164 | ASSAM | RAILWAYS | SILCHAR VAIRENGTE SAIRANG ROAD PKG-1 | NHIDCL | N24002127 | 2-2023 | 7/2026 | N.A. | 7/2026 | 1,256.90 | N.A. | 1,256.90 | 539.19 | 40.36
165 | ASSAM | RAILWAYS | SILCHAR VAIRENGTE SAIRANG ROAD PKG-2 | NHIDCL | N24002128 | 3-2023 | 8/2026 | N.A. | 8/2026 | 1,716.21 | N.A. | 1,716.21 | 989.94 | 64.56
166 | ASSAM | RAILWAYS | FOUR LANNING OF BADARPUR BYPASS FROM DESIGN CHAINAGE KM 27+300 AT CROSSING WITH NH-6 | NHIDCL | N24002129 | 2-2023 | 8/2026 | N.A. | 8/2026 | 574.26 | N.A. | 574.26 | 297.70 | 54.97
167 | ASSAM | RAILWAYS | TAMENGLONG- MAHUR ROAD PKG-7 | NHIDCL | N24002130 | 12-2023 | 3/2026 | N.A. | 3/2026 | 846.82 | N.A. | 846.82 | 407.11 | 68.95
168 | ASSAM | RAILWAYS | CONSTRUCTION OF 4-LANE PANCHGRAM BYPASS FROM DESIGN CHAINAGE KM 15+500 ON NH-37 (OLD NH-53) AT KALIN | NHIDCL | N24002154 | 3-2023 | 2/2027 | N.A. | 2/2027 | 728.97 | N.A. | 728.97 | 290.90 | 43.16
169 | ASSAM | RAILWAYS | WIDENING/IMPROVEMENT TO 4-LANE WITH PAVED SHOULDER FROM KM 55+000 (NAGABANG GAMSUK) TO KM 82+514 (OY | NHIDCL | N24002155 | 3-2023 | 3/2027 | N.A. | 3/2027 | 665.47 | N.A. | 665.47 | 213.67 | 50.88
170 | ASSAM | RAILWAYS | BILASIPURA- GUWAHATI ROAD PKG-1 | NHIDCL | N24002225 | 2-2024 | 8/2027 | N.A. | 8/2027 | 1,081.15 | N.A. | 1,081.15 | 33.93 | 2.76
171 | ASSAM | RAILWAYS | SILCHAR-JIRIBAM PKG-1 | NHIDCL | N24002226 | 1-2024 | 1/2028 | N.A. | 1/2028 | 957.95 | N.A. | 957.95 | 0.00 | 21.98
172 | ASSAM | RAILWAYS | BILASIPURA- GUWAHATI ROAD PKG-2 | NHIDCL | N24002229 | 11-2023 | 6/2027 | N.A. | 6/2027 | 1,338.61 | N.A. | 1,338.61 | 0.50 | -
173 | ASSAM | RAILWAYS | BADARPUR ? CHURAIBARI PKG-6 | NHIDCL | N24002230 | 3-2024 | 3/2027 | N.A. | 3/2027 | 870.00 | N.A. | 870.00 | 0.00 | 5.86
174 | ASSAM | RAILWAYS | KARIMGANI - SUTARKANDI SECTION ON SILCHAR-CHURAIBARI PKG-7 | NHIDCL | N24002231 | 2-2024 | 2/2027 | N.A. | 2/2027 | 791.79 | N.A. | 791.79 | 0.00 | 1.02
175 | ASSAM | RAILWAYS | CONSTRUCTION OF 4 LANE GAURIPUR BYPASS ON NH-17 IN THE STATE OF ASSAM | MoRTH | N24002237 | 3-2024 | 10/2026 | N.A. | 10/2026 | 421.15 | N.A. | 421.15 | 0.00 | -
176 | ASSAM | RAILWAYS | CONSTRUCTION OF 2 LANE BARPETA BYPASS FROM KM 77+900(BARADI) TO KM 86+150( DEURIKUCHI) (LENGTH=8.25K | MoRTH | N24002238 | 3-2023 | 8/2026 | N.A. | 8/2026 | 173.65 | N.A. | 173.65 | 0.00 | -
177 | ASSAM | RAILWAYS | SILCHAR- CHURAIBARI PKG-5 | NHIDCL | N24002243 | 2-2024 | 10/2027 | N.A. | 10/2027 | 1,258.13 | N.A. | 1,258.13 | 0.00 | -
178 | ASSAM | RAILWAYS | 4 LANING OF JORHAT TO JHANJI SECTION FROM KM. 453.00 TO KM. 491.08 (DESIGN KM 403.200 TO KM 454.240) | NHIDCL | N24000319 | 6-2015 | 8/2023 | N.A. | 7/2025 | 437.39 | N.A. | 437.39 | 586.89 | 97.43
179 | ASSAM | RAILWAYS | FOUR LANING OF JHANJHI JN TO DEMOW SECTION FROM KM. 491.050 TO KM. 535.250(DESIGN KM 490.800 TO KM 5 | NHIDCL | N24000320 | 6-2015 | 3/2024 | N.A. | 10/2025 | 463.49 | N.A. | 463.49 | 517.62 | 78.19
180 | ASSAM | RAILWAYS | 4 LANING FROM JAMUGURI TO BISWANATH CHARIALI FROM KM 182 TO KM 208 OF NH-52 | NHIDCL | N24000431 | 1-1991 | 6/2019 | Jun-2019 | 7/2025 | 520.01 | N.A. | 520.01 | 306.13 | 98.42
181 | ASSAM | RAILWAYS | 4 LANING FROM RANGAGARA TO KALIABHOR TINALI FROM KM 297.00 TO KM 315.315 OF NH-37 ON EPC BASIS. | NHIDCL | N24000438 | 12-2015 | 12/2018 | Jul-2021 | 12/2025 | 289.99 | N.A. | 289.99 | 233.23 | 88.03
182 | ASSAM | RAILWAYS | 4 LANING OF NH-37 SECTION BETWEEN DEMOW TO END OF MORAN BYPASS (FROM KM. 534.800 TO KM. 561.700) O | NHIDCL | N24000582 | 1-2016 | 1/2016 | N.A. | 7/2025 | 294.17 | N.A. | 294.17 | 396.49 | 98.40
183 | ASSAM | RAILWAYS | 4 LANING OF NH 37 SECTION BETWEEN END OF MORAN BYPASS TO BOGIBEEL JUNCTION NEAR LAPETKETA (KM. 561 | NHIDCL | N24000583 | 1-2016 | 12/2021 | N.A. | 7/2025 | 252.00 | N.A. | 330.30 | 242.97 | 95.42
184 | ASSAM | RAILWAYS | 4-LANING OF HAPACHARA - TULUNGIA SECTION | NHIDCL | N24001246 | 3-2020 | 12/2022 | N.A. | 6/2024 | 220.20 | N.A. | 220.20 | 217.31 | 97.76
185 | ASSAM | RAILWAYS | 2-LANING OF CHURACHANDPUR TUIVAI SECTION OF NH-102B (PKG- IB) | NHIDCL | N24001269 | 3-2020 | 3/2022 | Jun-2025 | 8/2025 | 216.49 | 241.52 | 216.49 | 114.38 | 87.02
186 | ASSAM | RAILWAYS | 4-L DHUBRI PHULBARI BRIDGE WITH APPROACH ROAD | NHIDCL | N24001326 | 11-2020 | 9/2028 | N.A. | 9/2028 | 4,997.04 | N.A. | 4,997.04 | 2,464.49 | 62.82
187 | ASSAM | RAILWAYS | 2-LANING FROM YAINGANGPOKPI TO FINCH CORNER (PKG-I) | NHIDCL | N24001331 | 3-2020 | 6/2022 | May-2025 | 12/2025 | 261.13 | N.A. | 261.13 | 70.08 | 57.50
188 | ASSAM | RAILWAYS | 2-LANING FROM YAINGANGPOKPI TO FINCH CORNER (PKG-II) | NHIDCL | N24001332 | 3-2020 | 6/2022 | Apr-2025 | 12/2025 | 217.50 | N.A. | 217.50 | 89.21 | 68.03
189 | ASSAM | RAILWAYS | DABOKA KATHKATI PACKAGE-5 | NHIDCL | N24001366 | 3-2021 | 1/2023 | N.A. | 11/2024 | 288.85 | N.A. | 288.85 | 247.78 | 100.00
190 | ASSAM | RAILWAYS | TULUNGIA-JOGIGHOPA-PAIKAN ROAD PKG-7 | NHIDCL | N24001368 | 3-2021 | 1/2024 | N.A. | 10/2025 | 286.72 | N.A. | 286.72 | 159.30 | 82.90
191 | ASSAM | RAILWAYS | CONSTRUCTION OF 2-LANE MAJOR BRIDGE INCLUDING APPROACHESOVER BRAHMAPUTRA BETWEEN MAJULI ON NORTH BAN | MoRTH | N24001408 | 2-2021 | 7/2025 | N.A. | 7/2025 | 925.47 | 1,019.17 | 925.47 | 192.50 | 30.65
192 | BIHAR | CIVIL AVIATION | CONSTRUCTION OF NEW DORNESTIC TERMINAL BUILDING AND OTHER STRUCTURES, PHASE I AND II | AAI | N04000082 | 5-2018 | 10/2022 | Nov-2025 | 11/2025 | 1,216.90 | N.A. | 1,216.90 | 1,029.05 | 93.14
193 | BIHAR | CIVIL AVIATION | DARBHANGA:DEVELOPMENT OF NEW CIVIL ENCLAVE AT DARBHANGA, BIHAR. SH- CONSTRUCTION OF NEW TERMINAL BUI | AAI | N04000112 | 7-2024 | 7/2026 | N.A. | 7/2026 | 911.66 | N.A. | 911.66 | 113.58 | 20.75
194 | BIHAR | DEPARTMENT OF HIGHER EDUCATION | CONSTRUCTION OF ACADEMIC AND RESIDENTIAL COMPLEX UNDER PHASE-II FOR THE CAMPUS OF IIT PATNA | CPWD EDUCATION | N28000100 | 2-2016 | 6/2017 | N.A. | 1/2024 | 496.18 | 496.00 | 460.00 | 390.15 | 100.00
195 | BIHAR | DEPARTMENT OF HIGHER EDUCATION | PERMANENT CAMPUS FOR IIM BODH GAYA | CPWD EDUCATION | N42000009 | 9-2018 | 9/2020 | N.A. | 3/2025 | 375.00 | N.A. | 375.00 | 342.18 | 100.00
196 | BIHAR | PETROLEUM | BARAUNI REFINERY CAPACITY EXPANSION FROM 6.0 TO 9.0 MMTPA | IOCL | N16000386 | 1-2020 | 4/2023 | Aug-2026 | 8/2026 | 14,810.00 | 18,113.00 | 18,113.00 | 11,055.42 | 89.00
197 | BIHAR | PETROLEUM | CGD PROJECT AT KHAGARIA, SAHARSA AND MADHEPURA | IOCL | N16000423 | 6-2019 | 12/2029 | Mar-2030 | 3/2030 | 163.00 | N.A. | 163.00 | 96.08 | 40.10
198 | BIHAR | PETROLEUM | INSTALLATION OF BITUMEN MANUFACTURING UNIT ALONG WITH ALLIED FACILITIES AT BARAUNI | IOCL | N16000453 | 1-2022 | 4/2025 | N.A. | 5/2026 | 389.00 | N.A. | 389.00 | 38.25 | 35.40
199 | BIHAR | PETROLEUM | CITY GAS DISTRIBUTION PROJECTS AT GOPALGANJ SIWAN WEST CHAMPARAN EAST CHAMPARAN AND DEORIA DISTRICTS | BPCL | N16000523 | 12-2022 | 6/2030 | N.A. | 6/2030 | 3,919.00 | N.A. | 3,919.00 | 382.99 | 13.60
200 | BIHAR | PETROLEUM | CITY GAS DISTRIBUTION PROJECTS AT DARBHANGA, MADHUBANI, SUPAUL, SITAMARHI AND SHEOHAR DISTRICTS | BPCL | N16000524 | 12-2022 | 3/2030 | N.A. | 3/2030 | 3,638.00 | N.A. | 3,638.00 | 390.34 | 20.80
201 | BIHAR | PETROLEUM | BARH STPP(3X660MW) NTPC | NTPC | 180100242 | 2-2005 | 10/2011 | Jul-2023 | 3/2025 | 8,692.97 | 21,312.11 | 21,312.11 | 22,561.37 | 95.00
202 | BIHAR | PETROLEUM | BUXAR THERMAL POWER PLANT (1320 MW) | SJVN | N18000194 | 3-2019 | 1/2024 | N.A. | 10/2025 | 10,439.09 | N.A. | 14,390.09 | 11,845.16 | 91.56
203 | BIHAR | PETROLEUM | EASTERN REGION EXPANSION SCHEME: 43 [ERES: 43] | PGCIL | N18000421 | 5-2025 | 5/2026 | N.A. | 5/2026 | 343.00 | N.A. | 343.00 | 0.00 | -
204 | BIHAR | PETROLEUM | EASTERN REGION EXPANSION SCHEME: 44 [ERES: 44] | PGCIL | N18000422 | 5-2025 | 5/2026 | N.A. | 5/2026 | 409.00 | N.A. | 409.00 | 0.00 | -
205 | BIHAR | PETROLEUM | KHAGARIA-KUSHESHWAR ASTHAN (NL) (ECR) | ECR | 220100257 | 4-1997 | 12/2024 | N.A. | 3/2027 | 614.45 | 614.45 | 614.45 | 483.57 | 52.00
206 | BIHAR | PETROLEUM | HAJIPUR-SUGAULI VIA VAISHALI (NL), ECR | ECR | 220100303 | 4-2003 | 12/2014 | N.A. | 12/2026 | 2,066.78 | 2,087.36 | 2,087.36 | 2,454.59 | 73.00
207 | BIHAR | PETROLEUM | NEW B.G. LINE FROM ARARIA TO GALGALIA (THAKURGUNG), NEFR | NFR | N22000087 | 9-2006 | 12/2024 | N.A. | 6/2025 | 2,650.00 | 2,132.03 | 4,351.54 | 4,074.75 | 92.00
208 | BIHAR | PETROLEUM | SAKRI-HASANPUR ROAD (NL) | ECR | N22000171 | 4-1999 | (N.A.) | 3/2027 |  | 325.00 | 735.20 | 735.20 | 604.94 | 78.00
209 | BIHAR | PETROLEUM | ARARIA-SUPAUL (NL) | ECR | N22000177 | 4-2008 | 3/2024 | N.A. | 5/2025 | 1,605.17 | 1,605.17 | 1,605.17 | 1,749.92 | 65.00
210 | BIHAR | PETROLEUM | JAYNAGAR-BIJALPURA INCLUDING EXTENSION BIJALPURA- BARDIBAS(NEPAL) GC | ECR | N22000181 | 4-2009 | 3/2022 | N.A. | 3/2026 | 819.00 | 548.00 | 783.83 | 566.62 | 75.00
211 | BIHAR | PETROLEUM | SAMASTIPUR-DARBANGHA | ECR | N22000329 | 5-2015 | 3/2025 | N.A. | 10/2025 | 519.33 | 519.33 | 519.33 | 651.94 | 80.00
212 | BIHAR | PETROLEUM | KIUL - GAYA DOUBLING PROJECT | ECR | N22000349 | 12-2015 | 9/2024 | N.A. | 2/2025 | 2,462.11 | 1,200.20 | 1,771.07 | 1,896.91 | 99.00
213 | BIHAR | PETROLEUM | RAMPUR DUMRA - TAL - RAJENDRAPUL DOUBLING INCLUDING GANGA BRIDGE | ECR | N22000350 | 12-2015 | 12/2024 | N.A. | 12/2025 | 2,373.64 | 1,491.47 | 1,600.00 | 1,776.70 | 77.00
214 | BIHAR | PETROLEUM | SAGAULI VALMIKINAGAR DOUBLING 109.7 KM | ECR | N22000472 | 4-2016 | 12/2024 | N.A. | 6/2025 | 1,215.54 | 1,215.54 | 1,215.54 | 1,595.74 | 91.00
215 | BIHAR | PETROLEUM | MUZAFFARPUR SAGAULI DOUBLING 100.60 KM | ECR | N22000473 | 4-2016 | 6/2024 | N.A. | 5/2025 | 1,586.22 | 1,185.73 | 1,300.00 | 1,487.54 | 96.00
216 | BIHAR | PETROLEUM | FATUHA-ISLAMPUR INCL. MM FOR EXTENSION OF NEW LINE FORM BIHARSHARIF-BARBIGHA, DANIYAWAN- BIHARSHARIF, | ECR | N22000476 | 4-1991 | 3/2023 | N.A. | 5/2025 | 1,473.30 | 803.09 | 2,722.16 | 2,794.05 | 90.00
217 | BIHAR | PETROLEUM | BARAUNI- BACHWARA 3RD AND 4TH LINE | ECR | N22000524 | 7-2022 | 7/2027 | N.A. | 12/2025 | 486.00 | N.A. | 486.00 | 135.31 | 33.00
218 | BIHAR | PETROLEUM | JHAJHA - BATIA (UMBRELLA WORK PB#23/2018-19/NR) | ECR | N22000526 | 2-2019 | 6/2028 | N.A. | 12/2026 | 496.47 | N.A. | 496.47 | 22.55 | -
219 | BIHAR | PETROLEUM | SONENAGAR BYE PASS LINE FROM CHIRALAPOTHU TO BAGHA BISHUNPUR | ECR | N22000528 | 10-2022 | 10/2027 | N.A. | 12/2026 | 234.00 | 223.69 | 223.69 | 22.57 | -
220 | BIHAR | PETROLEUM | KATIHAR-KUMEDPUR AND KATIHAR- MUKURIA (64.5 KM) (UMBRELLA WORK PB#57/2019-20/NR) | NFR | N22000570 | 8-2022 | 8/2027 | N.A. | 8/2026 | 745.00 | N.A. | 1,500.00 | 356.14 | 35.00
221 | BIHAR | PETROLEUM | 4L GREENFIELD ALIGNMENT FROM KALYANAPUR TO TAL DASHRAHA OF NH-119D (PKG-III) | NHAI | N24001697 | 2-2023 | 2/2025 | N.A. | 12/2025 | 1,358.00 | N.A. | 1,358.00 | 228.72 | 22.00
222 | BIHAR | PETROLEUM | FOUR LANING OF MUNGER TO MIRZACHAUKI (NH-80) SECTION FROM NEAR RASULPUR TO MIRZACHAUKI (DESIGN CH | NHAI | N24001698 | 8-2022 | 8/2024 | Dec-2025 | 12/2025 | 1,198.02 | N.A. | 1,198.02 | 43.77 | -
223 | BIHAR | PETROLEUM | CONSTRUCTION OF 4 LANE ELEVATED SECTION AND AT- GRADE IMPROVEMENTS AT BEGUSARAI TOWN SECTION OF NH-3 | NHAI | N24001699 | 3-2022 | 12/2024 | Dec-2025 | 12/2025 | 312.58 | N.A. | 312.58 | 205.99 | 85.88
224 | BIHAR | PETROLEUM | SIX LANNING OF AURANGABAD TO BIHAR/JHARKHAND BORDER SECTION OF NH-19 (OLD NH-2) FROM KM. 209.827 TO | NHAI | N24001700 | 12-2021 | 3/2024 | Dec-2024 | 12/2024 | 552.55 | 553.00 | 553.00 | 378.25 | 86.60
225 | BIHAR | PETROLEUM | FOUR LANING OF MUNGER TO MIRZACHAUKI (NH-80) SECTION FROM START OF EXISTING BHAGALPUR BYPASS TO RASU | NHAI | N24001701 | 4-2022 | 4/2024 | Sep-2025 | 9/2025 | 1,769.50 | N.A. | 1,769.50 | 69.23 | -
226 | BIHAR | PETROLEUM | CONSTRUCTION OF 4 LANE ELEVATED HIGHWAY AND AT-GRADE IMPROVEMENTS AT GOPALGANJ TOWN FROM DESIGN CH: | NHAI | N24001702 | 12-2021 | 9/2024 | N.A. | 6/2025 | 184.90 | 185.00 | 185.00 | 166.56 | 99.78
227 | BIHAR | PETROLEUM | 6 L OF AURANGABAD TO BIHAR- JHARKHAND BORDER (CHORDAHA) SECTION FROM KM. 180.000 TO KM. 209.827 OF N | NHAI | N24001703 | 2-2022 | 5/2025 | N.A. | 5/2025 | 786.81 | 787.00 | 787.00 | 0.00 | 8.30
228 | BIHAR | PETROLEUM | FOUR LANING OF MUNGER TO MIRZACHAUKI (NH-80) SECTION FROM KHARIA VILLAGE JUNCTION TO START OF EXISTI | NHAI | N24001704 | 3-2021 | 3/2024 | Sep-2025 | 9/2025 | 1,020.84 | N.A. | 1,020.84 | 163.19 | -
229 | BIHAR | PETROLEUM | FOUR LANING OF MUNGER TO MIRZACHAUKI (NH-80) SECTION FROM MUNGER TO KHARIA VILLAGE JUNCTION DESIGN C | NHAI | N24001705 | 3-2022 | 3/2024 | Dec-2025 | 12/2025 | 1,485.66 | N.A. | 1,485.66 | 35.16 | -
230 | BIHAR | PETROLEUM | BAKHTIYARPUR RAJAULI PKG-II FROM KM 54.405 TO KM 101.630 NH20 | NHAI | N24001709 | 9-2020 | 4/2023 | Dec-2024 | 12/2024 | 897.45 | N.A. | 1,090.00 | 1,037.63 | 97.85
231 | BIHAR | PETROLEUM | FOUR LANING OF PARARIA TO MOHANIA SECTION OF NH 319 (OLD NH 30) FROM KM. 54+530 (DESIGN CHAINAGE) TO | NHAI | N24001712 | 8-2020 | 7/2023 | May-2025 | 5/2025 | 690.00 | N.A. | 690.00 | 770.73 | 98.90
232 | BIHAR | PETROLEUM | BALANCE WORK OF TWO LANING WITH PAVED SHOULDER OF PIPRAKOTHI?MOTIHARI- RAXAUL SECTION OF NH-28A FRO | NHAI | N24001715 | 12-2018 | 10/2020 | N.A. | 1/2024 | 333.60 | 466.59 | 461.41 | 460.38 | 100.00
233 | BIHAR | PETROLEUM | IMPROVEMENT TO TWO LANE WITH PAVED SHOULDERS OF NH 122B FROM KM 29.730 TO KM 72.348 IN STATE OF BIH | MoRTH | N24001870 | 2-2022 | 11/2024 | N.A. | 11/2025 | 624.43 | N.A. | 624.43 | 292.16 | 88.00
234 | BIHAR | PETROLEUM | WIDENING AND STRENTHENING FROM KM 70.15 TO KM 121.025 OF NH-80 | MoRTH | N24001875 | 3-2021 | 1/2025 | N.A. | 7/2025 | 477.54 | N.A. | 477.54 | 360.27 | 94.50
235 | BIHAR | PETROLEUM | WIDENING and STRENTHENING FROM KM132.895 TO KM 190.15 NH-80 | MoRTH | N24001876 | 3-2021 | 3/2024 | N.A. | 9/2025 | 566.15 | N.A. | 566.15 | 258.29 | 58.60
236 | BIHAR | PETROLEUM | CONSTRUCTION OF NEW 4-LANE BRIDGE (PARALLEL TO EXISTING VIKRAMASHILA SETU)FROM KM 8+920 TO KM 13+375 | MoRTH | N24001877 | 7-2020 | 5/2027 | N.A. | 5/2027 | 1,110.23 | N.A. | 1,110.23 | 478.96 | 42.90
237 | BIHAR | PETROLEUM | IMPROVEMENT TO TWO LANE WITH PAVED SHOULDERS OF NH-319A FROM KM 0 TO KM 45 IN STATE OF BIHAR UNDER | MoRTH | N24001878 | 2-2022 | 12/2024 | N.A. | 7/2025 | 427.29 | N.A. | 427.29 | 210.22 | 80.00
238 | BIHAR | PETROLEUM | CONSTRUCTION OF PROPOSED 4_LANE REVELGUNJ BYPASS NH-19 IN THE STATE OF BIHAR ON EPC MODE CONNECTING | MoRTH | N24001879 | 3-2022 | 7/2025 | N.A. | 10/2025 | 295.24 | N.A. | 295.24 | 93.14 | 63.05
239 | BIHAR | PETROLEUM | CONSTRUCTION OF 6- LANE BRIDGE AND ITS APPROACHES ACROSS RIVER GANGA AS PART OF PATNA RING ROAD (NH- | NHAI | N24002062 | 3-2023 | 9/2027 | N.A. | 9/2028 | 3,012.27 | N.A. | 3,012.27 | 303.67 | 10.83
240 | BIHAR | PETROLEUM | BALANCE WORK - WB-10 (GANDAK BRIDGE) KM 402.00 TO KM 440.00 (DEVANPUR - KOTWA) | NHAI | N24002063 | 12-2021 | 1/2024 | N.A. | 3/2026 | 210.05 | N.A. | 210.05 | 104.35 | 69.00
241 | BIHAR | PETROLEUM | PERMANENT RECTIFICATION OF 3 NOS. OF BLACK SPOTS IN PROJECT HIGHWAY NH-27 OF U.P BORDER - DEWAPUR - | NHAI | N24002064 | 12-2022 | 12/2025 | N.A. | 12/2025 | 381.80 | N.A. | 381.80 | 119.56 | 52.00
242 | BIHAR | PETROLEUM | 4L GREENFIELD ALIGNMENT OF AMAS TO SHIVRAMPUR FROM 0.000 KM. TO 55.002 KM. OF NH 119 D (PKG-I) | NHAI | N24002065 | 2-2022 | 3/2025 | N.A. | 3/2025 | 1,390.92 | N.A. | 1,390.92 | 17.54 | 22.56
243 | BIHAR | PETROLEUM | 4L GREENFIELD ALIGNMENT OF SHIVRAMPUR TO RAMNAGAR FROM KM. 55.002 TO KM. 109.300 OF NH 119 D (PKG-I | NHAI | N24002066 | 2-2022 | 7/2025 | N.A. | 7/2025 | 1,494.31 | N.A. | 1,494.31 | 38.28 | 4.59
244 | BIHAR | PETROLEUM | IMPROVEMENT OF 2 LANE WITH PAVED SHOULDER OF STRETCH FROM BIKRAMGANJ DAWATH MELAYABAGH NAWANAGR -DUM | MoRTH | N24002133 | 3-2021 | 3/2025 | N.A. | 8/2025 | 178.63 | N.A. | 178.63 | 124.52 | 96.00
245 | BIHAR | PETROLEUM | CONSTRUCTION OF 4 LANE ROB AND ITS APPROACHES AT THE LEVEL OF CROSSING (L C NO. 29-B) OF KM 29 (EKAN | MoRTH | N24002193 | 3-2023 | 7/2026 | N.A. | 7/2026 | 201.08 | N.A. | 201.08 | 25.42 | 28.00
246 | BIHAR | PETROLEUM | CONSTRUCTION OF 6-LANE ELEVATED / EXTRA DOSE CABLE BRIDGE ON RIVER GANGA PARALLEL TO AND WESTERN SID | MoRTH | N24002194 | 1-2024 | 11/2027 | N.A. | 11/2027 | 3,064.45 | N.A. | 3,064.45 | 142.38 | 5.19
247 | BIHAR | PETROLEUM | ESTIMATE FOR IMPROVEMENT TO TWO LANE WITH PAVED SHOULDER FROM RAMNAGAR TO ROSEDA FROM (KM 3.500 TO 4 | MoRTH | N24002195 | 1-2022 | 4/2026 | N.A. | 4/2026 | 495.16 | N.A. | 495.16 | 134.57 | 11.50
248 | BIHAR | PETROLEUM | CONSTRUCTION OF BHABHUA BYPASS FROM CH. 10+800(DESIGN CH. 10+800) TO CH. 19+860 (DESIGN CH. 18+150) | MoRTH | N24002196 | 2-2022 | 3/2026 | N.A. | 7/2026 | 179.86 | N.A. | 179.86 | 26.15 | -
249 | BIHAR | PETROLEUM | IMPROVEMENT TO TWO LANE WITH PAVED SHOULDER FROM JUNCTION OF NH-22 NEAR HAJIPUR TO JUNCTION OF NH-12 | MoRTH | N24002197 | 2-2024 | 2/2026 | N.A. | 2/2026 | 226.15 | N.A. | 226.15 | 14.44 | 20.00
250 | BIHAR | PETROLEUM | IMPROVEMENT TO TWO LANE WITH PAVED SHOULDERS OF BH/WBBORDER-AMDABAD-MANIHARI SECTION FROM DESIGN KM | MoRTH | N24002198 | 1-2022 | 3/2026 | N.A. | 3/2026 | 353.27 | N.A. | 353.27 | 29.82 | 2.50
251 | BIHAR | PETROLEUM | PERMANENT RECTIFICATION OF 4 NOS. OF BLACKSPOTS ON NH 27 OF KOTWA MEHSI MUZAFFARPUR SECTION FROM | NHAI | N24002220 | 12-2022 | 11/2026 | N.A. | 11/2026 | 410.75 | N.A. | 410.75 | 50.64 | 26.20
252 | BIHAR | PETROLEUM | 4L OF GREENFIELD ALIGNMENT FROM KM. 47.000 TO KM. 89.210 OF BALBHADARPUR TO BELA NAWDA SECTION OF NH | NHAI | N24002221 | 2-2022 | 3/2026 | N.A. | 3/2026 | 2,185.75 | N.A. | 2,185.75 | 595.71 | 12.84
253 | BIHAR | PETROLEUM | PATNA-MUZZAFFARPUR | NHAI | N24000165 | 8-2010 | 2/2013 | N.A. | 6/2025 | 671.30 | N.A. | 671.30 | 1,830.13 | 98.87
254 | BIHAR | PETROLEUM | 4-LANNING OF CHAPRA-HAJIPUR | NHAI | N24000187 | 1-2011 | 7/2013 | Jan-2026 | 1/2026 | 575.00 | N.A. | 575.00 | 573.48 | 89.81
255 | BIHAR | PETROLEUM | REHABILITATION AND UPGRADING TO 2 LANES/2 LANE WITH PAVED SHOULDERS CONFIGURATION OF BIRPUR - BIHPUR | MoRTH | N24000382 | 1-2014 | 10/2019 | Aug-2025 | 8/2025 | 675.00 | N.A. | 780.77 | 764.76 | 97.50
256 | BIHAR | PETROLEUM | FOUR OF SIMARIA - KHAGARIA SECTION OF NH-31 | NHAI | N24000480 | 12-2015 | 4/2019 | Mar-2025 | 11/2025 | 1,041.10 | 567.00 | 639.58 | 553.73 | 97.68
257 | BIHAR | PETROLEUM | FOUR LANING OF BAKHTIYARPUR - MOKAMA SECTION OF NH-31 | NHAI | N24000507 | 12-2015 | 12/2019 | N.A. | 8/2025 | 1,167.45 | N.A. | 1,182.94 | 775.79 | 99.43
258 | BIHAR | PETROLEUM | REHABILITATION AND UPGRADING TO 2 LANES/2 LANE WITH PAVED SHOULDERS (KM 40 TO KM 219.945) OF NH-104 | MoRTH | N24000531 | 2-2016 | 11/2018 | N.A. | 8/2025 | 319.68 | N.A. | 503.28 | 453.00 | 98.80
259 | BIHAR | PETROLEUM | CONSTRUCTION OF REHABILITATION AND UPGRADING TO 2 LANES/2 LANE(FOR LOT-I-KM 40.00 TO KM 65.400 AND K | MoRTH | N24000576 | 2-2016 | 5/2016 | N.A. | 8/2025 | 178.85 | N.A. | 278.54 | 232.61 | 98.35
260 | BIHAR | PETROLEUM | PROCUREMENT, AND CONSTRUCTION OF REHABILITATION AND UPGRADING TO 2 LANES/2 LANE(FOR LOT-III-KM 156.5 | MoRTH | N24000578 | 2-2016 | 5/2016 | N.A. | 8/2025 | 553.30 | N.A. | 706.39 | 712.38 | 98.00
261 | BIHAR | PETROLEUM | FOUR LANING OF GAYA-HISUA- RAJGIRI-NALANDA-BIHARSHARIF SECTION (KM0.00 TO 92.935) ON NH-82 IN BIHAR | MoRTH | N24000579 | 1-2014 | 10/2016 | N.A. | 8/2025 | 1,408.85 | N.A. | 2,138.16 | 1,739.19 | 97.00
262 | BIHAR | PETROLEUM | TWO-LANNING WITH PAVED SHOULDER OF MAHSHKUNT-SAHARSA- PURNEA SECTION FROM EXISTING KM.89.020 (DESIGN | NHAI | N24000665 | 3-2017 | 3/2020 | Dec-2025 | 12/2025 | 672.89 | 893.92 | 893.92 | 714.74 | 86.71
263 | BIHAR | PETROLEUM | SIX LANNING OF AUNTA- SIMARIA(GANGA BRIDGE WITH APPROACH ROADS) SECTION OF NH- 31 | NHAI | N24000696 | 8-2017 | 2/2022 | Oct-2024 | 8/2025 | 950.64 | 1,161.00 | 1,168.33 | 1,156.29 | 99.56
264 | BIHAR | PETROLEUM | CONSTRUCTION OF NEW LINK (NH- 133B) FROM KM 0/00 (KM 200/87 OF SAHIBANJ BYPASS) IN JHARKHAND TO KM 15 | NHAI | N24000714 | 12-2017 | 10/2024 | Dec-2026 | 12/2026 | 2,598.00 | N.A. | 1,978.01 | 1,427.02 | 77.90
265 | BIHAR | PETROLEUM | REHABILITATION AND UPGRADATION OF TWO LANING OF MAHESHKHUNT - SAHARSA - PURNEA SECTION PKG - I | NHAI | N24000723 | 1-2018 | 12/2021 | Aug-2025 | 12/2025 | 573.70 | 644.50 | 726.99 | 509.99 | 82.51
266 | BIHAR | PETROLEUM | DEVELOPMENT OF NEWLY DECLARED NH-527C FROM MAJHAULI TO CHAROUT SECTION TO 2 LANE WITH PAVED SHOULDER | NHAI | N24000813 | 3-2018 | 11/2021 | Dec-2024 | 8/2025 | 496.20 | 470.18 | 470.18 | 399.41 | 98.50
267 | BIHAR | PETROLEUM | CONSTRUCTION OF A NEW 4 LANE MAJOR BRIDGE ACROSS RIVER KOSI AT PHULAUT INCLUDING RHABILITATION AND | MoRTH | N24000943 | 9-2018 | 6/2024 | N.A. | 5/2026 | 1,478.40 | N.A. | 1,478.40 | 972.42 | 75.15
268 | BIHAR | PETROLEUM | CONSTRUCTION OF A NEW 4 LANE BRIDGE PARALLEL TO EXISTING MG SETU WITH ITS APPROACHES FROM KM 0.00 | MoRTH | N24001201 | 2-2019 | 9/2024 | N.A. | 9/2026 | 2,926.42 | N.A. | 2,926.42 | 1,354.63 | 59.29
269 | BIHAR | PETROLEUM | BALANCE WORK OF 4- LANING OF PATNA-GAYA-DOBHI SECTION (KM. 0.00 TO KM. 127.217) OF NH-83 IN THE STAT | NHAI | N24001303 | 10-2013 | 12/2020 | Dec-2024 | 12/2024 | 649.90 | N.A. | 750.00 | 711.53 | 98.30
270 | BIHAR | PETROLEUM | BALANCE WORK OF 4- LANING OF PATNA-GAYA-DOBHI SECTION (KM. 39.00 TO KM. 83.00) OF NH-83 IN THE STATE | NHAI | N24001304 | 10-2013 | 11/2020 | Dec-2024 | 12/2024 | 446.97 | 598.48 | 740.50 | 638.80 | 96.30
271 | BIHAR | PETROLEUM | BALANCE WORK OF 4- L ANING OF PATNA-GAYA-DOBHI SECTION (KM.83.00 TO KM. 127.217) OF NH-83 IN THE STA | NHAI | N24001305 | 10-2013 | 11/2020 | Dec-2024 | 12/2024 | 464.09 | 605.53 | 765.12 | 698.25 | 97.30
272 | BIHAR | PETROLEUM | CONSTRUCTION OF 2 LANE BRIDGE ACROSS RIVER KOSI WITH APPROACH ROAD FROM BHEJA TO BAKAUR SECTION OF N | NHAI | N24001371 | 10-2019 | 8/2023 | Apr-2026 | 4/2026 | 1,101.99 | N.A. | 1,101.99 | 890.20 | 78.48
273 | BIHAR | URBAN DEVELOPMENT | PATNA METRO RAIL CORPORATION LIMITED | PATNA METRO RAI | N28000148 | 2-2019 | 6/2024 | N.A. | 6/2024 | 13,365.77 | N.A. | 13,925.50 | 3,318.85 | 45.31
274 | BIHAR | URBAN DEVELOPMENT | SEWER NETWORK SPS AND STP BEGUSARAI | BUIDCO | N30000026 | 3-2018 | 7/2021 | Dec-2019 | 4/2025 | 230.06 | N.A. | 230.06 | 261.47 | 97.00
275 | BIHAR | URBAN DEVELOPMENT | I AND D AND STP WORKS FOR BHAGALPUR | BUIDCO | N30000027 | 10-2017 | 9/2020 | Nov-2020 | 9/2025 | 254.13 | 413.29 | 413.29 | 126.67 | 90.00
276 | BIHAR | URBAN DEVELOPMENT | SEWER NETWORKS SPS AND STP HAJIPUR | BUIDCO | N30000035 | 3-2018 | 8/2021 | Mar-2018 | 9/2025 | 305.19 | N.A. | 305.19 | 346.46 | 95.00
277 | BIHAR | URBAN DEVELOPMENT | SEWER NETWORKS, SPS AND STP, MUNGER | BUIDCO | N30000036 | 3-2018 | 10/2021 | Mar-2018 | 6/2024 | 294.02 | 350.79 | 522.85 | 428.70 | 100.00
278 | BIHAR | URBAN DEVELOPMENT | SAIDPUR SEWER NETWORK PATNA | BUIDCO | N30000039 | 4-2015 | 1/2021 | N.A. | 6/2022 | 268.63 | N.A. | 493.85 | 491.13 | 100.00
279 | BIHAR | URBAN DEVELOPMENT | SEWERAGE SYSTEM WITH SEWER NETWORK PATNA KARMALICHAK | BUIDCO | N30000044 | 3-2017 | 5/2021 | Mar-2017 | 2/2023 | 277.42 | 253.98 | 277.42 | 355.31 | 100.00
280 | BIHAR | URBAN DEVELOPMENT | SEWERAGE SYSTEM AND STP FOR KANKARBAG ZONE PATNA | BUIDCO | N30000050 | 8-2017 | 6/2022 | N.A. | 12/2025 | 578.89 | 453.83 | 578.89 | 165.88 | 53.00
281 | BIHAR | URBAN DEVELOPMENT | SEWERAGE SYSTEM AND STP FOR DIGHA ZONE, PATNA | BUIDCO | N30000051 | 8-2017 | 6/2022 | N.A. | 12/2025 | 824.00 | 734.09 | 824.00 | 385.33 | 55.00
282 | CHHATTISGARH | URBAN DEVELOPMENT | GEVRA EXPANSION OCP (SECL) (35-70) MTY | SECL | 060100093 | 6-2010 | 3/2023 | Mar-2026 | 3/2026 | 11,816.40 | N.A. | 11,816.40 | 6,617.04 | 77.20
283 | CHHATTISGARH | URBAN DEVELOPMENT | PELMA OCP(15.00MTY) | SECL | N06000045 | 10-2022 | 3/2023 | N.A. | 3/2033 | 1,624.59 | N.A. | 1,725.04 | 15.53 | 17.00
284 | CHHATTISGARH | URBAN DEVELOPMENT | CHHAL OC SEAM -III (6.00 MTY) | SECL | N06000104 | 12-2013 | 3/2022 | Jun-2025 | 6/2025 | 610.63 | N.A. | 610.63 | 576.48 | 85.00
285 | CHHATTISGARH | URBAN DEVELOPMENT | AMERA OC RCE | SECL | N06000123 | 2-2015 | 3/2018 | Mar-2026 | 3/2026 | 335.97 | N.A. | 335.97 | 87.47 | 42.00
286 | CHHATTISGARH | URBAN DEVELOPMENT | AMGAON OPENCAST PROJECT RCE | SECL | N06000135 | 7-2015 | 3/2020 | Mar-2026 | 3/2026 | 316.10 | N.A. | 316.10 | 188.33 | 71.00
287 | CHHATTISGARH | URBAN DEVELOPMENT | MAHAMAYA OPENCAST PROJECT | SECL | N06000164 | 5-2018 | 3/2026 | N.A. | 3/2026 | 410.26 | N.A. | 410.26 | 180.94 | 38.00
288 | CHHATTISGARH | URBAN DEVELOPMENT | JHIRIA WEST OPENCAST PROJECT | SECL | N06000166 | 1-2024 | 3/2029 | N.A. | 3/2029 | 366.94 | N.A. | 366.94 | 33.67 | 41.00
289 | CHHATTISGARH | URBAN DEVELOPMENT | BAROUD OC EXPANSION (3-10 MTY) | SECL | N06000197 | 8-2020 | 3/2029 | N.A. | 3/2029 | 2,309.80 | N.A. | 2,309.80 | 916.35 | 47.00
290 | CHHATTISGARH | URBAN DEVELOPMENT | JAMPALI OCP RCE | SECL | N06000198 | 5-2020 | 3/2024 | Mar-2025 | 6/2025 | 278.64 | N.A. | 278.64 | 210.90 | 82.00
291 | CHHATTISGARH | URBAN DEVELOPMENT | PORDA CHIMTAPANI OCP (10 MTY) | SECL | N06000199 | 12-2020 | 3/2029 | N.A. | 3/2029 | 2,310.12 | N.A. | 2,310.12 | 83.30 | 10.00
292 | CHHATTISGARH | URBAN DEVELOPMENT | DIPKA OC EXPANSION 40 MTY | SECL | N06000200 | 12-2020 | 3/2029 | N.A. | 3/2029 | 5,241.40 | N.A. | 5,241.40 | 2,821.87 | 37.30
293 | CHHATTISGARH | URBAN DEVELOPMENT | JAGANNATHPUR OC RCE (3.0 MTY) | SECL | N06000232 | 7-2016 | 3/2020 | Mar-2026 | 3/2026 | 459.49 | N.A. | 459.49 | 264.00 | 92.00
294 | CHHATTISGARH | URBAN DEVELOPMENT | KATKONA RO UG PROJECT (1.74 MTY) | SECL | N06000274 | 1-2023 | 3/2029 | N.A. | 3/2029 | 329.22 | N.A. | 329.22 | 60.38 | 2.00
295 | CHHATTISGARH | DEPARTMENT OF HIGHER EDUCATION | C/O PERMANENT CAMPUS OF IIT BHILAI AT KUTHELABHATA, DURG CHHATTISGARH, STAGE I PHASE I. | CPWD EDUCATION | N28000141 | 3-2020 | 7/2022 | Feb-2024 | 3/2024 | 808.62 | 879.22 | 808.62 | 640.70 | 100.00
296 | CHHATTISGARH | POWER | WESTERN REGION EXPANSION SCHEME XXV | PGCIL | N18000350 | 2-2023 | 11/2023 | N.A. | 8/2025 | 385.84 | N.A. | 385.84 | 370.41 | 95.00
297 | CHHATTISGARH | POWER | LARA SUPER THERMAL POWER PROJECT, STAGE-II (2X800 MW) | NTPC | N18000381 | 8-2023 | 6/2028 | N.A. | 6/2028 | 15,530.00 | N.A. | 15,530.00 | 2,124.99 | 6.50
298 | CHHATTISGARH | POWER | KIRANDUL - JAGDALPUR DOUBLING | ECOR | N22000318 | 12-2012 | 3/2020 | N.A. | 3/2024 | 1,588.70 | N.A. | 1,553.11 | 1,534.73 | 94.90
299 | CHHATTISGARH | POWER | JHARSUGUDA-BILASPUR 4TH LINE | SECR | N22000484 | 4-2015 | 10/2024 | Dec-2023 | 12/2025 | 2,140.34 | 2,135.34 | 2,135.34 | 2,306.80 | 88.00
300 | CHHATTISGARH | POWER | KHARSIA DHARAMJAIGARH WITH SPUR LINE EAST CORRIDOR-PHASE I | IRCON | N22000489 | 4-2013 | 9/2018 | N.A. | 3/2026 | 3,055.00 | N.A. | 3,438.39 | 3,117.24 | 93.00
301 | CHHATTISGARH | POWER | Gauge conversion of Raipur(Kendri)- Dhamtari and Abhanpur-Rajim branch (67.20 km) | SECR | N22000572 | 7-2011 | 10/2024 | N.A. | 6/2025 | 1,171.30 | N.A. | 1,171.30 | 617.69 | 82.00
302 | CHHATTISGARH | POWER | NIPANIA-BHATAPRA (14.4 KM) 4TH LINE (PB#72/NR/2022-23) | SECR | N22000573 | 9-2022 | 12/2026 | N.A. | 12/2026 | 170.49 | N.A. | 170.49 | 0.13 | 2.00
303 | CHHATTISGARH | POWER | 4TH LINE - BHATAPARA-HATHBAND (8.8 KM) (PB#72/NR/2022-23) | SECR | N22000574 | 12-2022 | 12/2026 | N.A. | 12/2026 | 177.03 | N.A. | 177.03 | 14.52 | 2.00
304 | CHHATTISGARH | POWER | 4TH LINE - BHILAI-BHILAI NAGAR (8.8 KM) (PB#72/NR/2022-23) | SECR | N22000575 | 9-2022 | 9/2026 | N.A. | 9/2026 | 169.06 | N.A. | 177.34 | 1.72 | 2.00
305 | CHHATTISGARH | POWER | 4TH LINE - DADHAPARA-BELHA (9.2 KM) (PB#72/NR/2022-23) | SECR | N22000576 | 9-2022 | 9/2026 | N.A. | 9/2026 | 169.06 | N.A. | 169.06 | 17.96 | 30.00
306 | CHHATTISGARH | POWER | 4TH LINE - RAJNANDGAON- DONGARHGARH (31.2 KM) (PB#72/NR/2022-23) | SECR | N22000577 | 9-2022 | 9/2026 | N.A. | 9/2026 | 328.34 | N.A. | 328.34 | 38.80 | 20.00
307 | CHHATTISGARH | POWER | 3RD AND 4TH LINE - SARAGBUNDIA AND MADWARANI | SECR | N22000579 | 9-2022 | 9/2026 | N.A. | 9/2026 | 167.64 | N.A. | 167.64 | 0.00 | -
308 | CHHATTISGARH | POWER | DOUBLING OF BORIDAND - AMBIKAPUR ( SURAJPUR) | SECR | N22000580 | 6-2022 | 6/2030 | N.A. | 3/2027 | 1,376.20 | 1,242.94 | 1,242.94 | 217.79 | 12.00
309 | CHHATTISGARH | POWER | DALLIRAJHARA - ROWGHAT (95 KM) {PART OF DALLIRAJHARA-JAGDALPUR (235 KM)} | RVNL | N22000602 | 3-2008 | 6/2025 | N.A. | 6/2025 | 1,627.56 | N.A. | 1,627.56 | 1,349.09 | -
310 | CHHATTISGARH | POWER | CHIRIMIRI-NAGPUR HALT | SECR | N22000616 | 10-2018 | 6/2030 | N.A. | 6/2030 | 241.00 | N.A. | 241.00 | 0.00 | -
311 | CHHATTISGARH | POWER | DEVELOPMENT OF SIX LANE SARGI- BASANWAHI OF NH 130 CD FROM KM.42+800 TO 99+500 UNDER RAIPUR VISAKHAPA | NHAI | N24001588 | 12-2021 | 1/2025 | N.A. | 12/2025 | 1,470.73 | N.A. | 1,470.73 | 700.39 | 83.00
312 | CHHATTISGARH | POWER | DEVELOPMENT OF SIX LANE JHANKI SARGI OF NH 130 CD FROM KM.0+000 TO 42+800 UNDER RAIPUR VISAKHAPATTNA | NHAI | N24001593 | 11-2021 | 9/2024 | N.A. | 4/2026 | 1,368.19 | N.A. | 1,368.19 | 928.78 | 96.50
313 | CHHATTISGARH | POWER | 4 LANE OF BILASPUR TO URGA PROJECT (KM 0.00 TO KM 70.2) OF NH- 130A | NHAI | N24001611 | 4-2020 | 3/2024 | N.A. | 12/2025 | 1,855.59 | 2,523.86 | 2,523.86 | 730.18 | 94.27
314 | CHHATTISGARH | POWER | UP GRADATION OF NH 930 SHERPAR TO KOHKA FROM KM 67.880 TO KM 114.860 TO TWO LANE WITH PAVED SHOULDER | MoRTH | N24001917 | 3-2020 | 5/2024 | N.A. | 6/2025 | 278.97 | N.A. | 278.97 | 206.61 | 87.00
315 | CHHATTISGARH | POWER | UP GRADATION OF NH 130C ABHANPUR TO PAUND FROM NK KM 0.000 TO KM. 40.380 TO TWO LANE WITH PAVED SHOU | MoRTH | N24001919 | 12-2020 | 9/2023 | Feb-2025 | 6/2025 | 193.16 | N.A. | 193.16 | 103.83 | 81.00
316 | CHHATTISGARH | POWER | UPGRADATION OF NH 130A MUNGELI TO PONDI FROM NH KM. 51.600 TO KM. 77.870 KM. 80.970 TO 96.970 TO 2 | MoRTH | N24001920 | 3-2021 | 9/2024 | N.A. | 5/2025 | 218.57 | N.A. | 218.57 | 136.26 | 89.00
317 | CHHATTISGARH | POWER | DEVELOPMENT OF SIX LANE BASANWAHI-MARANGPURI OF NH 130 CD FROM KM.99+500 TO 124+661 UNDER RAIPUR VIS | NHAI | N24002017 | 3-2022 | 10/2025 | N.A. | 9/2026 | 1,307.16 | N.A. | 1,307.16 | 252.68 | 36.23
318 | CHHATTISGARH | POWER | CONSTRUCTION OF 6 LANE DURG RAIPUR ARANG BYPASS PKG 1 SECTION OF NH 53 FROM CH 0.000 TO CH 44.50 | NHAI | N24002045 | 6-2022 | 7/2025 | N.A. | 7/2025 | 1,828.00 | N.A. | 1,828.00 | 575.00 | 47.51
319 | CHHATTISGARH | POWER | CONSTRUCTION OF 6 LANE DURG RAIPUR ARANG BYPASS PKG 2 SECTION OF NH 53 FROM CH 44+500 TO CH.92+230 I | NHAI | N24002046 | 6-2022 | 5/2025 | N.A. | 5/2025 | 1,958.94 | 1,959.00 | 1,958.94 | 725.20 | 40.88
320 | CHHATTISGARH | POWER | REHABILITATION AND UPGRADATION OF NH 43 KANKER TO BEDMA SECTION KM. 130 TO 180 | MoRTH | N24001217 | 1-2016 | 8/2016 | N.A. | 6/2025 | 497.14 | 572.66 | 572.66 | 385.27 | 60.00
321 | CHHATTISGARH | POWER | REHABILITATION AND UPGRADATION OF NH 78 FROM KM 373.505 TO 469.300 AMBIKAPUR TO PATHALGAON SECTION | MoRTH | N24001221 | 1-2016 | 10/2016 | N.A. | 3/2025 | 624.98 | N.A. | 731.50 | 620.67 | 100.00
322 | CHHATTISGARH | POWER | REHABILITATION AND UPGRADATION OF NH 78 FROM KM 469.000 TO 531.000 PATTHALGAON TO KUNKURI | MoRTH | N24001222 | 3-2016 | 7/2016 | N.A. | 12/2025 | 452.94 | N.A. | 435.61 | 322.59 | 70.00
323 | CHHATTISGARH | POWER | CONSTRUCTION OF 4 NOS GRADE SEPARATOR BETWEEN KM. 281.000 TO KM 307.600 KM. 286.400 KUMHARI KM. 299. | MoRTH | N24001227 | 3-2018 | 1/2019 | N.A. | 5/2025 | 349.03 | N.A. | 349.03 | 316.52 | 98.00
324 | CHHATTISGARH | POWER | UPGRADATION AND WIDENING OF BILASPUR TO MUNGELI SECTION NH- 130A | MoRTH | N24001228 | 11-2017 | 5/2019 | N.A. | 5/2025 | 188.80 | N.A. | 188.80 | 136.81 | 97.00
325 | CHHATTISGARH | STEEL | NMDC SLURRY PIPE LINE PROJECT - PHASE-1 | NMDC | N12000124 | 11-2015 | 6/2023 | Jul-2024 | 12/2025 | 2,907.00 | 5,427.06 | 5,427.06 | 2,955.56 | 80.70
326 | CHHATTISGARH | STEEL | SCREENING PLANT-III AT KIRANDUL | NMDC | N12000127 | 3-2021 | 8/2024 | N.A. | 1/2026 | 2,092.97 | 2,718.84 | 2,718.84 | 1,503.52 | 71.31
327 | CHHATTISGARH | STEEL | CONSTRUCTION OF RESIDENTIAL TOWERS AT BIOM KIRANDUL COMPLEX | NMDC | N12000130 | 7-2021 | 11/2024 | N.A. | 12/2025 | 282.44 | 349.75 | 349.75 | 238.99 | 81.86
328 | CHHATTISGARH | STEEL | REPLACEMENT OF CONVERTER VESSELS, TRUNNION RINGS, SUPPORT SYSTEM AND INSTALLATION OF SECONDARY EMISS | SAIL | N12000131 | 10-2023 | 6/2026 | N.A. | 6/2026 | 471.83 | N.A. | 471.83 | 109.38 | 31.06
329 | CHHATTISGARH | STEEL | REBUILDING OF COKE OVEN BATTERY NO.7 AND 8 OF BHILAI STEEL PLANT | SAIL | N12000134 | 11-2023 | 10/2025 | N.A. | 10/2025 | 884.10 | N.A. | 884.10 | 411.94 | 72.24
330 | CHHATTISGARH | STEEL | REPLACEMENT OF HOT LEVELLER-1 OF PLATE MILL AT BHILAI STEEL PLANT | SAIL | N12000137 | 7-2024 | 7/2026 | N.A. | 7/2026 | 198.62 | N.A. | 198.62 | 0.00 | 6.76
331 | CHHATTISGARH | URBAN DEVELOPMENT | CONSTRUCTION729 QUARTERS (TYPE II-180 TYPE III-364 TYPE IV-112 TYPE V- 68 TYPE-VI-5 SHOPS COMMUNI | CPWD | N28000149 | 5-2019 | 9/2020 | Oct-2024 | 10/2024 | 299.97 | 299.97 | 299.97 | 272.05 | 93.00
332 | DELHI | CIVIL AVIATION | CONSTRUCTION OF COMBINED OPERATIONAL OFFICES FOR DGCA, BCAS, AAIB, AERA AND AAI AT SAFDARJUNG AIRPOR | AAI | N04000076 | 11-2016 | 4/2020 | Apr-2024 | 4/2024 | 303.80 | 374.98 | 351.21 | 344.93 | 100.00
333 | DELHI | DPIIT | INDIA INTERNATIONAL CONVENTION AND EXPO CENTRE | IICC FOR DPIIT | N40000002 | 11-2017 | 12/2019 | N.A. | 4/2024 | 4,773.00 | N.A. | 5,401.00 | 4,969.89 | 100.00
334 | DELHI | FINANCE | C/O RESIDENTIAL COMPLEX BUILDING FOR CENTRAL BOARD OF INDIRECT TAXES AND CUSTOMS AT SECTOR-9, DWARKA | NPCC | N07000001 | 7-2018 | 4/2022 | N.A. | 4/2022 | 228.50 | N.A. | 220.27 | 176.28 | 85.00
335 | DELHI | HOME AFFAIRS | ESTABLISHMENT OF CENTRAL ARMED POLICE FORCE INSTITUTE OF MEDICAL SCIENCES(CAPFIMS) AT NEW DELHI | CPWD FOR MHA | N28000071 | 10-2013 | 10/2019 | N.A. | 9/2024 | 1,219.21 | 2,091.53 | 2,091.53 | 1,947.12 | 100.00
336 | DELHI | HOME AFFAIRS | CONSTRUCTION OF HEADQUARTER BUILDING OF CRPF AT LODHI ROAD NEW DELHI | CPWD FOR MHA | N45000002 | 6-2019 | 7/2022 | N.A. | 9/2025 | 277.35 | N.A. | 277.35 | 111.00 | 66.00
337 | DELHI | RAILWAYS | ANAND VIHAR-TILAK BRIDGE 3RD AND 4TH LINE | NR | N22000281 | 4-2012 | 3/2023 | N.A. | 12/2027 | 586.36 | N.A. | 699.00 | 178.54 | 45.00
338 | DELHI | RAILWAYS | SIX LANE ACCESS CONTROLLED OF DELHI SAHARANPUR HIGHWAY FROM AKSHARDHAM NH 9 JUNCTION TO DELHI UP BOR | NHAI | N24001771 | 6-2020 | 12/2024 | N.A. | 12/2024 | 1,479.22 | N.A. | 1,479.22 | 1,491.26 | 99.00
339 | DELHI | RAILWAYS | 6L ACCESS CONTROLLED HIGHWAY FROM DND MAHARANI BAGH JN. WITH JAITPUR PUSHTA ROAD OF NH 148NA FROM | NHAI | N24001773 | 5-2020 | 7/2024 | N.A. | 9/2025 | 1,467.44 | N.A. | 1,942.89 | 1,214.36 | 91.58
340 | DELHI | RAILWAYS | DEVELOPMENT OF 6L UER-II (PACKAGE-I) (NH-1 NEAR BAKOLI TILL KARALA KANJHAWALA ROAD) FROM KM. (-)0.70 | NHAI | N24001777 | 7-2020 | 10/2023 | N.A. | 6/2025 | 2,171.80 | N.A. | 2,171.80 | 958.13 | 99.99
341 | DELHI | RAILWAYS | DWARKA EXPRESSWAY FROM KM - 0.600 TO KM 5.300 - PKG-I (SHIVMURTI CHOWK-RUB NEAR DWARKA SECTOR 21) | NHAI | N24001779 | 3-2018 | 9/2022 | N.A. | 9/2025 | 2,507.00 | N.A. | 3,030.73 | 1,155.70 | 95.05
342 | DELHI | RAILWAYS | 8L OF DWARKA EXPRESSWAY PKG-II (RUB NEAR DWARKA SECTOR 21- DL/HR BORDER) FROM 5.300 KM.TO 9.500 KM. O | NHAI | N24001781 | 1-2018 | 10/2021 | N.A. | 8/2025 | 2,067.67 | N.A. | 2,160.00 | 1,496.49 | 99.40
343 | DELHI | RAILWAYS | DEVELOPMENT OF 6L UER II [PACKAGE - II] (KARALA KANJHAWALA ROAD TILL NANGLOI - NAJAFGARH ROAD) FROM | NHAI | N24001825 | 7-2020 | 10/2023 | N.A. | 8/2025 | 1,894.96 | N.A. | 1,894.96 | 741.88 | 98.25
344 | DELHI | TELECOMMUNI CATIONS | SETTING UP PHYSICAL INFRASTRUCTURE FOR THE NATIONAL INSTITUTE OF COMMUNICATION FINANCE(NICF) AT GHIT | CPWD FOR TELECO | N28000115 | 10-2014 | 3/2018 | N.A. | 10/2025 | 248.20 | N.A. | 248.20 | 236.97 | 98.00
345 | DELHI | TELECOMMUNI CATIONS | DELHI MRTS PHASE-III | DMRC | N28000056 | 9-2011 | 3/2016 | Aug-2021 | 8/2021 | 38,585.00 | 43,095.35 | 40,180.91 | 40,685.45 | 100.00
346 | DELHI | TELECOMMUNI CATIONS | REDEVELOPMENT OF GPRA COLONY AT NAUROJI NAGAR | NBCC | N28000105 | 7-2016 | (N.A.) |  |  | 2,694.00 | N.A. | 2,694.00 | 2,247.61 | 98.00
347 | DELHI | TELECOMMUNI CATIONS | REDEVELOPMENT OF GENERAL POOL RESIDENTIAL COLONY AT SRINIWASPURI NEW DELHI PHASE-I | CPWD | N28000128 | 10-2016 | 7/2021 | N.A. | 6/2024 | 1,180.00 | N.A. | 1,100.80 | 36.69 | 2.00
348 | DELHI | TELECOMMUNI CATIONS | REDEVELOPMENT OF GPRA AT KASTURBA NAGAR PHASE I | CPWD | N28000129 | 10-2016 | 3/2022 | N.A. | 6/2024 | 1,128.00 | N.A. | 1,128.00 | 740.35 | 68.00
349 | DELHI | TELECOMMUNI CATIONS | DELHI METRO PHASE IV THREE PRIORITY CORRIDORS | DMRC | N28000135 | 7-2019 | 3/2025 | N.A. | 3/2026 | 24,948.65 | N.A. | 24,948.65 | 16,369.75 | 67.19
350 | DELHI | TELECOMMUNI CATIONS | CONSTRUCTION OF 184 MULTI STORIED FLATS FOR HON'BLE MPS AT BKS MARG, NEW DELHI | CPWD | N28000153 | 1-2022 | 11/2024 | Aug-2025 | 8/2025 | 646.52 | N.A. | 646.52 | 506.00 | 94.00
351 | DELHI | TELECOMMUNI CATIONS | REDEVELOPMENT OF GPRA AT NETAJI NAGAR NEW DELHI PACKAGE 2 | NBCC | N28000156 | 10-2016 | 3/2024 | Aug-2025 | 3/2025 | 1,536.72 | N.A. | 1,536.72 | 507.85 | 91.50
352 | DELHI | WATER RESOURCES | CONSTRUCTION OF 564 MLD 124 MGD WASTE WATER TREATMENT PLANT WITH EFFLUENT STANDARDS OF BOD ? 10MG/L | DJB | N30000014 | 3-2017 | 12/2022 | N.A. | 3/2025 | 665.78 | N.A. | 665.78 | 782.51 | 100.00
353 | GOA | CIVIL AVIATION | EXTENSION OF EXISTING INTEGRATED TERMINAL BUILDING AND ALLIED WORKS AT GOA AIRPORT. | AAI | N04000095 | 11-2017 | 9/2021 | Aug-2025 | 8/2025 | 255.69 | 255.69 | 255.69 | 125.92 | 86.75
354 | GOA | DEPARTMENT OF HIGHER EDUCATION | CONSTRUCTION OF PERMANENT CAMPUS FOR NATIONAL INSTITUTE OF TECHNOLOGY GOA AT CUNCOLIM, GOA. | CPWD EDUCATION | N42000002 | 5-2019 | 8/2021 | N.A. | 12/2024 | 303.90 | N.A. | 390.40 | 360.00 | 99.30
355 | GOA | ROAD TRANSPORT AND HIGHWAYS | CONSTRUCTION OF SIX LANE ELEVATED CORRIDOR FROM KM. 508.000 TO KM. 513.150 INCLUDING APPROACHES ON N | MoRTH | N24002181 | 4-2023 | 4/2026 | N.A. | 4/2026 | 641.46 | N.A. | 641.46 | 0.00 | -
356 | GUJARAT | CIVIL AVIATION | C/O NEW GREENFIELD AIRPORT AT HISSAR, RAJKOT, GUJARAT | AAI | N04000088 | 1-2018 | 8/2022 | Dec-2024 | 12/2024 | 1,405.00 | N.A. | 1,405.00 | 1,304.63 | 100.00
357 | GUJARAT | CIVIL AVIATION | EXTENSION OF TERMINAL BUILDING, PTT, APRON AND CAR PARK AT SURAT AIRPORT. | AAI | N04000093 | 8-2018 | 2/2021 | Mar-2025 | 3/2025 | 353.25 | N.A. | 353.25 | 348.78 | 100.00
358 | GUJARAT | CIVIL AVIATION | DEVELOPMENT OF NEW GREENFIELD AIRPORT AT DHOLERA, AHMEDABAD (GUJARAT). PHASE-1. | AAI | N04000099 | 6-2022 | 12/2025 | N.A. | 12/2025 | 1,305.00 | 1,143.95 | 1,143.95 | 648.65 | 61.00
359 | GUJARAT | COAL | 50 MW WIND POWER PROJECT PART OF 150 MW SECI HYBRID | NLC | N06000292 | 7-2022 | 6/2025 | Jan-2026 | 1/2026 | 383.84 | N.A. | 383.84 | 303.50 | 41.00
360 | GUJARAT | COAL | REDEVELOPMENT OF SANTHAL FIELD | ONGC | N16000279 | 2-2017 | 3/2026 | N.A. | 3/2026 | 1,162.56 | N.A. | 1,162.56 | 1,156.90 | 94.10
361 | GUJARAT | COAL | ACRYLICS OR OXO-ALCOHOL PROJECT AT GUJARAT REFINERY | IOCL | N16000382 | 11-2019 | 5/2023 | Mar-2024 | 7/2025 | 5,251.00 | 5,894.00 | 5,894.00 | 4,689.83 | 99.70
362 | GUJARAT | COAL | PETROCHEMICAL AND LUBE INTEGRATION PROJECT AT GUJARAT REFINERY | IOCL | N16000409 | 9-2020 | 8/2024 | Dec-2025 | 12/2025 | 18,936.00 | N.A. | 18,936.00 | 11,161.74 | 82.50
363 | GUJARAT | COAL | AUGUMENTATION OF SALAYA MATHURA CRUDE OIL PIPELINE SYSTEM | IOCL | N16000411 | 10-2020 | 8/2023 | Jun-2025 | 6/2025 | 1,614.00 | N.A. | 1,614.00 | 1,139.60 | 100.00
364 | GUJARAT | COAL | REDEVELOPMENT OF LINCH FIELD | ONGC | N16000428 | 4-2021 | 3/2025 | N.A. | 7/2025 | 631.03 | 860.04 | 860.04 | 435.64 | 76.60
365 | GUJARAT | COAL | REDEVELOPMENT OF SOBHASAN COMPLEX | ONGC | N16000431 | 8-2021 | 2/2026 | N.A. | 2/2026 | 885.63 | 1,286.67 | 1,286.67 | 584.23 | 71.40
366 | GUJARAT | COAL | COMMERCIAL POLYMER FLOODING PROJECT IN BECHRAJI FIELD | ONGC | N16000444 | 1-2022 | 11/2024 | N.A. | 11/2025 | 621.40 | N.A. | 621.40 | 137.69 | 21.40
367 | GUJARAT | COAL | INSTALLATION OF NEW BITUMEN UNIT ALONG WITH ALLIED FACILITIES AT GUJARAT | IOCL | N16000454 | 1-2022 | 9/2024 | N.A. | 5/2026 | 328.00 | N.A. | 328.00 | 101.12 | 51.30
368 | GUJARAT | COAL | RESTORATION OF GAS TERMINAL, PHASE-I (PART-A), HAZIRA PLANT | ONGC | N16000477 | 5-2022 | 2/2025 | N.A. | 9/2025 | 249.43 | N.A. | 249.43 | 209.42 | 93.70
369 | GUJARAT | COAL | KALOL REDEVELOPMENT PROJECT | ONGC | N16000481 | 8-2022 | 3/2027 | N.A. | 3/2027 | 1,487.41 | N.A. | 1,487.41 | 952.00 | 60.00
370 | GUJARAT | COAL | OLD PIPE LINE REPLACEMENT (OPRP) GROUP-A | ONGC | N16000483 | 7-2021 | 7/2025 | N.A. | 7/2025 | 173.03 | N.A. | 169.84 | 143.32 | 86.50
371 | GUJARAT | COAL | REVAMPING OF SV STATIONS, GAS TERMINAL AND KRIBHCO TERMINAL | ONGC | N16000514 | 11-2022 | 8/2026 | N.A. | 8/2026 | 837.34 | N.A. | 837.34 | 187.10 | 46.70
372 | GUJARAT | COAL | GUJARAT 200 MW (GUVNL TENDER) | NTPC | N18000295 | 1-2021 | 7/2022 | Mar-2026 | 3/2026 | 842.27 | 1,049.61 | 1,049.61 | 779.79 | 66.00
373 | GUJARAT | COAL | Bagodara Solar Power Project | SJVN | N18000297 | 5-2021 | 10/2022 | N.A. | 12/2025 | 339.35 | N.A. | 339.35 | 317.59 | 51.86
374 | GUJARAT | COAL | DAYAPAR WIND ENERGY PROJECT 150MW | NTPC | N18000319 | 11-2021 | 5/2023 | Aug-2025 | 8/2025 | 937.80 | N.A. | 937.80 | 803.82 | 100.00
375 | GUJARAT | COAL | DAYAPAR WIND ENERGY PROJECT 200MW | NTPC | N18000345 | 7-2022 | 3/2025 | Jan-2026 | 1/2026 | 1,316.02 | N.A. | 1,316.02 | 324.36 | 28.00
376 | GUJARAT | COAL | KHAWDA 1255MW SOLAR PROJECT (KHAWDA SOLAR PARK) | NTPC | N18000346 | 9-2022 | 9/2024 | Feb-2026 | 2/2026 | 7,179.54 | 7,235.79 | 7,235.79 | 5,220.20 | 89.00
377 | GUJARAT | COAL | BHUJ SOLAR 300MW (TRANCHE-IV WIND SOLAR HYBRID) | NTPC | N18000349 | 11-2022 | 3/2024 | Mar-2026 | 3/2026 | 1,442.60 | N.A. | 1,442.60 | 793.56 | 2.51
378 | GUJARAT | COAL | ESTABLISHMENT OF KHAVDA POOLING STATION 3 (KPS3) IN KHAVDA RE PARK | PGCIL | N18000357 | 3-2023 | 12/2024 | N.A. | 7/2025 | 922.30 | N.A. | 922.30 | 830.14 | 90.50
379 | GUJARAT | COAL | TRANSMISSION NETWORK EXPANSION IN GUJARAT ASSOCIATED WITH INTEGRATION OF RE PROJECTS FROM KHAVDA POT | PGCIL | N18000358 | 3-2023 | 3/2025 | N.A. | 7/2025 | 815.12 | N.A. | 815.12 | 758.09 | 100.00
380 | GUJARAT | COAL | KHAVDA-2, GUJARAT- ESTABLISHMENT OF KHAVDA POOLING STATION-2 (KPS2) IN KHAVDA RE PARK | PGCIL | N18000359 | 3-2023 | 12/2024 | N.A. | 8/2025 | 966.79 | N.A. | 966.79 | 870.10 | 93.60
381 | GUJARAT | COAL | KHAVDA PHASE-II-PART B, GUJARAT- TRANSMISSION SCHEME FOR EVACUATION OF 4.5 GW RE INJECTION AT KHAVDA | PGCIL | N18000360 | 3-2023 | 3/2025 | N.A. | 9/2025 | 1,167.55 | N.A. | 1,167.55 | 957.39 | 90.00
382 | GUJARAT | COAL | KHAVDA PHASE-II-PART C, GUJARAT- TRANSMISSION SCHEME FOR EVACUATION OF 4.5 GW RE INJECTION AT KHAVDA | PGCIL | N18000361 | 3-2023 | 3/2025 | N.A. | 9/2025 | 2,820.99 | N.A. | 2,820.99 | 2,418.00 | 82.60
383 | GUJARAT | COAL | KHAVDA 1200MW (4X300MW) IN KHAVDA RE PARK | NTPC | N18000365 | 6-2023 | 12/2024 | Jan-2026 | 1/2026 | 6,283.81 | N.A. | 6,283.81 | 1,828.84 | 42.00
384 | GUJARAT | COAL | DAYAPAR WIND- III (HYBRID TRANCHE- V) | NTPC | N18000366 | 5-2023 | 1/2025 | Mar-2026 | 3/2026 | 1,095.01 | N.A. | 1,095.01 | 382.54 | 18.00
385 | GUJARAT | COAL | TS FOR EVACUATION OF POWER FROM POTENTIAL RE ZONE IN KHAVDA AREA OF GUJARAT UNDER PH-IV PART E3 | PGCIL | N18000383 | 7-2023 | 7/2025 | N.A. | 9/2025 | 334.00 | N.A. | 334.00 | 63.46 | 21.00
386 | GUJARAT | COAL | TS FOR EVACUATION OF ADDITIONAL 7GW RE POWER FROM KHAVDA RE PARK UNDER PHASE-III PART B [VATAMAN TRA | PGCIL | N18000384 | 12-2023 | 12/2025 | N.A. | 6/2026 | 3,752.00 | N.A. | 3,752.00 | 1,463.23 | 20.00
387 | GUJARAT | COAL | TS FOR EVACUATION OF POWER FROM 7GW REZ IN KHAVDA AREA UNDER PHASE-IV PART E2 | PGCIL | N18000390 | 5-2024 | 5/2026 | N.A. | 2/2026 | 679.00 | N.A. | 679.00 | 67.90 | 16.80
388 | GUJARAT | COAL | AUGMENTATION OF TRANSFORMATION CAPACITY AT JAM KHAMBHALIYA PS [GIS] [SPV NAME POWERGRID JAM KHAMBHAL | PGCIL | N18000398 | 10-2024 | 7/2026 | N.A. | 7/2026 | 329.00 | N.A. | 329.00 | 9.87 | 1.00
389 | GUJARAT | COAL | TRANSMISSION SYSTEM FOR EVACUATION OF POWER FROM POTENTIAL RENEWABLE ENERGY ZONE IN KHAVDA AREA OF G | PGCIL | N18000400 | 10-2024 | 10/2026 | N.A. | 10/2026 | 4,766.00 | N.A. | 4,766.00 | 333.62 | 5.10
390 | GUJARAT | COAL | PROVISION OF DYNAMIC REACTIVE COMPENSATION AT KHAVDA POOLING STATION 1 [KPS1] AND KHAVDA POOLING STA | PGCIL | N18000402 | 11-2024 | 11/2026 | N.A. | 11/2026 | 501.00 | N.A. | 501.00 | 5.01 | 1.00
391 | GUJARAT | COAL | TRANSMISSION SYSTEM FOR EVACUATION OF POWER FROM POTENTIAL RENEWABLE ENERGY ZONE IN KHAVDA AREA OF G | PGCIL | N18000405 | 11-2024 | 5/2029 | N.A. | 5/2029 | 24,819.00 | N.A. | 24,819.00 | 1,240.30 | 1.00
392 | GUJARAT | COAL | 600 MW SOLAR POWER PROJECT UNDER CPSU SCHEME | NHPC | N18000406 | 4-2022 | 3/2026 | Mar-2023 | 11/2026 | 4,100.45 | N.A. | 4,100.45 | 11.05 | 5.00
393 | GUJARAT | COAL | AUGMENTATION OF TRANSFORMATION CAPACITY AT KPS2 AND KPS2 | PGCIL | N18000411 | 3-2025 | 3/2027 | N.A. | 3/2027 | 466.00 | N.A. | 466.00 | 6.52 | -
394 | GUJARAT | COAL | AUGMENTATION OF BANASKANTHA (RAGHANESDA) PS (GIS) | PGCIL | N18000412 | 3-2025 | 3/2027 | N.A. | 3/2027 | 172.00 | N.A. | 172.00 | 1.72 | -
395 | GUJARAT | COAL | MIYAGAM-KARJAN-DABHOI-SAMLAYA (GC) | WR | N22000142 | 4-2011 | 3/2021 | Oct-2026 | 10/2026 | 844.10 | 844.10 | 844.10 | 605.51 | 41.00
396 | GUJARAT | COAL | ANAND GODHRA DOUBLING PROJECT 79 KMS | WR | N22000504 | 4-2017 | 12/2024 | Jun-2025 | 6/2025 | 692.26 | 692.26 | 692.26 | 688.88 | 100.00
397 | GUJARAT | COAL | 4TH LINE BETWEEN BAREJADI NANDEJ (GERATPUR)- SANAND (38.20 KM) (AHMEDABAD BYPASS). | WR | N22000532 | 2-2023 | 3/2027 | Mar-2027 | 3/2027 | 961.67 | 961.67 | 961.67 | 103.15 | 16.00
398 | GUJARAT | COAL | QUADRUPLING BETWEEN GANDHIDHAM - ADIPUR WITH Y CONNECTION AT ADIPUR FOR PROVIDING DIRECT ENTRY TOWAR | WR | N22000533 | 2-2023 | 12/2025 | Dec-2025 | 12/2025 | 152.44 | 152.44 | 152.44 | 19.54 | 63.00
399 | GUJARAT | COAL | RAJKOT-KANALUS (111.20 KM) | WR | N22000535 | 10-2021 | 10/2026 | Jun-2026 | 6/2026 | 1,080.58 | 1,080.58 | 1,080.58 | 315.70 | 72.00
400 | GUJARAT | COAL | HIMMATNAGAR-KHEDBRAHMA (54.83 KM) | WR | N22000537 | 6-2022 | 8/2025 | Jul-2025 | 7/2025 | 354.99 | 482.42 | 482.42 | 322.59 | 96.00
401 | GUJARAT | COAL | PETLAD-BHADRAN (22.5 KM) | WR | N22000538 | 5-2022 | 5/2030 | Dec-2025 | 12/2025 | 202.50 | 307.12 | 307.12 | 81.76 | 8.00
402 | GUJARAT | COAL | NADIAD-PETLAD (37.26 KM) | WR | N22000539 | 5-2022 | 6/2030 | N.A. | 12/2025 | 335.34 | 461.91 | 461.91 | 74.35 | 7.00
403 | GUJARAT | COAL | SAMLAYA-TIMBA ROAD (53.53 KM) | WR | N22000540 | 2-2023 | 3/2030 | Jul-2026 | 7/2026 | 670.00 | 670.17 | 670.17 | 101.79 | 12.00
404 | GUJARAT | COAL | SAMNI-JAMBUSAR (24.08 KM) | WR | N22000541 | 5-2022 | 3/2030 | Dec-2025 | 12/2025 | 216.72 | 349.93 | 349.93 | 86.46 | 25.00
405 | GUJARAT | COAL | VIJAPUR-AMBLIYASAN (41.53 KM) | WR | N22000547 | 5-2022 | 8/2025 | Oct-2025 | 10/2025 | 309.81 | 415.38 | 415.38 | 263.13 | 85.00
406 | GUJARAT | COAL | ADRAJ MOTI-VIAJAPUR (39.75 KM) | WR | N22000548 | 5-2022 | 8/2025 | Sep-2025 | 9/2025 | 296.54 | N.A. | 296.54 | 178.95 | 80.00
407 | GUJARAT | COAL | NEW BG LINE BETWEEN NALIYA- JAKHAU PORT | WR | N22000550 | 2-2023 | 1/2028 | Dec-2026 | 12/2026 | 410.46 | 410.46 | 410.46 | 5.89 | 2.00
408 | GUJARAT | COAL | NEW BG LINE INTERSECTION (5 NOS) BETWEEN GERATPUR-SANAND AND BOTAD-AHMEDABAD (16.51 KM) (PB29/NR/20 | WR | N22000551 | 10-2022 | 10/2027 | Oct-2027 | 10/2027 | 437.21 | N.A. | 437.21 | 43.26 | 9.00
409 | GUJARAT | COAL | TARANGA HILL ABU ROAD VIA AMBAJI NEW LINE | NWR | N22000592 | 7-2022 | 7/2030 | N.A. | 12/2026 | 2,798.16 | N.A. | 2,798.16 | 1,103.16 | 12.50
410 | GUJARAT | COAL | JUNAGARH -VISAVADAR (42.28) KM | RVNL | N22000600 | 6-2022 | 9/2028 | N.A. | 12/2026 | 493.00 | N.A. | 492.83 | 0.00 | -
411 | GUJARAT | COAL | MODASA- SHAMLAJI NEW LINE ( MM OF AHMEDABAD-HIMMATNAGAR- UDAIPUR (299.2 KM)) | WR | N22000622 | 9-2012 | 3/2027 | Mar-2026 | 3/2026 | 261.68 | 261.68 | 261.68 | 202.70 | 58.00
412 | GUJARAT | COAL | CONSTRUCTION OF ROB WITH APPROACHES IN LIEU OF L C NO 165 OF AHMEDABAD PALANPUR BETWEEN RAILWAY STAT | MoRTH | N24001427 | 6-2020 | 4/2023 | Sep-2024 | 9/2024 | 166.21 | N.A. | 166.21 | 97.12 | 93.00
413 | GUJARAT | COAL | CONSTRUCTION OF FOUR LANE EXPRESSWAY FROM START OF SARDAR PATEL RING ROAD TO SINDHREJ VILLAGE (CH. 0 | NHAI | N24001443 | 5-2020 | 3/2024 | Jul-2025 | 7/2025 | 690.30 | 929.95 | 929.95 | 841.74 | 94.22
414 | GUJARAT | COAL | CONSTRUCTION OF FOUR LANE EXPRESSWAY FROM START OF SINDHREJ VILLAGE (CH. 22.00 TO CH. 48.52) SECTION | NHAI | N24001444 | 5-2020 | 1/2024 | Jul-2025 | 7/2025 | 882.00 | 1,229.37 | 1,229.37 | 1,042.67 | 91.54
415 | GUJARAT | COAL | CONSTRUCTION OF FOUR LANE EXPRESSWAY FROM START OF VEJALLKA VILLAGE TO START OF DSIR ZONE OF AHMEDAB | NHAI | N24001445 | 5-2020 | 7/2023 | Jun-2025 | 6/2025 | 691.52 | 903.85 | 903.85 | 893.47 | 99.45
416 | GUJARAT | COAL | CONSTRUCTION OF FOUR LANE EXPRESSWAY FROM START OF DSIR ZONE OF AHMEDABAD DISTRICT TO ADHELAI VILLAG | NHAI | N24001446 | 5-2020 | 12/2023 | Jun-2025 | 6/2025 | 894.00 | 1,261.58 | 1,261.58 | 1,166.51 | 97.28
417 | GUJARAT | COAL | DELHI VADODARA GREENFIELD ALIGNMENT SECTION OF NH 148N PACKAGE 26 | NHAI | N24001515 | 9-2020 | 2/2024 | N.A. | 3/2026 | 1,542.02 | N.A. | 1,542.02 | 989.98 | 68.50
418 | GUJARAT | COAL | DELHI VADODARA GREENFIELD ALIGNMENT SECTION OF NH 148N PACKAGE 27 | NHAI | N24001516 | 9-2020 | 2/2024 | Aug-2025 | 8/2025 | 1,185.69 | N.A. | 1,185.69 | 980.41 | 93.52
419 | GUJARAT | COAL | DELHI VADODARA GREENFIELD ALIGNMENT SECTION OF NH 148N PACKAGE 30 | NHAI | N24001518 | 11-2019 | 9/2023 | N.A. | 8/2025 | 1,669.56 | N.A. | 1,669.56 | 1,094.58 | 98.12
420 | GUJARAT | COAL | DELHI VADODARA GREENFIELD ALIGNMENT SECTION OF NH 148N PACKAGE 28 | NHAI | N24001519 | 9-2020 | 11/2023 | N.A. | 7/2025 | 1,198.55 | N.A. | 1,198.55 | 911.23 | 95.78
421 | GUJARAT | COAL | DELHI VADODARA GREENFIELD ALIGNMENT SECTION OF NH 148N PACKAGE 31 | NHAI | N24001520 | 11-2019 | 5/2024 | N.A. | 8/2025 | 1,604.06 | N.A. | 1,604.06 | 1,245.52 | 95.73
422 | GUJARAT | COAL | UP-GRADATION TO 4-LANE WITH PAVED SHOULDER OF BHIMASAR JUNCTION OF NH-41 TO ANJAR BHUJ UPTO AIRPORT | NHAI | N24001785 | 3-2022 | 6/2025 | N.A. | 6/2025 | 1,373.06 | 1,085.00 | 1,373.06 | 662.04 | 90.67
423 | GUJARAT | COAL | CONSTRUCTION OF EIGHT LANE ACCESS CONTROLLED EXPRESSWAY FROM KM 103.400 TO KM 128.000 OF VADODARA MU | NHAI | N24001786 | 3-2021 | 3/2024 | N.A. | 3/2026 | 1,259.00 | 2,652.24 | 1,910.00 | 278.29 | 34.08
424 | GUJARAT | COAL | CONSTRUCTION OF EIGHT LANE EXPRESSWAY FROM KM 190.000 TO KM 217.500 GANDEVA TO ENA SECTION OF VADODA | NHAI | N24001789 | 7-2020 | 8/2023 | N.A. | 7/2025 | 1,710.30 | 2,665.08 | 1,927.00 | 908.08 | 90.56
425 | GUJARAT | COAL | SANCHORE - SANTALPUR FROM KM 67.000- KM 99.000 OF NH-754K (AJ- RGBS-PACKAGE-3) | NHAI | N24001790 | 2-2020 | 8/2023 | Dec-2024 | 12/2024 | 752.30 | N.A. | 766.20 | 452.13 | 98.14
426 | GUJARAT | COAL | 4L OF BAL WORKS OF TALAJA - MAHUVA FROM 54.990 KM. TO 100.450 KM. OF OLD NH-8E (PACKAGE-II) | NHAI | N24001792 | 3-2021 | 9/2022 | N.A. | 1/2025 | 536.03 | N.A. | 536.03 | 480.77 | 100.00
427 | GUJARAT | COAL | 4L OF BAL WORKS OF MAHUVA TO KAGVADAR FROM 100.450 KM. TO 140.470 KM. OF NH-8E (PKG- III) | NHAI | N24001793 | 3-2021 | 9/2022 | N.A. | 5/2025 | 485.75 | N.A. | 485.75 | 393.88 | 99.57
428 | GUJARAT | COAL | SANCHORE - SANTALPUR FROM KM 99.000- KM 130.073 OF NH-754K (AJ- RGBS-PACKAGE-4) | NHAI | N24001794 | 2-2020 | 3/2023 | Dec-2024 | 12/2024 | 778.15 | N.A. | 785.67 | 547.22 | 99.70
429 | GUJARAT | COAL | 4L KODINAR - VERAVAL (PACKAGE VI) FROM KM. 222.400 TO KM. 230.00 (KODINAR BYPASS) OF NH-8E (NH 51 NE | NHAI | N24001827 | 3-2022 | 3/2023 | N.A. | 4/2025 | 162.73 | N.A. | 162.73 | 131.79 | 100.00
430 | GUJARAT | COAL | UPGRADATION AND STRENGTHENING TO 2 LANE PS FROM KM 95/500 TO KM 129/775 OF NH 168 G IDAR BHILODA SA | MoRTH | N24002014 | 9-2022 | 12/2023 | Dec-2025 | 12/2025 | 237.28 | N.A. | 237.28 | 0.34 | -
431 | GUJARAT | COAL | UPGRADATION TO 4L PS DIVIDED CARRIAGEWAY FROM PATAN (NEAR RAJPUR) TO GOJARIYA FROM KM 52.000 TO KM 1 | NHAI | N24002034 | 12-2021 | 3/2025 | N.A. | 3/2025 | 1,181.34 | 1,181.00 | 1,181.34 | 555.81 | 79.50
432 | GUJARAT | COAL | WIDENING TO 6L OF EXISTING 4L JETPUR - GONDAL - RAJKOT SECTION FROM KM. 117.600 TO KM. 185.00 ON NH- | NHAI | N24002035 | 9-2023 | 9/2025 | N.A. | 9/2025 | 2,070.44 | N.A. | 2,070.44 | 545.53 | 37.86
433 | GUJARAT | COAL | UPGRADATION OF DHORAJI JAMKANDORNA KALAVAD SECTION OF NH 927D FROM DESIGN CHAINAGE KM 00 TO KM 58.11 | MoRTH | N24002117 | 10-2022 | 2/2024 | Feb-2026 | 2/2026 | 246.60 | 291.00 | 291.00 | 27.57 | 15.00
434 | GUJARAT | COAL | UPGRADATION TO TWO LANE WITH PAVED SHULDER CONFIGUARATION FROM KM 00 TO 47 OF NH 351 MAHUVA TO BADHA | MoRTH | N24002118 | 12-2022 | 2/2024 | Aug-2025 | 8/2025 | 173.06 | N.A. | 219.00 | 0.15 | -
435 | GUJARAT | COAL | WORK OF DEVELOPMENT AND CONSTRUCTION OF ELEVATED CORRIDORFROM KM 38/660 TO KM 42/690 (ISCON JUNCTION | MoRTH | N24002182 | 3-2023 | 3/2026 | N.A. | 3/2026 | 530.20 | N.A. | 530.20 | 0.00 | -
436 | GUJARAT | COAL | WIDENING 2 LANE TO 4-LANE FROM KM 92/320 TO KM 115/320 (VAV CHOKDI- SATLASANA TO TO VRUNDAVAN CHOKDI, | MoRTH | N24002183 | 3-2022 | 3/2026 | N.A. | 3/2026 | 151.13 | N.A. | 171.00 | 0.00 | -
437 | GUJARAT | COAL | FOUR LANING OF KAGAVADAR - UNA SECTION OF NH-8E FROM KM 139.915 TO KM 180.478 (PACKAGE-IV) IN THE ST | NHAI | N24000569 | 5-2016 | 9/2019 | May-2024 | 6/2025 | 723.64 | N.A. | 723.64 | 562.31 | 97.00
438 | GUJARAT | COAL | 4-LANNING OF KODINAR TO VERAVAL SECTION OF NH-8E FROM KM 221.610 TO KM 263.000 | NHAI | N24000592 | 7-2016 | 7/2020 | N.A. | 5/2025 | 829.97 | N.A. | 829.97 | 486.93 | 96.98
439 | GUJARAT | COAL | SIX LANNING FROM KM. 401.200 TO 494.410 OF NH-8 ON HYBRID ANNUITY MODE UNDER NHDP-V(PKG VI)REG. | NHAI | N24000649 | 1-2017 | 12/2020 | Oct-2025 | 10/2025 | 1,251.11 | 1,527.75 | 1,527.75 | 685.73 | 91.08
440 | GUJARAT | COAL | CONSTRUCTION OF EIGHT LANE VADODARA KIM EXPRESSWAY FROM KM 254.430 TO KM 279.000 (KIM TO ANKLESHWAR | NHAI | N24000834 | 3-2018 | 10/2021 | May-2025 | 7/2025 | 1,161.39 | 1,738.03 | 1,404.00 | 684.22 | 83.00
441 | GUJARAT | COAL | CONSTRUCTION OF MISSING LINKS (SINGLE LANE) IN LAKHPAT GADULI HAJIPIR ODMA KHAVDA DHOLAVIRA MAUVANA | MoRTH | N24000925 | 10-2018 | 11/2020 | Sep-2024 | 9/2024 | 400.76 | 394.44 | 394.44 | 287.04 | 87.00
442 | GUJARAT | COAL | AHMEDABAD METRO RAIL PROJECT PHASE 1 | AMR | N28000122 | 11-2014 | 12/2018 | N.A. | 8/2025 | 10,773.00 | N.A. | 12,924.55 | 12,486.28 | 99.90
443 | GUJARAT | COAL | AHMEDABAD METRO RAIL PROJECT PHASE II | AMR | N28000137 | 3-2019 | 3/2024 | N.A. | 12/2025 | 5,384.17 | N.A. | 5,384.17 | 4,135.88 | 87.68
444 | GUJARAT | COAL | SURAT METRO RAIL PROJECT | AMR | N28000138 | 3-2019 | 3/2024 | N.A. | 6/2026 | 12,020.32 | N.A. | 12,020.32 | 7,043.17 | 67.49
445 | HARYANA | HEALTH AND FAMILY WELFARE | ALL INDIA INSTITUTE OF MEDICAL SCIENCES AT MANETHI, HARYANA. | HITES | N21000032 | 3-2019 | 3/2023 | Mar-2026 | 3/2026 | 1,294.34 | 1,294.34 | 1,294.34 | 307.21 | 26.14
446 | HARYANA | HOME AFFAIRS | C/o separate family accommodation (Phase-I) on EPC basis for SSB at Faridabad (Haryana)" | CPWD FOR MHA | N28000147 | 1-2020 | 10/2023 | Mar-2025 | 8/2025 | 166.98 | 170.23 | 170.23 | 150.98 | 97.50
447 | HARYANA | PETROLEUM | R and D CAMPUS II AT FARIDABAD | IOCL | N16000375 | 6-2019 | 12/2022 | Jul-2025 | 3/2026 | 2,281.94 | 3,219.94 | 3,219.94 | 1,744.23 | 63.10
448 | HARYANA | PETROLEUM | CAPACITY EXPANSION OF PANIPAT REFINERY FROM 15 TO 25 MMTPA | IOCL | N16000412 | 2-2021 | 9/2024 | Dec-2025 | 12/2025 | 34,627.00 | 38,231.00 | 38,231.00 | 21,454.90 | 87.60
449 | HARYANA | PETROLEUM | POLY BUTADIENE RUBBER PLANT AT PANIPAT | IOCL | N16000458 | 3-2022 | 3/2025 | Jun-2026 | 6/2026 | 1,459.00 | 2,948.62 | 2,948.62 | 930.86 | 68.30
450 | HARYANA | POWER | IMPLEMENTATION OF LILO OF BOTH CIRCUITS OF 400KV VIDHYACHAL PS TO SASAN D/C LINE AT HINDALCO SWITCHY | PGCIL | N18000420 | 2-2025 | 12/2026 | N.A. | 12/2026 | 370.00 | N.A. | 370.00 | 0.00 | -
451 | HARYANA | POWER | DOUBLING BETWEEN BHIWANI-DOBH BAHALI | NWR | N22000604 | 2-2023 | 2/2028 | Mar-2026 | 3/2026 | 471.06 | N.A. | 471.06 | 121.18 | 55.00
452 | HARYANA | POWER | DOUBLING BETWEEN REWARI- KATHUWAS (27.73 KM) | NWR | N22000606 | 2-2023 | 6/2027 | May-2026 | 5/2026 | 352.41 | N.A. | 352.41 | 179.38 | 53.00
453 | HARYANA | POWER | 4-LANING OF GOHANA-SONIPAT (PKG- 2) SECTION FROM KM 40.601 TO KM 78.837 (LENGTH = 38.236KM) OF NH-352 | NHAI | N24001535 | 7-2020 | 7/2022 | May-2024 | 8/2025 | 899.00 | 1,882.46 | 1,882.46 | 1,123.98 | 97.86
454 | HARYANA | POWER | CONSTRUCTION OF FOUR LANE GREENFIELD PROJECT OF DELHI- AMRITSAR-KATRA EXPRESSWAY (PHASE-I PKG-III) F | NHAI | N24001633 | 12-2020 | 12/2023 | Mar-2024 | 7/2025 | 1,430.88 | 1,813.91 | 1,813.91 | 1,190.27 | 99.90
455 | HARYANA | POWER | CONSTRUCTION OF FOUR LANE GREENFIELD PROJECT OF DELHI- AMRITSAR-KATRA EXPRESSWAY (PHASE-I PKG-IV) FRO | NHAI | N24001634 | 1-2021 | 12/2023 | Mar-2024 | 7/2025 | 1,306.95 | 1,564.14 | 1,564.14 | 949.76 | 99.97
456 | HARYANA | POWER | 4 LANING OF JAGADHRI TAJEWALA ROAD SECTION OF NH 907 (OLD NH 73A) UNDER NH(O) (PKG 1) IN THE STATE O | NHAI | N24001635 | 3-2022 | 2/2025 | N.A. | 2/2025 | 1,269.50 | N.A. | 1,269.50 | 176.00 | 53.00
457 | HARYANA | POWER | 4- LANING OF ROHTAK-JIND SECTION FROM KM. 307+000 TO KM. 347+800 OF NH-71 AND CONNECTING LINK FROM K | NHAI | N24001673 | 3-2020 | 3/2023 | Nov-2024 | 7/2025 | 510.97 | N.A. | 510.97 | 529.00 | 97.30
458 | HARYANA | POWER | CONSTRUCTION OF GURGAON - PATAUDI - REWARI SECTION OF NH- 352W (DESIGN LENGTH 46.11 KM) AS FEEDER ROU | NHAI | N24001774 | 12-2020 | 11/2023 | N.A. | 6/2024 | 1,524.03 | N.A. | 1,524.03 | 1,105.10 | 67.61
459 | HARYANA | POWER | CONSTRUCTION OF PROPOSED REWARI BYPASS (DESIGN LENGTH 14.4 KM) NH-11 AS A FEEDER ROUTE IN THE STATE | NHAI | N24001775 | 2-2020 | 1/2023 | Dec-2024 | 12/2024 | 808.31 | N.A. | 958.00 | 930.44 | 100.00
460 | HARYANA | POWER | UPGRADATION OF EXISTING 4 LANE ISMAILABAD-AMBALA SECTION (KM. 0+000 TO KM 42+500) (PART OF AMBALA-KO | NHAI | N24002037 | 1-2023 | 12/2025 | N.A. | 3/2026 | 609.32 | 609.00 | 609.00 | 204.06 | 52.50
461 | HARYANA | POWER | CONSTRUCTION OF 6-LANE GREENFIELD KARNAL RING ROAD STARTING FROM NH-44 NEAR VILLAGE SHAMGARH (DESIGN | NHAI | N24002038 | 11-2022 | 8/2025 | N.A. | 8/2025 | 1,691.45 | 1,998.00 | 1,998.00 | 649.71 | 58.76
462 | HARYANA | POWER | CONSTRUCTION OF 6-LANE GREENFIELD AMBALA RING ROAD STARTING FROM JUNCTION WITH SHAMLI-AMBALA SECTION | NHAI | N24002039 | 2-2023 | 10/2025 | N.A. | 10/2025 | 1,088.64 | 1,178.00 | 1,178.00 | 425.85 | 53.55
463 | HARYANA | POWER | DEVELOPMENT OF SIX-LANE ACCESS CONTROLLED HIGHWAY FROM RANIPUR BARSI (SAHARANPUR DISTRICT) TO ADHOYA | NHAI | N24002040 | 4-2022 | 5/2025 | N.A. | 5/2028 | 1,554.21 | N.A. | 1,554.21 | 522.92 | 54.00
464 | HARYANA | POWER | DEVELOPMENT OF SIX-LANE ACCESS CONTROLLED HIGHWAY FROM ADHOYA MUSALMANA (AMBALA DISTRICT) TO SADOPUR | NHAI | N24002041 | 4-2022 | 5/2025 | N.A. | 5/2025 | 1,491.71 | N.A. | 1,491.71 | 706.26 | 49.70
465 | HARYANA | POWER | CONSTRUCTION OF 4-LANING OF BHIWANI HANSI ROAD SECTION OF NH 148B (DESIGN LENGTH 42.934 KM) UNDER BH | NHAI | N24002042 | 11-2022 | 12/2025 | N.A. | 12/2025 | 1,322.13 | N.A. | 1,322.13 | 393.46 | 93.01
466 | HARYANA | POWER | CONSTRUCTION OF 4-LANE GREENFIELD JALBEHRA - SHAHBAD SECTION OF NH ? 152G FROM KM 0+000 TO KM 22+850 | NHAI | N24002043 | 3-2022 | 6/2025 | N.A. | 10/2025 | 927.22 | 1,173.66 | 1,173.66 | 504.21 | 83.50
467 | HARYANA | POWER | 4L AMBALA - KALAAMB FROM KM. - 0.800 TO KM. 33.015 OF OLD NH-72 | NHAI | N24002044 | 6-2023 | 6/2025 | N.A. | 6/2025 | 629.16 | N.A. | 629.16 | 154.00 | 98.90
468 | HARYANA | POWER | CONSTRUCTION OF GREENFIELD CONNECTIVITY TO JEWAR INTERNATIONAL AIRPORT FROM DND FARIDABAD BALLABHGAR | NHAI | N24002048 | 7-2022 | 6/2025 | N.A. | 3/2026 | 2,414.67 | 2,898.00 | 2,898.00 | 1,232.13 | 49.10
469 | HARYANA | DEPARTMENT OF HIGHER EDUCATION | ESTABLISHMENT OF PERMANENT CAMPUS PHASE 1 OF IIM SIRMAUR | CPWD EDUCATION | N42000008 | 9-2018 | 6/2022 | Dec-2024 | 8/2025 | 392.51 | N.A. | 446.43 | 316.16 | 91.50
470 | HIMACHAL PRADESH | DEPARTMENT OF HIGHER EDUCATION | CONSTRUCTION OF PERMANENT CAMPUSES OF CENTRAL UNIVERSITY OF HIMACHAL PRADESH AT DEHRA AND DHARAMSHAL | CPWD | N42000011 | 3-2021 | 11/2024 | Jul-2025 | 7/2025 | 512.37 | 300.45 | 300.45 | 169.63 | 74.00
471 | HIMACHAL PRADESH | POWER | LUHRI HYDROELECTRIC PROJECT (STAGE1) | SJVN | N18000279 | 11-2020 | 1/2026 | N.A. | 12/2028 | 1,810.56 | N.A. | 3,584.53 | 1,732.67 | 51.32
472 | HIMACHAL PRADESH | POWER | DHAULASIDH HYDROELECTRIC PROJECT (66 MW) | SJVN | N18000291 | 10-2020 | 11/2025 | N.A. | 3/2027 | 687.97 | N.A. | 1,511.87 | 891.77 | 67.61
473 | HIMACHAL PRADESH | POWER | SUNNI DAM HYDRO ELECTRIC PROJECT | SJVN | N18000344 | 1-2023 | 4/2028 | N.A. | 12/2028 | 2,614.51 | N.A. | 4,540.71 | 948.35 | 29.41
474 | HIMACHAL PRADESH | RAILWAYS | BHANUPALI-BILASPUR BERI NL | RVNL | N22000273 | 4-2008 | 12/2026 | N.A. | 3/2025 | 13,370.29 | N.A. | 6,753.42 | 5,369.57 | -
475 | HIMACHAL PRADESH | RAILWAYS | REHABILITATION AND UPGRADATION TO 2-LANE CONFIGURATION OF ASHYARI-SHRI KYARI SECTION (KM 50.000 TO K | MoRTH | N24001422 | 2-2021 | 9/2021 | N.A. | 7/2024 | 345.89 | N.A. | 345.89 | 178.19 | 95.08
476 | HIMACHAL PRADESH | RAILWAYS | REHABILITATION AND UPGRADATION TO 2-LANE CONFIGURATION OF HAMIRPUR-KARNOHAL SECTION (KM 141.000 TO K | MoRTH | N24001447 | 8-2020 | 12/2024 | N.A. | 12/2024 | 371.93 | N.A. | 371.93 | 154.04 | 81.00
477 | HIMACHAL PRADESH | RAILWAYS | REHABILITATION AND UPGRADATION TO 2-LANE CONFIGURATION OF KALWAHAN-MANDI SECTION (KM 208.950 TO KM 2 | MoRTH | N24001470 | 8-2020 | 4/2025 | N.A. | 4/2025 | 314.32 | N.A. | 314.32 | 49.26 | 51.00
478 | HIMACHAL PRADESH | RAILWAYS | REHABILITATION AND UPGRADING FROM 2 L TO 4 L FROM BHANGBAR(NEAR RANITAL) TO KANGRA BYPASS SECTION OF | NHAI | N24001808 | 3-2021 | 12/2024 | Dec-2024 | 12/2024 | 1,322.95 | 1,442.47 | 1,442.47 | 888.73 | 96.61
479 | HIMACHAL PRADESH | RAILWAYS | CONVERSION OF PARTIALLY EXCAVATED ESCAPE TUNNEL TO UNIDIRECTIONAL TWO LANE TUNNEL (INCLUDING CONSTRU | NHAI | N24001809 | 5-2022 | 3/2024 | Dec-2024 | 12/2024 | 469.95 | N.A. | 280.00 | 302.91 | 98.57
480 | HIMACHAL PRADESH | RAILWAYS | 4L SUNDER NAGAR BYPASS FROM KM173.900 TO KM 179.600 OF NH-21 IN THE STATE OF HP | NHAI | N24001810 | 2-2022 | 6/2024 | N.A. | 6/2024 | 190.60 | N.A. | 163.00 | 103.48 | 100.00
481 | HIMACHAL PRADESH | RAILWAYS | 4L OF MO - SIHUNI FROM KM. 42.00 TO KM. 51.00 OF OLD NH-20 (NEW NH-154) (PACKAGE-IB) | NHAI | N24001811 | 4-2021 | 6/2024 | N.A. | 5/2025 | 583.93 | 770.00 | 770.00 | 173.60 | 100.00
482 | HIMACHAL PRADESH | RAILWAYS | 4L OF HP/PUNJAB BO4L OF HP/PUNJAB BORDER - MO FROM KM. 11.00 TO KM. 42.00 OF OLD NH-20 (NEW NH-154) | NHAI | N24001812 | 3-2021 | 5/2024 | N.A. | 12/2025 | 1,002.11 | 1,361.79 | 1,361.76 | 190.30 | 46.68
483 | HIMACHAL PRADESH | RAILWAYS | 4L OF END OF PINJORE BYPASS - BADDI - NALAGARH SECTION (KM. 4.200 TO KM. 35.370) OF NH21A | NHAI | N24001813 | 7-2021 | 9/2024 | N.A. | 9/2024 | 1,692.05 | N.A. | 1,692.05 | 942.14 | 21.60
484 | HIMACHAL PRADESH | RAILWAYS | IMPROVEMENT/CONSTRUCTION OF EXISTING CLASS-5 ROAD TO NH INTERMEDIATE LANE SPECIFICATION WITH HARD SH | BRO | N24001915 | 3-2021 | 6/2026 | N.A. | 6/2026 | 230.54 | N.A. | 230.54 | 20.16 | 28.00
485 | HIMACHAL PRADESH | RAILWAYS | IMPROVEMENT/CONSTRUCTION OF EXISTING CLASS 5 ROAD TO NH INTERMEDIATE LANE SPECIFICATION WITH HARD SH | BRO | N24001916 | 3-2021 | 5/2026 | N.A. | 5/2026 | 314.67 | N.A. | 314.67 | 76.05 | 47.00
486 | HIMACHAL PRADESH | RAILWAYS | PKG NAME: 4L OF KATHLIGHAT TO SHAKRAL VILLAGE FROM KM 128.835 TO KM 146.300 OF NH- 5 (SHIMLA BYPASS | NHAI | N24002049 | 3-2022 | 4/2026 | N.A. | 4/2026 | 1,703.48 | 2,278.00 | 2,278.00 | 651.98 | 14.50
487 | HIMACHAL PRADESH | RAILWAYS | REHABILITATION AND UPGRADATION TO 4L CONFIGURATION and STRENGTHENING OF SIHUNI TO RAJOL FROM KM 51.0 | NHAI | N24002050 | 2-2022 | 9/2025 | N.A. | 9/2025 | 696.65 | 698.46 | 698.46 | 391.62 | 67.73
488 | HIMACHAL PRADESH | RAILWAYS | CONSTRUCTION OF NEW 2 LANE WITH PAVED SHOULDER OF HAMIRPUR BYPASS (PACKAGE IVA) OF NH-88 (NEW NH-103 | NHAI | N24002051 | 7-2022 | 10/2025 | N.A. | 10/2025 | 739.39 | N.A. | 739.39 | 347.45 | 81.53
489 | HIMACHAL PRADESH | RAILWAYS | REHABILITATION AND UP-GRADATION OF EXISTING ROAD TO 2L PS FROM END OF HAMIRPUR BYPASS (NEAR CHILBAHA | NHAI | N24002052 | 2-2022 | 4/2025 | N.A. | 4/2025 | 1,146.19 | N.A. | 1,146.19 | 940.81 | 71.23
490 | HIMACHAL PRADESH | RAILWAYS | REHABILITATION AND UP-GRADATION TO 4L CONFIGURATION AND STRENGTHENING OF THANPURI TO PAROR SECTION F | NHAI | N24002192 | 6-2022 | 12/2025 | N.A. | 12/2025 | 815.69 | 815.69 | 815.69 | 400.63 | 33.56
491 | HIMACHAL PRADESH | RAILWAYS | FOUR LANNING OF NERCHOWK- PANDOH BYPASS SECTION OF NH- 21(PACKAGE-I KM 190.000 TO KM 221.305) UNDER NH | NHAI | N24000613 | 9-2016 | 7/2020 | N.A. | 3/2025 | 1,273.71 | N.A. | 1,478.61 | 1,450.53 | 97.43
492 | HIMACHAL PRADESH | RAILWAYS | FOUR LANING OF SOLAN-KAITHLIGHAT SECTION OF NH-22 (NOW NH-5) FROM KM 106.139 TO KM 129.050, ON EPC M | NHAI | N24000852 | 3-2018 | 5/2021 | Dec-2024 | 12/2024 | 478.74 | N.A. | 1,514.46 | 1,349.59 | 83.00
493 | HIMACHAL PRADESH | RAILWAYS | REHABILITATION AND UPGRADATION TO 2-LANE/2-LANE WITH PAVED SHOULDERS/4-LANE CONFIGURATION OF PAONTA | MoRTH | N24001381 | 8-2020 | 4/2021 | N.A. | 4/2021 | 272.98 | N.A. | 272.98 | 140.69 | 100.00
494 | HIMACHAL PRADESH | RAILWAYS | REHABILITATION AND UPGRADATION TO 2-LANE CONFIGURATION OF HEWNA-ASHYARI SECTION (KM 25.000 TO KM 50. | MoRTH | N24001382 | 8-2020 | 3/2021 | N.A. | 7/2024 | 242.80 | N.A. | 242.80 | 100.95 | 94.76
495 | HIMACHAL PRADESH | RAILWAYS | REHABILITATION AND UPGRADATION TO INTERMEDIATE LANE CONFIGURATION OF SHRI KYARI- GUMMA SECTION (KM 75 | MoRTH | N24001383 | 8-2020 | 4/2021 | N.A. | 4/2021 | 349.20 | N.A. | 349.20 | 239.34 | 100.00
496 | HIMACHAL PRADESH | CIVIL AVIATION | JAMMU - CONSTRUCTION OF NEW CIVIL ENCLAVE | AAI | N04000107 | 7-2022 | 6/2026 | N.A. | 6/2026 | 861.37 | N.A. | 861.37 | 154.30 | 30.25
497 | JAMMU AND KASHMIR | DEPARTMENT OF HIGHER EDUCATION | CONSTRUCTION OF PERMANENT CAMPUS OF IIM JAMMU (PHASE 1) | CPWD EDUCATION | N28000130 | 3-2019 | 7/2022 | Jan-2025 | 1/2025 | 424.93 | N.A. | 500.91 | 448.15 | 96.00
498 | JAMMU AND KASHMIR | DEPARTMENT OF HIGHER EDUCATION | CONSTRUCTION OF PERMANENT CAMPUS IIT JAMMU (PHASE 1C) | CPWD EDUCATION | N28000131 | 1-2018 | 4/2023 | Apr-2025 | 4/2025 | 676.00 | 1,144.68 | 1,144.68 | 54.75 | 100.00
499 | JAMMU AND KASHMIR | DEPARTMENT OF HIGHER EDUCATION | C/O AIIMS AT AWANTIPORA (KASHMIR) JAMMU AND KASHMIR | CPWD FOR HEALTH | N28000150 | 3-2019 | 9/2025 | N.A. | 11/2025 | 1,828.00 | N.A. | 1,577.00 | 1,302.38 | 64.50
500 | JAMMU AND KASHMIR | DEPARTMENT OF HIGHER EDUCATION | CONSTRUCTION OF AIIMS AT JAMMU VIJAYPUR, SAMBA JAMMU AND KASHMIR | CPWD FOR HEALTH | N21000029 | 3-2019 | 9/2023 | May-2025 | 5/2025 | 1,404.00 | 1,642.00 | 1,642.00 | 1,461.68 | 100.00
501 | JAMMU AND KASHMIR | PETROLEUM | SETTING UP A COMMON USER PETROLEUM TERMINAL AT JAMMU FOR RE-SITEMENT OF EXISTING DEPOTS OF PSU OMCS | BPCL | N16000500 | 4-2021 | 3/2025 | N.A. | 3/2025 | 676.89 | N.A. | 676.89 | 503.55 | 76.00
502 | JAMMU AND KASHMIR | PETROLEUM | CGD PROJECT AT JAMMU DISTRICTS | IOCL | N16000527 | 3-2022 | 3/2032 | Sep-2034 | 9/2034 | 538.00 | N.A. | 538.00 | 4.09 | 0.60
503 | JAMMU AND KASHMIR | POWER | PAKAL DUL HYDRO ELECTRIC PROJECT (1000 MW) | CVPPPL | N18000172 | 10-2014 | 4/2020 | Jul-2025 | 12/2026 | 8,112.12 | N.A. | 12,727.76 | 6,692.58 | 70.00
504 | JAMMU AND KASHMIR | POWER | KIRU HYDRO ELECTRIC PROJECT | CVPPPL | N18000278 | 3-2019 | 8/2024 | N.A. | 12/2026 | 4,287.59 | N.A. | 5,409.00 | 2,713.25 | 63.87
505 | JAMMU AND KASHMIR | POWER | RATLE HE PROJECT | NHPC | N18000324 | 2-2021 | 2/2026 | N.A. | 8/2028 | 5,281.94 | N.A. | 5,281.94 | 1,011.56 | 23.57
506 | JAMMU AND KASHMIR | POWER | KWAR HE PROJECT | CVPPPL | N18000363 | 5-2022 | 11/2026 | N.A. | 3/2028 | 4,526.12 | N.A. | 4,526.12 | 1,159.97 | 22.15
507 | JAMMU AND KASHMIR | POWER | TRANSMISSION SCHEME FOR EVACUATION OF POWER FROM RATLE HEP (850 MW) AND KIRU (624 MW): PART B | PGCIL | N18000417 | 3-2025 | 3/2027 | N.A. | 3/2027 | 219.00 | N.A. | 219.00 | 0.00 | -
508 | JAMMU AND KASHMIR | POWER | BALANCE WORKS OF FOUR LANING FROM RAMBAN KM 151.00 TO BANIHAL KM 187.00 OF NH-1A (NOW NH-44) WITH VA | NHAI | N24001472 | 9-2021 | 12/2023 | Jun-2024 | 6/2024 | 811.19 | N.A. | 811.19 | 848.72 | 99.00
509 | JAMMU AND KASHMIR | POWER | CONSTRUCTION OF FOUR LANE RINGROAD BYPASS SRINAGAR CITY | NHAI | N24001511 | 3-2021 | 2/2024 | Oct-2025 | 10/2025 | 2,919.96 | N.A. | 2,919.96 | 2,334.99 | 70.00
510 | JAMMU AND KASHMIR | POWER | FOUR LANING OF JAMMU-AKHNOOR PKG-1 | NHIDCL | N24001543 | 7-2022 | 1/2025 | N.A. | 10/2025 | 245.34 | N.A. | 245.34 | 57.20 | 40.95
511 | JAMMU AND KASHMIR | POWER | DELHI-AMRITSAR-KATRA EXPRESSWAY (PHASE-II PKG-XVI) EXISTING JAKH (VIJAYPUR)-KUNJWANI SECTION OF NH-4 | NHAI | N24001550 | 9-2021 | 9/2024 | Dec-2025 | 12/2025 | 1,821.72 | 1,917.32 | 1,917.32 | 1,005.37 | 83.71
512 | JAMMU AND KASHMIR | POWER | DELHI-AMRITSAR-KATRA EXPRESSWAY (PHASE-II PKG-XIV) FROM JUNCTION WITH PATHANKOT- GURDASPUR ROAD (NH-5 | NHAI | N24001551 | 10-2021 | 9/2024 | Dec-2025 | 12/2025 | 3,044.02 | 3,044.02 | 3,044.02 | 1,589.44 | 70.21
513 | JAMMU AND KASHMIR | POWER | DELHI-AMRITSAR-KATRA EXPRESSWAY (PHASE-II PKG-XV) [JUNCTION WITH HIRANAGAR ROAD NEAR VILLAGE GURHA B | NHAI | N24001552 | 10-2021 | 9/2024 | Feb-2026 | 2/2026 | 2,714.95 | 2,714.95 | 2,714.95 | 1,663.19 | 85.78
514 | JAMMU AND KASHMIR | POWER | CORRIDOR EFFICIENCY IMPROVEMENT INCLUDING REMOVAL OF BLACK SPOTS IN LAKHANPUR - SAMBA SECTION OF NH- | NHAI | N24001619 | 8-2022 | 6/2024 | Jun-2025 | 6/2025 | 200.05 | 200.05 | 208.92 | 153.30 | 63.20
515 | JAMMU AND KASHMIR | POWER | CONSTRUCTION OF TUNNELS/VIADUCTS AT IDENTIFIED SLIDING/SLIP ZONES AT KM 130.550 TO KM.130.750; KM. | NHAI | N24001620 | 9-2021 | 10/2023 | Dec-2025 | 12/2025 | 442.14 | N.A. | 442.14 | 352.62 | 19.88
516 | JAMMU AND KASHMIR | POWER | 4L OF KM.165.092 TO KM.171.855 (NORTH BOUND) AND FROM KM.166.895 TO KM.173.638 (SOUTH BOUND), EXCL. | NHAI | N24001621 | 7-2021 | 8/2024 | Jul-2025 | 7/2025 | 614.48 | N.A. | 614.48 | 187.59 | 7.00
517 | JAMMU AND KASHMIR | POWER | 4L TWIN TUBE TUNNEL INCLUDING APPROACHES FROM DIGDOL TO KHUNI NALLAH (NORTH BOUND CONNECTING WITH EX | NHAI | N24001622 | 7-2021 | 6/2024 | Jul-2025 | 7/2025 | 1,401.87 | N.A. | 1,401.87 | 751.11 | -
518 | JAMMU AND KASHMIR | POWER | BANIHAL BYPASS (DELINKED FROM SRINAGAR - BANIHAL) FROM KM. 187.00 TO KM. 189.350 | NHAI | N24001623 | 1-2020 | 1/2024 | Feb-2025 | 2/2025 | 336.01 | N.A. | 336.01 | 223.02 | 34.00
519 | JAMMU AND KASHMIR | POWER | CONSTRUCTION OF EMERGENCY LANDING FACILITY FROM KM. 246.60 TO KM. 249.70 ON SRINAGAR - BANIHAL SECTI | NHAI | N24001624 | 7-2019 | 10/2020 | Apr-2023 | 9/2024 | 157.05 | N.A. | 157.05 | 139.54 | 100.00
520 | JAMMU AND KASHMIR | POWER | 4L OF TWIN TUBE TUNNEL CONFIGURATION INCLUDING APPROACHES FROM MAROG TO DIGDOL (FROM KM.154.210 TO K | NHAI | N24001627 | 7-2021 | 2/2025 | May-2026 | 5/2026 | 1,912.17 | N.A. | 1,912.17 | 148.88 | -
521 | JAMMU AND KASHMIR | POWER | JAMMU - AKHNOOR SECTION OF NH 144A PKG-3B | NHIDCL | N24001833 | 7-2022 | 3/2025 | N.A. | 8/2025 | 198.28 | N.A. | 198.28 | 85.49 | 71.09
522 | JAMMU AND KASHMIR | POWER | REHABILITATION AND UPGRADATION TO 2 LANE WITH PAVED SHOULDER FROM EXISTING CHAINAGE KM 102 TO KM 13 | BRO | N24001897 | 3-2021 | 7/2024 | Mar-2025 | 3/2024 | 642.24 | N.A. | 642.24 | 345.14 | 95.00
523 | JAMMU AND KASHMIR | POWER | REHABILITATION AND UPGRADATION TO 2 LANE WITH PAVED SHOULDER FROM EXISTING CHAINAGE KM 30.000 TO K | BRO | N24001898 | 7-2020 | 11/2024 | N.A. | 11/2024 | 272.49 | N.A. | 272.49 | 133.66 | 87.24
524 | JAMMU AND KASHMIR | POWER | REHABILITATION AND UPGRADATION TO 2 LANE WITH PAVED SHOULDER FROM EXISTING CHAINAGE KM 134.95 TO KM | BRO | N24001899 | 2-2021 | 7/2024 | N.A. | 3/2025 | 395.25 | N.A. | 395.25 | 140.42 | 64.00
525 | JAMMU AND KASHMIR | POWER | REHABILITATION AND UPGRADATION TO 2 LANE WITH PAVED SHOULDER FROM EXISTING CHAINAGE KM 49.150 TO KM | BRO | N24001900 | 3-2020 | 8/2024 | N.A. | 3/2025 | 796.97 | N.A. | 796.97 | 323.85 | 79.00
526 | JAMMU AND KASHMIR | POWER | REHABILITATION AND UPGRADATION TO 2 LANE WITH PAVED SHOULDER FROM EXISTING CHAINAGE KM 64.535 TO K | BRO | N24001901 | 3-2020 | 9/2023 | N.A. | 3/2025 | 152.93 | N.A. | 152.93 | 90.30 | 78.27
527 | JAMMU AND KASHMIR | POWER | CONSTRUCTION OF TWIN TUBE TUNNELS ON JAMMU KASHMIR RING ROAD (NH-244A) BETWEEN DESIGN CH. 50+600 TO | NHAI | N24001926 | 3-2023 | 6/2025 | N.A. | 3/2026 | 939.86 | N.A. | 939.86 | 475.07 | 69.93
528 | JAMMU AND KASHMIR | POWER | CONSTRUCTION OF 4 LANE WITH PAVED SHOULDER FROM (DESIGN CH. 14+200 TO 24+400), (DESIGN CH. 35+300 TO | BRO | N24001998 | 6-2022 | 8/2025 | N.A. | 8/2025 | 832.46 | N.A. | 823.46 | 227.50 | 46.00
529 | JAMMU AND KASHMIR | POWER | 2L NH-1 FROM KM 8.660 TO KM 33.775 (SUMBAL TO WAYUL) TO 4L DUAL CARRIAGEWAY NH STANDARD AS PART OF S | NHAI | N24002059 | 9-2022 | 6/2026 | Jun-2026 | 12/2026 | 1,183.60 | N.A. | 1,183.60 | 197.13 | 16.63
530 | JAMMU AND KASHMIR | POWER | DELHI AMRITSAR KATRA EXPRESSWAY (PHASE-II PKG XVIII) DEVELOPMENT AND UPGRADATION OF FOUR LANE ACCESS | NHAI | N24002060 | 3-2023 | 11/2025 | N.A. | 3/2026 | 1,107.00 | N.A. | 975.38 | 338.91 | 38.81
531 | JAMMU AND KASHMIR | POWER | 4/6L ACCESS CONTROL EXPRESSWAY FROM DESIGN CHAINAGE KM 515.000 TO 528.300 (KUNJWANI TO SIDHRA SECTIO | NHAI | N24002061 | 8-2022 | 6/2025 | N.A. | 2/2026 | 2,474.47 | N.A. | 2,894.74 | 923.64 | 40.17
532 | JAMMU AND KASHMIR | POWER | REHABILITATION AND UPGRADATION TO 2 LANE WITH PAVED SHOULDER FROM DESIGN CHAINAGE KM 162.800 TO KM | BRO | N24002119 | 10-2022 | 1/2026 | N.A. | 1/2026 | 562.45 | N.A. | 562.45 | 99.06 | 25.00
533 | JAMMU AND KASHMIR | POWER | CONSTRUCTION OF 4 LANE WITH PAVED SHOULDER (PATTAN BYPASS) GREENFIELD BYPASS FROM EXISTING CH. KM 24 | BRO | N24002179 | 3-2023 | 7/2026 | N.A. | 7/2026 | 980.21 | N.A. | 980.21 | 300.02 | 8.00
534 | JAMMU AND KASHMIR | POWER | REHABILITATION AND UPGRADATION TO 2 LANE WITH PAVED SHOULDER FROM EXISTING CHAINAGE KM 166.100 TO KM | BRO | N24002180 | 9-2021 | 7/2026 | N.A. | 7/2026 | 734.64 | N.A. | 734.64 | 19.60 | 8.00
535 | JAMMU AND KASHMIR | POWER | CONSTRUCTION OF 2 LANE WITH PAVED SHOULDERS (BARAMULLA BYPASS) GREENFIELD BYPASS FROM EXISTING CH. K | BRO | N24002185 | 3-2023 | 9/2026 | N.A. | 9/2026 | 992.43 | N.A. | 992.43 | 338.33 | -
536 | JAMMU AND KASHMIR | POWER | WIDENING AND STRENGTHENING OF RAFIABAD-KUPWARA-CHOWKIBAL- TANGDHAR-CHAMKOT (NH-701) ROAD FROM DESIGN | BRO | N24002210 | 3-2024 | 5/2027 | N.A. | 5/2027 | 1,404.94 | N.A. | 1,404.94 | 0.00 | -
537 | JAMMU AND KASHMIR | POWER | FOUR LANING OF UDHAMBUR - RAMBAN SECTION OF NH-1A | NHAI | N24000488 | 12-2015 | 12/2018 | Nov-2024 | 11/2024 | 2,136.97 | 2,644.00 | 2,644.00 | 2,386.51 | 99.50
538 | JAMMU AND KASHMIR | POWER | CONSTRUCTION OF STAND ALONE RING ROAD/ BYPASS AROUND JAMMU CITY IN THE STATE OF J AND K ON EPC MODE | NHAI | N24000717 | 12-2017 | 7/2021 | Jul-2025 | 7/2025 | 1,471.75 | 1,471.75 | 1,903.98 | 1,731.65 | 98.94
539 | JAMMU AND KASHMIR | POWER | UP-GRADATION TO 4-LANE WITH PAVED SHOULDER OF JAMMU- AKHNOOR ROAD SECTION OF NH-144A FROM GANESH VIHA | NHIDCL | N24000868 | 3-2018 | 7/2021 | Aug-2023 | 10/2025 | 253.44 | N.A. | 253.44 | 191.14 | 83.23
540 | JAMMU AND KASHMIR | POWER | CONSTRUCTION OF (I) CONNECTING ROAD FROM Z-MORH TUNNEL TO ZOJILA TUNNEL AND (II) 14.150 KM LONG BI-D | NHIDCL | N24001256 | 8-2020 | 9/2026 | N.A. | 9/2026 | 6,808.69 | N.A. | 6,808.69 | 3,013.84 | 49.92
541 | JAMMU AND KASHMIR | POWER | UP-GRADATION TO 2-LANE WITH PAVED SHOULDER FROM KM 12.850 TO KM20.300 OF 7.450KM LENGTH ON GOHA-KHEL | NHIDCL | N24001264 | 7-2020 | 4/2022 | Oct-2024 | 10/2026 | 228.39 | N.A. | 228.39 | 69.32 | 88.09
542 | JAMMU AND KASHMIR | POWER | UP-GRADATION TO 2-LANE WITH PAVED SHOULDER FROM KM 20.300 TO KM 29.030 OF 8.730 KM LENGTH ON GOHA-K | NHIDCL | N24001266 | 7-2020 | 4/2022 | Nov-2023 | 8/2025 | 210.79 | N.A. | 210.79 | 72.72 | 93.63
543 | JAMMU AND KASHMIR | POWER | KHELLANI-KHANABAL PKG-1 | NHIDCL | N24001323 | 3-2021 | 9/2022 | Oct-2024 | 11/2024 | 486.45 | N.A. | 486.45 | 126.73 | 96.84
544 | JAMMU AND KASHMIR | POWER | KHELLANI-KHANABAL PKG-3 | NHIDCL | N24001341 | 3-2021 | 12/2022 | Oct-2024 | 5/2025 | 398.51 | N.A. | 398.51 | 80.64 | 98.36
545 | JAMMU AND KASHMIR | POWER | KHELLANI-KHANABAL PKG-2 | NHIDCL | N24001394 | 7-2021 | 2/2023 | Jun-2025 | 6/2026 | 512.43 | N.A. | 512.43 | 71.65 | 51.75
546 | JAMMU AND KASHMIR | POWER | KHELLANI-KHANABAL PKG-4 | NHIDCL | N24001395 | 7-2021 | 8/2023 | Dec-2025 | 6/2026 | 859.67 | N.A. | 859.67 | 196.00 | 44.02
547 | JAMMU AND KASHMIR | POWER | KHELLANI-KHANABAL PKG-5 | NHIDCL | N24001396 | 7-2021 | 2/2023 | Mar-2025 | 8/2025 | 497.09 | N.A. | 497.09 | 178.73 | 90.01
548 | JAMMU AND KASHMIR | POWER | GOHA-KHELLANI PKG-3 | NHIDCL | N24001397 | 2-2021 | 3/2023 | Feb-2025 | 3/2025 | 431.28 | 433.08 | 431.28 | 372.31 | 100.00
549 | JHARKHAND | POWER | RAJRAPPA RCE OCP ( 3.0 MTY) | CCL | N06000087 | 12-2009 | 3/2016 | N.A. | 3/2027 | 510.85 | N.A. | 510.85 | 488.57 | 75.00
550 | JHARKHAND | POWER | MURAIDIH UG TURN-KEY PROJECT | BCCL | N06000096 | 2-2011 | 4/2014 | N.A. | 12/2026 | 339.88 | N.A. | 339.88 | 190.48 | 70.00
551 | JHARKHAND | POWER | MOONIDIH XV SEAM UG | BCCL | N06000098 | 8-2011 | 3/2019 | N.A. | 5/2026 | 1,230.27 | N.A. | 1,230.27 | 620.97 | 81.00
552 | JHARKHAND | POWER | CHITRA EAST (RCE) OCP | ECL | N06000169 | 8-2018 | 3/2026 | Mar-2026 | 3/2026 | 513.98 | N.A. | 513.98 | 228.35 | 51.00
553 | JHARKHAND | POWER | TETARIAKHAR EXPANSION OCP | CCL | N06000186 | 11-2019 | 3/2023 | N.A. | 3/2027 | 243.52 | N.A. | 243.52 | 44.64 | 26.00
554 | JHARKHAND | POWER | PACHWARA SOUTH COAL BLOCK | NLC | N06000193 | 7-2013 | 9/2028 | N.A. | 9/2028 | 2,242.92 | 2,242.90 | 2,242.90 | 1,151.23 | 54.00
555 | JHARKHAND | POWER | PATHERDIH 2.5 NLW COAL WASHERY | BCCL | N06000194 | 10-2015 | 4/2018 | N.A. | 3/2026 | 334.27 | N.A. | 334.27 | 135.86 | 47.00
556 | JHARKHAND | POWER | REVISED PROJECT REPORT MAGADH EXPANSION OCP | CCL | N06000216 | 8-2020 | 3/2028 | N.A. | 3/2028 | 7,254.37 | N.A. | 7,254.37 | 1,527.57 | 38.00
557 | JHARKHAND | POWER | EXPANSION PROJECT AMRAPALI OCP | CCL | N06000217 | 8-2020 | 3/2028 | N.A. | 3/2028 | 5,136.15 | N.A. | 5,136.15 | 1,092.17 | 43.00
558 | JHARKHAND | POWER | UCE OF EPR OF NORTH URIMARI OCP | CCL | N06000218 | 7-2021 | 3/2029 | N.A. | 3/2029 | 778.80 | N.A. | 778.80 | 694.11 | 75.00
559 | JHARKHAND | POWER | KOTRE BASANTPUR PACHMO OCP | CCL | N06000237 | 8-2020 | 3/2032 | N.A. | 3/2032 | 625.40 | 625.40 | 625.40 | 441.24 | 41.00
560 | JHARKHAND | POWER | CHANDRAGUPT OCP | CCL | N06000238 | 8-2020 | 3/2032 | N.A. | 3/2032 | 973.50 | N.A. | 973.50 | 440.56 | 12.40
561 | JHARKHAND | POWER | SIRKA OCP | CCL | N06000239 | 5-2020 | 3/2028 | N.A. | 3/2028 | 222.82 | N.A. | 222.82 | 139.31 | 51.00
562 | JHARKHAND | POWER | JHARKHAND LAIYO OCP | CCL | N06000240 | 8-2020 | 3/2031 | N.A. | 3/2031 | 764.57 | N.A. | 764.57 | 145.80 | 28.00
563 | JHARKHAND | POWER | EPR TAPIN SOUTH OCP | CCL | N06000241 | 11-2020 | 3/2028 | N.A. | 3/2028 | 230.41 | N.A. | 230.41 | 21.12 | 18.30
564 | JHARKHAND | POWER | EPR PUNDI OCP | CCL | N06000242 | 11-2020 | 3/2027 | N.A. | 3/2027 | 713.35 | N.A. | 713.35 | 236.57 | 21.00
565 | JHARKHAND | POWER | EPR ROHINI KARKATA OCP | CCL | N06000243 | 1-2021 | 3/2028 | N.A. | 3/2028 | 1,020.42 | N.A. | 1,020.42 | 83.44 | 18.00
566 | JHARKHAND | POWER | EXPANSION OF KONAR OCP | CCL | N06000245 | 1-2022 | 3/2032 | N.A. | 3/2032 | 799.34 | N.A. | 799.34 | 416.73 | 32.00
567 | JHARKHAND | POWER | EXPANSION OF KARO OCP | CCL | N06000246 | 1-2022 | 3/2029 | N.A. | 3/2029 | 908.47 | N.A. | 908.47 | 217.68 | 21.00
568 | JHARKHAND | POWER | EXPANSION OF ASHOK OCP | CCL | N06000247 | 5-2021 | 3/2028 | N.A. | 3/2028 | 2,898.28 | N.A. | 2,898.28 | 176.50 | 20.00
569 | JHARKHAND | POWER | AMALGAMATED NTST KUJAMA OCP 8.5 MTY | BCCL | N06000273 | 1-2023 | 3/2030 | N.A. | 3/2030 | 4,011.85 | N.A. | 4,011.85 | 398.49 | 25.10
570 | JHARKHAND | POWER | HURA C OC | ECL | N06000275 | 8-2022 | 3/2029 | N.A. | 3/2029 | 859.41 | N.A. | 859.41 | 448.72 | 62.00
571 | JHARKHAND | POWER | CHUPERBHITA- SIMLONG OCP | ECL | N06000280 | 12-2023 | 3/2037 | Mar-2037 | 3/2037 | 979.08 | N.A. | 979.08 | 0.00 | 0.01
572 | JHARKHAND | POWER | BLOCK-E OCP (15 MTY) | BCCL | N06000287 | 3-2024 | 3/2029 | N.A. | 3/2029 | 5,850.83 | N.A. | 5,850.83 | 5.96 | 2.00
573 | JHARKHAND | POWER | JARANGDIH OCP | CCL | N06000295 | 2-2020 | 3/2029 | N.A. | 3/2029 | 414.37 | N.A. | 414.37 | 85.60 | -
574 | JHARKHAND | DEPARTMENT OF HIGHER EDUCATION | 2000 BOYS HOSTEL(1000 DOUBLE BEDDED ROOM) AT ISM DHANBAD | CPWD EDUCATION | N28000067 | 9-2012 | 3/2016 | N.A. | 3/2016 | 171.86 | N.A. | 171.86 | 174.48 | 99.00
575 | JHARKHAND | PETROLEUM | DEVELOPMENT OF JHARIA CBM BLOCK (PHASE-1) | ONGC | N16000445 | 11-2019 | 1/2024 | Mar-2025 | 6/2025 | 431.00 | N.A. | 431.00 | 204.31 | 58.00
576 | JHARKHAND | PETROLEUM | LAYING OF NATURAL GAS PIPELINE FROM HAZARIBAGH TO RANCHI | IOCL | N16000480 | 3-2023 | 2/2026 | N.A. | 2/2026 | 202.07 | N.A. | 202.07 | 52.94 | 42.95
577 | JHARKHAND | PETROLEUM | CGD PROJECT IN BIHAR JHARKHAND | HPCL | N16000497 | 6-2022 | 6/2030 | N.A. | 6/2030 | 1,377.00 | N.A. | 1,377.00 | 282.88 | 24.15
578 | JHARKHAND | PETROLEUM | NORTH KARANPURA STPP (3X660 MW) | NTPC | N18000177 | 2-2014 | 6/2019 | Oct-2022 | 3/2025 | 16,242.90 | N.A. | 16,242.90 | 17,323.08 | 98.00
579 | JHARKHAND | PETROLEUM | PATRATU STPP-I (3X800MW) | NTPC | N18000275 | 11-2017 | 3/2023 | N.A. | 3/2026 | 17,112.00 | N.A. | 17,112.00 | 17,219.35 | 81.00
580 | JHARKHAND | PETROLEUM | BADAM COAL MINING PROJECT | NTPC | N18000367 | 2-2019 | 10/2024 | Apr-2027 | 4/2027 | 501.79 | 784.39 | 501.79 | 368.94 | 59.79
581 | JHARKHAND | PETROLEUM | KERANDARI COAL MINING PROJECT | NTPC | N18000370 | 9-2015 | 11/2019 | Mar-2025 | 3/2025 | 1,553.00 | 2,896.64 | 2,896.64 | 2,095.17 | 64.00
582 | JHARKHAND | PETROLEUM | KODERMA-TILAIYA (NL), ECR | ECR | 220100305 | 4-2002 | 3/2023 | N.A. | 12/2025 | 1,625.87 | 1,625.87 | 1,700.00 | 2,039.52 | 80.00
583 | JHARKHAND | PETROLEUM | BONDAMUNDA RANCHI DOUBLING | SER | N22000396 | 3-2016 | 6/2024 | N.A. | 6/2026 | 3,029.04 | 3,029.04 | 3,029.04 | 2,436.91 | 84.50
584 | JHARKHAND | PETROLEUM | LODHMA TO PISKA LINK LINE BY PASSING HATIA/RANCHI WITH Y CONNECTION (17.2 KM) | SER | N22000508 | 4-2018 | 6/2026 | N.A. | 6/2026 | 501.52 | N.A. | 472.50 | 275.97 | 4.00
585 | JHARKHAND | PETROLEUM | DOUBLING OF PRADHANKHUNTA JN - PATHERDIH BAZAR-BHOJUDIH | ECR | N22000529 | 11-2022 | 11/2027 | N.A. | 3/2026 | 202.00 | 349.22 | 349.22 | 76.94 | 2.00
586 | JHARKHAND | PETROLEUM | KHARAGPUR-ADITYAPUR - 3RD LINE (132 KM) | RVNL | N22000595 | 12-2015 | 3/2025 | N.A. | 3/2025 | 3,249.98 | N.A. | 3,270.07 | 2,899.45 | -
587 | JHARKHAND | PETROLEUM | 3RD LINE BETWEEN DHANBAD SONNAGAR | RVNL | N22000599 | 11-2016 | 3/2026 | N.A. | 3/2026 | 8,975.00 | N.A. | 7,906.38 | 4,705.38 | -
588 | JHARKHAND | PETROLEUM | GARHWA ROAD - RAIL OVER RAIL | ECR | N22000610 | 3-2017 | 6/2024 | N.A. | 2/2026 | 262.71 | N.A. | 262.71 | 227.86 | 70.00
589 | JHARKHAND | PETROLEUM | GOMOH - FLYOVER FOR DOWN TRAINS | ECR | N22000611 | 1-2018 | 3/2023 | N.A. | 3/2026 | 686.03 | N.A. | 487.73 | 419.46 | 45.00
590 | JHARKHAND | PETROLEUM | HARIHARGANJ TO PARWA MODE SECTION FROM KM 23.284 TO KM 57.049 OF NH-98 | NHAI | N24001589 | 9-2020 | 3/2024 | Dec-2024 | 4/2025 | 755.26 | N.A. | 1,039.00 | 635.78 | 88.10
591 | JHARKHAND | PETROLEUM | 4L FROM KM 196.87 (SANKHA) TO KM 219.6 (KHAJURI) ON NH-75 [REHLA / GARHWA BYPASS] | NHAI | N24001590 | 9-2020 | 10/2023 | Dec-2024 | 1/2025 | 748.99 | N.A. | 903.00 | 831.75 | 100.00
592 | JHARKHAND | PETROLEUM | ELEVATED CORRIDOR IN RANCHI CITY FROM KM 0.00 TO KM 3.260 OF NH-75 INCLUDING DOWN RAMP ON NH-23 FROM | NHAI | N24001594 | 2-2022 | 1/2025 | Mar-2025 | 3/2025 | 534.73 | N.A. | 534.73 | 282.33 | 99.57
593 | JHARKHAND | PETROLEUM | 4L OF PALMA TO GUMLA SECTION OF NH23 FROM KM. 26.00 TO KM. 89.170 ON HAM MODE IN THE STATE OF JHARKH | NHAI | N24001595 | 8-2020 | 3/2024 | Sep-2025 | 9/2025 | 1,034.00 | 1,879.55 | 1,879.55 | 41.50 | 97.30
594 | JHARKHAND | PETROLEUM | 4L OF MIRZA CHAUKI TO FARKKA SECTION OF NH80 FROM KM 215.00 TO KM 260.00 ON HAM MODE IN THE STATE OF | NHAI | N24001596 | 11-2021 | 7/2023 | Jun-2025 | 12/2025 | 1,302.72 | 1,504.80 | 1,504.80 | 957.00 | 75.74
595 | JHARKHAND | PETROLEUM | FOUR LANING WITH PAVED SHOULDER OF SECTION FROM KM 53.600 (GOLA ON NH-320) TO KM 81.446 (ORMANJHI ON | NHAI | N24001854 | 6-2023 | 6/2025 | N.A. | 6/2025 | 1,214.93 | 1,324.95 | 1,462.00 | 808.69 | 75.50
596 | JHARKHAND | PETROLEUM | WIDENING TO 2-LANE WITH PAVED SHOULDER FROM KM 0.00 TO 44.00 (KURU-GHAGHRA SECTION) OF NH- 143A INCLU | MoRTH | N24001922 | 2-2020 | 8/2023 | N.A. | 12/2024 | 153.01 | N.A. | 153.01 | 83.63 | 96.23
597 | JHARKHAND | PETROLEUM | WIDENING AND STRENGTHENING OF EXISTING PAVEEMNT TO TWO LANE WITH PAVED SHOULDERS FROM KM 116.00 TO K | MoRTH | N24001923 | 1-2022 | 7/2024 | N.A. | 12/2024 | 315.21 | N.A. | 315.21 | 117.26 | 80.00
598 | JHARKHAND | PETROLEUM | WIDENING AND STRENGTHENING TO TWO LANE WITH PAVED SHOULDER/TWO LANE+ PAVED SHOULDER WITH SERVICE ROA | MoRTH | N24001924 | 3-2022 | 8/2025 | N.A. | 8/2025 | 514.22 | N.A. | 514.22 | 15.19 | 6.10
599 | JHARKHAND | PETROLEUM | WIDENING AND STRENGTHENING/RECONSTRUCTION TO TWO LANE WITH PAVED SHOULDER/ TWO LANE WITH PAVED SHOUL | MoRTH | N24001925 | 3-2022 | 8/2025 | N.A. | 8/2025 | 423.18 | N.A. | 423.18 | 0.11 | -
600 | JHARKHAND | PETROLEUM | FOUR LANING OF KHAJURI TO WYNDHAMGANJ FROM KM 219.600 TO KM 260.483 ON NH-75 PKG SEC-V ON HAM | NHAI | N24002053 | 4-2022 | 9/2025 | N.A. | 9/2025 | 1,232.00 | 1,343.00 | 1,400.00 | 606.60 | 81.76
601 | JHARKHAND | PETROLEUM | FOUR LANING OF BHOGU TO SANKHA FROM KM 147.450 TO KM 196.870 ON NH-75 PKG SEC-III | NHAI | N24002054 | 10-2022 | 11/2025 | N.A. | 11/2025 | 1,390.77 | 1,391.00 | 1,600.00 | 319.69 | 75.01
602 | JHARKHAND | PETROLEUM | FOUR LANING OF BASUKINATH- DEOGHAR SECTION OF NH-114A FROM KM 85.081 TO KM 130.240 UNDER NHDP PHASE-I | NHAI | N24002055 | 3-2023 | 12/2025 | N.A. | 12/2025 | 1,444.94 | N.A. | 1,444.94 | 0.00 | -
603 | JHARKHAND | PETROLEUM | BHARATMALA PARIYOJANA OF BOKARO JAINA MORE - GOLA SECTION OF NH-320 FROM KM. 21.110 TO KM. 53.600 IN | NHAI | N24002056 | 6-2020 | 6/2025 | N.A. | 6/2025 | 964.64 | N.A. | 964.64 | 458.58 | 61.20
604 | JHARKHAND | PETROLEUM | FOUR LANING OF MEHGAMA HANSDIHA SECTION OF NH-33 FROM EXISTING KM 41.900 TO 93.000 IN THE STATE OF J | NHAI | N24002057 | 12-2022 | 5/2025 | N.A. | 5/2025 | 1,443.77 | N.A. | 1,443.77 | 0.00 | -
605 | JHARKHAND | PETROLEUM | SIX LANING OF BIHAR - JHARKHAND BORDER (CHORDAHA) TO GORHAR SECTION | NHAI | N24000726 | 1-2018 | 11/2021 | May-2026 | 5/2026 | 1,155.16 | N.A. | 950.49 | 657.82 | 73.00
606 | JHARKHAND | PETROLEUM | WIDENING TO 2 LANE WITH PAVED SHOULDERS AND GEOMETRIC IMPROVEMENT OF NH-114A FROM KM 141 TO KM 184 I | MoRTH | N24001216 | 12-2016 | 9/2021 | N.A. | 12/2024 | 196.00 | N.A. | 196.00 | 164.21 | 90.10
607 | JHARKHAND | STEEL | NEW SINTER PLANT AT BOKARO STEEL PLANT | SAIL | N12000095 | 3-2015 | 10/2017 | Nov-2026 | 11/2026 | 1,034.01 | 1,752.30 | 1,752.30 | 882.41 | 51.75
608 | JHARKHAND | STEEL | REVAMPING OF OLD SUB SYSTEM OF BLAST FURNACE 3 AT BOKARO STEEL PLANT | SAIL | N12000129 | 9-2023 | 7/2025 | Nov-2025 | 11/2025 | 513.82 | N.A. | 513.82 | 195.71 | 67.00
609 | JHARKHAND | STEEL | REBUILDING OF COKE OVEN BATTERY NO.6 OF BOKARO STEEL PLANT | SAIL | N12000133 | 11-2023 | 11/2026 | N.A. | 11/2026 | 627.31 | N.A. | 627.31 | 84.56 | 35.00
610 | JHARKHAND | STEEL | REPLACEMENT OF REMAINING 04 NOS. OF BATTERY CYCLONES WITH 04 NOS. OF ESPS IN SINTER PLANT-1 AT BSL | SAIL | N12000135 | 3-2024 | 6/2026 | N.A. | 6/2026 | 260.37 | N.A. | 260.37 | 44.22 | 18.00
611 | JHARKHAND | STEEL | REPLACEMENT OF EXISTING GRINDERS IN CRM-I & II AT BOKARO STEEL PLANT | SAIL | N12000142 | 1-2025 | 1/2027 | N.A. | 1/2027 | 211.94 | N.A. | 211.94 | 0.00 | -
612 | JHARKHAND | STEEL | SECONDARY EMISSION CONTROL IN CONVERTERS OF SMS-II AT BOKARO STEEL PLANT | SAIL | N12000143 | 1-2025 | 10/2026 | N.A. | 10/2026 | 207.13 | N.A. | 207.13 | 0.00 | 5.00
613 | KARNATAKA | CIVIL AVIATION | BELAGAVI AIRPORT- EXPANSION OF TERMINAL BUILDING AND ASSOCIATED WORKS | AAI | N04000105 | 6-2023 | 2/2026 | N.A. | 2/2026 | 322.45 | N.A. | 322.45 | 104.38 | 43.00
614 | KARNATAKA | CIVIL AVIATION | HUBBALI AIRPORT - CONSTRUCTION OF NEW DOMESTIC TERMINAL BUILDING AND MISCELLANEOUS WORKS | AAI | N04000108 | 6-2023 | 2/2026 | N.A. | 2/2026 | 320.47 | N.A. | 320.47 | 53.87 | 32.50
615 | KARNATAKA | DEPARTMENT OF HIGHER EDUCATION | CONSTRUCTION OF PERMANENT CAMPUS FOR INDIAN INSTITUTE OF TECHNOLOGY, DHARWAD (PHASE 1A) | CPWD EDUCATION | N42000006 | 7-2019 | 3/2022 | N.A. | 11/2025 | 851.00 | 851.00 | 930.36 | 918.06 | -
616 | KARNATAKA | DEPARTMENT OF HIGHER EDUCATION | ADDITIONAL INFRASTRUCTURE AT IISC BANGALORE SH RCC MONOLITHIC FOR MEN WOMEN HOSTEL | CPWD | N42000010 | 8-2021 | 2/2024 | Nov-2024 | 11/2024 | 316.25 | N.A. | 316.25 | 281.32 | 91.00
617 | KARNATAKA | PETROLEUM | CONSTRUCTION OF 80000MT LPG CAVERN AT MANGALORE | HPCL | N16000369 | 12-2018 | 12/2022 | Aug-2025 | 8/2025 | 854.00 | 854.00 | 854.00 | 717.44 | 99.70
618 | KARNATAKA | PETROLEUM | REVAMPING, AUGMENTATION OF FACILITIES AT EXISTING PORT TERMINAL AT MANGALORE | IOCL | N16000437 | 1-2022 | 7/2025 | Dec-2025 | 12/2025 | 463.00 | 500.62 | 500.62 | 244.46 | 71.10
619 | KARNATAKA | PETROLEUM | POWER SYSTEM UPGRADATION PROJECT | MANGALORE REFIN | N16000509 | 10-2023 | 2/2026 | N.A. | 2/2026 | 385.00 | N.A. | 385.00 | 129.72 | 59.70
620 | KARNATAKA | PETROLEUM | DEMO PLANT FOR PRODUCTION OF BIO-ATF | MANGALORE REFIN | N16000536 | 3-2024 | 3/2027 | N.A. | 3/2027 | 364.00 | N.A. | 364.00 | 22.78 | 10.10
621 | KARNATAKA | POWER | TS FOR INTRGRATION OF RE ZONE (PHASE II) IN KOPPAL II (PHASE A and B) AND GADAG II (PHASE A) IN KARN | PGCIL | N18000385 | 12-2023 | 12/2025 | N.A. | 12/2025 | 2,889.00 | N.A. | 2,889.00 | 1,011.29 | 36.70
622 | KARNATAKA | POWER | TS FOR SOLAR ENERGY ZONE IN BIDAR (2500MW), KARNATAKA [BIDAR TRANSMISSION LTD] | PGCIL | N18000388 | 2-2024 | 2/2026 | N.A. | 2/2026 | 2,148.00 | N.A. | 2,148.00 | 923.47 | 52.20
623 | KARNATAKA | POWER | SYSTEM STRENGTHENING AT KOPPAL- II AND GADAG-II FOR INTEGRATION OF RE GENERATION PROJECTS | PGCIL | N18000409 | 1-2025 | 1/2027 | N.A. | 1/2027 | 1,354.00 | N.A. | 1,354.00 | 16.25 | -
624 | KARNATAKA | POWER | AUGMENTATION OF TRANSFORMATION CAPACITY AT BIDAR PS | PGCIL | N18000410 | 2-2025 | 2/2027 | N.A. | 2/2027 | 288.00 | N.A. | 288.00 | 4.03 | -
625 | KARNATAKA | POWER | TRANSMISSION SCHEME FOR INTEGRATION OF DAVANAGERE / CHITRADURGA AND BELLARY REZ IN KARNATAKA | PGCIL | N18000419 | 3-2025 | 3/2027 | N.A. | 3/2027 | 3,453.00 | N.A. | 3,453.00 | 20.70 | -
626 | KARNATAKA | POWER | TUMKUR-CHITRADURGA-DAVENGERE NL | SWR | N22000256 | 4-2011 | 3/2019 | N.A. | 12/2027 | 1,876.00 | N.A. | 1,801.01 | 503.99 | 12.00
627 | KARNATAKA | POWER | BAGALKOT-KUDACHI NL | SWR | N22000258 | 4-2010 | 3/2027 | N.A. | 12/2028 | 1,378.00 | 1,378.00 | 1,378.00 | 646.95 | 34.00
628 | KARNATAKA | POWER | HOSPET-HUBLI-LONDA- VASCODAGAMA DL | RVNL | N22000297 | 4-2010 | 3/2027 | N.A. | 12/2026 | 5,060.36 | N.A. | 3,692.60 | 3,505.49 | -
629 | KARNATAKA | POWER | GADAG-WADI NL | SWR | N22000299 | 4-2013 | 3/2027 | N.A. | 3/2028 | 2,841.84 | N.A. | 2,841.84 | 1,352.94 | 29.00
630 | KARNATAKA | POWER | MARIKUPPAM - KUPPAM | SWR | N22000308 | 4-2012 | 3/2016 | N.A. | 12/2027 | 279.54 | 296.72 | 296.72 | 121.12 | 14.00
631 | KARNATAKA | POWER | KADUR CHIKMAGALUR SAKLESHPUR NEW LINE (93 KM) | SWR | N22000486 | 3-1996 | 6/2025 | N.A. | 3/2026 | 825.31 | 825.31 | 825.31 | 692.24 | 83.00
632 | KARNATAKA | POWER | BAIYYAPPANAHALLI-HOSUR (48 KM) | NCRTC | N22000542 | 4-2019 | 3/2026 | N.A. | 3/2026 | 375.67 | N.A. | 375.67 | 0.00 | -
633 | KARNATAKA | POWER | YESHVANTHPUR-CHANNASANDRA (21.7 KM) | NCRTC | N22000543 | 4-2019 | 3/2026 | N.A. | 3/2026 | 169.65 | N.A. | 169.65 | 71.75 | -
634 | KARNATAKA | POWER | BELGAUM-DHARWAD VIA KITTUR (73.10 KM) (UMBRELLA WORK PB#22/2019-20/NR) | SWR | N22000557 | 9-2020 | 12/2027 | N.A. | 3/2029 | 1,590.80 | 927.42 | 927.42 | 0.75 | -
635 | KARNATAKA | POWER | HASSAN (ALUR) - BELUR (32 KM) (UMBRELLA WORK PB#23/2018-19/NR) | SWR | N22000558 | 6-2019 | 4/2028 | N.A. | 3/2028 | 748.86 | 748.85 | 748.85 | 0.88 | 1.00
636 | KARNATAKA | POWER | SHIMOGA-SHIKARIPURA-RANEBENNUR (UMBRELLA WORK PB#23/2018-19/NR) | SWR | N22000559 | 9-2019 | 12/2027 | N.A. | 12/2028 | 1,453.73 | 994.47 | 994.47 | 87.33 | 7.00
637 | KARNATAKA | POWER | BANGALORE-WHITEFIELD-BANGALORE CITY-KRISHNARAJAPURAM QUADRUPLING | SWR | N22000621 | 3-2018 | 6/2025 | N.A. | 2/2026 | 492.87 | 492.87 | 492.87 | 254.35 | 75.00
638 | KARNATAKA | POWER | 4L OF ADDAHOLE TO BANTWAL CROSS SECTION INCLUDING FLYOVER AT KALLADKA TOWN | NHAI | N24001425 | 3-2021 | 11/2021 | Nov-2025 | 11/2025 | 1,100.88 | 1,687.31 | 1,687.31 | 1,156.26 | 80.30
639 | KARNATAKA | POWER | 4L OF ADDAHOLE TO BANTWAL CROSS SECTION | NHAI | N24001426 | 3-2021 | 10/2021 | Jul-2025 | 7/2025 | 317.90 | 572.01 | 572.01 | 370.84 | 98.00
640 | KARNATAKA | POWER | 6L FROM SANKESHWAR BYPASS TO MH KNT BORDER FROM KM. 555.017 TO KM. 592.853 OF NH-48 (PKG II) | NHAI | N24001598 | 1-2022 | 4/2025 | May-2026 | 5/2026 | 1,388.70 | 1,388.70 | 1,388.70 | 509.84 | 71.60
641 | KARNATAKA | POWER | BELAKERI PORT TO KUMTA - SIRSI ROAD FROM KM 0.00 - KM 4.265 OF BELEKERI PORT ROAD LINK RD. AND KM 4. | NHAI | N24001599 | 3-2018 | 12/2022 | Dec-2022 | 12/2025 | 440.16 | N.A. | 440.16 | 355.97 | 75.27
642 | KARNATAKA | POWER | BANGALORE/TN BORDER TO HOSKOTE | NHAI | N24001674 | 2-2023 | 2/2025 | Sep-2025 | 9/2025 | 1,240.60 | 1,181.68 | 1,181.68 | 952.87 | 83.25
643 | KARNATAKA | POWER | 6L OF MH/KN BORDER (NIMBAL VILLAGE) TO KN/TS BORDER (SINGNODI VILLAGE) FROM KM. 26.000 TO KM. 97.000 | NHAI | N24001676 | 12-2022 | 6/2025 | Mar-2026 | 6/2025 | 2,718.46 | N.A. | 2,718.46 | 438.90 | 54.52
644 | KARNATAKA | POWER | BALANCE WORK OF 2L PS FROM KM 30.800 TO 70.800 AND 2L WITH RIGID CARRIAGEWAY FROM 70.800 TO KM 84.12 | NHAI | N24001677 | 11-2022 | 5/2024 | Apr-2025 | 4/2025 | 226.76 | 226.76 | 226.76 | 86.76 | 71.95
645 | KARNATAKA | POWER | 6L FROM BELGAUM TO SANKESHWAR BYPASS FROM KM 515.000 TO KM 555.017 OF NH 48 | NHAI | N24001679 | 10-2022 | 4/2025 | Dec-2025 | 12/2025 | 1,479.30 | 1,479.30 | 1,479.30 | 676.61 | 83.98
646 | KARNATAKA | POWER | 4L OF SANNUR TO BIKARNAKATTE SECTION FROM KARKALA TO MANGALORE | NHAI | N24001680 | 3-2021 | 10/2024 | Jun-2026 | 6/2026 | 1,409.68 | 1,808.12 | 1,808.12 | 1,039.17 | 59.00
647 | KARNATAKA | POWER | TUMKUR - NELAMANGALA(6L) | NHAI | N24001681 | 8-2022 | 8/2025 | Mar-2026 | 3/2026 | 2,032.15 | 2,032.15 | 2,032.15 | 185.64 | 52.88
648 | KARNATAKA | POWER | UPGRADATION 2/4 LANE NH CONNECTIVITY UNDER SAGARMALA SCHEME SH 2 HAVERI YEKAMBI SH 69 YEKAMBI KUMTA | NHAI | N24001682 | 11-2021 | 3/2024 | Mar-2024 | 12/2026 | 294.62 | 309.90 | 309.90 | 57.86 | 15.14
649 | KARNATAKA | POWER | 4L OF CHANNARAYAPATNA BYPASS AND HASSAN BYPASS WITH STRUCTURES IN DEVIHALLI -HASSAN SECTION | NHAI | N24001684 | 9-2020 | 1/2023 | Sep-2020 | 5/2025 | 688.00 | 602.09 | 688.00 | 514.23 | 80.07
650 | KARNATAKA | POWER | FOUR LANING OF BETTADAHALLI TO SRIRAMPURA SECTION FROM KM. 166+100 (DESIGN KM. 170+415) TO KM. 217+0 | NHAI | N24001687 | 10-2021 | 10/2023 | Dec-2025 | 12/2025 | 1,331.77 | 2,082.98 | 2,082.98 | 483.94 | 77.06
651 | KARNATAKA | POWER | BALANCE WORK OF CONTSRUCTION OF TWO/FOUR LANE WITH PAVED SHOULDER FROM KM. 54.370 TO KM. 101.400 (BI | MoRTH | N24001936 | 3-2021 | 3/2023 | Jul-2024 | 7/2024 | 344.79 | N.A. | 344.79 | 10.00 | 90.00
652 | KARNATAKA | POWER | BALANCE WORK OF REHABILITATION AND UPGRADING TO 2LANE/2LANE WITH PAVED SHOULDER CONFIGURATION AND ST | MoRTH | N24001937 | 2-2023 | 2/2024 | Feb-2025 | 2/2025 | 398.48 | N.A. | 398.48 | 5.00 | 50.00
653 | KARNATAKA | POWER | CONSTRUCTION OF ELEVATED CORRIDOR FROM KM. 135.650 TO 136.300 ON 63, FROM KM. 249 TO KM. 250.050 ON | MoRTH | N24001938 | 6-2021 | 6/2024 | Jun-2025 | 6/2025 | 298.00 | N.A. | 298.00 | 10.70 | 52.00
654 | KARNATAKA | POWER | WIDENING TO 2 LANE WITH PAVED SHOULDERS FROM DESIGN KM 103.200 (EXISTING KM 103.200) TO DESIGN KM 11 | MoRTH | N24001940 | 1-2023 | 1/2026 | Sep-2025 | 9/2025 | 166.58 | N.A. | 166.58 | 3.54 | -
655 | KARNATAKA | POWER | WIDENING TO 4 LANE FROM KM. 133.00 TO 158.04 (DESIGN CHAINAGE KM. 130.88 TO 155.145) (SHIRUR CROSS T | MoRTH | N24001941 | 1-2023 | 1/2025 | Jan-2025 | 1/2025 | 350.69 | N.A. | 350.69 | 10.00 | 56.00
656 | KARNATAKA | POWER | WIDENING TO TWO LANE WITH PAVED SHOULDERS FROM KM. 33.13 TO KM. 40.23 AND KM. 52.00 TO KM. 71.00 (EX | MoRTH | N24001943 | 9-2022 | 3/2024 | Jan-2025 | 1/2025 | 172.98 | N.A. | 172.98 | 6.48 | 65.00
657 | KARNATAKA | POWER | WIDENING TO INTERMEDIATE/TWO LANE TO 2 LANE WITH PAVED SHOULDER FROM EXISTING CHANAGES KM 112.750 TO | MoRTH | N24001944 | 1-2023 | 6/2024 | Jul-2024 | 7/2024 | 255.88 | N.A. | 255.88 | 60.99 | 78.24
658 | KARNATAKA | POWER | WIDENING TO 2 LANE WITH PAVED SHOULDERS FROM KM 116.800 TO 149.070(DESIGN CHANGES) ON HOSADURGA HOL | MoRTH | N24001945 | 8-2022 | 2/2024 | Dec-2024 | 12/2024 | 170.34 | N.A. | 170.34 | 4.25 | 72.00
659 | KARNATAKA | POWER | WIDENING TO 2 LANES WITH PAVED SHOULDERS FROM KM 24.400 TO 27.270, 40.500 TO 41.900, 84.300 TO 88.20 | MoRTH | N24001946 | 11-2022 | 11/2024 | Nov-2024 | 11/2024 | 218.93 | N.A. | 218.93 | 10.00 | 95.25
660 | KARNATAKA | POWER | WIDENING TO EXISTING 2 LANE WITH PAVED SHOULDER TO 4 LANE WITH PAVED SHOULDER FROM DESIGN KM 153.00 | MoRTH | N24001947 | 2-2023 | 2/2025 | Feb-2025 | 2/2025 | 177.94 | N.A. | 177.94 | 6.66 | 47.00
661 | KARNATAKA | POWER | WIDENING TO 4 LANE FROM KM 51.60 TO 76.20 (HEBRI TO PARKALA) AND FROM KM 85.20 TO 88.90 (KARAVALI JU | MoRTH | N24001948 | 10-2022 | 10/2024 | Dec-2024 | 12/2024 | 355.72 | N.A. | 355.72 | 11.32 | 60.00
662 | KARNATAKA | POWER | FOUR LANING OF LEFT OVER WORKS OF HOSPET BELLARY KARNATAKA/ AP BORDER FROM KM.280.080 TO KM. 375.450 | NHAI | N24001989 | 3-2023 | 5/2025 | N.A. | 5/2025 | 830.28 | N.A. | 830.28 | 692.62 | 77.10
663 | KARNATAKA | POWER | DEVELOPMENT OF 6 LANE ACCESS CONTROLLED GREENFIELD HIGHWAY FROM KM. 97.000 TO KM. 162.500 MARADGI S | NHAI | N24001993 | 12-2022 | 10/2025 | N.A. | 10/2025 | 1,589.00 | N.A. | 1,589.00 | 732.47 | 63.15
664 | KARNATAKA | POWER | 4/6L OF BANGALORE - PUNE SECTION OF BYPASS CONNECTING DHARWAD - HUBLI FROM KM. 403.80 TO KM. 433.20 | NHAI | N24001994 | 5-2022 | 3/2023 | Sep-2025 | 9/2025 | 1,135.39 | N.A. | 1,135.39 | 396.27 | 70.68
665 | KARNATAKA | POWER | BALANCE WORK OF CONSTRUCTION OF TWO/FOUR LANE WITH PAVED SHOULDER FROM KM 422.000 TO 523.600 ( CHITR | MoRTH | N24002011 | 12-2021 | 6/2024 | Dec-2024 | 12/2024 | 516.96 | N.A. | 516.96 | 19.93 | 75.00
666 | KARNATAKA | POWER | WIDENING TO TWO LANE WITH PAVED SHOULDERS FROM KM 40.00 TO KM 75.00 (EXISTING CHAINAGES) OF MANGALOR | MoRTH | N24002012 | 3-2023 | 3/2025 | Mar-2025 | 3/2025 | 718.52 | N.A. | 718.52 | 24.81 | 23.00
667 | KARNATAKA | POWER | CONSTRUCTION OF TWO LANE WITH PAVED SHOULDER FROM KM.0 TO KM. 80 ON NH 548B (VIJAYAPURA- SANKESWAR SE | MoRTH | N24002013 | 3-2021 | 2/2022 | Oct-2024 | 10/2024 | 766.64 | N.A. | 766.64 | 13.55 | 75.00
668 | KARNATAKA | POWER | WIDENING TO 2 LANE WITH PAVED SHOULDERS FROM DESIGN KM 103.200 (EXISTING KM 103.200) TO DESIGN KM 11 | MoRTH | N24002186 | 3-2024 | 9/2025 | N.A. | 9/2025 | 166.58 | N.A. | 166.58 | 3.62 | -
669 | KARNATAKA | POWER | CONSTRUCTION OF 2 LANE WITH PAVED SHOULDER FROM KM 55.6 TO KM 90.7 (EXISTING CHAINAGES) OF NH- 766C ( | MoRTH | N24002187 | 2-2024 | 2/2026 | N.A. | 2/2026 | 313.56 | N.A. | 313.56 | 53.65 | -
670 | KARNATAKA | POWER | WIDENING TO 2L+PS FROM KM 71.00 TO 104.00 (EXISTING CHAINAGES) (SARJAPUR TO PATTADKALLU) ON BHANAPUR | MoRTH | N24002188 | 3-2024 | 3/2026 | N.A. | 3/2026 | 445.62 | N.A. | 445.62 | 33.24 | -
671 | KARNATAKA | POWER | WIDENING TO TWO LANE WITH PAVED SHOULDERS FROM KM 0.00 (DESIGN CHAINAGE 0.00) TO KM 23.338 (DESIGN C | MoRTH | N24002189 | 9-2024 | 3/2026 | N.A. | 3/2026 | 196.05 | N.A. | 196.05 | 2.34 | -
672 | KARNATAKA | POWER | STRENGTHENING AND WIDENING TO TWO LANE WITH PAVED SHOULDERS FROM KM.106.00 TO 153.00 OF NH-218 BIJAP | MoRTH | N24000334 | 3-2015 | 11/2015 | Aug-2024 | 8/2024 | 165.67 | N.A. | 165.67 | 126.47 | 98.99
673 | KARNATAKA | POWER | 4-LANING OF GOA/KARNATAKA BORDER-KUNDAPUR SECTION | NHAI | N24000462 | 7-2012 | 8/2016 | Jan-2020 | 12/2025 | 1,655.01 | 1,990.99 | 1,990.99 | 1,824.10 | 97.80
674 | KARNATAKA | POWER | WIDENING TO TWO LANE WITH PAVED SHOULDER FROM KM 544.200 TO KM 594.000 OF NH-150A HOSMANE CROSS ? PA | MoRTH | N24001156 | 1-2017 | 9/2017 | May-2023 | 5/2023 | 166.67 | N.A. | 264.34 | 192.08 | 100.00
675 | KARNATAKA | POWER | IMPROVEMENTS AND RECONSTRUCTION TO TWO LANE WITH PAVED SHOULDERS FROM KM 243.20 TO KM 290.20 OF NH | MoRTH | N24001157 | 8-2016 | 2/2017 | Jul-2024 | 7/2024 | 175.50 | N.A. | 241.60 | 178.73 | 90.01
676 | KARNATAKA | POWER | RECONSTRUCTION TO TWO LANE WITH PAVED SHOULDERS FROM DS. CH. 442+180 (EX. KM 448.00) TO DS. CH.485+2 | MoRTH | N24001158 | 3-2018 | 6/2019 | Dec-2023 | 12/2023 | 159.97 | N.A. | 242.61 | 113.15 | 100.00
677 | KARNATAKA | POWER | WIDENING TO TWO LANE WITH PAVED SHOULDERS FROM KM 20.150 TO KM 40.00 OF BC ROAD KOTTIGEHARA SECTION | MoRTH | N24001159 | 1-2018 | 7/2018 | N.A. | 3/2022 | 159.70 | N.A. | 159.70 | 142.88 | 100.00
678 | KARNATAKA | POWER | WIDENING TO TWO LANE WITH PAVED SHOULDER FROM KM 194.900 TO KM 243.200 OF NH-234 BANAVARA- HULIYAR | MoRTH | N24001160 | 9-2017 | 10/2018 | Apr-2022 | 4/2022 | 191.60 | N.A. | 191.60 | 112.01 | 100.00
679 | KARNATAKA | POWER | WIDENING TO TWO LANE WITH PAVED SHOULDERS FROM 24.600 TO 70.063 OF MUDIGERE TO KADUR SECTION OF NH- | MoRTH | N24001161 | 12-2017 | 1/2019 | Apr-2022 | 4/2022 | 297.30 | N.A. | 318.28 | 277.27 | 100.00
680 | KARNATAKA | POWER | IMPROVEMENT AND RECONSTRUCTION TO TWO LANE WITH PAVED SHOULDERS FROM KM 489.845 (NEW KM.58.125) AN | MoRTH | N24001162 | 3-2018 | 10/2018 | Nov-2022 | 11/2022 | 325.86 | N.A. | 386.41 | 356.76 | 100.00
681 | KARNATAKA | POWER | WIDENING TO 2 LANE WITH PAVED SHOULDERS FROM KM 0 TO 54 OF NH- 50 UNDER EPC MODE IN THE STATE OF KARN | MoRTH | N24001164 | 10-2016 | 3/2017 | Jul-2022 | 7/2022 | 396.96 | N.A. | 396.96 | 329.58 | 100.00
682 | KARNATAKA | POWER | WIDENING TO 2 LANE WITH PAVED SHOULDERS FROM KM 34.00 TO 70.900 OF NH-150 UNDER EPC MODE IN THE STAT | MoRTH | N24001165 | 11-2016 | 3/2017 | Oct-2021 | 10/2021 | 314.90 | N.A. | 314.90 | 233.95 | 100.00
683 | KARNATAKA | POWER | WIDENING TWO LANE WITH PAVED SHOULDERS FROM FROM KM.56.00 TO 106.00 OF NH-218 (218-KNT-2014-15- 775) | MoRTH | N24001166 | 3-2015 | 1/2016 | N.A. | 7/2024 | 159.12 | N.A. | 159.12 | 127.72 | 98.00
684 | KARNATAKA | POWER | ESTIMATE FOR WIDENING TWO LANE TO FOUR LANE FROM FROM KM.129.00 TO 144.00 OF NH-63 ANKOLA-GOOTY SECT | MoRTH | N24001168 | 5-2018 | 5/2018 | Dec-2023 | 12/2023 | 171.60 | N.A. | 171.60 | 129.72 | 100.00
685 | KARNATAKA | POWER | WIDENING TO TWO LANE WITH PAVED SHOULDER FROM KM 4.40 TO KM 56.00 OF NH-218 BIJAPURA-HUBLI SECTION U | MoRTH | N24001172 | 1-2017 | 8/2017 | N.A. | 6/2022 | 291.49 | N.A. | 291.49 | 238.77 | 100.00
686 | KARNATAKA | POWER | CONSTRUCTION OF MAJOR BRIDGE AT KM 180.865 ACROSS RIVER KRISHNA ON NH-167 HAGARI ? JADERCELA SECTION | MoRTH | N24001173 | 2-2017 | 5/2019 | N.A. | 10/2025 | 157.32 | 188.00 | 187.61 | 43.16 | 60.00
687 | KARNATAKA | POWER | WIDENING TO 2-LANE WIH PAVED SHOULDER FROM KM. 544.20 TO 594.00 (HOSAMANE CROSS TO PANDAVAPURA) SECT | MoRTH | N24001387 | 1-2017 | 9/2017 | May-2023 | 5/2023 | 264.34 | N.A. | 264.34 | 201.07 | 100.00
688 | KARNATAKA | POWER | CONSTRUCTION OF MAJOR BRIDGE ACROSS SHARAVATHI BACKWATERS AND APPROCHES BETWEEN AMBARGODU AND KALASA | MoRTH | N24001388 | 3-2019 | 12/2019 | Nov-2024 | 11/2024 | 423.15 | N.A. | 423.15 | 268.97 | 82.00
689 | KARNATAKA | STEEL | SCREENING PLANT-II, DONIMALAI | NMDC | N12000136 | 9-2023 | 8/2026 | N.A. | 8/2026 | 1,043.63 | N.A. | 1,043.63 | 201.25 | 21.50
690 | KARNATAKA | URBAN DEVELOPMENT | BANGALORE METRO RAIL PROJECT PHASE-2 | BMRCL | N28000058 | 2-2014 | 2/2021 | N.A. | 3/2025 | 26,405.14 | N.A. | 26,405.14 | 20,936.29 | -
691 | KARNATAKA | URBAN DEVELOPMENT | BANGALORE METRO RAIL PROJECT LIMITED. PHASE. 2A AND 2B | BMRCL | N28000151 | 6-2021 | 6/2026 | N.A. | 6/2026 | 14,788.10 | N.A. | 14,788.10 | 2,424.04 | -
692 | KERALA | CIVIL AVIATION | CALICUT AIRPORT - DEVELOPMENT OF ADDITIONAL RESA ON EITHER END ON RUNWAY 10-28 AT CALICUT AIRPORT | AAI | N04000111 | 6-2023 | 9/2025 | N.A. | 9/2025 | 484.57 | 323.98 | 323.98 | 74.67 | 18.30
693 | KERALA | DEPARTMENT OF HIGHER EDUCATION | C/O PERMANENT CAMPUS OF IIT PALAKKAD PHASE IA AT PUDESSERY VILLAGE,KANJIKODE WEST, DISTRICT PALAKKA | CPWD EDUCATION | N28000140 | 7-2019 | 3/2021 | N.A. | 11/2025 | 753.63 | N.A. | 753.63 | 411.86 | 67.00
694 | KERALA | PETROLEUM | REPLACEMENT AND EXTENSION OF JETTY PIPELINES AT KOCHI REFINERY | BPCL | N16000508 | 3-2023 | 3/2026 | N.A. | 3/2026 | 621.87 | N.A. | 621.87 | 180.09 | 82.50
695 | KERALA | PETROLEUM | SETTING UP POLYPROPYLENE UNIT AT KOCHI REFINERY | BPCL | N16000530 | 12-2023 | 10/2027 | N.A. | 10/2027 | 4,460.00 | N.A. | 4,460.00 | 240.70 | 11.10
696 | KERALA | RAILWAYS | TRIVANDRUM-KANYAKUMARI DOUBLING | SR | N22000399 | 2-2015 | 3/2024 | N.A. | 12/2027 | 1,431.90 | N.A. | 3,785.45 | 3,184.42 | 42.10
697 | KERALA | RAILWAYS | ERNAKULAM-KUMBALAM - PATCH DOUBLING (7.71 KM) | SR | N22000619 | 12-2010 | 3/2028 | N.A. | 12/2026 | 600.82 | N.A. | 595.39 | 282.77 | 8.00
698 | KERALA | RAILWAYS | KUMBALAM-THURAVUR - PATCH DOUBLING (15.59 KM) | SR | N22000620 | 12-2011 | 3/2027 | N.A. | 12/2026 | 812.85 | N.A. | 802.80 | 287.48 | 7.00
699 | KERALA | RAILWAYS | CONSTRUCTION OF 6 LANE ELEVATED CORRIDOR ALONG WITH DEVELOPMENT OF EXISTING 4 LANE ROAD AT GROUND LE | NHAI | N24001648 | 8-2022 | 1/2026 | N.A. | 1/2026 | 2,429.52 | N.A. | 2,429.52 | 1,185.00 | 62.02
700 | KERALA | RAILWAYS | SIX LANING OF PARAVOOR(DESIGN KM. 417+000) TO KOTTUKULANGARA(DESIGN KM. 454+500) SECTION OF NEW NH-6 | NHAI | N24001649 | 12-2021 | 2/2025 | Feb-2025 | 1/2026 | 3,273.61 | N.A. | 3,273.61 | 789.16 | 61.81
701 | KERALA | RAILWAYS | SIX LANING OF KADAMBATTUKONAM TO KAZHAKKOOTTAM SECTION OF NH- 66(OLD NH-47) FROM KM. 517+250 TO KM.54 | NHAI | N24001650 | 12-2021 | 1/2025 | Apr-2026 | 4/2026 | 3,635.64 | N.A. | 3,635.64 | 324.02 | 39.20
702 | KERALA | RAILWAYS | SIX LANING OF THURAVOOR (DESIGN KM. 378+612) TO PARAVOOR (DESIGN KM.417+000) SECTION OF NEW NH-66 (O | NHAI | N24001651 | 9-2021 | 9/2024 | Mar-2026 | 9/2024 | 2,878.97 | N.A. | 2,878.97 | 570.80 | 44.65
703 | KERALA | RAILWAYS | 6L MINOR BRIDGE (PALOLI PALAM) AT KM. 203.160 and MAJOR BRIDGE (MORAD) AT KM. 204.895 AND ALLIED WOR | NHAI | N24001652 | 3-2020 | 6/2022 | Feb-2024 | 6/2024 | 210.37 | 216.94 | 216.94 | 198.10 | 100.00
704 | KERALA | RAILWAYS | SIX LANING FROM KODUNGALLUR TO EDAPALLY SECTION OF NH ?66 (OLD NH-17) FROM DESIGN CHAINAGE 397+750 ( | NHAI | N24001653 | 11-2021 | 4/2025 | N.A. | 4/2025 | 3,565.82 | N.A. | 3,064.11 | 2,082.00 | 62.43
705 | KERALA | RAILWAYS | SIX LANING OF START OF KOLLAM BYPASS (KM.486+000) KADAMBATTUKONAM (KM.517+250) SECTION OF NEW NH-66 | NHAI | N24001654 | 6-2021 | 3/2025 | Feb-2026 | 2/2026 | 2,641.37 | N.A. | 2,641.37 | 607.07 | 76.90
706 | KERALA | RAILWAYS | SIX LANING FROM KAPPIRIKKAD TO THALIKULAM SECTION OF NH ? 66 (OLD NH-17) FROM DESIGN CH. 335+850 (EX | NHAI | N24001655 | 6-2021 | 2/2025 | N.A. | 11/2025 | 3,606.00 | 3,946.56 | 3,946.56 | 3,120.31 | 73.35
707 | KERALA | RAILWAYS | SIX LANING FROM THALIKULAM TO KODUNGALLUR SECTION OF NH ? 66 (OLD NH-17) FROM DESIGN CH.369+015 (EX. | NHAI | N24001656 | 6-2021 | 3/2025 | N.A. | 12/2025 | 2,595.00 | N.A. | 4,009.57 | 3,071.01 | 66.73
708 | KERALA | RAILWAYS | SIX LANING OF KOTTUKULANGARA (DESIGN KM. 454+500) TO START OF KOLLAM BYPASS (DESIGN KM. 486+000) SEC | NHAI | N24001657 | 6-2021 | 10/2024 | Dec-2025 | 12/2025 | 2,842.14 | N.A. | 2,842.14 | 477.69 | 71.30
709 | KERALA | RAILWAYS | SIX LANING OF RAMANATTUKARA JUNCTION TO START OF VALANCHERY BYPASS SECTION OF NH-66 (OLD NH- 17) FROM | NHAI | N24001658 | 1-2021 | 7/2024 | Mar-2025 | 3/2025 | 4,265.42 | N.A. | 4,728.40 | 3,474.31 | 99.10
710 | KERALA | RAILWAYS | SIX LANING FROM START OF VALANCHERY BYPASS TO KAPPIRIKKAD-SECTION OF NH-66(OLD NH-17) FROM DESIGN CH | NHAI | N24001659 | 2-2021 | 7/2024 | Mar-2025 | 3/2025 | 3,375.31 | 3,824.07 | 3,824.07 | 2,351.62 | 98.40
711 | KERALA | RAILWAYS | SIX LANING OF THALIPARAMBHA- MUZHAPILANGAD SECTION FROM KM 137.900 TO KM. 170.600 OF NH-17 (NEW NH | NHAI | N24001660 | 8-2020 | 2/2024 | Aug-2025 | 3/2026 | 2,714.60 | 3,557.65 | 2,714.60 | 1,904.06 | 72.77
712 | KERALA | RAILWAYS | 6L OF AZHIYUR-VENGALAM FROM KM. 189.200 TO KM. 230.400 OF NH-66 | NHAI | N24001661 | 10-2020 | 4/2024 | May-2025 | 3/2026 | 3,219.47 | 3,898.46 | 3,896.46 | 2,295.34 | 58.14
713 | KERALA | RAILWAYS | SIX LANING OF KT/KL BORDER (THALAPPDY) TO CHENGALA SECTION OF NH17 (NEW NH-66) FROM CH. 17.200 TO CH | NHAI | N24001662 | 5-2020 | 5/2024 | Nov-2021 | 7/2025 | 1,981.07 | 2,651.79 | 1,981.07 | 1,543.14 | 97.38
714 | KERALA | RAILWAYS | SIX LANING OF NEELESHWARAM TO THALIPARAMBHA SECTION FROM CH. 94+540 (EXISTING KM 96+450) TO CH. 134+ | NHAI | N24001663 | 6-2020 | 4/2024 | Oct-2021 | 3/2026 | 3,041.65 | 3,867.66 | 3,041.65 | 2,406.52 | 82.75
715 | KERALA | RAILWAYS | SIX LANING OF CHENGALA TO NEELESHWARAM SECTION OF NH-17 (NEW NH-66) FROM CH. 56+200 (EXISTING KM 57+ | NHAI | N24001664 | 6-2020 | 4/2024 | Oct-2021 | 3/2026 | 1,746.45 | 2,538.06 | 1,746.45 | 1,262.19 | 79.25
716 | KERALA | RAILWAYS | WIDENING/DEVELOPMENT OF EXISTING NH-85 FROM KM 0.000 TO KM 124.636 SECTION TO 2L/@L+PS SECTION IN TH | NHAI | N24002074 | 8-2022 | 6/2025 | N.A. | 6/2025 | 1,231.74 | N.A. | 1,231.74 | 486.00 | 49.70
717 | KERALA | RAILWAYS | 6-LANING OF KOZHIKODE BYPASS (CALICUT BYPASS) (I.E. VENGALAM JN. TO RAMANATTUKARA JN.) SECTION OF NH | NHAI | N24000784 | 2-2018 | 2/2023 | Dec-2024 | 7/2025 | 1,424.77 | 2,065.95 | 2,065.95 | 902.09 | 95.50
718 | KERALA | RAILWAYS | WIDENING TO 2 LANES WITH PAVED SHOULDERS FROM KM.87/000 TO 133/720 (NATTUKAL TO THANAU JN. IN PALAKK | MoRTH | N24001369 | 2-2017 | 8/2017 | Mar-2022 | 8/2024 | 294.28 | 296.53 | 296.53 | 286.80 | 98.00
719 | KERALA | RAILWAYS | WIDENING TO 2-LANE WITH PAVED SHOULDERS FROM KM 119/017 TO KM 161/300 ON NH 85 (OLD NH 49) | MoRTH | N24001370 | 2-2017 | 9/2017 | Jan-2023 | 8/2024 | 380.76 | 372.87 | 372.87 | 347.04 | 100.00
720 | KERALA | URBAN DEVELOPMENT | KOCHI METRO RAIL PROJECT PHASE II FROM JLN STADIUM TO INFOPARK VIA KAKKANAD | KMRCL | N28000158 | 7-2018 | 11/2026 | N.A. | 11/2026 | 1,957.05 | N.A. | 1,957.05 | 250.63 | 7.40
721 | LADAKH | CIVIL AVIATION | CONSTRUCTION OF TERMINAL BUILDING AND ASSOCIATED WORKS AT LEH AIRPORT | AAI | N04000078 | 7-2018 | 9/2021 | Oct-2025 | 10/2025 | 480.33 | 640.00 | 640.00 | 416.49 | 65.92
722 | LADAKH | ROAD TRANSPORT AND HIGHWAYS | CONSTRUCTION OF REALIGNMENT BETWEEN PANDRASS- PASHKYUN (TOTAL LENGTH 27.10 KM) ON ROAD ZOZILA-KARGIL | BRO | N24001999 | 11-2021 | 6/2025 | N.A. | 6/2025 | 426.14 | N.A. | 426.14 | 16.27 | 37.00
723 | LADAKH | ROAD TRANSPORT AND HIGHWAYS | KARGIL-ZANSKR PACKAGE-1 | NHIDCL | N24001343 | 3-2021 | 1/2023 | Dec-2024 | 11/2025 | 384.23 | N.A. | 384.23 | 162.54 | 60.40
724 | LADAKH | ROAD TRANSPORT AND HIGHWAYS | KARGIL-ZANSKR PACKAGE-2 | NHIDCL | N24001344 | 3-2021 | 1/2023 | Feb-2025 | 11/2025 | 404.89 | N.A. | 404.89 | 244.21 | 67.27
725 | LADAKH | ROAD TRANSPORT AND HIGHWAYS | KARGIL-ZANSKR PACKAGE-3 | NHIDCL | N24001345 | 8-2020 | 1/2023 | Aug-2025 | 8/2025 | 381.01 | N.A. | 381.01 | 230.28 | 76.11
726 | LADAKH | ROAD TRANSPORT AND HIGHWAYS | KARGIL-ZANSKR PACKAGE-8 | NHIDCL | N24001348 | 3-2021 | 1/2023 | Aug-2025 | 8/2025 | 398.37 | N.A. | 398.37 | 279.84 | 84.05
727 | LADAKH | CIVIL AVIATION | UPGRADATION OF JABALPUR AIRPORT | AAI | N04000087 | 6-2016 | 6/2021 | Jul-2024 | 7/2024 | 412.24 | N.A. | 412.24 | 403.17 | 100.00
728 | LADAKH | CIVIL AVIATION | DEVELOPMENT OF GWALIOR AIRPORT PHASE 01 | AAI | N04000098 | 10-2021 | 8/2023 | Aug-2024 | 8/2024 | 446.12 | 455.00 | 455.00 | 451.55 | 100.00
729 | LADAKH | CIVIL AVIATION | KANCHAN OC EXPANSION | SECL | N06000125 | 12-2014 | 3/2021 | Mar-2026 | 3/2026 | 371.04 | N.A. | 371.04 | 137.63 | 47.00
730 | LADAKH | CIVIL AVIATION | AMADAND OPENCAST EXPANSION PROJECT | SECL | N06000148 | 3-2016 | 3/2021 | Mar-2027 | 3/2027 | 869.44 | N.A. | 869.44 | 272.09 | 75.00
731 | LADAKH | CIVIL AVIATION | GANDHIGRAM UG MINE | WCL | N06000183 | 8-2019 | 3/2026 | N.A. | 3/2026 | 414.16 | N.A. | 414.16 | 11.75 | 28.00
732 | LADAKH | CIVIL AVIATION | BLOCK-B EXPANSION OPENCAST PROJECT | NCL | N06000184 | 7-2019 | 3/2023 | N.A. | 3/2027 | 998.71 | N.A. | 998.71 | 453.75 | 46.24
733 | LADAKH | CIVIL AVIATION | NIGAHI EXPANSION OCP (15 TO 25 MTPA) | NCL | N06000196 | 11-2020 | 3/2025 | N.A. | 3/2028 | 1,729.68 | N.A. | 1,729.68 | 772.95 | 44.93
734 | LADAKH | CIVIL AVIATION | RAMPUR BATURA OC (4.0 MTY) | SECL | N06000233 | 7-2019 | 3/2026 | N.A. | 3/2026 | 1,248.93 | N.A. | 1,248.93 | 490.58 | 44.00
735 | LADAKH | CIVIL AVIATION | TAWA III UG MINE | WCL | N06000250 | 12-2021 | 3/2027 | N.A. | 3/2027 | 314.09 | N.A. | 324.25 | 0.56 | 9.00
736 | LADAKH | CIVIL AVIATION | AMALGAMATED DHANKASA JAMUNIA UG (1.84 MTY) | WCL | N06000257 | 9-2022 | 3/2027 | N.A. | 3/2027 | 399.20 | N.A. | 497.01 | 64.13 | 42.00
737 | LADAKH | CIVIL AVIATION | VISHNUPURI UG TO OC | WCL | N06000260 | 11-2022 | 3/2029 | N.A. | 3/2029 | 220.62 | N.A. | 227.65 | 0.00 | 7.00
738 | LADAKH | CIVIL AVIATION | URDHAN OC | WCL | N06000265 | 1-2023 | 3/2031 | N.A. | 3/2031 | 206.88 | N.A. | 228.42 | 22.12 | 9.00
739 | LADAKH | CIVIL AVIATION | SHARDA UG | WCL | N06000266 | 9-2023 | 3/2028 | N.A. | 3/2028 | 166.25 | N.A. | 200.16 | 1.69 | 11.00
740 | LADAKH | PETROLEUM | ETHYLENE CRACKER PROJECT AT BINA REFINERY INCLUDING DOWNSTREAM PETROCHEMICAL PLANTS AND EXPANSION OF | BPCL | N16000518 | 5-2023 | 5/2028 | N.A. | 5/2028 | 43,367.00 | N.A. | 43,367.00 | 1,687.00 | 13.00
741 | LADAKH | POWER | SHAJAPUR 325MW SOLAR PV PROJECT | NTPC | N18000348 | 6-2022 | 3/2024 | Jun-2025 | 6/2025 | 1,530.49 | N.A. | 1,578.34 | 1,219.41 | 100.00
742 | LADAKH | POWER | TS FOR EVACUATION POWER RAJASTHAN REZ PH-IV (PART-2:5.5GW) (JAISALMER/BARMER COMPLEX): PART- C | PGCIL | N18000392 | 8-2024 | 8/2026 | N.A. | 8/2026 | 2,708.00 | N.A. | 2,708.00 | 622.84 | 25.70
743 | LADAKH | POWER | TRANSMISSION SYSTEM FOR EVACUATION OF POWER FROM RAJASTHAN REZ PH-IV [PART-2 5.5GW] [JAISALMER/BARME | PGCIL | N18000399 | 10-2024 | 10/2026 | N.A. | 10/2026 | 3,674.00 | N.A. | 3,674.00 | 345.36 | 12.70
744 | LADAKH | POWER | RAMGANJMUNDI-BHOPAL (NL),WCR | WCR | 220100314 | 4-2001 | 12/2025 | Dec-2025 | 6/2026 | 3,032.00 | 3,032.46 | 5,125.16 | 3,513.09 | 69.00
745 | LADAKH | POWER | RATLAM-MHOW-KHANDWA-AKOLA (GC) | WR | N22000120 | 4-2008 | 2/2027 | Feb-2027 | 2/2027 | 5,677.88 | 5,677.80 | 6,203.51 | 4,314.25 | 80.00
746 | LADAKH | POWER | KATNI - SINGRAULI DOUBLING PROJECT | WCR | N22000351 | 12-2015 | 12/2026 | Dec-2027 | 12/2027 | 2,445.29 | 2,445.30 | 4,353.50 | 3,122.03 | 92.00
747 | LADAKH | POWER | KATNI GRADE SEPARATOR/BYE PASS | WCR | N22000416 | 8-2016 | 9/2024 | Jun-2025 | 9/2024 | 1,247.64 | 1,247.64 | 2,300.00 | 1,453.81 | 89.00
748 | LADAKH | POWER | ANUPPUR-KATNI | SECR | N22000485 | 4-2015 | 12/2021 | Dec-2023 | 3/2025 | 1,860.94 | 1,680.00 | 2,311.02 | 1,955.51 | 100.00
749 | LADAKH | POWER | NIMACH BADI SADRI NEW LINE PROJECT | WR | N22000503 | 4-2017 | 3/2022 | Dec-2026 | 12/2026 | 495.18 | N.A. | 495.18 | 306.32 | 46.00
750 | LADAKH | POWER | NIMACH-RATLAM (133 KM) | WR | N22000536 | 10-2021 | 10/2027 | Dec-2025 | 12/2025 | 1,095.88 | 1,095.88 | 1,095.88 | 1,197.14 | 72.00
751 | LADAKH | POWER | SATNA - REWA (50 KM) | WCR | N22000554 | 11-2015 | 3/2026 | N.A. | 3/2026 | 500.00 | 40.00 | 500.00 | 1.41 | 80.00
752 | LADAKH | POWER | INDORE BUDNI (INDORE JABALPUR) | RVNL | N22000601 | 9-2018 | 9/2030 | N.A. | 9/2030 | 7,474.01 | N.A. | 7,393.75 | 1,004.86 | -
753 | LADAKH | POWER | 4LBERKHEDI TO GODPEHRA NH-44 | NHAI | N24001614 | 2-2022 | 11/2024 | N.A. | 12/2025 | 524.84 | N.A. | 524.84 | 2,455.45 | 60.00
754 | LADAKH | POWER | 4L OF SAGAR - MOHARI FROM KM.8 TO KM.50 (PKG-I) | NHAI | N24001615 | 3-2021 | 4/2024 | Jun-2025 | 6/2025 | 790.78 | N.A. | 790.78 | 2,141.21 | 77.02
755 | LADAKH | POWER | KATNI BYPASS FROM KM. 359.50 TO KM. 378.50 | NHAI | N24001618 | 9-2019 | 9/2022 | N.A. | 2/2025 | 194.40 | 235.00 | 235.00 | 208.32 | 98.84
756 | LADAKH | POWER | 4L OF CHANDESARA TO KHEDAKHAJURIYA FROM KM. 0.000 TO (-) 750 AND KM 0.000 TO KM 41.400 OF NH-752D | NHAI | N24001759 | 1-2020 | 6/2024 | Dec-2025 | 12/2025 | 909.84 | N.A. | 909.84 | 503.76 | 99.00
757 | LADAKH | POWER | INDORE - HARDA (PKG-III) [NANASA TO PIDGAON SECTION FROM KM 95.000 TO KM 142.445] | NHAI | N24001762 | 10-2021 | 1/2024 | Dec-2025 | 12/2025 | 1,146.22 | N.A. | 1,146.22 | 663.10 | 91.40
758 | LADAKH | POWER | INDORE - HARDA (PKG-I) [INDORE TO RAGHAV GARH FROM KM. 0.25 TO KM. 26.903] | NHAI | N24001766 | 1-2022 | 10/2024 | N.A. | 12/2025 | 1,011.29 | N.A. | 1,011.29 | 318.76 | 70.68
759 | LADAKH | POWER | 4L OF INDORE - BOREGAON (PKG-III) [BALWARA TO DHANGAON] FROM KM. 42.260 TO KM. 82.660 OF NH347BG AND | NHAI | N24001767 | 1-2021 | 4/2024 | N.A. | 12/2025 | 1,001.69 | N.A. | 1,001.69 | 520.29 | 83.00
760 | LADAKH | POWER | 4L OF OBEDULLGANJ - BUDNI SECTION FROM KM. 8.400 TO KM. 20.700 IN RATANPANI WILDLIFE AREA OF NH - 69 | NHAI | N24001770 | 2-2022 | 3/2024 | Mar-2025 | 7/2025 | 417.51 | N.A. | 417.51 | 312.94 | 100.00
761 | LADAKH | POWER | 2- LANE WITH PAVED SHOULDERS OF HINOTIYA TO MEHULWA FROM DESIGN KM 27+000 9OF EXISTING SH-19 KM 26+5 | NHAI | N24001921 | 8-2021 | 9/2025 | N.A. | 9/2025 | 581.65 | 592.03 | 581.65 | 135.75 | 45.78
762 | LADAKH | POWER | CONSTRUCTION OF MIHONA BYPASS, LAHAR BYPASS, DABOH BYPASS and BHANDER BYPASS (TOTAL LENGTH 20.60 KM) | MoRTH | N24001962 | 3-2022 | 12/2024 | N.A. | 3/2025 | 179.19 | N.A. | 179.19 | 47.91 | 96.00
763 | LADAKH | POWER | UPGRADATION OF NASRULLAGANI- REHTI-BUDHNI SCCTION TO 2-LANE WITH PAVED SHOULDER FROM KM 0+150 TO KM | MoRTH | N24001963 | 12-2021 | 10/2024 | N.A. | 9/2025 | 305.12 | N.A. | 305.12 | 71.47 | 34.46
764 | LADAKH | POWER | UPGRADATION and WIDENING OF JHARKHEDA- BERASIA - DHOLKHEDI FROM DESIGN KM 0+000 TO KM 87+900 (DESIGN | MoRTH | N24001964 | 3-2022 | 5/2025 | N.A. | 5/2025 | 365.21 | N.A. | 365.21 | 112.27 | 64.00
765 | LADAKH | POWER | REHABILITATION AND UPGRADATION OF KURWAI?MUNGAOLI?CHANDERI ROAD SECTION OF NH-346, FROM DESIGN CHAIN | MoRTH | N24001965 | 3-2022 | 2/2025 | N.A. | 12/2025 | 386.49 | N.A. | 386.49 | 77.42 | 48.77
766 | LADAKH | POWER | 4L GREENFIELD RUDHI TO DESHGAON (PKG V OF BETUL- KHANDWA/DESHGAON) - N/04015/06003/MP | NHAI | N24001967 | 11-2018 | 10/2025 | N.A. | 10/2025 | 521.21 | N.A. | 521.21 | 110.63 | 49.57
767 | LADAKH | POWER | REHABILITATION AND UPGRADATION TO 2-LANE WITH PAVED SHOULDER CONFIGURATION OF JIRAPUR- SUSNER-MP-RJ B | MoRTH | N24002018 | 1-2022 | 3/2025 | N.A. | 3/2025 | 239.72 | 232.22 | 232.22 | 73.40 | 100.00
768 | LADAKH | POWER | UPGRADATION OF DINDORI- SAGARTOLA-KABICHABUTRA (MP-CG BORDER) SECTION OF NH -45 FROM KM 0+00(DESIGN) | MoRTH | N24002019 | 1-2022 | 9/2025 | N.A. | 9/2025 | 329.14 | 319.09 | 319.09 | 52.70 | 50.12
769 | LADAKH | POWER | CONSTRUCTION OF KAITHI-PADARIA KALA BYPASS, PATNA-TAMOLI BYPASS, JASO BYPASS , NAGOD BYPASS (TOTAL L | MoRTH | N24002020 | 3-2022 | 10/2025 | N.A. | 10/2025 | 158.36 | 158.00 | 158.36 | 22.68 | 30.00
770 | LADAKH | POWER | BALANCE WORK OF 4L OF NAURADEHI SANCTUARY DE-SCOPED STRETCH OF HIRAN RIVER TO SINDOOR RIVER FROM KM. | NHAI | N24002067 | 1-2021 | 7/2023 | N.A. | 4/2025 | 178.18 | N.A. | 178.18 | 161.64 | 94.65
771 | LADAKH | POWER | CONSTRUCTION OF 4-LANE FROM BARELA TO MANEGAON SECTION OF NH-30 FROM DESIGN CH. 2.900 TO DESIGN CH. | NHAI | N24002068 | 12-2022 | 3/2025 | N.A. | 12/2025 | 652.33 | N.A. | 652.33 | 334.34 | 73.16
772 | LADAKH | POWER | CONSTRUCTION OF ADDITIONAL 3 LANE WITH PAVED SHOULDER (DESIGN LENGTH 8.87 KM) AS REALIGNMENT OF BAKA | NHAI | N24002069 | 7-2022 | 12/2024 | N.A. | 12/2024 | 209.29 | N.A. | 209.29 | 140.22 | 100.00
773 | LADAKH | POWER | INDORE - EDLABAD (PKG-II) [TEJAJINAGAR TO BALWARA] | NHAI | N24002070 | 1-2022 | 1/2025 | N.A. | 1/2026 | 1,162.80 | N.A. | 1,162.80 | 537.71 | 80.50
774 | LADAKH | POWER | CONSTRUCTION OF (I) 4-LANE HIGHWAY FROM VIDISHA TO HINOTIYA FROM KM. 0.000 TO KM. 27.000 (LENGTH=27 | NHAI | N24002077 | 9-2022 | 12/2025 | N.A. | 12/2025 | 1,000.63 | N.A. | 1,000.63 | 210.15 | 53.86
775 | LADAKH | POWER | FOUR LANING OF RAGHOGARH (DESIGN CH.29.300/EXISTING CH. 29.555) TO NANASA (DESIGN CH.92.971/EXISTING | NHAI | N24002166 | 3-2024 | 3/2026 | Mar-2026 | 3/2026 | 799.20 | N.A. | 799.20 | 306.28 | 35.10
776 | LADAKH | POWER | BALANCE WORKS OF 4 LANE DIVIDED CARRIAGEWAY OF MISSING LINK SECTION OF NH-39 (REWA BYPASS) FROM JUNC | NHAI | N24002200 | 4-2024 | 4/2026 | N.A. | 4/2026 | 355.36 | N.A. | 355.36 | 66.14 | 34.40
777 | LADAKH | POWER | UMARIYA TO SHAHDOL SECTION OF NH-78 IN MADYA PRADESH KM 68/4 TO 142/200 | MoRTH | N24000513 | 3-2015 | 8/2017 | Dec-2023 | 6/2025 | 511.83 | N.A. | 511.83 | 478.84 | 93.06
778 | LADAKH | URBAN DEVELOPMENT | BHOPAL METRO RAIL | MPMRCL | N28000124 | 11-2018 | 2/2023 | Jun-2028 | 6/2028 | 6,941.40 | N.A. | 6,941.40 | 3,043.74 | 42.16
779 | LADAKH | URBAN DEVELOPMENT | INDORE METRO RAIL | MPMRCL | N28000125 | 11-2018 | 2/2023 | Dec-2028 | 12/2028 | 7,500.80 | N.A. | 7,500.80 | 3,798.28 | 53.54
780 | MAHARASHTRA | CIVIL AVIATION | CONSTRUCTION OF NEW INTEGRATED TERMINAL BUILDING, RECONSTRUCTION OF OLD TERMINAL BUILDING, MODIFICAT | AAI | N04000079 | 3-2017 | 4/2021 | Dec-2023 | 12/2023 | 475.39 | N.A. | 533.56 | 533.14 | 100.00
781 | MAHARASHTRA | CIVIL AVIATION | EXTENSION OF RUNWAY WITH BLAST PAD, RESA, TAXIWAY, APRON, GSE AREA, ISOLATION BAY, NEW DOMESTIC TERM | AAI | N04000096 | 6-2017 | 12/2020 | Apr-2024 | 4/2024 | 255.68 | 270.00 | 270.00 | 267.86 | 100.00
782 | MAHARASHTRA | CIVIL AVIATION | AMALGAMATED YEKONA-I YEKONA-II | WCL | N06000132 | 8-2015 | 3/2025 | N.A. | 3/2025 | 727.28 | N.A. | 727.28 | 530.02 | 86.00
783 | MAHARASHTRA | CIVIL AVIATION | UKNI DEEP OC | WCL | N06000179 | 1-2019 | 3/2021 | Mar-2025 | 3/2025 | 237.06 | N.A. | 318.14 | 163.86 | 91.00
784 | MAHARASHTRA | CIVIL AVIATION | GHONSA EXPANSION DEEP OC | WCL | N06000205 | 3-2021 | 3/2028 | N.A. | 3/2029 | 184.71 | N.A. | 241.72 | 9.25 | 6.00
785 | MAHARASHTRA | CIVIL AVIATION | SASTI EXPANSION OC | WCL | N06000206 | 8-2020 | 3/2026 | N.A. | 3/2026 | 319.04 | N.A. | 371.59 | 68.64 | 24.00
786 | MAHARASHTRA | CIVIL AVIATION | DHUPTALA OC(SASTI UG TO OC) | WCL | N06000209 | 10-2021 | 3/2028 | N.A. | 3/2028 | 711.00 | N.A. | 720.87 | 159.15 | 33.00
787 | MAHARASHTRA | CIVIL AVIATION | ADASA UG TO OC (1.50 MTY) | WCL | N06000219 | 11-2018 | 3/2024 | Mar-2025 | 3/2025 | 316.00 | N.A. | 333.43 | 208.20 | 78.00
788 | MAHARASHTRA | CIVIL AVIATION | DINESH (MAKARDHOKDA-III) OC (8.0 MTY) | WCL | N06000222 | 2-2020 | 3/2027 | N.A. | 3/2027 | 822.88 | N.A. | 1,184.33 | 578.89 | 48.00
789 | MAHARASHTRA | CIVIL AVIATION | AMALGAMATED INDER-KAMPTEE DEEP OC (3.20 MTY) | WCL | N06000226 | 9-2018 | 3/2024 | Mar-2025 | 3/2025 | 235.90 | N.A. | 313.34 | 116.46 | 87.00
790 | MAHARASHTRA | CIVIL AVIATION | SAONER UG MINE I EXPANSION | WCL | N06000251 | 1-2022 | 3/2028 | N.A. | 3/2028 | 228.64 | N.A. | 253.51 | 118.34 | 27.00
791 | MAHARASHTRA | CIVIL AVIATION | SINGHORI DEEP OC | WCL | N06000252 | 5-2022 | 3/2029 | N.A. | 3/2029 | 335.75 | N.A. | 421.84 | 22.01 | 16.00
792 | MAHARASHTRA | CIVIL AVIATION | MAKARDHOKDA I EXPANSION OC | WCL | N06000253 | 6-2022 | 3/2026 | N.A. | 3/2026 | 361.87 | N.A. | 497.06 | 33.90 | 12.00
793 | MAHARASHTRA | CIVIL AVIATION | BHATADI EXPANSION OC | WCL | N06000254 | 5-2022 | 3/2028 | N.A. | 3/2028 | 580.60 | N.A. | 729.86 | 61.33 | 17.00
794 | MAHARASHTRA | CIVIL AVIATION | NEW MAJARI UG TO OC (3.0 MTY) | WCL | N06000255 | 9-2022 | 3/2027 | N.A. | 3/2027 | 402.27 | N.A. | 496.38 | 47.99 | 27.00
795 | MAHARASHTRA | CIVIL AVIATION | BHANEGAON OC (1.15MTY) | WCL | N06000256 | 9-2022 | 3/2028 | N.A. | 3/2028 | 405.20 | N.A. | 494.60 | 10.21 | 7.00
796 | MAHARASHTRA | CIVIL AVIATION | GOKUL EXPANSION OC | WCL | N06000264 | 4-2021 | 3/2026 | N.A. | 3/2026 | 309.58 | N.A. | 456.95 | 3.65 | 7.00
797 | MAHARASHTRA | CIVIL AVIATION | KOLGAON EXPANSION (DEEP) OC | WCL | N06000267 | 9-2023 | 3/2027 | N.A. | 3/2027 | 198.71 | N.A. | 206.19 | 0.55 | 5.00
798 | MAHARASHTRA | CIVIL AVIATION | AMALGAMATED GAURI PAUNI EXPANSION OC | WCL | N06000271 | 3-2024 | 3/2030 | N.A. | 3/2030 | 1,225.21 | N.A. | 1,428.25 | 52.83 | 17.00
799 | MAHARASHTRA | CIVIL AVIATION | GAURI CENTRAL OCM | WCL | N06000278 | 6-2024 | 3/2030 | N.A. | 3/2030 | 973.07 | N.A. | 1,015.07 | 0.00 | -
800 | MAHARASHTRA | CIVIL AVIATION | BALLARPUR NORTHWEST OC MINE | WCL | N06000282 | 12-2022 | 3/2029 | N.A. | 3/2029 | 360.18 | N.A. | 360.18 | 0.00 | -
801 | MAHARASHTRA | CIVIL AVIATION | NORTHERN EXTENSION OF MUNGOLI NIRGUDA DEEP OC | WCL | N06000283 | 6-2024 | 3/2029 | N.A. | 3/2029 | 1,024.91 | N.A. | 1,184.44 | 0.00 | -
802 | MAHARASHTRA | CIVIL AVIATION | AMALGAMATED GONDEGAON - GHATROHAN EXPANSION OCM | WCL | N06000284 | 9-2024 | 3/2029 | N.A. | 3/2029 | 668.54 | N.A. | 871.59 | 0.00 | -
803 | MAHARASHTRA | CIVIL AVIATION | WAGHODA UG | WCL | N06000293 | 1-2025 | 3/2030 | N.A. | 3/2030 | 379.30 | N.A. | 379.30 | 0.00 | -
804 | MAHARASHTRA | CIVIL AVIATION | KOLARPIMPRI EXPANSION OCM (2.50 MTY) | WCL | N06000294 | 2-2025 | 3/2030 | N.A. | 3/2030 | 630.37 | N.A. | 630.37 | 0.00 | -
805 | MAHARASHTRA | DEPARTMENT OF HIGHER EDUCATION | CONSTRUCTION OF IITB RESEARCH PARK AT IIT BOMBAY, POWAI, MUMBAI | CPWD EDUCATION | N28000117 | 1-2018 | 7/2020 | Nov-2023 | 2/2024 | 223.37 | 275.00 | 230.00 | 141.16 | 100.00
806 | MAHARASHTRA | HEALTH AND FAMILY WELFARE | 500 BEDDED HOSPITAL INCLUDING 50 SUPERSPECIALITY BEDS FOR ESIC AT PUNE | CPWD | N21000033 | 7-2022 | 9/2025 | N.A. | 9/2025 | 429.25 | N.A. | 429.25 | 99.08 | -
807 | MAHARASHTRA | HEALTH AND FAMILY WELFARE | LIFE EXTENSION OF WALL PLATFORMS OF MUMBAI HIGH AND HEERA FIELDS | ONGC | N16000213 | 12-2015 | 4/2018 | Dec-2023 | 6/2025 | 3,190.69 | 3,375.90 | 3,375.90 | 3,051.26 | 89.50
808 | MAHARASHTRA | HEALTH AND FAMILY WELFARE | SETTING UP 500KTPA PROPANE DEHYDROGENATION INTEGRATED WITH POLYPROPYLENE UNIT ALONG WITH OFFSITE AND | GAIL | N16000430 | 5-2019 | 4/2025 | Oct-2025 | 10/2025 | 8,797.00 | 11,256.00 | 11,256.00 | 6,694.98 | 84.50
809 | MAHARASHTRA | HEALTH AND FAMILY WELFARE | DEBOTTLENECKING AND AUGMENTATION OF CRYOGENIC FACILITIES AT URAN LPG IMPORT TERMINAL | BPCL | N16000442 | 4-2021 | 6/2024 | N.A. | 4/2025 | 1,164.69 | N.A. | 1,164.69 | 893.78 | 84.10
810 | MAHARASHTRA | HEALTH AND FAMILY WELFARE | EXPANSION OF CRYOGENICS GROUP BY SETTING UP NEW MANUFACTURING FACILITY | IOCL | N16000446 | 9-2021 | 10/2023 | Jun-2025 | 6/2025 | 378.00 | N.A. | 378.00 | 142.31 | 90.60
811 | MAHARASHTRA | HEALTH AND FAMILY WELFARE | CONSTRUCTION OF LUBE OIL BLENDING AND FILLING PLANT AT RASAYANI | BPCL | N16000452 | 5-2022 | 3/2024 | N.A. | 9/2024 | 423.39 | N.A. | 423.39 | 268.34 | 76.00
812 | MAHARASHTRA | HEALTH AND FAMILY WELFARE | ATF PIPELINE FROM JAWAHARLAL NEHRU PORT TRUST (JNPT) TO NAVI MUMBAI INTERNATIONAL AIRPORT (NMIA) | IOCL | N16000456 | 9-2022 | 8/2025 | N.A. | 3/2026 | 165.00 | N.A. | 165.00 | 79.17 | 69.80
813 | MAHARASHTRA | HEALTH AND FAMILY WELFARE | DAMAN UPSIDE DEVELOPMENT PROJECT (DUDP) IN TAPTI DAMAN BLOCK | ONGC | N16000470 | 6-2022 | 10/2025 | N.A. | 2/2026 | 4,144.41 | 6,406.90 | 6,406.90 | 3,203.26 | 80.50
814 | MAHARASHTRA | HEALTH AND FAMILY WELFARE | CGD PROJECT AT BEED, JALGAON AND JALNA DISTRICTS | IOCL | N16000487 | 3-2022 | 3/2030 | N.A. | 9/2031 | 865.00 | N.A. | 865.00 | 66.06 | 2.80
815 | MAHARASHTRA | HEALTH AND FAMILY WELFARE | ANDHERI RESIDENTIAL TOWERS MUMBAI | IOCL | N16000503 | 6-2017 | 5/2025 | Jun-2026 | 6/2026 | 281.35 | 389.67 | 389.67 | 218.84 | 50.80
816 | MAHARASHTRA | HEALTH AND FAMILY WELFARE | CONSTRUCTION OF ADDITIONAL TANKAGES AND ALLIED FACILITIES AT JNPT TERMINAL | IOCL | N16000504 | 4-2022 | 10/2024 | Aug-2026 | 8/2026 | 341.43 | 436.14 | 436.14 | 244.76 | 49.50
817 | MAHARASHTRA | HEALTH AND FAMILY WELFARE | INSTALLATION OF INDEPENDENT DE- AROMATIZED SOLVENTS PRODUCTION FACILITIES AT MUMBAI REFINERY | BPCL | N16000507 | 3-2023 | 7/2025 | N.A. | 7/2025 | 405.00 | N.A. | 405.00 | 189.80 | 81.50
818 | MAHARASHTRA | HEALTH AND FAMILY WELFARE | PART REPLACEMENT PIPELINE PROJECT (PRPP) | ONGC | N16000515 | 11-2022 | 5/2024 | Dec-2024 | 11/2025 | 1,219.48 | N.A. | 1,145.10 | 1,145.10 | 87.00
819 | MAHARASHTRA | HEALTH AND FAMILY WELFARE | POL AND LOBS INSTALLATIONS WITH RECEIPT PIPELINES AT RASAYANI | BPCL | N16000519 | 5-2023 | 5/2026 | N.A. | 5/2026 | 2,585.00 | N.A. | 2,585.00 | 525.74 | 56.50
820 | MAHARASHTRA | HEALTH AND FAMILY WELFARE | MHN TCPP PGC BGC PROJECT (MTPBP) | ONGC | N16000526 | 2-2024 | 5/2026 | N.A. | 5/2026 | 2,329.45 | N.A. | 2,354.23 | 672.00 | 45.90
821 | MAHARASHTRA | HEALTH AND FAMILY WELFARE | PRP-VIII GROUP B (NH AND BS ASSET) | ONGC | N16000533 | 6-2024 | 5/2026 | N.A. | 2/2026 | 2,379.84 | N.A. | 2,379.84 | 1,646.11 | 57.80
822 | MAHARASHTRA | HEALTH AND FAMILY WELFARE | HP TDAE UNIT IN MUMBAI REFINERY | HPCL | N16000534 | 6-2024 | 4/2026 | N.A. | 4/2026 | 240.00 | N.A. | 240.00 | 27.90 | 33.60
823 | MAHARASHTRA | HEALTH AND FAMILY WELFARE | INTEGRATED DEVELOPMENT OF 4 CONTRACT AREAS UNDER DSF2 | ONGC | N16000537 | 5-2023 | 4/2027 | N.A. | 4/2027 | 6,183.79 | N.A. | 6,183.79 | 0.00 | 12.60
824 | MAHARASHTRA | HEALTH AND FAMILY WELFARE | LUBE MODERNIZATION AND BOTTOM UPGRADATION PROJECT | HPCL | N16000540 | 12-2024 | 3/2028 | N.A. | 3/2028 | 4,679.00 | N.A. | 4,679.00 | 177.41 | 4.20
825 | MAHARASHTRA | POWER | BIKANER SOLAR POWER PROJECT | SJVN | N18000335 | 4-2022 | 5/2024 | N.A. | 9/2025 | 5,491.89 | 532.00 | 5,491.89 | 4,374.00 | 80.35
826 | MAHARASHTRA | POWER | TS FOR EVACUATION OF 7GW RE INJECTION AT KHAVDA PS UNDER PHASE-IV PART E4 | PGCIL | N18000377 | 11-2023 | 7/2025 | N.A. | 11/2025 | 224.00 | N.A. | 224.00 | 15.68 | 7.00
827 | MAHARASHTRA | POWER | AHMEDNAGAR-PARLI VAIJNATH(NL) CR | CR | 220100181 | 2-1997 | 3/2026 | N.A. | 1/2026 | 2,539.00 | N.A. | 4,957.27 | 4,909.30 | 97.00
828 | MAHARASHTRA | POWER | MUMBAI URBAN TRANSPORT PROJECT PHASE-II | MRTP | N22000092 | 4-2008 | 3/2014 | N.A. | 3/2014 | 8,087.11 | N.A. | 918.53 | 7,349.29 | -
829 | MAHARASHTRA | POWER | WARDHA-NANDED MAHARASHTRA | CR | N22000231 | 4-2008 | 3/2027 | N.A. | 1/2026 | 3,445.48 | N.A. | 3,445.34 | 3,156.47 | 47.00
830 | MAHARASHTRA | POWER | KALYAN-KASARA 3RD LINE | CR | N22000233 | 4-2011 | 12/2025 | N.A. | 12/2026 | 792.89 | N.A. | 1,395.79 | 882.04 | 50.00
831 | MAHARASHTRA | POWER | WARDHA-SEWAGRAM NGP 3RD LINE | CR | N22000250 | 4-2012 | 12/2025 | N.A. | 2/2026 | 540.02 | N.A. | 540.02 | 737.54 | 80.00
832 | MAHARASHTRA | POWER | WARDHA-BALHARSHAH - 3RD LINE (132 KM) | CR | N22000356 | 2-2015 | 12/2025 | N.A. | 3/2026 | 1,384.72 | N.A. | 1,384.72 | 1,590.45 | 67.00
833 | MAHARASHTRA | POWER | ITARSI-NAGPUR (BAL.) - 3RD LINE (267 KM) | CR | N22000358 | 2-2015 | 3/2027 | N.A. | 3/2027 | 2,449.91 | N.A. | 2,449.91 | 1,761.99 | 50.00
834 | MAHARASHTRA | POWER | PUNE-MIRAJ-LONDA (467 KM) | CR | N22000359 | 2-2015 | 2/2025 | N.A. | 5/2025 | 3,627.47 | 3,627.00 | 7,037.24 | 4,742.07 | 84.00
835 | MAHARASHTRA | POWER | DAUND - MANMAD (236 KM) | CR | N22000360 | 2-2016 | 12/2025 | N.A. | 1/2026 | 2,081.27 | N.A. | 2,081.27 | 2,768.50 | 88.00
836 | MAHARASHTRA | POWER | MANMAD - JALGAON - 3RD LINE (160 KM) | CR | N22000361 | 2-2016 | 12/2024 | N.A. | 3/2026 | 1,035.16 | N.A. | 1,558.75 | 1,692.15 | 97.00
837 | MAHARASHTRA | POWER | WARDHA - NAGPUR - 4TH LINE (76 KM) | CR | N22000362 | 2-2016 | 12/2025 | N.A. | 2/2026 | 638.00 | N.A. | 637.95 | 968.65 | 80.00
838 | MAHARASHTRA | POWER | RAJNANDGAON - NAGPUR - 3RD LINE (SECR) | SECR | N22000420 | 9-2016 | 12/2024 | N.A. | 12/2026 | 3,544.92 | N.A. | 3,544.25 | 3,081.12 | 95.00
839 | MAHARASHTRA | POWER | MUMBAI CENTRAL VIRAR VADODARA AHMEDABAAD TRAIN PROTECTION SYSTEM 500 RKM | WR | N22000434 | 3-2010 | 10/2024 | N.A. | 3/2024 | 311.00 | N.A. | 311.36 | 0.00 | -
840 | MAHARASHTRA | POWER | WADSA-GADHCHIROLI NEW LINE (52.36 KM) | SECR | N22000480 | 6-2018 | 3/2027 | N.A. | 12/2026 | 1,886.05 | N.A. | 1,880.61 | 807.87 | 25.00
841 | MAHARASHTRA | POWER | PACHORA-JAMNER WITH EXTENSION UPTO MALKAPUR NG TO BG | CR | N22000511 | 8-2022 | 8/2027 | N.A. | 3/2029 | 955.00 | N.A. | 2,089.25 | 117.54 | -
842 | MAHARASHTRA | POWER | SOLAPUR-TULJAPUR-OSMANABAD (UMBRELLA WORK) | CR | N22000513 | 1-2019 | 3/2028 | N.A. | 12/2027 | 904.92 | N.A. | 2,933.01 | 1,150.11 | 10.00
843 | MAHARASHTRA | POWER | DHULE (BORVIHIR)-NARDANA (UMBRELLA WORK) | CR | N22000514 | 1-2019 | 12/2026 | N.A. | 3/2028 | 492.76 | N.A. | 1,158.99 | 234.48 | 5.00
844 | MAHARASHTRA | POWER | KALYAN-MURBAD VIA ULHASNAGAR (UMBRELLA WORK) | CR | N22000515 | 2-2023 | 3/2027 | N.A. | 3/2027 | 836.12 | N.A. | 836.12 | 9.29 | -
845 | MAHARASHTRA | POWER | BARAMATI - LONAND | CR | N22000615 | 2-1999 | 3/2027 | N.A. | 3/2027 | 736.44 | N.A. | 1,843.90 | 712.06 | 50.00
846 | MAHARASHTRA | POWER | MUMBAI URBAN TRANSPORT PROJECT IIIA | MRVC | N22000627 | 4-2019 | 12/2027 | N.A. | 12/2027 | 33,690.00 | N.A. | 33,690.00 | 2,156.62 | -
847 | MAHARASHTRA | POWER | NAGPUR- NAGBHIR RAILWAY LINE GAUGE CONVERSION PROJECT | MRIDC | N22000629 | 10-2019 | 6/2024 | N.A. | 10/2025 | 1,400.00 | N.A. | 2,383.00 | 1,791.72 | 87.00
848 | MAHARASHTRA | POWER | UPGRADATION OF ADHALGAON- JAMKHED SECTION OF NH-548 D FROM KM 132/600 TO KM 195/375 TO TWO LANE WITH | MoRTH | N24001448 | 11-2021 | 2/2022 | N.A. | 2/2022 | 223.35 | N.A. | 223.35 | 209.36 | 87.88
849 | MAHARASHTRA | POWER | REPANPALLI TO SIRONCHA | MoRTH | N24001468 | 3-2022 | 6/2022 | N.A. | 6/2024 | 282.07 | N.A. | 282.07 | 34.65 | -
850 | MAHARASHTRA | POWER | TUNNEL AT KHAMBATAKI GHAT SECTION AND ITS APPROACHES FROM EXISTING KM. 771.730 TO EXISTING KM. 782.0 | NHAI | N24001486 | 2-2019 | 2/2022 | Dec-2024 | 8/2025 | 493.00 | N.A. | 493.00 | 409.36 | 77.64
851 | MAHARASHTRA | POWER | DHARAMPURI-LONAND FROM KM. 117.00 TO 166.40 (PKG-IV) ON MOHOL- ALANDI SECTION | NHAI | N24001488 | 9-2021 | 9/2023 | Dec-2024 | 8/2025 | 618.45 | N.A. | 618.45 | 672.67 | 96.90
852 | MAHARASHTRA | POWER | 6L OF KAGAL-SATARA SECTION FROM KM 658.000 TO KM 725.000 OF NH-48 (PKG-II) | NHAI | N24001493 | 12-2022 | 12/2024 | N.A. | 11/2025 | 1,749.86 | N.A. | 1,749.86 | 1,858.98 | 69.14
853 | MAHARASHTRA | POWER | 4L OF RATNAGIRI - KOLHAPUR SECTION OF NH-166 FROM KM 0.000 TO KM 19.769 AND KM 31.000 TO KM 67.140 ( | NHAI | N24001495 | 11-2022 | 11/2024 | N.A. | 9/2025 | 930.00 | N.A. | 930.00 | 675.62 | 77.15
854 | MAHARASHTRA | POWER | 4L OF BARAMATI TO INDAPUR (PKG-II) FROM KM. 41.400 TO KM. 84.550 OF NH- 965G (SAINT TUKARAM MARG) | NHAI | N24001502 | 9-2021 | 9/2023 | Jul-2025 | 8/2025 | 624.45 | 580.15 | 580.15 | 420.42 | 0.50
855 | MAHARASHTRA | POWER | 4L OF INDAPUR TO TONDLE (PKG-III) FROM KM.84.550 TO KM. 131.00 OF NH- 965G (SAINT TUKARAM MARG) | NHAI | N24001503 | 9-2021 | 9/2023 | Jan-2025 | 3/2025 | 667.66 | 666.21 | 666.21 | 610.63 | 3.00
856 | MAHARASHTRA | POWER | VADODARA MUMBAI EXPRESSWAY (PHASE II - PKG XI) [KM. 77.000 TO KM. 103.400] (GANJAD - TALSARI) | NHAI | N24001504 | 5-2022 | 5/2024 | Jun-2025 | 6/2025 | 1,260.00 | N.A. | 1,260.00 | 665.73 | 99.00
857 | MAHARASHTRA | POWER | VADODARA MUMBAI EXPRESSWAY (PHASE II - PKG XII) [KM. 50.700 TO KM. 77.000] (MASVAN - GANJAD) | NHAI | N24001505 | 3-2022 | 3/2024 | Jun-2025 | 6/2025 | 1,549.02 | N.A. | 1,549.02 | 699.00 | 87.24
858 | MAHARASHTRA | POWER | VADODARA MUMBAI EXPRESSWAY (PHASE II - PKG XIII) [KM. 26.582 TO KM. 50.700] (SHIRSAD - MASVAN) | NHAI | N24001506 | 2-2022 | 2/2024 | Jun-2025 | 6/2025 | 2,747.00 | N.A. | 2,747.00 | 1,130.30 | 84.22
859 | MAHARASHTRA | POWER | VADODARA MUMBAI EXPRESSWAY (PHASE II - PKG XIV) [KM. 3.000 TO KM. 20.200 OF SPUR] (SHIRSAD - AKLOLI) | NHAI | N24001507 | 11-2022 | 5/2024 | Jun-2025 | 6/2025 | 1,124.00 | N.A. | 1,124.00 | 483.84 | 75.15
860 | MAHARASHTRA | POWER | VADODARA MUMBAI EXPRESSWAY (PHASE II - PKG XVI) [KM. 43.000 TO KM. 69.800 OF SPUR] (AMNE - BHOJ) | NHAI | N24001508 | 11-2022 | 10/2024 | Jun-2025 | 6/2025 | 1,450.00 | N.A. | 1,450.00 | 718.65 | 86.02
861 | MAHARASHTRA | POWER | VADODARA MUMBAI EXPRESSWAY (PHASE II - PKG XV) [KM. 20.200 TO KM. 43.000 OF SPUR] (AKLOLI - AMNE) | NHAI | N24001521 | 11-2022 | 10/2024 | Jul-2025 | 7/2025 | 990.00 | N.A. | 990.00 | 406.91 | 77.38
862 | MAHARASHTRA | POWER | 6L OF KAGAL-SATARA SECTION FROM KM 592.240 TO KM 658.000 OF NH-48 (PKG-I) | NHAI | N24001546 | 1-2023 | 1/2025 | N.A. | 1/2025 | 1,025.20 | N.A. | 1,025.20 | 457.33 | 44.61
863 | MAHARASHTRA | POWER | BALANCE WORKS OF 4L PANVEL- INDAPUR SECTION OF NH-66 (OLD NH- 17) FROM KM 42.300 (KASU) TO KM 84.600 ( | NHAI | N24001607 | 10-2022 | 5/2024 | Dec-2025 | 12/2025 | 332.00 | N.A. | 332.00 | 283.14 | 74.75
864 | MAHARASHTRA | POWER | VADODARA MUMBAI EXPRESSWAY (PHASE II - PKG XVII) [KM. 69.800 TO KM. 79.783 OF SPUR] (BHOJ - MORBE) | NHAI | N24001608 | 9-2021 | 7/2025 | N.A. | 7/2025 | 2,208.68 | N.A. | 2,208.68 | 565.20 | 76.26
865 | MAHARASHTRA | POWER | BALANCE WORK OF 4 LANING OF PANVEL TO INDAPUR SECTION OF NH- 66(OLD NH- 17) FROM KM 0.000 (PANVEL) TO | NHAI | N24001609 | 1-2023 | 12/2023 | Jun-2025 | 9/2025 | 151.26 | N.A. | 151.26 | 153.77 | 89.80
866 | MAHARASHTRA | POWER | 4L OF EXISTING 2/4L STRETCH FROM LONAND TO DIVE GHAT (KM 166.400 TO KM 220.900 ) OF MOHOL ? ALANDI S | NHAI | N24001610 | 1-2022 | 5/2024 | Mar-2025 | 8/2025 | 1,833.73 | N.A. | 1,833.73 | 554.81 | 96.94
867 | MAHARASHTRA | POWER | FOUR LANING OF AURANGABAD- PAITHAN SECTION OF NH-752E ON EPC MODE IN THE STATE OF MAHARASHTRA . | NHAI | N24001795 | 10-2022 | 7/2024 | Jun-2025 | 12/2024 | 490.40 | N.A. | 289.00 | 275.78 | 96.00
868 | MAHARASHTRA | POWER | 4L OF RAJURA-KORPANA-ADILABAD ROAD UPTO M.S. BORDER FROM KM 32.910 TO KM 89.090 OF NH-353B | NHAI | N24001796 | 3-2022 | 10/2024 | Apr-2025 | 4/2025 | 1,013.33 | 1,013.33 | 1,111.33 | 355.07 | 62.01
869 | MAHARASHTRA | POWER | 6L OF WAINGANGA BRIDGE - BHANDARA (INCLUDING BHANDARA BYPASS) SECTION FROM KM 485.000 TO KM 499.800 | NHAI | N24001797 | 10-2021 | 1/2024 | N.A. | 5/2025 | 815.77 | N.A. | 815.77 | 732.70 | 100.00
870 | MAHARASHTRA | POWER | 4L MITIGATION MEASURE STRUCTURES ON CH/MH BORDER TO WAINGANGA BRIDGE SECTION OF NH- 53 | NHAI | N24001798 | 2-2021 | 11/2023 | N.A. | 5/2025 | 540.21 | N.A. | 540.21 | 457.12 | 100.00
871 | MAHARASHTRA | POWER | 4L OF NAGPUR-KATOL SECTION FROM KM. 13.00 TO KM. 62.900 OF NH-353J | NHAI | N24001799 | 2-2021 | 10/2023 | N.A. | 12/2025 | 1,166.96 | N.A. | 1,251.00 | 1,098.21 | 81.17
872 | MAHARASHTRA | POWER | BAL. WORKS OF FAGNE (KM. 510.000) TO MAHARASHTRA/GUJARAT BORDER (KM. 650.794) | NHAI | N24001804 | 12-2019 | 9/2022 | Jun-2024 | 12/2025 | 1,654.07 | N.A. | 980.00 | 887.38 | 97.66
873 | MAHARASHTRA | POWER | 4L OF RATNAGIRI - KOLHAPUR SECTION FROM KM 67.140 TO KM 112.340 OF NH-166 (PKG ? II) | NHAI | N24001834 | 5-2023 | 5/2025 | N.A. | 5/2025 | 839.00 | N.A. | 839.00 | 478.38 | 58.80
874 | MAHARASHTRA | POWER | 4L OF RATNAGIRI - KOLHAPUR SECTION FROM KM 112.340 TO KM 145.300 OF NH-166 (PKG?III) | NHAI | N24001835 | 5-2023 | 5/2025 | N.A. | 5/2025 | 986.00 | N.A. | 986.00 | 580.10 | 56.40
875 | MAHARASHTRA | POWER | REHABILITATION AND UP-GRADATION TO 4 LANE ROAD WITH PAVED SHOULDER CONFIGURATION OF SECTION FROM UND | MoRTH | N24001880 | 3-2022 | 7/2025 | N.A. | 7/2025 | 778.18 | N.A. | 778.18 | 135.78 | -
876 | MAHARASHTRA | POWER | CONSTRUCTION OF NEW FOUR LANE BYPASS TO PARBHANI CITY (PARWA TO ASOLA) KM 463/265 TO KM 481/180 (DES | MoRTH | N24001882 | 3-2022 | 10/2024 | N.A. | 10/2024 | 496.64 | N.A. | 496.64 | 0.00 | 8.00
877 | MAHARASHTRA | POWER | CONSTRUCTION OF 4 LANE FLYOVER AT NAGPUR RTO CHOWK TO NAGPUR UNIVERSITY CAMPUS FROM CH 2/250 TO 5/10 | MoRTH | N24001883 | 3-2021 | 3/2024 | N.A. | 4/2024 | 478.83 | N.A. | 478.83 | 233.48 | 65.00
878 | MAHARASHTRA | POWER | REHABILITATION AND UPGRADATION OF SATANA TO MANGRUL (CHANDWAD) SECTION OF NH752 G DESIGN CH: KM 64.0 | MoRTH | N24001884 | 3-2023 | 5/2025 | N.A. | 5/2025 | 428.80 | N.A. | 428.80 | 54.11 | 30.69
879 | MAHARASHTRA | POWER | REHABILITATION AND UP-GRADATION OF JINTUR- SHIRAD SHAHAPUR SECTION KM 258.300 TO KM 306.300 [DESIGN | MoRTH | N24001885 | 2-2023 | 12/2024 | N.A. | 12/2024 | 414.81 | N.A. | 414.81 | 0.00 | -
880 | MAHARASHTRA | POWER | DEVELOPMENT/WIDENING OF TALEGAON ? CHAKAN ? SHIKRAPUR ? NHAVARA SECTION OF NH 548DG (NHAVARA TO CHOU | MoRTH | N24001886 | 10-2022 | 8/2024 | N.A. | 8/2024 | 304.68 | N.A. | 304.68 | 97.09 | 59.00
881 | MAHARASHTRA | POWER | REHABILITATION AND UPGRADATION OF PARLI TO SIRSALA SECTION OF NH- 361F (KM 136+700 TO 115+000) (LENGT | MoRTH | N24001890 | 2-2023 | 12/2024 | N.A. | 12/2024 | 261.82 | N.A. | 261.82 | 70.59 | 46.00
882 | MAHARASHTRA | POWER | BALANCE WORK OF REHABILITATION AND UP-GRADATION TO NH-166F FROM MAHAD JUNCTION (AT KM 123/400 ON NH- | MoRTH | N24001891 | 7-2021 | 11/2023 | N.A. | 3/2024 | 256.54 | N.A. | 256.54 | 80.10 | 60.00
883 | MAHARASHTRA | POWER | REHABILITATION AND UPGRADATION OF SHIRAPUR JUNCTION TO SHIVAJI CHOWK (DESIGN CHAINAGE KM. 130+00 TO | MoRTH | N24001892 | 2-2023 | 12/2024 | N.A. | 12/2024 | 245.61 | N.A. | 245.61 | 43.39 | 33.00
884 | MAHARASHTRA | POWER | UPGRADATIOBN AND REHABILITATION OF SECTION OF NH 361 F FROM PARLI (00/000) TO GANGAKHED (30/400) TO | MoRTH | N24001896 | 11-2021 | 9/2023 | N.A. | 4/2024 | 224.44 | N.A. | 224.44 | 75.34 | 45.63
885 | MAHARASHTRA | POWER | REHABILITATION AND UP-GRADATION OF SABALKHED TO ASHTI SECTION FROM KM 37+900 TO KM 55+100 AND CHINCH | MoRTH | N24001902 | 12-2022 | 9/2024 | N.A. | 9/2024 | 213.32 | N.A. | 213.32 | 20.00 | 34.00
886 | MAHARASHTRA | POWER | REHABILITATION AND UP-GRADATION OF MUDKHED TO NANDED SECTION FROM KM. 372+000 TO KM 388+400 OF NH 16 | MoRTH | N24001903 | 8-2022 | 4/2025 | N.A. | 4/2025 | 206.54 | N.A. | 206.54 | 21.36 | 10.00
887 | MAHARASHTRA | POWER | KOPARGAON TO SAVALI VIHIR SECTION | MoRTH | N24001904 | 9-2022 | 7/2024 | N.A. | 7/2024 | 195.38 | N.A. | 195.38 | 29.59 | 19.76
888 | MAHARASHTRA | POWER | UP-GRADATION TO 4 LANING OF DAULTABAD T-POINT TO MALIWADA [FROM DESIGN KM.0.000 TO KM 4.000] AND UPG | MoRTH | N24001906 | 8-2022 | 3/2024 | N.A. | 3/2024 | 185.59 | N.A. | 185.59 | 63.56 | 48.00
889 | MAHARASHTRA | POWER | CONSTRUCTION OF SIX LANE FLYOVER AT KATRAJ JUNCTION AT KM, 3/880 OF NH 548-DD (VADGAON - KATRAJ - KO | MoRTH | N24001907 | 6-2021 | 2/2024 | N.A. | 3/2024 | 169.15 | N.A. | 169.15 | 36.94 | 35.96
890 | MAHARASHTRA | POWER | UPGRADATION OF EXHISTING 2 LANE FLEXIBLE PAVEMENT TO 2 LANE PAVED SHOULDERS RIGID PAVEMENT FROM DESI | MoRTH | N24001908 | 12-2021 | 5/2024 | N.A. | 5/2024 | 167.97 | N.A. | 167.97 | 35.28 | 36.76
891 | MAHARASHTRA | POWER | REHABILITATION AND UPGRADATION OF JAMKHED TO SAUTADA SECTION OF NH548 D (FROM KM 195.375 TO KM 208.7 | MoRTH | N24001910 | 9-2022 | 7/2024 | N.A. | 7/2024 | 157.62 | N.A. | 157.62 | 13.86 | 17.03
892 | MAHARASHTRA | POWER | PANGAON TO DHARMAPURI AND PARALI TO INJEGAON 2L+PS | MoRTH | N24001911 | 3-2018 | 7/2024 | N.A. | 12/2023 | 152.03 | N.A. | 152.03 | 81.35 | 97.57
893 | MAHARASHTRA | POWER | 4L OF INDORA CHOWK TO PACHPAOLI AND AGRASEN CHOWK - ASHOKA CHOWK | NHAI | N24002071 | 3-2023 | 6/2026 | N.A. | 6/2026 | 998.27 | N.A. | 998.27 | 348.48 | 48.34
894 | MAHARASHTRA | POWER | IMPROVEMENT OF EXISTING ALIGNMENT OF PANDHARPUR TOWN PART BYPASSED SECTION FROM WAKHARI TO LORD VITT | NHAI | N24002072 | 7-2022 | 10/2025 | N.A. | 10/2025 | 150.21 | 150.21 | 150.21 | 33.70 | 6.00
895 | MAHARASHTRA | POWER | REHABILITATION/UPGRADATION OF EXISTING HIGHWAY TO 2L+PS/4 LANE OF DHAWALI TO RAJOLI FROM DESIGN KM.1 | MoRTH | N24002169 | 3-2022 | 9/2025 | N.A. | 9/2025 | 316.44 | N.A. | 316.44 | 0.00 | -
896 | MAHARASHTRA | POWER | REHABILITATION/ UPGRADATION OF EXISTING HIGHWAY TO FOUR LANE STANDARDS IN KURKHEDA TOWN FROM (KM.413 | MoRTH | N24002170 | 3-2022 | 5/2025 | N.A. | 5/2025 | 163.86 | N.A. | 163.86 | 0.00 | -
897 | MAHARASHTRA | POWER | REHABILITATION AND UP-GRADATION FOR TALERE A?? GAGANBAWDAA?? KOLHAPUR ROAD (NH-166G) STRETCHES START | MoRTH | N24002171 | 2-2023 | 4/2025 | N.A. | 4/2025 | 249.13 | N.A. | 249.13 | 0.00 | -
898 | MAHARASHTRA | POWER | UP-GRADATION TO 4 LANE CONFIGURATION FOR THE WORK OF PETH NAKA TO SANGLI ROAD, NH- 166H, FROM KM 0+00 | MoRTH | N24002172 | 2-2023 | 12/2025 | N.A. | 12/2025 | 856.82 | N.A. | 856.82 | 0.00 | -
899 | MAHARASHTRA | POWER | REHABILITATION AND UP-GRADATION TO 2 LANE WITH PAVED SHOULDER CONFIGURATION OF MAHUD SANGOLA ROAD NH | MoRTH | N24002173 | 2-2023 | 4/2025 | N.A. | 4/2025 | 253.78 | N.A. | 253.78 | 0.00 | -
900 | MAHARASHTRA | POWER | UP-GRADATION TO FOUR LANE/ TWO LANE WITH PAVED SHOULDERS CONFIGURATION OF KALYAN - MURBAD - MALSHEJ | MoRTH | N24002174 | 2-2023 | 8/2026 | N.A. | 8/2026 | 984.07 | N.A. | 984.07 | 0.00 | -
901 | MAHARASHTRA | POWER | CONSTRUCTION OF FOUR-LANE CONCRETE ROAD FROM POLICE HEADQUARTER GONDIA CITY TO RAWANWADI VILLAGE (BI | MoRTH | N24002175 | 2-2023 | 8/2025 | N.A. | 8/2025 | 328.11 | N.A. | 328.11 | 0.00 | -
902 | MAHARASHTRA | POWER | REHABILITATION/UP GRADATION OF KARANJA ? KHERDA - MURTIZAPUR SECTION TO 4LANE+PAVED SHOULDER STANDA | MoRTH | N24002176 | 3-2023 | 2/2026 | N.A. | 2/2026 | 594.44 | N.A. | 594.44 | 0.00 | -
903 | MAHARASHTRA | POWER | REHABILITATION / UPGRADATION TO 4 LANE WITH PAVED SHOULDER OF EXISTING SECTION IN SILLOD TOWN WITH D | MoRTH | N24002177 | 3-2023 | 7/2025 | N.A. | 7/2025 | 153.79 | N.A. | 153.79 | 0.00 | -
904 | MAHARASHTRA | POWER | REHABILITATION, UPGRADATION AND WIDENING OF EXISTING HIGHWAY TO RIGID PAVEMENT 2 LANE WITH PAVED SHO | MoRTH | N24002178 | 2-2023 | 7/2026 | N.A. | 7/2026 | 723.13 | N.A. | 723.13 | 0.00 | -
905 | MAHARASHTRA | POWER | CONSTRUCTION OF FLYOVER AT KM.544.650 INCLUDING ROB ,SERVICE ROADS ,FOOTPATH FOR RCC DRAINS ON URBAN | NHAI | N24000442 | 12-2015 | 3/2019 | Nov-2023 | 7/2025 | 649.50 | N.A. | 649.50 | 623.82 | 94.10
906 | MAHARASHTRA | POWER | NAGPUR RING ROAD PACKAGE-2 | NHAI | N24000560 | 3-2016 | 7/2019 | Mar-2024 | 6/2025 | 591.66 | N.A. | 591.66 | 632.92 | 100.00
907 | MAHARASHTRA | POWER | 4-LANNING OF NH17 AND NEW NO. NH66 FROM KM 161/600 TO 205/400 UNDER HYBRID ANNUITY MODE | MoRTH | N24000584 | 3-2016 | (N.A.) | 12/2023 |  | 1,142.62 | 1,907.03 | 1,142.62 | 1,056.08 | 95.17
908 | MAHARASHTRA | POWER | 4-LANNING OF NH17 AND NEW NO. NH66 FROM KM 241/300 TO 281/300 UNDER HYBRID ANNUITY MODE | MoRTH | N24000585 | 3-2016 | (N.A.) |  |  | 1,101.58 | N.A. | 1,101.58 | 608.53 | -
909 | MAHARASHTRA | POWER | 4-LANNING OF BODHRE-DHULE SECTION(KM 390.000 TO 452.800) | NHAI | N24000656 | 3-2017 | 3/2020 | Jul-2022 | 12/2025 | 744.64 | N.A. | 1,007.00 | 467.65 | 97.69
910 | MAHARASHTRA | POWER | CONSTRUCTION OF 8 LANING OF EXISTING 4 LANE VADAPE TO THANE FROM KM 539.202 TO KM 563.000 SECTION OF | NHAI | N24000851 | 3-2018 | 7/2021 | N.A. | 12/2025 | 1,162.92 | 1,182.87 | 1,182.87 | 412.38 | 64.00
911 | MAHARASHTRA | POWER | SARSAM TO KOTHARI | MoRTH | N24001002 | 2-2016 | 7/2019 | N.A. | 12/2023 | 545.64 | N.A. | 545.64 | 232.64 | 93.68
912 | MAHARASHTRA | POWER | DIGRAS DARWAH KARANJA | MoRTH | N24001013 | 1-2017 | 6/2019 | N.A. | 12/2023 | 391.06 | 391.00 | 391.06 | 287.60 | 92.76
913 | MAHARASHTRA | POWER | DAHEGAON TO KUHI | MoRTH | N24001017 | 1-2017 | 6/2019 | N.A. | 12/2023 | 228.89 | 229.00 | 228.89 | 154.82 | 99.00
914 | MAHARASHTRA | POWER | WADI TO ASOLA | MoRTH | N24001022 | 1-2017 | 9/2019 | N.A. | 12/2023 | 363.82 | 364.00 | 363.82 | 154.65 | 93.15
915 | MAHARASHTRA | POWER | VITA TO NAGAJ | MoRTH | N24001050 | 3-2018 | 12/2019 | N.A. | 12/2023 | 304.58 | 305.00 | 304.58 | 154.68 | 68.39
916 | MAHARASHTRA | POWER | KARAD PATAN CHIPLUN GUHAGAR | MoRTH | N24001057 | 2-2017 | 6/2019 | N.A. | 6/2019 | 407.19 | 407.00 | 407.19 | 323.02 | -
917 | MAHARASHTRA | POWER | KARWANDI TO RAJURI | MoRTH | N24001058 | 3-2018 | 12/2019 | N.A. | 3/2024 | 276.95 | 277.00 | 276.95 | 160.94 | 92.06
918 | MAHARASHTRA | POWER | PALPHATA TO PHULAMBARI | MoRTH | N24001060 | 3-2018 | 12/2019 | N.A. | 12/2023 | 227.19 | 227.00 | 227.19 | 141.92 | 95.00
919 | MAHARASHTRA | POWER | NANDED TO JALKOT | MoRTH | N24001069 | 12-2017 | 9/2019 | N.A. | 9/2019 | 456.93 | 457.00 | 456.93 | 278.22 | 95.00
920 | MAHARASHTRA | POWER | PUNE RAIGARH DISTRICT BORDER TO MANGAON | MoRTH | N24001082 | 3-2018 | 12/2019 | N.A. | 12/2023 | 223.46 | N.A. | 223.46 | 123.46 | 100.00
921 | MAHARASHTRA | POWER | SATARA TO MHASWAD | MoRTH | N24001092 | 1-2017 | 7/2019 | N.A. | 12/2023 | 653.46 | N.A. | 653.46 | 369.62 | -
922 | MAHARASHTRA | POWER | MHASWAD TO TEMBHURNI | MoRTH | N24001099 | 1-2017 | 7/2019 | N.A. | 12/2023 | 488.60 | N.A. | 488.60 | 279.42 | 76.50
923 | MAHARASHTRA | POWER | PEN TO KHOPOLI | MoRTH | N24001106 | 3-2018 | 3/2018 | N.A. | 1/2024 | 301.39 | 302.00 | 301.39 | 170.12 | 82.07
924 | MAHARASHTRA | POWER | PANCHARAL TO MANDANGHAR | MoRTH | N24001107 | 7-2018 | 5/2020 | N.A. | 5/2020 | 381.08 | 302.00 | 381.08 | 45.66 | -
925 | MAHARASHTRA | POWER | NASRATPUR TO BARASGAON | MoRTH | N24001112 | 7-2016 | 9/2019 | N.A. | 9/2019 | 406.54 | 407.00 | 406.54 | 274.30 | -
926 | MAHARASHTRA | POWER | INDAPUR TO VADPALE | MoRTH | N24001114 | 1-2017 | 12/2019 | N.A. | 3/2024 | 1,202.52 | 1,656.94 | 1,202.52 | 1,450.82 | 61.42
927 | MAHARASHTRA | POWER | PAITHAN TO SHIRUR | MoRTH | N24001122 | 3-2017 | 6/2019 | N.A. | 3/2024 | 341.80 | N.A. | 341.80 | 226.19 | 79.00
928 | MAHARASHTRA | POWER | SHIRUR TO KHARDA | MoRTH | N24001123 | 2-2017 | 6/2019 | N.A. | 12/2023 | 381.77 | N.A. | 381.77 | 199.48 | 83.93
929 | MAHARASHTRA | POWER | AURANGABAD TO SILLOD | MoRTH | N24001124 | 2-2017 | 6/2019 | N.A. | 12/2023 | 456.32 | 541.93 | 456.32 | 355.54 | 94.07
930 | MAHARASHTRA | POWER | SILLOD TO FARDAPUR | MoRTH | N24001125 | 2-2017 | 6/2019 | N.A. | 12/2023 | 337.46 | 432.98 | 337.46 | 335.30 | 91.56
931 | MAHARASHTRA | POWER | BHOGAN KHURD TO KASHEDI | MoRTH | N24001132 | 9-2017 | 6/2021 | N.A. | 12/2023 | 743.21 | 743.00 | 743.21 | 911.64 | 88.69
932 | MAHARASHTRA | POWER | KANTE TO WAKED | MoRTH | N24001134 | 3-2016 | 11/2019 | N.A. | 12/2024 | 1,230.02 | 1,230.00 | 1,230.02 | 791.80 | -
933 | MAHARASHTRA | URBAN DEVELOPMENT | MUMBAI METRO LINE 3 (COLABA- BANDRA-SEEPZ) | MMRCL | N28000086 | 7-2013 | 3/2020 | Jul-2025 | 7/2025 | 23,136.00 | N.A. | 37,276.00 | 28,615.78 | 94.77
934 | MAHARASHTRA | URBAN DEVELOPMENT | NAGPUR METRO RAIL PROJECT PHASE II | NMRCL | N28000155 | 12-2022 | 12/2027 | N.A. | 12/2027 | 6,708.00 | N.A. | 6,708.00 | 895.38 | 23.82
935 | MAHARASHTRA | URBAN DEVELOPMENT | PCMC NIGDI PROJECT EXTENSION OF CORRIDOR 1 OF PUNE METRO PHASE 1 | MMRC | N28000157 | 10-2023 | 1/2027 | N.A. | 1/2027 | 910.18 | N.A. | 910.18 | 103.13 | 19.08
936 | MAHARASHTRA | URBAN DEVELOPMENT | PUNE METRO PHASE-1 EXTENSION FROM SWARGATE TO KATRAJ | MMRC | N28000160 | 9-2024 | 3/2029 | N.A. | 3/2029 | 2,954.53 | N.A. | 2,954.53 | 17.35 | 2.91
937 | MANIPUR | CIVIL AVIATION | CONSTRUCTION OF NEW INTEGRATED TERMINAL BUILDING, CONTROL TOWER CUM TECHNICAL BLOCK, APRON, LINK TAX | AAI | N04000100 | 11-2021 | 7/2024 | Dec-2025 | 12/2025 | 499.00 | N.A. | 499.00 | 154.47 | 40.82
938 | MANIPUR | RAILWAYS | JIRIBAM TO IMPHAL (TUPUI)(NL)(NEFR) | NFR | 220100288 | 4-2003 | 12/2026 | Mar-2028 | 3/2028 | 14,322.79 | 12,274.06 | 22,234.60 | 15,485.02 | 69.20
939 | MANIPUR | RAILWAYS | TAMENGLONG - MAHUR PKG-5 | NHIDCL | N24001436 | 8-2021 | 5/2023 | Jan-2025 | 1/2026 | 477.86 | N.A. | 477.86 | 246.09 | 84.87
940 | MANIPUR | RAILWAYS | TAMENGLONG - MAHUR PKG-6 | NHIDCL | N24001437 | 9-2021 | 5/2023 | Nov-2024 | 12/2025 | 311.18 | N.A. | 311.18 | 190.96 | 83.78
941 | MANIPUR | RAILWAYS | MARAM - PEREN PKG-3 | NHIDCL | N24001439 | 8-2021 | 5/2023 | Oct-2024 | 2/2025 | 467.41 | N.A. | 467.41 | 264.83 | 100.00
942 | MANIPUR | RAILWAYS | IMPHAL - KHONGSANG PKG-4 | NHIDCL | N24001453 | 8-2021 | 12/2023 | Jul-2025 | 12/2025 | 579.63 | N.A. | 579.63 | 180.72 | 72.50
943 | MANIPUR | RAILWAYS | CONSTRUCTION OF 2-LANING WITH HARD SHOULDER ROAD OF UKHRUL - TOLOI - TADUBI SECTION OF NH-102A FROM | NHIDCL | N24001473 | 9-2021 | 2/2024 | Mar-2025 | 7/2025 | 310.76 | N.A. | 310.76 | 129.15 | 96.77
944 | MANIPUR | RAILWAYS | IMPHAL - KHONGSANG PKG-5 | NHIDCL | N24001538 | 12-2021 | 5/2024 | Jan-2026 | 3/2026 | 410.68 | N.A. | 410.68 | 152.34 | 70.11
945 | MANIPUR | RAILWAYS | IMPHAL - KHONGSANG PKG-6 | NHIDCL | N24001539 | 12-2021 | 2/2025 | Sep-2025 | 12/2025 | 504.76 | N.A. | 504.76 | 190.26 | 78.25
946 | MANIPUR | RAILWAYS | AKASH BRIDGE - JESSAMI SECTION PKG-2 | NHIDCL | N24001540 | 3-2022 | 2/2025 | Feb-2025 | 3/2025 | 152.11 | N.A. | 152.11 | 73.48 | 100.00
947 | MANIPUR | RAILWAYS | CONSTRUCTION OF 2-LANING WITH HARD SHOULDER ROAD OF UKHRUL - TOLOI - TADUBI SECTION OF NH-102A FROM | NHIDCL | N24001974 | 9-2021 | 1/2025 | Aug-2025 | 8/2025 | 315.56 | N.A. | 315.56 | 137.81 | 88.74
948 | MANIPUR | RAILWAYS | LMPHAL TO JIRIBAM PKG-7 | NHIDCL | N24002028 | 1-2023 | 12/2025 | Dec-2025 | 3/2026 | 760.16 | N.A. | 760.16 | 157.48 | 62.92
949 | MANIPUR | RAILWAYS | UKHRUL TOLOI TADUBI PKG-2 | NHIDCL | N24002131 | 3-2023 | 2/2026 | Mar-2026 | 3/2026 | 578.98 | N.A. | 578.98 | 153.92 | 71.25
950 | MANIPUR | RAILWAYS | MARREM KHULLEN TO JESSAMI SECTION IMPHAL- UKHRUL - JESSAMI PKG-6 (DESIGN CHAINAGE KM 95.700 TO KM 14 | NHIDCL | N24002202 | 3-2023 | 12/2026 | N.A. | 12/2026 | 554.66 | N.A. | 554.66 | 17.79 | 15.00
951 | MANIPUR | RAILWAYS | IMPHAL-KOHIMA ROAD PKG-4B | NHIDCL | N24002203 | 9-2020 | 6/2026 | N.A. | 6/2026 | 268.98 | N.A. | 268.98 | 13.14 | 18.04
952 | MANIPUR | RAILWAYS | JESSAMI TO LAYNEN BRIDGE UKHRUL - JESSAMI PKG-7 | NHIDCL | N24002227 | 3-2023 | 6/2026 | N.A. | 6/2026 | 164.89 | N.A. | 164.89 | 3.83 | 9.78
953 | MANIPUR | RAILWAYS | IMPHAL-KOHIMA ROAD PKG-5A | NHIDCL | N24002232 | 9-2020 | 8/2026 | N.A. | 8/2026 | 228.97 | N.A. | 228.97 | 0.00 | 10.13
954 | MANIPUR | RAILWAYS | CHOITHAR TO MARREM KHULLEN SECTION IMPHAL- UKHRUL - JESSAMI PKG-5 | NHIDCL | N24002242 | 3-2023 | 3/2027 | N.A. | 3/2027 | 564.05 | N.A. | 564.05 | 0.00 | -
955 | MANIPUR | RAILWAYS | IMPHAL - KHONGSANG - JIRIBAM PKG- 2 | NHIDCL | N24002244 | 3-2021 | 3/2026 | N.A. | 3/2026 | 195.14 | N.A. | 195.14 | 4.42 | 11.53
956 | MANIPUR | RAILWAYS | 2-LANING OF CHURACHANDPUR TUIVAI SECTION OF NH-102B (PKG- 2A) | NHIDCL | N24001270 | 3-2020 | 6/2022 | Jun-2025 | 9/2025 | 292.24 | N.A. | 292.24 | 130.66 | 90.69
957 | MANIPUR | RAILWAYS | 2-LANING OF CHURACHANDPUR TUIVAI SECTION OF NH-102B (PKG- 2B) | NHIDCL | N24001271 | 6-2020 | 8/2022 | Jun-2025 | 10/2025 | 365.53 | N.A. | 365.53 | 156.31 | 77.69
958 | MANIPUR | RAILWAYS | IMPROVEMENT/UPGRADATION OF EXISTING 2-LANE TO 4-LANE DIVIDED HIGHWAY FROM TAPHOU KUKI TO DAILI SECTI | NHIDCL | N24001274 | 8-2020 | 4/2022 | Jun-2025 | 12/2025 | 379.39 | N.A. | 379.39 | 218.03 | 70.94
959 | MANIPUR | RAILWAYS | MARIAM - PEREN PKG-1A | NHIDCL | N24001349 | 2-2021 | 12/2022 | Mar-2025 | 12/2025 | 226.32 | N.A. | 226.32 | 105.78 | 74.48
960 | MANIPUR | RAILWAYS | MARIAM - PEREN (PKG 1B) | NHIDCL | N24001350 | 2-2021 | 12/2022 | Jan-2025 | 9/2025 | 188.36 | N.A. | 188.36 | 126.71 | 99.02
961 | MANIPUR | RAILWAYS | TAMENGLONG - MAHUR PKG-3 | NHIDCL | N24001354 | 3-2021 | 12/2022 | Sep-2024 | 11/2025 | 234.08 | N.A. | 234.08 | 139.45 | 92.82
962 | MANIPUR | RAILWAYS | SENAPATI- IMPHAL PKG-5B | NHIDCL | N24001400 | 3-2021 | 1/2023 | May-2025 | 10/2025 | 211.70 | N.A. | 211.70 | 83.79 | 71.06
963 | MANIPUR | RAILWAYS | IMPHAL - KHONGSANG PKG-3 | NHIDCL | N24001401 | 7-2021 | 3/2023 | Mar-2025 | 10/2025 | 467.00 | N.A. | 467.00 | 193.81 | 79.81
964 | MANIPUR | RAILWAYS | TAMENGLONG - MAHUR PKG-1 | NHIDCL | N24001402 | 7-2021 | 3/2023 | Jan-2025 | 1/2025 | 185.80 | N.A. | 185.80 | 117.78 | 100.00
965 | MANIPUR | RAILWAYS | TAMENGLONG - MAHUR PKG-2 | NHIDCL | N24001403 | 7-2021 | 3/2023 | Jan-2025 | 12/2025 | 483.87 | N.A. | 483.87 | 278.89 | 92.94
966 | MANIPUR | RAILWAYS | TAMENGLONG - MAHUR PKG-4 | NHIDCL | N24001404 | 7-2021 | 3/2023 | Feb-2025 | 3/2025 | 198.77 | N.A. | 198.77 | 127.86 | 100.00
967 | MANIPUR | RAILWAYS | CHURACHANPUR TUIVAI PKG-3 | NHIDCL | N24001405 | 7-2021 | 10/2023 | Mar-2025 | 12/2025 | 673.27 | N.A. | 673.27 | 382.37 | 80.28
968 | MEGHALAYA | DEPARTMENT OF HIGHER EDUCATION | CONSTRUCTION AND DEVELOPMENT OF NATINAL INSTITUTE OF TECHNOLOGY MEGHALAYA PERMANENT CAMPUS AT SOHRA | RITES OF HIGHER | N42000001 | 9-2013 | 9/2014 | Jul-2025 | 7/2025 | 484.32 | 429.70 | 494.52 | 270.55 | 84.00
969 | MEGHALAYA | DEPARTMENT OF HIGHER EDUCATION | REHABILITATION AND UPGRADATION OF NONGSTOIN TO WAHKAJI SECTION OF PROJECT ROAD KM 0.000 TO KM 43.06 | MoRTH | N24001441 | 8-2020 | 2/2022 | N.A. | 7/2025 | 302.88 | N.A. | 302.88 | 228.68 | 96.00
970 | MEGHALAYA | DEPARTMENT OF HIGHER EDUCATION | REHABITITATION AND UP GRADATION OF NONGSTOIN-RAMBRAI-KYRSHAI ROAD UP TO MEGHALAYA-ASSAM BORDER FROM | NHIDCL | N24001474 | 9-2021 | 5/2024 | May-2026 | 5/2026 | 359.86 | N.A. | 359.86 | 233.26 | 60.81
971 | MEGHALAYA | DEPARTMENT OF HIGHER EDUCATION | RANIKOR- MAHESHKHOLA- BAGHMARA PKG-2 | NHIDCL | N24001541 | 11-2021 | 6/2024 | Dec-2024 | 5/2025 | 283.50 | N.A. | 283.50 | 257.26 | 100.00
972 | MEGHALAYA | DEPARTMENT OF HIGHER EDUCATION | CONSTRUCTION OF 2-LANE WITH PAVED SHOULDER OF SHILLONG WESTERN BYPASS STARTING FROM NH-06 NEAR LADUM | NHIDCL | N24002156 | 3-2023 | 9/2026 | N.A. | 9/2026 | 620.30 | N.A. | 620.30 | 222.26 | 30.00
973 | MEGHALAYA | DEPARTMENT OF HIGHER EDUCATION | SHILLONG WESTERN BYPASS PACKAGE-2 | NHIDCL | N24002157 | 3-2023 | 9/2026 | N.A. | 9/2026 | 686.00 | N.A. | 686.00 | 293.36 | 25.52
974 | MEGHALAYA | DEPARTMENT OF HIGHER EDUCATION | CONSTRUCTION OF 2-LANE WITH PAVED SHOULDERS OF SHILLONG WESTERN BYPASS STARTING FROM NH-06 NEAR LADU | NHIDCL | N24002158 | 3-2023 | 9/2026 | N.A. | 9/2026 | 562.48 | N.A. | 562.48 | 297.91 | 25.27
975 | MEGHALAYA | DEPARTMENT OF HIGHER EDUCATION | DAINADUBI-DARUGIRI PKG-1B | NHIDCL | N24002233 | 3-2023 | 3/2027 | N.A. | 3/2027 | 705.83 | N.A. | 705.83 | 0.32 | 2.13
976 | MEGHALAYA | DEPARTMENT OF HIGHER EDUCATION | IMPROVEMENT AND WIDENING TWO LANNIG WITH PAVED SHOULDER OF NATIONAL HIGHWAY 127B FROM KM 31.500 (GOE | MoRTH | N24002239 | 12-2023 | 5/2027 | N.A. | 5/2027 | 504.00 | N.A. | 504.00 | 0.00 | -
977 | MEGHALAYA | DEPARTMENT OF HIGHER EDUCATION | WIDENING TO 2-LANE WITH GEOMETRIC IMPROVEMENTS OF TURA DALU ROAD UNDER JICA FUNDING FROM KM 85.000 T | NHIDCL | N24000771 | 4-2017 | 9/2021 | Jun-2025 | 6/2025 | 553.51 | 610.09 | 553.51 | 438.16 | 88.07
978 | MEGHALAYA | DEPARTMENT OF HIGHER EDUCATION | IMPROVEMENT/WIDENING TO 2-L WITH PAVED SHOULDER FROM (DESIGN KM 0.00 TO KM 10.670) / 4-LANING FROM ( | NHIDCL | N24001313 | 11-2020 | 12/2023 | Oct-2025 | 10/2025 | 351.12 | N.A. | 351.12 | 299.22 | 63.00
979 | MEGHALAYA | DEPARTMENT OF HIGHER EDUCATION | IMPROVEMENT/WIDENING TO 2-LANE WITH PAVED SHOULDER FROM (DESIGN KM 10.670 TO KM 37.550) BETWEEN SHIL | NHIDCL | N24001314 | 11-2020 | 12/2023 | N.A. | 8/2026 | 525.68 | N.A. | 525.68 | 434.50 | 32.00
980 | MEGHALAYA | DEPARTMENT OF HIGHER EDUCATION | IMPROVEMENT/WIDENING TO 2-LANE WITH PAVED SHOULDER FROM (DESIGN KM 45.760 TO KM 63.530) BETWEEN SHIL | NHIDCL | N24001334 | 11-2020 | 12/2023 | N.A. | 4/2026 | 445.51 | N.A. | 445.51 | 214.34 | 30.30
981 | MEGHALAYA | DEPARTMENT OF HIGHER EDUCATION | IMPROVEMENT/WIDENING TO 2-LANE WITH PAVED SHOULDER / 4-LANING FROM (DESIGN KM 63.530 TO KM 71.520) B | NHIDCL | N24001335 | 11-2020 | 12/2023 | N.A. | 11/2026 | 284.21 | N.A. | 284.21 | 107.86 | 24.00
982 | MIZORAM | RAILWAYS | BHAIRABI SAIRONG, NL, NEFR | NFR | N22000100 | 4-2008 | 3/2025 | N.A. | 6/2025 | 6,527.45 | 5,021.45 | 8,071.30 | 8,066.76 | 97.00
983 | MIZORAM | RAILWAYS | UP-GRADATION TO 2-LANE WITH PAVED SHOULDERS OF NGOPA - PAWLRANG SECTION OF NH 102B OF AIZAWL - IMPHA | NHIDCL | N24001975 | 9-2021 | 2/2025 | N.A. | 12/2025 | 523.78 | N.A. | 523.78 | 379.40 | 95.31
984 | MIZORAM | RAILWAYS | KEIFANG - TUVAI PKG-3 | NHIDCL | N24002027 | 12-2021 | 2/2025 | N.A. | 12/2025 | 500.88 | N.A. | 500.88 | 279.44 | 75.40
985 | MIZORAM | RAILWAYS | ZORINPUI- HMAWNGBU-LONGMASU (NH-502A) | NHIDCL | N24002204 | 2-2023 | 12/2026 | N.A. | 12/2026 | 781.85 | N.A. | 781.85 | 33.77 | 3.00
986 | MIZORAM | RAILWAYS | WIDENING AND UP-GRADATION TO 2- LANE WITH PAVED SHOULDER CONFIGURATION AND GEOMETRIC IMPROVEMENTS FRO | NHIDCL | N24000857 | 4-2017 | 4/2023 | N.A. | 4/2025 | 519.09 | N.A. | 785.65 | 670.91 | 97.51
987 | MIZORAM | RAILWAYS | WIDENING AND UP-GRADATION TO 2- LANE WITH PAVED SHOULDER CONFIGURATION AND GEOMETRIC IMPROVEMENTS FRO | NHIDCL | N24000858 | 4-2017 | 7/2023 | N.A. | 5/2024 | 640.07 | N.A. | 1,286.35 | 1,195.84 | 98.90
988 | MIZORAM | RAILWAYS | WIDENING AND UP-GRADATION TO 2- LANE WITH PAVED SHOULDER CONFIGURATION AND GEOMETRIC IMPROVEMENTS FRO | NHIDCL | N24000861 | 4-2017 | 4/2023 | N.A. | 4/2025 | 473.18 | N.A. | 688.25 | 541.04 | 95.00
989 | MIZORAM | RAILWAYS | WIDENING AND UP-GRADATION TO 2- LANE WITH PAVED SHOULDER CONFIGURATION AND GEOMETRIC IMPROVEMENTS FRO | NHIDCL | N24000862 | 4-2017 | 4/2023 | N.A. | 4/2025 | 537.82 | N.A. | 789.05 | 779.37 | 99.88
990 | MIZORAM | RAILWAYS | WIDENING AND UP-GRADATION TO 2- LANE WITH PAVED SHOULDER CONFIGURATION AND GEOMETRIC IMPROVEMENTS FRO | NHIDCL | N24000863 | 4-2017 | 6/2023 | N.A. | 5/2025 | 518.53 | N.A. | 906.76 | 849.68 | 97.90
991 | MIZORAM | RAILWAYS | WIDENING AND UP-GRADATION TO 2- LANE WITH PAVED SHOULDER CONFIGURATION AND GEOMETRIC IMPROVEMENTS FRO | NHIDCL | N24000864 | 4-2017 | 4/2024 | N.A. | 5/2025 | 404.29 | N.A. | 750.32 | 666.58 | 100.00
992 | MIZORAM | RAILWAYS | WIDENING AND UP-GRADATION TO 2- LANE WITH PAVED SHOULDER CONFIGURATION AND GEOMETRIC IMPROVEMENTS FRO | NHIDCL | N24000865 | 4-2017 | 9/2023 | N.A. | 5/2025 | 428.11 | N.A. | 746.39 | 613.69 | 99.82
993 | MIZORAM | RAILWAYS | CONSTRUCTION OF TWO LANE WITH PAVED SHOULDER OF SELLING-DULTE SECTION OF NH-06 (PKG-I) | NHIDCL | N24001278 | 3-2020 | 7/2022 | N.A. | 6/2024 | 206.88 | N.A. | 219.33 | 265.38 | 100.00
994 | MIZORAM | RAILWAYS | CONSTRUCTION OF TWO LANE WITH PAVED SHOULDER OF SELLING-DULTE SECTION OF NH-06 (PKG-III) | NHIDCL | N24001281 | 3-2020 | 7/2022 | N.A. | 10/2024 | 292.24 | N.A. | 331.17 | 294.78 | 94.40
995 | MIZORAM | RAILWAYS | DULTE- KWALKULH - CHAMPAI PKG.2 | NHIDCL | N24001356 | 3-2021 | 12/2022 | Apr-2024 | 4/2024 | 233.25 | N.A. | 233.25 | 172.09 | 100.00
996 | MIZORAM | RAILWAYS | TLABUNG - LUNGLEI PKG-A | NHIDCL | N24001358 | 3-2021 | 12/2022 | N.A. | 3/2026 | 698.44 | N.A. | 698.45 | 502.24 | 63.70
997 | MIZORAM | RAILWAYS | TLABUNG - LUNGLEI PKG-B | NHIDCL | N24001359 | 3-2021 | 1/2023 | N.A. | 3/2026 | 740.58 | N.A. | 740.58 | 373.89 | 61.00
998 | MULTI STATE | COAL | NILJAI EXPANSION (DEEP) OC (3.5 MTY) | WCL | N06000154 | 8-2016 | 3/2022 | Mar-2025 | 3/2025 | 319.76 | 319.76 | 319.76 | 183.67 | 98.00
999 | MULTI STATE | COAL | BINA KAKRI AMALGAMATION OCP 14 MTPA | NCL | N06000192 | 8-2020 | 3/2024 | N.A. | 3/2027 | 836.42 | N.A. | 836.42 | 778.71 | 89.08
1000 | MULTI STATE | DPIIT | NATIONAL INDUSTRIAL CORRIDOR PROJECT | DMIC FOR DPIIT | N40000001 | 9-2011 | 3/2027 | Mar-2032 | 3/2032 | 20,084.00 | 26,684.00 | 26,684.00 | 11,262.06 | 50.99
1001 | MULTI STATE | PETROLEUM | KOCHI-KOOTTANAD-BANGALORE- MANGALORE PIPELINE PHASE-II | GAIL | N16000285 | 6-2009 | 12/2012 | Dec-2025 | 12/2025 | 2,915.00 | 5,909.00 | 5,909.00 | 4,381.20 | 94.20
1002 | MULTI STATE | PETROLEUM | SRIKAKULAM ANGUL PIPELINE PROJECT | GAIL | N16000388 | 9-2019 | 7/2022 | Dec-2025 | 12/2025 | 2,658.34 | N.A. | 2,658.34 | 2,179.10 | 94.60
1003 | MULTI STATE | PETROLEUM | DHAMRA HALDIA PIPELINE PROJECT | GAIL | N16000391 | 3-2020 | 11/2022 | Dec-2025 | 12/2025 | 1,030.65 | N.A. | 1,030.65 | 841.90 | 86.80
1004 | MULTI STATE | PETROLEUM | MUMBAI NAGPUR JHARSUGUDA PIPELINE PROJECT | GAIL | N16000398 | 6-2020 | 5/2023 | Sep-2025 | 9/2025 | 7,844.25 | N.A. | 7,844.25 | 6,412.20 | 95.10
1005 | MULTI STATE | PETROLEUM | NORTH EAST GAS GRID | IGGL | N16000439 | 11-2020 | 3/2024 | Jul-2025 | 3/2027 | 9,265.00 | 9,265.00 | 9,265.00 | 6,270.19 | 84.51
1006 | MULTI STATE | PETROLEUM | GURDASPUR JAMMU PIPELINE | GAIL | N16000531 | 7-2023 | 7/2026 | Jul-2026 | 7/2026 | 521.92 | 521.92 | 521.92 | 153.20 | 35.50
1007 | MULTI STATE | PETROLEUM | COMPREHENSIVE SCHEME FOR THE STRENGHTENING OF THE TRANSMISSION AND DISTRIBUTION SYSTEM IN A P | PGCIL | N18000249 | 12-2014 | 12/2018 | Mar-2025 | 3/2027 | 4,754.42 | 9,129.32 | 9,129.32 | 7,602.44 | 81.70
1008 | MULTI STATE | PETROLEUM | NORTH EASTERN REGION POWER SYSTEM IMPROVEMENT PROJECT (NERPSIP) FOR SIX (6) STATES | PGCIL | N18000250 | 12-2014 | 12/2018 | Mar-2025 | 9/2025 | 5,111.33 | 6,700.00 | 6,700.00 | 5,230.02 | 96.00
1009 | MULTI STATE | PETROLEUM | TS FOR EVACUATION OF POWER FROM PAKALDUL HEP IN CHENAB VALLEY HEPS - LTA SYSTEM | PGCIL | N18000328 | 2-2022 | 4/2025 | N.A. | 8/2025 | 318.12 | N.A. | 318.12 | 254.50 | 98.00
1010 | MULTI STATE | PETROLEUM | TRANSMISSION SYSTEM STRENGTHENING FOR SRINAGAR-LEH TRANSMISSION SYSTEM | PGCIL | N18000330 | 3-2022 | 12/2024 | N.A. | 9/2025 | 288.71 | N.A. | 288.71 | 199.53 | 48.00
1011 | MULTI STATE | PETROLEUM | TRANSMISSION SYSTEM STRENGTHENING SCHEME FOR EVACUATION OF POWER FROM SOLAR ENERGY ZONES IN RAJASTHA | PGCIL | N18000331 | 2-2022 | 9/2023 | N.A. | 8/2025 | 359.47 | N.A. | 359.47 | 327.28 | 90.00
1012 | MULTI STATE | PETROLEUM | TRANSMISSION SYSTEM STRENGTHENING SCHEME FOR EVACUATION OF POWER FROM SOLAR ENERGY ZONES IN RAJASTHA | PGCIL | N18000332 | 5-2022 | 11/2023 | N.A. | 9/2025 | 1,666.00 | 2,218.00 | 2,218.00 | 2,029.28 | 94.10
1013 | MULTI STATE | PETROLEUM | TRANSMISSION NETWORK EXPANSION IN GUJARAT TO INCREASE ATC FROM ISTS: PART B | PGCIL | N18000337 | 7-2022 | 6/2023 | N.A. | 9/2025 | 4,546.26 | N.A. | 4,546.26 | 4,091.67 | 93.00
1014 | MULTI STATE | PETROLEUM | SYSTEM STRENGTHENING SCHEME FOR EASTERN AND NORTH EASTERN REGION | PGCIL | N18000343 | 10-2022 | 10/2025 | N.A. | 6/2025 | 307.87 | N.A. | 307.87 | 298.87 | 100.00
1015 | MULTI STATE | PETROLEUM | TRANSMISSION SYSTEM FOR KURNOOL WIND ENERGY ZONE SOLAR ENERGY ZONE (AP) PART-A PART B | PGCIL | N18000352 | 3-2023 | 11/2024 | N.A. | 9/2025 | 3,546.94 | N.A. | 3,546.94 | 2,837.55 | 94.00
1016 | MULTI STATE | PETROLEUM | ER WR TRANSMISSION LIMITED | PGCIL | N18000353 | 3-2023 | 3/2025 | N.A. | 6/2025 | 281.16 | N.A. | 281.16 | 281.15 | 100.00
1017 | MULTI STATE | PETROLEUM | NANGALDAM-TALWARA(NL),NR | NR | 220100188 | 3-1981 | 12/2025 | Jan-2027 | 6/2027 | 2,018.00 | 603.00 | 2,017.96 | 1,629.74 | 75.00
1018 | MULTI STATE | PETROLEUM | LALITPUR-SATNA-REWA-SINGRULI NL, (NCR) | WCR | 220100232 | 9-1998 | 3/2027 | N.A. | 3/2025 | 8,913.94 | 63.57 | 8,248.50 | 2,500.34 | 43.00
1019 | MULTI STATE | PETROLEUM | CHHAPRA-BALLIA UP | NER | N22000134 | 3-2013 | 2/2025 | N.A. | 12/2025 | 941.05 | 954.00 | 1,045.82 | 1,004.59 | 95.50
1020 | MULTI STATE | PETROLEUM | CHOTTAUDEPUR-DHAR(NL) | WR | N22000138 | 4-2007 | 12/2026 | Dec-2027 | 12/2027 | 1,793.65 | 1,793.63 | 1,793.63 | 1,641.84 | 59.00
1021 | MULTI STATE | PETROLEUM | DAHOD-INDORE VIA SARDARPUR, JHABUA AND DHAR (NL) | WR | N22000139 | 4-2007 | 2/2027 | Feb-2027 | 2/2027 | 1,942.00 | 1,873.10 | 2,873.11 | 3,119.79 | 59.00
1022 | MULTI STATE | PETROLEUM | GWALIOR-SEOPURKALA WITH EXTENSION TO KOTA (GC) | NCR | N22000148 | 4-2011 | 3/2025 | N.A. | 12/2024 | 2,912.96 | N.A. | 3,845.60 | 1,024.32 | -
1023 | MULTI STATE | PETROLEUM | DHOLPUR-SIRMUTTRA WITH EXTENSION TO GANGAPURCITY AND MOHARI-TANTPUR AND TANPUR- BANSI PAHARPUR | NCR | N22000158 | 4-2010 | 2/2019 | N.A. | 12/2026 | 746.83 | N.A. | 746.83 | 391.89 | 39.00
1024 | MULTI STATE | PETROLEUM | NEW BG LINE FROM BALURGHAT TO HILLY NFR | NFR | N22000206 | 4-2010 | 3/2027 | N.A. | 3/2027 | 1,208.67 | N.A. | 1,181.57 | 425.12 | 8.00
1025 | MULTI STATE | PETROLEUM | NEW BG LINE FROM JAGBANI TO BIRATNAGAR | NFR | N22000207 | 4-2010 | 3/2022 | Dec-2026 | 12/2026 | 401.65 | 485.96 | 485.96 | 361.33 | 86.00
1026 | MULTI STATE | PETROLEUM | MURKONGSELEK-PASIGHAT NL | NFR | N22000208 | 4-2011 | 3/2025 | N.A. | 11/2025 | 435.06 | N.A. | 1,249.35 | 803.88 | 54.00
1027 | MULTI STATE | PETROLEUM | PIRPAINTI-JASIDIH | ER | N22000219 | 4-2013 | 3/2028 | Mar-2028 | 3/2028 | 2,555.03 | N.A. | 2,610.84 | 1,140.05 | 45.00
1028 | MULTI STATE | PETROLEUM | KAZIPET-VIJAYAWADA 3RD LINE WITH ELECTRIFICATION | SCR | N22000261 | 4-2012 | 2/2025 | N.A. | 3/2025 | 1,953.00 | N.A. | 1,952.68 | 1,936.28 | -
1029 | MULTI STATE | PETROLEUM | DEOBAND (MUZAFFARNAGAR)- ROORKEE NL | NR | N22000274 | 4-2007 | 3/2024 | N.A. | 3/2025 | 1,053.23 | N.A. | 1,053.00 | 592.53 | 99.00
1030 | MULTI STATE | PETROLEUM | RAYADURGA-TUMKUR NL | SWR | N22000279 | 4-2007 | 9/2015 | N.A. | 2/2028 | 2,495.59 | 2,495.86 | 2,495.86 | 1,675.34 | 65.00
1031 | MULTI STATE | PETROLEUM | HOTGI-KUDGI-GADAG | SWR | N22000333 | 3-2015 | 12/2024 | N.A. | 2/2026 | 1,877.81 | 1,877.81 | 2,458.87 | 2,574.88 | 89.00
1032 | MULTI STATE | PETROLEUM | KAZIPET-BALHRSHA | SCR | N22000367 | 4-2015 | 1/2025 | N.A. | 1/2025 | 2,594.59 | N.A. | 2,909.00 | 2,862.60 | -
1033 | MULTI STATE | PETROLEUM | MUMBAI AHMEDABAD HIGH SPEED RAIL PROJECT | NHSRCL | N22000463 | 12-2015 | 8/2027 | N.A. | 8/2027 | 108,000.00 | N.A. | 108,000.00 | 78,839.00 | 52.89
1034 | MULTI STATE | PETROLEUM | WESTERN DEDICATED FREIGHT CORRIDOR | DFCC | N22000464 | 11-2007 | 3/2022 | N.A. | 3/2020 | 51,101.00 | N.A. | 51,101.00 | 47,476.00 | 83.00
1035 | MULTI STATE | PETROLEUM | CHANDIGARH-BADDI | NR | N22000467 | 4-2007 | 6/2025 | Dec-2026 | 12/2026 | 1,540.13 | 1,540.14 | 1,540.14 | 956.13 | 30.00
1036 | MULTI STATE | PETROLEUM | NARAYANGARH TO BHADRAK 3RD LINE (155 KM) | SER | N22000506 | 3-2019 | 12/2024 | N.A. | 6/2026 | 2,400.00 | N.A. | 1,866.31 | 2,112.20 | 61.00
1037 | MULTI STATE | ROAD TRANSPORT AND HIGHWAYS | 4/6L OF SPUR TO HARIDWAR (GREENFIELD) FROM KM. 0.000 TO KM. 49.000 | NHAI | N24001628 | 11-2021 | 2/2025 | Aug-2025 | 8/2025 | 2,155.95 | N.A. | 2,155.95 | 1,360.04 | 71.01
1038 | MULTI STATE | ROAD TRANSPORT AND HIGHWAYS | 6L WITH ACCESS CONTROL PROVISION SAHARANPUR BYPASS TO GANESHPUR SECTION FROM 13.89 KM TO 41.820 KM O | NHAI | N24001629 | 4-2022 | 11/2024 | Jul-2025 | 7/2025 | 796.65 | N.A. | 796.65 | 452.41 | 91.71
1039 | MULTI STATE | ROAD TRANSPORT AND HIGHWAYS | VARANASI-AURANGABAD KM.786 TO KM.978.40 | NHAI | N24000182 | 9-2011 | 3/2014 | N.A. | 6/2025 | 2,848.00 | N.A. | 3,241.56 | 3,901.66 | 90.42
1040 | MULTI STATE | SHIPPING AND PORTS | JAL MARG VIKAS PROJECT | IWAI | N25000072 | 1-2018 | 3/2023 | Dec-2025 | 12/2025 | 5,369.18 | 5,061.15 | 5,061.15 | 3,472.54 | 69.48
1041 | MULTI STATE | SHIPPING AND PORTS | PHASE-I OF CONSOLIDATION OF EXISTING CDR DATA CENTERS AND NIB-P3 DATA CENTERS WITH STATE OF THE ART | BSNL | N26000114 | 3-2020 | 6/2021 | Nov-2021 | 12/2025 | 461.42 | 461.42 | 461.42 | 166.02 | 81.00
1042 | MULTI STATE | SHIPPING AND PORTS | SUPER EDGE ROUTERS FOR BSNL INTERNET PROTOCOL - MULTI PROTOCOL LEBEL SWITCHING (IPMPLS) NETWORK and | BSNL | N26000115 | 3-2023 | 3/2024 | Jul-2024 | 3/2025 | 239.60 | N.A. | 239.60 | 179.63 | 100.00
1043 | MULTI STATE | SHIPPING AND PORTS | MPLS-IP BASED ACCESS AND AGGREGATION NETWORK (MAAN) IN BSNL ALONG WITH TEST AND MEASURING EQUIPMENT | BSNL | N26000116 | 5-2023 | 8/2024 | Nov-2024 | 6/2025 | 645.13 | N.A. | 645.13 | 348.03 | 89.15
1044 | MULTI STATE | SHIPPING AND PORTS | PLANNIN ENGINEERING SUPPLY INSTALLATION TESTING COMMISSIONING INTEGARTION and ANNUAL MAINTENANCE OF | BSNL | N26000117 | 6-2023 | 6/2025 | N.A. | 6/2025 | 24,556.35 | 24,544.55 | 24,544.55 | 8,211.15 | 95.54
1045 | MULTI STATE | SHIPPING AND PORTS | OPTICAL TRANSPORT NETWORK (OTN) PH-4 IN BSNL | BSNL | N26000118 | 2-2024 | 8/2025 | N.A. | 8/2025 | 810.99 | N.A. | 810.99 | 635.37 | 100.00
1046 | MULTI STATE | URBAN DEVELOPMENT | DELHI GHAZIABAD MEERUT RRTS CORRIDOR | NCRTC | N28000134 | 3-2019 | 6/2025 | N.A. | 6/2025 | 30,274.00 | N.A. | 30,274.00 | 25,812.28 | 86.80
1047 | NAGALAND | PETROLEUM | AUGMENTATION OF DIMAPUR DEPOT, DIMAPUR | IOCL | N16000529 | 8-2023 | 11/2027 | N.A. | 11/2027 | 227.62 | N.A. | 227.62 | 6.62 | 19.00
1048 | NAGALAND | RAILWAYS | NEW LINE FROM DIMAPUR TO ZUBZA(KOHIMA) NATIONAL PROJECT (NEFR) | NFR | N22000124 | 4-2006 | 3/2026 | N.A. | 12/2029 | 6,663.20 | 6,663.20 | 6,663.20 | 4,942.71 | 74.00
1049 | NAGALAND | RAILWAYS | MERANGKONG-TAMLU-MON (MTM) PKG-5 | NHIDCL | N24001438 | 7-2021 | 12/2023 | N.A. | 9/2025 | 161.73 | N.A. | 161.73 | 65.19 | 73.34
1050 | NAGALAND | RAILWAYS | WIDENING OF EXISTING SINGLE LANE / INTERMEDIATE LANE ROAD TO 2 LANE FROM KM 101 TO KM 125 OF NH 61 I | MoRTH | N24001465 | 6-2020 | 9/2024 | Jun-2026 | 6/2026 | 252.19 | N.A. | 252.19 | 14.33 | 20.27
1051 | NAGALAND | RAILWAYS | WIDENING TO EXISTING SINGLE LANE /INTERMEDIATE LANE TO 2 LANE FROM KM185.00 TO KM 220.00 OF NH- 61 (N | MoRTH | N24001466 | 3-2021 | 7/2024 | Dec-2025 | 12/2025 | 297.24 | N.A. | 297.24 | 150.10 | 80.31
1052 | NAGALAND | RAILWAYS | WIDENING TO EXISTING SINGRE/INTERMEDIATE RANE TO 2 LANE FROM KM 135 TO KM 147 AND FROM KM 156.00 TO | MoRTH | N24001467 | 3-2021 | 2/2024 | Mar-2025 | 3/2025 | 226.44 | N.A. | 226.44 | 140.24 | 100.00
1053 | NAGALAND | RAILWAYS | WIDENING OF EXISTING SINGLE LANE ROAD TO INTERMEDIATE LANE ROAD FROM MOKOKCHUNG TO CHARE VIA DIKHU I | MoRTH | N24001855 | 2-2021 | 6/2025 | Sep-2025 | 9/2025 | 192.93 | N.A. | 192.93 | 112.09 | 93.38
1054 | NAGALAND | RAILWAYS | PEREN-DIMAPUR PKG-3 | NHIDCL | N24001912 | 2-2021 | 6/2025 | N.A. | 12/2025 | 177.77 | 199.02 | 199.02 | 46.94 | 63.33
1055 | NAGALAND | RAILWAYS | WIDENING TO 2 LANE WITH HARD SHOULDER OF AKEGWO-AVANGKHU SECTION OF NH-202K FOR PACKAGE-I (DESIGN CH | NHIDCL | N24001976 | 12-2022 | 2/2026 | N.A. | 2/2026 | 430.24 | N.A. | 430.24 | 100.51 | 58.57
1056 | NAGALAND | RAILWAYS | WIDENING TO 2 LANE WITH HARD SHOULDER OF AKEGWO-AVANGKHU SECTION OF NH-202K FOR PACKAGE-II (DESIGN C | NHIDCL | N24001977 | 12-2022 | 2/2026 | N.A. | 2/2026 | 442.54 | N.A. | 442.54 | 50.60 | 28.05
1057 | NAGALAND | RAILWAYS | WIDENING TO 2 LANE WITH HARD SHOULDER OF AKEGWO-AVANGKHU SECTION OF NH-202K FOR PACKAGE-III (DESIGN | NHIDCL | N24001978 | 12-2022 | 2/2026 | N.A. | 2/2026 | 497.18 | N.A. | 497.18 | 168.20 | 66.03
1058 | NAGALAND | RAILWAYS | FOUR LANING OF EXISTING DIMAPUR KOHIMA ROAD FROM DESIGN KM 152.490 TO KM 166.700 (EXISTING KM 156.00 | NHIDCL | N24000688 | 3-2016 | 8/2022 | Sep-2025 | 9/2025 | 429.52 | 794.74 | 794.74 | 321.40 | 92.46
1059 | NAGALAND | RAILWAYS | (I) CONSTRUCTION OF FOUR/SIX LANING FROM KM 132.375 TO KM 158.058 (TOTAL NEW ALIGNMENT LENGTH OF 20. | NHIDCL | N24000752 | 2-2017 | 9/2020 | Feb-2023 | 4/2025 | 387.00 | 688.12 | 688.12 | 392.01 | 100.00
1060 | NAGALAND | RAILWAYS | (II) CONSTRUCTION OF DIMAPUR BYPASS (ASSAM PORTION) OF 4/6 LANE PAVEMENT ON EPC BASIS FROM EXISTING | NHIDCL | N24000753 | 3-2018 | 11/2022 | Aug-2024 | 4/2025 | 500.09 | 698.81 | 698.81 | 393.53 | 100.00
1061 | NAGALAND | RAILWAYS | CONSTRUCTION OF TWO LANE WITH HARD SHOULDERS OF MERANGKONG- TAMLU-MON ROAD FROM EXISTING KM 20.456 TO | NHIDCL | N24000763 | 3-2018 | 12/2021 | Aug-2022 | 8/2025 | 215.79 | N.A. | 215.79 | 132.93 | 80.38
1062 | NAGALAND | RAILWAYS | CONSTRUCTION OF TWO LANE WITH HARD SHOULDERS OF MERANGKONG- TAMLU-MON ROAD FROM EXISTING KM 60.345 TO | NHIDCL | N24000765 | 3-2018 | 9/2018 | Jun-2023 | 9/2025 | 323.98 | N.A. | 323.98 | 119.94 | 60.11
1063 | NAGALAND | RAILWAYS | CONSTRUCTION OF 2-LANE WITH PAVED SHOULDER OF KOHIMA- BYPASS ROAD FROM DESIGN KM10.500 TO 21.00KM [D | NHIDCL | N24001255 | 9-2020 | 10/2022 | Sep-2024 | 6/2026 | 277.44 | N.A. | 277.44 | 169.46 | 67.91
1064 | NAGALAND | RAILWAYS | CONSTRUCTION OF 2-LANE WITH PAVED SHOULDER OF KOHIMA- BYPASS ROAD FROM DESIGN KM21.0 TO KM32.0 [DESIG | NHIDCL | N24001257 | 8-2020 | 10/2022 | Jun-2025 | 12/2025 | 159.85 | 342.29 | 159.85 | 108.15 | 33.55
1065 | NAGALAND | RAILWAYS | CONSTRUCTION OF 2-LANE WITH PAVED SHOULDER OF KOHIMA- BYPASS ROAD FROM DSIGN KM32.0 TO KM43.454 [DES | NHIDCL | N24001258 | 8-2020 | 4/2022 | Apr-2023 | 8/2025 | 202.36 | N.A. | 202.36 | 75.39 | 32.67
1066 | NAGALAND | RAILWAYS | 2 LANING OF KOHIMA - JESSAMI SECTION (PACKAGE II) | NHIDCL | N24001282 | 3-2020 | 6/2022 | N.A. | 1/2026 | 355.79 | N.A. | 355.79 | 119.20 | 65.06
1067 | NAGALAND | RAILWAYS | 2 LANING OF KOHIMA - JESSAMI SECTION (PACKAGE V) | NHIDCL | N24001287 | 4-2020 | 12/2021 | Nov-2025 | 11/2025 | 330.80 | N.A. | 330.80 | 171.89 | 92.44
1068 | NAGALAND | RAILWAYS | CONSTRUCTION OF 2-LANE WITH PAVED SHOULDER OF KOHIMA- BYPASS ROAD FROM DESIGN KM 0.00 TO KM 10.500 [D | NHIDCL | N24001288 | 8-2020 | 4/2022 | Nov-2026 | 11/2026 | 232.29 | 350.88 | 232.29 | 79.69 | 17.31
1069 | NAGALAND | RAILWAYS | PEREN-DIMAPUR SECTION PKG-2 | NHIDCL | N24001406 | 7-2021 | 3/2023 | Sep-2025 | 9/2025 | 258.52 | N.A. | 258.52 | 89.46 | 81.40
1070 | ODISHA | RAILWAYS | BASUNDHARA (WEST) OC EXTN(7.00 MTY) | MCL | N06000112 | 5-2014 | 3/2019 | N.A. | 3/2028 | 479.15 | N.A. | 479.15 | 271.99 | 63.04
1071 | ODISHA | RAILWAYS | SIARMAL OCP (40.00MTY) | MCL | N06000113 | 2-2021 | 3/2029 | N.A. | 3/2029 | 5,194.96 | N.A. | 5,194.96 | 3,454.71 | 53.63
1072 | ODISHA | RAILWAYS | INTEGRATED LAKHANPUR-BELPAHAR- LILARI OCP | MCL | N06000167 | 5-2018 | 3/2027 | N.A. | 3/2027 | 2,434.75 | N.A. | 2,434.75 | 1,765.96 | 61.49
1073 | ODISHA | RAILWAYS | REORGANISATION OF BHARATPUR OCP EXPANSION | MCL | N06000171 | 11-2018 | 3/2029 | N.A. | 3/2029 | 2,838.87 | N.A. | 2,838.87 | 1,837.17 | 47.35
1074 | ODISHA | RAILWAYS | NAINI COAL MINE | SCCL | N06000203 | 3-2020 | 3/2024 | N.A. | 3/2027 | 494.30 | N.A. | 494.30 | 491.33 | 80.00
1075 | ODISHA | RAILWAYS | GOPALJI-KANIHA OCP | MCL | N06000229 | 4-2022 | 3/2028 | N.A. | 3/2028 | 6,107.87 | N.A. | 6,107.87 | 1,703.67 | 17.73
1076 | ODISHA | RAILWAYS | BALARAM EXPANSION OCP | MCL | N06000230 | 8-2020 | 3/2029 | N.A. | 3/2029 | 3,504.21 | N.A. | 3,504.21 | 1,026.96 | 52.44
1077 | ODISHA | RAILWAYS | SUBHADRA OCP | MCL | N06000249 | 5-2021 | 3/2029 | Mar-2029 | 3/2029 | 1,693.81 | N.A. | 1,693.81 | 1,277.82 | 40.05
1078 | ODISHA | RAILWAYS | NLC TALABIRA THERMAL POWER PROJECT (PHASE-1: 3 X 800 MW) | NLC | N06000270 | 1-2024 | 5/2029 | Mar-2030 | 3/2030 | 27,213.00 | N.A. | 27,213.00 | 1,928.60 | 1.55
1079 | ODISHA | RAILWAYS | RPR OF HINGULA EXPANSION OCP | MCL | N06000285 | 11-2022 | 3/2029 | N.A. | 3/2029 | 1,561.85 | N.A. | 1,561.85 | 49.85 | 23.57
1080 | ODISHA | RAILWAYS | BHUBANESWARI EXPANSION OCP | MCL | N06000286 | 3-2024 | 3/2031 | N.A. | 3/2031 | 5,366.28 | N.A. | 5,366.28 | 9.08 | 9.59
1081 | ODISHA | RAILWAYS | BALABHADRA OCP | MCL | N06000288 | 4-2023 | 3/2030 | N.A. | 3/2030 | 978.44 | N.A. | 978.44 | 209.50 | 7.68
1082 | ODISHA | RAILWAYS | INTEGRATED KULDA GARJANBAHAL OCP | MCL | N06000289 | 4-2023 | 3/2030 | N.A. | 3/2030 | 3,563.50 | N.A. | 3,563.50 | 505.09 | 4.00
1083 | ODISHA | DEPARTMENT OF HIGHER EDUCATION | INDIAN INSTITUTE OF SCIENCE EDUCATION AND RESEARCH BERHAMPUR | CPWD EDUCATION | N28000126 | 1-2019 | 3/2022 | N.A. | 10/2025 | 790.79 | N.A. | 790.79 | 708.50 | 97.00
1084 | ODISHA | MINES | 5TH STREAM ALUMINA REFINERY EXPANSION PROJECT | NALCO | N10000010 | 12-2014 | 4/2021 | Jun-2026 | 6/2026 | 4,103.00 | 5,677.40 | 5,677.40 | 3,831.39 | 74.52
1085 | ODISHA | MINES | UTKAL D AND E COAL BLOCK | NALCO | N10000011 | 5-2016 | 1/2020 | Nov-2023 | 3/2024 | 534.00 | N.A. | 1,021.97 | 829.39 | 88.50
1086 | ODISHA | MINES | CONVERSION OF FLAT BOTTOM SETTLERS AND WASHERS WITH A SINGLE TRAIN OF HRDS AND DCWS IN STREAMS 1 AND | NALCO | N10000012 | 12-2015 | 11/2020 | Sep-2025 | 8/2027 | 355.00 | 581.00 | 581.00 | 163.55 | 12.60
1087 | ODISHA | MINES | SOURCING OF BAUXITE ARRANGEMENT FOR 5TH STREAM ALUMINA REFINERY FROM SOUTH BLOCK MINING LEASE OF PAN | NALCO | N10000013 | 11-2017 | 4/2021 | May-2026 | 5/2026 | 483.00 | 483.00 | 495.00 | 387.75 | 89.43
1088 | ODISHA | MINES | POTTANGI BAUXITE MINES | NALCO | N10000016 | 5-2018 | 12/2024 | N.A. | 5/2025 | 1,437.00 | N.A. | 1,381.00 | 650.05 | 51.10
1089 | ODISHA | MINES | CONSTRUCTION OF RED MUD POND - II AT NALCO DAMANJODI ODISHA | NALCO | N10000017 | 9-2019 | 3/2023 | May-2024 | 5/2024 | 225.79 | N.A. | 270.66 | 5.00 | 100.00
1090 | ODISHA | PETROLEUM | INTEGRATED PARA XYLENE (PX) AND PURIFIED TEREPHTHALIC ACID (PTA) PROJECT AT PARADIP REFINERY | IOCL | N16000396 | 7-2020 | 1/2024 | Apr-2025 | 4/2026 | 13,805.00 | N.A. | 13,805.00 | 7,704.73 | 90.00
1091 | ODISHA | POWER | EASTERN REGION EXPANSION SCHEME XXIX | PGCIL | N18000351 | 3-2023 | 11/2025 | N.A. | 7/2025 | 524.04 | N.A. | 524.04 | 482.12 | 99.80
1092 | ODISHA | POWER | TALCHER THERMAL POWER PROJECT STAGE III(2X660 MW) | NTPC | N18000364 | 8-2022 | 5/2027 | N.A. | 12/2027 | 11,844.00 | N.A. | 12,539.00 | 3,703.12 | 21.40
1093 | ODISHA | POWER | KHURDA ROAD-BOLANGIR(NL)ECOR | ECOR | 220100284 | 4-1994 | 12/2026 | Dec-2026 | 12/2026 | 3,550.00 | 3,791.66 | 5,089.37 | 4,910.22 | 86.00
1094 | ODISHA | POWER | TALCHER-BIMALAGARH(NL)(ECOR) | ECOR | 220100328 | 4-2005 | 3/2025 | N.A. | 3/2026 | 1,928.10 | N.A. | 1,928.07 | 1,757.75 | 40.00
1095 | ODISHA | POWER | BHADRAK - NERGUNDI 3RD LINE | ECOR | N22000316 | 3-2013 | 11/2024 | Jan-2026 | 6/2026 | 1,284.39 | 1,284.39 | 1,284.39 | 1,297.80 | 80.00
1096 | ODISHA | POWER | JAGADALPUR-KORAPUT DOUBLING | ECOR | N22000376 | 4-2015 | 3/2024 | N.A. | 3/2022 | 1,547.38 | N.A. | 1,547.38 | 1,304.60 | 93.70
1097 | ODISHA | POWER | KORAPUT - SINGAPUR ROAD DOUBLING | ECOR | N22000379 | 4-2015 | 12/2027 | Mar-2026 | 3/2026 | 2,362.00 | 2,361.74 | 2,361.74 | 1,816.25 | 80.00
1098 | ODISHA | POWER | JARAPADA - BUDHAPANK WITH FLY OVER AT TALCHER ROAD 3RD AND 4TH LINE | ECOR | N22000380 | 4-2015 | 3/2027 | N.A. | 8/2026 | 820.61 | N.A. | 810.02 | 580.59 | -
1099 | ODISHA | POWER | BUDHAPANK - SALEGAON VIA RAJATGARH 3RD AND 4TH LINE. | ECOR | N22000381 | 4-2015 | 3/2026 | Nov-2025 | 11/2025 | 1,172.92 | N.A. | 2,022.75 | 1,971.33 | 80.00
1100 | ODISHA | POWER | VIZIANAGARAM -SAMABALPUR 3RD LINE | RVNL | N22000409 | 1-1991 | 12/2026 | N.A. | 12/2026 | 4,803.16 | N.A. | 4,803.16 | 4,691.52 | -
1101 | ODISHA | POWER | JEYPORE MALKANGIRI NEW LINE | ECOR | N22000516 | 2-2018 | 7/2033 | N.A. | 7/2033 | 2,344.00 | N.A. | 642.69 | 220.78 | 90.10
1102 | ODISHA | POWER | JEYPORE NABARANGPUR NEWLINE | ECOR | N22000517 | 7-2017 | 7/2028 | Dec-2029 | 12/2029 | 748.00 | N.A. | 747.91 | 0.00 | -
1103 | ODISHA | POWER | TALCHER - ANGUL NEW LINE WITH Y CONNECTION AT TALCHER | ECOR | N22000518 | 7-2018 | 12/2026 | N.A. | 12/2026 | 278.96 | 495.00 | 494.62 | 29.50 | -
1104 | ODISHA | POWER | KODINGAMALI BAUXITE MINES TO SINGARAM RAILWAY STATION | ECOR | N22000519 | 8-2022 | 8/2027 | N.A. | 8/2027 | 190.90 | N.A. | 190.90 | 10.00 | -
1105 | ODISHA | POWER | GANDHAMARDAN IRON ORE MINES TO GOALDIH STATION | ECOR | N22000520 | 9-2022 | 9/2027 | N.A. | 3/2028 | 189.93 | N.A. | 189.93 | 14.04 | -
1106 | ODISHA | POWER | BRUNDAMAL-JHARSUGUDA- FLYOVER CONNECTION FOR JOINING DN LINE | ECOR | N22000521 | 12-2009 | 12/2026 | N.A. | 12/2026 | 296.51 | N.A. | 297.00 | 162.44 | 10.00
1107 | ODISHA | POWER | BAGHUAPAL FLY OVER (20 KM) | ECOR | N22000522 | 8-2019 | 8/2027 | Aug-2027 | 8/2027 | 183.00 | 257.97 | 257.97 | 0.83 | -
1108 | ODISHA | POWER | ROURKELA-BONDAMUNDA A-CABIN 5TH LINE (10 KM) (UMBRELLA WORK PB#57/2019-20/NR) | SER | N22000571 | 9-2022 | 9/2026 | N.A. | 2/2026 | 209.75 | N.A. | 244.99 | 82.27 | 30.00
1109 | ODISHA | POWER | BALANCE WORK OF PANIKOILI RIMULI SECTION OF NEW NH-20 FROM KM 0.00 TO KM. 163.000 | NHAI | N24001647 | 8-2020 | 3/2022 | N.A. | 7/2025 | 200.00 | 154.73 | 154.73 | 150.38 | 100.00
1110 | ODISHA | POWER | 6L GREENFIELD KANDILI - ALURU SECTION OF NH-130-CD ROAD FROM KM 342+500 TO KM 365+033 (PACKAGE- OD-8 | NHAI | N24001665 | 12-2021 | 10/2024 | N.A. | 12/2025 | 1,592.00 | 1,592.00 | 1,592.00 | 1,127.76 | 78.13
1111 | ODISHA | POWER | 6L GREENFIELD BARAJA - KANDILI SECTION OF NH- 130-CD ROAD FROM KM 338+500 TO KM 342+500 (PACKAGE- OD | NHAI | N24001666 | 12-2021 | 9/2024 | N.A. | 8/2025 | 714.00 | 714.00 | 714.00 | 589.97 | 95.45
1112 | ODISHA | POWER | 6L GREENFIELD KALIAGURA ? BAUNSAGUAR SECTION OF NH-130-CD ROAD FROM KM 249+000 TO KM 293+000 (PACKAG | NHAI | N24001667 | 9-2021 | 5/2024 | N.A. | 12/2025 | 1,734.00 | 1,734.00 | 1,734.00 | 1,238.62 | 86.47
1113 | ODISHA | POWER | 6L OF BADAKUMARI - KARKI SECTION FROM KM 179.000 TO KM 226.500 OF NH-130-CD (PACKAGE ? OD-3) | NHAI | N24001668 | 3-2021 | 4/2024 | N.A. | 11/2025 | 1,249.00 | N.A. | 1,249.00 | 522.17 | 87.16
1114 | ODISHA | POWER | 6L OF DHANARA - HATIBENA SECTION FROM KM 124.611 TO KM 146.50 OF NH- 130-CD (PACKAGE ? OD-1) | NHAI | N24001669 | 2-2021 | 3/2024 | N.A. | 7/2025 | 586.00 | N.A. | 586.00 | 241.77 | 92.98
1115 | ODISHA | POWER | 6L OF KARKI ? KALIAGURA SECTION FROM KM 226.500 TO KM 249.000 OF NH-130-CD (PACKAGE ? OD-4) | NHAI | N24001670 | 2-2021 | 3/2024 | N.A. | 7/2025 | 593.00 | N.A. | 593.00 | 282.15 | 94.55
1116 | ODISHA | POWER | 6L OF HATIBENA - BADAKUMARI SECTION FROM KM 146.50 TO KM 179.00 OF NH-130-CD (PACKAGE ? OD- 2) | NHAI | N24001671 | 2-2021 | 3/2024 | N.A. | 7/2025 | 925.00 | N.A. | 925.00 | 460.47 | 97.00
1117 | ODISHA | POWER | 6L GREENFIELD BAUNSAGUAR - BARAJA SECTION OF NH-130-CD ROAD FROM KM 293+000 TO KM 338+500 (PACKAGE ? | NHAI | N24001678 | 8-2021 | 6/2024 | N.A. | 12/2025 | 1,460.00 | 1,460.00 | 1,460.00 | 986.76 | 91.52
1118 | ODISHA | POWER | CONSTRUCTION OF ROAD FROM KM 0/0 TO 72/0 OF NH-26 SUCH AS 4 LANE FROM KM 0/0 TO 21/0 (BARGARH TO BAR | MoRTH | N24001857 | 6-2020 | 12/2023 | Aug-2025 | 8/2025 | 414.24 | N.A. | 414.24 | 307.52 | 98.00
1119 | ODISHA | POWER | WIDENING AND STRENGTHENING TO 2L+PS INCLUDING LA OF KANDARPUR- BALIKUDA FROM KM 277/500 TO 318/970 OF | MoRTH | N24001858 | 3-2022 | 6/2025 | N.A. | 12/2025 | 499.79 | N.A. | 499.79 | 285.58 | 48.20
1120 | ODISHA | POWER | CONSTRUCTION OF BYPASS ON NH-59 FROM KM 336/350 TO 349/910 (13.56 KM) NEAR BERHAMPUR TOWN INCLUDING | MoRTH | N24001859 | 3-2021 | 3/2024 | N.A. | 8/2025 | 196.94 | N.A. | 196.94 | 71.55 | 93.00
1121 | ODISHA | POWER | CONSTRUCTION OF BYPASS TO NAYAGARH TOWN FROM KM 235.469 TO 252.482 OF NH-57 INCLUDING LAND ACQUISITI | MoRTH | N24001860 | 1-2022 | 4/2025 | N.A. | 8/2025 | 300.33 | N.A. | 300.33 | 203.81 | 70.00
1122 | ODISHA | POWER | CONSTRUCTION OF BYPASS TO KHORDHA TOWN FROM KM 294/000 TO 300/300 ON NH-57 INCLUDING LA IN THE STATE | MoRTH | N24001861 | 2-2022 | 11/2024 | Aug-2025 | 8/2025 | 157.49 | N.A. | 157.49 | 72.57 | 54.00
1123 | ODISHA | POWER | CONSTRUCTION OF BYPASS ROAD TO BALANGIR TOWN FROM KM 72/400 (DESING KM 0/0) TO KM 79/800 (DESIGN KM | MoRTH | N24001862 | 2-2022 | 10/2025 | Nov-2025 | 11/2025 | 238.78 | N.A. | 238.78 | 50.64 | 40.00
1124 | ODISHA | POWER | CONSTRUCTION OF 5 HL BRIDGES AT KM 379/000 (PANGAM), KM 439/400 (POTTERU), KM 444/237 (KONGURUKONDA) | MoRTH | N24001863 | 3-2021 | 6/2024 | Oct-2025 | 5/2025 | 154.05 | N.A. | 154.05 | 47.47 | 30.00
1125 | ODISHA | POWER | CONSTRUCTION OF FOUR LANE ROB AND ITS APPROACHES IN LIEU OF EXISTING LEVEL CROSSING NO. RV-71 AT KM | MoRTH | N24001864 | 11-2021 | 6/2025 | N.A. | 10/2025 | 154.49 | N.A. | 154.49 | 60.48 | 45.00
1126 | ODISHA | POWER | CONSTRUCTION OF 4 LANE ROB WITH APPROACHES IN LIEU OF LC NO. RV- 172 AT KM 176.00 OF NH-201 (PRESENT | MoRTH | N24001865 | 12-2021 | 5/2025 | Oct-2025 | 10/2025 | 324.09 | N.A. | 324.09 | 111.45 | 35.00
1127 | ODISHA | POWER | REHABILITATION AND UP GRADATION FROM 4 TO 8 LANING OF CHANDIKHOLE PARADIP SECTION OF NH 53 FROM KM. | NHAI | N24002078 | 12-2023 | 12/2025 | N.A. | 3/2026 | 711.00 | N.A. | 711.00 | 217.96 | 60.80
1128 | ODISHA | POWER | REHABILITATION AND UP GRADATION FROM 4 TO 8 LANING OF CHANDIKHOLE PARADIP SECTION OF NH 53 FROM KM | NHAI | N24002079 | 12-2023 | 12/2025 | N.A. | 3/2026 | 742.25 | N.A. | 742.25 | 223.47 | 55.10
1129 | ODISHA | POWER | REHABILITATION AND UP GRADATION FROM 4 TO 8 LANING OF CHANDIKHOLE PARADIP SECTION OF NH 53 FROM KM | NHAI | N24002080 | 12-2023 | 12/2025 | N.A. | 3/2026 | 762.75 | N.A. | 762.75 | 266.33 | 60.70
1130 | ODISHA | POWER | 3L MAJOR BRIDGE OVER RIVER BRAHMANI AT KM. 401.250 (DUBURI CHANDIKHOLE SECTION) OF NH 200 (NEW NH 5 | NHAI | N24002081 | 8-2022 | 1/2025 | N.A. | 12/2026 | 153.61 | N.A. | 153.61 | 22.77 | 34.49
1131 | ODISHA | POWER | WIDENING AND STRENGTHENLNG TO 2L+PS FROM KM 0.000 TO 40.000 (DHAUGAON- PODAMARI SECTION) OF NH 326 I | MoRTH | N24002135 | 3-2022 | 2/2026 | N.A. | 2/2026 | 186.52 | N.A. | 186.52 | 48.30 | 35.00
1132 | ODISHA | POWER | WIDENING AND STRENGTHENING TO 4L+PS/2L+PS FROM KM 0.000 TO 35.800 (KUAKHIA - MANGALPUR SECTION) OF N | MoRTH | N24002136 | 3-2022 | 2/2026 | N.A. | 2/2026 | 636.10 | N.A. | 636.10 | 264.98 | 36.53
1133 | ODISHA | POWER | REHABILITATION AND UP GRADATION FROM 4 TO 8 LANING OF CHANDIKHOLE ? PARADIP SECTION OF NH-53 (OLD NH | NHAI | N24002219 | 3-2024 | 10/2026 | N.A. | 10/2026 | 882.45 | N.A. | 882.45 | 82.62 | 14.10
1134 | ODISHA | POWER | DEVELOPMENT OF FOUR LANNING OF ANGUL-SAMBALPUR SECTION OF NATIONAL HIGHWAY NH-42 (NEW NH- 55 IN THE S | NHAI | N24000619 | 9-2016 | 8/2019 | N.A. | 7/2025 | 2,510.04 | N.A. | 2,510.04 | 1,181.34 | 99.98
1135 | ODISHA | POWER | REHABILITATION AND UPGRADATION OF CUTTACK ANGUL SECTION OF NH- 42 (NEW NH-55) TO 4 LANE (KM. 0+400 TO | NHAI | N24000715 | 12-2017 | 7/2020 | N.A. | 7/2025 | 686.65 | 565.00 | 686.65 | 574.26 | 98.00
1136 | ODISHA | POWER | REHABILITATION AND UP-GRADATION OF EXISTING 2-LANE TO 4 LANE OF DUBURI (KM 388.376) TO CHANDIKHOLE ( | NHAI | N24000733 | 1-2018 | 8/2022 | N.A. | 12/2025 | 633.68 | 492.83 | 633.68 | 560.38 | 86.00
1137 | ODISHA | POWER | REHABILITATION AND UP-GRADATION OF EXISTING 2-LANE TO FOUR LANE FROM TALCHAR TO END OF KAMAKHYANAG | NHAI | N24000734 | 1-2018 | 8/2021 | N.A. | 7/2025 | 614.48 | 503.30 | 757.12 | 664.48 | 99.00
1138 | ODISHA | POWER | REHABILITATION AND UPGRADATION OF CUTTACK-ANGUL SECTION TO 4 LANE (KM 60.20) TO (KM 112.0) PKG II ON | NHAI | N24000736 | 1-2018 | 9/2020 | N.A. | 7/2025 | 686.65 | 504.09 | 1,015.16 | 488.98 | 98.35
1139 | ODISHA | POWER | REHABILITATION AND UPGRADATION OF SIX LANING OF BHADRAK BALESHWAR SECTION (KM 136.50) TO (KM 199.141 | NHAI | N24000738 | 1-2018 | 9/2021 | N.A. | 12/2025 | 999.00 | 1,152.70 | 1,152.70 | 540.10 | 82.01
1140 | ODISHA | POWER | REHABILITATION AND UP-GRADATION TO 4-LANING OF RAJAMUNDA- BARKOTE SECTION OF NH-23 (NEW NH NO. 143) ( | NHAI | N24000739 | 1-2018 | 6/2021 | Jul-2025 | 7/2025 | 503.88 | 609.03 | 609.03 | 536.89 | 98.50
1141 | ODISHA | POWER | WIDENING TO 2LPS FROM 0/0 TO 119/0 OF NH-157 IN THE STATE OF ODISHA. | MoRTH | N24000912 | 8-2016 | 2/2017 | N.A. | 12/2025 | 287.70 | N.A. | 293.66 | 275.42 | 98.66
1142 | ODISHA | POWER | WIDENING TO 2LPS FROM 239/9 TO 294/3 OF NH-57 (NAYAGARH TO KHURDA) IN THE STATE OF ODISHA | MoRTH | N24000914 | 12-2016 | 8/2018 | N.A. | 9/2025 | 223.50 | N.A. | 223.50 | 220.50 | 100.00
1143 | ODISHA | POWER | WIDENING TO 2LPS FROM 269/30 TO 328/20 OF NH-49 IN THE STATE OF ODISHA | MoRTH | N24000917 | 3-2018 | 8/2018 | N.A. | 4/2025 | 199.16 | N.A. | 199.16 | 158.73 | 100.00
1144 | ODISHA | STEEL | REBUILDING OF COKE OVEN BATTERY- 2 ALONGWITH AUGMENTATION OF COKE HANDLING AND GAS HANDLING FACILITY | SAIL | N12000122 | 11-2020 | 5/2023 | Mar-2025 | 3/2025 | 377.18 | N.A. | 377.18 | 434.90
1145 | ODISHA | STEEL | INSTALLATION OF 4TH SLAB CASTER ALONG WITH ITS AUXILIARIES AND A NEW LADLE FURNACE IN SMS-II AT RSP | SAIL | N12000125 | 1-2022 | 5/2025 | Aug-2025 | 8/2025 | 970.18 | N.A. | 970.18 | 720.07 | 94.31
1146 | PUNJAB | DEPARTMENT OF HIGHER EDUCATION | CONSTRUCTION OF PERMANENT CAMPUS OF INDIAN INSTITUTE OF MANAGEMENT (IIM) AMRITSAR, PUNJAB. | CPWD EDUCATION | N28000142 | 10-2019 | 5/2022 | N.A. | 8/2025 | 348.24 | N.A. | 348.24 | 245.37 | 91.20
1147 | PUNJAB | PETROLEUM | SECOND GENERATION ETHANOL BIOREFINERY PROJECT, BATHINDA, PUNJAB | HPCL | N16000402 | 5-2020 | 2/2023 | Sep-2024 | 3/2026 | 1,421.46 | N.A. | 1,421.46 | 1,163.10 | 95.63
1148 | PUNJAB | PETROLEUM | BHATINDA SANGRUR PIPELINE | HPCL | N16000440 | 11-2021 | 5/2024 | Feb-2025 | 8/2025 | 367.00 | 397.00 | 397.00 | 334.26 | 91.90
1149 | PUNJAB | PETROLEUM | CGD PROJECT AT PATHANKOT DISTRICT | IOCL | N16000488 | 3-2022 | 3/2030 | Sep-2033 | 9/2033 | 151.00 | N.A. | 151.00 | 8.73 | 2.00
1150 | PUNJAB | RAILWAYS | LUDHIANA MULLANPUR DOUBLING | NR | N22000589 | 9-2020 | 3/2025 | N.A. | 7/2025 | 235.00 | N.A. | 235.00 | 7.99 | 98.00
1151 | PUNJAB | RAILWAYS | FEROZPUR - PATTI (25.72 KM) | NR | N22000614 | 4-2017 | 3/2027 | N.A. | 3/2027 | 299.74 | N.A. | 781.00 | 0.00 | -
1152 | PUNJAB | RAILWAYS | DELHI-AMRITSAR-KATRA EXPRESSWAY FROM JUNCTION WITH PATIALA-BATHINDA ROAD (NH-7) NEAR BHAWANIGARH TO | NHAI | N24001415 | 12-2020 | 4/2024 | Jul-2024 | 7/2024 | 881.00 | N.A. | 881.00 | 960.36 | 92.34
1153 | PUNJAB | RAILWAYS | DELHI-AMRITSAR-KATRA EXPRESSWAY FROM JUNCTION WITH LUDHIANA-MALERKOTLA ROAD (SH-11) NEAR BHOGIWAL VI | NHAI | N24001416 | 12-2020 | 1/2024 | Mar-2025 | 3/2025 | 989.66 | N.A. | 989.66 | 338.21 | 31.08
1154 | PUNJAB | RAILWAYS | DELHI-AMRITSAR-KATRA EXPRESSWAY FROM JUNCTION WITH LUDHIANA-MOGA ROAD (NH-5) NEAR MULLANPUR DAKHA TO | NHAI | N24001417 | 12-2020 | 4/2024 | Sep-2025 | 9/2025 | 1,234.40 | N.A. | 1,234.40 | 853.68 | 61.88
1155 | PUNJAB | RAILWAYS | DELHI-AMRITSAR-KATRA EXPRESSWAY FROM CH.KM 303+900 TO KM 319+400 OF MAIN EXPRESSWAY) AND AMRITSAR CO | NHAI | N24001418 | 12-2020 | 4/2024 | Sep-2025 | 9/2025 | 1,094.46 | N.A. | 1,094.46 | 802.93 | 62.99
1156 | PUNJAB | RAILWAYS | DELHI-AMRITSAR-KATRA EXPRESSWAY (PHASE-I PKG-XI) FROM JUNCTION WITH JALANDHAR - KAPURTHALA ROAD (NH- | NHAI | N24001419 | 2-2021 | 4/2024 | Nov-2024 | 11/2024 | 1,269.96 | N.A. | 1,269.96 | 585.86 | 43.45
1157 | PUNJAB | RAILWAYS | DELHI-AMRITSAR-KATRA EXPRESSWAY (PHASE-I PKG-XII) FROM JUNCTION WITH AMRITSAR-MEHTA- SRIHARGOBINDPUR- | NHAI | N24001420 | 2-2021 | 4/2024 | Dec-2025 | 12/2025 | 853.66 | N.A. | 853.66 | 177.27 | 20.65
1158 | PUNJAB | RAILWAYS | 4/6L GREENFIELD LUDHIANA RUPNAGAR HIGHWAY FROM JUNCTION WITH NE 05 VILLAGR NEAR TO MANEWAL (LUDHIANA | NHAI | N24001630 | 7-2021 | 2/2025 | N.A. | 2/2025 | 1,501.02 | N.A. | 1,501.02 | 282.00 | 75.00
1159 | PUNJAB | RAILWAYS | 6L OF IT CITY CHOWK TO KURALI CHANDIGARH ROAD | NHAI | N24001631 | 3-2021 | 10/2024 | N.A. | 10/2024 | 1,525.31 | N.A. | 1,525.31 | 290.00 | 95.00
1160 | PUNJAB | RAILWAYS | CONSTRUCTION OF FOUR LANE GREENFIELD PROJECT OF DELHI- AMRITSAR-KATRA EXPRESSWAY (PHASE-I PKG-V) FROM | NHAI | N24001632 | 1-2021 | 5/2024 | Jun-2025 | 8/2025 | 1,741.86 | 2,281.02 | 2,281.02 | 1,294.40 | 96.50
1161 | PUNJAB | RAILWAYS | CONSTRUCTION OF FOUR/SIX LANE GREENFIELD LUDHIANA ? RUPNAGAR NATIONAL HIGHWAY NO. NH-205K UNDER BHAR | NHAI | N24001636 | 5-2021 | 12/2024 | Oct-2026 | 10/2026 | 1,368.91 | 1,368.91 | 1,368.91 | 163.58 | 15.31
1162 | PUNJAB | RAILWAYS | DEVELOPMENT OF 6 LANE JALANDHAR BYPASS FROM KAHLWAN NATIONAL HIGHWAY 03 DESIGN KM 0.00 ENDING AT K | NHAI | N24001637 | 3-2021 | 1/2025 | N.A. | 1/2025 | 1,754.84 | N.A. | 1,754.84 | 1,145.02 | 40.01
1163 | PUNJAB | RAILWAYS | 4L GREENFIELD A. MALOUT BYPASS FROM CH. KM 44.500 TO CH. KM 35.500 ON NH-07 AND CH. KM 0.000 TO KM 6 | NHAI | N24001638 | 11-2021 | 7/2024 | Aug-2025 | 8/2025 | 646.42 | 646.42 | 646.42 | 481.67 | 96.00
1164 | PUNJAB | RAILWAYS | FOUR LANING OF MOGA TO BAJAKHANA LAMBWALI SECTION OF 105B GREENFIELD ALIGNMENT FROM DESIGN CHAINAGE | NHAI | N24001639 | 5-2020 | 12/2024 | Aug-2025 | 8/2025 | 864.23 | 864.23 | 864.23 | 434.88 | 65.00
1165 | PUNJAB | RAILWAYS | 6L AMRITSAR BATHINDA GREENFIELD SECTION FROM VILLAGE TIBA ON NE 5A TO JN. WITH MOGA JALANDHAR ROAD N | NHAI | N24001640 | 3-2021 | 11/2024 | N.A. | 11/2024 | 1,229.38 | N.A. | 1,229.38 | 762.83 | 48.58
1166 | PUNJAB | RAILWAYS | DELHI AMRITSAR KATRA EXPRESSWAY PHASE I SPUR III FROM JUNCTION WITH AMRITSAR JALANDHAR ROAD NH3 NEAR | NHAI | N24001641 | 3-2021 | 10/2024 | Dec-2025 | 12/2025 | 1,641.75 | N.A. | 1,641.75 | 188.55 | 26.01
1167 | PUNJAB | RAILWAYS | FOUR LANING OF AMRITSAR BYPASS FROM NEW TARN TARAN ROAD TO AJNALA ROAD FROM DESIGN KM. 0.750 TO DESI | NHAI | N24001642 | 2-2021 | 8/2024 | Dec-2025 | 12/2025 | 1,474.77 | N.A. | 1,474.77 | 475.88 | 75.25
1168 | PUNJAB | RAILWAYS | 4L OF AMRITSAR GHOMAN TANDA UNA SECTION FROM KM 8.270 TO KM 54.000 OF NH 503A PACKAGE I | NHAI | N24001643 | 12-2020 | 6/2024 | Jun-2025 | 6/2025 | 857.91 | N.A. | 857.91 | 164.88 | 41.02
1169 | PUNJAB | RAILWAYS | AMRITSAR AIRPORT JUNCTION RAMDAS FROM KM. 100.835 TO KM. 139.813 PKG IV | NHAI | N24001644 | 12-2020 | 9/2023 | Sep-2025 | 9/2025 | 524.88 | 416.58 | 416.58 | 157.14 | 73.00
1170 | PUNJAB | RAILWAYS | UP-GRADATION TO TWO LANE WITH PAVED SHOULDER CONFIGURATION OF NH-354 SECTION ARIFKES- FEROZEPUR-MUKTS | MoRTH | N24001960 | 3-2021 | 10/2023 | N.A. | 10/2025 | 263.19 | N.A. | 220.00 | 119.50 | 61.00
1171 | PUNJAB | RAILWAYS | WORK OF WIDENING/UPGRADATION OF 2-LANE WITH PAVED SHOULDER OF SRI MUKTSAR SAHIB TO MALOUT ROAD FROM | MoRTH | N24001961 | 3-2022 | 10/2023 | N.A. | 7/2025 | 152.58 | N.A. | 152.58 | 97.00 | 85.00
1172 | PUNJAB | RAILWAYS | 6L OF JODHPUR ROMANA (BATHINDA) - MANDI DABWALI (PUNJAB HARYANA BORDER) SECTION OF NH-54 FROM KM. 0. | NHAI | N24002075 | 12-2020 | 8/2025 | Aug-2025 | 8/2025 | 757.13 | 757.00 | 757.00 | 246.51 | 98.75
1173 | PUNJAB | RAILWAYS | 6L AMRITSAR-BATHINDA GREENFIELD SECTION FROM JN. WITH BHAGTA BHAI KA-BHADAUR ROAD NEAR DYALPURA BHAI | NHAI | N24002076 | 3-2021 | 10/2025 | Jun-2026 | 6/2026 | 2,029.17 | 2,029.00 | 2,029.00 | 84.23 | 47.00
1174 | PUNJAB | RAILWAYS | 6L ACCESS CONTROLLED LUDHIANA- BATHINDA GREENFIELD HIGHWAY FROM JN. WITH AMRITSAR-BATHANDA GREENFIELD | NHAI | N24002091 | 6-2021 | 9/2025 | Mar-2026 | 3/2026 | 906.51 | 906.51 | 906.51 | 170.39 | 54.00
1175 | PUNJAB | RAILWAYS | 6-LANE AMRITSAR-BATHINDA GREENFIELD SECTION OF NH-754A FROM JUNCTION WITH MOGA JALANDHAR ROAD (NH-70 | NHAI | N24002092 | 3-2021 | 10/2025 | N.A. | 10/2025 | 1,801.37 | N.A. | 1,801.37 | 1,075.64 | 51.20
1176 | PUNJAB | RAILWAYS | 6L OF AMBALA-CHANDIGARH GREENFIELD SECTION FROM KM. 0.000 TO KM. 25.000 WITH 4L SPUR TO LALRU FROM K | NHAI | N24002098 | 3-2022 | 10/2025 | N.A. | 10/2025 | 1,641.66 | N.A. | 1,641.66 | 100.00 | 55.00
1177 | PUNJAB | RAILWAYS | 4L OF EXISTING BEAS ? BABA BAKALA - DERA BABA NANAK SECTION FROM START OF BATALA BYPASS TILL INTERSE | NHAI | N24002100 | 10-2021 | 6/2025 | N.A. | 12/2025 | 1,003.38 | N.A. | 1,003.38 | 281.62 | 72.58
1178 | PUNJAB | RAILWAYS | 4L OF BEAS-MEHTA-BATALA-DERA BABA NANAK FROM INTERSECTION WITH JALANDHAR-AMRITSAR HIGHWAY (NH-3) NEA | NHAI | N24002101 | 8-2021 | 6/2025 | Dec-2025 | 12/2025 | 809.51 | N.A. | 809.51 | 220.73 | 53.54
1179 | PUNJAB | RAILWAYS | DELHI-AMRITSAR-KATRA EXPRESSWAY (PHASE-I SPUR-I) FROM JN. WITH KAPURTHALA - SULTANPUR LODHI ROAD (NH | NHAI | N24002102 | 1-2020 | 4/2026 | N.A. | 4/2027 | 2,165.23 | N.A. | 2,165.23 | 180.85 | 20.50
1180 | PUNJAB | RAILWAYS | WIDENING AND PAVED SHOULDER OF TOHANA (IN HARYANA) PUNJAB/HARYANA BORDER TO MOONAK-JAKHAL-BUDHLADA | MoRTH | N24000907 | 3-2018 | 8/2020 | N.A. | 6/2025 | 293.10 | N.A. | 315.00 | 318.24 | 100.00
1181 | PUNJAB | RAILWAYS | JALANDHAR-HOSHIARPUR SECTION OF NH-70 [NEW NH NO. 3] FROM EXISTING KM 11.400 TO KM 49.200 | MoRTH | N24000909 | 10-2017 | 10/2019 | N.A. | 12/2025 | 1,069.59 | N.A. | 1,069.59 | 739.08 | 44.00
1182 | PUNJAB | RAILWAYS | REHABILITATION AND UP GRADATION TO 2 LANE WITH PAVED SHOULDER OF NH-703A FROM MAKHU (DESIGN CH 0 000 | MoRTH | N24000910 | 3-2018 | 11/2020 | N.A. | 6/2026 | 170.57 | N.A. | 150.00 | 135.00 | 79.00
1183 | RAJASTHAN | CIVIL AVIATION | CONSTRUCTION OF NEW TERMINAL BUILDING AT JODHPUR AIRPORT | AAI | N04000101 | 5-2022 | 11/2024 | Oct-2025 | 10/2025 | 480.00 | N.A. | 480.00 | 254.71 | 77.75
1184 | RAJASTHAN | CIVIL AVIATION | UDAIPUR AIRPORT- CONSTRUCTION OF NEW INTEGRATED PASSENGER TERMINAL BUILDING | AAI | N04000104 | 6-2023 | 3/2026 | N.A. | 3/2026 | 887.00 | N.A. | 887.00 | 312.40 | 44.61
1185 | RAJASTHAN | COAL | NLCIL 300 MW SOLAR POWER PROJECT (PART OF 510 MW CPSU SCHEME) | NLC | N06000269 | 3-2023 | 9/2024 | N.A. | 11/2025 | 1,813.00 | N.A. | 1,813.00 | 746.26 | 66.00
1186 | RAJASTHAN | COAL | NEW MUNDRA-PANIPAT CRUDE OIL PIPELINE | IOCL | N16000435 | 12-2021 | 10/2024 | Dec-2025 | 12/2025 | 9,028.00 | N.A. | 9,028.00 | 6,734.76 | 82.30
1187 | RAJASTHAN | COAL | SETTING UP OF PETROCHEMICAL EVACUATION MARKETING TERMINAL (PEMT) AT BARMER | HPCL | N16000512 | 12-2023 | 12/2026 | N.A. | 12/2026 | 461.05 | N.A. | 461.05 | 98.70 | 47.50
1188 | RAJASTHAN | COAL | RAJASTHAN REFINERY PROJECT (HPCLRRL(JV)) |  | N16000513 | 10-2017 | 10/2022 | Mar-2025 | 12/2025 | 43,129.00 | 72,937.00 | 72,937.00 | 58,305.57 | 87.40
1189 | RAJASTHAN | COAL | CGD PROJECTS AT FAZILKA (EXCEPT AREA ALREADY AUTHORIZED) GANGANAGAR AND HANUMANGARH DISTRICTS | BPCL | N16000520 | 12-2022 | 6/2030 | N.A. | 6/2030 | 3,207.00 | N.A. | 3,207.00 | 324.65 | 21.90
1190 | RAJASTHAN | COAL | BHADLA-II 500MW SOLAR PV PROJECT | NTPC | N18000347 | 6-2022 | 3/2024 | Sep-2025 | 9/2025 | 2,598.92 | N.A. | 2,598.92 | 1,815.27 | 60.00
1191 | RAJASTHAN | COAL | TRANSMISSION SYSTEM SCHEME FOR EVACUATION OF POWER FROM REZ RAJASTHAN (8.1 GW) UNDER PHASE-II PART | PGCIL | N18000356 | 3-2023 | 9/2024 | N.A. | 9/2025 | 1,433.28 | N.A. | 1,433.28 | 1,290.22 | 91.90
1192 | RAJASTHAN | COAL | 300 MW SOLAR POWER PROJECT UNDER CPSU SCHEME | NHPC | N18000368 | 5-2022 | 11/2023 | N.A. | 9/2025 | 1,677.12 | N.A. | 1,677.12 | 1,295.80 | 92.00
1193 | RAJASTHAN | COAL | TS FOR EVACUATION OF POWER FROM REZ IN RAJASTHAN (20GW) UNDER PHASE-III, PART E1 | PGCIL | N18000373 | 8-2023 | 2/2025 | N.A. | 9/2025 | 688.74 | N.A. | 688.74 | 564.77 | 93.00
1194 | RAJASTHAN | COAL | TS FOR EVACUATION POWER FROM REZ IN RAJASTHAN (20GW) UNDER PHASE-III PART H | PGCIL | N18000374 | 10-2023 | 4/2025 | N.A. | 8/2025 | 2,211.00 | N.A. | 2,211.00 | 1,702.27 | 69.40
1195 | RAJASTHAN | COAL | TS FOR EVACUATION POWER FROM REZ IN RAJASTHAN (20GW) UNDER PHASE-III PART C1 | PGCIL | N18000375 | 10-2023 | 4/2025 | Oct-2025 | 10/2025 | 1,796.00 | N.A. | 1,796.00 | 1,149.44 | 77.30
1196 | RAJASTHAN | COAL | TS FOR EVACUATION POWER FROM REZ IN RAJASTHAN (20GW) UNDER PHASE-III PART B1 | PGCIL | N18000376 | 9-2023 | 4/2025 | N.A. | 9/2025 | 2,191.00 | N.A. | 2,191.00 | 1,511.45 | 75.70
1197 | RAJASTHAN | COAL | TS FOR EVACUATION POWER FROM REZ IN RAJASTHAN (20GW) UNDER PHASE-III PART J | PGCIL | N18000378 | 12-2022 | 3/2025 | Apr-2026 | 4/2026 | 331.00 | N.A. | 331.00 | 18.23 | 27.00
1198 | RAJASTHAN | COAL | TS FOR EVACUATION POWER FROM REZ IN RAJASTHAN (20GW) UNDER PHASE-III PART E2 | PGCIL | N18000379 | 11-2023 | 6/2025 | N.A. | 9/2025 | 428.00 | N.A. | 428.00 | 85.60 | 45.00
1199 | RAJASTHAN | COAL | TS FOR EVACUATION OF POWER FROM RAJASTHAN REZ PH-IV (PART-1) [BIKANER COMPLEX] PART A [BIKANER III N | PGCIL | N18000386 | 12-2023 | 12/2025 | N.A. | 12/2025 | 2,998.00 | N.A. | 2,998.00 | 1,439.18 | 47.10
1200 | RAJASTHAN | COAL | TS FOR EVACUATION OF POWER FROM RAJASTHAN REZ PH-IV (PART-1) [BIKANER COMPLEX] PART D [NEEMRANA II B | PGCIL | N18000387 | 12-2023 | 12/2025 | N.A. | 12/2025 | 2,056.00 | N.A. | 2,056.00 | 1,318.23 | 53.30
1201 | RAJASTHAN | COAL | TS FOR EVACUATION OF POWER FROM REZ IN RAJASTHAN (20GW) UNDER PH-III PART D [SIKAR KHETRI TRANSMISSI | PGCIL | N18000389 | 2-2024 | 8/2025 | N.A. | 9/2025 | 2,000.00 | N.A. | 2,000.00 | 1,200.00 | 58.00
1202 | RAJASTHAN | COAL | TS FOR EVACUATION POWER FROM RAJASTHAN REZ PH-IV (PART-2:5.5GW) PART-B (JAISALMER/BARMER COMPLEX) | PGCIL | N18000391 | 8-2024 | 8/2026 | N.A. | 8/2026 | 3,279.00 | N.A. | 3,279.00 | 491.85 | 18.60
1203 | RAJASTHAN | COAL | TS FOR EVACUATION POWER FROM RAJASTHAN REZ PH-IV (PART-2:5.5GW) (JAISALMER/BARMER COMPLEX) PART- C | PGCIL | N18000393 | 8-2024 | 8/2026 | N.A. | 8/2026 | 2,227.00 | N.A. | 2,227.00 | 489.94 | 18.60
1204 | RAJASTHAN | COAL | TS FOR EVACUATION POWER FROM RAJASTHAN REZ PH-IV (PART-2:5.5GW) (JAISALMER/BARMER COMPLEX) PART- E | PGCIL | N18000394 | 8-2024 | 8/2026 | N.A. | 8/2026 | 3,251.00 | N.A. | 3,251.00 | 650.20 | 16.20
1205 | RAJASTHAN | COAL | ADDITIONAL TRANSMISSION SYSTEM FOR EVACUATION OF POWER FROM BHADLA-III PS AS PART OF RAJASTHAN REZ P | PGCIL | N18000396 | 8-2024 | 2/2026 | N.A. | 2/2026 | 369.00 | N.A. | 369.00 | 10.30 | 3.80
1206 | RAJASTHAN | COAL | TRANSMISSION SYSTEM STRENGTHENING FOR INTERCONNECTIONS OF BHADLA-III AND BIKANER III COMPLEX [SPV NA | PGCIL | N18000397 | 8-2024 | 8/2026 | N.A. | 8/2026 | 1,382.00 | N.A. | 1,382.00 | 27.60 | 1.00
1207 | RAJASTHAN | COAL | TRANSMISSION SYSTEM FOR EVACUATION OF POWER FROM RAJASTHAN REZ PH -IV [PART-2 5.5 GW] [JAISALMER/BAR | PGCIL | N18000401 | 11-2024 | 11/2026 | N.A. | 11/2026 | 2,735.00 | N.A. | 2,735.00 | 27.35 | 3.80
1208 | RAJASTHAN | COAL | TRANSMISSION SYSTEM FOR EVACUATION OF POWER FROM RAJASTHAN REZ PH-IV [PART-3 (6GW)] [BIKANER COMPLEX | PGCIL | N18000403 | 11-2024 | 11/2026 | N.A. | 11/2026 | 5,969.00 | N.A. | 5,969.00 | 101.47 | -
1209 | RAJASTHAN | COAL | TRANSMISSION SYSTEM FOR EVACUATION OF POWER FROM RAJASTHAN REZ PH-IV [PART-3 (6 GW)] [BIKANER COMPLE | PGCIL | N18000404 | 11-2024 | 11/2026 | N.A. | 11/2026 | 5,357.00 | N.A. | 5,357.00 | 107.14 | 3.80
1210 | RAJASTHAN | COAL | RAJASTHAN REZ PH-V (PART-1: 4 GW) [SIROHI/NAGAUR] COMPLEX | PGCIL | N18000414 | 3-2025 | 3/2027 | N.A. | 3/2027 | 5,028.00 | N.A. | 5,028.00 | 20.12 | -
1211 | RAJASTHAN | COAL | AUGMENTATION AT FATEHGARH-II PS, FATEHGARH-IV PS (SECTION-II) AND BARMER-I | PGCIL | N18000415 | 3-2025 | 12/2026 | N.A. | 12/2026 | 404.00 | N.A. | 428.00 | 4.04 | -
1212 | RAJASTHAN | COAL | NOKH SOLAR PV PROJECT 735 MW | NTPC | N18000418 | 3-2022 | 4/2024 | Jul-2025 | 7/2025 | 4,189.17 | 4,378.17 | 4,378.17 | 213.45 | 97.00
1213 | RAJASTHAN | RAILWAYS | AGRA FORT-BANDIKUI | NCR | N22000553 | 6-2022 | 6/2027 | May-2026 | 5/2026 | 1,389.81 | N.A. | 987.83 | 42.46 | 12.00
1214 | RAJASTHAN | RAILWAYS | GUDHA THATHANA MITHRI TEST TRACK FOR RDSO | NWR | N22000593 | 4-2019 | 3/2025 | Jun-2025 | 6/2025 | 528.48 | N.A. | 500.85 | 357.48 | 98.00
1215 | RAJASTHAN | RAILWAYS | DEDICATED TEST TRACK FOR RDSO (PHASE II) | NWR | N22000594 | 11-2021 | 11/2026 | N.A. | 12/2025 | 466.42 | N.A. | 466.22 | 743.91 | 83.00
1216 | RAJASTHAN | RAILWAYS | DOUBLING BETWEEN CHURU- RATANGARH (42.81 KM) | NWR | N22000605 | 2-2023 | 2/2028 | N.A. | 6/2025 | 422.60 | N.A. | 422.60 | 216.78 | 95.00
1217 | RAJASTHAN | RAILWAYS | SAWAIMADHOPUR - BYPASS LINE (6.98 KM) (UMBRELLA WORK PB#57/2019- 20/NR) | NWR | N22000607 | 12-2022 | 6/2026 | May-2027 | 5/2027 | 304.00 | 239.54 | 239.54 | 133.73 | 35.00
1218 | RAJASTHAN | RAILWAYS | GC OF NATHDWARA - DEVGARH MADARIYA (82.5KM) | NWR | N22000608 | 1-2023 | 6/2028 | Dec-2026 | 12/2026 | 968.92 | N.A. | 968.92 | 410.60 | 42.00
1219 | RAJASTHAN | RAILWAYS | 2L+PS FOR WORK OF NH-325 (BALOTRA TO SANDERAO VIA JALORE) BY CONSTRUCTION OF BYPASSES:(1) ASOTRA- BR | MoRTH | N24001527 | 12-2021 | 5/2024 | Dec-2025 | 12/2025 | 411.40 | N.A. | 411.40 | 219.61 | 72.00
1220 | RAJASTHAN | RAILWAYS | WIDENING OF PACHPADRA-BAGUNDI SECTION TO 4 LANE FROM KM 73/60 TO 95/70 OF NH-25 ON EPC MODE IN THE | MoRTH | N24001528 | 1-2022 | 12/2024 | Aug-2025 | 8/2025 | 194.88 | N.A. | 194.88 | 105.69 | 83.00
1221 | RAJASTHAN | RAILWAYS | 44 LANE DIVIDED CARRIAGEWAY OF BARMER BYPASS OF NH-15 (NEW NH- 68) IN THE STATE OF RAJASTHAN ON EPC M | MoRTH | N24001529 | 12-2021 | 8/2024 | May-2025 | 5/2025 | 451.66 | N.A. | 451.66 | 401.78 | 99.00
1222 | RAJASTHAN | RAILWAYS | UPGRADATION TO TWO LANE PAVED SHOULDER OF KOTHUN-LALSOT- KAROLI-DHOLPUR ROAD NH-23 (OLD NH-11B) IN TH | MoRTH | N24001530 | 12-2021 | 9/2024 | N.A. | 8/2025 | 150.11 | N.A. | 150.11 | 82.83 | 88.00
1223 | RAJASTHAN | RAILWAYS | 4L GREENFIELD SPUR FROM DELHI- VADODARA GREENFIELD EXPRESSWAY NEAR BANDIKUI TO JAIPUR | NHAI | N24001557 | 3-2022 | 11/2024 | Aug-2025 | 8/2025 | 1,636.15 | N.A. | 1,636.15 | 553.96 | 99.80
1224 | RAJASTHAN | RAILWAYS | 4L OF KARWAR (KM. 281.980 OF NH-62 NAGAUR ROAD) TO DANGIYAVAS OF JODHPUR RING ROAD (PKG-II) | NHAI | N24001558 | 11-2021 | 8/2024 | Jul-2025 | 7/2025 | 736.75 | N.A. | 736.75 | 260.95 | 97.80
1225 | RAJASTHAN | RAILWAYS | 2L PS SRIGANGANAGAR TO RAISINGHNAGAR (DESIGN CHAINAGE - 0.500 KM TO DESIGN CHAINAGE 101.000 KM) (PACK | NHAI | N24001559 | 9-2021 | 6/2024 | Apr-2025 | 4/2025 | 672.35 | N.A. | 672.35 | 328.24 | 99.50
1226 | RAJASTHAN | RAILWAYS | DEOGARH (NEAR DHANDHANIYA)- RAJASTHAN/GUJARAT BORDER (PHASE-I) (AJ/DRGB-PACKAGE-6) | NHAI | N24001563 | 10-2019 | 8/2023 | Jul-2025 | 7/2025 | 846.59 | N.A. | 846.59 | 167.92 | 99.25
1227 | RAJASTHAN | RAILWAYS | DEOGARH (NEAR DHANDHANIYA)- RAJASTHAN/GUJARAT BORDER (PHASE-I) (AJ/DRGB-PACKAGE-7) | NHAI | N24001564 | 10-2019 | 7/2023 | Jul-2025 | 7/2025 | 662.08 | N.A. | 662.08 | 128.28 | 96.50
1228 | RAJASTHAN | RAILWAYS | DELHI-VADODARA GREENFIELD ALIGNMENT (NH-148N) (PKG-10) (CH. 292.950 TO CH. 319.400) [END OF INTERCHA | NHAI | N24001567 | 11-2019 | 10/2022 | Aug-2025 | 8/2025 | 1,272.97 | N.A. | 1,272.97 | 527.31 | 89.63
1229 | RAJASTHAN | RAILWAYS | DELHI-VADODARA GREENFIELD ALIGNMENT (NH-148N) (PKG-14) (CH. 388.420 TO CH. 419.000) [JUNCTION WITH N | NHAI | N24001568 | 11-2019 | 5/2023 | Jul-2025 | 7/2025 | 1,119.35 | N.A. | 1,119.35 | 1,447.44 | 99.80
1230 | RAJASTHAN | RAILWAYS | DELHI-VADODARA GREENFIELD ALIGNMENT (NH-148N) (PKG-09) (CH. 247.310 TO CH. 292.950) [JUNCTION WITH M | NHAI | N24001573 | 11-2019 | 12/2022 | Jul-2025 | 7/2025 | 1,658.06 | N.A. | 1,658.06 | 157.42 | 99.90
1231 | RAJASTHAN | RAILWAYS | DELHI-VADODARA GREENFIELD ALIGNMENT (NH-148N) (PKG-15) (CH. 419.000 TO CH.427.300) [JUNCTION WITH NH | NHAI | N24001612 | 7-2020 | 1/2024 | Dec-2025 | 12/2025 | 1,788.69 | N.A. | 1,788.69 | 965.50 | 78.50
1232 | RAJASTHAN | RAILWAYS | CONSTRUCTION OF TWO LANE WITH PAVED SHOULDER FOR FATEHPUR BYPASS, MANDAWA BYPASS AND JHUNJHUNU BYPAS | MoRTH | N24001866 | 3-2022 | 8/2024 | N.A. | 6/2025 | 186.29 | N.A. | 186.29 | 142.69 | 90.00
1233 | RAJASTHAN | RAILWAYS | UPGRADATION OF TWO LANE PAVED SHOULDER FROM SHAHPURA TO THANAGAZI OF NH-248A ON EPC MODE IN THE STAT | MoRTH | N24001867 | 3-2022 | 7/2024 | N.A. | 8/2025 | 174.34 | N.A. | 174.34 | 118.08 | 90.00
1234 | RAJASTHAN | RAILWAYS | Sagwara Bypass and Garhi- Partapur Bypass of NH-927A in the State of Rajasthan. | MoRTH | N24001868 | 3-2022 | 8/2025 | N.A. | 8/2025 | 187.65 | N.A. | 187.65 | 117.57 | 90.00
1235 | RAJASTHAN | RAILWAYS | UP-GRADATION TO 2 LANE WITH PAVED SHOULDER FROM CHARBHUJA AT DESIGN KM 0.00 (EXISTING KM 150.00) TO | MoRTH | N24001927 | 2-2022 | 9/2025 | N.A. | 9/2025 | 838.43 | N.A. | 838.43 | 455.87 | 99.00
1236 | RAJASTHAN | RAILWAYS | CONSTRUCTION OF 2 LANE WITH PAVED SHOULDER NORTHERN BYPASS PHASE-II OF KOTA CITY FROM DESIGN CHAINAG | MoRTH | N24001928 | 3-2022 | 4/2025 | N.A. | 12/2025 | 317.74 | N.A. | 317.74 | 136.23 | 13.00
1237 | RAJASTHAN | RAILWAYS | ADDITIONAL STRUCTURES ON 6LGURGAON-JAIPUR SECTION OF NH- 48 BETWEEN KM 42.700 TO KM 273.00 | NHAI | N24002058 | 8-2022 | 6/2024 | Jul-2025 | 7/2025 | 409.64 | N.A. | 409.64 | 240.90 | 81.65
1238 | RAJASTHAN | RAILWAYS | UPGRADATION TO 2 LANE WITH PAVED SHOULDER OF HANUMANGARH TO KENCHIYAN OF NH 54 ON EPC MODE IN THE ST | MoRTH | N24002167 | 3-2024 | 10/2026 | N.A. | 10/2026 | 334.64 | N.A. | 334.64 | 128.00 | 50.00
1239 | RAJASTHAN | RAILWAYS | UPGRADATION TO 2 LANE WITH PAVED SHOULDER FROM NEECHLI ODEN (NATHDWARA) AT DESIGN KM 88.800 TO BHATE | MoRTH | N24002168 | 3-2023 | 10/2026 | N.A. | 10/2026 | 606.61 | N.A. | 606.61 | 118.00 | 20.00
1240 | RAJASTHAN | RAILWAYS | CONSTRUCTION/ UP-GRATION OF FOUR/TWO LANE WITH PAVED SHOULDER OF NH68 FROM TANOT- RAMGARH BHADASAR-JA | NHAI | N24000795 | 2-2018 | 4/2021 | Jun-2025 | 6/2025 | 741.86 | 649.00 | 649.00 | 663.37 | 99.99
1241 | RAJASTHAN | RAILWAYS | 4L+PS OF NH -58 FROM BEAWAR- GOMTI (OLD CH KM 58.245 TO KM. 108.600) PKG-I. | MoRTH | N24001411 | 12-2020 | 10/2023 | N.A. | 12/2025 | 379.23 | N.A. | 379.23 | 268.62 | 96.10
1242 | SIKKIM | CIVIL AVIATION | PAKYONG AIRPORT- WIDENING OF BASIC STRIP AT WESTERN SIDE OF RUNWAY CHAINAGE 80M TO 920M I/C SLOPE ST | AAI | N04000110 | 11-2023 | 6/2026 | N.A. | 6/2026 | 323.26 | N.A. | 323.26 | 29.68 | 12.50
1243 | SIKKIM | DEPARTMENT OF HIGHER EDUCATION | CONSTRUCTION OF SIKKIM UNIVERSITY CAMPUS PHASE-I, PACKAGE -II AT YANGANG SOUTH SIKKIM | Sikkim Universi | N44000002 | 8-2020 | 1/2025 | N.A. | 1/2025 | 314.06 | N.A. | 303.55 | 157.24 | 80.00
1244 | SIKKIM | DEPARTMENT OF HIGHER EDUCATION | TEESTA VI HE PROJECT | NHPC | N18000325 | 3-2019 | 3/2024 | N.A. | 12/2027 | 5,748.04 | N.A. | 5,748.04 | 4,424.21 | 68.17
1245 | SIKKIM | DEPARTMENT OF HIGHER EDUCATION | RANGIT IV HE PROJECT | NHPC | N18000326 | 3-2021 | 5/2024 | N.A. | 12/2025 | 938.29 | N.A. | 1,828.11 | 1,524.17 | 89.45
1246 | SIKKIM | RAILWAYS | SEVOK RANGPO, NEFR | NFR | N22000102 | 4-2008 | 5/2015 | Dec-2027 | 12/2027 | 7,876.92 | 11,963.43 | 11,963.43 | 8,743.57 | 79.50
1247 | SIKKIM | RAILWAYS | CONSTRUCTION OF 2-LANE WITH PAVED SHOULDER GANGTOK BYPASS ROAD FROM RANIPOOL TO BURTUK (L=23.316KM) | MoRTH | N24001442 | 10-2021 | 5/2024 | Mar-2026 | 3/2026 | 385.15 | N.A. | 385.15 | 175.16 | 83.30
1248 | SIKKIM | RAILWAYS | CONSTRUCTION OF 2-LANE WITH PAVED SHOULDER INCLUDING GEOMETRIC IMPROVEMENT FROM KM 0.000 TO KM 16.00 | NHIDCL | N24000767 | 3-2017 | 4/2022 | May-2022 | 12/2023 | 375.80 | N.A. | 375.80 | 288.56 | 96.55
1249 | SIKKIM | RAILWAYS | CONSTUCTION/UPGRADATION OF EXISTING HIGHWAY TO 2 LANE WITH PAVED SHOULDER FROM KM 0.00 TO KM 13.00 N | NHIDCL | N24001251 | 3-2019 | 4/2022 | N.A. | 10/2025 | 402.94 | N.A. | 402.94 | 247.12 | 76.54
1250 | SIKKIM | RAILWAYS | CONSTUCTION/UPGRADATION OF EXISTING HIGHWAY TO 2 LANE WITH PAVED SHOULDER FROM KM 13.00 TO KM 25.600 | NHIDCL | N24001252 | 8-2020 | 4/2023 | Nov-2024 | 10/2025 | 295.97 | N.A. | 295.97 | 249.97 | 95.71
1251 | SIKKIM | RAILWAYS | CONSTRUCTION AND UPGRADATION OFEXISTINGROAD TO 2-LANE WITH PAVED SHOULDER INCLUDING GEOMETRIC IMPROV | NHIDCL | N24001261 | 8-2020 | 4/2023 | N.A. | 10/2025 | 311.00 | N.A. | 273.78 | 257.86 | 95.12
1252 | SIKKIM | RAILWAYS | CONSTRUCTION AND UPGRADATION OFEXISTINGROAD TO 2-LANE WITH PAVED SHOULDER INCLUDING GEOMETRIC IMPROV | NHIDCL | N24001262 | 7-2020 | 4/2023 | Aug-2024 | 10/2025 | 345.38 | 395.59 | 395.59 | 362.61 | 89.81
1253 | SIKKIM | RAILWAYS | CONSTRUCTION OF 2-LANE ROAD WITH PAVED SHOULDER (GREENFIELD ALIGNMENT) OF EXISTING STRETCH BETWEEN L | NHIDCL | N24001322 | 9-2020 | 5/2022 | Oct-2023 | 12/2025 | 183.31 | 439.56 | 439.56 | 355.31 | 51.85
1254 | SIKKIM | RAILWAYS | CONSTRUCTION OF 2-LANE SPECIFICATION ROAD WITH PAVED SHOULDER AS REALIGNMENT (GREENFIELD ALIGNMENT) | NHIDCL | N24001325 | 9-2020 | 5/2023 | Aug-2024 | 12/2025 | 262.84 | 414.20 | 414.20 | 221.86 | 49.20
1255 | SIKKIM | RAILWAYS | REHABILITATION AND UPGRADATION OF EXISTING ROAD TO 2-LANE WITH PAVED SHOULDER INCLUDING GEOMETRIC IM | NHIDCL | N24001327 | 8-2020 | 5/2022 | Oct-2023 | 12/2025 | 292.80 | N.A. | 292.80 | 202.92 | 61.41
1256 | SIKKIM | RAILWAYS | CONSTRUCTION AND UPGRADATION OF EXISTING ROAD TO 2-LANE WITH PAVED SHOULDER FROM KM27.200 (END OF RO | NHIDCL | N24001336 | 8-2020 | 4/2023 | Oct-2024 | 3/2026 | 230.45 | 244.91 | 244.91 | 206.95 | 82.80
1257 | SIKKIM | RAILWAYS | CONSTRUCTION AND UPGRADATION OF EXISTING ROAD TO 2-LANE WITH PAVED SHOULDER FROM NEW ROLEP BRIDGE AT | NHIDCL | N24001337 | 10-2020 | 11/2023 | Jul-2025 | 3/2026 | 493.42 | 478.79 | 478.79 | 308.18 | 59.49
1258 | SIKKIM | RAILWAYS | CONSTRUCTION OF 2-LANE WITH PAVED SHOULDER OF NEW GREEN FIELD ALIGNMENT FROM CHOCHENPHERI AT KM 52.0 | NHIDCL | N24001338 | 10-2020 | 12/2023 | Jun-2025 | 12/2026 | 816.79 | 786.60 | 786.60 | 332.24 | 45.90
1259 | SIKKIM | RAILWAYS | RISHI BORDER- ROLEP- MENLA PKG- 3B | NHIDCL | N24001362 | 12-2020 | 2/2024 | Dec-2025 | 12/2025 | 410.60 | 379.30 | 379.30 | 238.13 | 74.82
1260 | TAMIL NADU | CIVIL AVIATION | MODERNIZATION OF CHENNAI AIRPORT PHASE II, CHENNAI | AAI | N04000074 | 6-2018 | 2/2022 | Jun-2026 | 6/2026 | 2,467.00 | N.A. | 2,467.00 | 1,620.03 | 71.65
1261 | TAMIL NADU | CIVIL AVIATION | DEVELOPMENT OF TUTICORIN AIRPORT | AAI | N04000090 | 6-2019 | 3/2022 | Apr-2025 | 4/2025 | 380.87 | 451.74 | 451.74 | 362.06 | 100.00
1262 | TAMIL NADU | COAL | JAWAHAR KHANI OPENCAST (JK OC) MINE | SCCL | N06000259 | 12-2021 | 3/2025 | N.A. | 3/2026 | 297.88 | N.A. | 297.88 | 46.37 | 20.00
1263 | TAMIL NADU | COAL | 50 MW SOLAR POWER PROJECT - NEYVELI MINED OUT AREA | NLC | N06000279 | 5-2023 | 6/2025 | Nov-2025 | 11/2025 | 218.03 | N.A. | 218.03 | 148.89 | 40.00
1264 | TAMIL NADU | FINANCE | CONSTRUCTION OF 726 Nos RESIDENTIAL QUARTERS CHENNAI | CPWD FOR FINANC | N28000109 | 11-2017 | 11/2021 | N.A. | 11/2022 | 348.77 | N.A. | 348.77 | 223.39 | 100.00
1265 | TAMIL NADU | MINES | 25.5 MW WIND POWER PROJECT AT KAYATHAR IN TAMILNADU | NALCO | N10000014 | 9-2017 | 6/2019 | Dec-2025 | 12/2025 | 166.62 | 163.17 | 163.17 | 135.63 | 65.00
1266 | TAMIL NADU | MINES | IRUGUR-DEVANGONTHI POL PIPELINE | BPCL | N16000234 | 11-2012 | 2/2017 | Oct-2025 | 10/2025 | 678.00 | 1,732.00 | 1,732.00 | 642.76 | 64.10
1267 | TAMIL NADU | MINES | CBR 9 MMTPA PROJECT | CPCL | N16000434 | 1-2021 | 6/2025 | N.A. | 6/2025 | 31,580.00 | 31,580.00 | 36,354.00 | 1,326.17 | 10.20
1268 | TAMIL NADU | MINES | GRASS ROOT POL TERMINAL AT VALLUR, CHENNAI | IOCL | N16000438 | 1-2022 | 7/2024 | Jun-2025 | 12/2025 | 827.00 | 887.71 | 887.71 | 580.94 | 85.90
1269 | TAMIL NADU | MINES | LAYING OF POL PIPELINES IN COMMON CORRIDOR FOR PROPOSED GRASS ROOT TERMINAL AT VALLUR (CHENNAI) | IOCL | N16000455 | 1-2022 | 7/2024 | May-2026 | 5/2026 | 829.00 | N.A. | 829.00 | 259.48 | 60.16
1270 | TAMIL NADU | MINES | CGD PROJECT AT DHARMAPURI AND KRISHNAGIRI DISTRICTS | IOCL | N16000486 | 3-2022 | 3/2030 | N.A. | 12/2030 | 501.00 | N.A. | 501.00 | 112.66 | 5.30
1271 | TAMIL NADU | MINES | CGD PROJECTS AT THE NILGIRIS AND ERODE DISTRICTS | BPCL | N16000521 | 12-2022 | 3/2030 | N.A. | 3/2030 | 3,685.00 | N.A. | 3,685.00 | 213.89 | 11.20
1272 | TAMIL NADU | POWER | TRANSMISSION SYSTEM UNDER ISTS FOR EVACUATION OF POWER FROM KUDANKULAM UNIT - 3 AND 4 (2X1000 MW) | PGCIL | N18000408 | 1-2025 | 7/2028 | N.A. | 7/2028 | 548.00 | N.A. | 548.00 | 9.32 | 2.50
1273 | TAMIL NADU | RAILWAYS | EXTENSION OF MRTS FROM VELACHERY TO STN. THOMAS, MTP | MRTP | N22000028 | 4-2006 | 7/2024 | Aug-2025 | 8/2025 | 734.01 | 981.83 | 981.83 | 640.43 | 98.00
1274 | TAMIL NADU | RAILWAYS | TIDIVANAM-NAGARI (NL) | SR | N22000085 | 9-2006 | 9/2016 | Mar-2028 | 3/2028 | 3,631.34 | 3,631.34 | 3,631.34 | 873.31 | 15.00
1275 | TAMIL NADU | RAILWAYS | CHENNAI BEACH-CHENNAI EGMORE (4.3 KM) (UMBRELLA WORK PB#57/2019- 20/NR) | SR | N22000568 | 3-2022 | 3/2026 | Feb-2025 | 3/2025 | 359.60 | 274.20 | 310.00 | 305.93 | 95.00
1276 | TAMIL NADU | RAILWAYS | MORAPPUR-DHARMAPURI | SR | N22000618 | 2-2019 | 3/2028 | Mar-2028 | 3/2028 | 358.95 | N.A. | 358.95 | 40.09 | -
1277 | TAMIL NADU | RAILWAYS | NAGAPATTINAM THIRUTURAIPUNDI (38KM)- NEW LINE PROJECT | SR | N22000626 | 7-2008 | 3/2026 | Mar-2027 | 3/2027 | 677.12 | N.A. | 668.44 | 146.95 | 20.00
1278 | TAMIL NADU | RAILWAYS | FOUR LANING OF PUDUCHERRY (KM.29/000) TO POONDIYANKUPPAM (KM.67/000) SECTION OF NH-45A ON HAM UNDER | NHAI | N24001429 | 3-2018 | 11/2021 | Jul-2025 | 7/2025 | 1,294.47 | 1,588.40 | 1,588.40 | 867.34 | 98.72
1279 | TAMIL NADU | RAILWAYS | FOUR LANING OF SATTANATHAPURAM (KM.123/800) TO NAGAPATTINAM (KM.179/555) SECTION OF NH-45A ON HAM UN | NHAI | N24001431 | 3-2018 | 10/2020 | Jan-2026 | 1/2026 | 1,872.68 | 2,899.77 | 2,899.77 | 1,341.26 | 65.00
1280 | TAMIL NADU | RAILWAYS | CONSTRUCTION OF 4 LANE WITH PAVED SHOULDERS THIRUVAYARU BYPASS IN BETWEEN EXISTING KM.55/926 TO 62/6 | MoRTH | N24001455 | 2-2022 | 8/2022 | N.A. | 3/2025 | 191.33 | 207.97 | 207.97 | 100.42 | 100.00
1281 | TAMIL NADU | RAILWAYS | 4-LANING OF KAMALAPURAM - ODDANCHATRAM SECTION OF NH-209 | NHAI | N24001601 | 1-2019 | 1/2023 | Nov-2025 | 11/2025 | 1,051.69 | N.A. | 1,051.69 | 589.46 | 81.87
1282 | TAMIL NADU | RAILWAYS | 4-LANING OF MADATHUKULAM - POLLACHI SECTION OF NH-209 (NEW NH-83) | NHAI | N24001602 | 1-2019 | 12/2022 | Nov-2025 | 11/2025 | 1,409.38 | N.A. | 1,409.38 | 660.29 | 91.20
1283 | TAMIL NADU | RAILWAYS | 4-LANING OF MELUR - PILLAYARPATTI - KARAIKUDI SECTION OF NH-338, NH- 36, NH-383 | NHAI | N24001605 | 6-2018 | 3/2022 | N.A. | 8/2025 | 1,103.86 | N.A. | 1,103.86 | 568.15 | 87.00
1284 | TAMIL NADU | RAILWAYS | 4-LANING OF VADIPPATTI - THAMARAIPATTI SECTION OF NH-744A (MADURAI RING ROAD) | NHAI | N24001606 | 12-2018 | 3/2022 | Sep-2025 | 9/2025 | 854.94 | N.A. | 854.94 | 400.13 | 80.30
1285 | TAMIL NADU | RAILWAYS | BALANCE WORKS OF FOUR LANE FROM KM 43+950 (THIRUVALLUR BYPASS) TO KM 61+470 (VEPPAMPATTU BYPASS) PAS | NHAI | N24001692 | 1-2022 | 9/2024 | Feb-2025 | 8/2025 | 467.99 | N.A. | 468.00 | 113.05 | 84.34
1286 | TAMIL NADU | RAILWAYS | FOUR LANING OF NERALURU TO THORAPALLI AGRAHARAM SECTION OF NH-844 (PKG-I) FROM KM.0+000 TO KM.23+350 | NHAI | N24001693 | 9-2021 | 10/2024 | N.A. | 10/2024 | 1,751.18 | N.A. | 1,757.27 | 49.69 | -
1287 | TAMIL NADU | RAILWAYS | FOUR LANING OF THORAPALLI AGRAHARAM TO JITTANDAHALLI SECTION OF NH-844 (PKG-II) FROM KM.23+350 TO KM | NHAI | N24001694 | 2-2019 | 12/2023 | Dec-2024 | 12/2024 | 1,243.57 | N.A. | 1,243.57 | 171.63 | -
1288 | TAMIL NADU | RAILWAYS | FOUR LANING OF JITTANDAHALLI TO DHARMAPURI SECTION OF NH-844 (PKG-III) FROM KM.60+100 TO KM.94+460 | NHAI | N24001696 | 2-2019 | 8/2023 | Dec-2024 | 12/2024 | 1,291.37 | N.A. | 1,291.37 | 215.02 | -
1289 | TAMIL NADU | RAILWAYS | THOPPUR METTUR BHAVANI ERODE SECTION OF NH 544H FOR A LENGTH OF 85 KM | NHAI | N24001716 | 7-2022 | 8/2023 | Dec-2024 | 12/2024 | 186.50 | 242.40 | 242.40 | 34.33 | 100.00
1290 | TAMIL NADU | RAILWAYS | BANGALORE CHENNAI EXPRESSWAY PHASE-III PACKAGE III (ARAKKONAM TO KANCHEEPURAM) FROM KM 204.500 TO K | NHAI | N24001717 | 11-2020 | 8/2024 | N.A. | 3/2026 | 1,155.49 | 1,525.10 | 1,525.10 | 489.94 | 53.56
1291 | TAMIL NADU | RAILWAYS | BANGALORE CHENNAI EXPRESSWAY PHASE-III PACKAGE II (WALAJAHPET TO ARAKKONAM) FROM KM 180.000 TO KM 2 | NHAI | N24001718 | 12-2020 | 7/2024 | N.A. | 10/2025 | 843.48 | 1,077.40 | 1,068.60 | 434.49 | 91.26
1292 | TAMIL NADU | RAILWAYS | 4L BANGALORE-CHENNAI EXPRESSWAY FROM KM. 230.000 TO KM. 261.705 OF KANCHEPURAM TO SRIPERUMBUDUR SECT | NHAI | N24001719 | 2-2021 | 7/2024 | N.A. | 12/2025 | 2,948.31 | 3,605.73 | 3,605.73 | 820.23 | 78.11
1293 | TAMIL NADU | RAILWAYS | BANGALORE CHENNAI EXPRESSWAY PHASE-III ? PACKAGE I (GUDIPALA TO WALAJAJHPET) FROM KM 156.000 TO KM 1 | NHAI | N24001720 | 10-2020 | 5/2024 | N.A. | 10/2025 | 1,023.91 | 1,438.62 | 1,438.62 | 635.04 | 86.22
1294 | TAMIL NADU | RAILWAYS | FOUR LANING OF MAMALLAPURAM TO MUGAIYUR SECTION OF NH332A FROM KM 0.000 TO KM 31.000 | NHAI | N24001721 | 2-2019 | 5/2024 | Aug-2025 | 3/2026 | 1,008.99 | 1,360.53 | 1,360.53 | 324.81 | 50.33
1295 | TAMIL NADU | RAILWAYS | 6L OF MADURAVOYAL TO SRIPERUMBUDUR SECTION FROM KM. 13.800 TO KM. 37.000 OF NH-4 THROUGH STATE HIGH | NHAI | N24001722 | 11-2021 | 2/2023 | N.A. | 12/2024 | 463.44 | 463.07 | 463.44 | 334.80 | 99.00
1296 | TAMIL NADU | RAILWAYS | KARAIPETTAI TO WALAJAPET FROM KM 71.015 TO 107.091 | NHAI | N24001723 | 10-2018 | 2/2021 | N.A. | 8/2025 | 707.90 | 766.51 | 766.51 | 542.69 | 91.00
1297 | TAMIL NADU | RAILWAYS | 6L OF SRIPERUMBUDUR TO KARAIPETTAI FROM KM 37.000 TO KM 71.015 OF NH 48 | NHAI | N24001725 | 1-2019 | 5/2021 | N.A. | 1/2025 | 819.89 | 1,314.82 | 922.85 | 419.84 | 57.32
1298 | TAMIL NADU | RAILWAYS | CONSTRUCTION OF BYPASS TO GUDIYATHAM TOWN IN KM 23/100 ? 29/250 INCLUDING LA AND SHIFTING OF NH-234 | MoRTH | N24001828 | 1-2022 | 11/2024 | N.A. | 5/2025 | 221.03 | 243.95 | 243.95 | 176.50 | 100.00
1299 | TAMIL NADU | RAILWAYS | FOUR LANING OF OTTANCHATRAM TO PALANI SECTION FROM KM 30/700 TO KM 55/000 OF NH 209(NEW NH-83) INCLU | MoRTH | N24001829 | 10-2022 | 11/2024 | N.A. | 5/2025 | 172.15 | N.A. | 172.15 | 163.82 | 100.00
1300 | TAMIL NADU | RAILWAYS | CONSTRUCTION OF STRR (WEST SIDE)-NH948A-BALAGONDAPALLI (TAMIL NADU) TO KARNATAKA/TAMIL NADU BORDER F | NHAI | N24001968 | 4-2022 | 5/2025 | N.A. | 5/2025 | 1,260.74 | N.A. | 1,260.74 | 487.46 | 44.95
1301 | TAMIL NADU | RAILWAYS | 4L OF THIRUMANGALAM TO VADUGAPATTI SECTION FROM KM 0.000 TO KM 36.000 OF NH-744 | NHAI | N24002084 | 3-2022 | 2/2025 | N.A. | 9/2025 | 1,076.97 | N.A. | 1,076.97 | 540.46 | 87.42
1302 | TAMIL NADU | RAILWAYS | CONSTRUCTION OF NEW DOUBLE TIER 4 LANE ELEVATED CORRIDOR FROM CHENNAI PORT TO MADURAVOYAL IN CHENNAI | NHAI | N24002107 | 3-2023 | 5/2026 | N.A. | 5/2026 | 1,382.00 | N.A. | 1,382.00 | 0.00 | -
1303 | TAMIL NADU | RAILWAYS | CONSTRUCTION OF NEW DOUBLE TIER 4L ELEVATED CORRIDOR FROM CHENNAI PORT TO MADURAVOYAL IN CHENNAI DIS | NHAI | N24002108 | 3-2023 | 5/2026 | N.A. | 5/2026 | 1,618.96 | N.A. | 1,618.96 | 0.00 | -
1304 | TAMIL NADU | RAILWAYS | CONSTRUCTION OF NEW DOUBLE TIER 4L ELEVATED CORRIDOR FROM CHENNAI PORT TO MADURAVOYAL IN CHENNAI DIS | NHAI | N24002109 | 3-2023 | 5/2026 | N.A. | 5/2026 | 1,301.37 | N.A. | 1,301.37 | 0.00 | -
1305 | TAMIL NADU | RAILWAYS | CONSTRUCTION OF NEW DOUBLE TIER 4L ELEVATED CORRIDOR FROM CHENNAI PORT TO MADURAVOYAL IN CHENNAI DIS | NHAI | N24002110 | 3-2023 | 5/2026 | N.A. | 5/2026 | 1,207.40 | N.A. | 1,207.40 | 0.00 | -
1306 | TAMIL NADU | RAILWAYS | FOUR LANING OF MUGAIYUR TO MARAKKANAM SECTION OF NH-332A FROM KM 31.000 TO KM 62.000 | NHAI | N24002111 | 2-2019 | 12/2025 | May-2026 | 5/2026 | 825.94 | 1,116.13 | 1,116.13 | 344.92 | 40.55
1307 | TAMIL NADU | RAILWAYS | SIX LANING OF TUTICORIN PORT ROAD SECTION OF NH-7A (NEW NH- 138) FROM KM 0.000 TO KM 6.140 [EFFECTIVE | NHAI | N24002112 | 3-2023 | 7/2024 | N.A. | 7/2025 | 200.30 | N.A. | 200.30 | 113.71 | 93.11
1308 | TAMIL NADU | RAILWAYS | 4L OF LEFT-OVER WORKS INCLUDING ADDITIONAL STRUCTURES FROM KERALA/TAMIL NADU BORDER TO KANYAKUMARI S | NHAI | N24002113 | 3-2023 | 8/2025 | N.A. | 8/2025 | 1,141.78 | N.A. | 1,141.78 | 466.20 | 47.86
1309 | TAMIL NADU | RAILWAYS | 4L OF VADUGAPATTI TO THERKUVENGANALLUR (RAJAPALYAM) SECTION FROM KM 36.000 TO KM 71.600 OF NH744 UND | NHAI | N24002114 | 2-2022 | 4/2025 | N.A. | 10/2025 | 1,097.59 | N.A. | 1,317.06 | 705.17 | 97.80
1310 | TAMIL NADU | RAILWAYS | WIDENING TO 4L/4L+PS AND STRENGTHENING IN SELECTED STRETCHES FROM KM 0/8 TO 50/570 OF NH 532 INCLUD | MoRTH | N24002151 | 3-2022 | 1/2024 | N.A. | 7/2025 | 257.14 | 294.70 | 294.70 | 277.57 | 90.00
1311 | TAMIL NADU | RAILWAYS | WIDENING FROM 2L+PS TO 4L/4L+PS AND IMPROVEMENTS THE SELECTED STRETHCES FROM KM 26/5 - 81/2 INCLU | MoRTH | N24002152 | 3-2023 | 11/2023 | N.A. | 11/2025 | 274.84 | N.A. | 274.84 | 265.83 | 100.00
1312 | TAMIL NADU | RAILWAYS | STRENGTHENING OF 2L+PS FROM KM 17/8 ? 18/2, CONSTRUCTION OF 2L+PS FROM KM 18/2 TO KM 20/0 AND CONSTR | MoRTH | N24002153 | 3-2023 | 2/2024 | N.A. | 8/2025 | 169.68 | N.A. | 169.68 | 145.29 | 100.00
1313 | TAMIL NADU | RAILWAYS | CONSTRUCTION OF BYPASS TO MADURAI - ACHAMBATHU - VIRATIPATHU IN KM 6/850 - 10/382 OF NH 49 EXTN. (NE | MoRTH | N24002165 | 3-2022 | 8/2026 | N.A. | 8/2026 | 238.97 | 260.07 | 260.07 | 118.00 | 50.00
1314 | TAMIL NADU | RAILWAYS | ACCESS CONTROLLED HIGHWAY OF 4 LANE WITH PAVED SHOULDERS FROM TIRUVALLUR (DESIGN CHAINAGE KM 17+56) | NHAI | N24002216 | 12-2024 | 12/2026 | N.A. | 12/2026 | 1,376.10 | N.A. | 1,376.10 | 39.00 | 8.74
1315 | TAMIL NADU | RAILWAYS | FOUR LANNING OF CHOLOPURAM- THANJAVUR | NHAI | N24000697 | 8-2017 | 9/2020 | N.A. | 7/2025 | 1,176.37 | N.A. | 1,176.37 | 1,325.06 | 99.50
1316 | TAMIL NADU | RAILWAYS | 4-LANNING OF STHIYATHOPU- CHOLOPURAM | NHAI | N24000708 | 9-2017 | 8/2020 | Jul-2025 | 7/2025 | 1,227.87 | N.A. | 1,227.87 | 1,436.16 | 99.50
1317 | TAMIL NADU | RAILWAYS | FOUR LANINIG OF CHETTIKULAM TO NATHAM SECTION OF NH-785 FROM CHETTIKULUM (KM 7.300) TO NATHAM (KM. 3 | NHAI | N24000826 | 3-2018 | 10/2022 | Jul-2025 | 7/2025 | 505.35 | N.A. | 837.69 | 376.61 | 99.75
1318 | TELANGANA | COAL | KAKATIYAKHANI OPENCAST III PROJECT PHASE-1 | SCCL | N06000161 | 3-2017 | 3/2022 | N.A. | 3/2026 | 413.84 | N.A. | 413.84 | 397.54 | 85.00
1319 | TELANGANA | COAL | GODAVARIKHANI COAL MINE | SCCL | N06000202 | 7-2019 | 3/2023 | N.A. | 3/2026 | 438.98 | N.A. | 438.98 | 178.21 | 70.00
1320 | TELANGANA | COAL | VENKATESH KHANI COAL MINE | SCCL | N06000204 | 10-2020 | 3/2023 | N.A. | 3/2027 | 484.51 | N.A. | 484.51 | 318.12 | 55.00
1321 | TELANGANA | COAL | RCE OF RAMAGUNDAM OPENCAST II EXTENSION PROJECT | SCCL | N06000210 | 11-2015 | 3/2023 | N.A. | 3/2026 | 489.62 | N.A. | 489.62 | 405.54 | 70.00
1322 | TELANGANA | COAL | RCE OF INDARAM OPENCAST PROJECT | SCCL | N06000211 | 8-2017 | 3/2021 | N.A. | 3/2025 | 349.28 | N.A. | 424.81 | 402.64 | 80.00
1323 | TELANGANA | COAL | RCE OF KALYANIKHANI OPENCAST PROJECT | SCCL | N06000213 | 3-2016 | 3/2020 | N.A. | 3/2026 | 384.32 | N.A. | 384.32 | 265.53 | 75.00
1324 | TELANGANA | COAL | RCE OF KAKATHIYAKHANI OC - 2 PROJECT | SCCL | N06000214 | 8-2017 | 3/2020 | N.A. | 3/2026 | 442.42 | N.A. | 442.42 | 203.14 | 63.00
1325 | TELANGANA | COAL | GOLETI OPENCAST MINE | SCCL | N06000258 | 7-2021 | 3/2026 | N.A. | 3/2026 | 345.60 | N.A. | 345.60 | 72.09 | 20.00
1326 | TELANGANA | HEALTH AND FAMILY WELFARE | ESTABLISHMENT OF NATIONAL ANIMAL RESOURCE FACILITY FOR BIOMEDICAL RESEARCH AT HYDERABAD | CPWD FOR HEALTH | N28000098 | 10-2016 | 3/2020 | Jan-2025 | 1/2025 | 209.84 | 281.05 | 281.05 | 253.64 | 98.50
1327 | TELANGANA | HEALTH AND FAMILY WELFARE | COMPREHENSIVE PLANNING, DESIGNING, EXECUTION OF ALL INDIA INSTITUTE OF MEDICAL SCIENCES AT BIBINAGAR | HITES | N21000031 | 12-2018 | 7/2024 | N.A. | 12/2025 | 1,110.55 | N.A. | 1,110.55 | 753.76 | 83.07
1328 | TELANGANA | RAILWAYS | MANOHARABAD-KOTHPALL NEW LINE(SCR) | SCR | N22000032 | 4-2006 | 3/2027 | N.A. | 3/2025 | 1,160.00 | N.A. | 3,014.00 | 1,568.57 | -
1329 | TELANGANA | RAILWAYS | KHAMMAM-DEVARAPALLE PKG I [4L ACCESS CONTROLLED (GREENFIELD) FROM THALLAMPADU VILLAGE TO SOMAVARAM | NHAI | N24001482 | 8-2022 | 10/2024 | Aug-2022 | 12/2025 | 772.11 | N.A. | 772.11 | 558.24 | 80.51
1330 | TELANGANA | RAILWAYS | KHAMMAM DEVARAPALLE PKG II 4L ACCESS CONTROLLED (GREENFIELD) FROM SOMAVARAM VILLAGE TO CHINTAGUDEM V | NHAI | N24001483 | 2-2022 | 9/2024 | Feb-2022 | 9/2025 | 637.11 | N.A. | 637.11 | 415.98 | 85.40
1331 | TELANGANA | RAILWAYS | KHAMMAM-DEVARAPALLE PKG III [4L ACCESS CONTROLLED (GREENFIELD) FROM CHINTAGUDEM VILLAGE TO RECHERLA | NHAI | N24001484 | 9-2022 | 2/2024 | Sep-2022 | 9/2025 | 804.69 | N.A. | 804.69 | 514.29 | 91.20
1332 | TELANGANA | RAILWAYS | 4L OF KODAD (DESIGN KM 0.00/EXISTING KM 185.00 OF NH-65) TO KHAMMAM (DESIGN KM 31.800/EXISTING KM 29 | NHAI | N24001522 | 1-2021 | 1/2024 | Jan-2021 | 7/2025 | 1,307.95 | N.A. | 1,307.95 | 727.42 | 99.98
1333 | TELANGANA | RAILWAYS | 6 LANING OF EXISTING 4-LANE STRETCH FROM KALKALLU AT KM.454+000 TO GUNDLA POCHAMPALLY AT KM.471+000, | NHAI | N24001555 | 3-2022 | 1/2025 | N.A. | 1/2025 | 955.49 | N.A. | 955.49 | 233.46 | 35.96
1334 | TELANGANA | RAILWAYS | 6L OF EXISTING 4L FROM GUNDLAPOCHAMPALLY TO BOWENPALLY FROM KM 471.300 TO KM 481.331 OF NH-44 | NHAI | N24001556 | 12-2021 | 7/2024 | N.A. | 7/2024 | 521.53 | N.A. | 521.53 | 250.70 | 49.63
1335 | TELANGANA | RAILWAYS | 6L ACCESS CONTROLLED GREENFIELD HIGHWAY OF JULEKAL VILLAGE TO DINNEDEVARAPADU VILLAGE FROM KM 242.20 | NHAI | N24001625 | 1-2022 | 1/2025 | N.A. | 7/2025 | 1,227.57 | N.A. | 1,227.57 | 288.58 | 45.65
1336 | TELANGANA | RAILWAYS | 6L ACCESS CONTROLLED GREENFIELD HIGHWAY OF NANDINNE VILLAGE TO JULEKAL VILLAGE FROM KM 202.900 TO KM | NHAI | N24001626 | 2-2022 | 1/2025 | N.A. | 1/2025 | 972.06 | N.A. | 972.06 | 408.48 | 70.26
1337 | TELANGANA | RAILWAYS | WIDENING AND STRENGTHENING OF EXISTING 2 LANE WITH PAVED SHOULDER TO 4 LANE WITH PAVED SHOULDER FRO | MoRTH | N24002000 | 3-2021 | 7/2024 | N.A. | 7/2024 | 317.19 | N.A. | 317.19 | 178.64 | 72.00
1338 | TELANGANA | RAILWAYS | WIDENING TO 2 LANE WITH PAVED SHOULDERS OF MEDAK - SIDDIPET SECTION FROM KM 0/0 TO KM 69/978 OF NH- | MoRTH | N24002001 | 1-2022 | 1/2025 | N.A. | 1/2025 | 882.18 | N.A. | 882.18 | 376.66 | 73.14
1339 | TELANGANA | RAILWAYS | WIDENING AND IMPROVEMENT OF EXISTING CARRIAGE WAY TO 2 LANE WITH PAVED SHOULDERS FROM KM. 86/160 TO | MoRTH | N24002002 | 1-2022 | 12/2024 | N.A. | 12/2024 | 423.48 | N.A. | 423.48 | 166.39 | 71.65
1340 | TELANGANA | RAILWAYS | REHABILITATION AND UP-GRADATION OF VALIGONDA TO THORRUR SECTION TO TWO LANE WITH PAVED SHOULDERS FRO | MoRTH | N24002003 | 1-2022 | 12/2024 | N.A. | 12/2024 | 549.28 | N.A. | 549.28 | 257.89 | 74.75
1341 | TELANGANA | RAILWAYS | REHABILITATION AND UPGRADATION OF LB-NAGAR TO MALKAPUR SECTION TO 6-LANE MAIN CARRIAGEWAY WITH SERVI | MoRTH | N24002004 | 3-2021 | 7/2024 | N.A. | 7/2024 | 545.11 | N.A. | 545.11 | 198.03 | 76.64
1342 | TELANGANA | RAILWAYS | WIDENING TO TWO LANE WITH PAVED SHOULDERS OF 'BODHAN BASAR BHAINSA ' SECTION FROM KM 38/900 TO 95/3 | MoRTH | N24002005 | 3-2022 | 3/2025 | N.A. | 3/2025 | 644.45 | N.A. | 644.45 | 221.65 | 93.60
1343 | TELANGANA | RAILWAYS | ONSTRUCTION OF 4-LANE FLYOVER AT AMBERPET-X ROAD, HYDERABAD ON NH-202 IN THE STATE OF TELANGANA | MoRTH | N24002006 | 10-2017 | 6/2023 | N.A. | 6/2023 | 186.71 | N.A. | 186.71 | 149.64 | 92.10
1344 | TELANGANA | RAILWAYS | WIDENING TO TWO LANE WITH PAVED SHOULDERS FROM KM 0/000 TO KM 79/300 OF KALWAKURTHY - KOLLAPUR SECTI | MoRTH | N24002007 | 3-2022 | 7/2025 | N.A. | 7/2025 | 886.69 | N.A. | 886.69 | 252.22 | 67.94
1345 | TELANGANA | RAILWAYS | WIDENING TO 2 LANE WITH PAVED SHOULDERS OF SIDDIPET- ELKATHURTHY SECTION FROM KM 69/978 TO KM 133/6 | MoRTH | N24002008 | 1-2022 | 12/2024 | N.A. | 12/2024 | 578.85 | N.A. | 578.85 | 292.69 | 82.05
1346 | TELANGANA | RAILWAYS | WIDENING AND STRENGTHENING TO 2/4 LANE WITH PAVED SHOULDERS OF MAHABUBNAGAR ? CHINCHOLI SECTION FROM | MoRTH | N24002009 | 1-2022 | 1/2025 | N.A. | 7/2025 | 703.68 | N.A. | 703.68 | 210.72 | 76.45
1347 | TELANGANA | RAILWAYS | WIDENING AND STRENGTHENING TO 4 LANE / 2-LANE WITH PAVED SHOULDERS OF MAHABUBNAGAR- CHINCHOLI SECTION | MoRTH | N24002010 | 3-2022 | 3/2024 | N.A. | 10/2025 | 631.49 | N.A. | 631.49 | 75.33 | 28.98
1348 | TELANGANA | RAILWAYS | IMPROVEMENT OF GEOMETRICS OF THONDUPALLY TO KOTHUR FROM KM 22.300 TO KM 34.14 OF NH-44-RCW | NHAI | N24002082 | 2-2022 | 9/2024 | N.A. | 1/2026 | 541.58 | N.A. | 541.58 | 34.98 | -
1349 | TELANGANA | RAILWAYS | FOUR LANING OF KARIMNAGAR- WARANGAL SECTION OF NH-563 FROM DESIGN CH.48.860 KM NEAR SH-1 CH.170.400 K | NHAI | N24002083 | 3-2022 | 7/2025 | N.A. | 7/2025 | 2,146.86 | 2,413.00 | 2,414.46 | 999.54 | 72.35
1350 | TELANGANA | RAILWAYS | CONSTRUCTION OF 4-LANE ACCESS CONTROLLED GREENFIELD HIGHWAY SECTION ON NH-163G (KHAMMAM- VIJAYAWADA) | NHAI | N24002190 | 3-2023 | 8/2026 | N.A. | 8/2026 | 983.00 | N.A. | 983.00 | 0.00 | 8.50
1351 | TELANGANA | RAILWAYS | CONSTRUCTION OF 4-LANE ACCESS CONTROLLED GREENFIELD HIGHWAY SECTION ON NH-163G (KHAMMAM - VIJAYAWADA | NHAI | N24002236 | 3-2023 | 3/2025 | N.A. | 3/2027 | 832.62 | N.A. | 832.62 | 0.00 | -
1352 | TELANGANA | RAILWAYS | REHABILITATION AND UPGRADATION OF NH -565 FROM KM 1.00 TO 86.057 (NAKREKAL TO NAGARJUNSAGAR DAM SECT | MoRTH | N24000245 | 1-2014 | 3/2016 | Sep-2019 | 9/2019 | 270.00 | N.A. | 270.00 | 0.00 | 72.15
1353 | TELANGANA | RAILWAYS | REHABILITATION AND UPGRADATION OF NH-221 FROM KM 121/0 TO 165/00 (OF VIJAYAWADA-JAGDALPUR RUDRAMPUR | MoRTH | N24000247 | 10-2014 | 2/2017 | N.A. | 2/2017 | 295.47 | N.A. | 295.47 | 224.42 | 82.76
1354 | TELANGANA | RAILWAYS | EPC- CORRIDOR APPROACH WORKS - NH (O): WIDENING EXISTING 2 LANE TO 2 LANE WITH PAVED SHOULDERS IN KM | MoRTH | N24000248 | 3-2015 | 1/2017 | N.A. | 1/2017 | 153.21 | N.A. | 153.21 | 100.96 | 93.20
1355 | TELANGANA | RAILWAYS | WIDEINING TO TWO/FOUR LANE WITH PAVED SHOULDERS FROM EXISTING KM 182.120 TO KM 227.600 OF NH-167 ON | MoRTH | N24000980 | 10-2016 | 2/2019 | N.A. | 2/2019 | 298.32 | N.A. | 298.32 | 178.47 | -
1356 | TELANGANA | RAILWAYS | WIDEINING TO TWO/FOUR LANE WITH PAVED SHOULDERS FROM EXISTING KM 180.60 TO KM 223.00 OF NH-63 ON NIZ | MoRTH | N24000981 | 10-2016 | 3/2019 | N.A. | 3/2019 | 248.83 | N.A. | 248.83 | 173.79 | -
1357 | TELANGANA | RAILWAYS | WIDENING TO TWO LANE WITH PAVED SHOULDERS FROM KM 40/410 TO KM 84/037OF THIRUMALAGIRI TO SURYAPET SE | MoRTH | N24000982 | 1-2017 | 5/2019 | N.A. | 5/2019 | 244.54 | N.A. | 244.54 | 174.35 | 99.96
1358 | TELANGANA | RAILWAYS | WIDENING TO TWO LANE WITH PAVED SHOULDERS FROM KM 0/970 TO KM 40/410 OF JANAGAON-THIRUMALAGIRI OF NH | MoRTH | N24000983 | 1-2017 | 10/2019 | N.A. | 10/2019 | 196.52 | N.A. | 196.52 | 125.53 | 92.74
1359 | TELANGANA | RAILWAYS | WIDENING TO TWO LANE WITH PAVED SHOULDERS FROM KM 15.525 TO KM 62.880 OF JADCHERLA-KALWAKURTHY SECTI | MoRTH | N24000984 | 1-2017 | 12/2019 | N.A. | 12/2019 | 283.00 | N.A. | 283.00 | 259.15 | 99.32
1360 | TELANGANA | RAILWAYS | WIDENING TO TWO LANE WITH PAVED SHOULDERS FROM KM 67.00 TO 114.425 OF KALWAKURTHY- MALLEPALLY SECTION | MoRTH | N24000986 | 1-2017 | 5/2019 | N.A. | 5/2019 | 300.00 | N.A. | 300.00 | 239.93 | 99.09
1361 | TELANGANA | RAILWAYS | 6 LANING FROM KM 9.90 TO KM 19.948 (ARAMGARH-SAMSHABAD SECTION) OF HYDERABAD-SAMSHABAD SECTION OF NH | MoRTH | N24000987 | 1-2018 | 5/2020 | N.A. | 5/2020 | 283.15 | N.A. | 283.15 | 270.01 | 92.62
1362 | TELANGANA | RAILWAYS | WIDENING AND STRENGTHENING OF EXISTING 2-LANE TO 2-LANE WITH PAVED SHOULDERS FROM KM.159/0 TO 165/4 | MoRTH | N24000988 | 1-2018 | 12/2019 | N.A. | 12/2019 | 230.03 | N.A. | 230.03 | 231.31 | 100.00
1363 | TELANGANA | RAILWAYS | WIDENING AND STRENGTHENING OF EXISTING CARRIAGEWAY IN 2 LANE WITH PAVED SHOULDERS FROM KM.25/0 TO 59 | MoRTH | N24000989 | 2-2018 | 6/2020 | N.A. | 6/2020 | 206.13 | N.A. | 206.13 | 190.94 | 98.56
1364 | TELANGANA | RAILWAYS | REHABILITATION AND UPGRADATION OF NH-167 FROM DESIGN KM.113.900 TO 154.479 (MALLEPALLY - HALIYA SECT | MoRTH | N24000990 | 2-2018 | 11/2019 | N.A. | 11/2019 | 294.13 | N.A. | 294.13 | 198.75 | 90.10
1365 | TELANGANA | RAILWAYS | REHABILITATION AND UPGRADATION OF NH-167 FROM DESIGN KM.187.723 TO 234.434 (MIRYALAGUDA TO KODAD SEC | MoRTH | N24000993 | 3-2018 | 9/2020 | N.A. | 9/2020 | 322.81 | N.A. | 322.81 | 315.23 | 98.14
1366 | TELANGANA | RAILWAYS | CONSTRUCTION OF SIX LANE ELEVATED CORRIDOR FROM KM.7.950 (UPPAL) TO KM.14.200 OF NH-163 TO DE-CONGES | MoRTH | N24000994 | 3-2018 | 7/2020 | N.A. | 2/2026 | 626.76 | N.A. | 626.76 | 272.64 | 46.00
1367 | TELANGANA | RAILWAYS | REHABILITATION AND UP-GRADATION TO TWO LANE WITH PAVED SHOULDERS FROM KM 0/0 TO 72/6 OF NH-365 (NAKR | MoRTH | N24000996 | 1-2017 | 10/2019 | N.A. | 10/2019 | 605.08 | N.A. | 605.08 | 413.37 | 99.90
1368 | TELANGANA | RAILWAYS | REHABILITATION AND UP GRADATION FROM KM. 121/0 TO 154/0 OF NAKAREKAL ? MALLAMPALLY SECTION OF NH-365 | MoRTH | N24000997 | 3-2018 | 7/2019 | N.A. | 7/2019 | 192.67 | N.A. | 192.67 | 176.37 | 96.00
1369 | TELANGANA | RAILWAYS | WIDENING AND STRENGTHENING/ RECONSTRUCTION OF EXISTING PAVEMENT TO FOUR ALNE WITH PAVED SHOULDERS FR | MoRTH | N24000998 | 1-2019 | (N.A.) |  |  | 193.19 | N.A. | 249.72 | 222.58 | 100.00
1370 | TRIPURA | PETROLEUM | GRASS ROOT RAIL FED DEPOT AT SEKERKOTE, AGARTALA AS RESITEMENT OF EXISTING DHARMANAGAR DEPOT | IOCL | N16000495 | 6-2022 | 8/2025 | Sep-2025 | 9/2025 | 656.00 | N.A. | 656.00 | 427.77 | 83.17
1371 | TRIPURA | PETROLEUM | 2 LANING FROM MANU-SIMLUNG PKG-2 | NHIDCL | N24001542 | 2-2022 | 1/2025 | May-2025 | 5/2025 | 456.88 | N.A. | 456.88 | 122.67 | 50.18
1372 | TRIPURA | PETROLEUM | IMPROVEMENT AND WIDENING TO 2- LANE WITH EARTHEN PAVED SHOULDER FROM UDAIPUR TO SRIMANTAPUR | NHIDCL | N24001914 | 5-2023 | 11/2024 | N.A. | 12/2025 | 195.95 | N.A. | 195.95 | 46.46 | 45.42
1373 | TRIPURA | PETROLEUM | 4 LANE WITH PAVED SHOULDER AGARTALA BYPASS (WESTERN SIDE) CONNECTING NH-8 | NHIDCL | N24002132 | 3-2023 | 3/2027 | N.A. | 3/2027 | 2,026.05 | N.A. | 2,026.05 | 26.34 | 8.82
1374 | TRIPURA | PETROLEUM | REHABILITATION AND UP-GRADATION OF ROAD FROM DESIGN KM 25.250 TO KM 36.460 (TOTAL LENGH: 11.210 KM) | NHIDCL | N24002159 | 2-2020 | 3/2026 | N.A. | 3/2026 | 174.43 | N.A. | 174.43 | 9.54 | 16.61
1375 | TRIPURA | PETROLEUM | IMPROVEMENT AND WIDENING TO 2- LANE WITH PAVED SHOULDER OF ROAD FROM KM 101.300 TO KM 127.319 (TOTAL | NHIDCL | N24002160 | 1-2024 | 7/2026 | N.A. | 7/2026 | 431.78 | N.A. | 431.78 | 52.82 | 34.61
1376 | TRIPURA | PETROLEUM | KHOWAI ?TELIAMURA-AMARPUR- HARINA-SABROOM PACKAGE-2 | NHIDCL | N24002161 | 1-2024 | 9/2026 | N.A. | 9/2026 | 657.21 | N.A. | 657.21 | 95.71 | 32.85
1377 | TRIPURA | PETROLEUM | KHOWAI ?TELIAMURA-AMARPUR- HARINA-SABROOM PACKAGE-3 | NHIDCL | N24002162 | 1-2024 | 9/2026 | N.A. | 9/2026 | 670.90 | N.A. | 670.90 | 3.81 | 3.05
1378 | TRIPURA | PETROLEUM | CHAMPAK NAGAR TO KHAYERPUR SECTION (DESIGN KM 242+500 TO KM 261+610) | NHIDCL | N24002205 | 12-2023 | 9/2026 | N.A. | 9/2026 | 920.66 | N.A. | 920.66 | 81.54 | 24.56
1379 | TRIPURA | PETROLEUM | KHOWAI ?TELIAMURA-AMARPUR- HARINA-SABROOM SECTION PKG-4 | NHIDCL | N24002228 | 1-2024 | 12/2026 | N.A. | 12/2026 | 726.90 | N.A. | 726.90 | 7.36 | 3.85
1380 | TRIPURA | PETROLEUM | REHABILITATION AND UPGRADATION OF ROAD FROM KM 0.00 TO KM 18.600 OF KUMARGHAT-KAILASHAHAR SECTION | NHIDCL | N24001263 | 6-2020 | 1/2022 | Feb-2024 | 12/2024 | 277.50 | 302.02 | 302.02 | 262.91 | 99.94
1381 | TRIPURA | PETROLEUM | KAILASHAHAR TO KHOWAI PKG-4 | NHIDCL | N24001309 | 11-2020 | 6/2022 | Oct-2023 | 11/2024 | 159.13 | 171.50 | 171.50 | 84.33 | 100.00
1382 | TRIPURA | PETROLEUM | 2-LANING FROM JOLAIBARI - BELONIA | NHIDCL | N24001317 | 6-2020 | 1/2022 | N.A. | 4/2025 | 201.99 | N.A. | 287.47 | 148.22 | 100.00
1383 | TRIPURA | PETROLEUM | MANU-SIMLUNG ( PKG 4) | NHIDCL | N24001363 | 3-2021 | 12/2022 | N.A. | 12/2025 | 354.79 | N.A. | 354.79 | 34.08 | -
1384 | UTTAR PRADESH | CIVIL AVIATION | CCS INTERNATIONAL AIRPORT , LUCKNOW | AAI | N04000077 | 6-2018 | 9/2021 | Oct-2026 | 10/2026 | 1,383.00 | 1,938.00 | 3,291.81 | 2,652.63 | 80.58
1385 | UTTAR PRADESH | CIVIL AVIATION | DEVELOPMENT OF AYODHYA AIRPORT PHASE-01 | AAI | N04000094 | 3-2021 | 12/2022 | Jul-2025 | 7/2025 | 242.14 | 328.00 | 358.00 | 344.58 | 99.90
1386 | UTTAR PRADESH | CIVIL AVIATION | PRAYAGRAJ AIRPORT - CONSTRUCTION OF NEW TERMINAL BUILDING, SECOND LINK TAXI TRACK, APRON EXPANSION, | AAI | N04000102 | 5-2023 | 11/2024 | Jul-2025 | 7/2025 | 185.75 | 274.38 | 274.38 | 206.39 | 97.25
1387 | UTTAR PRADESH | CIVIL AVIATION | AGRA: DEVELOPMENT OF NEW CIVIL ENCLAVE AT AGRA AIRPORT. | AAI | N04000113 | 6-2024 | 7/2026 | N.A. | 7/2026 | 579.00 | N.A. | 579.00 | 72.23 | 13.00
1388 | UTTAR PRADESH | CIVIL AVIATION | VARANASI: DEVELOPMENT OF LAL BAHADUR SHASTRI INTERNATIONAL AIRPORT, VARANASI. | AAI | N04000114 | 7-2024 | 7/2027 | N.A. | 7/2027 | 2,869.65 | N.A. | 2,869.65 | 283.00 | 14.51
1389 | UTTAR PRADESH | COAL | NEYVELI UTTAR PRADESH POWER PROJECT LIMITED 1980 MW | NLC | N06000152 | 7-2016 | 11/2021 | Oct-2025 | 10/2025 | 17,237.00 | 21,780.94 | 21,780.94 | 19,949.00 | 91.39
1390 | UTTAR PRADESH | COAL | KHADIA EXPANSION OCP | NCL | N06000208 | 6-2021 | 3/2025 | N.A. | 3/2027 | 491.67 | N.A. | 491.67 | 202.24 | 40.86
1391 | UTTAR PRADESH | COAL | 60 KTA POLYPROPYLENE PROJECT | GAIL | N16000429 | 3-2019 | 4/2024 | Apr-2024 | 7/2025 | 910.56 | 1,299.02 | 1,299.02 | 974.00 | 96.90
1392 | UTTAR PRADESH | COAL | AUGMENTATION OF FACILITIES AT MATHURA BITUMEN PLANT | IOCL | N16000505 | 4-2022 | 4/2025 | Dec-2026 | 12/2026 | 260.12 | N.A. | 260.12 | 1.07 | 25.00
1393 | UTTAR PRADESH | COAL | GRASS-ROOT TERMINAL AT MIRZAPUR UTTAR PRADESH | IOCL | N16000506 | 9-2022 | 6/2026 | N.A. | 11/2026 | 980.45 | N.A. | 980.45 | 206.85 | 50.75
1394 | UTTAR PRADESH | COAL | CITY GAS DISTRIBUTION PROJECTS AT LAKHIMPUR KHERI , SITAPUR, BAHRAICH, SHRAVASTI,BALRAMPUR, | BPCL | N16000525 | 12-2022 | 6/2030 | N.A. | 6/2030 | 16,654.00 | N.A. | 16,654.00 | 550.36 | 9.70
1395 | UTTAR PRADESH | POWER | KHURJA SUPER THERMAL POWER PROJECT | THDCIL | N18000272 | 3-2019 | 9/2023 | N.A. | 8/2025 | 11,089.42 | 13,276.16 | 13,276.16 | 12,580.53 | 96.00
1396 | UTTAR PRADESH | POWER | SINGRAULI SUPER THERMAL POWER PROJECT, STAGE-III (2X800 MW) | NTPC | N18000382 | 3-2024 | 2/2030 | N.A. | 2/2030 | 17,195.31 | N.A. | 17,195.31 | 1,569.79 | 0.50
1397 | UTTAR PRADESH | POWER | TRANSMISSION SYSTEM FOR EVACUATION OF POWER FROM RAJASTHAN REZ PH-IV (PART-4: 3.5 GW): PART A | PGCIL | N18000407 | 12-2024 | 12/2026 | N.A. | 12/2026 | 5,846.00 | N.A. | 5,846.00 | 198.76 | 2.10
1398 | UTTAR PRADESH | POWER | TRANSMISSION SYSTEM FOR STRENGTHENING TO FACILITATE EVACUATION OF POWER FROM BHADLA/BIKANER COMPLEX | PGCIL | N18000423 | 12-2024 | 6/2026 | N.A. | 6/2026 | 213.00 | N.A. | 213.00 | 0.00 | -
1399 | UTTAR PRADESH | POWER | BURHWAL - GONDA - 3RD RUNNING LINE. | NER | N22000468 | 4-2016 | 3/2025 | N.A. | 9/2025 | 1,015.59 | N.A. | 1,450.00 | 1,277.57 | 52.00
1400 | UTTAR PRADESH | POWER | SHAHGANJ-BHATNI-PHEPHNA-INDARA, MAU-SHAHGANJ (EXCL. MAU-INDARA) PATCH DOUBLING. | NER | N22000470 | 4-2016 | 12/2024 | N.A. | 8/2025 | 1,177.96 | N.A. | 2,145.00 | 2,050.16 | 85.00
1401 | UTTAR PRADESH | POWER | JHANSI MANIKPUR AND KHAIRAR BHIMSEN DOUBLING | NCR | N22000495 | 3-2018 | 3/2026 | N.A. | 3/2027 | 4,329.53 | N.A. | 4,329.53 | 2,125.66 | 50.00
1402 | UTTAR PRADESH | POWER | JHANSI BINA DOUBLING | NCR | N22000496 | 9-2016 | 3/2022 | N.A. | 4/2026 | 2,002.00 | N.A. | 2,001.00 | 1,745.48 | 90.00
1403 | UTTAR PRADESH | POWER | MATHURA-JHANSI-3RD LINE (273.80 KM) | RVNL | N22000501 | 6-2016 | 12/2024 | N.A. | 12/2024 | 5,323.39 | N.A. | 5,190.26 | 5,046.07 | -
1404 | UTTAR PRADESH | POWER | SURFACE TRIANGLE LINE BETWEEN BHADURA STATION AND NEW CROSSING STN KARMA DOUBLING | ECR | N22000525 | 10-2022 | 10/2027 | N.A. | 10/2027 | 199.96 | N.A. | 199.96 | 55.09 | -
1405 | UTTAR PRADESH | POWER | MUGHALSARAI - ALLAHABAD - 3RD LINE | NCR | N22000544 | 8-2019 | 12/2026 | N.A. | 12/2026 | 2,649.44 | N.A. | 2,390.00 | 83.10 | 55.00
1406 | UTTAR PRADESH | POWER | ALIGARH-HARDUAGANJ FLYOVER (22 KM) | NCR | N22000545 | 4-2020 | 6/2026 | N.A. | 6/2026 | 1,456.89 | 1,244.13 | 1,456.89 | 10.14 | 8.20
1407 | UTTAR PRADESH | POWER | LALITPUR - BIRARI WITH FLYOVER AT LALITPUR | NCR | N22000546 | 3-2017 | 12/2024 | N.A. | 11/2025 | 356.09 | N.A. | 356.00 | 213.97 | 65.00
1408 | UTTAR PRADESH | POWER | ALIGARH-DAUD KHAN - 3RD LINE 6.9 KM AND CONSTRUCTION OF FLYOVER AT DAUD KHAN | NCR | N22000562 | 4-2019 | 12/2025 | N.A. | 12/2025 | 451.99 | 779.49 | 779.49 | 122.08 | 44.00
1409 | UTTAR PRADESH | POWER | ALLAHABAD-BAMHRAULI - 4TH LINE (10 KM) WITH FLY-OVER AT SUBEDARGANJ | NCR | N22000563 | 4-2019 | 3/2026 | N.A. | 3/2026 | 494.11 | N.A. | 494.11 | 42.61 | 42.00
1410 | UTTAR PRADESH | POWER | BHANDAI - FLYOVER FOR ETAWAH BOUND DOWN TRAINS | NCR | N22000564 | 4-2019 | 12/2025 | N.A. | 3/2026 | 187.21 | N.A. | 250.17 | 1.29 | 8.00
1411 | UTTAR PRADESH | POWER | SAHJANWA - DOHRIGHAT | NER | N22000565 | 8-2019 | 3/2029 | N.A. | 12/2027 | 371.77 | N.A. | 1,319.75 | 577.85 | 5.00
1412 | UTTAR PRADESH | POWER | BAHRAICH - NANPARA -NEPALGANJ (56.15 KM) | NER | N22000566 | 7-2020 | 12/2024 | N.A. | 8/2025 | 950.00 | N.A. | 500.00 | 424.74 | 25.00
1413 | UTTAR PRADESH | POWER | BAHRAICH SRAVASTI BALRAMPUR (TULSIPUR) | NER | N22000569 | 10-2018 | 10/2030 | N.A. | 3/2028 | 4,939.78 | N.A. | 4,939.78 | 1,334.98 | 7.50
1414 | UTTAR PRADESH | POWER | JANGHAI PRATAPGARH AMETHI DOUBLING | NR | N22000583 | 11-2017 | 3/2025 | N.A. | 12/2025 | 721.72 | N.A. | 1,100.00 | 58.98 | 70.00
1415 | UTTAR PRADESH | POWER | BARABANKI MALHAUR 3RD AND 4TH LINE (32.84 KM) | NR | N22000590 | 1-2019 | 3/2025 | Jan-2026 | 1/2026 | 323.85 | N.A. | 407.00 | 18.91 | 59.00
1416 | UTTAR PRADESH | POWER | DOUBLING BETWEEN JAUNPUR JN- ZAFFARABAD (6.28 KM) | NR | N22000591 | 3-2023 | 12/2026 | N.A. | 12/2026 | 177.33 | N.A. | 177.33 | 0.89 | 10.00
1417 | UTTAR PRADESH | POWER | JANGHAI-PHAPHAMAU - DOUBLING WITH ELECTRIFICATION (46.79 KM) | RVNL | N22000596 | 11-2018 | 3/2025 | N.A. | 3/2025 | 357.48 | N.A. | 409.38 | 362.09 | -
1418 | UTTAR PRADESH | POWER | BHATNI - AUNRIHAR WITH ELECTRIFICATION (125 KM) (EXCL INDARA - MAU (116.95 KM)) | RVNL | N22000598 | 5-2018 | 12/2024 | N.A. | 2/2025 | 2,529.46 | N.A. | 2,529.46 | 1,636.33 | -
1419 | UTTAR PRADESH | POWER | MATHURA - VRINDAVAN (11 KM) | NCR | N22000612 | 8-2022 | 6/2025 | N.A. | 6/2025 | 402.88 | N.A. | 402.88 | 0.00 | -
1420 | UTTAR PRADESH | POWER | DOMINGARH - GORAKHPUR - GORAKHPUR CANTT - KUSUMHI - 3RD RUNNING LINE (21.15 KM) | NER | N22000613 | 11-2016 | 2/2025 | N.A. | 7/2025 | 351.03 | N.A. | 500.37 | 494.01 | 86.50
1421 | UTTAR PRADESH | POWER | CONSTRUCTION OF 6 LANE BRIDGE ON GANGA ON NH-96 AND ITS APPROACHES IN PHAPHAMAU ALLAHABAD ON EPC MOD | MoRTH | N24001421 | 7-2018 | 2/2024 | N.A. | 8/2025 | 1,948.25 | N.A. | 1,948.25 | 1,146.61 | 79.00
1422 | UTTAR PRADESH | POWER | CONSTRUCTION OF FOUR-LANE ELEVATED VIADUCT FROM KM.4+634 TO KM.6+345 ON NH-24A INCLUDING RETAINING W | MoRTH | N24001424 | 3-2021 | 9/2023 | N.A. | 1/2025 | 185.09 | 269.81 | 269.81 | 266.35 | 100.00
1423 | UTTAR PRADESH | POWER | REHABILITATION AND UPGRADATION TO 2 LANE WITH PS OF RADHAITA TO PILIBHIT SECTION OF 46.130 KM | MoRTH | N24001456 | 4-2020 | 2/2024 | N.A. | 1/2025 | 199.39 | 212.96 | 199.39 | 200.01 | 100.00
1424 | UTTAR PRADESH | POWER | REHABILITATION AND UPGRADATION TO 2 LANE WITH PS OF MIRANPUR KATRA TO RADHAITA SECTION OF NH- 730C F | MoRTH | N24001457 | 4-2020 | 7/2024 | N.A. | 9/2025 | 172.50 | 169.56 | 172.50 | 106.06 | 76.00
1425 | UTTAR PRADESH | POWER | 2-LANE WITH PS OF BEWAR TO NEAR KARRI VILLAGE SECTION OF NH-92 FROM KM.0.00 TO 30.00 UNDER GNHCP | MoRTH | N24001461 | 4-2020 | 3/2024 | N.A. | 8/2025 | 236.47 | N.A. | 236.47 | 145.95 | 88.00
1426 | UTTAR PRADESH | POWER | 2-LANE WITH PS OF NEAR KARRI VILLAGE TO ETAWAH SECTION OF NH- 92 FROM KM.30.000 TO 57.346 UNDER GNHCP | MoRTH | N24001462 | 4-2020 | 7/2024 | N.A. | 8/2025 | 211.09 | N.A. | 211.09 | 147.58 | 96.00
1427 | UTTAR PRADESH | POWER | PROJECTS- REHABILITATION AND UPGRADATION OF NH-731A FROM KM 0.00 TO KM.35.00 | MoRTH | N24001464 | 3-2021 | 8/2023 | N.A. | 8/2025 | 264.86 | N.A. | 264.86 | 129.12 | 84.00
1428 | UTTAR PRADESH | POWER | IMPROVEMENT AND UPGRADATION TO TWO LANE WITH PAVED SHOULDER CONFIGURATION FROM EXISTING KM 55.00 TO | MoRTH | N24001469 | 11-2021 | 5/2024 | N.A. | 7/2025 | 307.11 | N.A. | 307.11 | 199.38 | 91.00
1429 | UTTAR PRADESH | POWER | R/U TO 2-LANE WITH PS OF BEWAR TO ALLAHGANJ SECTION OF NH-730C FROM KM.0.00 TO 52.770 UNDER GNHCP | MoRTH | N24001471 | 4-2020 | 11/2024 | N.A. | 7/2025 | 325.24 | 340.16 | 325.24 | 284.35 | 98.00
1430 | UTTAR PRADESH | POWER | WIDENING AND UPGRADATION TO FOUR LANE CONFIGURATION FROM KM.34.900 (BHADOHI) TO KM.73.134 (JAUNPUR) | MoRTH | N24001479 | 3-2021 | 5/2024 | N.A. | 8/2025 | 395.62 | 392.03 | 395.62 | 281.93 | 76.00
1431 | UTTAR PRADESH | POWER | WIDENING AND STRENGTHENING FROM KM 0.00 TO KM 15.089 OF NH- 334A (PURKAJI-LAKSAR-HARIDWAR ROAD) TO TW | MoRTH | N24001480 | 10-2021 | 4/2024 | N.A. | 3/2025 | 227.06 | N.A. | 227.06 | 141.89 | 100.00
1432 | UTTAR PRADESH | POWER | 6L ACCESS-CONTROLLED HIGHWAY FROM (GANESHPUR) TO(NEAR MOHAND) OF GANESHPUR ? DEHRADUN SECTION FROM K | NHAI | N24001523 | 3-2021 | 10/2023 | Jul-2025 | 7/2025 | 836.24 | N.A. | 836.24 | 792.55 | 98.85
1433 | UTTAR PRADESH | POWER | 6L OF ACCESS-CONTROLLED HIGHWAY FROM MOHAND TO DAAT KALI TUNNEL OF GANESHPUR ? DEHRADUN SECTION FROM | NHAI | N24001524 | 3-2021 | 10/2023 | Jul-2025 | 7/2025 | 990.28 | N.A. | 990.28 | 997.62 | 98.89
1434 | UTTAR PRADESH | POWER | WIDENING AND STRENGTHENING OF SECTION FROM BHARTHANA CHOWK TO KODARKOOT (KM. 0.00 TO KM. 40.00) OF | MoRTH | N24001587 | 3-2020 | 9/2024 | N.A. | 8/2025 | 262.37 | 343.77 | 343.77 | 278.92 | 85.00
1435 | UTTAR PRADESH | POWER | 4L SPUR OF SHAMLI-MUZZAFARNAGAR CONNECTING NH-709AD (PANIPAT- SHAMLI-MUZAFFARNAGAR) AND NH-58 (MEERUT | NHAI | N24001726 | 1-2023 | 8/2024 | N.A. | 8/2024 | 391.26 | N.A. | 391.26 | 14.12 | 80.30
1436 | UTTAR PRADESH | POWER | IMPROVEMENT AND UP-GRADATION OF EXISTING ROAD TO 2/4L PS FROM KM 40.000 TO 88.750, START OF KHUTAR B | NHAI | N24001727 | 3-2022 | 2/2025 | N.A. | 9/2025 | 762.62 | N.A. | 838.68 | 571.23 | 95.50
1437 | UTTAR PRADESH | POWER | 4L SPUR OF PANIPAT - SHAMLI CONNECTING NH-709AD (PANIPAT ? SHAMLI ? MUZAFFARNAGAR) AND NH- 709A (KARN | NHAI | N24001729 | 8-2022 | 4/2024 | N.A. | 7/2025 | 326.79 | N.A. | 329.79 | 113.42 | 98.50
1438 | UTTAR PRADESH | POWER | 4L FROM GAJU VILLAGE AT KM 32.982 TO DEVINAGAR BYPASS (END) AT KM 208.000 OF NH 530B (PKG 1C) | NHAI | N24001730 | 12-2021 | 1/2025 | N.A. | 3/2025 | 1,384.79 | N.A. | 1,384.79 | 657.94 | 97.98
1439 | UTTAR PRADESH | POWER | 6L GREENFIELD KANPUR - LUCKNOW (EXPRESSWAY) PKG II FROM KM. 28.500 TO KM. 73.744 | NHAI | N24001731 | 12-2021 | 5/2025 | May-2025 | 9/2025 | 2,470.64 | N.A. | 2,335.00 | 691.28 | 94.68
1440 | UTTAR PRADESH | POWER | IMPROVEMENT AND UP-GRADATION OF EXISTING ROAD TO 4L PS FROM KM 229.070 TO 260.800, END OF HARDOI DIS | NHAI | N24001732 | 12-2021 | 10/2024 | N.A. | 9/2025 | 540.97 | N.A. | 540.97 | 314.76 | 94.76
1441 | UTTAR PRADESH | POWER | 6L ACCESS CONTROLLED GREENFIELD HIGHWAY OF JUNCTION OF EPE (VILL.-MAVIKALAN) TO VILL.- LOHADDA FROM K | NHAI | N24001733 | 3-2022 | 8/2024 | N.A. | 7/2025 | 1,602.48 | N.A. | 1,602.48 | 454.77 | 94.00
1442 | UTTAR PRADESH | POWER | 6L ACCESS CONTROL GREENFIELD HIGHWAY OF VILL-LOHADDA TO VILL- KARAUNDA MAHAJAN FROM KM. 27.000 TO KM. | NHAI | N24001734 | 3-2022 | 8/2024 | N.A. | 7/2025 | 1,335.45 | N.A. | 1,335.45 | 480.89 | 85.02
1443 | UTTAR PRADESH | POWER | 6L ACCESS CONTROL GREENFIELD HIGHWAY OF VILL-KHYAWARI TO VILL- LATIFPUR AT SAHARANPUR BYPASS FROM KM | NHAI | N24001735 | 3-2022 | 8/2024 | N.A. | 7/2025 | 1,428.19 | N.A. | 1,428.19 | 544.15 | 89.50
1444 | UTTAR PRADESH | POWER | 6L ACCESS CONTROL GREENFIELD HIGHWAY OF VILL-KARAUNDA MAHAJAN TO VILL-KHYAWARI FROM KM. 56.500 TO K | NHAI | N24001736 | 1-2022 | 8/2024 | N.A. | 7/2025 | 1,159.96 | N.A. | 1,159.96 | 515.80 | 98.69
1445 | UTTAR PRADESH | POWER | 4LPS OF MUZAFFARNAGAR TO MIRANPUR SECTION OF NH-709AD, PKG-III | NHAI | N24001737 | 11-2021 | 4/2024 | N.A. | 4/2024 | 923.15 | N.A. | 923.15 | 455.61 | 100.00
1446 | UTTAR PRADESH | POWER | 2LPS OF BIJNOR TO KOTAWALI SECTION OF NH-709AD, PKG-IV | NHAI | N24001738 | 9-2021 | 10/2023 | Dec-2024 | 12/2024 | 300.79 | N.A. | 300.79 | 122.56 | 80.61
1447 | UTTAR PRADESH | POWER | REHABILITATION and UPGRADATION FROM 2 LANE TO 4 LANE OF NH STRETCH UNDER BHARATMALA PARIYOJANA FOR U | NHAI | N24001739 | 10-2019 | 11/2023 | Dec-2024 | 12/2024 | 1,779.83 | N.A. | 2,200.00 | 1,066.00 | 100.00
1448 | UTTAR PRADESH | POWER | 4L OF SHAMLI BYAPSS- SAHARANPUR FROM KM 92.2 TO KM 155.025 SECTION OF NH-709B, PKG-II | NHAI | N24001744 | 5-2019 | 11/2022 | N.A. | 7/2025 | 779.17 | N.A. | 779.17 | 71.39 | 98.50
1449 | UTTAR PRADESH | POWER | KANPUR LUCKNOW EXPRESSWAY PKG- 1 CONSTRUCTION OF 6-LANE TO EIGHT LANE OF KANPUR LUCKNOW EXPRESSWAY (N | NHAI | N24001745 | 12-2021 | 7/2025 | Jul-2025 | 7/2025 | 1,972.10 | N.A. | 1,936.00 | 504.87 | 67.00
1450 | UTTAR PRADESH | POWER | 2-LANE EXISTING RAMPUR BYPASS OF RAMPUR TO BE DEVELOPED TO 4- LANE ON EPC MODE IN THE STATE OF UTTAR | NHAI | N24001746 | 3-2021 | 4/2024 | Jul-2025 | 7/2025 | 364.47 | N.A. | 364.47 | 209.19 | 92.98
1451 | UTTAR PRADESH | POWER | 4 LANING OF NAJIBABAD BYPASS OF NH-119 FROM KM. 105.423 TO KM. 118.373 (EXCLUDING 2.45 KM. OF NH-74 | NHAI | N24001753 | 2-2022 | 6/2024 | Jun-2025 | 6/2025 | 570.98 | 570.98 | 570.98 | 424.98 | 97.49
1452 | UTTAR PRADESH | POWER | SPUR OF MEERUT-GARH- MUKTESHWAR SECTION(NH-709A) CONNECTING NH-119 AND NH-58 BYPASSING MEERUT TOWN | NHAI | N24001754 | 1-2022 | 10/2024 | N.A. | 10/2024 | 953.79 | N.A. | 953.79 | 384.66 | 71.02
1453 | UTTAR PRADESH | POWER | 4-LANING OF MEERUT NAJIBABAD SECTION FROM KM. 11.500 TO KM 39.250 AND KM 86.590 TO KM. 112.545.IN TH | NHAI | N24001755 | 10-2019 | 3/2023 | Dec-2024 | 12/2024 | 1,936.68 | N.A. | 2,458.03 | 1,380.90 | 100.00
1454 | UTTAR PRADESH | POWER | 4 LANE CONNECTOR FROM DELHI MEERUT EXPRESSWAY KM 50.000 TO KM 8.520 OF NH 235 IN THE STATE OF UTTAR | NHAI | N24001772 | 8-2021 | 3/2024 | Dec-2024 | 12/2024 | 1,147.26 | N.A. | 1,147.26 | 172.34 | 60.00
1455 | UTTAR PRADESH | POWER | VARANASI RING ROAD (PKG-II) CONNECTING SANDAHA VILLAGE (KM 11.70 / NH-29) WITH REVASA VILLAGE (KM 81 | NHAI | N24001826 | 2-2019 | 2/2022 | Jun-2025 | 12/2025 | 927.77 | N.A. | 1,603.00 | 1,202.77 | 91.25
1456 | UTTAR PRADESH | POWER | SIX LANE ACCESS CONTROLLED OF DELHI SAHARANPUR HIGHWAY FROM DELHI UP BORDER TO EPE JUNCTION CH.14.75 | NHAI | N24001830 | 6-2020 | 11/2023 | Dec-2024 | 12/2024 | 2,002.79 | N.A. | 2,002.79 | 1,989.85 | 99.00
1457 | UTTAR PRADESH | POWER | 4L FROM MATHURA BYPASS (START) AT EXISTING KM. 154.20 OF NH-44 TO GAJU VILLAGE AT KM 32.982 OF NH-53 | NHAI | N24001851 | 1-2022 | 3/2025 | N.A. | 3/2025 | 1,738.20 | N.A. | 1,738.20 | 742.13 | 65.00
1458 | UTTAR PRADESH | POWER | 6L OF AGRA BYPASS (NORTHERN) CONNECTING KM. 174.500 OF NH-2 (NEW NH-19) TO KM. 141.000 OF YAMUNA EXP | NHAI | N24001852 | 10-2021 | 2/2025 | N.A. | 2/2025 | 957.62 | N.A. | 957.62 | 832.80 | 86.00
1459 | UTTAR PRADESH | POWER | CONSTRUCTION OF LEFT OUT PORTION OF AGRA INNER RING ROAD CONNECTING VILLAGE DEORI TO NH- 44 VILLAGE B | NHAI | N24001853 | 10-2021 | 9/2024 | Mar-2025 | 3/2025 | 772.05 | N.A. | 772.05 | 593.39 | 67.50
1460 | UTTAR PRADESH | POWER | CONSTRUCTION OF 4-LANE GREEN FIELD HIGHWAY FROM KM. 35.000 TO KM. 49.155 OF NH-731A WITH PAVED SHOUL | MoRTH | N24001929 | 1-2022 | 10/2025 | N.A. | 10/2025 | 697.66 | N.A. | 697.66 | 318.82 | 98.00
1461 | UTTAR PRADESH | POWER | BALANCE WORKS OF 4-LANNING OF RAMPUR-KATHGODAM SECTION OF NH-87 (NEW NH NO. 09) FROM KM. 0.000 (KM 1 | NHAI | N24001992 | 8-2022 | 2/2024 | Jul-2025 | 7/2025 | 199.31 | 244.26 | 244.26 | 190.10 | 97.62
1462 | UTTAR PRADESH | POWER | CONSTRUCTION OF TWO LANE WITH PAVED SHOULDER HIGHWAY FROM DESIGN CH.0.000 TO CH.49.2OO OF NH- 731B ON | MoRTH | N24001996 | 3-2022 | 11/2025 | N.A. | 11/2025 | 640.18 | 602.76 | 602.76 | 487.39 | 81.00
1463 | UTTAR PRADESH | POWER | CONSTRUCTION OF SHOHRATGARH BYPASS ON NH-730 UNDER EPC MODE IN THE STATE OF UTTAR PRADESH | MoRTH | N24001997 | 10-2022 | 5/2025 | N.A. | 2/2026 | 189.31 | N.A. | 189.31 | 59.91 | 22.00
1464 | UTTAR PRADESH | POWER | IMPROVEMENT AND UPGRADATION TO TWO LANE WITH PAVED SHOULDER CONFIGURATION FROM EXISTING KM 90.00 TO | MoRTH | N24002015 | 11-2021 | 6/2025 | N.A. | 8/2025 | 403.36 | 328.49 | 403.36 | 150.57 | 73.00
1465 | UTTAR PRADESH | POWER | CONSTRUCTION OF PRATAPGARH BYPASS (EXTENSION) CONNECTING NH-31 TO NH-330 | MoRTH | N24002016 | 10-2022 | 6/2025 | N.A. | 8/2025 | 225.17 | N.A. | 225.17 | 96.56 | 55.00
1466 | UTTAR PRADESH | POWER | WIDENING TO FOUR LANE WITH PAVED SHOULDER FROM DESIGN KM.49.200 TO KM.89.285 OF NH-731B ON EPC MODE | MoRTH | N24002029 | 3-2022 | 1/2026 | N.A. | 1/2026 | 917.91 | 956.30 | 917.91 | 615.53 | 47.00
1467 | UTTAR PRADESH | POWER | CONSTRUCTION OF TWO LANE WITH PAVED SHOULDER FROM EXISTING KM.0.000 TO KM.55.610 (DESIGN KM. 0.000 T | MoRTH | N24002031 | 12-2021 | 2/2026 | N.A. | 2/2026 | 840.93 | 773.58 | 840.93 | 524.04 | 44.00
1468 | UTTAR PRADESH | POWER | CONSTRUCTION OF 4-LANE HIGHWAY WITH PAVED SHOULDERS FROM KM 49.155 TO KM 74.700 OF NH-731A ON HYBRID | MoRTH | N24002032 | 1-2022 | 1/2026 | N.A. | 1/2026 | 1,156.72 | N.A. | 1,156.72 | 407.20 | 70.00
1469 | UTTAR PRADESH | POWER | DEVELOPMENT OF SIX-LANE ACCESS CONTROLLED HIGHWAY FROM GOGWAN JALALPUR (SHAMLI DISTRICT) TO RANIPUR | NHAI | N24002036 | 4-2022 | 5/2025 | N.A. | 5/2025 | 1,843.59 | N.A. | 1,843.59 | 843.87 | 50.20
1470 | UTTAR PRADESH | POWER | GARHMUKTESHWAR (KM. 83.200 OF NH-24) TO MEERUT (KM. 9.860 OF NH- 235) INCLUDING CONNECTOR TO NH- 119 | NHAI | N24002073 | 10-2019 | 10/2023 | N.A. | 6/2025 | 2,068.99 | 2,171.00 | 2,171.00 | 209.60 | 53.08
1471 | UTTAR PRADESH | POWER | CONSTRUCTION OF FOUR LANE HIGHWAY FORM GHAZIPUR BALLIA UP BIHAR STATE BORDER (GREENFIELD) SECTION OF | NHAI | N24002086 | 10-2022 | 7/2025 | N.A. | 7/2025 | 1,706.47 | N.A. | 1,706.47 | 719.13 | 77.25
1472 | UTTAR PRADESH | POWER | CONSTRUCTION OF FOUR LANE HIGHWAY FROM GHAZIPUR BALLIA UP BIHAR STATE BORDER (GREENFIELD) SECTION OF | NHAI | N24002087 | 10-2022 | 10/2025 | N.A. | 10/2025 | 1,493.14 | N.A. | 1,493.14 | 93.30 | 66.00
1473 | UTTAR PRADESH | POWER | CONSTRUCTION OF FOUR LANE HIGHWAY FROM GHAZIPUR BALLIA UP BIHAR STATE BORDER (GREENFIELD) SECTION OF | NHAI | N24002088 | 10-2022 | 8/2025 | N.A. | 8/2025 | 1,493.50 | N.A. | 1,493.50 | 492.86 | 58.00
1474 | UTTAR PRADESH | POWER | CONSTRUCTION OF FOUR LANE HIGHWAY FROM GHAZIPUR BALLIA UP BIHAR STATE BORDER GREENFIELD SECTION OF N | NHAI | N24002089 | 10-2022 | 6/2025 | N.A. | 6/2025 | 617.87 | N.A. | 617.88 | 106.20 | 72.00
1475 | UTTAR PRADESH | POWER | CONSTRUCTION OF FOUR-LANE ?WESTERN SIDE SPUR OF RAMPUR- RUDRAPUR SECTION CONNECTING NH-24 TO NH-87 BY | NHAI | N24002090 | 3-2021 | 11/2024 | Dec-2025 | 12/2025 | 646.27 | N.A. | 646.27 | 110.65 | 52.09
1476 | UTTAR PRADESH | POWER | IMPROVEMENT , UP-GRADATION OF NH-734 SECTION OF MORADABAD - THAKURDWARA - KASHIPUR: ?PACKAGE-I: MORA | NHAI | N24002093 | 10-2022 | 9/2025 | N.A. | 2/2026 | 1,841.92 | N.A. | 1,841.92 | 449.98 | 54.40
1477 | UTTAR PRADESH | POWER | IMPROVEMENT AND UP-GRADATION OF EXISTING ROAD TO 4L PS FROM KM 123.650 TO 175.080, FROM START OF SHA | NHAI | N24002094 | 9-2022 | 11/2025 | N.A. | 11/2025 | 1,212.26 | N.A. | 1,212.26 | 361.81 | 34.19
1478 | UTTAR PRADESH | POWER | FOUR LANING OF SONAULI GORAKHPUR SECTION OF NH 29E (NEW NH 24) FROM DESIGN CH. 0.000 TO DESIGN CH. 7 | NHAI | N24002095 | 12-2021 | 3/2025 | N.A. | 3/2025 | 2,555.50 | N.A. | 2,555.50 | 966.89 | 63.57
1479 | UTTAR PRADESH | POWER | CONSTRUCTION OF 4 LANE GREEN FIELD NORTHERN EAST SIDE GORAKHPUR BYPASS (26.616 KMS) STARTING FROM NH | NHAI | N24002096 | 2-2023 | 1/2026 | N.A. | 1/2026 | 1,973.98 | N.A. | 1,973.98 | 736.14 | 48.50
1480 | UTTAR PRADESH | POWER | STRENGTHENING OF EXISTING 4L AYODHYA BYPASS SECTION FROM DESIGN KM.121.600 TO KM. 144.020 OF NH 28 ( | NHAI | N24002097 | 2-2023 | 9/2025 | N.A. | 8/2025 | 526.45 | N.A. | 526.45 | 228.37 | 83.00
1481 | UTTAR PRADESH | POWER | CONSTRUCTION OF RING ROAD AROUND KANPUR FROM KM.000 TO KM. 23.325 (CHACHENDI SACHENDI I TO MAHARAJPU | NHAI | N24002104 | 1-2023 | 6/2026 | N.A. | 6/2026 | 1,754.00 | N.A. | 1,754.00 | 350.78 | 35.20
1482 | UTTAR PRADESH | POWER | CONSTRUCTION OF NEW 4 LANE PRAYAGRAJ SOUTHERN BYPASS (PHASE-I) FROM DESIGN KM 43+200 (AT MAHUWARI VI | NHAI | N24002105 | 8-2023 | 6/2026 | N.A. | 6/2026 | 1,378.36 | N.A. | 739.00 | 213.86 | 30.89
1483 | UTTAR PRADESH | POWER | CONSTRUCTION OF NEW 4 LANE PRAYAGRAJ SOUTHERN BYPASS FROM DESIGN KM 50.860 (NABABA URF NIBI KALA UPA | NHAI | N24002106 | 8-2023 | 3/2025 | N.A. | 10/2025 | 993.77 | N.A. | 349.48 | 372.98 | 92.98
1484 | UTTAR PRADESH | POWER | CONSTRUCTION OF MARIAHU BYPASS WITH FOUR LANE PAVED SHOULDER CONFIGURATION (KM.53.540 TO KM.59.200) | MoRTH | N24002115 | 3-2023 | 8/2025 | N.A. | 2/2026 | 438.24 | 362.39 | 438.24 | 211.72 | 39.00
1485 | UTTAR PRADESH | POWER | REHABILITATION AND UPGRADATION FROM KM 51.600 TO KM 75.700 OF NH- 321G (NUHKHAS TO ETAH SECTION) TO T | MoRTH | N24002116 | 1-2022 | 8/2025 | N.A. | 8/2025 | 343.54 | N.A. | 343.54 | 75.96 | 42.00
1486 | UTTAR PRADESH | POWER | CONSTRUCTION OF JASRA BYPASS WITH FOUR LANE PAVED SHOULDER CONFIGURATION FROM KM. 379.670 ON NH-76 ( | MoRTH | N24002120 | 2-2023 | 9/2025 | N.A. | 9/2025 | 274.06 | N.A. | 274.06 | 135.53 | 88.00
1487 | UTTAR PRADESH | POWER | IMPROVEMENT AND UP-GRADATION TO TWO LANE WITH PAVED SHOULDER CONFIGURATION FROM EXISTING KM. 420.00 | MoRTH | N24002121 | 1-2022 | 9/2025 | N.A. | 2/2026 | 509.65 | N.A. | 509.65 | 188.84 | 34.00
1488 | UTTAR PRADESH | POWER | REHABILITATION AND UP-GRADATION FROM KM. 0.000 TO KM. 40.390 OF NH- 730S (MAHARAJGANJ ? NICHLOUL ? TH | MoRTH | N24002134 | 3-2023 | 12/2025 | N.A. | 12/2025 | 809.25 | N.A. | 809.25 | 279.77 | 35.00
1489 | UTTAR PRADESH | POWER | CONSTRUCTION OF FOUR LANE HIGHWAY WITH PAVED SHOULDER FROM KM.74.700 TO KM.112.950 OF NH- 731A (I/C Y | MoRTH | N24002138 | 3-2022 | 6/2026 | N.A. | 6/2026 | 1,141.67 | N.A. | 1,141.67 | 423.37 | 50.00
1490 | UTTAR PRADESH | POWER | CONSTRUCTION OF BALRAMPUR BYPASS WITH 2L FLEXIBLE PAVEMENT CONFIGURATION FROM KM.223.000 OF NH-330 T | MoRTH | N24002150 | 12-2022 | 2/2026 | N.A. | 2/2026 | 515.69 | N.A. | 515.69 | 187.80 | 37.00
1491 | UTTAR PRADESH | POWER | WIDENING TO 4L RIGID PAVEMENT CONFIGURATION FROM KM 90.00 TO KM 100.800 OF NH-96 (KM 42.O TO KM 53.3 | MoRTH | N24002199 | 12-2022 | 11/2026 | N.A. | 11/2026 | 309.63 | N.A. | 309.63 | 13.52 | 15.00
1492 | UTTAR PRADESH | POWER | IMPROVEMENT AND UP-GRADATION TO TWO LANE WITH PAVED SHOULDER/FOUR LANE CONFIGURATION FROM EXISTING K | MoRTH | N24002201 | 1-2022 | 5/2027 | N.A. | 5/2027 | 974.19 | N.A. | 974.19 | 616.12 | 14.00
1493 | UTTAR PRADESH | POWER | REHABILITATION AND UPGRADATION TO FOUR LANE ROAD FROM KM 70.500 TO KM 78.600 OF NH-92 UNDER EPC MODE | MoRTH | N24002211 | 1-2022 | 1/2027 | N.A. | 1/2027 | 296.02 | N.A. | 296.02 | 27.96 | -
1494 | UTTAR PRADESH | POWER | WIDENING AND STRENGTHENING FROM DESIGN KM. 67.280 TO KM. 88.622 OF NH-727A (SALEMPUR- MAIRWA ROAD) TO | MoRTH | N24002212 | 3-2023 | 7/2026 | N.A. | 7/2026 | 371.89 | N.A. | 371.89 | 151.99 | 45.00
1495 | UTTAR PRADESH | POWER | REHABILITATION and UP-GRADATION TO 2L+PS FROM KM. 0.0 TO KM. 7.80 AND KM. 35.400 TO KM. 52.345 (DESI | MoRTH | N24002213 | 3-2023 | 7/2026 | N.A. | 7/2026 | 701.02 | N.A. | 701.02 | 270.54 | 22.00
1496 | UTTAR PRADESH | POWER | CONSTRUCTION OF AMETHI BYPASS (PART-II) AT KM.30.050 OF NH-931 UNDER EPC MODE IN THE STATE OF UTTAR | MoRTH | N24002214 | 12-2022 | 2/2027 | N.A. | 2/2027 | 283.86 | N.A. | 283.86 | 58.92 | 7.00
1497 | UTTAR PRADESH | POWER | WIDENING TO 4L FROM KM.108.50 TO 139.00 OF NH-135A PKG-II (JAUNPUR TO AKBARPUR SECTION) ON HAM IN TH | MoRTH | N24002234 | 3-2023 | 3/2027 | N.A. | 3/2027 | 1,511.57 | N.A. | 1,511.57 | 154.69 | 12.00
1498 | UTTAR PRADESH | POWER | CONSTRUCTION OF RAEBARELI RING ROAD (PHASE-2) WITH FOUR LANE CONFIGURATION FOR RAEBARELI CITY IN THE | MoRTH | N24002235 | 3-2022 | 5/2027 | N.A. | 5/2027 | 1,273.72 | N.A. | 1,273.72 | 330.15 | -
1499 | UTTAR PRADESH | POWER | IMPROVEMENT AND UP-GRADATION OF NH-227B (84 KOSI PARIKRAMA MARG) PACKAGE ?I, FROM KM 228.920 (JAGARN | MoRTH | N24002240 | 3-2022 | 11/2026 | N.A. | 11/2026 | 912.50 | N.A. | 912.50 | 388.50 | 1.00
1500 | UTTAR PRADESH | POWER | IMPROVEMENT AND UP-GRADATION OF NH-227B (84 KOSI PARIKRAMA MARG) PACKAGE ?III, FROM KM.47.800 (GOSAI | MoRTH | N24002241 | 3-2022 | 11/2026 | N.A. | 11/2026 | 587.97 | N.A. | 587.97 | 107.68 | 3.00
1501 | UTTAR PRADESH | POWER | CONSTRUCTION OF BASTI RING ROAD (PHASE-I) WITH 4L CONFIGURATION FOR BASTI CITY IN THE STATE OF UTTAR | MoRTH | N24002245 | 12-2022 | 6/2027 | N.A. | 6/2027 | 1,138.72 | N.A. | 1,138.72 | 263.70 | -
1502 | UTTAR PRADESH | POWER | CONSTRUCTION OF RING ROAD FOR RAEBARELI CITY (PHASE -I) ON EASTERN SIDE OF NH 24B | MoRTH | N24000331 | 12-2019 | 4/2022 | N.A. | 7/2025 | 282.41 | N.A. | 319.96 | 276.35 | 88.00
1503 | UTTAR PRADESH | POWER | 4-LANNING OF HARIDWAR-NAGINA SECTION OF NH 74 FROM (KM 204.300 OF NH 58) TO KM 73.00 | NHAI | N24000564 | 3-2016 | 7/2020 | Jul-2025 | 7/2025 | 1,408.00 | 1,659.12 | 1,659.12 | 1,336.33 | 91.39
1504 | UTTAR PRADESH | POWER | SIX LANING OF HAPUR BYPASS TO MORADABAD SECTION INCLUDING HAPUR BYPASS FROM KM 50.000 (DESIGN CHAINA | NHAI | N24000798 | 3-2018 | 11/2021 | N.A. | 6/2025 | 2,140.93 | N.A. | 2,140.93 | 2,081.52 | 100.00
1505 | UTTAR PRADESH | POWER | TWO / FOUR LANING OF RAEBARELI - JAGDISHPUR SECTION OF NH-330A FROM KM. 0.000 TO KM. 47.800 (DESIGN | NHAI | N24001306 | 10-2020 | 3/2023 | N.A. | 8/2025 | 724.60 | N.A. | 724.60 | 569.96 | 96.00
1506 | UTTAR PRADESH | URBAN DEVELOPMENT | KANPUR METRO RAIL PROJECT | LMRCL | N28000144 | 5-2019 | 3/2024 | N.A. | 3/2027 | 11,076.48 | N.A. | 11,076.48 | 8,839.21 | 72.60
1507 | UTTAR PRADESH | URBAN DEVELOPMENT | AGRA METRO RAIL PROJECT | LMRCL | N28000145 | 5-2019 | 3/2024 | N.A. | 6/2027 | 8,379.62 | N.A. | 8,379.62 | 5,116.00 | 54.70
1508 | UTTAR PRADESH | WATER RESOURCES | INTERCEPTION AND DIVERSION WORKS AND STP AT MUZAFFARNAGAR UTTAR PRADESH | UPJalNigam | N30000021 | 1-2019 | 12/2021 | Jan-2020 | 3/2025 | 231.79 | 234.03 | 234.03 | 141.79 | 100.00
1509 | UTTAR PRADESH | WATER RESOURCES | SEWERAGE SCHEME INTERCEPTION AND DIVERSION WITH STP WORKS AT MEERUT UTTAR PRADESH | UPJalNigam | N30000024 | 2-2019 | 6/2022 | N.A. | 12/2025 | 681.78 | N.A. | 690.71 | 13.34 | 27.00
1510 | UTTARAKHAND | CIVIL AVIATION | CONSTRUCTION OF DOMESTIC PASSENGER TERMINAL BUILDING AT DEHRADUN AIRPORT, DEHRADUN | AAI | N04000085 | 7-2018 | 9/2020 | Sep-2024 | 9/2024 | 456.86 | 500.00 | 500.00 | 483.96 | 100.00
1511 | UTTARAKHAND | POWER | TEHRI PUMPED STORAGE PLANT(1000MW) | THDCIL | N18000010 | 7-2006 | 7/2010 | Jun-2022 | 9/2025 | 1,657.00 | 4,825.60 | 8,182.00 | 8,046.19 | 98.30
1512 | UTTARAKHAND | POWER | TAPOVAN-VISHNUGAD HEP (4X130MW) | NTPC | N18000014 | 11-2006 | 3/2013 | Dec-2021 | 4/2029 | 2,978.48 | N.A. | 10,907.00 | 7,007.93 | 72.40
1513 | UTTARAKHAND | POWER | VISHNUGAD PIPALKOTI HYDRO ELECTRIC PROJECT | THDCIL | N18000042 | 8-2008 | 6/2013 | N.A. | 3/2027 | 2,491.58 | 3,860.35 | 6,823.72 | 4,918.46 | 71.00
1514 | UTTARAKHAND | POWER | LATA-TAPOVAN HYDRO ELECTRIC POWER PROJECT 3X57 MW | NTPC | N18000142 | 7-2012 | 8/2017 | N.A. | 8/2017 | 1,527.00 | N.A. | 1,527.00 | 149.93 | -
1515 | UTTARAKHAND | RAILWAYS | RISHIKESH - KARNAPRAYAG NEW LINE | RVNL | N22000406 | 4-2011 | 12/2025 | N.A. | 3/2025 | 38,953.15 | N.A. | 24,659.00 | 18,820.04 | -
1516 | UTTARAKHAND | RAILWAYS | 6L ACCESS-CONTROLLED HIGHWAY OF DAAT KALI TUNNEL - DEHRADUN OF GANESHPUR ? DEHRADUN SECTION FROM KM. | NHAI | N24001525 | 3-2021 | 3/2024 | May-2025 | 5/2025 | 169.08 | N.A. | 169.08 | 105.77 | 99.99
1517 | UTTARAKHAND | RAILWAYS | UPGRADATION AND 4L OF HARIDWAR BYPASS FROM KM 0.000 (KM 188.100 OF NH-58) TO KM. 15.100 (KM 5.100 OF | NHAI | N24001526 | 8-2021 | 10/2024 | Aug-2025 | 8/2025 | 1,377.79 | 1,384.11 | 1,377.79 | 684.93 | 58.41
1518 | UTTARAKHAND | RAILWAYS | 4L MEDINIPUR TO BALLUPUR FROM KM. 458.65 TO KM. 487.65 OF NH- 07(PKG-2) | NHAI | N24001553 | 3-2022 | 2/2025 | Nov-2025 | 11/2025 | 1,092.90 | 1,092.90 | 1,092.90 | 463.92 | 89.25
1519 | UTTARAKHAND | RAILWAYS | 4L POANTA SAHEB?MEDNIPUR FROM KM. 435.65 TO KM. 458.65 OF NH- 07(PKG-1) | NHAI | N24001990 | 6-2022 | 5/2025 | Oct-2025 | 10/2025 | 524.54 | 683.26 | 683.26 | 91.94 | 74.78
1520 | UTTARAKHAND | RAILWAYS | ACCESS ROAD/BRIDGE CONNECTIVITY FROM NH-09 AT KM.40 NEAR JAGBUDA BRIDGE (INDIA) TO BOUNDARY PILLAR | NHAI | N24001991 | 5-2022 | 9/2024 | Nov-2026 | 11/2026 | 314.31 | N.A. | 314.31 | 178.52 | 71.79
1521 | UTTARAKHAND | RAILWAYS | CONSTRUCTION FOR MITIGATION MEASURES KM 368.00-UTTARAKHAND- TO KM 433.00 ON NH-07-PKG-1 | NHIDCL | N24002163 | 12-2023 | 12/2025 | N.A. | 12/2025 | 216.88 | N.A. | 216.88 | 82.19 | 75.80
1522 | UTTARAKHAND | RAILWAYS | CONSTRUCTION FOR MITIGATION MEASURES KM 450.00-UTTARAKHAND- TO KM 468.00 ON NH-07-PKG-3 | NHIDCL | N24002164 | 12-2023 | 12/2025 | N.A. | 12/2025 | 250.33 | N.A. | 250.33 | 46.63 | 48.50
1523 | UTTARAKHAND | RAILWAYS | CONSTRUCTION FOR MITIGATION MEASURES PKG-2 | NHIDCL | N24002206 | 12-2023 | 6/2026 | N.A. | 6/2026 | 259.64 | N.A. | 259.64 | 18.62 | 20.23
1524 | UTTARAKHAND | RAILWAYS | 4-LANING OF KASHIPUR-SITARGANJ SECTION | AMR | N24000465 | 11-2012 | 8/2016 | N.A. | 8/2016 | 605.84 | N.A. | 605.84 | 0.00 | -
1525 | UTTARAKHAND | RAILWAYS | 2 LANE WITH PAVED SHOULDER FROM KM 399.00 TO KM 430.00 OF KARANPARYAG TO CHAMOLI UNDER CHARDHAM PARI | NHIDCL | N24000742 | 3-2018 | 11/2020 | N.A. | 3/2024 | 403.36 | N.A. | 403.36 | 340.32 | 100.00
1526 | UTTARAKHAND | RAILWAYS | 2 LANE WITH PAVED SHOULDER FROM KM 430.00 TO KM 468.00 OF CHAMOLI TO PAINI UNDER CHARDHAM PARIYOJNA | NHIDCL | N24000743 | 3-2018 | 11/2020 | N.A. | 3/2024 | 417.24 | N.A. | 417.24 | 344.20 | 100.00
1527 | UTTARAKHAND | RAILWAYS | RECONSTRUCTION WITH GEOMETRIC IMPROVEMENT OF EXISTING 2 LANE/INTERMEDIATE LANE TO 2LANE WITH PAVED S | MoRTH | N24000772 | 12-2017 | 12/2019 | N.A. | 12/2019 | 257.34 | N.A. | 257.34 | 232.69 | 100.00
1528 | UTTARAKHAND | RAILWAYS | RECONSTRUCTION WITH GEOMETRIC IMPROVEMENT OF EXISTING 2 LANE/INTERMEDIATE LANE TO 2LANE WITH PAVED S | MoRTH | N24000773 | 12-2017 | 12/2019 | N.A. | 12/2019 | 200.34 | N.A. | 200.34 | 227.98 | 100.00
1529 | UTTARAKHAND | RAILWAYS | WIDENING OF EXISTING SINGLE LANE ROAD TO TWO LANE WITH PAVED SHOULDERS CONFIGURATION FROM KM. 235.00 | MoRTH | N24000774 | 12-2017 | 12/2019 | N.A. | 12/2019 | 248.22 | N.A. | 248.22 | 236.80 | 100.00
1530 | UTTARAKHAND | RAILWAYS | RECONSTRUCTION WITH GEOMETRIC IMPROVEMENT OF EXISTING 2 LANE/INTERMEDIATE LANE TO 2LANE WITH PAVED S | MoRTH | N24000775 | 6-2017 | 6/2019 | N.A. | 6/2019 | 282.08 | N.A. | 282.08 | 234.97 | 100.00
1531 | UTTARAKHAND | RAILWAYS | RECONSTRUCTION WITH GEOMETIC IMPROVEMENT OF EXISTING TWO LANE TO 2- LANE WITH PAVED SHOULDERS CONFIG | MoRTH | N24000776 | 11-2017 | 11/2019 | N.A. | 11/2019 | 232.81 | N.A. | 232.81 | 201.58 | 100.00
1532 | UTTARAKHAND | RAILWAYS | RECONSTRUCTION WITH GEOMETIC IMPROVEMENT OF SINGLE LANE TO 2- LANE WITH PAVED SHOULDER CONFIGURATION | MoRTH | N24000777 | 11-2017 | 11/2019 | N.A. | 11/2019 | 283.51 | N.A. | 283.51 | 278.51 | 100.00
1533 | UTTARAKHAND | RAILWAYS | RECONSTRUCTION WITH GEOMETRIC IMPROVEMENT OF EXISTING SINGLE/INTERMEDIATE LANE TO 2LANE WITH PAVED S | MoRTH | N24000778 | 11-2017 | 11/2019 | N.A. | 11/2019 | 266.52 | N.A. | 266.52 | 250.34 | 100.00
1534 | UTTARAKHAND | RAILWAYS | RECONSTRUCTION WITH GEOMETRIC IMPROVEMENT OF EXISTING SINGLE/INTERMEDIATE LANE TO 2 LANE WITH EAR | MoRTH | N24000779 | 2-2018 | 2/2020 | N.A. | 2/2020 | 418.88 | N.A. | 418.88 | 339.71 | 94.00
1535 | UTTARAKHAND | RAILWAYS | REHABILITATION AND UP GRADATION OF 2 LANE/ 2 LANE WITH PAVED SHOULDER FROM EXISTING KM. 172.900 TO K | MoRTH | N24000780 | 2-2018 | (N.A.) |  |  | 293.68 | N.A. | 293.68 | 244.25 | 100.00
1536 | UTTARAKHAND | RAILWAYS | CONSTRUCTION OF KUND BYPASS FROM EXISTING KM 33+130 TO KM 41+260 (EXISTING LENGTH: 8.130 KM); DESIGN | MoRTH | N24000781 | 5-2018 | 5/2020 | N.A. | 5/2020 | 248.00 | N.A. | 248.00 | 120.50 | 67.00
1537 | UTTARAKHAND | RAILWAYS | REHABILITATION AND UPGRADATION OF 2 LANE WITH PAVED SHOULDER FROM EXISTING KM. 195.175 TO KM. 220.00 | MoRTH | N24000782 | 3-2018 | (N.A.) |  |  | 460.73 | N.A. | 461.00 | 0.00 | -
1538 | UTTARAKHAND | RAILWAYS | CONSTRUCTION OF 4.5 KM LONG SILKYARA TUNNEL BETWEEN KM 25.40 TO 50.25 KM (TUNNEL WORK) | NHIDCL | N24000855 | 3-2018 | 7/2022 | N.A. | 9/2026 | 1,383.78 | N.A. | 1,383.78 | 714.33 | 64.27
1539 | UTTARAKHAND | RAILWAYS | RECONSTRUCTION WITH GEOMETRIC IMPROVMENT OF EXISTING INTERMEDIATE LANE TO 2 LANE WITH PAVED SHOULDER | MoRTH | N24001130 | 8-2016 | 12/2017 | N.A. | 12/2017 | 234.88 | N.A. | 234.88 | 237.19 | 100.00
1540 | WEST BENGAL | CIVIL AVIATION | CONSTRUCTION OF ATC TOWER AND TECHNICAL BLOCK AT NSCBI AIRPORT KOLKATA | AAI | N04000080 | 1-2016 | 3/2020 | Dec-2023 | 12/2023 | 458.00 | N.A. | 458.00 | 251.64 | 100.00
1541 | WEST BENGAL | CIVIL AVIATION | AIRSIDE CAPACITY ENHANCEMENT OF NSBI AIRPORT, KOLKATA | AAI | N04000081 | 1-2019 | 11/2021 | May-2023 | 5/2023 | 389.71 | 397.00 | 397.00 | 396.61 | 100.00
1542 | WEST BENGAL | CIVIL AVIATION | NSCBI AIRPORT KOLKATA: RE- CONSTRUCTION OF RIGID POSITIONS OF SECONDARY RUNWAY, 'K' AND 'A' TAXIWAY | AAI | N04000109 | 4-2023 | 10/2025 | N.A. | 10/2025 | 328.30 | N.A. | 328.30 | 91.70 | 42.50
1543 | WEST BENGAL | CIVIL AVIATION | BAGDOGRA AIRPORT: DEVELOPMENT OF NEW CIVIL ENCLAVE AT BAGDOGRA AIRPORT. SUB-HEAD : CONSTRUCTION OF N | AAI | N04000115 | 8-2024 | 3/2027 | N.A. | 3/2027 | 1,549.00 | N.A. | 1,549.00 | 239.75 | 9.62
1544 | WEST BENGAL | CIVIL AVIATION | RANIGANJ MASTER PLAN | ECL | N06000163 | 8-2009 | 8/2019 | N.A. | 8/2019 | 2,661.73 | N.A. | 5,146.48 | 787.60 | 42.00
1545 | WEST BENGAL | CIVIL AVIATION | SIDULI MINE (OC AND UG) | ECL | N06000165 | 5-2018 | 3/2027 | N.A. | 3/2027 | 535.18 | N.A. | 535.17 | 5.00 | 14.00
1546 | WEST BENGAL | CIVIL AVIATION | NAKRAKONDA KUMARDIH B OCP | ECL | N06000170 | 8-2018 | 3/2029 | N.A. | 3/2029 | 502.68 | N.A. | 502.67 | 71.07 | 25.51
1547 | WEST BENGAL | CIVIL AVIATION | SHYAMSUNDARPUR UG INCLUDING SAPI UNIT | ECL | N06000191 | 4-2020 | 3/2026 | Mar-2026 | 3/2026 | 483.65 | N.A. | 483.65 | 55.53 | 12.09
1548 | WEST BENGAL | CIVIL AVIATION | 2.0 MTPA BHOJUDIH NLW WASHERY | BCCL | N06000195 | 12-2015 | 9/2020 | N.A. | 7/2025 | 384.57 | N.A. | 384.57 | 351.16 | 97.00
1549 | WEST BENGAL | CIVIL AVIATION | SONEPUR BAZARI EXPANSION OC | ECL | N06000220 | 7-2021 | 3/2029 | N.A. | 3/2029 | 5,365.88 | 5,366.00 | 5,365.88 | 562.41 | 17.38
1550 | WEST BENGAL | CIVIL AVIATION | EXPANSION PR OF JHANJRA UG (5.00 MTY) | ECL | N06000223 | 4-2020 | 3/2029 | N.A. | 3/2029 | 1,210.12 | N.A. | 1,210.12 | 495.37 | 40.00
1551 | WEST BENGAL | CIVIL AVIATION | MOHANPUR EXPANSION OC PHASE II | ECL | N06000236 | 11-2020 | 3/2026 | N.A. | 3/2026 | 888.99 | N.A. | 888.99 | 89.54 | 30.25
1552 | WEST BENGAL | CIVIL AVIATION | BONJEMEHARI EXPANSION OCP | ECL | N06000244 | 8-2021 | 3/2026 | Mar-2026 | 3/2026 | 570.12 | N.A. | 570.11 | 81.58 | 16.00
1553 | WEST BENGAL | CIVIL AVIATION | ITAPARA OC | ECL | N06000272 | 12-2023 | 3/2030 | N.A. | 3/2030 | 929.10 | N.A. | 929.10 | 65.03 | 6.80
1554 | WEST BENGAL | CIVIL AVIATION | UCE OF TILABONI UG | ECL | N06000276 | 1-2023 | 3/2029 | N.A. | 3/2029 | 749.07 | N.A. | 749.07 | 52.09 | 10.30
1555 | WEST BENGAL | CIVIL AVIATION | UCE OF PARASEA BELBAID REORGANISATION UG | ECL | N06000277 | 1-2023 | 3/2029 | Mar-2028 | 3/2028 | 389.10 | N.A. | 389.10 | 131.42 | 16.41
1556 | WEST BENGAL | CIVIL AVIATION | PARASCOLE JAMBAD OCP | ECL | N06000281 | 11-2024 | 3/2037 | N.A. | 3/2037 | 1,193.55 | N.A. | 1,193.55 | 6.04 | 0.01
1557 | WEST BENGAL | DEPARTMENT OF HIGHER EDUCATION | CONSTRUCTION OF TWO NOS GIRLS HOSTELS AND ONE NO BOYS HOSTEL OF 500 CAPACITY EACH G PLUS 8 STOREYED | CPWD EDUCATION | N28000146 | 3-2020 | 6/2020 | N.A. | 3/2024 | 193.83 | N.A. | 193.83 | 187.65 | 99.00
1558 | WEST BENGAL | MINES | CONSTRUCTION OF BASEMENTG FLOOR10 STORIES BUILDING FOR THE STATE OF THE ART, DG, GSI AT SECTOR-V, SA | CPWD | N10000015 | 4-2019 | 4/2022 | N.A. | 8/2026 | 255.37 | N.A. | 255.37 | 74.13 | 40.00
1559 | WEST BENGAL | PETROLEUM | DURGAPUR-HALDIA PIPELINE PROJECT | GAIL | N16000275 | 3-2017 | 12/2020 | Dec-2025 | 12/2025 | 1,740.00 | 2,433.15 | 2,433.15 | 2,193.80 | 90.00
1560 | WEST BENGAL | PETROLEUM | HALDIA PANAGARH PIPELINE PROJECT | HPCL | N16000478 | 11-2022 | 11/2025 | N.A. | 11/2025 | 1,010.00 | N.A. | 1,010.00 | 573.18 | 80.09
1561 | WEST BENGAL | PETROLEUM | CGD PROJECT AT EAST MEDNIPORE, WEST MEDNIPORE AND JHARGRAM DISTRICTS | IOCL | N16000491 | 3-2022 | 3/2030 | N.A. | 6/2031 | 609.00 | N.A. | 609.00 | 56.00 | 2.10
1562 | WEST BENGAL | PETROLEUM | CGD PROJECT IN WEST BENGAL 11TH ROUND | HPCL | N16000498 | 6-2022 | 6/2030 | N.A. | 6/2030 | 2,628.00 | N.A. | 2,628.00 | 320.83 | 24.10
1563 | WEST BENGAL | PETROLEUM | CITY GAS DISTRIBUTION PROJECTS AT ALIPURDUAR AND COOCH BEHAR | BPCL | N16000522 | 12-2022 | 3/2030 | N.A. | 3/2030 | 1,017.00 | N.A. | 1,017.00 | 168.34 | 31.90
1564 | WEST BENGAL | POWER | RAMMAM-III HEPP (3X40 MW) | NTPC | N18000178 | 9-2014 | 9/2019 | Dec-2024 | 3/2029 | 1,381.84 | N.A. | 1,803.00 | 1,302.76 | 43.68
1565 | WEST BENGAL | POWER | TARAKESWAR - BISHNUPUR NEW BG LINE (NL), ER | ER | 220100272 | 4-2000 | 3/2019 | Feb-2026 | 2/2026 | 1,188.91 | N.A. | 2,582.49 | 1,283.98 | 75.00
1566 | WEST BENGAL | POWER | NEW WORK FOR CONSTRUCTION OF METRO RAILWAY FROM NOAPARA- BARASAI VIA BIMANBANDER (MTP) | KOMRCL | N22000108 | 4-2010 | 8/2026 | N.A. | 3/2016 | 4,829.60 | N.A. | 2,397.72 | 197.20 | 17.00
1567 | WEST BENGAL | POWER | NEW WORK FOR CONSTRUCTION OF METRO RAILWAY FROM BARANAGAR TO BARRACKPORE AND DAKSHINESHWAR (MTP) | RVNL | N22000109 | 4-2010 | 12/2026 | N.A. | 12/2025 | 2,298.42 | N.A. | 2,733.86 | 392.98 | -
1568 | WEST BENGAL | POWER | NEW WORK FOR CONSTRUCTION OF METRO RAILWAY FROM NSCB AIRPORT TO NEW GARIA VIA RAJARHAT (MTP) | RVNL | N22000110 | 4-2010 | 12/2025 | N.A. | 3/2026 | 8,964.35 | N.A. | 8,964.35 | 7,387.40 | -
1569 | WEST BENGAL | POWER | NEW WORK FOR CONSTRUCTION OF METRO RAILWAY FROM JOKA TO BINOY BADAL DINESH BAGH. | RVNL | N22000111 | 4-2010 | 12/2026 | N.A. | 12/2026 | 4,834.54 | N.A. | 4,834.54 | 3,918.86 | -
1570 | WEST BENGAL | POWER | PURULIA TO KOTSHILA DOUBLING (39.1 KM) | SER | N22000510 | 4-2018 | 12/2024 | N.A. | 3/2025 | 393.83 | N.A. | 393.83 | 319.21 | 100.00
1571 | WEST BENGAL | POWER | NAHATI - RANAGHAT 3RD LINE (MM OF KALINARAYANPUR - KRISHNANAGAR) | ER | N22000624 | 7-2015 | 3/2025 | N.A. | 3/2026 | 1,000.00 | N.A. | 283.54 | 171.63 | 44.00
1572 | WEST BENGAL | POWER | EAST WEST METRO CORRIDOR KOLKATA | KOMRCL | N22000628 | 2-2009 | 9/2016 | N.A. | 9/2016 | 4,874.58 | 8,575.00 | 10,442.41 | 0.00 | -
1573 | WEST BENGAL | POWER | KALIPAHARI - BAKHTARNAGAR 5TH LINE (17.61 KM) | ER | N22000630 | 4-2024 | 6/2027 | N.A. | 6/2027 | 350.46 | N.A. | 350.46 | 0.00 | -
1574 | WEST BENGAL | POWER | SITARAMPUR BYE - PASS LINE (6.59 KM) | ER | N22000631 | 2-2023 | 3/2027 | N.A. | 3/2027 | 461.64 | N.A. | 461.64 | 26.87 | -
1575 | WEST BENGAL | POWER | MURARAI - BARHARWA 3RD LINE (48.90 KM) | ER | N22000632 | 5-2025 | 5/2028 | N.A. | 5/2028 | 935.19 | N.A. | 935.19 | 0.00 | -
1576 | WEST BENGAL | POWER | SIX LANE OF PALSIT TO DANKUNI SECTION FROM 588.870 TO KM. 652.700 | NHAI | N24001747 | 3-2020 | 9/2024 | N.A. | 9/2024 | 2,193.23 | 2,314.00 | 2,314.00 | 2,085.00 | 97.04
1577 | WEST BENGAL | POWER | SIX LANING OF NATIONAL CORRIDOR NH19 FROM PANAGARH TO PALSIT IN THE STATE OF WEST BENGAL UNDER BHARA | NHAI | N24001748 | 3-2021 | 9/2024 | N.A. | 12/2025 | 2,200.93 | N.A. | 2,622.05 | 2,622.05 | 97.60
1578 | WEST BENGAL | POWER | FOUR LANING OF PURULIYA BYPASS SECTION OF NH 32 IN THE STATE OF WEST BENGAL ON EPC MODE | NHAI | N24001749 | 8-2021 | 8/2023 | N.A. | 9/2025 | 557.55 | N.A. | 567.31 | 473.26 | 91.41
1579 | WEST BENGAL | POWER | CONSTRUCTION OF NEW 4 LANE BRIDGE OVER RIVER GANGA AT DOWNSTREAM OF FARAKKA BARRAGE INCLUDING APPROA | NHAI | N24001750 | 8-2018 | 12/2021 | N.A. | 8/2025 | 622.04 | N.A. | 622.04 | 579.31 | 91.64
1580 | WEST BENGAL | POWER | DEVELOPMENT TO 4/6-LANNING OF NH- 31 (NEW NH-10) WITH BOTH SIDE SERVICE ROADS FROM KM 569.258 TO KM 5 | MoRTH | N24001850 | 3-2022 | 9/2025 | Sep-2025 | 9/2025 | 995.04 | 995.04 | 995.04 | 422.06 | 51.21
1581 | WEST BENGAL | POWER | CONSTRUCTION OR 4 LANE RANIGANJ BYPASS OF LENGTH 5 261 KM ON NH 60 NEW NH 14 FROM KM 273 00 OF NH | MoRTH | N24002184 | 3-2023 | 3/2026 | Mar-2026 | 3/2026 | 410.83 | N.A. | 410.83 | 164.34 | 37.50
1582 | WEST BENGAL | POWER | CONSTRUCTION OF ROB AND ITS APPROACHES IN LIEU OF LEVEL CROSSING NO 10 B T AT KM 307 050 OF NH 60 B | MoRTH | N24002191 | 3-2016 | 8/2025 | N.A. | 8/2025 | 155.87 | N.A. | 155.87 | 21.68 | 10.61
1583 | WEST BENGAL | POWER | 4 LANING OF NH-31D FROM GHOSHPUKUR - SALSALABARI ( KM 0.00 TO KM . 83.785) | NHAI | N24000463 | 12-2015 | 6/2018 | May-2024 | 8/2023 | 1,083.00 | 1,414.01 | 1,414.01 | 1,080.05 | 100.00
1584 | WEST BENGAL | POWER | SIX-LANING OF BARWA ADDA- PANAGARH | NHAI | N24000515 | 4-2014 | 9/2016 | N.A. | 5/2025 | 1,665.00 | N.A. | 4,980.13 | 4,980.13 | 100.00
1585 | WEST BENGAL | POWER | REHABILITATION AND UP GRADATION OF EXISTING ROAD TO 2-LANE WITH PAVED SHOULDER CONFIGURATION IN PURU | NHAI | N24000788 | 3-2018 | 9/2022 | Dec-2022 | 12/2025 | 841.57 | 708.30 | 708.30 | 12,485.63 | 96.49
1586 | WEST BENGAL | POWER | CONSTRUCTION OF NEW ROAD AT THE MISSING LINK PORTION OF NH-81 ALONG THE APPROVED ALIGNMENT BETWEEN H | MoRTH | N24000874 | 3-2016 | 11/2018 | Dec-2023 | 9/2025 | 271.17 | 291.20 | 291.20 | 199.72 | 82.56
1587 | WEST BENGAL | POWER | UPGRADATION OF NH-81 WITH A MINIMUM OF 2-LANE WITH PAVED SHOULDER CONFIGURATION STARTING FROM KM 19. | MoRTH | N24000880 | 2-2018 | 9/2020 | Jan-2024 | 2/2025 | 426.18 | 426.18 | 426.18 | 364.92 | 100.00
1588 | WEST BENGAL | POWER | REBUILDING OF COKE OVEN BATTERY NO.4 OF DURGAPUR STEEL PLANT | SAIL | N12000132 | 11-2023 | 12/2026 | N.A. | 12/2026 | 916.78 | N.A. | 916.78 | 110.08 | 10.98
1589 | WEST BENGAL | POWER | INSTALLATION OF NEW BAR MILL AT DURGAPUR STEEL PLANT | SAIL | N12000138 | 9-2024 | 6/2027 | N.A. | 6/2027 | 2,115.44 | N.A. | 2,115.44 | 100.12 | 19.97
1590 | WEST BENGAL | POWER | UP-GRADATION OF BLAST FURNACE NO. 3 AT DURGAPUR STEEL PLANT | SAIL | N12000139 | 9-2024 | 6/2026 | N.A. | 6/2026 | 758.09 | N.A. | 758.09 | 35.34 | 2.50
1591 | WEST BENGAL | POWER | REVAMPING OF AIR POLLUTION CONTROL SYSTEMS OF SP-1 AT DURGAPUR STEEL PLANT | SAIL | N12000140 | 11-2024 | 5/2026 | N.A. | 5/2026 | 196.40 | N.A. | 196.40 | 0.19 | 1.00
1592 | WEST BENGAL | POWER | THIRD LADLE FURNACE IN SECONDARY REFINERY UNIT AT IISCO STEEL PLANT | SAIL | N12000141 | 11-2024 | 7/2026 | N.A. | 7/2026 | 227.96 | N.A. | 227.96 | 2.61 | 29.00
1593 | WEST BENGAL | WATER RESOURCES | INTERCEPTION AND DIVERSION WITH STP AT MAHESHTALA | KMDA | N30000032 | 5-2018 | 2/2022 | N.A. | 8/2025 | 198.43 | 224.69 | 286.97 | 77.79 | 98.00
1594 | WEST BENGAL | WATER RESOURCES | INTERCEPTION DIVERSION TREATMENT WORKS AT TOLLYS NULLAH ADI GANGA | KMDA | N30000034 | 8-2017 | 9/2022 | Jan-2023 | 12/2026 | 307.12 | N.A. | 653.67 | 0.00 | -
1595 | WEST BENGAL | WATER RESOURCES | INTERCEPTION AND DIVERSION WITH STP AT HUGHLY-CHINSURAH | KMDA | N30000042 | 5-2018 | 2/2022 | Sep-2020 | 3/2025 | 160.00 | 154.73 | 154.73 | 93.32 | 92.00